## Sheet1
PROJECT NAME | INTERIM SUPPORT AND CAPACITY BUILDING TO MINALOC TO IMPLEMENT NATIONAL SOCIAL PROTECTION STRATEGY AND SOCIAL PROTECTION IMPLEMENTATION PLAN
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (2014/15)
Reduced poverty and vulnerability | Number of people living below extreme income poverty line in VUP sectors (UN Population Projections and EICV Poverty Rate) (C) | Planned | 1730594 (33.36%) |  |  | 1,604,847 (27.07%) Attribution to DFID 24,219
Achieved
Source
VUP Household Poverty Surveys
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (2013)
| Extreme income poverty depth in targeted VUP sectors (VUP monitoring data) (C) | Planned | 33.6% |  |  | 29.7%
Achieved
Source
VUP Household Poverty Surveys
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Strengthened systems and capacity in MINALOC to implement NSPS and SPIP | Key actions in SPIP FY 2011/12 implemented | Planned | NSPS and SPIP in place | Leadership, coordination and capacity in the social protection sector strengthened | Finance and M&E capacity and systems strengthened | MINALOC able to implement SPIP (Dec 2012) | TA is effective and has impact Other DPs sustain the current level of commitment to the SP sector.
Achieved
Source
Joint Sector Review reports
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Staff in place and capacity strengthened | Planned | 1 staff in place | Review of MINALOC staffing | 2 new SP staff in place and 2 redeployed (July 2012) | SP team capacity strengthened (Dec 2012)
Achieved
Source
Joint Sector Review reports
INPUTS (£) 100,000 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 100000 |  | 0 |  |  | 100
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumption
Leadership, coordination and capacity in the social protection sector strengthened | Leadership and coordination mechanisms established and roadmap agreed upon | Planned | Draft of groups' membership shared with SWG members | Membership of leadership and coordination mechanisms agreed | ToRs for all SPSWG leadership and coordination mechanisms agreed | Two tiered SPSWG with sub committees in finance, policy and learning and strengthening social protection systems established and operational Feb 2012) | MINALOC recruits new staff to the social protection team by July 2012
Achieved
Source
Social Protection Sector Working Group Meeting minutes
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| No. and quality of proposals for social protection inputs to EDPRS | Planned | 0 | Identification of key issues from EDPRS I self-evaluation | Key issues discussed and prioritised by SP SWG | Development of quality proposals for social protection inputs to EDPRS (March 2012)
Achieved
Source
Social Protection Sector Working Group Meeting
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Capacity of new MINALOC staff | Planned | 0 | 2 new staff in post and 2 existing staff redeployed to SP in MINALOC | Capacity building of new and redployed staff | Increased staffing and capacity in MINALOC SP team (July 2012- staffing, Dec 2012 - capacity)
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Progress made to establishing sector wide financial system | SPSFM plans in place | Planned | Membership of SPSWG Finance sub-committee drafted | Agreed MTEF aligned and consistent with SPIP | Annual Operational Plan to operationalise the SP Sector Funding Mechanism | Pre-requisites in place for establishment of a sector financing mechanism (April 2012) | Development partners agree to the SWAp
Achieved
Source
SP SWG meetings
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Finance strategy | Planned | NSPS and SPIP in place | Recommendations on financing implications of NSPS | Recommendations on potential sources of funding | Development of financing strategy for NSPS supported (April 2012)
Achieved
Source
SP SWG meetings
IMPACT WEIGHTING (%) | Output Indicator 2.3 | Source | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Strengthened systems for delivery and monitoring programmes | Progress towards SP MIS | Planned | Mapping for national MIS system underway | Finalise and present mapping to SP SWG |  | TORs for SP MIS design developed and agreed (Jan 2012) | Continued support of World Bank to development of the SP MIS
Achieved
Source
World Bank, SP SWG
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Progress towards harmonisation of VUP, RDRC and FARG DS and income generation programmes | Planned | VUP, FARDC and RDRC now managed under RLDSF | Discuss options for study and present to SP SWG |  | TORs for study of harmonising VUP, RDRC and FARG DS and income generation programmes developed and agreed (Feb 2012)
Achieved
Source
SP SWG
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Mediium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)