Annex A: DFID. PLAC National Assembly Logical Framework – Goal, Purpose, Outputs
PROJECT NAME: STRENGTHENING NIGERIA’S NATIONAL ASSEMBLY AND THE ELECTORAL PROCESS
GOAL	Indicator 1	Baseline	Target 2012 2013			Target 2013 - 2014		Target 2014- 2015
Strengthening the Key Pillars of Democratic Governance in Nigeria	Increased Representation and Civic Participation as reflected on the Ibrahim Mo PHR Index	26 (2011)	Index / 27			Index / 29		Index / 31

INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£)	Govt (£)		Other (£)			Total (GBP)
	£4,065,681.92	---		---			£4,065,681.92
INPUTS (HR)	DFID (FTEs)

OUTCOME 1:	Indicator: 1	Baseline	Target (2012 - 2013)			Target (2013 -2014)		Target (2014 -2015)			Assumption
Improved Effectiveness and Efficiency of the National Assembly	Number of major pieces of NA legislation that reflect citizens concerns and improve accountability and transparency and electoral and constitutional reform	1	1			2		3			Senate and House of Representatives are ready t collaborate for the quick passage of legislation. / National Assembly is responsive to pressures for institutional reform from civil society and other pressures

	Indicator: 2	Baseline	Target (2012 -2013)			Target (2013 – 2014)		Target (2014 -2015)
	No of procedural reforms adopted by the NA in furtherance of the legislative reform agenda in increasing accountability and transparency	0	2			3		4

Output 1.1	Indicator 1	Baseline	Target (2012 - 2013)			Target (2013 - 2014)		Target (2014 - 2015)			Assumption
Improved representation by targeted National Assembly members and Committees.	% bills considered for which public hearings/ citizen’s inputs were sought	No of bills with public hearing / total no of bills considered	5% Improvement			10% improvement		5%improvement (election year)			Sufficient political will and pressure exerted on National Assembly to reform its processes and respond to demands of civil society and constituents / National Assembly is functional and willing to receive TA and other support

		Records from the National Assembly, proceedings and hansard
	Indicator 2	Baseline	Target (2012 - 2013)			Target (2013 - 2014)		Target (2014 - 2015)
	% of key amendments to the constitution and electoral act that reflect civil society inputs /position.	0	5%			10%		15%

IMPACT WEIGHTING
40%
		RISK RATING
		Medium
INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£)	Govt (£)		Other (£)			Total (GBP)
	£843,000	--		--			£843,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 1.2	Indicator 1	Baseline	Target (2012 - 2013)		Target (2013 - 2014)		Target (2014 - 2015)		Assumptions
Improved Law Making Capacity of the National Assembly	Number of Legislative Committees that receive technical assistance	0	5		6		8		Combination of critical mass of Legislators and pressure from media and civil society in favour of change / NASS House and Senate able to work together on critical issues
		Source
		Technical assistance would include support to committee hearing, workplan development, adoption if best practice templates etc
	Indicator 2	Baseline	Target (2012 – 2013)		Target (2013 - 2014)		Target (2014 - 2015)
	Better Quality legislative process and legislation by National Assembly (scale: 1=poor, 5=excellent)	1	1		2		3
		Source
		Annual reviews, NASS reports
IMPACT WEIGHTING									RISK RATING
25%									Medium
INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£)	Govt (£)		Other (£)		Total (GBP)		DFID SHARE (%)
	£529,600	---				£529,600		100%
INPUTS (HR)	DFID (FTEs)

OUTPUT 1.3	Indicator 1	Baseline	Target 2012 - 2013		Target 2013 – 2014		Target (2014 – 2015)		Assumptions
Increased oversight of the Executive and MDAs by supported National Assembly Committees	Quality of actions by supported committees that reflect oversight of the executive. / (scale: 1=poor, 5=excellent)	1	2		3		4
		Indicator Definition / Source
		Actions here would include investigative hearing, oversight visits, committee hearings, etc; Source: Committee and Media Reports
	Indicator 2	Baseline	Target 2012 - 2013		Target 2013 – 2014		Target (2014 - 2015)
	Quality of NA committees conducting budget oversight hearings / (scale: 1=poor, 5=excellent)	1	2		3		4
		Indicator Definition / Source
		Committee reports and media report
IMPACT WEIGHTING									RISK RATING
25%									Medium
INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£)	Govt (£)		Other (£)		Total (GBP)		DFID SHARE (%)
	£243,580	---		---		£243,580		100%
INPUTS (HR)	DFID (FTEs)
	0.1

	Indicator 1	Baseline	Target (2012 -2013)				Target (2013 – 2014)				Target (2014 – 2015))				Assumptions
Outcome 2: / Increased CSO Participation in Legislative and Electoral Processes	None														Space remains open for civil society to participate in democracy and accountability issues
OUTPUT 2.1	Indicator 2	Baseline	Target (2012 -2013)				Target (2013 -2014)				Target (2014 - 2015)				Assumptions
Strengthen the role of civil society organisations and the Media in policy and legislative processes	Number of CSOs supported that undertake independent engagement of the legislature.	15	20				25				30				The National Assembly is open and willing to interact and engage with civil society organisations

IMPACT WEIGHTING		Risk Rating
25%		Medium
INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£)	Govt (£)		Other (£)					Total (GBP)
	£647,520	----							£647,520
INPUTS (HR)

Output 2.2	Indicator 1	Baseline	Target (2012 - 2013)				Target (2013 - 2014)				Target (2014-2015
Increased CSO Capacity to monitor the electoral process through the Election Situation Room platform1	Number of civil society leaders trained/ sensitised on elections, rights and responsibilities	50	60				75				100 / The National Assembly is open and willing to interact and engage with civil society organisations / PLAC is resourced and able to be the catalyst for making the Situation Room happen

	Indicator 2	Baseline	Target (2012 - 2013)				Target (2013 - 2014)				Target (2014 – 2015 / 4
	Quality and effectiveness of CSO monitoring of the electoral processes2 (scale, 1=poor, 5=excellent)[1]	2	3				3

IMPACT WEIGHTING
	Indicator 3	Baseline		Target (2012 - 2013)				Target (2013 - 2014)				Target (2014 - 2015)
	Effectiveness of Situation Room (scale, 1=poor, 5=excellent)	2		3				3				4

25%		RISK RATING / Medium
INPUTS (£) This is a process programme. Figures are indicative and subject to change	DFID (£) / £723,220	Govt (£) / ---			Other (£) / ---					Total (GBP) / £723,220

INPUTS (HR)	DFID (FTEs)
	0.1
[1] The Election Situation Room is constituted as a broad committee of civil society actors and serves as melting pot of ideas where suggestions are generated and canvassed in response to key developments and gaps in the electoral processes. 2 This indicator is to be measured by DFID annual review process

Strengthening Nigeria’s National Assembly And The Electoral Process - Logical Framework – Activities
OUTPUT 1.1	Activity 1	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 -2015)	Risks	Monitoring Officer
Improved representation by targeted National members and Committees	Technical assistance to Select National Assembly Committees and members, in response to Legislative Initiatives and reform / b. 2 Technical Strategy sessions of Priority Committees (eg. Appropriations, Petroleum, Electoral Matters)	Identification of partner Committees to work with in the areas of MDGs and financial oversight / 2 technical training sessions with select National Assembly Committees on strategy development. / b. 2 Technical Strategy sessions of Priority Committees (eg. Appropriations, Petroleum, Electoral Matters)	Identification of partner Committees to work with in the areas of MDGs and financial oversight / 2 technical training sessions with select National Assembly Committees on strategy development. / b. 2 Technical Strategy sessions of Priority Committees (eg. Appropriations, Petroleum, Electoral Matters)	Identification of partner Committees to work with / In the areas of MDGs and financial oversight / 2 technical training sessions with select National Assembly Committees on strategy development. / b. 2 Technical Strategy sessions of Priority Committees (eg. Appropriations, Petroleum, Electoral Matters)	Limited or no reform by the National Assembly, / Cooperation from members limited, / Political calculations and pressure compromises drive to reform or pass reform bills
	Activity 2	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
	Support to the National Assembly’s House of Representatives Legislative Agenda	3 Working team/technical committee meetings to strategise on key reform issues / 1 Best practice Legislative template, material, workplan developed / 1 strategy review meeting of the House of Representatives to better coordinate and deliver on Legislative Agenda	3 Working team/technical committee meetings to strategise on key reform issues / 1 Best practice Legislative template, material, workplan developed / 1 strategy review meeting of the House of Representatives to better coordinate and deliver on Legislative Agenda	3 Working team/technical committee meetings to strategise on key reform issues / Review carried out of Best practice Legislative templates, materials, workplan and report of review disseminated / 1 strategy review meeting of the House of Representatives to better coordinate and deliver on Legislative Agenda / Synthesis report produced of best practice materials and templates targeted at newly elected legislators to create awareness of legislative initiatives and models to the newly elected members of the National Assembly	Leadership challenges could delay or limit rate of reform, / Political resistance to reforms by entrenched interests
	Activity 3	Target (2012 - 2013	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
	Support to National Assembly to undertake Study missions to acquire best practice knowledge from other established legislatures in order to further deliver on legislative reforms.	Design and initiation of coordination arrangements, including identifying countries for study mission / Implement two study missions for select National Assembly members and bureaucrats respectively / Strategy meeting to synthesise and formulate outcome and lessons learnt from study mission / Produce outcome document of study mission for information sharing with other legislators and staff of the National Assembly	Design and initiation of coordination arrangements, including identifying countries for study mission / Implement two study missions for select National Assembly members and bureaucrats respectively / Strategy meeting to synthesise and formulate outcome and lessons learnt from study mission / Produce outcome document of study mission for information sharing with other legislators and staff of the National Assembly	Review and overview of study missions carried out / Generate a standard report for information sharing on all of the lessons learnt	Resistance to information sharing / Scheduling of study tour within the legislative calendar

OUTPUT 1.2		Activity 1	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
Improved Law Making Capacity of the National Assembly		Technical assistance to the National Assembly Committees to facilitate Constitution amendment, Electoral Act reform and passage of important reform bills	1 retreat meetings of Constitution Reform Committee to deliberate on reform issues / Synthesis and drafts of best practice guidelines and suggestions for amendments of provisions of the Constitution and the Electoral Act produced / Advocacy on Key Constitutional and legislative reform issues supported for passage through production of materials and its dissemination / 6 Zonal Public Hearings each of the Constitution Review Committee (both House and Senate) of the 6 geo- political zones to be supported	2 retreat meetings of Constitution Reform Committee to deliberate on reform issues / Synthesis and drafts of best practice guidelines and suggestions for amendments of provisions of the Constitution and the Electoral Act produced / Advocacy on Key Constitutional and legislative reform issues supported for passage through production of materials and its dissemination	2 retreat meetings of Constitution Reform Committee to deliberate on reform issues / Advocacy on Key Constitutional and legislative reform issues supported for passage through production of materials and its dissemination / Develop and Provide training and lessons learnt materials to newly elected legislators / Strategic review of the legislative direction and achievements of the 7th National Assembly and proposals for engaging the 8th National Assembly	High due to pressures and partisan divisions
Output 1.3		Activity 1	Target (2012 - 2013)	Target (2013 – 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
Increased Oversight of the Executive and MDAs by supported National Assembly Committees		Enhancing select National Assembly Committees knowledge and ability to appropriate and oversight public expenditure	Identification of partner committees in revenue, appropriations, and financial oversight; identification of staff partners / 2 Technical training sessions and support for MDGs related, revenue, appropriation and financial oversight committee(s)	Identification of partner committees in revenue, appropriations, and financial oversight; identification of staff partners / 2 Technical training sessions and support for MDGs related, revenue, appropriation and financial oversight committee(s)	Identification of partner committees in revenue, appropriations, and financial oversight; identification of staff partners / 2 Technical training sessions and support for MDGs related, revenue, appropriation and financial oversight committee(s)	Executive branch resistance to release of information. Tensions between House and Senate diminishes cooperation
		Activity 2	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
		Technical assistance to Committees of the National Assembly to improve their use of best practice Guides and templates in oversight activities	Synthesis of best practice guides developed and made available / 3 National Assembly Committees supported to understand and use best practice guides, templates and IT	Review and dissemination of best practice guides and templates / Synthesis of best practice guides developed and made available / 3 National Assembly Committees supported to understand and use best practice guides, templates and IT	Review and dissemination of best practice guides and templates / 5 National Assembly Committees supported to understand and use best practice guides, templates and IT	Resistance from bureaucrats in Committees used to a particular way of doing things

OUTPUT 2.1		Activity 1	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
Strengthen the Role of Civil Society Organisations and the Media in Policy and Legislative Processes		Support CSOs to influence legislation at the National Assembly in priority areas of electoral reform, Constitution review, gender equality, freedom of information, petroleum, health, education, poverty, youths, etc.	15 organisations supported to engage with the Committees on Constitution Review and Electoral reform / Technical training to 20 organisations and 15 media institutions to engage with committees on the priority areas of education, health, youths and policy advocacy	2 research studies / conducted / 15 organisations supported to engage with the Committees on Constitution Review and Electoral reform / Technical training to 23 organisations and 15 media institutions to engage with committees on the priority areas of education, health, youths and policy advocacy	2 research studies / Technical training to 25 organisations and 15 media institutions to engage with committees on the priority areas of education, health, youths and policy advocacy	Low level of CSOs working on legislative issues
		Activity 2	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
		Support to the National Assembly Civil Society Liaison Office to increase their ability to expand CSO engagement and collaboration with the National Assembly	Capacity assessment and technical assistance plan developed for the CSOLO / 2 Training sessions for the CSOLO staff on data management, IT competence and knowledge / 2 Technical training on CSO relations and advocacy	2 Training sessions for the CSOLO staff on data management, IT competence and knowledge / 2 Technical training on CSO relations and advocacy	2 Training sessions for the CSOLO staff on data management, IT competence and knowledge / 2 Technical training on CSO relations and advocacy	Low level of CSOs working on legislative issues
		Activity 3	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
		Legislative Internship Programme to provide technical assistance and support to members and committees of the National Assembly	Screen and identify 20 volunteers for internship / Provide training and deploy the 20 interns for a six weeks period / Deploy interns to no less than 12 Committees/members of the National Assembly / Organise two briefing/debriefing sessions with interns	Screen and identify 20 volunteers for internship / Provide training and deploy the 20 interns for a six weeks period / Deploy interns to no less than 12 Committees/members of the National Assembly / Organise two briefing/debriefing sessions with interns		Low qualified interns able to impact skills on the committees / Unwillingness and resistance from staff and bureaucrats in National Assembly to “outsiders” coming in
	OUTPUT 2.2	Activity 1	Target (2012)	Target (2013)	Target (2014)	Risks	Monitoring Officer
	Increased CSO Capacity to monitor the Electoral Process through the Election Situation Room Platform	Effective CSO Monitoring of Elections in Nigeria, through the setting up of a Situation Room	2 meetings of CSOs to articulate strategies to observe elections / 2 briefing sessions for the media on the socio-economic state of the nation, including on electoral preparations and matters / Constitution and operation of Communication Room for Situation Room for Ondo State	2 meetings of CSOs to articulate strategies to observe elections / 2 briefing sessions for the media on the socio-economic state of the nation, including on electoral preparations and matters	2 meetings of CSOs to articulate strategies to observe elections / 2 briefing sessions for the media on the socio-economic state of the nation, including on electoral preparations and matters / Constitution and operation of Communication Room for Situation Room for Osun, Anambra and Ekiti States / Constitution and operation of Communication Room for Situation Room for the 2015 General Elections
		Activity 2	Target (2012 - 2013)	Target (2013 - 2014)	Target (2014 - 2015)	Risks	Monitoring Officer
		Use of New Media	Listserve/IT/website set up and used in e-mail messaging / Bulk SMS messaging / Social Media network and advertisement	Listserve/IT/website set up and used in e-mail messaging / Bulk SMS messaging / Social Media network and advertisement	Listserve/IT/website set up and used in e-mail messaging / Bulk SMS messaging / Social Media network and advertisement	ICT challenges \