Annual Review - Summary Sheet

Title: Access to Justice through Paralegal Services and Restorative Justice
Programme Value: £18.5 million		Review Date: December 2016
Programme Code: 203227	Start Date: January 2013	End Date: December 2018

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019
Programme Score	A	A+	A+	A+
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

Bangladesh is widely perceived as a role model in the developing world for making substantial progress towards achieving the Millennium Development Goals (MDGs): the country has had a steady economic growth rate of 6-7% in the last few years and has reduced its dependence on foreign aid. The Government’s commitment to the Sustainable Development Goals (SDGs) is evident from its Mapping Plan linking the SDGs to its 7th Five Year Plan (SFYP)[1] and other relevant national strategies. Goal 16 (Peace, Justice and Strong Institutions) is critical for Bangladesh to succeed in all areas. The specific topic of prison reform on the international fora has continued gaining importance through the passing of the Revised Standard Minimum Rules for the Treatment of Prisoners (Nelson Mandela Rules) by the UN General Assembly in January 2016.
[1] 7th Five year Plan Government of Bangladesh 2016.

Despite significant gains in a number of areas, national and international human rights observers are still concerned about the human rights situation and the respect for democratic principles in Bangladesh. For example, the Government has placed an amendment to the Child Marriage Restraint Act 1929 before parliament to reduce the marriageable age of girls to 16 under special circumstances. This is not compatible with several laws, including the Children Act 2013, and various international commitments. In October 2016, the Parliament of Bangladesh passed the Foreign Donations (Voluntary Activities) Regulation Bill 2016 that increases the control of the NGO Affairs Bureau over NGOs, which is likely to decrease freedom of action within the public space. Meanwhile, the controversial Information and Communication Technology Act, 2006 (amended in 2009 and 2013) remains in force.

Against this backdrop, support from the “Access to Justice through Paralegal Services and Restorative Justice” (A2J) project provided opportunities for the Government of Bangladesh (GoB) to review and incorporate the experience of other countries into both penal policies and their prison systems. In the SFYP, the Government committed to creating mechanisms to help to reduce the case backlog and improve access to justice[2]. The target group of the programme is mostly composed of poor people who are denied their political and social human rights, such as the right to freedom, equality and access to legal services. The efforts to reduce the number of arrests, provide free legal aid and expedite the release from imprisonment all directly improve the situation of poor people and their families. However, there is a need for increased recognition of the role that NGOs and development organisations can play in enhancing: access to justice for the poor and vulnerable, measures to strengthen alternate dispute resolution mechanisms, legal aid, and digitisation of the Judiciary. The relationship that the project has built with the Government demonstrates that the project has flexibility in its outreach work, and influence over policy implications in the area of criminal justice.

The project completed its fourth year of implementation at the end of December 2016. By placing paralegals in prisons, courts and police stations, the project focuses on offering legal services at the various entry points of the criminal justice system and, working on reducing the number of new cases from entering the system. Paralegals help divert cases to local dispute mechanisms, such as mediation and Restorative Justice (RJ), the latter which brings the offender and victim together with their families, guided by a trained mediator, which ends with an agreement of compensation or restitution, thus resolving the crime with healing instead punishment, and saving time, resources and money. The project continued to help the rehabilitation of released prisoners through productive employment and reintegration into society. Support from the Government, the Judiciary and NGOs have helped to provide skills development training, drug referral services and life skills trainings. This has a positive impact, particularly on the socially weak and poor families of prisoners, by enabling them to provide for their families’ livelihoods and improve their living conditions after their release. The project continues to deliver better value for money. From project inception until December 2016, the UK’s support through the project had benefited over 306,565 households and provided assistance in the release of 10,761 prisoners. The strengthening of alternative dispute resolution mechanisms in 8 districts has led to the diversion and the subsequent resolution of 9,118 cases through RJ and mediation. An analysis of the value for money is available at the end of this report, however, the Internal Rate of Return stands at 116%.

Actions on Previous Recommendations

The previous recommendations were around: i) identifying opportunities to make the functions performed by the paralegals sustainable in the justice system – the project supported a study on the role of CCC that provided a number of options for further examination with key stakeholders; progress - on track; ii) revising the outcome indicator to reflect the changes that can be influenced by the project - while the impact statement remains unchanged, its scope has been broadened to link it with the Sustainable Development Goal 16[3], regarding peace, justice and strong institutions; progress - fully implemented; iii) improving monitoring and follow up of RJ sessions; progress - fully implemented; iv) establishing a mechanism for the partner NGOs to track a sample of prisoners who complete skills development training and those being provided with referral services; progress – fully implemented; and v) raising awareness about the incidence of prisoners suffering from mental health issues; progress – partially implemented. The actions on the recommended areas are detailed in each of the Output Scoring pages.
[3] Sustainable Development Goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions ( https://sustainabledevelopment.un.org/sdg16)

Summary of recommendations for the next year

 Recommendation 1: Present the findings of the CCC study to key Government decision-makers at the National level, for enhancing the sustainability of the CCCs, and incorporate policy changes in a policy matrix for improved policy dialogue with key stakeholders. By June 2017.

Recommendation 2: Pilot working approaches recommended in the CCC study between the paralegals and National Legal Aid Services Organisation (NLASO)/District Legal Aid Committee (DLAC) in selected districts to strengthen Government legal aid, and explore paralegal sustainability options. By October 2017.

Recommendation 3: Pursue opportunities for partnership with the Supreme Court Legal Aid Committee (SCLAC) for matters related to jail appeals, as poor prisoners await the final result of their appeal for a long time. Such a partnership should help release people from prison earlier and reduce case backlog. By November 2017.

Recommendation 4: Foster the relationship between the departments under the Ministry of Home Affairs, such as Prisons, Police and Directorate of Narcotics Control (DNC), for better coordination of activities. Facilitate joint-up planning and implementation between the DNC and the Prisons to ensure sustainability. By October 2017.

Recommendation 5: Use the findings of the midline survey conducted by the media monitoring agency to refine outreach strategies. These findings should assist the project in improving messages for increased outreach and assess the influence the messages have had on people’s ability to access justice. By October 2017

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203227/
DevTracker Link to Log frame:	As above

Outline of the programme

UK Aid is providing £18.5 million over six years (January 2013 - December 2018) to scale up the existing project “Improvement of the Real Situation of Overcrowding in Prisons” (IRSOP). The project was designed to reduce prison overcrowding and address some of its underlying causes. The disproportionate number of prisoners awaiting trial whilst in custody, for example, is linked to the large number of outstanding investigations by police and the pending caseload in courts, lack of access to legal assistance, compounded by the absence of alternatives to imprisonment and poor administration. UK Aid combines GBP18.5 million with GBP 3.4 million from Germany to extend the scope of the project from 5 to 40 districts from January 2013-December 2018, making the total cost of the scale up from 5 to 40 districts GBP 21.9 million. The project works with prisoners and justice seekers (the poor, marginalised and vulnerable people who need justice services) in prisons, police stations and courts. It provides services at the community level, supports awareness-raising about laws and legal services, and contributes to the better functioning of the system through supporting increased coordination among the organisations that make up the Bangladesh criminal justice system.

The anticipated result of the UK assistance is to ‘enable more people in Bangladesh, particularly the poor, prisoners, women and children to get accountable, efficient and effective justice services.’

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The overall outcome of the project is to improve access to justice in 40 of the total 64 districts in the country by reducing the number of cases sent via the formal criminal justice system. This is expected to benefit up to 2 million poor people and reduce the remand population by up to 17,750 in 40 districts. There are two indicators for this outcome:

Indicator 1: Number of households, especially those of prisoners, poor and women, benefitting from improved access to accountable, efficient and effective justice services. [Milestone 2016: 96, 610]

Indicator 2: Number of districts with improved access to paralegal service activities. [Milestone 2016: 10 districts, in addition to existing 20 districts]

During the reporting year, the UK’s support through the project benefited 145,884 households, and provided assistance in the release of 4,221 prisoners. The Paralegal Advisory Services (PAS) have contributed to reduce the length of incarceration of under-trial prisoners. The scope and depth of involvement of Government Officials is detailed later. The strengthening of alternative dispute resolution mechanisms in 8 districts has led to the diversion and the subsequent resolution of 3,800 cases from the formal justice system through RJ and mediation in the reporting year.

The Independent Advisory Panel that is yet to be formed by DFID and GIZ will assess Indicator 1 through qualitative assessment scorecards as per the recommendation from the Mid Term Review of early 2016. However, this Indicator can be measured qualitatively through the changes the project has seen in each of the Outputs during the reporting year, and highlighted in each of the Output pages. For example, the project has demonstrated the effectiveness of the CCCs in improving the operational functioning of the justice system at the district level, working on local solutions for local problems. It is evident that the progress and support of the CCCs drives them to work more efficiently, creating an appetite for policy makers for reform. Also, it is evident that there is a substantial increase in the number of disputes solved locally through RJ in the reporting year, as opposed to mediation. This increased acceptance of the principles of RJ in resolving local disputes at the local level, demonstrates a potential mechanism for a less costly and more equal and just platform for resolving disputes for all stakeholders. The project is also tracking 30% of released prisoners to assess what impact the rehabilitation and training activities are really having.

The UK’s support through the project ensured that during the reporting year, the number of districts with improved access to paralegal service activities increased from 20 to 30 districts. The project is on track for rolling out to the final 10 in the coming year.

The project has adopted an approach towards identifying opportunities for policy advocacy and reform in legislation. A draft policy matrix which has been developed that is expected to track any policy implications and their influence on the project. This includes for instance, policy advocacy regarding the use of the District Legal Aid Committees (DLAC)[4] for mediation of compoundable[5] disputes. The project is currently looking at strengthening the capacity of DLAC by building linkages with those who can refer cases. Some of the key policy areas and laws which are likely to have an impact on the project outcome over time include: bail, sentencing, The Prisons Act 1894, The Probation of Offenders Ordinance 1960 and The Evidence Act 1872, etc.
[4] DLAC: The National Legal Aid Services Organisation (NLASO) operates through the district level set ups (DLAC) headed by a staff member to manage and disperse legal aid at the district level.
[5] Following Section 345 (1) of the Bangladeshi Code of Criminal Procedure (1898), compoundable cases are petty offences which can be solved within the community through alternative dispute resolution mechanisms.

The collaboration with the BMZ financed project “Justice Reform and Corruption Prevention” (JRCP) has ensured that field experience from the project is shared with the key policy makers such as the Ministry of Home Affairs (MoHA) and the Ministry of Law, Justice and Parliamentary Affairs (MoLJPA).

The project demonstrates that it is currently on track despite the heightened security concern that has emerged after the incident of terrorism in July 2016 in Dhaka. This saw increased arrests and restricted staff movements, and has made it more difficult for the implementing partners to work within the prison system. A2J extended its outreach to 30 districts as planned and has deployed paralegals to increase access to justice services and increased the outreach of alternate dispute resolution, RJ and rehabilitation interventions.

Overall output score and description

Output Scoring
Number	Output Description		Weight	Output Performance
1	Paralegal Advisory Services		60%	Outputs moderately exceeded expectation (A+)
2	Restorative Justice mechanisms to reduce inflow of cases into the Justice System		20%	Outputs substantially exceeded expectation (A++)
3	Strategies for Reducing Recidivism through skills training and support for referral to services		10%	Outputs moderately did not meet expectation (B)
4	Empowerment through Information: More people better able to access laws and services.		10%	Outputs met expectation (A)
Annual Output Scoring			100%	All outputs scored
Annual Output Score		A+
Annual Output Performance		Outputs moderately exceeded expectation

Key lessons:

    - The effectiveness of the CCCs tends to rise when key decision-makers from the main agencies[6] are present. For example, the District Judge and Deputy Commissioner, in a number of CCCs, made it mandatory for the key members of the main agencies to be at each CCC, rather than their deputies.
      [6] Such as, but not limited to: Police, Prisons, District Administration, Public Prosecutor, District Judiciary and Medical Department.
    - Working with institutions like prisons requires the capacity to be flexible and sensitive to the concerns of the prison authorities. The heightened security situation in the second half of the reporting year caused access to the prisons for some of the project’s activities to be limited and therefore impacted the achievements in that area.
    - Exposure visits help to demonstrating the potential impact of reform to senior decision-makers, for example the visit to training academies for prison officers and wardens in India has galvanised the Prison Directorate to move towards drafting a modern training curriculum.
    - Timing and location of Restorative Justice sessions are important for the safety and security of women attempting to resolve disputes at the district level. In order to be considered gender sensitive, RJ sessions must take place at a neutral place and be finished by 3pm to ensure women can return home in the daylight. There are safety implications for women travelling to and going to court – long waits, travelling late or early and unreliable trials.
    - The integration of Value for Money analysis continues to help the monitoring system and tools and the financial management system, and ensures that the implementing partners will also focus on outcomes rather than solely inputs and outputs.

Key actions:

The monitoring tools of the project reported following progresses.

During the reporting year, the project expanded its work from 20 to 30 districts and 33 prisons. A2J is now working with nine implementing partners[7] and has trained and deployed 220 paralegals, of whom 33% are women. The project has established CCCs in 30 districts and contributed to reduce case backlog by 51% from the cases that were identified by them. To date, 4,796 cases have been diverted from the formal justice system and the police, 54% of which have been sent to the community for mediation and 34% have been diverted to village court[8]. 2,328 prisoners were provided skill development training in marketable trades, deepening relationships with private organisations in this area, and 1,854 were provided motivational and life skills training. Overall, 8,565 prisoners were identified as having problems with drug abuse and counselling has been provided for both the prisoner and their family for those needing it. 5,803 were referred to rehabilitation services.
[7] Bangladesh Legal Aid and Services Trust (BLAST), BRAC, Madaripur Legal Aid Association, RDRS-Bangladesh, Dhaka Ahsania Mission (DAM), Agragati Shangstha, Light House, Friends In Village Development Bangladesh (FIVDB), Association for Community Development (ACD)
[8] Village Courts are the lowest administrative unit of the judicial system in Bangladesh.

The project continues to support the Inter-Ministerial Committee meetings that were introduced by the Home Affairs and Law Ministries in 2014. The objective of these high level committee meetings is to find joint solutions to case backlog, prison overcrowding and options for legal reform. The Ministers of MoLJPA and MoHA head the meetings together with the engagement of representatives from MoHA, Police, Prisons, and the Justice and Legislative Division at the highest level. The fourth meeting took place in June 2016. Points of discussion were partnerships for Legal Aid Services, legal and policy reform (specifically the amendments of the Prisons Act and Jail Code) and a national RJ policy.

Has the log-frame been updated since the last review?

Yes, the log-frame has been revised to broaden the scope of the impact indicator, and one outcome indicator has been changed following a number of discussions between DFID and GIZ in mid-2016. These changes stem from the recommendations in last year’s report to revise the outcome indicator to one that measures changes that can be influenced by the project, as well as from the recommendation from Independent Commission for Aid Impact (ICAI) to change the indicator as there are too many other factors that influence the original one.

While the impact statement remains unchanged, its scope has been broadened to link it with the Sustainable Development Goal 16[9], regarding peace, justice and strong institutions. The original impact indicator has been changed, as it was felt that the “number of households” was not reflective of the overall impact of the project. Two new indicators are suggested, which include the Rule of Law Index (RoLI)[10] and the Index Gender Development (GDI)[11]. The RoLI measures country performance using 44 indicators across eight primary rules of law factors including Criminal Justice, Absence of Corruption, Open Government, Fundamental Rights, etc. The GDI measures gender gaps in human development achievements by accounting for disparities between women and men in three basic dimensions of human development - health, knowledge and living standards. It has been included to ensure that DFID’s focus on women and girls is included as a key measure of performance. Both these indicators are available on an annual basis for Bangladesh through independent sources such as the World Justice Project and the UN Human Development Report.
[9] Sustainable Development Goal 16: Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions ( https://sustainabledevelopment.un.org/sdg16)
[10] World Justice Project ,Rule of Law Index (ROLI), http://worldjusticeproject.org/rule-of-law-index
[11] The United Nations Development Programme, Gender Development Index (GDI), http://hdr.undp.org/en/content/gender-development-index-gdi

The outcome statement remains unchanged. However, one of the outcome indicators has been changed and replaced, as recommended in last year’s review, with one which is better able to track the influence of the project on the outcome statement. This new indicator for the outcome level is the original indicator for the impact level, as it was concluded that it is a better reflection of the outcome, rather than impact, of this project. It reads; “Number of households, especially those of prisoners, poor and women, benefitting from improved access to accountable, efficient and effective justice services.” The original outcome indicator, “X % of under-trial prisoners reduced in target prisons”, is influenced by several factors beyond the control of the project. This indicator has therefore been removed. These changes have accepted by DFID as these do not compromise the commitments made under this project.

## C: DETAILED OUTPUT SCORING

Output Title	Paralegal Aid Services (PAS)
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s) as per log-frame	Milestones	Progress (Current Year)
Number of districts	30	30
# released under-trial prisoners	3,200	4,221
# Paralegal Service activities	144,000	147,686
# persons assisted at court	64,000	66,586
# persons assisted at police stations	5,000	5,644
Criminal Cases identified by CCC as backlog are reduced by 10% in 10 districts	25%	2,154 cases presented in the 10 oldest CCCs; 51% of backlog cases were resolved

Case Study on Paralegal Advisory Services (PAS):

Taher Ali, 60, was convicted of theft in 2004. His conviction warrant was not issued and he was sent to prison on a custody warrant. The prison therefore could not fix a release date, and so Taher was left inside, forgotten, until the paralegals found him 12 years later. Taher case was included in the list of long pending cases at the 7th CCC meeting in Moulvibazar district. The Honourable Joint Chairs asked the committee to take steps immediately to expedite the process of his release, but Taher’s documents could not be found. Instead, based on the evidence of the register in the General Registry Office, the Chief Judicial Magistrate was able to reconstruct a shadow document from the General Diary and a conviction warrant was issued by the Court the very next day. Taher was released in October 2016, after being in prison for 8 years longer than his sentence. / Taher’s children are now grown up. While in prison, his wife had taken a brave step to leave her remote village and start a job as a support staff in Dhaka in order to support the family. Taher is now fully dependent on his wife’s income. However, in his long tenure inside prison, he learnt some weaving and carpentry skills through training sessions, so he is looking forward to starting a business soon with these new skills.

Key Points

The Paralegals and the CCCs are the two main activities for this Output. There are currently 220 Paralegals (73 women, 33%) deployed in 30 project districts and 33 prisons. The project places a special focus on recruiting women paralegals in a male dominant environment. On average each paralegal assisted 268 people during the reporting year. The growing credibility of the paralegals enabled them to be more effective in various locations to provide legal assistance at courts, police stations and within prisons, in which Paralegal ‘activities’, or actions, totalled 147,686 this year. These actions are necessary for moving cases through the system. The work of the paralegals has brought to the fore the need for reform of the Prisons Act 1894 and Prisoner’s Act 1900 and led to a growing recognition of the need to examine the prison system not as a “space where people are confined, but as centres of correction”[12].
[12] The Prime Minister of Bangladesh, Daily Star newspaper, Bangladesh, 11 April 2016, http://www.thedailystar.net/city/pm-prisons- correction-centres- 1207423
The approach to assist people outside prison has also been effective in helping a 123,824 people at courts, and 14,159 people at police stations since the inception of the project. Of these, paralegals pay particular attention to women’s cases and give them priority where possible due to the specific difficulties faced by women in legal disputes, especially those with a family. Paralegals have assisted 43,185 women at courts and 4,143 women at police stations. This is a very high proportion considering the low numbers of women that attend courts and police stations to resolve disputes.
The CCCs are currently active in all 30 of the project districts and are jointly chaired by the District Judge and District Commissioner. Their decisions have assisted in reducing the backlog of cases through the more timely submission of police and medical reports, more frequent appearance of witnesses in courts and active identification of cases requiring legal assistance.
The project commissioned a study[13] to examine the work of the CCCs which concluded that at the district level, various decisions had been made within the CCCs which proved them as instrumental in moving cases forward in the districts, such as (a) establishing a proper communication system between relevant institutions to ensure a smoother trial process (b) ensuring that witnesses are reachable through the mandatory inclusion of mobile phone numbers in the police reports, and (c) arranging monthly court dates to avoid the prisoners always being ‘on-call’.
[13] Hasan M. et al. Study on CCCs, established by A2J. 7th August 2016.

At the national level, CCCs have demonstrated an impact, such as (a) encouraging inter-ministerial discussion on policy and practice issues and (b) identifying evidence of actual blockages in the criminal justice system pipeline. A long term concern of many CCCs is the fragmented legislation on prisons; CCCs frequently discuss the need for a comprehensive Jail Code which brings together the Prisoners’ Act, No. III of 1900, the Prisons Act No. IX 1894 and the Jail Code 1864. In the last Inter-ministerial meeting this was discussed in detail, and relevant counterparts went on a study mission to prepare for this to happen. Next steps on the comprehensive Jail Code will be discussed in the Inter-ministerial meeting in early 2017. Since the inception of the project, there have been over 500 CCC meetings with a multitude of stakeholders from various justice institutions supported by paralegals. Combined, this represents over two years of work by Government officials, outside both the scope and time of their jobs, looking at local solutions to local problems to reduce the case backlog and the prison population in their districts.

Summary of responses to issues raised in previous annual reviews (where relevant)

The recommendations made in previous reviews were both about the sustainability of the work that the paralegals do: identifying opportunities for making functions performed by paralegals sustainable; and strategizing whether paralegals could be sustainably integrated into the justice system. These were both considered by a CCC study commissioned by the project, which looked at different approaches for the sustainability of paralegals in the justice system and identified specific potential future options. These include (i) Placing the paralegals under the District Legal Aid Officer with adequate budgetary allocation from National Legal Aid Services Organization (NLASO); (ii) The continuation of the paralegal service under NGO management financed by a separate fund managed by the District Legal Aid Office; (iii) Providing the paralegals with a long-term career path, making them self-sustaining by offering their services for a fee under formal recognition by the Judiciary as a legitimate professional cadre. However, it is challenging to find an option that integrates the paralegals within a sustainable structure, yet enabling them to function relatively independently and with the same authority to enter the prisons and do their work as they currently have. The sustainability of paralegals is also being actively considered in various stakeholder forums and was also discussed at the Inter-Ministerial Meeting held in June 2016. The digitisation of the criminal justice system is one identified way to make the functions performed by the paralegals sustainable.

Key recommendations

Recommendation 1: Present the findings of the CCC study to key Government decision-makers at the National level, for enhancing the sustainability of the CCCs, and incorporate policy changes in a policy matrix for improved policy dialogue with key stakeholders. By June 2017.

Recommendation 2: Pilot working approaches recommended in the CCC study between the paralegals and National Legal Aid Services Organisation (NLASO)/District Legal Aid Committee (DLAC) in selected districts to strengthen Government legal aid , and explore paralegal sustainability options. By October 2017.

Recommendation 3: Pursue opportunities for partnership with the Supreme Court Legal Aid Committee (SCLAC) for matters related to jail appeals, as poor prisoners await the final result of their appeal for a long time. Such a partnership should help release people from prison earlier and reduce case backlog. By November 2017.

Output Title	Restorative Justice
Output number per LF		2	Output Score	A++
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
# matters resolved within the community using RJ and Mediation techniques	1,200	3,800 (2,158 mediation, 1,642 RJ )
# matters diverted from the formal CJS	1,550	2,143

Case study on Restorative Justice and Mediation
Roksana was happily married to her husband Panna. In 2015, her sister’s husband Jahangir borrowed 25000 taka from her and promised to pay her back within 6 months. However, months passed, and Jahangir did not repay the money. He also stopped coming over to Roksana’s house. After a while, Roksana started pressuring her sister to pay back the money. Still, Jahangir’s excuses were endless. The two sisters started getting in heated arguments, Roksana and Panna started having disagreements. / After a year, Panna and Roksana threatened Jahangir with a lawsuit if he failed to pay their money back. Roksana went to Local Union Parishad member Laili Begum to seek advice on legal matters. Laili Begum advised Roksana to consider resolving the matter through Restorative. After negotiating with Panna and Roksana, the RJ facilitator held meetings with Jahangir and his wife. Eventually on 25th May, 2016 a final meeting was organized. Both Roksana and Jahangir decided that Jahangir would pay 23000 of the borrowed 25000 taka. Roksana said in front of everyone that she relinquished the amount of Taka 2000 considering the financial condition of her sister’s family. Jahangir and his wife also apologized for not paying back the money in due time and promised never to repeat this act. Roksana is grateful that even after such a dispute, her relationship with her sister and her husband continued to thrive, all because of Restorative Justice.

Key Points

The milestones of this output have both been substantially exceeded. This is due to the growing acceptance of the Restorative Justice facilitators and the concept of mediation as a legitimate alternative form of dispute resolution growing momentum. This component has results from 8 districts for this reporting year but activities have now been rolled out to 10 districts, despite difficulties faced due to the heightened security situation, at various administrative levels. There are now 4,878 mediators, of which 35% are women. The project has a growing team of 649 RJ facilitators, of which approximately 30% are women.

The percentage of the total number of matters resolved within the community, when both victim and perpetrator have come to an agreement and a decision has been implemented, using RJ, rather than old mediation process, has increased from 863 (29%) in 2015 to 1,642 (43%) in the reporting year. This is an important impact as RJ focuses on both victim and perpetrator, with the perpetrator repairing damage caused to the victim and the community. Mediation is the first step in this process. It is evident that there is rising acceptance of RJ in the communities of the project working districts. This is beneficial also because RJ is more gender equal than some mediation practices. Under both the RJ and Reducing Recidivism outputs, 47% of the frontline project staff are women. Further, 34% of RJ Facilitators providing voluntary services to the project are women, and 51% of the master trainers used as resource persons for RJ trainings are women.

Workshops on the local criminal justice system and RJ with a focus on gender issues continue to be conducted yearly for the UP Chairman, Members and Members of the community based organisations. To date, 48 workshops have been conducted at the Union Parishad offices under the project working areas to ensure people involved with local mediation processes have knowledge on gender and inequality issues along with relevant laws and procedures. These workshops have seen an average of 32.24% women participation.

This output continues its diversion activities from the various institutions at district level, including the police and the Union Council/Parishad. In order to raise more awareness about the availability of these services at the local level and facilitate the process through inclusion of more stakeholders, the project supported a series of meetings with DLAC, which has the mandate to resolve cases through mediation. The project is exploring ways of expanding the impact in its working districts, for instance by developing informal partnerships with police officials at district and sub-districts (Upazila) levels to strengthen the opportunities for diversion for compoundable cases from the police station back to the community. Two workshops were held with the police in the reporting year, which have included the village police. These police are able to provide a better linkage between the RJ Facilitators and the police stations to encourage diversion.

The RJ and mediation cases that were resolved in the current year comprised of petty assault, fraud and personal property damage. A breakdown of the cases initiated in the reporting year shows that 34% of the 3,800 cases resolved were initiated by women. 57% of the cases were resolved through mediation while 43% were resolved through RJ. The majority of the cases concerning women were cases of petty assault, injury, demand of dowry and fraud.

Table 2: Restorative Justice and Mediation (2016)
Categories of Complaint/Conflict	Number of Applicant			Number of Opponent			No. of Successful Mediation	No. of Successful RJ	Total
	Total	Male	Female	Total	Male	Female
Petty assault	1281	918	363	1281	946	335	782	499	1281
Crop Damage	106	74	32	106	85	21	79	27	106
Personal Property Damage	668	448	220	668	522	146	307	361	668
Fraud	865	631	234	865	728	137	295	570	865
Harassment	360	269	91	360	307	53	286	74	360
Early marriage	0	0	0	0	0	0	0	0	0
Gambling	21	8	13	21	17	4	8	13	21
Threat of Assault	47	42	5	47	44	3	47	0	47
Others	16	12	4	16	16	0	14	2	16
Sub Total	3800	2526	1274	3800	3074	726	2158	1642	3800

It is to be noted that the number of cases resolved does not fully capture the process of negotiation and facilitation that is required to resolve some of the cases. While the cases may take many sittings to resolve, through the active role of the Union Organizer, the RJ Facilitator and other members of the community, it can be resolved without incurring any costs. More importantly, the methods used are able to reduce conflict within local communities, families and friends. RJ has been a very powerful instrument in resolving community issues and ensuring that relationships are restored.

Summary of responses to issues raised in previous annual reviews

The previous review pointed to the need for careful monitoring and follow-up of the RJ facilitators by the partner NGOs to ensure that the processes of RJ facilitation were being closely adhered to. The project has developed guidelines and a quality assurance checklist that is now being used in all RJ sessions. This checklist ensures that all the important requirements of an RJ session are met, and provides a learning opportunity for the facilitator if for some reason they are not. Further, quarterly quality assurance visits to the field are now conducted in order for project staff to individually monitor partner NGO staff to be able to give instant feedback to facilitators to improve the outcome of RJ sessions.

Output Title	Strategies for Reducing Recidivism
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
x number of identified suitable prisoners attend skill development training	1,500 vocational skills	1,332 / (1,179 inside, 153 outside prisons)
	3,120 motivational skills	1,854
x number of drugs/alcohol related cases referred	1,900	2,687

Case study on Strategies for Reducing Recidivism:
Jamal Uddin (31), who lived in Bangshal, Dhaka with his family, lost both his parents early in his life and was introduced to drugs at a young age. He stopped studying after his school exams and became addicted to multiple drugs. As a result, Jamal Uddin grew distant from his family. In January 2016, Jamal was arrested for possessing drugs. He met project staff in prison. They motivated him to undertake drug addiction treatment outside the prison through counselling. Jamal agreed to tackle his drug addiction. After one month, he received bail and met with the rehabilitation supervisor cum counsellor. With the consent of Jamal’s family, A2J project arranged his admission into the Drug Treatment and Rehabilitation centre of Dhaka Ahsania Mission. Counselling was also given to Jamal’s family in order to create the suitable environment for him to come back to. After successfully completing the treatment, Jamal Uddin started to lead a drug free life. He contacted the project staff hoping to get a job in the Rehabilitation Centre to help people like his former self. A job was arranged for him in the Drug Treatment and Rehabilitation centre of Dhaka Ahsania Mission and he started working as a Trainee staff member. Jamal Uddin is now a productive and earning member of the family and an inspiration to others.

Key Points

This output moderately did not meet expectation. It focuses on rehabilitation and the reduction of recidivism through a number of specific services: skills development training inside and outside prison, life/motivational skills training and counseling and referrals and treatment options for drug dependent prisoners. This output’s results come from the 8 working districts; the project has rolled out to two new districts this year (Rajshahi and Sylhet) despite the difficulties highlighted below. It is particularly difficult to measure the actual rate of recidivism due to the lack of a proper system and the limited resources to track a prisoner through the various criminal justice institutions.

The project faced some challenges this year which affected the results of this output. For example, the prison authorities stopped all skills development training inside prison for a few months, and then allowed it again late in the year but in only three districts instead of the 8 working districts. This decision was taken due to the heightened security concerns in the country at the time, which means that the already understaffed system found it even harder to move and manage groups of prisoners to and from training, and could not consider this training as a priority over security. Besides this, the availability of convicted prisoners for skills development training was also limited as the jail authorities assigned these prisoners for many prison duties. However, 1,332 prisoners were provided skills development training both inside and outside prison in the reporting year, such as electrician training and training for men to work at beauty parlour. Out of the trained prisoners, 574 prisoners were released in the reporting year. The project tracked 326 trained prisoners after they had been released. 34 people were not yet employed. However, 3o% of those who were employed were not employed before entering prison, generating an increase in employment of 30% after the training. The average income of those employed who were also employed before entering prison had increased by 12%. The project expects that the Government will give permission to expand access back to the 8 working districts but it is not yet clear when this may happen.

The project is providing life skills training, called motivational skills by the Prison Authorities. This training focuses on supporting the successful transition of prisoners back into the society following their release. Life skills training such as problem solving, decision making and mental stress management was arranged for 1,332 under-trial and convicted prisoners in the 8 working districts. A training of trainers (ToT) was provided to NGO staff early in the reporting year to conduct the life skills training, however approval from the prison authorities for these trainers to access the prison was only given from August, thus delaying the impact. The project continues to work with drug and alcohol related cases and providing referrals combined with counseling services. Referrals for drug dependent prisoners have been provided to 2,687 prisoners. The project tracked 156 people who were referred, given counseling or given medical support. Of these, 61% were reported to be earning an income.

The project is working on increasing the collaboration between the Department of Narcotic Control (DNC) and the Prison Directorate, and consequently DNC provided guest facilitators for the three-day training organized by the project. The project also helps to institute quarterly DNC meetings with local drug rehabilitation centres, civil surgeons and relevant prison officials to discuss drug abusers’ treatment and rehabilitation options.

A special budgetary allocation has been made in the PNGO contracts for the extremely vulnerable and marginalized people, especially women, children and persons with disabilities. This is to ensure holistic support for their rehabilitation and reintegration back into society. Further, there is now one female counsellor as well as a male counsellor at each prison site in the project districts.

Summary of responses to issues raised in previous annual reviews

The previous annual review recommended that the project establish a mechanism for their partner NGOs to track 30% to 40% of the prisoners who completed skills development training and 5% to 10% of those being provided with referral services and “life skills” upon release, and raise awareness about the incidence of prisoners suffering from mental health issues with the relevant prison officials.

The prison authorities recognize the mental health of prisoners as a significant issue. They are considering the baseline study for this in 2017. In the meantime, the project undertook a research study that aims to further highlight the need for counselling and therapy. It is anticipated that the prison authorities will allow the study inside prisons in the next reporting year. This will enable the project to triangulate results and share findings with key prison officials.

Key recommendations

Recommendation 4: Foster the relationship between the departments under the Ministry of Home Affairs, such as Prisons, Police and Directorate of Narcotics Control (DNC), for better coordination of activities. Facilitate joint-up planning and implementation between the DNC and the Prisons to ensure sustainability. By October 2017.

Output Title	Outreach and Empowerment
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% of under-trial prisoners understand law and know how to improve situation	30%	49%
% of prisoners in pilot districts with treatable problems know where to go.	30%	71% of treatable drug dependent prisoners know where to go for treatment.
Media campaign to reach 5.76 million people, including women, under-trial prisoners and ex-offenders with information on how to better access laws and services	Media campaign with outreach to 1 million people in 2016.	Media campaign has had an outreach to 3,126,144 people (print media: 2,110,963 print materials: 298,760; community radio: 579,840; courtyard meeting: 102,381; forum theatre: 34,200)

Key Points

The project has exceeded progress on all three indicators under this output. Overall, since the inception of the project, the project has organized 5,274 Paralegal Aid Clinics (PLCs), in which 60,392 under-trial prisoners have attended. The total number of participants in the sessions including repeat attendees takes the number to 126,785. 25% of participants in the PLCs are women, and women also attended the repeat sessions in much greater numbers. Of those who attend these sessions, 36% were seeking legal assistance, and we referred to the paralegals to both DLAC and the implementing NGOs.
Table 3: Para-Legal Aid Clinics (Inception to December 2016)
No. of PLC		No. of new prisoners attended for first time*		No. of old prisoners attended previously		Total Attended Prisoners			Seeking Legal Assistance
		Male	Female	Male	Female	Male	Female	Total
Total	5274	41,752	14,853	34,142	32,271	79,661	47,124	126,785	20,393
(%)	100%	74%	26%	51%	49%	63%	37%	100%	36%

There are several mechanisms through which the impact of the PLCs is being recorded. Pre and post surveys are being administered to prisoners attending the sessions, and beneficiary feedback surveys have also been initiated by the project. A beneficiary survey administered randomly to 120 prisoners found that 72% of the people in prison had reported that they had attended the PLC. 49% of those attending the session said that they had an improved understanding of the law[14] and 98% were satisfied with what they had learnt.[15] The beneficiary survey also indicated that the course content of the PLC found to be most useful was Government legal aid and bail, with 62% of women reporting that they had found the session on bail the most beneficial to them.
[14] Pre and Post Survey in PLC sessions. 2016.
[15] Beneficiary Feedback Survey of 120 prisoners in 2016.

Table 3: Beneficiary Feedback of PLCs of Topics that were most beneficial.
Topic	Male		Female		Total
	N	%	N	%	N	%
Govt. Legal Aid	22	44.90	13	35.14	35	40.70
Bail	24	48.98	23	62.16	47	54.65
Steps of Criminal Cases and Court Etiquette	1	2.04	0	0.00	1	1.16
Guilty Plea	1	2.04	1	2.70	2	2.33
Compounding	1	2.04		0.00	1	1.16
Total sample	49	100	37	100	86	100

The project has initiated a media campaign using different forms of print and electronic media and has more than reached its target of 1 million people in the current year, reaching 2,110,963. The national level campaign has used a diversified set of products and dissemination strategies. The campaign in the print media is through message dissemination in 30 districts in local newspapers and large posters placed in relevant community areas. Newspaper and poster messages mostly included information on the services, eligibility, and contact information of the NLASO.

The print media campaign is accompanied by the community radio and local level grass-roots campaign in 10 districts. The Bangladesh National Network of Community Radio, a non-profit NGO has been engaged for the community radio campaigns. 10 community radio stations broadcasted project messages in the reporting year, with a combined outreach to more than 579,840 people. The radio messages this year have had a focus on access to justice and legal aid, and the project has taken advantage of notable days, such as the 16 days of activism against violence against women, to broadcast these messages. For the next year, a long term plan has been developed for more regular radio stations on project activities in 10 districts. However, further monitoring is required to assess the real impact this outreach work is having. For this purpose, an independent media monitoring company has been contracted in the reporting year, which will assist in identifying the outreach and actual impact of the highlighted media campaign

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no recommendations made by the last review on this element of the project.

Key Recommendations:

Recommendation 5: Use the findings of the midline survey conducted by the media monitoring agency to refine outreach strategies. These findings should assist the project in improving messages for increased outreach and assess the influence the messages have had on people’s ability to access justice. By October 2017.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers of the project have not changed significantly from the last few years. In 2016, the personnel cost saw a reduction of GBP 195.427,49 due to the departure of some staff members earlier in the year, and due to security reasons, the programme field visits costs have been lower. The operational cost saw a total increase of GBP 232.650,32 in the reporting year. The cost of paralegals incurred by the assigned PNGO remained high and the key stakeholders started to gather in Dhaka instead of the field, which costs more under the head of programme costs. The increase can also be explained by the expansion of the programme to new districts. GIZ has put a system in place to ensure that procurement decisions are in compliance of the procurement rules of BMZ and international quality standards. Technical assistance has been made available through a balance of international and national consultants for enhancing the impact of the project. The capacity of Government staff as well as project and NGO staff has been further strengthened as a measure of sustainability. The project has achieved the majority of its expected targets and is ahead in achieving some of the output targets.

VfM performance compared to the original VfM proposition in the business case

At design the project was expected to have an Internal Rate of Return (IRR) of 68%. The project continues to generate evidence that is required and test this against the assumptions made at appraisal. Some of the key assumptions included the cost to the criminal justice system of imprisoning a person, the opportunity cost of people incarcerated, legal and other costs associated with imprisonment or dealing with the legal system. A2J identified that the actual costs that people incur are significantly higher than estimated in the Business Case and thus the benefits that are expected to accrue are likely to lead to higher value for money metrics. The project recalculated the expected project benefits based on these actual values and continues to find that the Internal Rate of Return of the Project stands at 116%.

Assessment of whether the programme continues to represent value for money

The project continues to represent significant value for money. Having achieved most of its quantitative milestones, the project has shifted its attention to qualitative aspects of its work. It has been focusing on quality enhancement and ensuring the long-term sustainability of the mechanisms it has put in place through policy advocacy, legislative reform, institutional strengthening and providing opportunities for learning and sharing through field experience and exposure to regional and international experience. This focus is likely to have potential impact on the policies and laws governing the criminal justice system in Bangladesh. The project undertook three full day training sessions on VFM in the reporting year: one for relevant Government stakeholders, one for relevant PNGO staff and one for project staff.

Quality of financial management

The Project has utilised €13.02 million or 57% of the total DFID allocation until December 31st, 2016. The project has established a strong financial system that routinely assesses its expenditure patterns and forecasts. All internal audits, spot checks and external audits of both the project and the service providers were undertaken routinely. DFID’s due diligence guidance on financial management is used as one of the selection criteria in identifying NGOs for implementing project activities. External audit firm undertook spot checks of partner’s field offices to ensure that they are abiding by the terms of the agreement in terms of the staffing, procurement and financial management aspects. However, in recent months, some of these visits have had to be curtailed due to security concerns. However, in the first quarter of 2017, a combined visit is planned. For real-time financial reporting, one PNGO’s financial system has been computerised. The computerised financial bookkeeping and reporting will commence in the 1st quarter of 2017.

Date of last narrative financial report	December , 2016
Date of last audited annual statement	December , 2016

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

The project assesses its delivery, reputational and fiduciary risks on an on-going basis. The delivery risks are impacted by the overall political and security environment in the country, which has further deteriorated over the last year. This has led to a higher security level and restricted movement of staff. The project continues to assess security risks with the support of the Risk Assessment team in the GIZ Bangladesh Country Office. The heightened security situation also leads to an increase in the under-trial prison population as many suspects are simply put behind bars. The terrorist attack in July did not fully hamper the undertaking of daily activities. The work of the paralegals, counselors and rehabilitation supervisors has continued without much hindrance.

However, the heightened risk perception from terrorism has led to the prison authorities to initially cancel, but then significantly reduce the skills development training work of output 3 to only 3 districts, which led to the underachievement of some of its milestones.

The reputational risks that could arise out of poor quality implementation are being mitigated through focus on staff and partner training, supervision and monitoring. A system of random spot checks and data quality management is routinely followed which examines the records of the paralegals and RJ facilitators and mediators. .

Financial risk is dealt with by regular audits at several levels. The project is audited by external auditors and is also subject to audits by the highest auditing authority of the German Government.

Outstanding actions from risk assessment

There are no outstanding actions as the Project is in compliance with measures regarding monitoring, security and financial aspects.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe: Yes

The project is on track to deliver against almost all targets and milestones. The project is currently planning to close the Project by 31st December, 2018.

Performance of partnerships

The main partner of the project is the Ministry of Home Affairs, which approves all its activities. The National Project Director at the Ministry has been supportive of project activities. At a broader level, the project has built partnerships with the Ministry of Law and the Anti-Corruption Commission in the context of the BMZ financed project which is working on policy reform and improved governance. Further, the time given by the Government of Bangladesh to this project emphasizes the ownership and contribution they have toward the objectives.

It is evident that the project has expanded its partnerships at both the national and local level. At the national level, the project has initiated collaboration with the Department of Narcotics Control and the National Legal Aid Services Organisation. At the local level, the project is working with a host of institutions and building partnerships with the Prison Directorate, the Police and the Courts in order to improve their functioning through the CCC. It has recently initiated a dialogue with other affiliated departments such as District Legal Aid Committee, the Department of Social Welfare, the Department of Women’ Affairs, etc., to assess opportunities for further assistance to its target group. The project is now partnering with eight NGOs in the delivery of its activities. While these NGOs are contracted to the project as service providers, the strengthening of their capacity in the provision of justice services is leading to the development of a cadre of trained professionals in the country. The use of Village Courts has also enhanced people’s confidence and recourse to these local mechanisms for dispute resolution.

Asset monitoring and control

The project maintains a record of all assets electronically using the GIZ inventory control software. All inventory items are entered, tagged and can be counterchecked with inventory records and periodically verified physically by the internal and external auditors. While some of the assets are maintained by GIZ at the Project office in Bangladesh, some are being utilised in the field by the PNGO staff. The NGOs asset registers are checked routinely No frauds have been reported to date.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles do not directly affect DFID funding for the A2J project as no funds pass through the government system.  The Principles include a commitment to strengthening domestic accountability that relates closely to the mandate of A2J.  While there are concerns about ongoing political instability, and a contraction of the space for independent media and civil society, there are also some signs of Government of Bangladesh commitment to increasing accountability in some of the areas the project works on, ranging from active engagement at the district and national level with the key stakeholders including the court, police, prosecutors, to improve access to justice services e.g. increasing legal aid provision, reducing case backlog, sharing information, policy and regulatory reform, etc.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The project has a robust system of information management in which beneficiaries are tracked and the basic information regarding the people assisted at the various locations is recorded. The project tracks a certain proportion of those who have been released to assess the impact of skills development training, motivational skills and the extent to which the drug referral advice has been sought. Similarly, all cases that have been facilitated by the RJ Facilitator or mediated are tracked. As per suggestions and feedback from DFID, the project has also tracked each of the key assumptions made about the nature of benefits at appraisal and tracked these over time. The project has data on the socio-economic profile of its beneficiaries and is using this for its cost-benefit analysis. The Counsellors and Rehabilitation Supervisors also track the prisoners who are provided skills development training and drug referral and counselling services and assess the impact of these on job placement, rehabilitation and reduction in recidivism. The project has commissioned a number of studies, which include an assessment of the CCC, a study on under-trial population, and research for media monitoring. Beneficiary feedback surveys have also been undertaken to assess beneficiary experience of various interventions.

Monitoring progress throughout the review period

The project is monitored though various means including supervision by the Project Steering Committee held at the Ministry of Home Affairs, regular bilateral meetings between DFID and GIZ to review project progress and risks, and filed visits. Besides these, an evaluability assessment is scheduled to take place in 2017 to look at the questions we like an evaluation to answer, and what level of evidence there is to base an evaluation on. The Terms of Reference of this assessment will be developed jointly with GIZ.

The Project produces the following reports: Monthly Progress Report, Monthly Key Statistics, Monthly Trend Graphs, case studies, beneficiary feedback tables and tracks the Internal rate of Rate and Net Present Value calculations on Excel Template, Narrative progress and financial reports.

The project has included both qualitative and quantitative data for monitoring. Qualitative data includes case studies from the field which showcase the stories of the people that the project helps on a daily basis.