## 3DF Logframe
PROJECT NAME : | Three Diseases Fund for HIV, TB and Malaria
IMPACT | Impact Indicator 1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
Reduce the burden of communicable diseases in Myanmar. See Comment #1 | HIV prevalence | Planned | 0.63% (NAP Progress Report 2008) | Not set nationally for 2009 See comment #2 | Not set nationally for 2010 See comment #2 | 0.59% | 0.58%
|  | Achieved |  | 0.61% | 0.6% | 0.65%
Source
NAP Progress Reports and HIV Estimates and Projections Myanmar 2008-2015
| Impact Indicator 2 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of sex workers that are HIV infected | Planned | 18.38% (NAP Progress report 2008) | 15.6% See Comment #3 | 14% See Comment #3 | 10% (HIV Operational Plan 2010-2015) | 9.5% (HIV Operational Plan 2011-2015)
|  | Achieved |  | 11.2% | 11.4% | 9.39%
Source
HSS data, NAP Progress Reports
| Impact Indicator 3 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of men who have sex with men (MSM) who are HIV infected | Planned | 28.8% (NAP Progress report 2008) | 27% See Comment #4 | 25% See Comment #4 | 20.5% (HIV Operational Plan 2010-2015) | 19.5% (HIV Operational Plan 2011-2015)
|  | Achieved |  | 22.3% | 11% | 7.75%
Source
HSS data, NAP Progress reports
| Impact Indicator 4 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of injecting drug users (IDUs) that are HIV infected | Planned | 37.5% (NAP Progress report 2008) | 27% See Comment #5 | 25% See Comment #5 | 31.2% (HIV Operational Plan 2010-2015) | 28.7% (HIV Operational Plan 2011-2015)
|  | Achieved |  | 34.6% | 28.1% | 21.91%
Source
HSS data, NAP Progress reports
| Impact Indicator 5 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| TB prevalence | Planned | 169/100,00 (WHO Global TB Control Report 2008) | Not set nationally for 2009 See comment #6 | Not set nationally for 2010 See comment #6 | Under Review - June 2011 | 461/100,000 (2015)
|  | Achieved |  | 598/100,000 | 613/100,000 | Not yet available
Source
WHO Global Tuberculosis Control Reports and Myanmar TB Prevalence Survey (2011 publication)
| Impact Indicator 6 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| TB mortality rate | Planned | 12.3/100,000 See comment #7 | Not set nationally for 2009 See comment #7 | Not set nationally for 2010 See comment #7 | Under Review- June 2011 | 55/100,000 (2015)
|  | Achieved |  | 13/100,000 | 41/100,000 | Not yet available
Source
WHO Global Tuberculosis Control Reports and Myanmar TB Prevalence Survey (2011 publication)
| Impact Indicator 7 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Malaria death rate | Planned | 2.19/100,000 See comment #8 | Not set nationally for 2009 See comment #8 | 1.83/100,000 (per NMCP NSP) | Not set nationally for 2011 | Not set nationally for 2012
|  | Achieved |  | 1.94/100,000 | 1.33/ 100,000 | Not yet available
Source
NMCP Malaria National Strategic Plan (2010-2015)
| Impact Indicator 8 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Malaria morbidity rate | Planned | 8.74/1,000 See comment #9 | Not set nationally for 2009 | 5.56 / 1,000 (per NMCP NSP | Not set nationally for 2011 | Not set nationally for 2012
|  | Achieved |  | 11.83/1000 | 11.7/1,000 | Not yet available
Source
NMCP Malaria National Strategic Plan (2010-2015)
OUTCOME | Outcome Indicator 1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumptions
To resource a programme of activities to reduce transmission and enhance provision of treatment and care for HIV/AIDS, TB and malaria for the most in need populations | Budget (by disease) contributed to the national response by 3DF | Planned | HIV: USD13.8M TB: USD3.4M Malaria: USD4M | HIV: USD 16.65 M TB: USD 6.83 M Malaria: USD 5.91M | HIV: USD 15.02 M TB: USD 2.77 M Malaria: USD 3.44 M | HIV: USD 7,320,508 TB: USD 2,127,684 MAL: USD 3,664,321 INT: USD 877,411 | HIV: USD 1,333,393 TB: USD 856,904 Malaria: USD 190,000 Integrated: USD 51,267 | Wider public health policy and practice improves and is adequately resourced National data is accurate and available Appropriate policy and programmes supported by the Government and all stakeholders Funds are made available by donors National Operational plans and budgets are robust and prioritised Disease specific programmes are effective Government and other resources mobilised
|  | Achieved |  | USD 22.87 M HIV: USD14.06 M TB: USD 5.01 M Malaria: USD 3.80M | USD 22.77 M HIV: USD15.85 M TB: USD 2.501M Malaria: USD 4.41 M | USD 24.5 M HIV: USD 8.13 M TB: USD 3.55 M Malaria: USD11.39 M Integrated : USD 1.43 M
Source
3DF Budget and Expenditure Reports
| Outcome Indicator 2 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of persons at high risk accessing voluntary counseling and testing (VCT): High risk groups – See Comment #10 | Planned | 3,815 (Sex Workers) 1,330 (Men-who-have-sex-with-men) 2,100(people who inject drugs) - See Comment # 10 | 4,703 2,414 2,295 | 4,730 2,560 2,957 | 6,197 2,952 3,909 | 1,739 883 1,415
|  | Achieved |  | 12,444 6,168 (SWs) 2,683 (MSMs) 3,598 (IDUs) | 15,704 7,593 (SWs) 4,358 (MSMs) 3,753 (IDUs) | 19,160 9,730 (SWs) 7,022 (MSMs) 2,408 (IDUs)
Source
VCCT registers
| Outcome Indicator 3 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of people living with HIV in need receiving ART (including package of support) - See Comment #11 | Planned | 6804 | 10619 | 14856 | 16050 | 455
|  | Achieved |  | 9623 | 15,898 M-8,956 F-6,942 | 22001
Source
Facility ART registers/databases
| Outcome Indicator 4 |  | Baseline 2009 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percent of adults and children known to be alive and on treatment 12 months after initiation of antiretroviral therapy - See Comment #12 | Planned | 87% | 87% | 85% | 81% | 82%
|  | Achieved |  | 87% (relates to MSF-H data as the only reporting partner) | All I.Ps reporting above 85% | 87%
Source
Facility ART registers/databases
| Outcome Indicator 5 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of known HIV-infected pregnant women who received antiretrovirals to reduce the risk of mother-to-child transmission in Myanmar - See Comment #13 | Planned | 36% (436/1214) | 17% (450/2600) | 15% (460/3050) | 71% (2,520/3,536) | 75% (2601/3,468)
|  | Achieved |  | 55.4% (UNGASS 2009 report) | 69.11% | 54.3%
Source
UNGASS reports
| Outcome Indicator 6 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| TB case detection rate, by sex - See Comment #14 | Planned | Under Review | at least 75% | at least 75% | 75% | 275/100,000
|  | Achieved |  | 94% | 71% | 87%
Source
National Tuberculosis Prevalence Survey 2011
| Outcome Indicator 7 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| TB treatment success rate by sex - See Comment #14 | Planned | 85% (2008) | at least 85% | at least 85% | at least 85% | at least 85%
|  | Achieved |  | 85% | 83.1% | 85%
Source
National Tuberculosis Annual Reports
| Outcome Indicator 8 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage (and number) of households in project area that have at least 1 bednet - See Comment #15 | Planned | 5.95% (166,499 households) | 7.36% (229,506 households) | 5.11% (320,347 households) | Existing grants = 11.7% (381,567 households) MARC = 35% of Tier 1 area | MARC 35% of Tier 1 area
|  | Achieved |  | 7.14% (230,423) | 12.26% (399,399) | 6.7%
Source
Household bed net ownership questionnaires, net distribution records
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £34.1 million |  |  | Ausaid - £10,244,277 Denmark - £3,229,200 EU - £14,739,913 Netherlands - £4,070,169 Norway - £4,571,087 SIDA - £10,586,240 | £81.4 million | 42%
INPUTS (HR) | DFID (FTEs)
Health Adviser (0.3), Programme Officer (0.05)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumption
Sufficient commodities are resourced and distributed for the three diseases through 3DF activities | Total number of condoms distributed (including those sold) of which: - Commercial Sex Worker - Men-who-have-sex-with-men - See Comment #16 | Planned | 6,610,147 - 1,973,992 (Commercial Sex Worker) - 415,833 (Men-who-have-sex-with-men) -See Comment # 16 | 15,373,000 1,157,680 861,947 | 12,000,000 1,386,950 1,003,439 | 13,500,000 1,200,000 560,000 | 656,100 245,968 4,580 | Disease specific programmes are effective Partners are able to implement to scale across the country Access to national level data is available Activities can be implemented as planned across the whole country Implementation is effective for all partners IP are interested in developing their own in-country distribution and commodity tracking systems.
|  | Achieved |  | 15,790,925 2,412,014 (CSWs) 662,687 (MSMs) | 15,717,355 2,570,684 (CSWs) 602,428 (MSMs) | 13,072,478 2,365,842 (CSWs) 712,211 (MSMs)
Source
Condom distribution reports
| Output Indicator 1.2 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of needles distributed (including those sold) to IDUs | Planned | 1459249 | 1744891 | 2587591 | 6400000 | 2534000
|  | Achieved |  | 2377939 | 2902403 | 5706497
Source
Needle and syringe distribution records
| Output Indicator 1.3 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of LLINs distributed during the reporting period by 3DF Ips - See Comment #17 | Planned | 79361 | 84850 | 199200 | 190,000 MARC = 352,000 (Jul 2011 - Jun 2012) | 41330
|  | Achieved |  | 80159 | 109395 | 411,500 Round1+2+3 = 327,243 MARC = 84,257
Source
LLIN distribution summary reports
| Output Indicator 1.4 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of ITNs/bednets re/treated per reporting period by 3DF Ips - See Comment #17 | Planned | 299732 | 367535 | 409280 | 370,000 MARC = 228,000 (Jul 2011 - Jun 2012) | 85800
|  | Achieved |  | 388887 | 430535 | 371,521 Round 1+2+3 = 365,078 MARC = 6,443
Source
ITN/bednet retreatment summary reports
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
35% | Number of rapid diagnostic tests (RDTs) distributed and used by trained village health workers/GPs and health facilities - See Comment # 17 and 18 | Planned | 351988 | 598545 | 752446 | 750,000 MARC = 372,000 (Jul 2011 - Jun 2012) See Comment # 18 | 298165
|  | Achieved |  | 419334 | 703503 | 733,824 Round 1+2+3 = 665,262 MARC = 68,562
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Routine surveillance data |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Not disaggregated at output level
INPUTS (HR) | DFID (FTEs)
Not disaggregated at output level
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumption
Services are sufficient to address the needs of those most affected by HIV, TB, and malaria | Number of people living with HIV involved in self help groups in project areas, by sex -See Comment #19 | Planned | 4660 | 4535 | 5718 | 15,528 (M-8,689, F-6,839) | 493 (M-243, F-250) | Disease specific programmes are effective Enabling environment prevails Partners are able to implement to scale across the country Access to national level data is available Implementation is effective for all partners
|  | Achieved |  | 8,594 M - 3,743 F - 4,851 | 11,432 M-5,764 F-5,668 | 17,335 M-9,194 F-8,141
Source
Programme monitoring reports
| Output Indicator 2.2 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of persons who have been treated for an STI in this reporting period including: - Sex worker - Men-who-have-sex-with-men - See Comment #20 | Planned | 6,389 (Sex Workers) 2,185 (men-who-have-sex-with-men) | 10,758 5,069 | 10,926 5,132 | 5,653 800 - See Comment #20 | 101
|  | Achieved |  | 11,159 8,157 (SWs) 3,002 (MSM) | 12,292 9,009 (SWs) 3,283 (MSM) | 10,487 6,690 (SWs) 3,797 (MSM)
Source
Facility registers/databases, patient/client records and registers, or other program monitoring tools.
| Output Indicator 2.3 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of people receiving community home-based package of support (without ARV) in project areas, by sex | Planned | 9125 | 9225 | 11205 | 10,937 (M- 5,460, F-5,477) | 1,180 (M- 504, F-676)
|  | Achieved |  | 12,669 M - 6152 F - 6,517 | 14,576 M - 6,992 F - 7,584 | 12,982 M - 6,397 F - 6,585
Source
Facility registers/databases, patient/client records and registers, or other program monitoring tools.
| Output Indicator 2.4 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of HIV-infected pregnant women who received antiretrovirals to reduce the risk of mother-to-child transmission (by 3DF IPs) -See Comment #21 | Planned | 329 (2008) | 627 | 1189 | 316 -See Comment #21 | 70
|  | Achieved |  | 479 | 407 | 404
Source
Facility records/registers
| Output Indicator 2.5 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of new pulmonary TB smear positive cases detected by sex by 3DF IPs | Planned | 34,192 (2008) | 44000 | 46500 | 43359 | Nil
|  | Achieved |  | 41065 | 42,318 M - 27,835 F - 14,326 | 42093
Source
Reports on treatment outcomes, Township TB registers, TB treatment Cards, reports on TB case registration
| Output Indicator 2.6 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of TB suspected cases referred to health facilities, by sex | Planned | 26,089 (2008) | 22035 | 36507 | 40000 | 1,650 (M-1,220; F- 430)
|  | Achieved |  | 16761 | 28539 | 49338
Source
TB laboratory registers, quarterly reports on TB case registration in health facilities, referral records and other program monitoring tools.
| Output Indicator 2.7 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Number of confirmed and probable malaria cases (by age and sex) treated in accordance with national malaria treatment guidelines by project clinics, and/or private franchised clinics, and/or health workers (community or village) in project areas -See Comment #17 and #22 | Planned | 424,270 | 582415 | 689,080 | Existing grants = 565, 000 (M- 285,500, F- 285,000; <5 years of age 63,000, >5 years of age 476,000) MARC = 104,000 (P.f); 50,000 (P.v) (Jul 2011 - Jun 2012) | Pf = 66,714 Pv = 37,971 (M - 66,698 & F - 37,987) (<5 yrs - 10,721& >5 yrs - 93,964 )
|  | Achieved |  | 427020 | 600,059 M<5- 35,528 >5- 328,257 F<5- 24,674 >5- 201,698 | 402,365 Round 1+2+3 = 375,949 M<5- 16,565 >5- 225,090 F<5- 14,153 >5- 120,141 MARC = 26,416 (M<5- 1,282, >5- 14,650, F<5- 1,166, >5- 9,318 )
Source
Clinic records, patient registries, HMIS, CHW/VHW records
IMPACT WEIGHTING (%) | Output Indicator 2.8 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
35% | Number of high risk/priority townships with 3DF supported activities -See Comment #23 | Planned | TB: 325 of 325 Malaria:116 of 180 priority T/S HIV:55 of 76 priority T/S | 325 of 325 118 of 180 priority T/S 55 of 76 | 325 of 325 245 of 280 endemic townships 60 of 76 | 325 of 325 259 of 284 endemic townships (Existing & MARC) 64 of 76 | 25 of 325 29 of 284 endemic townships (Existing & MARC) 27 of 76
|  | Achieved |  | TB: 325 of 325 Malaria:118 of 180 HIV:62 of 76 | TB: 325 of 325 Malaria: 250 of 284 HIV: 64 of 76 | TB: 325 of 325 Malaria: 254 of 284 HIV: 66 of 76
|  |  | Source |  |  |  |  | RISK RATING
|  |  | 3DF activity and coverage data |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Not disaggregated at output level
INPUTS (HR) | DFID (FTEs)
Not disaggregated at output level
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumption
Funds are allocated in line with Fund Board policies and in response to national plans, and are accounted for in a transparent manner | Percentage of FB recommendations implemented by the FM within given deadline | Planned | 100% (2008) | 100% | 100% | 100% | 100% | Wider policy environment reinforces impact and emphasis on key priorities Fund priorities reflect international best practice and learning Transparent and open relationship among FB, FM and IPs Fund management in line with Fund Board policies
|  | Achieved |  | 89% | 94.12% | 92%
Source
3DF Annual Reports
| Output Indicator 3.2 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage 3DF IPs which are either local NGOs, CBOs or civil society organizations | Planned | 13% | no target set - will report exact figures | no target set - will report exact figures | no target set - will report exact figures | no target set - will report exact figures
|  | Achieved |  | 11 (35%) | 11 (33%) | 11 (34%)
Source
3DF Annual Reports
| Output Indicator 3.3 |  | Baseline 2007-2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage (and Number) of audit areas (both FM and IPs) rated as “high priority” by auditors | Planned | 12% (3 for FM, 2007) 10% (22 for Ips, 2008) | 0 for all parties | 0 for all parties | 0 for all parties | 0 for all parties
|  | Achieved |  | Fund Manager 6% (1) I.Ps 11% (27) | 0 for all parties | Not yet available
Source
Audit reports
| Output Indicator 3.4 |  | Baseline 2009 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of IPs “satisfied” with the grant allocation process | Planned | 79% | 80% | 80% | 90% | Not reported in 2012
|  | Achieved |  | 79% | 90% | 78%
Source
Survey by 3DF
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline 2010 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
10% | Percent IPs with at least 5% of grant resources dedicated to M&E | Planned | 73% | 80% | 100% | 85% | 50%
|  | Achieved |  | 2009 budgets disallow such calculation | 72.73% | 56%
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Budget review |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Not disaggregated at output level
INPUTS (HR) | DFID (FTEs)
Not disaggregated at output level
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumption
Fund flow and IP performance are monitored and evaluated | Percentage of IPs for whom the 3DF successfully completes the Performance Assessment Framework per given deadline | Planned | 100% (2008) | 100% | 100% | N/A | N/A | Government enables access for implementation and monitoring Equity, coverage and impact are monitored Implementing partners have capacity to effectively monitor their programmes Fund Manager has effective M&E system in place
|  | Achieved |  | N/A | N/A | N/A
Source
3DF Annual Reports
| Output Indicator 4.2 |  | Baseline 2009 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
| Percentage of relevant indicators received from IPs that are disaggregated by sex and by given deadline | Planned | 42% | 100% | 100% | 100% | 100%
|  | Achieved |  | 42% | 86% | 85%
Source
IP Reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012)
10% | Percentage of actual monitoring visits which occurred of those planned | Planned | 96% (2008) | 100% | 100% | 100% | 100%
|  | Achieved |  | 92% (no travel authorisations were refused) | 82% | 78%
|  |  | Source |  |  |  |  | RISK RATING
|  |  | 3DF Annual Reports |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Not disaggregated at output level
INPUTS (HR) | DFID (FTEs)
Not disaggregated at output level
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2008 | Milestone 1 (2009) | Milestone 2 (2010) | Milestone 3 (2011) | Milestone 4 (2012) | Assumption
Results from 3DF are used to inform program development both internally and externally | Number of presentations at TSGs and CCM meetings about 3DF programmes | Planned | 3 (2008) | 4 | 5 | 3 | 3 | Enabling environment prevails Programme and national strategies are open and responsive Results are synthesized and communicated effectively
|  | Achieved |  | 7 | 1 | 14
IMPACT WEIGHTING (%) |  |  | Source |  |  |  |  | RISK RATING
10% |  |  | 3DF Annual Reports |  |  |  |  | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
Not disaggregated at output level
INPUTS (HR) | DFID (FTEs)
Not disaggregated at output level
Annual, non-cumulative targets are included, unless otherwise noted.
Comment 1: The targets will be those set by the National Programs to which the 3DF will contribute. 2012 impact indicator targets are for the full year, as these targets will transition to the 3MDG Fund.
Comment 2: Myanmar with a low prevalence epidemic concentrated among high-risk groups does not consider HIV prevalence among the general population to be a good indicator for its epidemic. Traditionally, this indicator is reported in UNGASS reports.
Comment 3: 2011 target based on Operational Plan 2011-2015.
Comment 4: The baseline established in the 2007 HSS is based on a small sample and may change with additional data.
Comment 5: National level targets were set during the Global Fund Round 9 application process.
Comment 6: The incidence rate for Myanmar may be readjusted once the results of the National Prevalence Survey are finalised; thus, the prevalence estimates and targets may need readjustment as well. In setting a baseline for its Round 9 Global Fund application, Myanmar used the 1990 TB prevalence estimate of 419/100,000; thus, its goal for 2015 (Year 5) of the Global Fund grant when its second TB prevalence survey is to be conducted is 210/100,000.
Comment 7: The baseline data is from NTP Annual Report 2008 (Published in November 2009). No target set for subsequent years.
Comment 8: The baseline is taken from the draft Malaria NSP 2010-2015. The morbidity and mortality rate are available only for 2007.
Comment 9: The baseline is taken from draft Malaria NSP 2010-2015. The morbidity and mortality rate are available only for 2007.
Comment 10: This indicator is the numerator of the UNGASS Indicator #8. To derive the denominator (number of most-at-risk population included in the sample) a BSS or another specialized survey will be required.
Comment 11: Previously, 3DF collected two similar indicators (Number of people over 13 years old with advanced HIV infection receiving antiretroviral combination therapy, and Number of children aged 0-13 with advanced HIV infection who receive antiretroviral combination treatment). The current indicator within the NAP NSP includes the phrase “include package of support”. However, in collecting this data the NAP does not distinguish between those who receive a package of support and those who do not. 2009-2011 targets are cumulative.
Comment 12: Following the UNGASS guideline, NAP introduced this indicator in July 2009. MSF-Holland 12 month survival data used as baseline.
Comment 13: The numerators and denominators above are based on projections for 2008-2015. 2011 figure is from the 2011-2015 HIV Operational Plan.
Comment 14: The 3DF provides budgetary support to WHO to strengthen TB programs. While the 3DF’s support is instrumental in improvements in the case detection rate and treatment success rate, these indicators are dependent upon successful actions undertaken by the NTP. With all townships covered by DOTS, it is assumed that the case detection rate estimate is based on DOTS coverage. Treatment success rate will only be measured for those NGOs which are supported by 3DF and offer TB treatment. In 2012, the NTP will report Case Notification Rate.
Comment 15: 3DF will only report on its own project areas. In order to correctly calculate the percentage, this will require the relevant IP to either do their own survey or rely on a survey produced by the NMCP. Baseline and targets are calculated on previously collected “population protected by bednets” data, with the assumption that one household has on average 5 family members (using NMCP assumption). 2010 target has decreased due to increase in the denominator due to larger number of total households in the expanded coverage area from 2010. 2011 target is based on 2010 household figures provided by partners, estimated 80% coverage for NGOs and 6.5% for NMCP. MARC indicator wording is "Percentage of household with at least one LLIN per two people in targeted areas".
Comment 16: 2009 target is procurement target for the total number of condoms.
Comment 17: MARC Related Targets. Milestone 3 (2011) targets refer to July 2011 - June 2012 period. Milestone 4 (2012) targets refer to calendar year (January - December, 2012).
Comment 18: The NMCP in its NOP uses the indicators “Number of patients tested for malaria using RDT” and “Quality assurance system on malaria RDT functional”. The indicator used by 3DF is dependent upon the RDT being both distributed AND used; thus, the number of RDTs distributed will exceed those figures used both in the baseline and targets. For MARC targets, there is a possibility of double counting of targets within existing large-scale projects.
Comment 19: “Number of people living with HIV involved in self help groups to provide psychosocial support among them in order to reduce stigma and discrimination” was reported in 2008. 2009-2011 targets are cumulative.
Comment 20: Targets for PSI have not been included due to their use of frequency figures rather than head counts.
Comment 21: UNPFA in 2010 calculated 2 pregnant women each 12 months per 46 townships (1104), but due to capacity issues and community awareness this target was unachievable. 2011 target revised. Targets lowered due to partners phasing out in 2011. Also UNFPA used HIV prevalence among pregnant women 0.98% (HSS 2009) to calculate 2011 target. 3DF supported UNFPA for counselling and testing for 25,000 pregnant women.
Comment 22: The wording for this indicator in the NMCP NSP is “Number of malaria cases (probable and confirmed) treated according to national malaria treatment guidelines”. While the wording for the 3DF indicator is slightly more expanded, it does not change the substantive meaning of the indicator, except that it excludes clinics within public health system. Thus, it is applied to only project areas and can also be included within the reporting on the national response. While the baseline figure is not disaggregated by age or sex, future reporting will be. In 2011, PSI was unable to provide targets by sex and age group. For MARC targets, there is a possibility of double counting of targets within existing large-scale projects.
Comment 23: The 2008 malaria baseline is the number of 3DF townships which are among the 180 malaria priority townships in Myanmar. From 2010 the 3DF reached all 180 priority townships and expanded its coverage beyond aiming at the 280 endemic townships.
* Orange Highlighted baselines were revised June 2011.