Annex A

DFID Rwanda

Business Case and Intervention Summary:
Creation of the National Fund for Climate & Environment

v.1.5

March 2012

Table of Contents

Appendices

1. Logical Framework
2. Economic Appraisal
3. Climate & Environment Assurance Note
Intervention Summary
Title: Creation of the National Fund for Climate & Environment (FONERWA)
What support will the UK provide?
UK support will enable the creation of a National Fund for Climate and the Environment in Rwanda. / The creation of the Fund is an integral part of the recently approved Government of Rwanda’s National strategy for Climate Change and Low Carbon Development.[1] The Fund is identified in the strategy as a vital enabling pillar for implementation. / The UK will support the operation of the Fund for an initial period of 2 years at an estimated cost of £1.5 million. These funds have already been identified and approved in the DFID Rwanda Operational Plan and the concept note was approved by the International Climate Fund (ICF) Board in July 2011. This is an innovative intervention and evidence of impact is currently limited. Therefore £200k will be earmarked for in-depth impact evaluation.
[1] Republic of Rwanda: Green Growth and Climate Resilience, National Strategy for Climate Change and Low Carbon Development, October 2011

Why is UK support required?
Rwanda is highly vulnerable to climate change as it is strongly reliant on rain-fed agriculture both for rural livelihoods and its significant exports of tea and coffee. The country has experienced a temperature increase of 1.4°C since 1970, higher than the global average, and can expect an increase in temperature of up to 2.5°C by the 2050s from 1970. Average annual rainfall may increase by up to 20% by the 2050s from 1970, increasing the risk of landslides, crop losses and damage to infrastructure.[2] / Rwanda also imports all of its oil-based products so any increase in oil price has a significant negative effect on GDP and economic growth.[3] Rwanda is fortunate in that it has large, untapped clean energy resources, in the form of geothermal, hydro and solar, which have the potential to meet Rwanda’s electricity needs and replace oil-fuelled power plants. This could offer domestic energy security and support socio-economic development whilst significantly reducing greenhouse gas (GHG) emissions that contribute to global climate change. / The Government of Rwanda is determined to set the economy on a low carbon and climate resilient development trajectory. DFID have been working with the Government in support of its climate and environment objectives since 2009, most recently in the development of a National Strategy for Climate Change and Low Carbon Development which was approved by the Rwandan Cabinet in October 2011. The challenge Rwanda now faces is in implementation of the Strategy. / The initial implementation phase needs to focus on creating and building institutions that will enable Rwanda to access international and bilateral climate finance, mainstream climate resilience and low carbon development into the national development plans and achieve its vision of being a low carbon and climate resilient middle income economy by 2050. A key recommendation from the Strategy was the creation and operation of a National Fund for Climate and the Environment. / The rationale for the Fund stems from growing recognition amongst both donors and recipients that a coordinated, streamlined approach to climate financing is needed to respond to developing countries’ adaptation and low carbon needs, and that such coordination would best be achieved through a ‘devolution’ of management to developing country governments.[4] The purpose of the Fund is therefore to facilitate and coordinate access to domestic, bilateral, multilateral and international climate funding streams and align them with national development programmes that contribute to low carbon development and climate resilient growth in Rwanda. The Fund, recently enabled in Law[5], will be an integral part of the Rwandan government and financial institutional architecture and could also promote new and innovative ‘green’ private sector initiatives. / DFID Rwanda support will be used to establish and run the Fund for an initial two year period. We will do this by direct procurement of a team of international and national experts. The team will be tasked with securing long term financing for the Fund’s operation after the initial two year start up period, as well as capitalisation of the Fund. We hope to be in a position to capitalise the Fund from the ICF within 1 year of its operation. This will be the subject of a separate Business Case to be submitted by the end of this financial year. / The opportunity to support this intervention exists due to the strong commitment by the Government of Rwanda to address the effects of climate change and drive low carbon growth.
[2] Ibid.
[3] Econometric modelling conducted as part of the Baseline Report to inform the National Strategy, (unpublished) suggests that a 10% increase in the price of oil will lead to a reduction in GDP by 1.5%
[4] Capacity Development for Development Effectiveness Facility (2010) op cit; Agulhas (2011) Realising the Potential: Making the most out of climate finance - A synthesis report from six country studies: Cameroon, Ghana, Kenya, Morocco, South Africa and Tanzania, Draft report to OECD, http://www.oecd.org/dataoecd/27/38/48597031.pdf . Similar funds to that proposed by Rwanda have recently been, or are in the process of being, established in Indonesia, Bangladesh, Brazil and Ethiopia
[5] FONERWA Law (reference to follow)

What are the expected results?
The intended impact of the programme is wealth creation and poverty reduction in Rwanda through low carbon and climate resilient economic growth. / The expected outcome is that Rwanda is able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development in line with the National Strategy for Climate Change and Low Carbon Development. / The programme will contribute to the outcome through supporting the operation of the Climate and Environment Fund for the first two years. Specific outputs will be: (1) securing capitalisation of the Fund from government of Rwanda, development partners and other sources; (2) building national capacity for managing the Fund, through technical assistance; (3) facilitating Steering Committee decisions on early proposals approaching the Fund for support through day-to-day administration and quality assurance; (4) monitoring and evaluation of Fund results. / Expected results are: / A minimum of £4m resources mobilised for Rwanda’s climate and environment objectives by August 2014 / Strengthened national capacity for managing the Fund: at least 70% of the Secretariat comprised of trained national staff by August 2014 / Decisions reached on a minimum of 15 proposals by August 2014 / Evaluation of early Fund results carried out by early 2015 / The initial 2-year operation of the Fund will be attributable to DFID. The longer term impact of the fund will be attributable to future contributors and the Government of Rwanda.

Business Case
1. Strategic Case

A. Context and need for a DFID intervention / The economic impacts of climate variability are already being felt in Rwanda and these are predicted to get worse[6]. Recent analysis shows that there is an urgent need to protect development gains made so far, and strong economic incentives to set Rwanda on a low carbon development trajectory[7]. / Rwanda is currently highly vulnerable to climate change particularly given its strong reliance on rain-fed agriculture, both for rural livelihoods and exports of tea and coffee. It also depends on hydropower for half of its electricity generation, a driver of economic growth. The country has experienced an average temperature increase of 1.4°C since 1970, higher than the global average, and can expect an increase in temperature of up to 2.5°C by the 2050s from 1970.[8] Rainfall is highly variable in Rwanda but average annual rainfall may increase by up to 20% by the 2050s from 1970.[9] Projections for East Africa over Rwanda and Burundi show an increasing trend in rainfall intensity for both rainy seasons which is likely to cause floods and storms which result in landslides, crop losses and damage to infrastructure. Temperature rise may increase the spread of vector-borne diseases, impacting on animal and human health, and could negatively affect crop yields, impacting food security and export earnings. Higher temperatures result in higher altitudes at which tea and coffee can be grown, which will significantly impact the land available for tea and coffee, and may result in land use conflict. / Rwanda also imports all of its oil-based products so any increase in oil price has a significant negative effect on GDP and economic growth. Rwanda is fortunate in that it has large untapped clean energy resources in geothermal, hydro and solar, as well as a large methane gas resource in Lake Kivu. Together these have the potential to meet Rwanda’s electricity needs and replace oil-fuelled power plants. This would have the co-benefit of providing domestic energy security and supporting socio-economic development whilst significantly reducing greenhouse gas (GHG) emissions that contribute to global climate change. The challenge Rwanda now faces lies in financing the exploitation of these energy resources and funding activities that help improve resilience to future climate impacts. / The Government of Rwanda approved a National Strategy for Climate Change and Low Carbon Development on the 14th of October 2011. The Strategy, produced with DFID support, represents the first phase of a national programme designed to place Rwanda on a low carbon and climate resilient growth trajectory and is a pivotal moment in Rwanda’s development. The Strategy provides the framework for climate change and low carbon development to be incorporated into the next Economic Development and Poverty Reduction Strategy (EDPRS II) which will be drafted in 2012. The government now faces the challenge of implementing and funding the Strategy, and has requested donor support in order to do so. / This challenge is made harder by the fact that, despite significant international commitments, the international climate finance landscape has become complex and fragmented, with a proliferation of multilateral climate funds. There is a growing recognition that a more coordinated approach to climate financing is needed to respond to developing countries’ adaptation and low carbon needs, and that such coordination would best be achieved through a ‘devolution’ of management to developing country governments[10]. / In order to respond to the needs set out in the National Strategy for Climate Change and Low Carbon Development and streamline incoming climate finance, the Government of Rwanda has created the legal framework for a National Fund for Climate and the Environment. The aim of the Fund is to secure resources to implement the Strategy, through facilitating and coordinating access to bilateral, multilateral and international climate funding streams and aligning them with national development programmes that contribute to low carbon development and climate resilient growth in Rwanda. The Fund will also promote new and innovative ‘green’ private sector initiatives. / DFID support to the Government of Rwanda’s climate change objectives, as set out in the National Strategy, contributes directly to DFID’s Business Plan 2011-2015 commitment six: ‘Combat Climate Change’, and specifically to commitment 6.2: ‘Support developing countries’ adaptation and low carbon growth’. It is also aligned to every one of the strategic objectives and ministerial priorities laid out in the International Climate Fund’s Implementation Plan 2011 – 2015.[11] / Evidence underpinning intervention / We understand the potential impacts of a changing and increasingly variable climate in Africa[12]. And we are beginning to understand the potential economic impacts[13]. We know that additional resources are needed, and resources have been committed. However, developing country governments are finding it difficult to access these funds and turn them into concrete actions and results. / Coordinated cross-sectoral funding for climate change is innovative. Few developing countries have developed a comprehensive Climate Change and Low Carbon Growth Strategy, and fewer still have experience of implementation through coordinated funding.[14] Evidence of whether it will work is extremely limited. Despite this there is strong appetite at international level for interventions that strengthen developing country governments’ capacity to manage and coordinate climate funds.[15] / In the region and globally there are other donors working on similar initiatives in developing countries, often in partnership with DFID.[16] These are at various stages of development but none is yet advanced enough to be able to demonstrate effectiveness. None that we are aware of are up and running in Sub Saharan Africa. / In Rwanda, DFID is currently the only donor seriously pursuing this approach. There are other initiatives that support climate change action and policy in various sub sectors but these remain largely uncoordinated.[17] / Due to the limited availability of evidence we will develop an in depth impact evaluation programme to accompany the programme. The results of this will be used not only to improve the effectiveness of the Fund but to feed into the design of similar interventions in other developing countries.
B. Impact and Outcome that we expect to achieve / The expected outcome is that Rwanda is able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development in line with the National Strategy for Climate Change and Low Carbon Development and the Economic Development and Poverty Reduction Strategy. / By supporting a cross-sectoral approach to implementation of the Strategy, in line with government objectives, future climate and low carbon development funding in Rwanda will be able to achieve results across all sectors of the Government of Rwanda’s Economic Development and Poverty Reduction Strategy. / The intended impact is to contribute to wealth creation and poverty reduction in Rwanda through low carbon and climate resilient economic growth. / Supporting the implementation of the National Strategy will help protect other DFID funding streams such as General Budget Support and Sector Budget Support against the risks associated with climate change and climate variability.
[6] ‘Review of the Economic Impacts of Climate Change in Rwanda’, Stockholm Environment Institute (SEI) 2009, DFID funded http://www.rema.gov.rw/ccr/climate_change_report.html
[7] Rwanda National Strategy for Climate Change (2011)
[8] SEI (2009)
[9] Ibid.
[10] Agulhas (2011)
[11] http://www.decc.gov.uk/publications/basket.aspx?FilePath=11%2ftackling-climate-change%2finternational-climate-change%2f3390-international-climate-fund-implementation-plan-201.pdf&filetype=4#basket
[12] Possibilities for Africa in global action on climate change, Grantham Institute, February 2009
[13] SEI (2009)
[14] The few examples are: Indonesia, who have recently established a Climate Change Fund (focused on forestry) and Bangladesh, who have set up a Climate Change Resilience Fund.
[15] Agulhas (2011)
[16] Other DFID interventions helping to establish in country climate finance facilities are being developed in Ghana, Tanzania, Kenya, Ethiopia, and the Caribbean.
[17] Climate Change; Stocktake of UN Activity, Rwanda Case Study, GHK February 2010

2. Appraisal Case

A. What are the feasible options? / Two options are considered feasible in terms of meeting the needs set out in the Strategic Case. A third option (do nothing) is included as the counterfactual against which the other options are compared. A fourth option: add £1.5m to general budget support (GBS), was rejected on the grounds that earmarking GBS for climate change purposes would not be feasible. Not only would it be unprecedented, and against GBS principles to earmark resources for a particular purpose, it would also have little impact without complementary technical assistance which would significantly add to the costs of the programme. The increased transaction costs for the government of Rwanda would also be difficult to justify for such a small proportion (~1%) of DFID’s GBS contribution. The feasible options are outlined below: / Option 1: Support the creation and initial operation of the National Fund for Climate and the Environment. DFID Rwanda, at the request of the Government of Rwanda, would finance the creation of the National Fund for Climate and the Environment and support its operation for the first two years of its existence, with a view to capitalising the Fund, once established. This will enable climate action across all sectors of the Government of Rwanda’s Economic Development and Poverty Reduction Strategy and facilitate the growth of a ‘green’ and innovative private sector. It is in line with HMG commitments on aid effectiveness and builds national capacity to manage climate change and support low carbon economic growth. It provides the UK with significant leverage on policy dialogue both in Rwanda and elsewhere. It will provide a platform for accessing and coordinating bilateral and international climate finance. But this approach is innovative and largely untested in the field of climate finance. / How would the Fund work? / The design of the Fund has not yet been finalised but the current proposal from the team of consultants working on Fund design is as follows: / Staff: nine members of staff comprising the chief fund manager, a fund planning and budgeting specialist, a resource mobilisation specialist, initially 3 sectoral specialists (agriculture, energy and private sector), a monitoring and evaluation specialist, a finance management specialist and an accountant. Of these, the chief fund manager and four other members of staff are expected to be non-local staff. Other international specialists may be available on a call-down basis. The chart below illustrates the proposed structure. / Note: FONERWA is the french acronym for the National Climate and Environment Fund / Location: the law enabling the creation of the Fund requires that the secretariat be based in the Rwanda Environment Management Authority (REMA), an implementating authority operating under the Ministry of Environment and Natural Resources. Whilst housing the Fund within the Ministry of Finance (MoF) would be attractive from a mainstreaming point of view, the MoF are concerned about setting a precedent for other cross-cutting funds and spreading their already stretched administrative resources too thinly. Nor do they have the technical (climate and environment) expertise. However, MoF will be represented on the Steering Committee of the Fund (see below). / Governance: The governance structure is likely to comprise a Steering Committee (with representatives from different government of Rwanda (GoR) ministries and observers from Development Partners (DPs), Civil Society Organisation (CSOs) and the private sector (PS)) overseeing the work of a Technical Committee who will carry out the initial screening facilitated by the Fund staff (the secretariat). / Accounting/audit arrangements: GoR procedures will be followed in line with international declarations on aid effectiveness[18] and the spirit of a Sector Wide Approach (SWAp). The Secretariat will produce the accounts and financial reports. The Office of the Auditor General will audit the budget on an annual basis. / Fund resources: Analagous to other funds (i.e. Public Financial Management (PFM) and National Institute of Statistics Rwanda (NISR) funds), initial capitalisation options are expected to take the form of a ‘basket’ fund including resources from the government of Rwanda (through environmental fines and fees and consolidation of other funds), bilateral and multi-lateral development partners and international sources of climate finance. / What the Fund will support: proposals will be screened according to agreed criteria aligned with GoR priorities, as articulated in the National Strategy for Climate Change and Low Carbon Development. These criteria are being developed as part of the Fund design process. The Fund could potentially support a wide-range of proposals, across the majority of sectors. The National Strategy set out a number of ‘Programmes of Action’, which could be developed into proposals for the Fund. Examples include promoting the use of fertiliser enriched compost (which reduces demand for inorganic fertiliser, lowers greenhouse gas emissions and increases farm profitability); supporting improved measurement of water resources; supporting sustainable small-scale renewable energy installations in rural areas (e.g. through providing low-interest loans to private sector investors). The fund can also support proposals where the main costs are picked up by other GoR budget lines or other forms of donor support and the Fund provides the incremental funding required to meet the additional climate change-related costs. For example, the Ministry of Education, or another donor might finance the primary costs of a school building programme but may submit a proposal to the Fund to cover the additional cost of providing better flood protection around school sites. A decision from the Steering Committee is expected to take a maximum of three months from receipt of the proposal by the Fund manager. / Type of financing instruments: A mixture of instruments is envisaged including grants, loans and guarantees, depending on need. In the short term it is expected that most proposals will come from government ministries (and possibly NGOs) and that the bulk of disbursements will be in grant form. However, this will change over time as the fund grows in size and is able to manage more complex financial instruments and once management of the Fund and accountability mechanisms are firmly in place. A proportion of Fund resources are intended for development of sectoral proposals aimed at leveraging private finance. / Sustainability: REMA will initially manage the Fund through the Secretariat (with support from international consultants). The fund management responsibility will be fully handed over to REMA/GoR officials as the capacity is built over time. The team will be tasked with securing long term financing for the Fund’s operation after the initial two year start up period, as well as capitalisation of the Fund. / Option 2: Support one or more key sectors in Rwanda to become ‘climate smart’ through supplementing our existing sector budget support and financial aid programmes. Candidates for this could be agriculture, social protection, health and/or education. This would build capacity at a sector level and would demonstrate to other sectors the potential benefit of undergoing the same evolution. However, it is unprecedented to earmark sector budget support for particular uses and so we would need to use dialogue around our SBS to encourage the government to use part of the funding for climate and environment purposes. Furthermore, this option would not support national ability to plan economy wide and the potential to improve access to international finance would be limited. Should the national process be stalled, it does provide a good interim step. However, there is no sign that national level commitment is abating. Evidence is moderate around adaptation interventions in sectors such as social protection, livelihoods and agriculture.[19] / Option 3: No DFID support for implementation of the National Strategy. This would delay the creation of the Climate & Environment Fund as there are no other donors in Rwanda in a position to take this forward. Delaying the creation of the Fund will allow the uncoordinated proliferation of climate change related projects to continue and opportunities to access additional resources will be compromised without capacity being developed at a country level. This would limit Rwanda’s ability to mainstream low carbon development and climate resilience into national development plans. This option is the ‘Do Nothing’ counterfactual against which other options are compared
B. Assessing the strength of the evidence base for each feasible option / Option 1: There are examples of other ‘basket funds’ having been established in Rwanda to meet cross-cutting needs[20], however evidence of impact related to the creation of national level institutions to enable access to climate resources is limited. The need to build institutional capacity in Rwanda in order to improve access to climate finance and the ability to use it to address climate issues is great[21] and not limited to Rwanda.[22] International financial commitments to support developing countries in Africa are increasing but the weak capacity in country is constraining the ability to absorb this finance.[23] This option would not only address this but also provide valuable lessons for other developing countries and development partners alike who are trying to tackle this problem. / Although evidence of impact may be limited, evidence of need is strong and supports an innovative approach such as this. An impact evaluation of an intervention in this area would provide valuable evidence and lessons that would be of use to others considering similar action. / Option 2: There is relatively strong evidence of how various sector level interventions can improve resilience to the effects of climate and also an increasing body of evidence of the impacts of pursuing a low carbon development trajectory.[24] In the case of resilience it is generally a matter of a better understanding of the risks posed by a changing climate to existing development initiatives and making appropriate adjustments to designs and economic analyses to take this into account. For example the design of a road may change when climate change predictions are taken into account by increasing the size and frequency of culverts[25]; or a social protection programme may overlay climatic predictions on existing vulnerability maps in order to better target support, or to help to pre-empt natural disasters and mitigate their impacts.[26] Similar examples exist for health care strategies, livelihoods and agriculture. / Although the evidence base is relatively strong for the impact of a sector-based approach, the benefits would be limited to specific sectors and may not lead to increased support across the breadth of the national development planning process. This could have implications for poverty reduction and growth if key sectors are not factoring climate change and environmental sustainability into design of their programmes. For instance, if large infrastructure projects do not account for future climate variability in their design, then not only could maintenance costs be higher but structures could be irreparably damaged by extreme weather events, resulting in a waste of resources. / Option 3: There is medium to strong evidence that business as usual will present significant risks to Rwanda’s development trajectory, and high costs to the economy over the coming decades[27]. The Fund will most likely go ahead without our support, but would take much longer to become operational and would most likely be significantly weaker. This may jeopardise its long term viability which will mean delays in the implementation of the National Strategy for Climate Change and Low Carbon Development. Losing momentum now may put at risk the long term viability of the Fund and the opportunity to demonstrate that such an approach can work may be lost. / In the table below, the quality of evidence for each option is rated as strong, medium or limited. / Option Evidence rating / 1 Limited / 2 Medium / 3 Medium / Climate change and environment assessment / The relevant climate and environment ‘success criteria’ for this intervention is the extent to which options are able to support the implementation of the Rwanda National Strategy for Climate and Low Carbon Development and deliver results. Both options 1 and 2 would contribute towards implementation, with option 1 offering more scope for economy-wide mainstreaming of climate and environment. Further assessment against climate and environment risks and opportunities is summarised below: / Option 1: Analysis of risks and opportunities for different sectors has been extensively covered in the Sector Working Papers annexed to the National strategy for Climate Change and Low Carbon Development[28], the Economics of Climate Change in Rwanda study[29] and the Climate Change Strategic Evaluation of the DFID Rwanda Programme[30] which includes a full screening of the GoR’s Economic Development and Poverty Reduction Strategy. All conclude that risks are high, but opportunities even higher. This option would therefore attract a category B under risks and A under opportunities. / Option 2: At a sector level the same assessments suggests a medium category would apply depending on the sector. The higher priority sectors would be agriculture and social protection. Opportunities would therefore attract a category B overall. The risk remains that focussing on one sector does not address the climate related issues across all development plans. Therefore this option attracts a category B under risk. / Option 3: This approach addresses none of the risks and develops none of the opportunities. This therefore attracts a category A under risk and a category C under opportunities. / As mentioned above significant analysis has already been conducted and no further work is deemed necessary at this stage. Climate and Environment risks and opportunities are addressed further in the Management Case and logframe. / Option Climate change and environment / risks and impacts Climate change and environment opportunities / 1 B A / 2 B B / 3 A C / Key: A = high potential risk / opportunity; B = medium / manageable potential risk / opportunity; C = low or no potential risk / opportunity / Theory of change / The diagram below sets out the theory of change which links the outputs, outcome and intended impact, focusing at input and output level on option 1. This relationship and the indicators which will be used to monitor progress are reflected in more detail in the logframe at appendix A. / Evidence: / Outcome → impact level: limited. Evidence of impact related to the creation of national level institutions to enable access to climate resources is limited. Only a few examples of national level climate change funds exist (Indonesia, Bangladesh, Brazil) and have not been in operation long enough to generate lessons that could be applied to Rwanda. / Outputs → outcome level: limited. Several sources highlight the need to build institutional capacity in Rwanda in order to improve access to international climate finance[31], pointing towards weak capacity in country constraining the ability to absorb finance.[32] However, given the innovative nature of the intervention, there is little evidence to say whether a capitalised, well-managed fund will be sufficient to ensure climate and environment is fully mainstreamed into national development plans. / Inputs → outputs level: medium. Experience from procurement for the design of the National Climate & Environment Fund suggests that there are several institutions with interest in, and experience of, fund management combined with climate and environment expertise. Other funds (though not related to Climate & Environment) have also been successfully established in Rwanda e.g. a Public Financial Management Basket Fund, a Microfinance Capacity Building Fund and a Microfinance Guarantee Fund, all involving elements of capacity building, resource mobilisation and project delivery. This would suggest that sufficient supply and expertise exists for the delivery of the programme objectives. / Impact: contribute to wealth creation and poverty reduction through low carbon, climate resilient growth / - Climate and environment is mainstreamed into EDPRS / - Climate & environment programmes complement wider pro-poor activities / - Strong macro performance continues / Outputs: / - Capitalisation of the fund / - National fund management capacity built / - Delivery of early projects / - Monitoring and evaluation / Inputs: £1.5m funding staffing and operational costs for the first two years of Fund operation / - Other donors are willing/able to contribute to a well-designed and effective Fund / - Donors willing to follow GoR priorities / - Private sector is interested in investing in low carbon and/or climate resilient activities / - Wider enabling environment supports private sector investment / - £1.5m is sufficient for initial two years of operation / - Procurement process secures sufficient level and quality of expertise / 3. Inputs to Outputs / DFID funding pays for mix of high quality national and international experts who are able to build capacity of national staff, mobilise resources from different sources and facilitate the process of getting projects approved. / 1. Outcome – Impact / Increased funding and capacity for mainstreaming climate change into national programmes helps Rwanda develop increased resilience to future climate impacts and improve access to energy, contributing to economic growth without reliance on high cost imported fossil fuels. / 2. Outputs – Outcome / Availability of resources and evidence from early ‘demonstration’ projects encourages public and private sector to develop strong proposals for climate and environment programmes in line with national objectives, which are approved and implemented. / Outcome: Rwanda able to finance and further develop national programmes and private sector initiatives in line with the CC Strategy & EDPRS II / Intended pathway / Mechanism / Assumptions / 1 / 2 / 3
C. What are the costs and benefits of each feasible option? / In the economic appraisal that follows, the costs and benefits of options 1 and 2 are compared against option 3 (the counterfactual). More detail of the economic appraisal is provided in appendix B. / Incremental costs: Incremental costs for options 1 and 2 are compared to the counterfactual (option 3) and set out in the table below. Cost estimates are based on early discussions with the team of consultants undertaking design work for the Fund (managed by CDKN). For ease of comparison, we have assumed that a similar total amount of funding would be made available for option 2 as for option 1 and that an equivalent amount of money would be set aside for evaluation. / Option Item (figures given in £’000s) 2012/13 2013/14 2014/15 Total / 1 Staffing costs 500 375 0 875 / Operational costs 250 175 0 425 / Monitoring and evaluation 50 00 150 200 / Total 800 550 150 1500 / 2 Uplift to existing budget support and financial aid programmes 750 550 0 1300 / Monitoring and evaluation 50 00 150 200 / Total 800 550 150 1500 / Incremental Benefits: The expected benefits of the programme are challenging to quantify given uncertainty over the specific activities that would be financed under either option 1 or 2. In addition, the innovative nature of the intervention means that there is little evidence to support key assumptions. As such, any estimates are likely to be subject to a high degree of uncertainty. We have approached this by taking a very conservative approach to estimating impacts. / Option 1: support the creation and initial operation of a National Fund / We have attempted to quantify two types of benefits arising from the creation and operation of a National Fund for Climate and the Environment: / Additional finance leveraged / A key objective of the initial operation phase will be to identify and mobilise additional sources of finance from the government, donors and the private sector. Key donors include Sweden (who chair the Sector Working Group on Environment and Natural Resources), UNDP (who have supported work on environmental sustainability), the Netherlands (who focus on renewable energy and biomass), the World Bank (renewable energy), Germany (renewable energy) and the EU (who recently supported a Strategic Environmental Assessment of the agriculture sector). Early discussions with the EU, SIDA (Sweden) and KfW (Germany) suggest that they would consider allocating new resources to an operational, well-managed Fund. We have assumed that each of these donors would contribute £1m per year to the Fund, in addition to their planned expenditure. Given the time it takes to programme additional funds, we have assumed that only one donor is able to contribute in year one but three contribute in year two. This is a conservative estimate, given the scale of the challenge, the existence of international commitments to finance climate change[33], the presence in the sector of other donors who may also wish to contribute and the previous track record of donors in providing large-scale support to specific sectors in Rwanda when clear plans of action are identified. / Improved coordination of donor and government funds / A recent self-assessment carried out for the climate and environment sub-sector[34] pointed to the need to move away from a fragmented, project-based approach to ensure long term sustainability of outcomes. The report also recommended taking measures to strengthen coordination of funding streams. The National Climate Change and Low Carbon Development Strategy identifies 31 separate funds that are currently, or soon to be, available for potential climate finance in Rwanda. Better coordination amongst donors, international funds and the government of Rwanda, combined with a clear and transparent framework for programme funding would be expected to improve the technical efficiency with which resources are used. There is little evidence to indicate the size of the expected efficiency gains. We have made a conservative assumption that this intervention will lead to a 1% improvement in the operational efficiency of current climate and environment expenditure (estimated at ~£38m in 2011). This assumption is tested as part of the sensitivity analysis and break even analysis. This suggests that annual efficiency benefits arising from the Fund could be in the region of £400k per year. / In addition to the quantified benefits above, there are also likely to be further benefits that we have not been able to quantify, which could potentially be very large. These include: / Improved ability of the government of Rwanda to implement an economy-wide approach to climate resilient, low carbon development resulting in improved allocative efficiency of domestic and donor spend / Benefits from actual projects/programmes supported e.g. an increase in the number of poor people who are supported to cope with the impacts of climate change; an increase in the number of poor people with access to clean energy, a reduction in CO2 emissions relative to ‘business as usual’ / Increased knowledge and capacity within the government of Rwanda to address the challenges brought by climate change / Reduced transaction costs for donors from being able to use the same government of Rwanda systems for monitoring results / increased transparency and accountability around use of (national and international) climate finance will help raise awareness of the issues at national and international level / Successful implementation of Rwanda’s National Climate Change and Low Carbon Development Strategy will strengthen Rwanda’s voice in international climate negotiations, improving the chance of an equitable outcome / The contribution to the evidence base in a new and innovative area enabling lessons to be shared with other developing countries looking to follow suit. / Option 2: support one or more key sectors in Rwanda to become ‘climate smart’ through supplementing existing budget support and financial aid programmes / This option may deliver similar types of benefits as under option one, but with more limited scope. For instance, the demonstration effects from activities in particular sectors may be sufficient to encourage additional resources from other donors and sector budgets, however this is unlikely to be at the scale expected under a well-managed Fund. There is little evidence to support assumptions around the quantity of additional finance that option 2 might leverage. We have assumed that other donors may follow our lead and increase their Sector Budget Support (SBS) funding by a similar proportion to DFID, in order to address climate and environment related needs in the sector. Taking the agriculture sector as an example, an £1.5m uplift would represent an increase of around 15% in DFID support to the sector. If other donors with SBS commitments in the sector were also to increase their funding by around 15%, this would result in around £3.2m of additional resources to the sector. / The scope for improved coordination of donor funds would be limited to the sectors of focus. Even then, it is unlikely that the same level of coordination would be achieved through a sector budget support-type approach as through option 1 as other issues may crowd out the discussion. We have assumed for option 2 that the same level of efficiency savings are achieved, but for the agriculture sector only, using agriculture spend as a proportion of total spend to factor down the efficiency savings expected from option 1. On this basis, option 2 is expected to provide around £30k in efficiency savings per year. / Many of the wider benefits identified under option 1 might also apply to option 2, although to a lesser degree. For instance, we would expect to see increased knowledge and capacity within the targeted sector but it is unlikely that this benefit would extend across the broader government programme, as in option 1. Benefits from actual projects and programmes supported may be on a par with option 1, depending on the particular programmes identified under each option. / Balance of Costs and Benefits: In the table below, options 1 and 2 are compared to option 3 (do nothing) which is used as the baseline. Both options 1 and 2 look cost-effective with the estimated benefits outweighing the costs in both cases. Option 1 would appear the most cost-effective of the two options with an Net Present Value (NPV) of around £3m and a Benefit Cost Ratio (BCR) of 3.1 (i.e. £1 of expenditure brings £3.10 worth of benefits). The inclusion of unquantified benefits would further strengthen the economic case for both options, more so for option 1. / All values in £000s / 2012/13 2013/14 2014/15[35] Total / Option 1: Support the creation and operation of a National Fund for Climate and the Environment Programme costs / Staff costs 500 375 0 875 / Operational costs 250 175 0 425 / Monitoring and evaluation 50 0 150 200 / Total costs 800 550 150 1500 / Discounted costs 800 500 124 1424 / Monetised programme benefits / Finance leveraged 1000 3000 0 4000 / Efficiency savings 384 405 0 789 / Total benefits 1384 3405 0 4789 / Discounted benefits 1384 3096 0 4480 / Summary / Present Value costs 1424 / Present Value benefits 4480 / Net Present Value (NPV) 3056 / Benefit Cost Ratio (BCR) 3.1 / Option 2: support key sectors to become climate smart Programme costs / Uplift to Sector Budget Support (SBS) 750 550 0 1300 / Monitoring and evaluation 50 0 150 200 / Total costs 800 550 150 1500 / Discounted costs 800 500 124 1424 / Monetised programme benefits / Finance leveraged 1288 1288 0 2576 / Efficiency savings 26 27 0 53 / Total benefits 1314 1315 0 2628 / Discounted benefits 1314 1195 0 2509 / Summary / Present Value costs 1424 / Present Value benefits 2509 / Net Present Value (NPV) 1085 / Benefit Cost Ratio (BCR) 2 / Uncertainty in assumptions: Given the high degree of uncertainty the assumptions driving the quantified benefits of the programmes, we also conducted break-even analysis to identify, for example, the quantified benefits that would be required for the programme benefits to just offset the costs. Present value costs are around £1.4m. In order to break-even, the Fund would need to leverage at least this amount of additional funding from donors and/or other government resources. Alternatively, in the absence of additional finance, the Fund would need to deliver efficiency savings in relation to current expenditure of around 2%. It is important to remember that there are likely to be several other sources of potential benefits that we have not been able to quantify, as described above, which are likely to significantly enhance the economic case. / Financial sustainability: We would expect DFID support to cover operational costs for the first two years. The management team associated with the Fund will be tasked with securing long term financing for their operation after the initial two-year start up period, as well as capitalisation of the Fund. The government of Rwanda are committed (through the law establishing the Fund) to provide resources from environmental fees and fines to capitalise the fund. Since these are unlikely to be large, other resources for capitalisation will be sought from bilateral and multi-lateral donors and may be made available from other Government of Rwanda budget lines. / Attribution: The initial 2-year operation of the Fund, and its outputs (as quantified in the cost benefit analysis), will be attributable to DFID. Outcomes arising from the first two years of operation will be attributable to DFID and those who provide capital for the fund in proportion to their relative contributions. The longer term outcomes and impact of the fund will be attributable to future contributors and the Government of Rwanda. / On the basis of the economic appraisal and the climate and environment assessment, the preferred option is Option 1: support the initial operation of the National Fund for Climate and the Environment.
D. What measures can be used to assess Value for Money? / Within the appraisal, Value for Money (VfM) indicators have been identified to help assess the economy, efficiency and effectiveness of the programme. These measures will be tracked through Annual Reviews and Project Completion Reports in order to help indicate whether the intervention continues to represent good Value for Money. These measures are summarised below: / VfM measure / Economy Operational cost per proposal considered by the Steering Committee / Effectiveness Additional donor finance mobilised / Government of Rwanda finance mobilised / Private sector finance leveraged / Number of poor people made more resilient to future climate impacts / Number of additional households with energy access / Efficiency Net Present Value / Benefit Cost Ratio / Some of the outputs of the programme, particularly those related to capacity building are challenging to assess based purely on traditional economic appraisal indicators which rely heavily on quantitative inputs. We therefore plan to appraise vfm through a results-based monitoring and evaluation framework as set out in the Management Case.
E. Summary Value for Money Statement for the preferred option / On the basis of the appraisal outlined above, we are confident that this programme offers value for money. On the basis of the analysis, the preferred option is Option 1: support the creation and initial operation of the National Fund for Climate and Environment. Under this option, taking account of monetised costs and benefits, the Net Present Value (NPV) is positive (i.e. benefits are expected to outweigh costs by around £3m) and the benefit cost ratio (BCR) is around 3.1 (i.e. £1 of expenditure brings £3.10 of benefits). / However, these quantified benefits are highly dependent on several assumptions and evidence to support these is weak. Nevertheless, the conservative approach taken to estimate the monetised benefits and the identification of further unquantified benefits, suggest that the ‘true’ NPV is likely to be significantly higher than the figure estimated in this appraisal, further strengthening the economic case.
[18] Notably the Paris Declaration on Aid Effectiveness, the Accra Agenda for Action and the Busan Partnership documents: http://www.oecd.org/document/18/0,3746,en_2649_3236398_35401554_1_1_1_1,00.html
[19] Lindsey Jones, Susanne Jaspars, Sara Pavanello, Eva Ludi, Rachel Slater, Alex Arnall, Natasha Grist and Sobona Mtisi, Responding to a changing climate: Exploring how disaster risk reduction, social protection and livelihoods approaches promote features of adaptive capacity, ODI, August 2010, http://www.odi.org.uk/resources/details.asp?id=4790&title=climate-change-disaster-risk-reduction-adaptive-capacity-social-protection
[20] e.g. Public Financial Management Basket Fund, Microfinance Capacity Building Fund, National Institute of Statistics of Rwanda (NISR), National Election Commission and the Microfinance Guarantee Fund
[21] SEI (2009)
[22] Stern Review on the Economic of Climate, 2006, http://webarchive.nationalarchives.gov.uk/+/http:/www.hm treasury.gov.uk/sternreview_index.htm
[23] Climate Finance in Sub Saharan Africa, ODI, November 2011, http://www.odi.org.uk/resources/details.asp?id=6151&title=climate-finance-sub-saharan-africa
[24] Rwanda National Strategy for Climate Change (2011)
[25] Climate Compatible Development in the Infrastructure Sector - An overview of the opportunities and challenges at the nexus of climate change, infrastructure and development, ODI and Engineers Against Poverty, June 2011, http://www.odi.org.uk/resources/details.asp?id=5770&title=climate-compatible-development-infrastructure-sector
[26] ODI, (2010)
[27] SEI (2009)
[28] Rwanda National Strategy for Climate Change ((2011)
[29] SEI (2009)
[30] DFID (2011)
[31] SEI (2009)
[32] ODI (2011)
[33] The Copenhagen Accords committed developed countries to raise $100 billion per year by 2020 to help developing countries tackle climate change
[34] Environment & climate change sub-sector, EDPRS self-assessment report Feb 2012, unpublished
[35] We have assessed the costs and benefits of the Fund over a two year appraisal period (hence no operational costs and benefits show for year 3). However, for completeness, we have included the costs of the independent evaluation which will accrue in year 3

3. Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / DFID will contract directly for the supply of services. This is the preferred approach of the Rwanda Environmental Management Authority who will be managing the Fund secretariat with the support of the international consultants contracted under this project. The alternative would be to procure indirectly through Government of Rwanda (GoR) systems. However, this would likely take longer and impose additional administrative burden on already stretched GoR resources. Given limited capacity within REMA to run the procurement exercise, the Director General of REMA has asked DFID to mange the process. The Director General of REMA will participate in the evaluation of tenders and sit on the Steering Group for the project. / The terms of reference for Fund operation are currently being developed as part of the design work for the Fund (managed by CDKN). / Procurement of these services will be through competitive open tendering according to DFID and Official Journal of the European Union (OJEU) procedures. In following these procedures, the DFID Rwanda team will be supported by colleagues from DFID’s Procurement Group (PrG).
B. How does the intervention design use competition to drive commercial advantage for DFID? / The use of tendering for the procurement will insure that commercial advantage is achieved through competition. The evaluation of bids and proposals will be based on the bidders’ ability to deliver a specified set of services to a satisfactory standard, within the budget available. Scoring each bid against commercial criteria (e.g. competitiveness of fee rates, a clear financial plan and consideration of financial risks etc.) will be a key part of the evaluation process. However, evaluation will not be conducted on the basis of cost alone: additional considerations such as quality and past performance will also be considered, in order to ensure that optimum value for money is obtained.
C. How do we expect the market place will respond to this opportunity? / Procurement for the design phase of the Fund elicited several high-quality bids, of which several involved consortia of institutions. Other funds (though not related to Climate & Environment) have also been recently established in Rwanda e.g. a Public Financial Management Basket Fund, a Microfinance Capacity Building Fund, National Institute of Statistics of Rwanda (NISR), National Election Commission and a Microfinance Guarantee Fund, all with some external support. This indicates that sufficient supply and expertise exists for the delivery of the programme objectives. / We will be asking for bidders to indicate how they intend to provide the range of services required under the Fund i.e. we expect bidders to present us with a complete ‘package’ enabling Fund operation; we will not be recruiting individual experts. / Whilst it is not clear that there is currently sufficient capacity within the region to provide the totality of required services, there is scope for partnerships between institutions in the region and elsewhere. Consortia of institutions will be encouraged to bid. We will also raise awareness of the project amongst regional institutions through advertising the contract in local and regional publications. / Given the innovative nature of the Fund, the quantity of funding on offer and the scope for applying this model in other developing countries it is reasonable to expect a good response to the invitation to tender.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Staff costs are expected to make up around three quarters of total costs with other operational costs comprising around one quarter of the total. However, we would expect to see staff costs falling over time (by around 25% by year two) as international experts are slowly phased out and replaced by locally-trained staff. / In assessing bids, we will ensure that staff costs are comparable with day rates set out in DFID call down contracts. We will also ensure that other costs are consistent with Government of Rwanda and DFID admin and allowance limits. / The added value of the programme will be measured in terms of delivery against the outputs and outcomes identified in the logframe attached at appendix A. The logframe will be reviewed every six months to ensure its continued applicability and usefulness as a monitoring tool. The logframe will form a key part of a results-based contract with the successful bidder. / The successful bidder will be required to provide DFID with a detailed budget and expenses breakdowns to allow monitoring of spend. Regular monitoring will minimise DFID exposure to financial risks.
E. What is the intended Procurement Process to support contract award? / Subject to approval of this Business Case, procurement will take place through open and competitive tender in accordance with the procedures set out in the Official Journal of the European Union (OJEU). / Initial identification of bidders will take place through an invitation for expression to interest to respond to a clear set of Terms of Reference. Short-listed bidders will then be asked to submit a full proposal for consideration by the evaluation panel, comprising representatives from DFID and the Government of Rwanda.
F. How will contract & supplier performance be managed through the life of the intervention? / A results-based Terms of Reference (ToR), the successful proposal and subsequent clarifications will form the basis for the contract with the supplier. This will include a robust implementation plan, including an adequate risk register and key performance indicators. / A clear logframe is included at appendix A which sets out anticipated results, with measurable indicators under each output. / The project team will provide quarterly written updates on progress to the DFID project manager, supplemented by meetings/teleconferences where appropriate. This will help mitigate and manage risks of poor supplier performance.

4. Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The expected cost of the programme is £1.5m over two years, commencing in FY2012/13 and ending in FY2014/FY201415. The period of funding could be extended based on the availability of suitable funds and programme performance. / The breakdown of costs and allocation of funds by year is as follows: / (£000s) / Cost item 2012/13 2013/14 2014/15 Total / Staff costs 500 375 0 875 / Operational costs 250 175 0 425 / Monitoring and evaluation 50 0 150 200 / Total 800 550 150 1500 / The successful bidder will be required to provide DFID with quarterly financial and narrative progress against approved annual work plan and budget, agreed with the government of Rwanda. These reports will detail expenditure incurred as well as realistic projections of spend for the next quarter on all budget activity lines as well as risks associated with project delivery which may impact on spend. / The DFID programme manager will rigorously reconcile these forecasts against (i) relevant data on ARIES; (ii) the approved work plan and budget; (iii) previous reports, disbursements and past spending trends. Any discrepancies will be promptly raised with the contractor and necessary changes to forecasts agreed. The Lead Adviser will also be consulted on all financial issues identified as well as any changes to forecasts on ARIES that need to be made.
B. How will it be funded: capital/programme/admin? / The programme will be funded from programme RDEL resources, and has been budgeted for in the Operational Plan for DFID Rwanda. The concept note for this programme was approved by the International Climate Fund (ICF) Board in July 2011. / There are no contingent, or actual, liabilities.
C. How will funds be paid out? / Funds will be paid out in stages according to an agreed payment schedule, and linked to agreed deliverables/outputs.
D. What is the assessment of financial risk and fraud? / DFID will lead procurement and supervision of the international consultants who will support the Government of Rwanda in managing the Fund for the first two years of its operation. The competitive tendering process aims to mitigate against financial risk and fraud by assessing bids against criteria including evidence of a clear financial plan and financial management capacity including consideration of financial risks. The successful bidders will be required to sign a binding contract with DFID, requiring that funds are used for their intended purpose, are linked to agreed deliverables and that expenditure is properly accounted for. / Since the Government of Rwanda (through REMA) will manage the Fund (with support from international consultants), consideration also needs to be given to the fiduciary risk associated with use of government systems. DFID’s 2011 Fiduciary Risk Assessment (FRA)[36] suggested the fiduciary risk relating to Public Financial Management (PFM) was moderate, with a positive trajectory of change. The corruption risk was also assessed as moderate, with a flat trajectory of change. / For PFM, the positive trajectory of change reflects the progress between the 2007 and 2010 Public Expenditure and Financial Accountability (PEFA) assessments with 12 of the 28 indicators improving. Despite this progress the FRA identified a number of significant weaknesses including in relation to accounting, recording and reporting, and legislative scrutiny. DFID’s programme of support to the government’s PFM Reform Strategy (including support to the Office of the Auditor General and support to Parliament, with a particular emphasis on the Public Accounts Committee and the Budget Committee) will help to address the accounting weaknesses both through capacity building and systems strengthening. The international staff and the Fund team as a whole will be responsible for monitoring, reporting and accounting for spend, following Government of Rwanda rules and procedures. This should help further minimise fiduciary risks for the Fund.
E. How will expenditure be monitored, reported, and accounted for? / DFID expenditure will be monitored, reported and accounted for by the Lead Adviser and the programme manager in DFID Rwanda. / The successful bidder will be asked to an annual audited statement, supplemented by quarterly statements of expenditure, listing how DFID’s money has been spent, together with details of any unspent funds. This will enable DFID to check that funds have been spent as laid out in the budget breakdown. / DFID funds will only be paid out according to an agreed payment schedule, and on provision of evidence that agreed outputs have been delivered. / For the Fund as a whole, monitoring, reporting and accounting for spend will be the responsibility of the Fund manager, following Government of Rwanda rules and procedures. The Secretariat will produce the accounts and financial reports which will be reviewed by the Steering Committee and audited by the Office of the Auditor General on an annual basis.
[36] DFID (2012) Donor Fiduciary Risk Assessment of General Budget Support (GBS) in Rwanda

5. Management Case

A. What are the Management Arrangements for implementing the intervention? / The project lead will be DFID Rwanda’s Climate Change and Low Carbon Growth Adviser. She will be supported by the Programme Manager for the Economic Growth Team. Input will also be required from the Results Team, particularly when it comes to evaluation (see section D below). / Day-to-day management of the project will be in partnership with the Government of Rwanda. The Steering Group for the project will comprise representatives from DFID, Rwanda Environment Management Authority (REMA) and the Climate and Development Knowledge Network (CDKN). Other representatives from relevant ministries, particularly the Ministry for Environment and Natural Resources (MINIRENA) and the Ministry of Finance and Economic Planning (MINECOFIN) and experts from the donor community, may also be invited to participate. / Views from prospective beneficiaries of the Fund will be sought through engagement with Sector and Working Groups (SWGs)[37] and fed into the governance of the project and its evaluation. / Performance of the programme will be monitored by the Project Steering Group on the basis of quarterly financial and narrative progress reports from the project team.
B. What are the risks and how these will be managed? / The key risks (and opportunities) and mitigating actions are set out in the table below. All risks are owned by the Lead Advisor. Currently all risks are within DFID Rwanda’s risk appetite. / Risk (opportunity) Triggers Mitigating (enhancing) actions Residual probability Residual impact / Insufficient capital is available to support fund objectives Little revenue available from environmental fees & fines / GoR unwilling to provide additional funds given other priorities / Donors are not willing/able to provide additional support Use influence in Budget Support Harmonisation Group (BSHG) to encourage budget lines for Climate & Environment (C&E) / Raise awareness of the Fund amongst other bi- and multi- donors, in Rwanda and globally / Apply to ICF for finance to capitalise the Fund Med High / Fungibility between donor and GoR funds reduces resources available GoR reduces support to the Fund as donor/other contributions increase Use influence in BSHG to encourage budget lines for Climate & Environment Med Low / Climate & Environment (C&E) considered lower priority by GoR, reducing resources available Climate change given lower priority in EDPRS II Work through SWGs to ensure climate and environment objectives are reflected in EDPRS II Low Med / Shortage of good quality proposals coming to the Fund, particularly from other sectors Sectors lack capacity to develop strong proposals to bring to Fund Use General Budget Support (GBS) policy dialogue to encourage sectors to devote capacity and resources to C&E / Fund to provided detailed feedback when projects are rejected / Use ‘Programmes of Actions’ from National Climate Change and Low Carbon Development Strategy and examples from other countries, to encourage proposals Med Med / Fund supports proposals that have negative C&E impacts C&E screening not applied effectively / Political pressure to support specific activities Work through design Steering Group (SG) to ensure that robust C&E screening procedures are developed as part of design phase / Ensure (through logframe) that fund manager applies C&E screening effectively Low Low / Key funding ‘windows’ are not allocated sufficient funding Donors earmark funding for particular ‘windows’ Work through design SG to support GoR in ensuring allocation approach meets GoR objectives and delivers vfm Med Med / Legal restrictions limit fund manager’s ability to make use of innovative financing instruments Design of fund rules out certain approaches Work through design SG to ensure widest possible range of financing options are available Med Med / Fund diverts staff and capacity from other REMA functions Good people are drawn from other parts of REMA into the Fund, leaving capacity gaps elsewhere Fund provides for recruitment and training of additional staff / The Fund contains a specific capacity building component Low Low / Once trained, local staff move on Higher paid positions elsewhere Use contractual terms and competitive salaries to retain staff Low Med / Insufficient interest from private sector Enabling environment is discouraging to investors / Insufficient investment opportunities Work through design SG to ensure wide range of financing options available Low Low
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / Monitoring of the programme will be carried out using the logframe attached at appendix A. / Quarterly implementation progress reports outlining progress against logframe milestones will be prepared by the service provider, agreed with the government and Rwanda, and presented alongside the financial reports. This will help in identifying opportunities and gaps as well as areas where progress is off-track to ensure action is taken in a timely manner. This is particularly important given the innovative nature and short time period of the project. The reports will present a narrative of progress as well as quantitative progress towards logframe milestones (set out in Excel format). Where progress towards milestones is off-track, the report should include measures taken (to be taken) to ensure progress remains (gets back) on track. / Despite the relatively small amount of DFID funding involved, the lack of evidence that is currently available for this type of intervention in the climate and environment sector, its innovative nature and strategic importance, points towards the need for a more in-depth evaluation than might otherwise be required. / The Evaluation Plan will be worked up in more detail following approval of the Business Case. An outline is set out below. / Purpose of the evaluation To provide evidence of the degree to which the initial operation of the Fund has been efficient and effective in achieving its objectives with the aim of informing future phases of the Fund and other developing countries looking to learn lessons from Rwanda’s experience. / Key users of the evaluation The government of Rwanda, donors and other organisations considering capitalising the Fund, other developing countries considering adopting a similar approach / Planned date of evaluation to be completed by March 2015 (to cover the first two years of Fund operation) / Key evaluation questions To what extent has the Fund delivered its intended outputs? / To what extent have outcomes been delivered? / What has been the impact of the first few years of Fund operation? / What contribution has the Fund made to mainstreaming of climate change into EDPRS II? / Design and methods envisaged The evaluation will be an impact evaluation using mixed methods including a survey to determine the baseline, literature review and interviews. Similar methods will be used during the evaluation / Will the baseline data and logframe provide the data necessary to answer the evaluation questions? The evaluation team will be procured during the first year of the project to ensure that they are involved in different stages of the evaluation and can support the project in identifying and putting in place measures to ensure adequate information is available to facilitate an effective impact evaluation. This work will also support project monitoring e.g. by helping to develop monitoring methodologies. / How does the evaluation approach fit with the existing evidence base? This intervention is innovative and largely untested in the field of climate finance. The evaluation will make an important contribution to the evidence base. / The role of stakeholders Views from intended beneficiaries of the Fund will be sought through engagement with Sector- and Sub-Sector Working Groups and fed into the evaluation. / Budget available for evaluation £200k / How will suitable evaluators for this work be identified and contracted? Contractual arrangements will follow DFID procurement guidance. / Strategy for communicating evaluation findings The findings of the evaluation will be shared with the government of Rwanda and key stakeholders through Sector Working Group meetings. The evaluation report will be published on DFID sites and other climate change fora. Findings will also be shared more widely through DFID Climate & Environment Adviser networks. / A logical framework (logframe), setting out the expected outputs, outcome and impact along with milestones and indicators for the programme is attached at Appendix A. This supports the business case and takes, as its starting point, the theory of change outlined in section B of the appraisal case. The logframe forms the basis of the monitoring strategy for the programme. / Some aspects of the logframe (e.g. milestones, targets) may be subject to revision as the design of the Fund is finalised and as part of contract negotiations. / Progress against logframe targets will be kept under regular review with the help of quarterly (maximum 10-page) quantitative and narrative progress reports and a more detailed annual report. Formal project scoring will take place annually (August 2013) and at project completion (August 2014) and will compare results actually achieved against the planned milestones and targets set out in the agreed logframe.
[37] Sector- and Sub-Sector Working Groups take place once a month and are an opportunity for dialogue between the GoR, development partners and other stakeholders including civil society and the private sector.

Appendix 1: Logframe

Quest No of logframe: 3427169

Logframe to be updated following appointment of Fund Management Team, whose initial tasks will include validating the reporting and M&E frameworks and setting baselines. The FMT is expected to be in place in September 2012 and logframe targets finalised by end December 2012.

PROJECT TITLE	Creation of the National Fund for Climate & Environment (FONERWA)
IMPACT	Impact Indicator 1	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
Contribute to wealth creation and poverty reduction in Rwanda through low carbon and climate resilient economic growth	Number of people who have built resilience to climate change impacts (disaggregate by income and gender where possible)	[to add]	[to add]	[to add]	[to add]
		Source
		Indicator under development by DFID Climate & Environment Dept. Not currently measured by GoR but included in FONERWA M&E framework.
	Impact Indicator 2	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
	Number of people with access to clean energy (disaggregate by income and gender where possible)	[to add]	[to add]	[to add]	[to add]
		Source
		Ministry of Infrastructure M&E framework, annual Ministry reports, included in FONERWA M&E framework

OUTCOME	Outcome Indicator 1	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)	Assumptions
Rwanda able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development	Number of sectors receiving support from the Fund	0	2	3	5	- Climate and environment is mainstreamed into EDPRS II - Climate & environment programmes complement wider pro-poor activities - Strong macro performance continues
		Source
		Fund manager progress reports, agreed with REMA
	Outcome Indicator 2	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
	Number of projects on track to meeting at least 80% of their targets (disaggregate by government, private sector, civil society organisation)	0	2	5	8
		Source
		Fund manager progress reports, agreed with REMA
	Outcome Indicator 3	Baseline (April 2012)	Milestone 1	Milestone 2	Target (September 2014)
	% of initial local technical staff recruited who are retained at end of project period	0	n/a	n/a	3
		Source
		Fund manager progress reports, agreed with REMA
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID share (%)
	1.5m	-	-	1.5m	100%
INPUTS (HR)	DFID (FTEs)
	0.5 C&E Adviser; 0.1 Programme manager; 0.1 Results & Evaluation adviser

OUTPUT 1	Output Indicator 1.1	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)	Assumptions
Significant resources made available for spend on climate and environment projects and programmes	Amount of government resources spent on climate & environment (a) through the Fund; (b) through other channels (disaggregated by sector)	(a) 0 (b) [to add]	(a) £0.5m (b) [to add]	(a) £1m (b) [to add]	(a) £2m (b) [to add]	Other donors are willing/able to contribute to a well-designed and effective Fund - Donors willing to follow GoR priorities - Private sector is interested in investing in low carbon and/or climate resilient activities - Wider enabling environment supports private sector investment
		Source
		Fund manager progress reports, agreed with REMA; Joint Sector Reviews
	Output Indicator 1.2	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
	Quantity of development partner resources mobilised (a) through the Fund; (b) outside the Fund (disaggregated by bilateral and multilateral resources)	(a) 0 (b) [to add]	(a) - (b) [to add]	(a) £1m (b) [to add]	(a) £3m (b) [to add]
		Source
		Fund manager progress reports, agreed with REMA, Joint Sector Reviews
IMPACT WEIGHTING	Output indicator 1.3	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
35%	Quantity of private finance mobilised by the Fund	0	£1m	£4m	£10m
		Source				RISK RATING
		Progress reports from Fund manager				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID share (%)
	0.65m	-	-	0.65m	100%
INPUTS (HR)	DFID (FTEs)
	0.2 C&E Adviser

OUTPUT 2	Output Indicator 2.1	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)	Assumptions
National Climate and Environment Fund management capacity built	% of the Fund Secretariat made up of locally-trained technical staff	0	10%	50%	80%	- Trained staff remain in the Fund Secretariat - Sufficient numbers of staff to cope with workload

IMPACT WEIGHTING		Source				RISK RATING
35%		Fund manager progress reports, agreed with REMA				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID share (%)
	0.65m	-	-	0.65m	100%
INPUTS (HR)	DFID (FTEs)
	0.2 C&E Adviser

OUTPUT 3	Output Indicator 3.1	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)	Assumptions
Delivery of early finance for climate and environment activities	Number of proposals1 (a) reviewed and (b) approved by the Steering Committee	(a) 0 (b) 0	(a) 5 (b) 3	(a) 10 (b) 5	(a) 15 (b) 8	Sufficient numbers of high quality proposals are received - Steering Committee and Technical Committee meet regularly and function effectively
		Source
		Fund manager progress reports, agreed with REMA
	Output Indicator 3.2	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
	Number of low carbon, climate resilient development proposals financed through the Fund	0	3	5	8
		Source
		Fund manager progress reports, agreed with REMA
IMPACT WEIGHTING	Output indicator 3.3	Baseline (April 2012)	Milestone 1 (April 2013)	Milestone 2 (December 2013)	Target (September 2014)
20%	Amount of finance disbursed	0	£0.2m	£2m	£5m
		Source				RISK RATING
		Fund manager progress reports, agreed with REMA				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID share (%)
	0m	tbd	-	0m	No DFID resources
INPUTS (HR)	DFID (FTEs)
	0.1 C&E Adviser

OUTPUT 4	Output Indicator 4.1	Baseline (April 2012)	Milestone 1 (Dec 2012)	Milestone 2	Target (September 2014)	Assumptions
Monitoring and evaluation systems in place	Monitoring and evaluation system for project monitoring is in place and fully operational by December 2012	No system in place	System agreed, validated and fully operational	n/a	System agreed, validated and fully operational	- Sufficient M&E capacity and expertise is available - Results are shared widely and lessons acted upon
		Source
		Fund manager progress reports, agreed with REMA
IMPACT WEIGHTING	Output indicator 4.2	Baseline (April 2012)	Milestone 1 (Jan 2013)	Milestone 2	Target (March 2015)
10%	Full independent evaluation completed	No evaluation	Baselines established and agreed	n/a	Evaluation findings obtained and agreed
		Source				RISK RATING
		Deliverables from independent evaluation				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID share (%)
	0.2m			0.2m	100%
INPUTS (HR)	DFID (FTEs)
	0.1 Results & Evaluation Adviser

1 Captures projects and programmes with climate and environment as their focus and also proposals for the Fund to cover the incremental climate and environment costs associated with new/existing programmes in other sectors

Appendix 2 : Economic Appraisal

Summary and Recommendations

The programme aims to support the implementation of Rwanda’s National Strategy for Climate Change and Low Carbon Development. It will do this through helping to create and build institutions that will enable Rwanda to access international and bilateral climate finance and mainstream climate resilience and low carbon development into national development plans.

This appraisal uses available evidence and conservative assumptions to estimate the expected costs and benefits of the proposed programme. The analysis suggests that the programme is likely to offer value for money. On the basis of the analysis, the preferred option is Option 1: support the creation and initial operation of the National Fund for Climate and Environment. Under this option, taking account of monetised costs and benefits, the Net Present Value (NPV) is positive (~£3m) and the benefit cost ratio (BCR) is around 3.1 (i.e. £1 of expenditure brings £3.10 of benefits). However, please note that the quantified benefits are highly dependent on several key assumptions (see below).

The quantified benefits are:
- Additional finance leveraged from bilateral & multilateral donors (additional finance from the GoR budget and the private sector is potentially significant but has not been quantified here)
- Improved coordination of donor funds resulting in improved (technical) efficiency

There are also likely to be further benefits that we have not been able to quantify such as:
- Benefits from actual projects supported under the Fund e.g. an increase in the number of poor people who are supported to cope with the impacts of climate change; an increase in the number of poor people with access to clean energy
- Increased knowledge and capacity within the government of Rwanda to address the challenges brought by climate change
- Improved ability of the government of Rwanda to implement an economy-wide approach to climate resilient, low carbon development resulting in improved efficiency of domestic spend
- increased transparency and accountability around use of (national and international) climate finance will help raise awareness of the issues at national and international level
- Successful implementation of Rwanda’s National Climate Change and Low Carbon Development Strategy will strengthen Rwanda’s voice in international climate negotiations, improving the chance of an equitable outcome
- Increased scope for policy dialogue on climate change between the UK and Rwanda
- The contribution to the evidence base in a new and innovative area enabling lessons to be shared with other developing countries looking to follow suit

These unquantified benefits, and the conservative approach taken to estimate the monetised benefits, suggest that the ‘true’ NPV is likely to be significantly higher than the figure estimated in this appraisal, further strengthening the economic case.

However, the benefits depend critically on several key assumptions which are based on expert judgement, rather than strong evidence, given the innovative nature of this intervention. Given the uncertainty surrounding several of the assumptions we also conducted break-even analysis to identify, for example, the quantified benefits that would be required for the programme benefits to just offset the costs. Present value costs are around £1.4m. In order to break-even, the Fund would need to leverage at least this amount of additional funding from donors and/or other government resources. Alternatively, in the absence of additional finance, the Fund would need to deliver efficiency savings in relation to current expenditure of around 2%. We will use the monitoring and evaluation plan for this programme to test some of the assumptions made in the economic appraisal, particularly around resource mobilisation and improved coordination. Please see Section D of the Management Case for more information.

Rationale for intervention

There are several grounds for DFID intervention in this instance:
- Market failure: the climate change problem is essentially one of market failure: there is an external cost (‘or negative externality’) imposed on society from emissions of greenhouse gases but because, in the absence of government intervention, this cost is not reflected in market prices and therefore not borne by emitters, they will tend to emit too much from society’s point of view. The 2006 Stern Review described this ‘externality’ as “the greatest and widest-ranging market failure ever seen”.[38] Other market failures that may justify government intervention include capital market constraints leading to low level of investment in low carbon technologies, and information asymmetries which can dampen investment flows and prevent individuals from taking action necessary to improve their resilience to future climate impacts
  [38] Stern Review (2006), Executive Summary page 1
- Government inefficiencies: At an international level: the climate finance landscape is complex and fragmented with a proliferation of multilateral and bilateral climate funds. Accessing these sources of finance can be costly and time-consuming for developing countries and the outcome uncertain, making it hard to address climate-related needs. At a national level: a lack of clear policy signals and a coordinated approach to addressing climate change challenges may dampen private sector investment
- Inequitable distribution of resources leading to inequitable outcomes: The effects of climate change present a serious threat to the sustainability of and progress towards the Millennium Development Goals (MDGs). The poorest people are most vulnerable to the impacts of climate change as, by definition, they tend to lack the resources that would enable them to bounce back from climate-related shocks. This intervention would help ensure that climate change is incorporated into the next Economic Development and Poverty Reduction Strategy (EDPRS), being drafted in 2012.

In the absence of DFID intervention (i.e. in the counterfactual) we would anticipate significant delays in implementation of the National Climate Change and Low Carbon Development Strategy. The National Fund for Climate & the Environment would be created in name but there may be long delays in it becoming operational due to a lack of funds: there are no other donors in Rwanda in a position to take this forward, and the limited finance available from the national budget is unlikely to be sufficient to cover both Fund operation and implementation activities. The absence of an operational Fund or finance available at sector level would limit Rwanda’s ability to mainstream low carbon development and climate resilience into national development plans.

Options considered

We consider three options, including the ‘do nothing’ option (option 3) which we use as a baseline against which to compare other options.

Option 1: support the creation and initial operation of a National Fund for Climate and the Environment. This will enable climate action across all sectors of the EDPRS and facilitate the growth of a ‘green’ and innovative private sector. The probability of success will depend on national level commitment to address climate change challenges and the willingness of donors to provide additional support. National-level capacity to bring forward proposals to the Fund will also be a key factor determining success.

Option 2: support one or more key sectors in Rwanda to become ‘climate smart’ through supplementing existing budget support and financial aid programmes. This approach would build capacity and provide support at sector-level. However, it would not support national capability to plan economy wide, nor offer the same scope for attracting and coordinating external sources of finance as option 1. Compared to option 1, it is therefore likely to offer a lower probability of successfully delivering programme outcomes.

Option 3: do nothing
Under this option, no additional DFID support for climate and environment activities is provided. See section 2 above for assessment of likely impacts if DFID chooses not to support either of the above options.

Intervention logic & evidence

In conducting the economic appraisal, we look at the types of impacts that the intervention could bring about based on the available evidence and the theory of change underpinning the programme. The diagram below sets out the theory of change which links the outputs, outcome and intended impact, focusing at input and output level on option 1. This relationship and the indicators which will be used to monitor progress are reflected in more detail in the logframe at appendix A.

Impact: contribute to wealth creation and poverty reduction through low carbon, climate resilient growth
- Climate and environment is mainstreamed into EDPRS
- Climate & environment programmes complement wider pro-poor activities
- Strong macro performance continues
Outputs:
- Capitalisation of the fund
- National fund management capacity built
- Delivery of early projects
- Monitoring and evaluation
Inputs: £1.5m funding staffing and operational costs for the first two years of Fund operation
- Other donors are willing/able to contribute to a well-designed and effective Fund
- Donors willing to follow GoR priorities
- Private sector is interested in investing in low carbon and/or climate resilient activities
- Wider enabling environment supports private sector investment
- £1.5m is sufficient for initial two years of operation
- Procurement process secures sufficient level and quality of expertise
3. Inputs to Outputs
DFID funding pays for mix of high quality national and international experts who are able to build capacity of national staff, mobilise resources from different sources and facilitate the process of getting projects approved.
1. Outcome – Impact
Increased funding and capacity for mainstreaming climate change into national programmes helps Rwanda develop increased resilience to future climate impacts and improve access to energy, contributing to economic growth without reliance on high cost imported fossil fuels.
2. Outputs – Outcome
Availability of resources and evidence from early ‘demonstration’ projects encourages public and private sector to develop strong proposals for climate and environment programmes in line with national objectives, which are approved and implemented.

Outcome: Rwanda able to finance and further develop national programmes and private sector initiatives in line with the CC Strategy & EDPRS II
Intended pathway
Mechanism
Assumptions
1
2
3

Evidence:
1. Outcome → impact level: limited
Evidence of impact related to the creation of national level institutions to enable access to climate resources is limited. Only a few examples of national level climate change funds exist (Indonesia, Bangladesh, Brazil) and have not been in operation long enough to generate lessons that could be applied to Rwanda.
2. Outputs → outcome level: limited
Several sources highlight the need to build institutional capacity in Rwanda in order to improve access to international climate finance[39], pointing towards weak capacity in country constraining the ability to absorb finance.[40] However, given the innovative nature of the intervention, there is little evidence to say whether a capitalised, well-managed fund will be sufficient to ensure climate and environment is fully mainstreamed into national development plans.
[39] SEI (2009)
[40] ODI (2011)

3. Inputs → outputs level: medium
Experience from procurement for the design of the National Climate & Environment Fund suggests that there are several institutions with interest in, and experience of, fund management combined with climate and environment expertise. Other funds (though not related to Climate & Environment) have also been successfully established in Rwanda e.g. a Public Financial Management Basket Fund, a Microfinance Capacity Building Fund and a Microfinance Guarantee Fund, all involving elements of capacity building, resource mobilisation and project delivery. This would suggest that sufficient supply and expertise exists for the delivery of the programme objectives.
Incremental costs

Incremental costs for options 1 & 2 are compared to the counterfactual (option 3) and set out in table 1. Cost estimates are based on early discussions with the team of consultants undertaking design work for the Fund (managed by CDKN). For ease of comparison, we have assumed that a similar total amount of funding would be made available for option 2 as for option 1 and that an equivalent amount of money would be set aside for evaluation.

Table 1: Annual costs for options 1 and 2, relative to option 3
Figures given in £’000s.
Option	Item	2012/13	2013/14	2014/15	Total
1	Staffing costs	500	375	0	875
	Operational costs	250	175	0	425
	Monitoring and evaluation	50	00	150	200
	Total	800	750	150	1500
2	Uplift to existing budget support and financial aid programmes	750	550	0	1300
	Monitoring and evaluation	50	0	150	200
	Total	800	750	150	1500

Incremental Benefits

The expected benefits of the programme are challenging to quantify given uncertainty over the specific activities that would be financed under either option 1 or 2. In addition, the innovative nature of the intervention means that there is little evidence to support key assumptions. As such, any estimates are likely to be subject to a high degree of uncertainty. We have approached this by taking a very conservative approach to estimating impacts.

Several common assumptions underpin the analysis:
- We have assumed that the benefits of the programme accrue only for the two years of DFID support (i.e. the appraisal period is from 2012-2014). This represents a conservative approach, since we may expect benefits from effective mainstreaming support in the first two years of implementation of the Climate Change Strategy to continue well after DFID funding is withdrawn.
- All prices are in 2012 prices
- Costs and benefits are discounted using a discount rate of 10%. This is the discount rate used for all economic appraisals in DFID Rwanda.
- In the absence of intervention, expenditure on climate and environment activities is expected to increase in line with economic growth (8.8% in 2011).

Option 1: support the creation and initial operation of a National Fund
We have attempted to quantify two types of benefits arising from the creation and operation of a National Fund for Climate and the Environment:

Additional finance leveraged
Early work on the design of the Fund suggests that there is a funding gap of around $6bn, comparing current spend with that required to meet the objectives of the Strategy. Even meeting a small fraction of the funding gap would require a concerted effort on the part of the government of Rwanda, private investors, bilateral and multilateral donors. The law enabling the Fund specifies that environmental fees and charges will flow directly to the Fund, providing early capitalisation. However, initial analysis suggests these sources will only provide around $40-50k per year. Other environmental funds (such as the forestry and water funds) are likely to be subsumed into the National Fund, providing an additional $1m upfront, plus approximately $200k per year. However, a key objective of the initial operation phase will be to identify and mobilise additional sources of finance from the government, donors and the private sector.

Key donors interested in this area include Sweden (who chair the Sector Working Group on Environment and Natural Resources), UNDP (who have supported work on environmental sustainability), the Netherlands (who focus on renewable energy and biomass), the World Bank (renewable energy), Germany (renewable energy) and the EU (who recently supported a Strategic Environmental Assessment of the agriculture sector). Early discussions with the EU, SIDA (Sweden) and KfW (Germany) suggest that they would consider allocating new resources to an operational, well-managed Fund. We have assumed that each of these donors would contribute £1m per year to the Fund, in addition to their planned expenditure. Given the time it takes to programme additional funds, we have assumed that only one donor is able to contribute in year one but three contribute in year two.

This is a conservative estimate, given the scale of the challenge, the existence of international commitments to finance climate change[41], the presence in the sector of other donors who may also wish to contribute and the previous track record of donors in providing large-scale support to specific sectors in Rwanda when clear plans of action are identified. For instance, many donors, including DFID bring significant experience of delivering general and sector budget support in Rwanda. In the agriculture sector alone, confirmed sector budget support is in the region of £92m over four years, with a further £56m proposed.[42] However, we feel this conservative assumption is justified, given the risk that although actual contributions may well be higher, there is a risk that not all resources will be ‘new and additional’ i.e. some may diverted from planned expenditure elsewhere in Rwanda and/or brought forward from an existing aid agreement.
[41] The Copenhagen Accords committed developed countries to raise $100 billion per year by 2020 to help developing countries tackle climate change(2009)
[42] DFID Agriculture Sector Budget Support Business Case, Nov 2011

As well as leveraging donor resources, we would also expect the Fund to mobilise resources from other Government of Rwanda budget lines, including drawing on resources provided for general budget support, where DFID have highlighted climate change as a priority. However, we have not attempted to quantify the additional resources leveraged in this way since to do so we would need to know the opportunity cost of increasing spending on climate change (i.e. if government resources are not spent on climate and environment programmes, where would they otherwise have been spent?). In addition, the innovative nature of this approach means that there is little evidence to support assumptions on the quantity of resources mobilised from government resources. The same is true of the quantity of private finance leveraged, which we have also not attempted to quantify.

Improved coordination of donor and government funds (technical efficiency)

Most current support for climate and environment interventions in Rwanda tends to be project-based. A recent self-assessment carried out for the sector[43] pointed to the need to move to a more programme-based approach to ensure long term sustainability of outcomes. The report also recommended taking measures to strengthen coordination of funding streams. The National Climate Change and Low Carbon Development Strategy identifies 31 separate funds that are currently, or soon to be, available for potential climate finance in Rwanda. Better coordination amongst donors, international funds and the government of Rwanda, combined with a clear and transparent framework for programme funding would be expected to improve the efficiency with which resources are used.
[43] Environment & climate change sub-sector, EDPRS self-assessment report Feb 2012, unpublished

The integration of the Fund with government systems, and its location within REMA make it reasonable to estimate technical efficiency improvements as a percentage of existing (and potential future) resources available for spending on climate and environment-related activities. This is a conservative assumption since the Fund also aims to influence spend across all government programmes (i.e. through mainstreaming climate and environment). Such fiscal gains could then be ploughed back into those same activities, generating a proportional increase in the quality/quantity of services being provided. There is little evidence to indicate the size of the expected efficiency gains. We have made a conservative assumption that this intervention will lead to a 1% improvement in the operational efficiency of current climate and environment expenditure (estimated at £38m in 2011). This assumption is tested as part of the sensitivity analysis and break even analysis. This suggests that annual efficiency benefits arising from the Fund could be in the region of £400k per year.

In addition to the quantified benefits above, there are also likely to be further benefits that we have not been able to quantify and which could potentially be very large. These include:
Improved ability of the government of Rwanda to implement an economy-wide approach to climate resilient, low carbon development resulting in improved allocative efficiency of domestic (and donor) spend
- Benefits from actual projects/programmes supported e.g. an increase in the number of poor people who are supported to cope with the impacts of climate change; an increase in the number of poor people with access to clean energy
- Increased knowledge and capacity within the government of Rwanda to address the challenges brought by climate change
- Reduced transaction costs for donors from being able to use the same government of Rwanda systems for monitoring results
- increased transparency and accountability around use of (national and international) climate finance will help raise awareness of the issues at national and international level
- Successful implementation of Rwanda’s National Climate Change and Low Carbon Development Strategy will strengthen Rwanda’s voice in international climate negotiations, improving the chance of an equitable outcome
- The contribution to the evidence base in a new and innovative area enabling lessons to be shared with other developing countries looking to follow suit.

Option 2: support one or more key sectors in Rwanda to become ‘climate smart’ through supplementing existing budget support and financial aid programmes

This option would help build capacity at a sector level and would demonstrate to other sectors the potential benefit of undergoing the same process of becoming ‘climate smart’. However, the potential to improve access to international finance would be more limited than under option 1 since there would be no central Fund to coordinate resource requirements and manage the process of implementing the Strategy. Similarly, the scope for improved coordination of donor funds would also be limited. These potential benefits are considered in turn:

Additional finance leveraged
The demonstration effects from activities in particular sectors may be sufficient to encourage additional resources from other donors and sector budgets, however this is unlikely to be at the scale expected under a well-managed Fund. There is little evidence to support assumptions around the quantity of additional finance that option 2 might leverage. We have assumed, optimistically, that one or two other donors may follow our lead and increase their Sector Budget Support (SBS) funding by a similar proportion to DFID, in order to address climate and environment related needs in the sector. Taking the agriculture sector as an example, a £1.5m uplift would represent an increase of around 15% in DFID support to the sector. The EU are the only other donor in the sector showing significant interest in climate and environment issues. If they were to uplift their agriculture SBS commitment by the same proportion, this would result in around £1.3m of additional resources to the sector per year.

Improved coordination of donor funds

The scope for improved coordination of donor funds would be limited to the sectors of focus. Even then, it is unlikely that the same level of coordination would be achieved through a sector budget support-type approach as through option 1 as other issues may crowd out the discussion. We have assumed for option 2 that the same level of efficiency savings are achieved, but for the agriculture sector only, using agriculture spend as a proportion of total spend to factor down the efficiency savings expected from option 1. On this basis, option 2 is expected to provide around £30k in efficiency savings per year.

Many of the wider benefits identified under option 1 might also apply to option 2, although to a lesser degree. For instance, we would expect to see increased knowledge and capacity within the targeted sector but it is unlikely that this benefit would extend across the broader government programme, as in option 1. Benefits from actual projects and programmes supported may be on a par with option 1, depending on the particular programmes identified under each option.

Balance of Costs and Benefits

The results of the cost-benefit analysis of all three options are outlined below. The cost benefit analysis set out below represents only a partial analysis and is driven by several assumptions which are explored in more detail in section 8 (risks & uncertainty) and outlined in the technical note.

In the table below, options 1 and 2 are compared to option 3 (do nothing) which is used as the baseline. Both options 1 and 2 look cost-effective with the estimated benefits outweighing the costs in both cases. Option 1 would appear the most cost-effective of the two options with an NPV of ~£3m and a BCR of 3.1 (i.e. £1 of expenditure brings £3.10 worth of benefits). The inclusion of unquantified benefits would further strengthen the economic case for both options, more so for option 1.

Table 2: Balance of costs and benefits under options 1 & 2
All values given in £’000s
		2012/13	2013/14	2014/15[44]	Total
Option 1: Support the creation and operation of a National Fund for Climate and the Environment	Programme costs
	Staff costs	500	375	0	875
	Operational costs	250	175	0	425
	Monitoring and evaluation	50	0	150	200
	Total costs	800	550	150	1500
	Discounted costs	800	500	124	1424
	Monetised programme benefits
	Finance leveraged	1000	3000	0	4000
	Efficiency savings	384	405	0	789
	Total benefits	1384	3405	0	4789
	Discounted benefits	1384	3096	0	4480
	Summary
	Present Value costs	1424
	Present Value benefits	4480
	Net Present Value (NPV)	3056
	Benefit Cost Ratio (BCR)	3.1
Option 2: support key sectors to become climate smart	Programme costs
	Uplift to Sector Budget Support (SBS)	750	550	0	1300
	Monitoring and evaluation	50	0	150	200
	Total costs	800	550	150	1500
	Discounted costs	800	500	124	1424
	Monetised programme benefits
	Finance leveraged	1288	1288	0	2576
	Efficiency savings	26	27	0	53
	Total benefits	1314	1315	0	2628
	Discounted benefits	1314	1195	0	2509
	Summary
	Present Value costs	1424
	Present Value benefits	2509
	Net Present Value (NPV)	1085
	Benefit Cost Ratio (BCR)	2
[44] We have assessed the costs and benefits of the Fund over a two year appraisal period (hence no operational costs and benefits show for year 3). However, for completeness, we have included the costs of the independent evaluation which will accrue in year 3

Risks and uncertainty
There are several potential risks (and also some opportunities) that may affect the success of the programme to varying degrees. These are set out in table 3 below and considered in more detail in the Management Case.

Table 3: Risks/opportunities affecting programme outcomes
Risk/opportunity	Probability (L/M/H)	Impact / (-ve/ +ve)	Considered in sensitivity/break-even analysis?
Insufficient capital is available to support fund objectives	M	– – –	Yes
International climate finance through the Green Climate Fund is available and channelled through the Fund	L	++	No
Benefits from improved donor coordination are lower than expected	L	–	Yes
Fungibility between donor and GoR funds reduces resources available	L	–	Implicitly considered in B-E analysis
C&E considered lower priority by GoR, reducing resources available	L	–	Implicitly considered in B-E analysis
Fund supports proposals that have negative C&E impacts	L	– –	No – relates to unquantified benefit
Key funding ‘windows’ are not allocated sufficient funding	M	– – –	No – relates to unquantified benefit
Legal restrictions limit fund manager’s ability to make use of innovative financing instruments	M	– – –	No – relates to unquantified benefit
Once trained, local staff move on	M	– – –	No – relates to unquantified benefit
Insufficient interest from private sector	M	– – –	No – relates to unquantified benefit

Given the uncertainty surrounding several of the assumptions driving the quantified benefits of the programmes, we also conducted break-even analysis to identify, for example, the quantified benefits that would be required for the programme benefits to just offset the costs. Present value costs are around £1.4m. In order to break-even, the Fund would need to leverage at least this amount of additional funding from donors and/or other government resources. Alternatively, in the absence of additional finance, the Fund would need to deliver efficiency savings in relation to current expenditure of around 2%. It is important to remember that there are likely to be several other sources of potential benefits that we have not been able to quantify, which are likely to significantly enhance the economic case.

We have also considered the impact on costs and benefits of extending the appraisal period to five years and assuming that the Fund would become operational without DFID support following a two-year delay. Given that over time, we would also expect increases in the quantity of finance leveraged (as results are delivered and more international climate finance becomes available) and continued efficiency savings, a longer appraisal period improves the economic case for option 1.

Incidence of costs and benefits (distributional impacts)
We have not conducted a detailed distributional impact assessment for the programme, since to do so would require prior knowledge of the activities to be financed in the first two years of the Fund. However, we would expect the programme to deliver proportionately greater benefits to the poor in Rwanda, since poor people tend to be those who are most reliant on the environment for their livelihoods and most vulnerable to future climate impacts.

Financial sustainability
We would expect DFID support to cover operational costs for the first two years. The management team associated with the Fund will be tasked with securing long term financing for their operation after the initial two-year start up period, as well as capitalisation of the Fund. The government of Rwanda are committed (through the law establishing the Fund) to provide resources from environmental fees and fines to capitalise the fund. Since these are unlikely to be large, other resources for capitalisation will be sought from bilateral and multi-lateral donors and may be made available from other Government of Rwanda budget lines.
Attribution to DFID
The initial 2-year operation of the Fund will be attributable to DFID. The longer term impact of the fund will be attributable to future contributors and the Government of Rwanda.

List of data/evidence sources:
Republic of Rwanda: Green Growth and Climate Resilience, National Strategy for Climate Change and Low Carbon Development, October 2011
Stockholm Environment Institute (2009) Economics of Climate Change in Rwanda http://www.rema.gov.rw/ccr/climate_change_report.html
Capacity Development for Development Effectiveness Facility (2010) op cit; Agulhas (2011) Realising the Potential: Making the most out of climate finance - A synthesis report from six country studies: Cameroon, Ghana, Kenya, Morocco, South Africa and Tanzania, Draft report to OECD, http://www.oecd.org/dataoecd/27/38/48597031.pdf
Possibilities for Africa in global action on climate change, Grantham Institute, February 2009
Climate Change; Stocktake of UN Activity, Rwanda Case Study, GHK February 2010
Appendix 3 : Climate & Environment Assurance Note

Intervention Details
Title	Department	Budget
Creation of the National Fund for Climate & Environment (FONERWA)	DFID Rwanda	£1.5m

Responsible Officers
Title	Name	Department
Project Owner		DFID Rwanda
Climate Change and Low Carbon Development Adviser		DFID-Rwanda

Appraisal
Success Criteria	Sensitivity Analysis
Options are assessed against the extent to which they support the implementation of the Government of Rwanda’s National Strategy for Climate and Low Carbon Development	Conducted separately as part of comprehensive Strategic Programme Review (SPR) of the climate change risks and opportunities of the DFID-Rwanda programme which includes a full screening of the GoR’s Economic Development and Poverty Reduction Strategy
Climate & environment category
Risks & impacts / The preferred option is categorised as ‘B’ (medium/manageable) for risks compared to ‘A’ (high) in the counterfactual	Opportunities / The preferred option is categorised as ‘A’ (high potential opportunity) compared to ‘C’ (low) in the counterfactual

Management
Risks and opportunities defined	Climate & Environment Measures agreed	Climate & Environment Measures in log-frame
Yes – risks and opportunities affecting the delivery of Climate and Environment objectives identified in Section B of the management case	Yes – measures identified to mitigate risks in section B of the management case	Logframe includes measures to monitor C&E performance

Evidence
Relevant documents
Business case and project intervention summary / Climate change screening of DFID Rwanda’s portfolio, Harewelle International Ltd and the Global Climate Adaptation Partnership, 2010 pp.38-39

SIGNED OFF BY: Environment Screening note Adviser

DATE: 12/03/2012