Business Case

Summary Sheet

Title: Yemen Social Protection Programme (YeSP) (Phase 1)
Programme Summary: To help reduce extreme poverty and vulnerability and increase individual, household and community resilience in response to the ongoing humanitarian crisis in Yemen. This will be done through improved access to cash based social safety nets, restoring and improving access to basic services and improving livelihoods.
Results under YESP		SFD (@$612m)	SWF	Total	DFID share
Outcome
# people benefitting from cash based support under YeSP (% female)				11.2m (44%)	1.77m (44%)
SFD # of direct beneficiaries of wage employment (# of wage beneficiaries of Safety Net &Community and Local Development programs)		3.2m (44%)
SWF: # of direct beneficiaries of emergency cash transfers			8m (45%)
# people with access to basic services (health, water, education) (% female)		1.9 m (51%)		1.9 m (51%)	342,000 (51%)
# of working days created (from all interventions)		21m		21m	3.8m
(i) # women (% disabled children) and (ii) children benefitting from nutrition interventions		(i) 80,000 (10%) / (ii) 16,000		(i) 80,000 (10%) / (ii) 16,000	(i) 14,400 (10%) / (ii) 2,880

Programme Value: up to £70m with £47m for Phase 1 covered in this BC		Country/ Region: Yemen/ MENAD
Programme Code:	Start Date: / May 2018	End Date: / Phase 1 until 2020/21 when we will consider an extension until March 2023 of a further £23 million based on an assessment of need, value for money, results and risk.
Overall programme risk rating:	MajorMajor
Vault Number:	TBC

Intervention Summary (2 pages max)
After 3 years of conflict, Yemen is the world’s largest humanitarian crisis. More than 75% of the population need humanitarian assistance; over 33% face extreme food shortages and are at risk of starvation; malnutrition rates of children and mothers are increasing; and poverty has increased for an estimated 55% of the population. The ability of people, households and communities to cope has been eroded. Yemen’s social protection system and its institutions are experiencing strains.

The UK will provide up to £47 million over 3 years (2018/19 to 2020/21) to the Yemen Social Protection Programme (YeSP). It will help to reduce extreme poverty and vulnerability and increase resilience in response to the ongoing humanitarian crisis in Yemen. It will help: (i) poor and vulnerable people to buy food and essential goods; and (ii) preserve and sustain social protection institutions who help the poorest. YeSP will do this through supporting cash transfers, improving access to basic services and providing livelihood opportunities. At the outcome level, it will contribute[1]: (i) up to 11m people benefitting from safety net programmes[1] (44% women). This includes unconditional cash transfers for up to 8m people (of whom 45% are women and 11% are disabled); (ii) creating 21m workdays; and (iii) providing 80,000 women and children with nutrition interventions (including 10% disabled children). Specifically YeSP will
[1] SFD and SWF will receive broader funding from other donors
[1] The social safety net is a collection of services provided by the state or other institutions such as friendly societies. It includes welfare, unemployment benefit, universal healthcare, homeless shelters, and sometimes subsidized services such as public transport, which prevent individuals from falling into poverty beyond a certain level.
1. Maintain and expand cash-based social safety nets (50%): providing £20.8m to improve the purchasing power of poor and vulnerable people helping them to buy food and essential goods. £16.5m will reach up to 5m people with support for: conditional cash transfers (CCTs) in exchange for work; CCTs for the attendance of pregnant and lactating mothers at nutrition screening services; and employment in service delivery support. Delivery will be via a Memorandum of Understanding (MOU) to the Social Fund for Development (SFD) under their social safety nets operations. £4.33m will be for unconditional cash transfers, reaching up to 1.5m households (HHs), (8m people) on the Social Welfare Fund (SWF) beneficiary list via a co-financing agreement with the World Bank (WB).
2. Restore and improve access to essential basic services and assets (28%): £11.5m to maintain and improve the provision of essential services. This will be through: building and rehabilitating schools, clinics, water points and agricultural land and training personnel to deliver health, education and nutrition services. Delivery will be via a MOU to SFD under the community and local services component. DFID will only make finances for public asset construction available upon satisfactory conclusion of a review of SFD’s internal controls and quality assurance processes for construction projects expected during the programme’s first year.
3. Enhance livelihoods (7%): £3.1m to support livelihoods for the poorest through microfinance grants and loans, small and micro-enterprise development, and village savings and loans schemes. Delivery will be via a MOU to SFD under the Small and Microenterprise Development component.
4. Strengthen Institutions, programme management and monitoring (PMM) (15%): (£6.1m) will support the delivery of YeSP. It will focus on management and supervision as well as hiring a third-party monitoring (TPM) agency and potentially an evaluation.
5. Contingency: £5.5m will be held co-financing of the emergency unconditional cash transfer component.

The proportion of costs for key project activities above is based on current plans. This may vary due to the operational environment and relative performance of each activity.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
YeSP supports the UK Aid Strategy, the Single Departmental Plan (SDP) and DFID Yemen’s (DFIDY) Business Plan (BP). It directly contributes to tackling extreme poverty and helping the Yemen’s’ most vulnerable people (Strategic Objective - SO4). It indirectly supports efforts to: strengthen resilience and response to crises (SO2); strengthen peace, security and governance (SO1).It is central to DFIDY’s efforts to leave no one behind and supports Strategic Defence and Security Review commitments to spend at least 50% of DFID’s budget in fragile states and regions annually. YeSP will also support DFIDY’s approach to cash-based programming (in line with the Grand Bargain) and improving delivery and monitoring and evaluation mechanisms.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
YeSP will contribute to DFID’s SDP results on water and sanitation for health (22,320 people provided with access to water) and education (49,104 students having access to education further disaggregated by gender). These results come from the basic services component which DFID will only make disbursements after an internal review. Its contribution to DFID’s total SDP results is minor; there is limited scope to scale.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Yes. This support will complement that provided by other donors and support the delivery of the UN Yemen Humanitarian Response Plan (YHRP). YeSP will help enhance coordination between humanitarian and development actors by helping to maintain key Yemeni institutions until they can be once again funded domestically in the longer term.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Yes. Cross-HMG funds would not align with the objectives of this programme and are not sufficient in scale.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
Meeting the needs of the most vulnerable is built into all DFIDY’s programmes. This programme also links to the wider DFIDY Humanitarian portfolio.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
This programme is designed to be flexible so that activities can be reprioritised should the needs and the nature of the conflict changes. Partners have demonstrated flexibility, for example, through scaling up support to cash for work programmes so people at risk of starvation are provided with an income to buy food. We will work with partners to monitor activities quarterly to review activities and reprioritise or adapt activities as required based on evidence.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
YeSP is within DFIDY’s risk appetite. With mitigating measures put in place, our assessment is that the residual risk is major, due to the operational context and associated fiduciary risks; some are common in DFYD’s portfolio. A fuller assessment is covered in the management case. Key risks include:
- (Fiduciary) weak internal financial management giving rise to possible corruption and fraud. This will be mitigated by engaging an independent payment delivery agency with transparent and robust internal controls for the disbursement of emergency cash payments to SWF beneficiaries;
- (Fiduciary) centralised organisational structure with insufficient checks/balances, including Board oversight. This will be mitigated by increased donor engagement of SFD management operations including discussions on improving interim governance arrangements.
- (External context) political interference creating disruptions to delivery and supervision. This will be mitigated by having robust security protocols based on local knowledge. DFIDY also has an independent monitoring programme in place which will also help to verify the use of funds.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
Partners will provide DFID with regular communications stories and use UK Aid branding, where appropriate, with exemptions granted if this presents a security threat. A visibility statement agreed with partners will be put in place setting out what assets and supplies will display the UK aid logo.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
Yes. The business case scored 2 in the Quality Assurance Unit (QAU) process. Reviewers noted that the business case presents a strong rationale for intervention in the humanitarian context and that support to develop national social protection systems will promote longer-term sustainability. Recommendations made to strengthen delivery will be incorporated into the programme’s detailed design at inception and reflected in the delivery plan.
Does the SRO and team have the capability and resources to deliver this programme?
The SRO has the capability and resources to deliver with support from a Programme Manager. They will scrutinise delivery and risks through reporting from partners and monitor the project’s delivery plan. In addition, the core programme team will draw on the support of cross-cutting advisers to ensure the programme is well managed and achieving its intended results.
Strategic Case

A: Context and need for an intervention

Yemen has a long history of conflict, instability and pervasive poverty. The country faces state fragmentation, endemic corruption, rapid population growth, deep-rooted gender inequality, poor provision of basic services, and a weak economy. As a result, even before the current conflict, the UN assessed that 16 million Yemenis needed some form of humanitarian assistance. In 2016, Yemen ranked 168 out of 188 countries on the Human Development Index (HDI)[2].
[2] See the 2016 UNDP Human Development Report. http://hdr.undp.org/sites/default/files/2016_human_development_report.pdf

Since early 2015, Yemen has suffered from conflict. This has led to the world’s largest food security crisis and the largest outbreak of cholera ever recorded in a single year with almost one million suspected cases in 2017. As of December 2017 22.2 million people (76% of the population[3]) were in need of some form of humanitarian aid[4]. This is an increase of 1.5m since June 2017 (15%). The scale and severity of humanitarian needs are a direct result of the conflict. 8.4 m people are at risk of starvation. Fewer than half of Yemen’s health facilities are functioning, and some 16 million people lack adequate access to clean water or sanitation.
[3] Yemen’s population is currently 27.5 million https://data.worldbank.org/country/yemen-rep?view=chart
[4] Humanitarian Needs Overview, 2018

Yemen has had a long history of conflict, instability and deep poverty. Following repeated cycles of conflict and political crises, both poverty and inequality increased over the last 15 years, making Yemen the poorest country in the Middle East. The country faces a range of deep-seated development challenges including state fragmentation, rapid population growth, deep-rooted gender inequality, poor provision of basic services, water scarcity and a poorly managed and weak economy that is dependent on declining oil reserves and now subject to capture by conflict parties. There is also endemic corruption and high youth unemployment. The escalating conflict continues to inflict civilian casualties and cause extensive damage to public and private infrastructure.

The collapse of the economy is having a direct effect on the purchasing power of the most vulnerable households. Since the onset of the conflict, official oil and gas exports producing vital revenue have halted. Yemen’s foreign exchange reserves have decreased as a direct result. The Central Bank of Yemen (CBY) is now challenged to conduct basic services with importers struggling to access foreign exchange for commercial imports of basic necessities. This has a direct impact on consumers as Yemen is reliant on imports for 90% of its food. The reduction in food imports and currency depreciation has pushed up food prices, diminished households’ purchasing power and fuelled black market activity. Public sector salaries have been unpaid for over a year affecting over a million civil servants, and delivery of public services. Pre-conflict, 25% of households relied on government salaries, of which 31% were food insecure.  By 2016, 35% of the total population reported that they had lost their main source of income. The poorest and most vulnerable (including Internally Displaced Persons (IDPs); female headed HHs, widows, the elderly, and disabled) are affected the most by these challenges. The inter-linked political, economic and now humanitarian crises have deepened already severe poverty, vulnerability and gender inequality. In this context, with governance systems and institutions disintegrating, public services collapsing, investment in a robust social protection system is crucial.

Pre-crisis, Yemen had broad SP system. However, after war broke out, much of Yemen’s SP system stopped functioning. Prior to the conflict, Yemen had social assistance; social development programmes, grant and production support programmes, social insurance and SP programmes targeting those with special needs. These national programs were established in the mid-1990s, and their capacity was developed over two decades with intensive investments from the donor community and the Government of Yemen (GoY). SP programmes helped to contribute to poverty reduction in Yemen from 40.1% in 1998 to 34.8% in 2005[5]. Since the conflict began in 2015, large parts of Yemen’s SP system have ceased to operate and GoY support stopped altogether.
[5] Social Protection and Safety Nets in Yemen, Ali Azaki December 2015. Institute of Development Studies.

Women and girls continue to be marginalised. Even before the current crisis, women and girls faced discriminatory social norms that limited their economic, social and political participation. Yemen was ranked last out of 142 countries in the World Economic Forum’s Global Gender Gap Index in 2014[6]. Yemen ranks highest in the Gender Inequality Index[7] and performs poorly against a range of indicators. Conflict has exacerbated gender inequalities, and women and girls face insecure livelihoods and lack of safety and access to basic services[8]. Conflict and displacement have increased rates of violence against women and girls and early marriage.[9], [10].
[6] ## World Economic Forum (2014). The global gender gap report 2014, Geneva: World Economic Forum, 2014, http://reports.weforum.org/global-gender-gap-report-2014/
[7] World Food Program (2012) Yemen – Comprehensive Food Security Survey, 2012, www.wfp.org/content/yemen-comprehensive-food-security-survey-2012
[8] Heinze, M and Baabbad, M. (2017) “Women nowadays do anything.” Women’s role in conflict, peace and security in Yemen, SaferWorld, CARPO and YPC https://www.saferworld.org.uk/resources/publications/1125-awomen- nowadays-do-anythinga-womenas-role-in-conflict-peace-and-security-in-yemen United Nations (2017) Humanitarian Needs Overview 2017: Yemen. http://reliefweb.int/sites/reliefweb.int/files/resources/YEMEN%202017%20HNO_Final.pdf
[9] Gressmann, W (2016) From the Ground Up: Gender and Conflict Analysis in Yemen, Oxfam http://policy- practice.oxfam.org.uk/publications/from-the-ground-up-gender-and-conflict-analysis-in-yemen-620112
[10] Amnesty International (2015) Yemen the Forgotten War https://www.amnesty.org/en/latest/news/2015/09/yemen- the-forgotten-war/

YeSP will help to address some the challenges faced by Yemen by increasing purchasing power of households, supporting key SP institutions and providing targeted support to women. The Social Fund for Development (SFD) has a long track record of providing social safety nets and supporting Small and Medium Enterprise (SMEs) which will also help to support the informal economy and livelihoods. In addition, support to Social Welfare Fund (SWF) beneficiary through the provision of emergency cash payments through the World Bank’s Yemen Emergency Crisis Response Project will help increase resilience of households. It will complement DFID’s other humanitarian interventions designed to avert famine for example through the World Food Programme’s distribution of food to vulnerable populations. The project’s ability to deliver assumes the external macroeconomic fundamentals (people assess to markets and price stability) hold.

The Social Fund for Development (SFD)

One of the Yemeni SP institutions[11] that has continued to operate nationally is the Social Fund for Development (SFD). SFD’s objectives are to: 1) improve access to basic services; 2) enhance economic opportunities, and; 3) reduce the vulnerability of the poor. SFD provides a safety net for some of Yemen’s poorest and most vulnerable people through: community led development delivered through conditional cash based support to restore and improve access to basic services and assets (e.g. clinics, schools, water points); capacity building for local level planning and service delivery; and providing economic opportunities (e.g. through access to microfinance).
[11] World Bank 2017: http://www.worldbank.org/en/news/feature/2017/01/17/preserving-institutions-in-yemen-that-help-people-now-and-will-be-vital-for-future-recovery; UN Humanitarian Plus Straegy (2018); and DFID Yemen Business Plan 2018.

SFD has delivered results at scale (see Annex 1). The previous SFD Phase IV Crisis Response Plan (2011-18) delivered four main areas:
- Community Led Development (CLD) providing basic services (including education, health, water and sanitation), reconstructing and rehabilitating facilities and training personnel.
- Labour Intensive Public Works (LIPW): cash-for-work schemes providing short-term employment for vulnerable households whilst creating community assets.
- Empowerment for Local Development (ELD): local level capacity building for development, including support to NGOs, Village Cooperative Councils and local authorities.
- Small and Micro-Enterprise Development (SMED): support to the policy environment, microfinance loans to individuals and small businesses, and grants to improve production value chains.

SFD is supported by IFIs and bilateral donors. SFD is supported by the World Bank, Islamic Development Bank and bilateral donors including: the European Union (EU); USA; Germany; and the Netherlands. Under Phase IV, SFD spent $779m on programming but its ability to spend was severely affected when the conflict broke out. In September 2014, the World Bank suspended its support to SFD due to uncertainty over future support to Yemen; this was followed by the Bank suspending all disbursements to the entirety of its Yemen portfolio. A number of other donors also followed suit including: Saudi Fund, Kuwait Fund, OPEC Fund, and Abu Dhabi Fund. Donor support resumed and new agreements were signed in 2017 including by the Bank, once SFD re-programmed project lines to adapt to the circumstances. The GoY contributed $113 million to SFD operations between 2011 and 2014. DFID has supported SFD since 2005 and is the second largest donor after the World Bank. DFID provided £108.5m to Phase IV ($167.2m), or 18% of the total budget ($912m – including SFD operations expenses and cost of studies and evaluations).

1. SFD Phase V (2018-20) will continue to deliver support to the poorest and most vulnerable affected by conflict and the humanitarian crisis. It aims to create an estimated 21m work days, with c.3.2m people (c.44% women), benefitting from access to basic services and 0.6m from income support. SFD V will work via three programme areas:
  1. Social Safety and Labour Intensive Works Programme (SSN): this will include cash for work (CfW), cash for social services (CSS) and a conditional cash transfer on nutrition.  CfW activities will give access to clean water and encourage better water use through for example rainwater harvesting and terrace rehabilitation. Budget $404.m (54% of total).
  2. Community and Local Development (CLD): this will restore basic services though infrastructure and service delivery in the sectors of education, health, water and sanitation as well as capacity-building of local entities for service delivery.  Under the CLD, SFD will continue to promote and support self-help initiatives where communities volunteer in many initiatives that provide services such as clean water and improving access roads. Encouraging and building on communities willingness and enthusiasm is important given the absence of government institutions providing services created an environment conducive for self-help initiatives. Budget c.$285.5m (38% of total).
  3. Small and Microenterprise Development and Promotion services (SMED and SMEPS): this will support small and medium enterprises (SMEs by providing financial and technical support to Micro-Finance Institutions, Village Savings and Loan Associations as well as business development of SMEs such as farmers, Primary Health Care workers where over 100,000 temporary and permanent job opportunities are expected to be created.  Budget $60.5m (8% of total).

Social Welfare Fund (SWF)

1. The SWF provided an unconditional cash transfer (CT) to the poor and vulnerable to protect them against extreme poverty. Since the conflict broke out in 2015 the GoY and donors and IFIs (e.g. World Bank, US, EU and UNICEF) ceased funding to SWF resulting in some of Yemen’s most vulnerable and poorest households losing a crucial safety net at a critical time[12].
  [12] At the governorate level, 51.7% of affected people were concentrated in Taiz; 12.6% Hodeida; 9.6% Hajja 9.4% Ibb; 9.3%; 5.5% Lahj and 5.3% Amran. Yemen Socio-Economic Update (YSEU) (Issue 29, Nov. 2017). Ministry of Planning and International Cooperation, Economic Studies and Forecasting. Nov 2017.
2. The World Bank has now set up a system to pay SWF beneficiaries outside of GoY systems and is investing on improving it. As a direct response to the food crises and risk of famine in Yemen, in May 2017 the World Bank approved the Yemen Emergency Crisis Response Project (YECRP). The US$200 million projects provide cash transfers for up to 1.5m poor and vulnerable households (8m people) on an existing SWF beneficiary list. The United Nations Children’s Fund (UNICEF) is the implementing partner, with support from the US to the programme management and monitoring component (e.g. technical assistance and also systems to improve targeting). The average payment to a HH has not changed at 5,000 Yemeni Riyals (YER)/ HH/ month (c. $13-15 as a result of exchange rate depreciation), received quarterly through a network of contracted private pay agents in Yemen (such as through micro-finance agents).
3. Results: To date, the World Bank cash transfers programme has made two quarterly payments (November 2017 and March 2018) across all 22 Governorates with a third round of payments planned for August 2018. A further three rounds of payments is planned thereafter but will require additional financing. Third party monitoring of the first quarter (Q1) payments shows:
- 1.33 million households received Q1 payments (against a total of 1.58m – i.e. 84%). Of these, 44% were direct female recipients.
- 83% of surveyed female recipients and 93% of the male reported they used the cash for food, medicine and repayment of household debt (e.g. food bought on credit).
- 79.5% of the beneficiaries received their cash within the first visit to the payment centre.
- 85.7% of the local actors and leaders interviewed believed the project helps the Yemeni people.
- 97.6% of beneficiaries reported they received the right amount of cash entitlement.

The use of cash transfers in Yemen

Cash transfers are one of the best ways to reach those who need aid the most. This conclusion is supported by strong evidence and the Grand Bargain. The Yemen Cash and Markets Working Group (CMWG) conducted a study looking at the functionality of different types of market systems and the communities’ preference for various response options. This review in December 2017[13] concluded that cash transfers are a good means for providing support to the poor and most vulnerable in Yemen. CTs can scale amounts or coverage, with limited or no inflationary impact. Communities preferred beneficiary targeting based on economic status rather than geographic or categorical status (e.g. being an internally displaced person)[14]. Beneficiaries used the support to buy food commodities, cooking gas, and hygiene items.
[13] Inter Agency Joint Cash Study: Market Functionality and Community perceptions of cash based assistance. December 2017.
[14] Supported by the conclusions of the Inter Agency Joint Cash Study: Market Functionality and Community perceptions of cash based assistance. December 2017.

More can be done to improve delivery of CTs. There are delivery challenges in Yemen including the need for: better targeting; improved beneficiary verification (e.g. via unique identifiers such as biometrics); and improved payment systems (e.g. to increase availability of cash for beneficiaries and use of mobile/ e cash where possible). Donors in Yemen also agreed in January 2018 to:
(i) Increase the use of humanitarian cash (and more multi-purpose cash[2]), where appropriate;
[2] Multi-Purpose Cash Grants enable beneficiaries to adapt to the changing circumstances and to tailor their purchases to meet their specific needs.
(ii) Improve the alignment, harmonisation and coordination between humanitarian and social protection actors and institutions;
(iii) Improve data and evidence to enable harmonised planning and complementary (e.g. targeting lists); and
(iv) Build on systems that can scale.

UK support to SFD and SWF beneficiaries will:
1. Help to protect, preserve and improve the key SP institutions. The joint statement of social protection actors to the World Humanitarian Summit concluded that humanitarian actors should work to progressively move chronic humanitarian caseloads into social protection systems where possible. This means developing or supporting safety nets or social assistance delivery mechanisms alongside the provision of humanitarian assistance. In Yemen maintaining, sustaining and improving SFD and the provision of cash transfers to the SWF beneficiary list will help to preserve the institutional foundations for this transition humanitarian caseloads in the longer term. Working closely with the World Bank, there is an opportunity to leverage wider donor and UN support to help rebuild and reform the SP sector in Yemen. A fully domestically financed social protection system is unlikely in the short-medium term. SWF beneficiary list and SFD will continue to be largely donor funded. In the longer term the sustainability of SFD and SWF is contingent on securing Government revenue. In the next 10 years, we would hope to see domestically resourced, shock responsive social protection systems in Yemen.
2. Help address immediate needs, reduce extreme poverty and vulnerability and increase individual, household and community resilience in response to the protracted humanitarian crisis in Yemen. This will be done through improved access to better quality safety nets and basic services as well as enhanced livelihood opportunities.
3. Support improvements in the delivery of cash transfers through improving a) the alignment, harmonisation and coordination between humanitarian and social protection actors b) data and evidence and improvements in targeting lists.

C: UK comparative advantage

The UK is respected as a global leader on social protection, humanitarian reform and a trailblazer in bringing about the use of cash in a variety of crises (such as in Kenya and Lebanon). In Yemen, this is backed by our continued investment on social protection systems with over 10 years of engagement, principally through SFD, enabling it to function in the absence of enduring GoY support since the conflict broke out. DFID’s unearmarked funding has played a critical part in SFD being able to respond flexibly to the changing needs (e.g. by scaling up labour intensive public works and rehabilitating damaged public infrastructure). Our technical assistance is viewed[15] as valuable and has helped shape the programme as it stands.
[15] Feedback from SFD staff during the Programme Completion Review for Phase IV support.

DFID Yemen has an integrated humanitarian and development portfolio in contrast to a number of other donors (e.g. unlike EU’s ECHO/DEVCO and USAID’s equivalents) making it well-placed to take a protracted crisis approach, bridging development and humanitarian financing to work more closely. DFID plays a convening role in both programming and policy, influencing key donors (e.g. US, Japan and Germany) to align better on the use of cash in Yemen. Additionally, as IDA’s largest donor through our executive Board we have pushed for stronger delivery and results of the World Bank’s operations in fragile and conflict affected states leading to a number of policy commitments and a doubling of resources for FCAS.

D. Impact and Outcome that we expect to achieve

The expected impact, outcomes and results* from YeSP are:
- Impact: A reduction in extreme poverty and vulnerability in Yemen.
- Outcome: To build and support strong and adaptive social protection systems which provide safety nets, basic services and enhanced livelihoods for the most vulnerable people in Yemen.

Table 1: Proposed results leveraged under YESP
Outcome	SFD (@$612m)	SWF	Total	DFID share[16]
# people benefitting from support under YeSP (% female)			11.2m (44%)	1.77m (44%)
SFD # of direct beneficiaries of wage employment (# of wage beneficiaries of Safety Net &Community and Local Development programs)	3.2m (44%)
SWF: # of direct beneficiaries of cash transfers		8m (45%)
# people with access to key services (% female)	1.9 m (51%)		1.9 m (51%)	342,000 (51%)
# of working days created (from all interventions)	21m		21m	3.8m
(i) # women (% disabled children) and (ii) children benefitting from nutrition interventions	(i) 80,000 (10%) / (ii) 16,000		(i) 80,000 (10%) / (ii) 16,000	(i) 14,400 (10%) / (ii) 2,880
[16] These indicative results are based on budget estimates from SFD of $612m in support for Phase V supported at 18% and SWF beneficiary reach of 1.5m HHs (8m people) supported at 15% in Q3 by DFID.

*All data will be disaggregated where relevant and possible: # or %: female; IDPs/ returnees; Youth; children; disabled/ special needs; elderly. Figures given above are for DFID attributed share.
Compliance with the Gender Equality Act
1. In developing this Business Case, we have taken into account gender-related differences in the needs of those affected and will encourage our partners to ensure appropriate responses, in compliance with the International Development (Gender Equality) Act 2014. All partners will collect and analyse data disaggregated according to age and gender in order to provide quality analysis and evidence to inform targeted interventions. We will ensure the relevant delivery and accountability mechanisms are gender-sensitive, so that services are effectively delivered to women and their feedback is considered.
2. SFD recognises the additional impact of poverty on women and girls and the challenges they face in accessing the same opportunities as men and boys. Currently, 44% of beneficiaries from SFD overall are women. SFD explicitly seeks to improve its impact on women and girls e.g. measures to enable women to undertake more cash for work; targeting female entrepreneurs in their support to microfinance. SFD’s basic services work is enabling more girls to attend school and women to access health facilities. SFD disaggregates data by sex wherever possible and reports on this basis. SWF reaches 1.5m households (8m people), and 45% of its beneficiaries are women. The program was designed to target the chronically poor, orphans, and vulnerable children, widows, persons with disabilities, the elderly and female-headed households. Field facilitation is supported by social workers, mostly women, to ensure reaching out to female beneficiaries; and the TPM agency will include female workers to also reach women and ensure that they are able to voice any potential concerns or complaints.
Disability
The GoY’s 2013 Demographic and Health Survey (supported in part by DFID) collected data on disability. The final report was published in 2015. The survey found that 3.6% of the population (c. 885K people), had some form of disability. An estimated 6,000 people have been left disabled – most as a result of a blast, mine, or gunshot. Currently, 11% of SWF’s 1.5m HHs are registered as disabled (165,000 HHs with each HH having an average of 7 people). SFD works to integrate children with special needs into ordinary schools. During the last phase of support, 7,540 special needs children were integrated, of whom, 52% were female[17]. We will work with partners so that that they: include disability in their vulnerability targeting criteria (e.g. for CTs); use the Washington Group questions when identifying people with disabilities; and disaggregate data on key indicators where the benefits are delivered at the individual or possibly at the household level.
[17] See: http://www.sfd-yemen.org/category/11
Terrorism and financing
We will work with partners to ensure steps are taken to address conflict sensitivity as detailed in the appraisal case. Terrorist groups including Al-Qaeda in the Arab Peninsula and Daesh-Yemen are active in Yemen. Partners and all downstream partners are expected to make themselves aware of, and partners to sign compliance with, the relevant counter terrorist financing legislation. Due diligence and delivery chain mapping is undertaken on all partners to reduce risk and provide further assurance over the use of UK funds.

Safeguarding
In avoiding doing harm, DFID Yemen will ensuring that interventions do not: sustain unequal power relations; reinforce social exclusion and predatory institutions; exacerbate conflict; contribute to human rights risks; create or exacerbate resource scarcity, climate change and/or environmental damage; increase communities’ vulnerabilities to shocks and trends. DFID Yemen will undertake an enhanced due diligence assessment of safeguarding policies of both SFD and UNICEF in advance of implementation. These will be incorporated into project management cycle pin line with good practice and other programmes in the overall portfolio. We will ensure interventions do not displace/undermine local capacity or impose long-term financial burdens on partner governments.

Appraisal Case

A: What are the feasible options that address the need set out in the Strategic Case?

Three feasible options have been identified that address the need set out in the Strategic Case as well as a counterfactual (“do nothing”). These are the only viable mechanisms for supporting social protection in Yemen. Emergency Humanitarian Cash transfers can be delivered through other partners but these vehicles cannot deliver at the scale required to reach those in need (it would take a significant investment of time and resources to develop the systems and capacity to match the scale of these mechanisms). Supporting SFD and SWF beneficiaries through their well-established systems can also lead to strengthening systems:

Option 1: Do nothing.

Option 2: Support SFD only.

Option 3: Co-finance support to SWF beneficiaries only.

Option 4: Support both SFD and SWF beneficiaries.

Option 1: Do nothing

What is proposed? How would it work? Under Option 1, DFID Yemen would not fund any further support to social protection systems in Yemen. Other donors can reasonably be expected to continue support. The UK will indirectly support social protection in this counterfactual because the World Bank is likely to continue to prioritise financing its YECRP project to support SWF cash transfers. These will be drawn from IDA resources which the UK contributes c.12% of the total financing.

Risks: There are two main risk factors. First, with limited resources available for support to the remaining Yemeni institutions, this would make worse already dire humanitarian crises where around 10 million people are in need of food assistance. Second, there would be a missed opportunity of failing to influence social protection and wider systems and thereby undermining key Yemeni institutions.

Balance of advantages and disadvantages: While ‘Doing nothing’ would free up funds for other programme priorities in DFIDY’s portfolio it will severely limit the number of partners we can do work with given SFD and SWF’s ability to reach at least 8 million people, including the rural poor. Furthermore, it is unlikely other donors would step in to fill the gap left by DFID and there is a chance that others may reduce their support.

Option 2: Support SFD only

What is proposed? How would it work? Support only to the implementation of SFD’s Crisis Response Plan, Phase V would focus our support over a three year period costing £34.5 million (including cost for evaluating of the programme; £57.2 over five years in total) to enhance the resilience of the most vulnerable communities and households to cope with multi-dimensional needs, whether of a chronic long-term nature or those needs emerging as a result of the on-going conflict; SFD will achieve this through supporting income generation, livelihood opportunities, restored basic services and reviving Small and Medium-scale Enterprises (SMEs).

1. Expected results (dependent on amount of total donor funding received) include:
  1. 3.2 people reached across the country with income opportunities;
  2. 21 million work days created
  3. 1.9 million people with access to key services; and
  4. 80,000 women and 16,000 children (including 1,600 disabled children) accessing nutrition interventions.

Evidence: Evidence for supporting this option is as follows:
	Global	Yemen
Social Protection/ Labour Intensive Public Works	Strong: Social assistance has proven to improve household food security and dietary diversity, stimulate health service use, increase women’s decision-making power and choice, reduce incidences of child labour, raise school attendance and help foster economic autonomy[18]. Predictable social transfers can protect the poor from the impacts of shocks, including the erosion of productive assets and minimise negative coping practices. / Receipt of the public works wage usually leads to a temporary reduction in the depth of poverty, but rarely results in a drop in headcount poverty. Outcomes are dependent on the value of the wage, the duration of employment, the cyclical provision of employment, and the distribution of benefits arising from the assets created.	Strong: SFD’s LIPW programmes have been successful at targeting poor and deprived communities and at meeting their priority needs An impact evaluation of the SFD LIWP[19] found “statistically significant program effects on food consumption, debt repayment and durable goods ownership,” and that “the LIWP program played a role in cushioning targeted communities from the economic shock of 2010–2011, averting possible longer term consequences related to selling off assets and increased debt, and positive impacts of the LIWP created infrastructure on water availability. A more recent review of LIPW[20] in SFD concluded Overall, LIWP has positive short term benefits for beneficiaries. In the longer term, the assets created are of generally good quality. Income gains were used to increase staple food consumption, reduce levels of indebtedness and protect loss of sustainable assets to cope with the crisis. There was improved access to water where projects focused on water availability However, benefits were found to be unequally distributed across participants as the crisis had attracted participation of households that would have normally self-selected out of enlisting for workfare. Wages set on a piece-rate basis, created greater rewards for workers involved in more skill-intensive tasks. There was no detectable impact on animal asset ownership, consumption of higher value foods and ownership of goods such as clothing and household utensils.
Community Led Development	Mixed: A 5 country rigorous impact evaluation from CDD/R in conflict affected countries[21] concluded that, as currently designed, implemented, and evaluated, CDD/R delivers tangible economic outcomes more than it generates social changes related to governance and social cohesion. CDD/R programming is better at producing outcomes directly associated with the project rather than broader changes in society	Mixed: SFD has seen to be effective at extending a participatory, community led development models across Yemen particularly to rural and remote areas. Two institutional assessments focused on SFD’s indirect contribution to national public/private implementation capacity, both through the transfer of ‘expertise’ and co-operative arrangements for implementation and policy development. SFD’s operations have reached about 25% of Yemen’s 40,000 villages[22] and more than 50% of the rural population[23].
Microfinance	Mixed: A rigorous randomized evaluation of the "traditional" micro-lending model was undertaken in India[24]. The findings suggest that access to microcredit has important effects on household expenditure patterns and the creation and expansion of businesses, but no effect on health, education, women’s decision-making, or average monthly expenditure overall, at least in the short term. It is possible that impacts on education, health, or women’s empowerment would emerge after a longer time, when the investment impacts (may) have translated into higher total expenditure for more households. However, at least in the short-term, microcredit alone does not appear to be a recipe for changing education, health, or women’s decision-making.	Mixed: A 2014 review of existing evidence of microfinance showed that the impact is mixed, not up to date and reliant on SFD’s own assessments. SFD reported a positive impact on micro finance beneficiaries. Its assessments (in 2003, 2006 and 2009) suggests this increased people’s income, improved their living standards, empowered women and created more job opportunities for communities. SFD (2008) that conducted a market study on women reported that most of women microfinance clients are engaged on a very small scale of activities, most of them are home based enterprises. However Aliriani (2002) reported that microfinance could have reached more poor people. This was reinforced by an IFC study (2007) that said there is a promising market for microfinance in Yemen but dependent entirely on the education of clients, loan facilitation and finally training and consulting clients.
[18] Ibid.
[19] The evaluation was funded by the U.K. Department for International Development, conducted during 2011–2013 by the University of California Berkley and RAND Corporation.
[20] Highlights of findings and conclusions of SFD ‘Labour intensive Public Works Programme’ (LIWP) Sharon Beatty and Khalid Al Dubai, 21 September 2017. The LIWP is implemented by SFD in eight governorates: Amran, Sana’a, Ibb, Dhamar, Mukulla, Hajja, Hodeida, and Raymah. Of these 8, this study selected 4 for inclusion in the sample: Amran, Sana’a, Ibb, and Dhamar. The evaluation selected these 4 governorates as they have sufficient numbers of “completed” projects which also include the most common LIWP interventions. The other 4 governorates were excluded because either they had not yet reported at least 2 completed projects by the time the study was being designed, or, in the case of Mukulla, security concerns prevented its selection.
[21] Afghanistan, Democratic Republic of Congo (DRC), Aceh (Indonesia), Liberia and Sierra Leone.
[22] SFD Management Information System, Jul. 2013.
[23] Based on the 2004 Yemen Population Census, 73 per cent of Yemen’s 19.3 million population live in rural areas.
[24] The Miracle of Microfinance? Evidence from a Randomised evaluation. Abhijit Banerjee, Esther Duflo, Rachel Glennerster. American Economic Journal: Applied Economics. March 01, 2014

More detailed information on evidence can be found at Annex 2.

Risks: The key risks are as follows and are the similar to those in previous programmes of support. These risks are managed ensuring that the net risk is brought to acceptable levels:

Delivery Risks:
- Insecurity and access. Though limited by the conflict, SFD’s access has improved over the last year. SFD assesses that 4% of the country is currently inaccessible (13 districts), and a further 14% (45 Districts) are either partially accessible or difficult to access. While SFD will continue to alert donors where this risk escalates impacting on delivery of the programme, access will continue to be a risk dictated by how the conflict evolves. The UK is engaging politically in advocating for a peaceful end to the conflict and improved humanitarian access.
- Banking sector issues. A number of risks are connected to the banking sector including: a) the availability of cash from banks (liquidity). This is particularly problematic for SFD’s employment-generating labour intensive works projects in which beneficiaries are paid in cash; b) the depreciation in the local currency the YER which could impact the purchasing power of icash transfers; c) the decreasing number of international banks willing to do business with Yemeni banks (de-risking), which could lead to challenges in donor funds arriving in Yemen. SFD are taking an active lead on managing risks associated with the liquidity crisis by meeting with bank officials to secure agreement that they prioritise SFD transactions. DFIDY tracks banking risks and is also involved in supporting the Central Bank of Yemen restore its ability to manage domestic liquidity.
- Volatility of fuel supplies and prices: SFD’s ability to deliver in a cost effective manner is impacted by the volatility of fuel supplies and rising prices. To mitigate this risk SFD is continuing to adapt to changing circumstances including stockpiling central reserves of fuel and moving towards solar energy.
Fiduciary Risk:
Misuse of Funds including instances of fraud and corruption. We judge SFD to have strong processes to guard against fraud and corruption (further details in the risk management section below) but it remains a major risk since there is a higher degree of risk involved on cash payments, beneficiary targeting and verification. Following recommendations from the 2016 Internal Audit, DFIDY engaged with SFD’s downstream partners to assess and recommend improvements to comply with fraud and corruption policies. SFD has also rolled out new fraud and corruption training for all staff and increasing HQ checks on projects. In addition, SFD hold donor funds in separate commercial bank accounts making it easier for donors to track. DFID’s independent monitoring programme will also help to verify the use of funds. SFD’s internal and external audits will be reviewed by DFID helping to ensure that any issues raised are managed appropriately.
Other Risks:
There are other risks around political interference and conflict sensitive programming, which also need to be managed (see management case for mitigation measures). We will conduct a due diligence assessment on SFD to ensure they are robust policies and practices in place to minimise the risk of sexual exploitation and harassment.

Balance of advantages and disadvantages: Option 2 would have the advantages of: (i) continuing to support one of the few Yemeni institutions that has a national geographical coverage and a sub-national presence; (ii) having a direct impact on individual, household and community resilience through its three components; (iii) making use of, and developing existing local community capacity; (iv) building on tried and tested delivery relationships and channels and avoiding set up costs and delays during a critical time for Yemen; and (v) having the potential to reach up to 3.2m poor and vulnerable people. The option has disadvantages, notably: (i) scale and reach to those most vulnerable; (ii) quality of cash for work activities and delays in payments; (iii) ability to reach women is constrained in cash for work.

Option 3: Co-finance support to SWF beneficiaries only

What is proposed? How would it work?: This programme would focus only on reaching the SWF beneficiaries and have two major elements: (i) Supporting the provision of emergency unconditional cash transfers; (ii) Programme management and monitoring. DFID funding (GBP) will be paid into a World Bank Trust Fund. The World Bank will then transfer funds in US dollars to UNICEF. UNICEF HQ will pay funds into a payment agent’s account in US dollars with the payment agency being required to deposit YER equivalent of US dollar in UNICEF’s YER account at the auction rate, before receiving US dollars in offshore account. The payment agency will make cash payments (5,000 YER for a family of 7 per month, or just over $10 USD) to all 8 million SWF beneficiaries (1.5 million households) at fixed and mobile sites as well as through mobile payments.

Managing the beneficiary database and case management will be supported by an international cash transfer (CT) firm, with technical expertise and international experience in CT delivery systems, as well as extensive experience in Yemen’s CT programme. The terms of reference for consultancy firms will be developed and agreed upon by UNICEF and the World Bank. The firm will provide technical support and day-to-day implementation support, including through a local service provider hired by the firm. A grievance redress mechanism (GRM) will also be supported by a firm, and an independent agency will be hired to perform CT performance audit (TPM). Additionally, field facilitation will be supported by a consultancy firm.

To the extent possible, the management of the delivery cycle will be automated to minimise the potential for errors and support accountability. Cash delivery is through a contractual arrangement with financial institutions with experience in delivering cash assistance and will demonstrate adequate geographical coverage to reach beneficiaries. To the extent possible, payment agents will be encouraged to use technology in cash delivery, including mobile banking. Social accountability and risks of leakage/fraud will be mitigated through a multi- layered implementation and monitoring process: secure electronic beneficiary list will be transferred to payment agency through secure data exchange protocols; implementing a GRM mechanism; and TPM which will include assessing beneficiary experience with regards to the benefits received as well as the delivery processes.

1. Expected results include:
  1. reach 1.5m households (8 million people, including 45% women beneficiaries and 11% disabled) across all 22 governorates

Evidence: Evidence for supporting this option is as follows:
	Global	Yemen
Cash Transfers	Strong: Cash transfers have a range of positive effects including improvements in education, health and nutrition, employment (including child labour) and empowerment of women and girls. Cash transfers contribute to reducing food insecurity with households receiving transfers typically spend more and consume more food. Cash transfer offer good value for money and have a significant impact on reducing the depth of poverty if the poor can access the programmes.	Limited: There remains a limited amount of Yemen-specific evidence on the impacts of Cash transfers. However the 2013 the Yemen National Social Protection Monitoring Survey (NSPMS) showed that at least 70% of SWF beneficiaries depended on cash transfers to purchase food and strengthen their livelihoods, cash assistance prevented vulnerable households from resorting to negative coping strategies, and social cash transfers helped beneficiaries to improve their access to basic social services, including health, nutrition, water and sanitation, and education.

More detailed information on evidence can be found at Annex 2.

Risks: The key risks are as follows and will be managed to ensure that the net risk is brought to acceptable levels:

Delivery Risks:
  1. Institutional capacity: UNICEF, as with other agencies, has limited prior experience in delivering CTs on a national scale in Yemen, despite UNICEF’s existing overall capacity and experience in implementing cash transfers. To mitigate this risk UNICEF has enlisted the services of qualified consulting firms to support management and monitoring of cash transfers including beneficiary administration and engage a wide network of social workers with previous experience with CT beneficiaries that exist in all districts.
  2. Lack of qualified service providers: Challenges UNICEF may face in identifying highly qualified service providers due to the security situation. To mitigate this risk, UNICEF will conduct market research and proactively invite potentially qualified firms to submit bids as well as provide robust training and capacity development to firms’ staff at the bid preparation stage
  3. Banking sector: Potential lack of capacity of the national system to exchange and absorb the US dollars required in the envisioned timeframe. This risk will be mitigated by UNICEF consulting the World Bank to determine most appropriate financial partners.
  4. Increased financial counter-party risks as a result of the funds being brought into the country. The ratings on political, governance, fiduciary, and technical risks remain unchanged (High), but new risks have been identified. Political risk of potential disruptions to payment delivery and supervision will be mitigated through robust security protocols based on local knowledge on security threats and involving political actors at the national, governorate, and local level in communication and payment facilitation; and
  5. Elite Capture: The governance risk of elite capture will be mitigated through the careful selection of politically neutral payment delivery agencies (increasing the opportunities for working across the political divide) and robust design of payment delivery procedures. This risk will further managed by: carefully negotiating security and non-interference at distribution sites with the key de facto political forces; avoiding distribution in areas where such guarantees cannot be achieved and making funds available for collection in the more secure areas; using TPM and audits to identify and investigate such instances; implementing robust recipient identification procedures; prohibiting collection of benefits by proxies; and promoting mobile banking for implementation where possible. Finally, project activities will be suspended in areas where political and governance risks cannot be effectively managed.
Fiduciary Risks:
  1. Fiduciary Risks: Risks related to the financial management structure, corruption, and fraud will be mitigated through engagement of an independent payment delivery agency with transparent and robust internal controls and oversight procedures. UNICEF will consult with the World Bank to determine the most appropriate financial partners (i.e. banks) and the banking risks. Technical design risk factors relate to the operational challenges that are likely to affect payment delivery; these will be managed through: (a) engagement of payment delivery agencies with extensive networks of local agents, robust internal controls and a proven track record of handling large volumes of payment transfers; and (b) providing operational guidance and capacity building to payment agencies.

Balance of advantages and disadvantages: Option 3 would have the following advantages: (i) it has the biggest coverage and will reach households that are both labour poor as well chronically poor and vulnerable (e.g. elderly, disabled, female- headed households, etc.); (ii) working with the World Bank and UN institutions in Yemen offers scope for wider systems reform (e.g. recertification of beneficiary lists; potential to influence an increase in CT levels in SWF), as well as enhanced coordination between humanitarian and development partners; (iii) It would be straight forward to administer. Option 3 does have disadvantages, notably: (i) It would end DFIDs longstanding relationship with SFD, a key Yemeni development institution; and (ii) It presents new risks to DFID by working to support the SWF beneficiary list where there are concerns on targeting; (iii) It raises questions from a sustainability point of view given that the support is short term and complementary to larger IDA resources; (iv) The purchasing power of this payment has declined over time due to inflation and depreciation of the YER. The current estimation of a minimum food basket is YER 29,500[25] per household of 7 members per month, and meets 80% of the monthly household food needs.). This is equivalent to $70 (at a rate of YER 421 to the $). Given the average level of support to a HH is YER 5,000, this is now covering only 17% of a minimum food basket. While the optimal policy response is for transfers to be revised to a level which can help the poorest households achieve the minimum food basket costs, this needs to be balanced with factors of targeting, affordability/sustainability and conflict sensitivity (the World Bank claims that revising the payment amount could lead to additional grievances and expectations from recipient). This will be an ongoing technical debate which can be shaped by UK input.
[25] This is based on the revised estimations from the Food Security and Agriculture Cluster in January 2018.

Option 4: Support both SFD and SWF beneficiaries.

What is proposed? How would it work?: This programme would combine a focus on SFD and SWF: (i) Maintaining and expanding safety net provision (e.g. cash for works (maximum amount of YER 150,000 per household for unskilled labour, and maximum for households providing skilled labour is 500,000 YER) , monthly stipendsto young people (18-35 years) to provide nutrition services and employment in social service provision and emergency cash transfers worth 5,000 (YER) each month via SWF in response to the humanitarian crises); (ii) Restoring essential basic services and assets through community and local development reconstructing and rehabilitating facilities and training personnel; and (iii) Improving livelihoods e.g. through microfinance grants and loans, small and micro-enterprise development and support to the policy environment. The following results are expected:

Table of results under option 4:
Outcome	SFD (@$612m)	SWF	Total
# people benefitting from support under YeSP (% female)			11.2m (44%)
SFD # of direct beneficiaries of wage employment (# of wage beneficiaries of Safety Net &Community and Local Development programs)	3.2m (44%)
SWF: # of direct beneficiaries of emergency cash transfers		8m (45%)
# people with access to key services (% female)	1.9 m (51%)		1.9 m (51%)
# of working days created (from all interventions)	21m		21m
(i) # women (% disabled children) and (ii) children benefitting from nutrition interventions	(i) 80,000 (10%) / (ii) 16,000		(i) 80,000 (10%) / (ii) 16,000

Evidence: Evidence for supporting this option above, with more detail presented in Annex 2.

Risks: In addition to the risks noted in options 2 and 3 above, the main risks which are rated as either m include: political and governance, macroeconomic, sector strategies and policies, technical design of the project, institutional capacity for implementation and sustainability, fiduciary, environment and social, and stakeholder risks. The overall risk rating is major given the context. The open and transparent process taken to appoint a new Managing Director in 2013 proved critical for donor confidence, securing trust both in SFD’s commitment to good financial management and political neutrality. DFID has mitigated risk through Independent Monitoring, Anti-Corruption Counter-Fraud policy and a due diligence assessment, which in 2017 included a review of SFD’s downstream partners.

Balance of advantages and disadvantages: Option 4 would combine the advantages noted above for options 2 and 3, and have some additional advantages: (i) it helps to build both SFD and SWF as Yemeni institutions for the provision of social protection in Yemen; (ii) it has the biggest coverage and will reach households that are both labour poor as well chronically poor and vulnerable (e.g. elderly, disabled, female-headed households, etc.); (iii) working with the World Bank and UN institutions in Yemen offers scope for wider systems reform (e.g. recertification of beneficiary lists; potential to influence an increase in CT levels in SWF), as well as enhanced coordination between humanitarian and development partners; (iv) It would be relatively straight forward to administer. Option 4 has disadvantages noted in options 2 and 3 above.

B: Appraisal of Feasible Options against Critical Success Criteria

The three feasible options have been appraised against critical success criteria (CSC), identified as critical to achieving the programme outcome. CSC and their ratings are shown in Table 2.

Table 2: Critical Success Criteria (CSC) and weights

Critical Success Criteria	Description	Rating	Weight
Supporting institutions and systems	Maintaining and improving institutions and systems for social service delivery	Very important	4
Coverage and reach	Extent to which programme interventions are national in scope and reach the highest number of poor and vulnerable (chronic and acute)	Very Important	5
Opportunity for system change > sustainability	Extent to which the programme interventions offer opportunities for wider systems reforms with activities adopted after the end of the programme	Important	4
Complementarity	Complementarity with other development partners (including multi-laterals); links to other DFID Yemen programming (e.g. humanitarian) and opportunity to asupport other programme results e,g, food security	Important	4
Manageability	Feasibility of the option, and extent to which the option is likely to be able to be delivered in practice to achieve VfM and expected results	Important	4

Each of the three options, and the comparator, was considered against the CSC and rated ‘High’, ‘Medium’ and ‘Low’ (and intermediate classifications e.g. ‘Low–Medium’) against each criterion. The results are presented in Table 3.

- Option 1 (‘Do nothing’ option) is not assessed against CSCs.
- Option 2 (Tackle chronic poverty, vulnerability and build resilience through SFD only) scores highest against the manageability criterion, is assessed as medium on all other criteria.
- Option 3 (Tackle acute poverty, vulnerability and build resilience and support SWF beneficiaries only) scores highest against the manageability criterion, is assessed as medium on all others.
- Option 4 (Tackle chronic and acute poverty, vulnerability and build resilience through working with both SFD and SWF beneficiaries) scores highest against the coverage and reach, opportunity for system change and more sustainability and complementarity criterion, and is assessed as medium on the supporting key institutions and manageability criteria.

Table 3:	Rating of feasible options against Critical Success Criteria

Critical Success Criteria	Option 2: SFD	Option 3: SWF	Option 4: Both
Supporting key institutions	Medium	Low	Medium – High
Coverage and reach	Medium	Medium	Medium
Opportunity for system change > sustainability	Medium	Medium-Low	Medium – High
Complementarity	Medium	Medium	Medium – High
Manageability	Medium-High	High	Medium

CSC ratings have been scored as follows:
- Low is given a score of '2' or ‘3’.
- Low–Medium is given a weight of 4.
- Medium' is assessed as a score of '5' or '6'.
- Medium–High rates a score of '7'.
- High scores '8' or '9'.

Scores against each CSC were then multiplied by the 'weight' of each criterion, as shown in Table 4.

Table 4: Options analysis

Critical Success Criteria	Weight	Option 2	Option 3	Option 4
1. Supporting key institutions	5	5	2	7
Weighted score		25	10	35
2. Coverage and reach	5	5	5	7
Weighted score		25	25	35
3. Opportunity for system change > sustainability	4	5	4	7
Weighted score		20	16	28
4. Complementarity	4	5	5	5
Weighted score		20	20	20
5. Manageability	3	7	8	5
Weighted score		21	24	15
TOTAL SCORE		111	95	133

Table 4 shows that Option 4 emerges as the highest ranked option with a score of 133, followed by Option 2 with a score of 111, and Option 3 with 95.

Summarising appraisal against feasible critical success criteria (CSC) - The narrative discussion in the appraisal and the results of the CSC analysis, suggest a trade-off between all options. The ranking is robust to variations in weighting. Option 4 scores highest as it is likely to generate the highest coverage and reach, and most opportunity for system change and more sustainability in terms of how it supports key institutions in the short term, delivers complementarity and its potential for longer term systems change and sustainability. Manageability is a risk with Option 4 and there are also risks related to delivering on the potential opportunity for systems change. Based on the discussion of the options and the CSC analysis, Option 4 is preferred.

C: Theory of Change of the preferred option
Building on the conclusions drawn and the subsequent additional analysis, the proposed approach is to support Option 4 as the preferred option with the following Theory of Change (see Figure 3).

D: Expected outcomes, outputs and results
Expected outputs and results expected under YeSP are detailed in Table 5[26].
[26] All data will be disaggregated where possible: # or %: female; IDPs/ returnees; Youth; children; disabled/ special needs; elderly.

Table 5: Expected outcomes, outputs and results under YeSP
Key results leveraged under YESP		SFD (@$612m)	SWF	Total	DFID share[27]
Outcome
# people benefitting from support under YeSP (% female)				11.2m (44%)	1.77m (44%)
SFD # of direct beneficiaries of wage employment (# of wage beneficiaries of Safety Net &Community and Local Development programs)		3.2m (44%)
SWF: # of direct beneficiaries of emergency cash transfers			8m (45%)
# people with access to key services (% female)		1.9 m (51%)		1.9 m (51%)	342,000 (51%)
# of working days created (from all interventions)		21m		21m	3.8m
(i) # women (% disabled children) and (ii) children benefitting from nutrition interventions		(i) 80,000 (10%) / (ii) 16,000		(i) 80,000 (10%) / (ii) 16,000	(i) 14,400 (10%) / (ii) 2,880
Output 1: Maintain and expand safety nets
1.1	SFD: # people with direct cash based safety net support (30% female; 20% Internally Displaced Persons (IDP); and 35% Youth), including: / # direct beneficiaries of cash for work / # direct beneficiaries of cash for services / # direct beneficiaries of conditional cash for pregnant women and mothers undertaking nutrition screening	1.3m (44%) / i. 0.6m (36%) / ii. 7,000 / iii. 80,000		1.3m (44%)	0.234m (44%)
1.2	SFD: # Indirect beneficiaries from cash for work / i. # Households (HH) / ii. # people in the HH	i. 255,000 / ii.1.7m		i. 255,000 / ii.1.7m	45,900 / 306,000
1.3	SWF: # of people benefitting from unconditional cash transfers (% female)		8m (45%)	8m (45%)	0.225m (45%)
Output 2: Restore and improve access to basic services
2.1	Local development: # Village councils formed/ activated	2,400		2,400	432
2.2	Water & sanitation: / i. # people provided with access to water / ii. # people provided with access to sanitation / iii. # people benefiting from cholera preventive measures support	i. 124,000 / ii. 83,728 / iii. 800,000		i. 124,000 / ii. 83,728 / iii. 800,000	i. 22,320 / ii. 15,071 / iii. 144,000
2.3	Education: / i. # of students having access to education (% female) / ii. # classrooms rehabilitated* / iii. # special needs pupils supported to access education (% female)	i. 272,800 (42%) / ii. 3,440 / iii. TBC		i. 272,800 (42%) / ii. 3,440 / iii. TBC	i. 49,104 / ii. 619 / iii. TBC
2.4	Health & nutrition: / i. # health facilities constructed/ renovated and equipped* / ii. # people benefited from basic mental health care/psychosocial support (% female) / iii. # mothers and children U5 transferred to treatment centres	i. 64 / ii. 33,600 (70%) / iii. 32,000		i. 64 / ii. 33,600 (70%) / iii. 32,000	i. 11 / ii. 6,048 / iii. 5,760
2.5	Roads: km of roads improved	1,687km		1,687km	304km
Output 3: Enhance livelihood opportunities
3.1	# Number of active microfinance clients/ borrowers (% women)	100,000 (50%)		100,000	18,000 (50%)
3.2	# of income generating activities created/ sustained	3,500		3,500	630
3.3	# of businesses supported	10,000		10,000	1,800
3.4	# of job opportunities created/sustained from microfinance services	17,600		17,600	3,168
Output 4: Institutional strengthening
4.1	% of SFD beneficiaries satisfied with project participatory approach	70%		70%	70%
4.2	% of SWF beneficiaries who are receiving the full transfer amount		100%	100%	100%
4.3	% of registered grievances that are addressed within the timeframe specified in the project implementation manual	80%		80%	80%
[27] These indicative results are based on budget estimates from SFD of $612m in support for Phase V supported at 18% and SWF beneficiary reach of 1.5m HHs (8m people) supported at 15% in Q3 by DFID.

*subject to satisfactory review of construction projects

E: Economic Appraisal
We appraise the economic arguments of the preferred option (4) compared to the no intervention option (1), following the critical success criteria analysis – the optimal choice compromises both elements of options (2) and (3). If we apply a cost/benefit framework then Option 1 could be defined as the counterfactual scenario where resources are used instead for Yemen’s humanitarian programme.

A cost/benefit analysis in Net Present Value terms (NPV), and by extension a sensitivity analysis is not employed in this appraisal. This is principally because we are only confident in being able to accurately estimate DFID’s direct financial costs. We do not attempt to quantify benefits – given the highly uncertain operating context and scarcity of recent data available in Yemen, it is likely that assumptions will result in a misleading empirical estimation of the flow of associated benefits.

The scarcity of data also means that Value for Money (VfM) arguments of the associated interventions are limited for now. It is a priority for DFID Yemen to work on building up the data and strengthen the methodologies for assessing the VfM of social protection programmes, including cash transfer programmes in emergencies which currently focus on effectiveness and speed of response. There are a number of efficiency considerations that need to be further developed during implementation. While the VFM indicators still need to be finalised for both the SFD and SWF components, an approach is set out in the proceeding VFM section on how improvements can be made during implementation.

The lack of recent impact-level evidence does not change our confidence that SFD is able to adapt and deliver at a national scale. Since 2011 it has been able to continue its operations with implementation of 82 per cent of its projects in 300 districts out of the country's 333. Our confidence in SFD is also backed up by its performance under SFD IV which DFID supported. Its PCR score was an ‘A’ meaning that it achieved outputs in line with expectations.

OPTION RESOURCE COSTS

The total cost of DFID planned support to the YeSP is £70m over 5 years with a programme break review at 3 years: £34.5 million will support SFD equally over the first three financial years (with the possibility of extending the programme a further £23 million for a further 2 years); with up to £12.5 million to be contributed to the Bank’s YECRP in 2018.

A number of wider costs linked to the interventions are not captured, separate to DFID’s direct contribution:
- The most significant set of ongoing costs are those of the SWF unconditional emergency cash transfers over the project period under the World Bank’s YECRP which the UK will co-finance. At a minimum the Bank estimates c$250million/annum is needed to cover 1.5 million households, keeping the current value of the transfers fixed (at 5,000 Yemeni Riyals for a family of 7 per month, or just over $10 USD). We have been reassured the Bank will continue to prioritise financing the programme from its own resources (Yemen’s IDA allocation) or externally (e.g. a donor-financed trust fund to support reconstruction and recovery) for the next two years. It is not expected the GoY will be in a position to part–finance these expected costs during this time or in the medium-term.
- The total cost of the SFD programme ($612.5 million). SFD management has proposed three funding scenarios (see table 6) which activities will be funded from the final budget that they receive. DFID has framed this business case around the SFD’s second scenario – we expect that other donor contributions will be sufficient to meet the costs of this central scenario.
- Costs of advisory and programme management support from DFID Yemen. It is assumed that the Social Development Adviser and a programme manager from the existing socio-economic development team will undertake the management of this programme.
- Associated costing variations due to the changing macroeconomic situation, such as the exchange rate and inflation: These include changes to the amount of transfer needed to maintain purchasing power and input costs (labour or materials). As DFID’s contributions are expressed in sterling, this does not affect how much it costs but it does affect how far it goes. Most penitently this affects the relative value of cash transfers from SFD’s LIPW component and the SWF. Good practice would favour a change of the value of transfer to maximise the poverty reducing effects of the target household.

Table 6: SFD Progamme Delivery
Scenario	Budget	No. of beneficiaries (of services created and direct beneficiaries of cash transfers)	% of which are female	No. of businesses supported through Small and Micro Enterprises Development
1	$750 million	4,020,244	44%	10,000
2	$612.1 million	3,218,895	44%	10,000
3	$510.6 million	2,617,884	44%	10,000

OPTION (4) BENEFITS

Expected benefits derived from the SFD
In appraising the economic case and supporting evidence of SFD activities, we examine the key benefit from labour intensive works. A reasonable amount of existing literature exists on this in Yemen and to an extent in other developing countries. These give a sense of the combination of the immediate and longer-term impacts of SFD; as it accounts for the significant proportion of SFD’s costs.

There are wider benefits of SFD’s interventions including in particular the provision of education but we do not quantify these. DFID had previously estimated the return to be 7% in 2011 but it would be misleading to quantify its benefits now due to the operating context. However, the case for continued investment in SFD as a Yemeni institution delivering basic services including in education and health across the country is now stronger. In the absence of national delivery by authorities, and outside of the private sector and multilateral assistance (mostly in the form of stipends to teachers), SFD is the only Yemeni institution which can deliver basic education across Yemen. In health, only about 50% clinics are fully functional. While the economic value cannot be quantified, preserving SFD as an institution is essential to support any transition from conflict towards recovery.

(A) Labour Intensive Public Works (LIPW) - expanding/maintaining social safety net provision and building public asset bases
SFD expects to create 21 million working days through labour intensive public works (LIPW). This type of employment will not lead to transformative economic growth in Yemen. However, the primary purpose of employment created under SFD is to transfer income support during a period of continued economic collapse. The transmission of economic benefits from LIPW is reasonably well understood in terms of income generation for targeted individuals from the exchange of labour.

As an instrument for income provision, global evidence on LIPW programmes appears particularly good at reaching the poorest in remote rural areas. Impact evaluations demonstrated that it increased household income, resulting in enhanced food security and reductions in household debts. They also found an increase in transport related assets (mini- busses) accumulated in targeted communities as compared to in the control group of communities.

Evidence of SFD's capacity at targeting poor and deprived communities and at meeting their priority needs is good. A recent evaluation showed that in treated communities, 74 per cent of households had at least one member participating in LIPW. Benefits were, however, quite unequally distributed across participants due to the fact that the crisis attracted participation of households that would have normally self-selected out of enlisting for workfare. Wages were set on a piece-rate basis, creating greater rewards for workers involved in more skill-intensive tasks. In spite of this, benefits were progressively distributed, with more aggregate benefits going to the poor.

An effective workfare programme design also comprises the following considerations:
1. The transfer impact, i.e. direct transfer benefits (cash or in-kind) to participating households. Possible wider impacts on the local labour market overall wage levels, will be felt both by participating households and non-participating households whose incomes are below the post-programme general area wage. This positive impact may be offset by negative impacts on labour demand due to higher wages in the programme area. In the context of Yemen, the substitutability between that of an outside wage is likely to be extremely limited due to the economic collapse and SFD targeting the rural poor where labour markets are weaker. The estimated range of direct transfer benefits in 2011 to participating households, assuming a 60 percent wage share in spending and 50-60 percent net income gain, was 30-40 percent of total spending per annum. This is likely to be higher now given that wages are estimated to be lower.
2. Indirect impacts from the economic benefits of assets created under the LIPW. These would typically also be spread among a wider population than participants. SFD Phase V will be placing a special emphasis on the creation of productive assets: hence these impacts may be particularly large. The aggregate economic impacts of assets created from such workfare efforts are generally held to be positive. Global analysis confirms this and rates of return on projects have been estimated at 22 percent. Total benefits will be moderated by the programme’s need to replace damaged asset stock
3. The consumption smoothing or insurance function that LIPW may perform by acting as an effective wage floor. Whether or not households participate in the programme, such insurance benefits may promote less risk-averse behaviour by households in production and portfolio choices, as downside income variability is contained. The ability of the LIPW to provide such a ‘guarantee’ for employment remains unclear; hence the value of the insurance benefits is not very predictable.

In humanitarian situations like Yemen, an emphasis is placed on LIPW recipients avoiding undertaking negative strategies. A regular income might prevent negative coping strategies such as taking children out of school, selling productive assets such as livestock etc. which have a huge economic cost. The duration of employment is another important factor, as many Public Works Programmes (PWPs) provide only short periods of ad hoc employment rather than a regular predictable source of additional income as with direct social transfers (see Devereux et al, 2007). SFD’s approach demonstrates careful consideration for this - programme participants are guaranteed employment of between 9 -12 months receiving $1,200 during this period.

The balance in relative importance of the above impacts is an empirical question, which cannot be answered with a degree of confidence in the current context of Yemen. However, it is clear both in theory and from available evidence internationally that analyses which focus only on the direct transfer benefits of programmes to both poor and non-poor households are likely to be significant in and also underestimate aggregate economic impacts of programmes.

Expected benefits derived from SWF

(B) Cash transfers for 1.5 million vulnerable households
In general terms, the economic case in using cash transfers is similar to that for the LIPW. Global evidence on the use of cash transfers for social protection and in emergency situations is strong. A comprehensive (systematic) study of cash transfer programmes across the world conducted by the ODI shows that strong evidence exists linking cash transfers and reductions in monetary poverty. The evidence consistently showed an increase in total expenditure and food expenditure and a reduction in poverty measures. However, this did not translate into reduced poverty rates in all cases. This was possibly because transfer levels were not high enough and / or the transfer was not received for a long enough period of time.

The two critical departures of unconditional cash transfer approaches when compared with LIPW are: (1) public assets are not created and (2) without participants’ needing to provide labour there is potential for work disincentives depending on the level of transfer (relative to the local wage levels). On the latter, the same ODI systematic review also investigated this and the evidence did not support these concerns.

Specific evidence on the economic impact SWF is more limited than what is available for SFD. A pre-war UNICEF survey (2012–2013) estimated that at least 70 percent of SWF beneficiaries depended on cash transfers to purchase food and strengthen their livelihoods; cash assistance prevented vulnerable households from resorting to negative coping strategies; and social cash transfers helped beneficiaries to improve their access to basic social services, including health, nutrition, and education. With poverty in Yemen likely to be higher now, we expect that the use of cash transfers by households for immediate consumption of food and livelihoods is likely to be higher than the earlier UNICEF study.

In appraising the project, the Bank has quantified support (through the YECRP) which is expected to yield a substantial return overall, given the additional life-saving need. A rate of return of the invested resources is linked to assisting poor families, including mothers and children to cope with famine, and temporarily afford a minimum food intake. It is presumed to be life saving for about 30 percent of the target group. It therefore yields a calculated return of about 70 percent, particularly due to the avoidance of famine for mothers and children.

The Bank has taken steps to improve the SWF’s operations since resuming support last year. These refinements further strengthen SWF’s economic case:
- Improving targeting, by working together with SWF and UNICEF to revise the beneficiary list through the use of data and local stakeholder consultations. There is likely to be a significant saving in the programme if the targeting mechanism is improved to minimise the inclusion/exclusion error. This is also a strong VFM argument for supporting the programme.
- Conflict sensitivity by establishing a grievance redress mechanism (GRM) to minimise distress and potential conflict of non-beneficiaries.
- Switching the main modality of disbursing cash through microfinance institutions for better predictability and lower transfer costs. The efficiency gains of delivering cash assistance in SWF through this model should also be seen in light of other social protection and food security modalities available in Yemen. The expected 7 cent cost to deliver a dollar of cash makes it one of the most efficient ways of addressing food insecurity.

While the Bank have taken steps to improve SWF, there are still a number of areas that remain unaddressed. A 2016 ODI study[28] usefully identifies these (these are summarised before the Bank’s recent involvement, based on interviews conducted of recipients of SWF beneficiaries and existing evidence available. The most critical issue is that the small value of the SWF transfer (now up to 5,000 YER) limits its impact in terms of consumption smoothing as a family with six people receives an amount equivalent of $30 per quarter – this is inadequate to feed the family or meet other basic needs based on the minimum food basket costing six-times as much as the transfer value. This cannot be addressed fully now as SWF and the Bank has chosen to preserve outreach to 1.5 million households and to ensure the long-term financial sustainability of the approach and conflict sensitivity (so that recipients do not receive varying amounts at different times).
[28] https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/8312.pdf

(C) Levering additional financing through World Bank internal resources
We are confident that our support will lever further World Bank financing for SWF. Our co-financing contributes to an existing Bank project disbursing cash transfers to 1.5 million households. Our support can lever up to $200m additional World Bank funding for their Yemen Emergency Crisis Response Project Phase 3 when it goes to the Board later in 2018. This is enough for three further quarterly disbursements. It also strengthens the case for the Bank seeking additional financing from the World Bank’s Crisis Response Window by demonstrating burden share of the project with UK (and we expect US) contributions.

Additional arguments to keep the SWF disbursements going during this time are of a humanitarian (life-saving) nature. The Bank estimates the economic returns can be higher for the investment by up to a factor of four, if full funding of the cash transfer programme extends to beyond a year.

F: Value for Money

Methodology for assessing Value for Money (VfM)
DFID uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that UK aid maximises its impact. The assessments (below) show that the proposed option demonstrates VfM. The programme’s complexity requires ongoing monitoring and analysis of how change is being achieved.

Key cost drivers
As previously discussed access restrictions cost drivers such as exchange rate depreciation, private sector contraction, increased prices of fuel and higher costs of construction materials remains a key project risk. The interruption of funding in 2013/14 - 2017 led SFD to enact cost-saving measures, including reducing staff numbers (and salaries), more local hires and remote monitoring. SFD is a systemically important client in local banks helping to minimise the impact of the crisis on operations.

We can expect some ability to manage costing variations. This includes internal measures such as the operating expenses for monitoring and evaluation not exceeding 10%, assuming the central funding scenario ($612.5million over 5 years) can be secured. The headline figure includes salaries and wages; maintenance; utilities; rents; travel; stationery; consultancy services; public relations; and miscellaneous items such as fuel, petrol and oil, facility security, SFD share of staff health insurance, legal consultancy and cleaning costs. DFID will continue to monitor this through financial reporting to ensure cost drivers are effectively being used.

Costs for YECRP will be driven by similar external factors affecting our funding to SFD with one exception – SWF cash transfers are fixed in local currency so donor contributions are subject to exchange rate risk. This currently favours donors due to the severe balance of payments issues facing Yemen’s economy. However, increases to basic food items will dilute the value of the support provided. The cost of contracting may be higher due to the limited competition from local markets.

Economy
SFD’s operating costs were originally set at 6.4% of total costs which compared favourably to the UN pooled fund mechanism (at 8%). While operating costs averaged 4.5% during the previous phase of support, independent audits showed they crept up in 2015 and 2016 (9.9% and 12.7% respectively). This is significantly higher than pre-conflict (3.2% in 2014). One key reason was that operating costs became proportionally higher because of a reduced overall budget. SFD has informed us that the expected figure for operational costs against total costs will be around 7% if the programme can be fully delivered.

YCERP – The management cost associated for this project will not exceed 13% as agreed with the Bank and is much lower than if the agreement was made directly with UNICEF. DFID will provide a one-off £7 million payment to this project which will ensure continuity. An additional £5.5 million could be made available if a financing gap exists at the level of the overall YECRP project.

Efficiency
SFD - DFID’s contribution is one of a number of donor contributions (other to be clarified in due course which will help to determine activities covered by the final budget). This approach enables donors to provide assistance at scale which covers the whole country. This only works if donors continue to support SFD at levels similar to the past and in line with SFD projections. This is more likely if SFD is realistic in its ambitions ensuring it has sufficient capacity to deliver against its programme of work and budget. DFID will continue to mitigate this risk through encouraging other donor support and SFD to put in place a donor engagement strategy.

The PCR concludes that SFD remains an efficient means to crowd in other forms of non-donor financing. SFD’s microfinance component levered private sector investments totalling $4 million from the business community in the previous period.

YCERP – providing cash transfers is a more efficient form of support than other comparable alternatives. In the case of Yemen, a comparable non-cash approach is delivering food vouchers to households through the World Food Programme (WFP) – this costs twice as much to deliver the same financial value of assistance. Working more closely with the World Bank may give an opportunity crowd-in wider donor support start to rebuild and reform the social protection sector in Yemen. Funding the emergency cash transfers through the Bank will enable a higher level of scrutiny from within the Bank to our contribution and should be less of an administration burden on DFID.

Table 7a: efficiency of unconditional cash transfers through World Bank (source: Bank and UNICEF)
Intervention	Total cost for delivering $1 of assistance	Notes
Cash transfers – SWF through WB (option 4)	$1.07	Excludes Bank/UNICEF management fee of 13%
Cash transfers – SWF through UNICEF	$1.07	Excludes UNICEF management fee of 18%
WFP In-kind voucher-based assistance	$2.24	Total cost of WFP’s HRP 2017 response in-kind voucher components

Effectiveness
Going forward, effectiveness will be measured for both the SFD and YCERP contribution by assessing progress against targets and how meeting these targets have had an impact in Yemen e.g. on households in receipt of cash for work completed and benefits to the community of the assets created. In the case of SFD, we will ensure realistic targets based on budget availability are set. This will help to avoid over-stating what SFD intends to achieve which will bring into question its effectiveness overall as an organisation.

As mentioned in earlier sections a proportion (10%) of YESP’s total costs are for project management and monitoring purposes. This provides DFIDY with risk management measures (especially fiduciary) and also for the two national institutions with resources to improve operational efficiency. It will be a crucial area to assess as part of DFIDY‘s project cycle management processes.

Equity
SFD is a neutral, non-partisan and autonomous institution that works to benefit all Yemenis. It has no political affiliation and has consolidated its reputation as a development agency working to benefit all vulnerable individuals and communities irrespective of their political, territorial or sectarian affiliations. Beneficiary needs are the guiding factors for SFD responses. SFD interventions will also target youth and women since women and girls in conflict affected areas are the most vulnerable group.

YCERP - The most vulnerable Yemenis (e.g. elderly, disabled, female- headed households, etc.) will be reached through our support to the emergency cash transfers project. These people are unable to take up work opportunities and do not currently benefit from the cash for work program as originally envisaged by the project.

G: Value for Money Summary Statement for the preferred option

The deteriorating political, economic and security context in Yemen has had a significant impact on the nature of VFM considerations. Over the life of the project we expect that SFD operations will continue to experience rising input costs. However we judge that it is VfM to act now, as YESP will help to build resilience in the face of the humanitarian crisis..

Going forward we will continue to monitor VFM through the 4E’s framework as part of the project cycle management processes. Drawing from DFID’s guidance, VfM should be measured at all points in the results chain from input level up to outcome and impact. The logframe will be finalised during the finalisation of the SFD business plan and also when a decision is reached on the co-co-financing arrangements for the SWF support. To shape our future VFM monitoring work, the table below sets out some example indicators that if tracked and compared with international benchmarks

Table 7b: Proposed indicative Indicators of VfM
VfM measures	Indicator
Economy	Per capita spend per beneficiary in SFD and SWF / Service delivery agent salary in SFD / Cost per service delivery agent trained in SFD
Efficiency	Method of delivering safety nets, basic services at local level and livelihoods opportunities / Method of collecting data and feedback loops e.g. use of ICT / Targeting accuracy
Effectiveness	Improvements in capacity of services to deliver quality outcomes
Equity	Number of vulnerable and women accessing quality safety nets, services and livelihood opportunities / Improved support for inclusive safety nets, basic services and livelihoods, particularly for those with disabilities / Difference in access to services between the richest and poorest quintiles

Commercial Case
Yemen Emergency Crisis Response Project (YECRP)
DFID will contribute to the Yemen Emergency Crisis Response Project (YECRP) trust fund to enable quarterly emergency cash payments to SWF beneficiaries delivered through UNICEF. Our support will be made through a one off payment, contributing to one of the quarterly payment round.

The UK will contribute to the emergency cash payments. The World Bank is seeking funding from its Crisis Response window to meet the funding requirements for future quarterly payments to beneficiaries. The Bank will have a strengthened case to access these funds if it can demonstrate co-financing from other donors – the US is already providing funding and the World Bank is continuing to seek support from other donors.

A trust fund administration agreement with the World Bank will be put in place. This trust fund will be a hybrid between bank executed and recipient executed. Management and supervision costs applied by the World Bank will not exceed 13%. The management cost may be subject to small change when the Banks Trust Fund Department finalise the administration agreement with DFID. Any changes will be agreed with DFID to ensure they are justified and kept to a minimum. The management cost will cover Bank preparation and supervision of the project (which is $80,000), standard Bank central cost recovery (5%) and indirect costs (7%) which UNICEF, the implementing partner will charge.

Social Fund for Development
The UK will support the Social Fund for Development (SFD) with un-earmarked funding with the exception of funding SFD’s cultural heritage work and rehabilitation/reconstruction of schools and health facilities. Our funding will be used by SFD as deemed most appropriate to progress activities across their portfolio and will fund activities across most sectors that SFD operates with notable exclusions as agreed between both parties, for example Cultural Heritage.

A Memorandum of Understanding will be drawn up between the Social Fund for Development and DFID which will clearly set out what is expected from SFD in terms of reporting.

Assurances on partner organisation’s capability and capacity to deliver

Ability to Deliver
Emergency Cash Transfers: The World Bank has an established relationship with DFID and we judge them to have sufficient resources and good systems in place to manage donor funding. We will however, need a fuller assessment to confirm that this is the case. The WB will be responsible for administration whilst implementation of the cash transfers will be delivered by UNICEF. UNICEF has partnered with DFID Yemen for many years and has demonstrated the ability to deliver successfully in a very difficult context. UNICEF has experience in implementing a US-funded grant to support the readiness of cash transfer systems, for which the World Bank is also providing technical support. UNICEF has experience working with national cash transfer programmes since 2011. In addition, UNICEF has been delivering cash transfer projects using SWF delivery systems and has recently successfully delivered two rounds of cash transfers through YECRP. The World Bank assessed that this experience along with UNICEF’s capacity, field presence and social protection mandate, make UNICEF the most suitable partner for the World Bank to implement this component of the YECRP.

Third party monitoring (TPM) of the YECRP contribution will be conducted by an independent consultancy firm contracted by UNICEF. The WB assessment of UNICEF deems them to have acceptable procurement procedures. DFID’s own due diligence assessment and central assurance assessment of UNICEF agrees with that of the Bank. The key objectives of the TPM will be to ensure ongoing monitoring of the payment distribution processes, post-transfer monitoring and investigation of specific cases as recommended by UNICEF. TPM will include assessing beneficiary experience with regards to the benefits received as well as the delivery processes.

SFD is the largest single component of Yemen’s social safety net which provides a network of expertise. SFD is one of the few remaining Yemeni institutions investing in Yemen’s development. With over twenty years of experience it has become a primary partner in Yemen for international donors, including the World Bank and the Germans. SFD has worked to gain and maintain the confidence of all its stakeholders by protecting its reputation of political neutrality, which has helped to ensure wide reach across the country including to areas where international partners such as the UN have difficulty accessing.

DFID conducted an internal due diligence assessment of SFD in 2016. That alongside our ongoing partnership with SFD since 2011 gives us assurances over their ability to deliver. The assessment identified a number of key findings which DFID have continued to monitor. These include:

  1. Many donors suspended or reduced funds to SFD at the onset of the conflict in 2015 which posed a great threat to SFD’s ability to function effectively. Although some funds remain suspended, funding levels are seeing an upward trend as SFD moves into its next phase;
  2. The Board of Directors have not met since 2014, due to the conflict. However, SFD's operations including signing funding agreements, approving projects, managing funds have not been affected since they are normally (legally) the responsibility of the HQ represented by the Managing Director as per SFD's establishment law and manual. Donors have also played a greater role in terms of oversight in approving SFD's key documents such as the SFD's strategic plans and annual financial statements (the most recent external audit were approved in 2016) Under phase V, enhancing this interim governance should be strengthened. For an example the project-based governance arrangements set in the Yemen Emergency Crisis Response project YECRP where UNDP, SFD and PWP are represented. We, with DFID internal audit, and other donors are exploring this with SFD.
  3. The banking system in Yemen. We have encouraged SFD to monitor the situation in order to mitigate any developing risks. In addition, SFD have implemented mitigating measures such as introducing mobile banking as a mechanism for paying beneficiaries, or where required, using alternative channels such as money exchangers. SFD have also aligned the exchange rate with active international agencies in Yemen.

A DFID internal audit in December 2016 identified a number of areas to strengthen, including on fraud, financial management, due diligence, risk management and monitoring. DFID has worked with SFD to seek assurances that improvements have been and continue to be made in these areas. All external audits of SFD were unqualified and any issues followed up with SFD.

As we look to undertake a new due diligence assessment for the next phase of the project we will recommend this is undertaken in conjunction with other donors where feasible to reduce SFD’s burden.

DFID’s Independent Monitoring Programme has undertaken two studies of SFD. The latest study found that SFD has had positive benefits for beneficiaries in the short term by providing an important social safety net in the form of cash payments for work. The reviewers verified that payments to beneficiaries had been spent on the purchase of essential items. In the longer term the assets created through the programme were generally perceived as being of good quality and important for the community as a whole as they will provide continuing benefits into the future. In addition, the reviewers also found technical, recording and process issues with the programme specifically on data accuracy, and implementation of quality and targeting standards and protocols which varied greatly across governorates, suggesting that some compliance issues exist at branch office level.

DFID shared these reports and has encouraged other donors to also share their own TPM findings.

Recommendations have been shared with SFD and we expect that SFD continues to address them. SFD has remained responsive to the changing needs in the country by adapting its approach to contribute to relief, recovery and humanitarian efforts.

SFD has well established advanced information management, procurement and finance systems. Improvements are being made to the management information system (MIS) which will allow donors access to view information. This MIS helps to provide accountability to all stakeholders including donors; beneficiaries etc. as well as enable learning and development. The system will help SFD to improve its performance as well as provide donors and stakeholders with sufficient data and information on the status of financial contributions and the implementation progress of projects and benefits generated.

Procurement Capability
A 2008 study conducted by the Ministry of Education with support from KfW Development Bank, described SFD as the most efficient agency in Yemen in building schools due to its robust procurement system. This procurement system is still in place – confirmed by two capacity assessment studies that were carried out in 2016 by independent auditors contracted by the EU and UNDP. Procurement procedures promote open competition and aim to ensure that invested funds are used for the intended development purposes, with due attention to considerations of economy and efficiency. SFD has a dedicated Procurement Unit, which is responsible for a range of tasks including ensuring that procedures for subproject procurements are applied; preparing and reviewing SFD’s procurement plan and updating Standard Bidding Documents for civil works, goods and consultants’ contracts; maintaining a roster of consultants and contractors etc.

The World Bank has assessed UNICEF’s procurement procedures as acceptable against its own procurement framework. UNICEF will procure a number of consultancy services, including a TPM agency as part of the monitoring activities to follow up on the implementation of the cash transfer programme. The terms of reference for this TPM will be developed and agreed upon by UNICEF and the Bank helping to provide additional scrutiny. It is not envisaged that DFID will have a role in the procurement/selection of the TPM.

Due to the difficult operating environment in Yemen, there is a higher risk to project implementation including potentially limited capacity and quality of consultancy firms related to project implementation and monitoring support. These may be related to: limited number of qualified bidders; limited banking and market capacity; and limited supply of field staff to be hired by sub-contracted firms. These factors may complicate or delay project procurement. To mitigate this risk UNICEF will conduct market research and proactively invite potentially qualified firms to submit bids as well as provide robust training and capacity development to firms’ staff at the bid preparation stage.

Delivery Risk
Given the difficult operating environment across Yemen delivery risk will remain major. To manage this risk, delivery chains have been mapped to enhance visibility of UK funds.

.DFID will provide un-earmarked funding to SFD. The financial case sets out the SFD delivery chain for the portfolio. The delivery chain map will be further developed before a MOU is signed between SFD and DFID. SFD will provide formal updates to the delivery chain at each annual review with further ad hoc updates being provided as and when deemed necessary. SFD financial reporting will clearly show in which areas DFID funds have been spent as well as provide a clear forecast across these areas.

Funds will flow to SFD’s bank account at the Commercial Bank of Yemen, and then onto SFD HQ in Sana’a where 10% management cost will be deducted. The remaining funds will be dispersed to the nine branch offices who in turn will direct funding to individual project lines with commercial contractors/suppliers and community groups as needed. Funding will also flow to all technical units with the SFD Small and Medium Enterprise Development and Small and Medium Enterprise Promotion Services technical units also disbursing funds to Micro-Finance Institutions (MFIs) from a selection of partners including Azal MF; Abyan MF; Al-Amal; Al Awael; Nama' MF; National MF; Yemen Microfinance Network; and Al-Kuraimi. SFD mitigates against any bank transfer risk by sending an instruction to the bank and holding funds in a designated account before transferring a specific amount to a sub-project's account, contractor, supplier or consultant.

Figure 4: SFD delivery chain
SFD has taken several mitigation measures to minimise risks involved in implementing activities as well as financial measures by having accounts in more than one commercial bank, and has recently started applying the UNDP operational exchange rate, thus current currency exchanges are now performed at a rate close to the open market rate. This will be important for SFD to continue to ensure affordability of planned work, coverage, forecasting and accountability. Since the funding agreement with SFD will be in GBP then we are cushioned from any exchange rate risk but DFID should continue to be aware of the exchange rate issues as any losses may delay or stall activities. One risk is the possibility of donor funds being misused. SFD manages this risk in a number of ways including: through smaller tranches of funds from donors being deposited in a commercial bank; independent verification; and ensuring fraud and corruption training for all staff is made available as well as increasing HQ checks on projects. To note that funds from donors are directly deposited in to a specific commercial bank account for each financing agreement.

In addition to the above, to further minimise risks, DFID funds are transferred to SFD in small tranches based on quarterly forecasts. SFD maintains accounts in several local banks, each of whom are making efforts to provide cash liquidity to keep up with SFD’s disbursement rates. SFD manages delivery risk by engaging payment delivery agencies with extensive networks of local agents, robust internal controls and a proven track record of handling large volumes of payment transfers. It also provides operational guidance and capacity building to payment agencies. Liquidity in Yemen continues to be an issue which is particularly problematic for SFD’s employment-generating labour intensive works projects. SFD pro-actively manages this risk by meeting with bank officials to secure agreement to prioritise SFD transactions.

Figure 5: Emergency cash transfer delivery chain

Achieving VFM
The previous VFM assessment sets out the numerous considerations of Value for Money. In line with DFID Yemen’s VFM strategy we will need to follow through the key issues (cost drivers, monitoring efficiency of cash transfers) as part of ongoing project monitoring. As a first step these matters will be reflected in the final logframe and as part of other routine project cycle management processes e.g. Annual reviews.

Financial Case

Overview of costs
The total cost of YeSP will be up to £70m over 5 years. This will be split as follows:
  1. SFD: Up to £57.5 million over 5 years. This flexibility allows SFD to scale up if deemed the most appropriate response. We will assess annually to evaluate changes in the context which affect results, VfM and risk and partner performance. In addition, a more formal review point will be stipulated after 3 years and continuation will be dependent on need and partner performance. As part of this, we will also set aside £20,000 for a joint due diligence assessment of SFD.
  2. Co-financing to SWF beneficiaries: Up to £12.5m to the YCERP in 2018.
  3. Contingency: In line with DFID Yemen’s business plan, we will allow for programme flexibility in the timing of activities and payments to adapt to the dynamic context in Yemen and respond to spikes in immediate needs. For example, the World Bank will trigger its request for contingency funding by confirming a funding gap. Updates to the MoU will be undertaken on confirmation by the Head of Programmes that budget is available and confirmation by the SRO on satisfaction of programme performance.
  4. Evaluation: we will set aside £700,000 of the total budget for an evaluation.
SFD monitoring and evaluation costs are included under three categories: evaluation studies conducted by the monitoring and evaluation (M&E) unit, projects monitoring visits conducted by sectoral units and branch offices; and quality assurance visits conducted by Technical Unit staff. Each unit drafts an annual M&E plan which is reviewed and revised on a quarterly basis as needed. SFD will be able to track M&E costs e.g. in 2017 the cost was $899,000 which represents 1% of total disbursements.

DFID funding to the YCERP will be paid directly to the World Bank. $2.5 million, approximately £1.76 million of this contribution will be used to meet 50% the programme and monitoring costs of the project (the US has already confirmed that they will meet 50% of the total cost of this component). Although oversight measures and mitigation are considered adequate, the project still represents high risk but it is deemed that the return on investment is also high due to the vital support that will be made available to the most vulnerable Yemenis. Since the World Bank is a major funder of this project their oversight will help to provide additional assurance to DFID. UNICEF is a co-signatory to the Financial Management Framework Agreement between the World Bank and UN Agencies, which provides for the use of the UN’s Financial Regulations, will help to mitigate financial risk through agreed reporting requirements, a joint resolution mechanism for serious issues that merit further scrutiny, including fraud and corruption, the inclusion of appropriate remedies (including the right to suspend or to terminate disbursements) and clear responsibilities between the Bank and UNICEF. This level of scrutiny from the World Bank will help to assure DFID that funds are being spent on the intended purpose.

DFID has funding allocated from its current resource allocation for the next two years totalling £175m/annum. Approval for the outer years of the SFD funding arrangement (totalling £23 million) will be need to be sought from HMT. This funding will come from the RDEL budget. A review point will be made after three years to assess continued performance and to agree continuation into the outer years.

DFID will provide pre-financing upon receiving an official request from SFD and the World Bank. The SRO will confirm, on written confirmation from the partners of need, that each payment tranche does not constitute a payment in advance of need. The funding arrangements will stipulate our contribution in GBP. SFD funds will be disbursed at agreed quarterly intervals as set out in the MOU. Payment to the World Bank to support the emergency cash transfers will be formulised through a trust fund agreement for a one off payment with any agreement to further payments through an amendment to the original agreement. Payment tranches for SFD will be agreed based on delivery plans and partner capacity. The SRO will approve any changes to the planned forecasted spend including delaying payment where implementation is delayed against previous tranches and exceptionally bringing forward budget where resources are required to meet spikes in need.

The continuing conflict could impact on the operational costs for our partners e.g. scarcity of fuel resulting in higher costs or a delay in delivery of activities (e.g. such as rehabilitation of water sources) if access to fuel is not possible. Cash transfers under the YECRP and SFD Cash for Work programme where the cost of living exceeds payments made to beneficiaries will reduce beneficiaries’ purchasing power and will lessen the impact of providing this support as the cost of a basic food basket of essential goods will increase. We will expect our partners to ensure there are contingency plans e.g. stock-piling, in place to help lessen the impact. In the case of our funding to YECRP in particular we will continue to work with the World Bank to support an increase to the cash transfer level. This is challenging at the moment as the World Bank has confirmed resources resources are limited and they don’t want to reduce the number of beneficiaries reached.

Cost profiling and planning
DFID will profile costs as follows within the first two years of the programme with the remainder to be split over the final three years, see Table 8 below (SFD component based on best case funding scenario but this will be amended as necessary once there is clarity on final budget):

Table 8: DFID financial profile for the first two years
Component		Timing			Amount (RDEL)
Social Fund for Development – core support		November 2018 (covering costs for November to March 2019 – includes £20,000 for joint donor due diligence assessment on SFD)			£11.5 million
		April 2019 (covering costs for April to June 2019)			£2.5 million
		June 2019 (covering costs for July to September 2019)			£2.5 million
		September 2019 (covering costs for October to December 2019)			£3.25 million
		December 2019 (covering costs for January to March 2020)			£3.25 million
Emergency Cash Transfer – World Bank		November 2018			£7 million
Contingency brought forward		TBC upon confirmation of need
Component 1 – Funding to SFD
Funding Type: 111 – Not for Profit Organisation
Benefiting Country: (e.g. Yemen)
	Input Sector		Input Sector Code	Percentage Allocation
1	Social Protection, Social Infrastructure and Services		16011	100%
Component 2 – Funding for Emergency Cash Transfers
Funding Type: - 109 – Multilateral Organisation
Benefiting Country: (e.g. Yemen)
	Input Sector		Input Sector Code	Percentage Allocation
1	Social Protection, Social Infrastructure and Services		16011	100%

Financial and Fraud risk assessment
Yemen features at 170 out of 176 countries on the Transparency International Corruption Perceptions Index. Partners therefore operate in a context where there is a high likelihood of fraud risk.

All partners funded through this business case are judged to have strong financial and other processes to guard against fraud and corruption but it remains a risk as opportunities continue to exist through the delivery chain. This judgement is based on information shared with partners and past experience of working with SFD. SFD, systems for reporting fraud and corruption will be reassessed through a further due diligence assessment.

Given the conflict in Yemen, the delivery of cash transfers to a large number of beneficiaries, over a large geographical area, with several entities involved in implementation is high risk. This could pose significant financial management challenges and increase risk of errors and leakages.

The main financial and fraud risks and mitigation measures are detailed in the table below:

Social Fund for Development
Risk	Mitigation
Poor governance of payment procedures leads to under/over payment to beneficiaries giving way to fraudulent activities.	SFD to ensure processes adequately address this risk through adjusting processes where necessary and clarifying payment details to beneficiaries. Independent monitoring continues to verify the use of / funds and report any issues relating to cash payments.
Financial decision making resting with the Managing Director without any checks or balances could lead to fraud.	Internal and external audit reports scrutinised to ensure funds are used for the intended purpose and no issues are raised regarding fraud. In addition, the Managing Director continues to update the Chair Person of the board on major issues. The Managing Director continues to be supported through the decision making process by the Projects and Policy Committee (PPC), made up of nine Unit Heads. The PPC is responsible for addressing operational issues, reviewing appropriate procedural policies and approving new projects when funding is available. DFID will also be working together with donors and SFD to for greater interim oversight of decision-making during phase 5.
Procurement procedures inadequate leading to aid diversion and terrorist organisations being funded	SFD’s contracts the beneficiary communities of the infrastructure to implement under the project, under supervision of consultants employed by SFD. Members of the community are also trained on all aspects of project cycle, design, procurement, implementation and monitoring. / SFD work on the principle that the context of conflict requires that more care be applied in the selection and targeting of beneficiary communities. SFD use a transparent allocation of funds based on national statistics indicators at governorate and district levels, below this level, selection of the community beneficiaries is based on a transparent eligibility criteria and consultations with communities and leaders. At a programme level, ensuring transparency in the procurement processes, including those of community contracting, both demonstrates best practise and reduces conflict among communities as well as funding to terrorist organisations being minimised..
Funds are lost due to inadequate controls and measures	SFD funds are deposited in a bank which has insurance meaning that the bank will bear any losses. SFD will transfer project funds directly to beneficiary accounts or to individuals without accounts through Al Amal Bank, the Post Office, and local agents, who assume the risk once funds have left SFD's account.
Emergency Cash Payment to SWF Beneficiaries
Poor targeting leads to double payments to beneficiaries as well as payments to ineligible recipients.	Analysis and control of the database of beneficiaries and list of payments.
Payment agencies (including downstream partners) having inadequate accounting and internal controls with undefined financial arrangements leading to a failure in delivering cash payment or less transparency which may give rise to fraudulent activity.	For SWF, DFID will not have a direct partnership with UNICEF however through the World Bank we will endeavour to ensure downstream partners are confirmed by name and any fraud risks through the delivery chain identified. This can include a rapid assessment of selected independent payment agents with transparency procedures and robust accounting and internal control practices; defined financial management arrangements for transfer of funds and required financial reports for payment; third party monitoring; and grievance redress mechanism (GRM) and leveraging social media to analyse community perception and feedback on a real-time basis and identify red flags for fraud to complement the GRM. In addition, at the local level, social workers will play the role of monitors but will not handle payments.
Poor systems, policies and procedures in place increasing likelihood of aid diversion	We will ensure that sufficient mitigation strategies such as robust targeting approaches and verification measures are in place to help minimise the risk of diversion of funds to terrorist groups or activities. The World Bank will follow a robust due diligence process and a full assessment of UNICEF’s corporate governance systems will be completed. In addition, the financial management framework between the Bank and the United Nations clearly sets out expectations on financial management in terms of preparation of accounts, requirement for audited financial statements detailing the activities funded. These requirements and requirements on anti-corruption and coercive practices will help safeguard against aid diversion and ensure that issues emerging are made transparent and managed appropriately. / Aid diversion will be mitigated by ensuring adequate supervision of the payment distribution process by the payment agent (downstream partner). TPM will be conducted by an independent consultancy firm. and will have three functions: (i) ongoing monitoring of the payment distribution processes; (ii) post-transfer monitoring; and (iii) investigation of specific cases as recommended by UNICEF. Ongoing TPM will involve spot-check visits to payment distribution and GRM sites to monitor the presence and performance of payment agents and GRM staff. Post-transfer TPM will include a performance audit to identify strengths and weakness in the implementation of the payment delivery. The performance audit will survey a sample of locations to capture beneficiary experiences with respect to awareness about the transfer, amounts received and ease of payment delivery procedures.

SFD has previously reported cases of fraud in elements of its programmes but state that no DFID funding has been involved. DFID will continue to remind SFD of its responsibilities in terms of reporting fraud or suspicions of fraud to DFID and also to ensure SFD’s downstream partners are made aware of their own responsibilities in this area. We will continue to scrutinise SFD’’s own reports including external audits as well as TPM reports that are available.

Following recommendations from the 2016 Internal Audit of DFID Yemen, we have undertaken a series of interviews with DFID-funded downstream partners of SFD, which included assessing fraud and corruption policies and practice. Key findings indicated that downstream partners were unaware of their own responsibilities in terms of reporting fraud cases to SFD. These findings have been shared with SFD and we are following up with SFD who have shown commitment in addressing the concerns by rolling out new fraud and corruption training for all staff and increasing HQ checks on projects. We are continuing to follow up with SFD to ensure weaknesses identified are fully addressed.

DFID will ensure that appropriate measures are in place including a robust risk matrix that will help tomitigate against any financial or fraud risks. As stated above, it is recognised that the nature of this cash transfer programme poses a high risk due to the delivery of cash to a large number of beneficiaries, over a large geographical area, with several entities involved in implementation. This risk is further compounded due to the ongoing conflict and volatile political situation. These factors therefore present significant financial management challenges to minimise the risk of fraud and prevent the risk of aid diversion.

In addition, oversight by the World Bank will help to mitigate financial risk through agreed reporting requirements, a joint resolution mechanism for serious issues that merit further scrutiny, including fraud and corruption, the inclusion of appropriate remedies (including the right to suspend or to terminate disbursements) and clear responsibilities between the Bank and its implementing partner.

Table 9: Monitoring, reporting and accounting for funds
Issue	Description
Reporting requirements	SFD will be required to produce progress reports every six months setting out progress against its results framework as well as information on risk, value for money etc. In addition, we will expect SFD to provide ad hoc reporting on risk as and when there is any emerging risks or existing risks are escalating. Financial reports will be required quarterly, along with each payment request, which will set out expenditure as well as a future forecast. Additional informal updates on a monthly basis will be expected. This level of detail will help to ensure that DFID does not make payments in advance of need and that our own internal systems are updated regularly. / SFD will also be required to share annual independent external audits with DFID. We will request that SFD also shares internal audits, including management responses. Where this is not possible then we will seek a clear explanation. These reports will be used to provide assurance that DFID funds are being used as intended and that results are being achieved as planned. / The Bank will provide quarterly financial and reconciliation reports and twice a year a more comprehensive progress report will be produced. These will be made available to DFID electronically. DFID will also have access to information from third party monitoring as needed. On completion of a trust fund a completion report is usually produced but due to the nature of DFID’s support i.e. a possible one off payment then alternative final reporting will be discussed and agreed if DFID does not seek to continue to support the emergency cash transfers project to SWF beneficiaries. / The Bank is responsible for verifying UNICEF six monthly progress and quarterly financial reports. If there are concerns, these will be noted in the Bank’s internal Implementation Status Report. UNICEF is also required to publish annual audited accounts, with the audit carried out by a firm approved by the Bank. These accounts are then placed on the Bank’s website at www.worldbank.org/projects. / A single audit report for the World Bank will be reviewed and issues will be raised with the partner as necessary. This is an audited account for the trust funds’ portfolio and a statement of assurance about the internal control systems that govern trust funds.
Asset management	Due to multi-donor support to SFD, DFID does not claim ownership of assets and therefore there is no need for an inventory to be shared with DFID (SMART rule 33). However, SFD do hold assets on their accounts and have been keeping track of projects damaged during the conflict, reporting that as of January 2018 in total 225 have been damaged, of which 54 have been fully destroyed and 123 partially destroyed. / YCERP –There is no plan to purchase large items and therefore no need to maintain an asset register.
Return of funds	Return of funds will be in line with requirements set out in the MOU i.e. unspent funds or remaining interest accrued at the end of the programme to be returned to DFID. / We do not expect a return of funds on our contribution to YCERP as our funding will been used to meet the needs of funding a full quarterly payment of emergency cash transfers. However, in the case that there are remaining funds the Bank will return the remaining balance as agreed in the Administration Agreement.

Management Case

Management Arrangements for implementing the intervention: Funding to SFD will be managed through a MOU. The funding to the World Bank will use the standard Administrative Agreement agreed between DFID and the World Bank. SFD’s organisational structure has three main levels: the Board of Directors, the Headquarters Office, based in Sana’a, and its nine branch offices based out in the governorates (apart from Sana’a, which is based in the HQ). See Figure 6 below.

SFD was set up in 1997 under Yemeni law as a national institution. As such, its financial systems are separate from government. The Board of Directors has an oversight role which will include approval of main policies, annual and five year work plans, review of progress and approval of SFD’s internal audit reports. The Board will not have funding decision making powers. Direct day-to-day management of SFD falls under the Managing Director and SFD management team, who is supported by both a permanent Yemeni team, housed at headquarters, and a significant number of temporary consultants. The HQ is in charge of overall operations. These include signing funding agreements; full management control over financial resources and identification and approval of projects. This level of autonomy ensures that SFD will continue to control all operational decisions and ensure it remain politically neutral. The HQ carries out its duties through the Procedural Policy Committee (PPC) and the Projects Approval Committee (PAC).

Figure 6: SFD’s organisational structure

There are eight technical units comprising education, health and social protection, water and environment, cultural heritage, training and organisational support, small and medium size enterprise development, agriculture and rural development, rural roads and Labour intensive works.

There are nine branch offices which are the implementing arm of SFD and are responsible for coordination with local communities, project identification, monitoring of implementation and quality assurance.. Furthermore, in time of crisis, they play an important role in monitoring the security situation and identifying the most adversely affected communities and the crucial needs emerging on ground. Branch Offices also have access to a large pool of consultants to assist in the wide scope of their functions. In recent times, and in response to national emergency needs, SFD has delegated more authority to the Branch Offices to enable initiating interventions rapidly. This delegation is coupled with close monitoring of the concerned units by the head office and maintaining a robust M&E.

SFD follows a community-driven development approach. Community engagement and feedback start from an early stage of a project and continues through the project cycle. Beneficiary engagement takes place through: community consultations during needs prioritisation; formation and training of different types of beneficiary committees; systematic complaints handling; monitoring and complaints handling during the implementation. Beneficiaries provide input into project evaluation. They are asked about their engagement, the prioritising of interventions and the quality of the project and its impact. Community empowerment as a delivery mechanism is led by the Empowerment for Local Development programme whereby SFD establishes community structures in order to plan and lead the development initiatives in local areas.

SFD has improved its on-line system for donors access to information. They also produce progress reports every six months setting out results against its work plan/results framework. DFID’s own third party monitoring as well as that of other donors will be used to triangulate the information received from SFD. Regular donor meetings will also be an opportunity to explore progress and challenge SFD where appropriate.

The MOU with SFD will set out expectations in terms of performance and VFM and state that if the situation in Yemen, e.g. access constraints severely limiting progress, renders our support untenable then we will assess our funding.

Our funding to YCERP will be disbursed to the World Bank who in turn will make payments to UNICEF the main implementing partner. UNICEF will contract partners to deliver against a number of activities including third party monitoring. We will work with the World Bank to ensure we are clear on which downstream partners have been contracted to deliver against the project. This will enable DFID to clarify downstream partner mapping.

Monitoring and Evaluation
Monitoring and Evaluation and reporting progress is the responsibility of implementing partners. Oversight of monitoring will be conducted in a number of ways through:
1. Oversight from within the World Bank over our contribution to the YECRP.
2. DFID’s regular review of progress reports from all partners, including third party monitoring reports from the UNICEF contracted YECRP independent monitoring partner.
3. DFID formal annual review where partners will be interviewed on progress.
4. SFD donor dashboard (currently under development) where on demand access to results will be available.
5. DFID Yemen’s own independent monitoring programme (IMP). The IMP provides DFID with oversight of partners in Yemen where we have no staff presence. The IMP conducts field visits and beneficiary interviews. The purpose of this oversight is to provide accountability for the delivery of output results. The IMP verifies that outputs have been delivered at scale, to the expected quality and appropriately targeted. The IMP provides implementing partners with recommendations for strengthening data systems and programme delivery.

We recognise that the data systems of both SFD and SWF will require strengthening to ensure that programme data is of high quality and we are able to monitor DFID’s commitments to ‘Leave No-One Behind’. We will ensure that data is disaggregated by geography, sex, age and disability. SFD and SWF are currently unable to disaggregate data. They make assumptions about the number of beneficiaries per HH. We will work with partners to ensure that commitment to creating a database of direct beneficiaries of cash transfers and their HH listing.

DFID for the first time will support SWF beneficiaries through a World Bank-executed Trust Fund. Given the context and the cost of the programme there is merit in assessing overall efficacy. We will earmark up to £700,000[29] of the total budget to explore an evaluation (procured by DFID using DFID’s Global Evaluation Framework Agreement). Separately we will explore supporting SFD by putting the evaluation designs and reports through DFID’s Evaluation Quality Assurance and Learning Service (EQUALS), joining their steering group and providing technical advice.
[29] The cost of the evaluation will be dependent on a range of factors including the range of stakeholders who will use the findings and the scope of the evaluation questions.

Partnership Principles and other conditions
SFD is an autonomous quasi-governmental institution whose management is delegated the responsibility under Yemeni law to determine how it will invest donor funds, while respecting accords approved with its donors. Since we will not be providing funding to the Government of Yemen through this programme the partnership principles do not apply.

Risks
Funding to partners to deliver projects in Yemen is higher risk due to the conflict. DFID will monitor risk by scrutinising partner reports, audit reports and third party monitoring reports. DFID will consider risks to delivering value for money and results. The overall residual risk rating for both SFD and the YECRP project is assessed as major.

Table 10 below sets out the key risks including mitigation actions. A due diligence assessment on SFD was completed in 2016. We will revisit the findings to ensure recommendations have been taken forward and explore the need for a further joint due diligence assessment with other donors. We will also continue to remind SFD that any changes or emerging risks should be reported to DFID at the earliest opportunity.

The grid below (figure 7) provides a visual on the gross risk (black text boxes) and residual risk (white text boxes) and how they relate to DFID Yemen’s risk appetite which is signified by the dotted line The numbers represent the risks that can be found in table 10.:

Figure 7: Risk Heat Map

        Table10: Risks and their mitigation
Risk Category	NO.	Risk	Likelihood	Impact	Gross Risk Rating	Mitigation	Residual Risk Rating
Funding to YECRP
Delivery	1	UNICEF institutional capacity and experience is insufficient to deliver cash transfers at scale in Yemen	Possible	Severe	SEVERE	UNICEF to enlist the services of qualified consulting firms with transparency procedures and robust accounting and internal control practices, defined financial management arrangements for transfer of funds to beneficiaries ensuring accurate targeting. TPM will also help to ensure partner agency performance is being delivered. In addition, UNICEF will engage a wide network of social workers with previous experience with CT beneficiaries that exist in all districts.	MAJOR
	2	Operational challenges affect payment delivery	Unlikely	Severe	MAJOR	Engage payment delivery agencies with extensive networks of local agents, robust internal controls and a proven track record of handling large volumes of payment transfers. / Provide operational guidance and capacity building to payment agencies	MODERATE
	3	Governance risk of elite capture	Possible	Severe	SEVERE	UNICEF to engage qualified consultants with expertise required to deliver cash payments across Yemen. Consultancy services will provide cash transfer technical and operational support, TPM, robust beneficiary identification procedures/validation, grievance redress facility and communication and field facilitation.	MAJOR
	4	UNICEF unable to identify highly qualified service providers due to the security situation	Possible	Severe	MAJOR	UNICEF to conduct market research and proactively invite potentially qualified firms to submit bids as well as provide robust training and capacity development to firms’ staff at the bid preparation stage	MODERATE
Fiduciary	5	Potential lack of capacity of the national financial system to exchange and absorb the US dollars required in the envisioned timeframe	Possible	Severe	SEVERE	UNICEF will consult World Bank to determine most appropriate financial partners and discuss other banking risks	MAJOR
	6	Poor financial management structure giving rise to corruption and fraud	Possible	Severe	SEVERE	Independent payment delivery agency with transparent and robust internal controls and oversight procedures engaged to monitor emergency cash payments to SWF beneficiaries	MAJOR
External Context	7	Political interference causes disruptions to payment delivery and supervision	Possible	Major	MAJOR	Robust security protocols based on local knowledge on security threats and involving political actors at the national, governorate, and local level in communication and payment facilitation	MAJOR
Social Fund for Development
Delivery	8	Insecurity and access constrains SFD’s progress	Possible	Severe	SEVERE	SFD continues to see an improvement in access and alerts donors where issues arise	MAJOR
	9	Volatility of fuel supplies and prices impact on SFD’s ability to deliver in a cost effective manner and lead to loss of power in SFD offices and projects	Possible	Major	MAJOR	SFD continue to adapt to changing circumstances on the ground including stockpiling central reserves of fuel and moving towards solar energy	MODERATE
	10	Liquidity crisis affects availability of cash from the banks (particularly problematic for SFD’s employment-generating labour intensive works projects)	Possible	Severe	SEVERE	SFD taking an active lead on managing risks associated with the liquidity crisis by meeting with bank officials to secure agreement that they prioritise SFD transactions. / DFID Yemen continues to track all banking risks.	MAJOR
	11	Further macroeconomic instability such as the depreciation in Yemeni Riyal and non-functioning markets	Almost Certain	Severe	SEVERE	DFID Yemen continues to monitor all banking risks and the impact on our programmes. Together with the Foreign Office, DFID lobbies the Central Bank of Yemen to enact policies to support the stabilisation of the currency	SEVERE
	12	Decreased number of international banks willing to do business with Yemeni banks leading to challenges in donor funds arriving in Yemen	Possible	Severe	SEVERE	SFD uses and explore other systems for including approved money exchangers and microfinance institutions. / DFID Yemen continues to monitor all banking risks and the impact on our programmes	MAJOR
External Context	13	SFD’s neutrality and autonomy compromised by political interference	Possible	Major	MAJOR	Ongoing monitoring. DFID Y with internal audit, and other donors, exploring improving internal governance during phase 5.	MODERATE
Operational	14	SFD progress is impacted by capacity constraints	Possible	Major	MAJOR	DFID to continue to seek assurance from SFD on its capacity to deliver against its budget and work plan, ensuring that they have the resources in place to monitor its activities across the country	MODERATE
Reputational	15	Conflict sensitivity and safeguarding not addressed	Unlikely	Severe	MAJOR	DFID to work with partners to ensure programmes are informed by conflict sensitivity analysis (e.g. through advisory input with partners). / DFID to ensure that no UK taxpayer funds are used to support individuals or entities associated with terrorism. / Partners and all downstream partners to make themselves aware of, and partners to sign compliance with, the relevant counter terrorist financing legislation. / DFID will undertake an enhanced due diligence assessment of safeguarding policies of both SFD and UNICEF in advance of implementation. We will use the findings to ensure that our partners have a robust approach in place including measures to help prevent interventions doing harm. These will be incorporated into project cycle management processes, in line with good practice with other programmes in the overall portfolio.	MODERATE
Fiduciary	16	DFID funds to SFD are misused	Possible	Severe	SEVERE	Funds from donors to SFD directly deposited in to a specific commercial bank account for each financing agreement. / Funds are transferred to SFD in small tranches based on quarterly forecasts. / SFD maintains accounts in several local banks, each of whom are making efforts to provide cash liquidity to keep up with SFD’s disbursement. / DFID independent monitoring programme verifies use of funds. / SFD's own internal monitoring, internal and external audits will be reviewed to ensure that any issues raised are managed appropriately. / DFID will continue to ensure that SFD Senior management are aware of DFID's zero-tolerance approach to fraud and corruption and reminded of their responsibility in terms of reporting fraud; / DFID will continue to work with SFD to ensure that downstream partners are aware of their own responsibilities in terms of reporting fraud cases to SFD; / SFD funds are deposited in a bank which has insurance meaning that the bank will bear any losses. / SFD will transfer project funds directly to beneficiary accounts or to individuals without accounts through Al Amal Bank, the Post Office, and local agents, who assume the risk once funds have left SFD's account. / SFD to continue fraud and corruption training for all staff and increase HQ checks on projects	MAJOR

List of Acronyms
CBA	Cost benefit analysis	M&E	Monitoring and Evaluation
CLD	Community Led Development	m	Million
CBY	Central Bank of Yemen	MoSAL	Ministry of Social Assistance and Labour
CfW	Cash for work	NGO	Non-governmental Organisation
CSS	Cash for social services	NSPMS	National Social Protection Monitoring Survey
CSoS	Comprehensive Social Survey	PMT	Proxy Means Test
CT	Cash Transfer	Q	Quarter
DFIDY	DFID Yemen	SFD	Social Fund for Development
ELD	Empowerment and local development	SWF	Social Welfare Fund
GoY	Government of Yemen	SO	Strategic Objective
GRM	Grievance and Redressal Mechanism	SRO	Senior Responsible Owner
HBS	Household Budget Survey	SME	Small and Medium Enterprise
HH	Household	SMEPS	SME Promotion Services
HNO	Humanitarian Needs Overview	SMED	SME Development
HDI	Human Development Index	SP	Social Protection
HQ	Headquarters	SSN	Social Safety Net
HSNP	Hunger and Safety Nets Programme	SDP	Single Departmental Plan
IDA	International Development Association	SDG	Sustainable Development Goals
ILO	International Labour Organisation	TPM	Third Party Monitoring
IDP	Internally Displaced People	UAE	United Arab Emirates
IMP	Independent Monitoring Programme	UNICEF	United Nations Children’s Fund
LIPW	Labour Intensive Public Works	YECRP	Yemen Emergency Crisis Response Project
MENAD	Middle East and North Africa Department	YER	Yemeni Rial

Annexes to the BC

Key SFD results from Phase IV
Evidence base to inform options choices

Annex 1: SFD Phase IV: Results to December 2017
Selected SFD Phase IV results		DFID share @ $167.2m (18%)
Projects completed and costs: 5,548 projects at a total contracted cost of about $779 million with a total disbursed amount of $912 million (of which about $90 million was disbursed during 2017).		999 projects
Key indicators	Dec 2017	DFID share (@18%)
1. Poverty Targeting: % of CLD and LIPW resources that go to the lowest 50% deprived HHs	69% CLD / 85% LIPW
2. Total # people supported: / a) Direct beneficiaries of SFD funded projects (#, % women) / b) Indirect beneficiaries from community livelihood assets	a) 9.1m (5m, 55%) / b) 329,123	a) 1.6m (880,000 55%) / b) 59,242
3. Employment created: Total # of workdays employment created	a) 35.1m	a) 6.3m
4. Reduced vulnerability through cash transfers: / a) # people directly benefitting from cash through LIPW only (% women, youth and IDPs*) / b) % of cash transferred spent on food, basic necessities and food related items / c) # women receiving conditional cash transfers for nutrition support	a) 1,316,493 / (30%, 58%, 16%) / b) 74% / c) 13,380	a) 236,969 / (30%, 58%, 16%) / b) 74% / c) 2,408
5. Education access: / a) Enrolment in schools supported by SFD, disaggregated by: / (i) Boys; (ii) Girls; (iii) Children with special needs / b) # of classrooms constructed and/or rehabilitated	a) / (i) 150,342 / (ii) 130,424 / (iii) 7,540 / b) 9,785	a) / (i) 27,062 / (ii) 23,476 / (iii) 1,357 / b) 1,761
7. Health and nutrition access: / a) # health facilities constructed/ renovated and equipped / b) # children under 5, pregnant and lactating mothers screened, identified as malnourished and referred for therapeutic feeding / c) # youth hired to support delivery of nutrition services / d) # work days created	a) 113 / b) 50,679 / c) 1,994 / d) 102,418	a) 20 / b) 9,122 / c) 359 / d) 18,435
8. Water and sanitation: / a) # people with access to improved water sources < 30 mins / b) % of HHs in rural CLD areas where time taken to collect water < 30 mins / c) #people with access to improved sanitation facilities	a) 1,150,537 / b) 77% (dry), 83% (rainy) / c) 317,965	a) 207,097 / b) – / c) 57,234
10. Rural road access: Total length of roads improved/ built (km)	1,420	256
11. Microfinance: / # active clients accessing microfinance services supported by SFD (% women)	85,716 (42.8%)	15,429

Source: SFD report to donors 7th Feb 2018, (* as set out for WB supported Yemen Emergency Reconstruction Project).

Source: DFID Annual Reviews and PCR

Annex 2: Evidence base to inform options choices in Appraisal section

Social Protection: Globally Good - Strong.
Social protection has proven potential to contribute to other SDGs The last two decades have seen an unprecedented rise in Governments using social-assistance as a means of reducing vulnerability and alleviating and averting deprivation[30]. Governments have also agreed indicators under SDG 1 to “implement nationally appropriate social protection systems….and by 2030 achieve substantial coverage of the poor and vulnerable”. The World Bank and ILO have also launched a joint plan of action on Universal Social Protection to ensure that no one is left behind[31]. For example, social assistance has proven potential to improve household food security and dietary diversity, stimulate health service use, increase women’s decision-making power and choice, reduce incidences of child labour, raise school attendance and help foster economic autonomy[32]. Social Protection now features as an indicator in SDG 10 (reduce income inequality) and SDG 5 (improving gender equality).
[30] Ibid.
[31] http://www.worldbank.org/en/news/feature/2015/07/27/wbg-and-ilo-co-launch-a-joint-plan-of-action-on-universal-social-protection
[32] Ibid.

Social assistance impacts mean it is also increasingly seen as a tool to strengthen the resilience of poor households against shocks and tangibly link humanitarian and development actors and approaches. For example, predictable social transfers can protect the poor from the impacts of shocks, including the erosion of productive assets and minimise negative coping practices. In the longer term, social protection can smooth consumption, improve nutrition and facilitate livelihood investments that build resilience to future shocks or crises[33]. In the run up to the World Humanitarian Summit, social protection actors (including the World Bank, UN agencies and bilateral donors) made a statement calling for a commitment to move chronic humanitarian caseloads of affected populations into social protection programmes and systems[34].
[33] FAO (2016) Social protection in protracted crises, humanitarian and fragile contexts Rome: FAO Available at: http://www.fao.org/3/a-i5656e.pdf
[34] SPIAC B (2016) How linking social protection and humanitarian action can bridge the development-humanitarian divide: A joint statement of social protection actors to the World Humanitarian Summit (downloaded from http://socialprotection.org/discover/publications/leaving-no-one-behind-how-linking-social-protection-and-humanitarian-action on 04 Sept 2016)

Cash transfers: Globally strong
There is strong international evidence that cash transfers deliver multiple outcomes for poor people[35],[36]. There is growing international evidence that cash transfers have a range of positive effects in contexts of chronic poverty,[37] as long as: i) the transfer value is adequate, ii) the duration of programme support is sustained, and iii) transfers are delivered in a timely and predictable manner. The main impacts are related to improvements in consumption, followed by increased health and education service utilisation, and investment in livelihoods activities[38]. Such programmes can offer good value for money[39] and can have a significant impact on reducing the depth of poverty if the poor can access the programmes.
[35] Grosh, Margaret, Carlo del Ninno, Emil Tesliuc and Azedine Ouerghi (2008) For protection and promotion: the design and implementation of effective safety nets. World Bank, Washington DC. Fiszbein, Ariel, Norman Schady, Francisco H G Ferreira, Niall Keleher, Pedro Olinto and Emmanuel Skoufias (2009) Conditional cash transfers: reducing present and future poverty. World Bank Research Report, Washington DC. Arnold, Catherine, Tim Conway and Matthew Greenslade (2011) Cash transfers: literature review. DFID Policy Division, London, April 2011. Bastagli, F et al (2016) Cash transfers: what does the evidence say? A rigorous review of programme impact and of the role of design and implementation features London: ODI
[36] Browne, E. (2015). Social protection: Topic guide. Birmingham, UK: GSDRC, University of Birmingham.
[37] DFID (2011) Cash Transfers Evidence Paper. Policy Division, Department for International Development
[38] On the hierarchy of uses of cash transfer income, see Devereux, S. (2002) Can social safety nets reduce chronic poverty? Development Policy Review 20 (5): 657-75
[39] Public Accounts Committee (2012) Report on Transferring Cash and Assets to the Poor

A recent rigorous literature review[40] (the largest globally to date) concludes that CTs are a powerful policy tool that can contribute to a range of outcomes – monetary poverty, education, health and nutrition, employment (including child labour) and empowerment of women and girls. In the context of resource scarcity, CTs can offer policy makers and practitioners an opportunity to deliver impact across multiple deprivations if we are to achieve the SDGs. CTs have a valuable role to play in achieving this. See Box 1 for a summary of the impacts of CTs on individual and HH level outcomes. One of the strongest and most consistent findings regarding the impact of CT programmes is their contribution to reducing food insecurity. Regardless of the form of transfer, households receiving transfers typically spend more on and consume more food.
[40] Bastagli, F.; Hagen-Zanker, J.; Harman, L.; Sturge, G.; Barca, V.;Schmidt, T.; Pellerano, L. Cash transfers: what does the evidence say? A rigorous review of the impacts of cash transfers and the role of design and implementation features. Overseas Development Institute, London (2016), 299p See: https://www.odi.org/publications/10505-cash-transfers-what-does-evidence-say-rigorous-review-impacts-and-role-design-and-implementation See: the full report; a summary of findings; and an annotated bibliography. This noted that there was a dearth of evidence for MENA (Middle East and North Africa) region and more evidence for conditional cash transfers than unconditional cash transfers.

Spill over effects of CTs: CTs can have significant spill-over effects. For example, in Northern Kenya[41], the spill-overs have benefitted non-receiving households, as well as local economies. The spill-over effects on local economies were statistically significant and favoured HHs that did not receive any transfers. The study[42] concluded that income benefits of Hunger and Safety Nets Programme (HSNP ) within counties are larger than the amount transferred to poor households. Whereas KES 464 million (approx. £3.3m) were transferred to households, local incomes increased by KES 856-945 million (nominal, approx. £6.1m – £6.7m) or KES 624 -661 million (inflation adjusted, £4.45m – £4.71m)[43]. Furthermore, the independent evaluation also found that HSNP had a positive effect on intra-household relationships, benefitted people’s physical and mental well-being, and strengthened social networks[44].
[41] Taylor, E. et al (2016). Evaluating Local General Equilibrium Impacts of Kenya Hunger Safety Nets Program, Phase 2 (HSNP2). Oxford Policy Management, pp. 1-23.
[42] The Local Economy-wide Impact Evaluation (LEWIE) conducted by OPM for HSNP Phase 2. OPM 2017.
[43] Taylor, E. et al (2016). Evaluating Local General Equilibrium Impacts of Kenya Hunger Safety Nets Program, Phase 2 (HSNP2). Oxford Policy Management, pp. 1-23.
[44] Otulana, S. et al (2016). Evaluation of the Kenya Hunger Safety Net Programme Phase 2. OPM, Oxford. http://www.opml.co.uk/sites/default/files/Evaluation_of_the_Kenya_Hunger_Safety_Net_Programme_Phase_2_Impact_Evaluation_Qualitative_Research_Study_Round_1_2_0.pdf

Box 1: Summary of the impacts of CTs on individual and HH level outcomes.
- Monetary poverty: Cash transfers reduce monetary poverty.
- Education: Cash transfers raise school attendance, but do not always lead to improved learning.
- Health and nutrition: Cash transfers stimulate health service use and improve dietary diversity, but there is less evidence that they affect the height and weight of children.
- Savings and investment: Cash transfers can help foster beneficiaries’ economic autonomy, through increased ownership and use of agricultural assets.
- Employment: Cash transfers are associated with a reduction in child labour. Most show either no effect or a positive effect on adults working.
- Empowerment: Cash transfers increase women’s decision-making power and choices, reduce physical abuse of women by men, but do not always reduce emotional abuse.
- Core design features: There is a strong evidence base showing that the size of the transfer and duration of its receipt play a role in supporting progress towards intended outcomes.
- Conditionality: Including an element of conditionality (in terms of health and education service use) can but does not necessarily lead to greater impacts in these areas; clear communication about the importance of using services is an element of conditionality clearly associated with greater service uptake.
- Payment mechanisms: A limited evidence base shows that different payment mechanisms can be linked to different outcomes.
- Complementary interventions and supply-side services: Complementary interventions and supply side services can strengthen the impacts of cash transfers.
Source: ODI

Humanitarian Cash transfers: The High Level Panel on Humanitarian Cash Transfers (2015) which was supported by the UK, produced strong evidence for the effectiveness of use of cash in humanitarian interventions and disaster preparedness[45]. The Panel recommended to increase the use of unconditional CTs for humanitarian aid, invest in readiness for cash transfers in contingency planning, while using the expertise of the private sector to deliver where markets are functioning.
[45] ODI and Centre for Global Development (2015).Doing Cash Differently. How cash can transform humanitarian aid. Report from the High Level Panel on Humanitarian Cash Transfers, https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9828.pdf

‘Shock-responsiveness’[46] is an emerging area of programme and system design, with most progress made in the social protection field. Shock-responsive systems are designed to not only be resilient to natural disasters, but also scale up in times of crises to provide expanded and adapted services to those in need, reducing the impact of disasters and helping people to get back on their feet more quickly. The most progress to date has been in the area of social protection, where attempts have been made to adapt social protection programmes in Kenya, Ethiopia, the Philippines and Pakistan (amongst others), so they can adapt to changes in need, including scaling horizontally (more coverage) and vertically (more services for the same participants). Recent DFID-funded research on social protection[47] concluded that to improve on the current humanitarian system, shock-responsive services should focus on: increasing comprehensiveness and coverage (without decreasing quality or equality); improving timeliness and predictability; reducing duplication; improving cost effectiveness; and promoting sustainability and government ownership.
[46] By ‘shock-responsive’ we mean the ways in which systems and programmes can be adapted to make them more resilient to shocks and more able to adapt to change in demand following shocks so that those affected are able to continue receiving the services that they need.
[47] Oxford Policy Management, in partnership with the Overseas Development Institute, the Cash Learning Partnership (CaLP) and INASP, has conducted a 2 year research programme on Shock-Responsive Social Protection Systems, funded by DFID and due to finish in 2017.

Labour Intensive Public Works: Globally mixed
There is less evidence on the impact of short-term public works (PW) employment on poverty. A global research paper[48] on CTs, including cash-for-work schemes, notes that there is extensive and potentially generalisable evidence that cash transfers, including cash-for-work schemes, have reduced the depth or severity of poverty. Receipt of the PW wage usually leads to a temporary reduction in the depth of poverty, but rarely results in a drop in headcount poverty. Outcomes are dependent on the value of the wage, the duration of employment, the cyclical provision of employment, and the distribution of benefits arising from the assets created.[49] Where employment has been provided on a repeated seasonal basis in association with other forms of input (agricultural extension, micro-finance etc.) there is evidence of significant poverty reduction.[50] Increases in productivity relating to the assets created under PW, particularly where linked to improved natural resource management, may have the potential to provide sustained benefits resulting in sustained poverty reduction.
[48] See: http://www.dfid.gov.uk/Documents/publications1/Transforming-Cash-Transfers-Yemen.pdf
[49] See McCord (2012) for a review of the evidence. McCord, A. (2012) Public Works and Social Protection in sub-Saharan Africa
[50] See Berhane et al (2011) on the PSNP in Ethiopia. Berhane, G., Hoddinott, J., Kumar, N., Taffesse, A. S., Diressie, M. T., Yohannes, Y., Sabates-Wheeler, R., Handino, M., Lind, J., Tefera, M and Sima, F. 2011. Evaluation of Ethiopia's Food Security Program: Documenting Progress in the Implementation of the Productive Safety Nets Programme and the Household Asset Building Programme, Brighton: Institute of Development Studies.

High quality impact evaluations from Ethiopia show that safety nets incorporating a LIPW component such as the Productive Safety Net Programme (PSNP), result in large and widespread gains in household welfare and rural development, particularly in the highland areas where it is better targeted and more mature (see Box 2 below).

Evidence shows that job creation projects are among the most effective means of stabilising communities and keeping peace immediately after conflict, and they buy time until the private sector can grow enough to absorb the labour supply at stable, market-clearing wages[51]. World Bank experience in post-conflict transitions also points directly to the critical role of youth employment and cash transfers in ‘buying time for peace’, that is, sustaining emergency efforts past the immediate relief phase and ushering in sustainable service[52].
[51] Beasley, Kenneth W. 2006. Job Creation in Post-Conflict Societies. U.S. Agency for International Development - Centre for Development Information and Evaluation.
[52] World Bank PAD1797. YEMEN EMERGENCY CRISIS RESPONSE PROJECT July 5, 2016

Box 2	Evidence from the PSNP LIPW programme in Ethiopia
Evidence suggests PSNP has had wider impacts through:
- Cash transfers: into poor communities generate significant multiplier effects (estimated at 1.84) as recipient households spend their additional income on local goods and services, providing a significant boost to incomes and growth in the locality.
- Gender equity: in some cases, PSNP has been able to incorporate provision for gender equity and female participation in programme governance and performance.
- Contributing to climate resilience, mitigation and disaster risk management programming and policy:
  - At national level: The PSNP’s Risk Financing Mechanism (RFM) helped Ethiopia to manage the 2011 Horn of Africa drought crisis without a famine. Over twenty years of investment in PSNP is estimated to save some £2.1bn ($3.3bn) compared to reliance on humanitarian responses.
  - At area level: in 2013/14, over 48,000 sub-projects were planned, requiring 104 million person days that have contributed to reversing soil erosion and environmental degradation; increasing carbon capture (1.45 m tonnes of CO2e sequestered in just two sample watersheds); and expanding the area served by small-scale irrigation and improving access to markets and schools.
Participation in PSNP:
adds significantly to pre-transfer income and consumption;
- has a significant impact on food security. Between 2010 and 2012, PSNP transfers reduced the average annual food gap of PNP beneficiaries – the number of months in which households struggle to feed themselves – by half (1.5 months); and resulted in a significant improvement in dietary diversity. The percentage of PSNP beneficiaries achieving full (12 months) food security rose from 17% in 2006 to 32% in 2012. Impact on food security has been particularly large for female-headed households.
- increases household spending on not only food but also non-food items (Kumar and Hoddinott 2013 pp, 27-9);
- has improved educational attainment (grade progression and completion), particularly for girls.
- appears to help to reduce the age at which girls marry and leave their parents household; and as such, contributes to tackling the serious problem of early and child marriage in Ethiopia;
- has been one of the three drivers of poverty reduction between 2005 and 2011 (World Bank 2015). The direct impact of PSNP transfers reduced the national poverty headcount rate by 1.6 percentage points in 2011, lifting more than 1.4 million people out of poverty. Indirect effects via higher agricultural productivity increase this impact further.
- has helped extremely poor households to invest in inputs and farm-level improvements which will improve agricultural productivity and allow them to manage their land more profitably, particularly when combined with livelihood support services.

1 In the same year (2011), humanitarian transfers reduced the poverty headcount by 0.4 percentage points, or c. 353,000 people. Source: PSNP Business Case July 2016

Community led development: Globally mixed
Community-Driven Development (CDD) through social funds is a popular policy instrument and delivery strategy in conflict-affected contexts. This is partly because they are seen to alleviate pressure on governments to deliver development and reconstruction outcomes by transferring resources and responsibilities to community actors. Social funds and CDD programmes have the (transformative) potential to generate impacts beyond meeting basic needs, such as creating more peaceful societies, building social cohesion[53] at the local level and thereby promoting trust in government[54].
[53] ### Building social cohesion in post-conflict situations (GSDRC Helpdesk Research Report 1332)
[54] Interventions to increase levels of trust in society (GSDRC Helpdesk Research Report 941)

However, the global evidence base on this is mixed. A rigorous, evidence focused literature review[55], examined 13 programmes, including SFD[56], against three distinct sets of impact indicators: (i) incomes, enterprise and access to services; (ii) social cohesion, stability and violence; and (iii) state-society relations. It is concluded that, although our understanding of the effectiveness of social funds and CDD in conflict-affected environments is limited by a low number of rigorous evaluations across a diverse range of contexts, as well as by an insufficient investigation of the relevant causal mechanisms, the findings suggested cause for cautious optimism. For example, pre-conflict, SFD showed statistically significant increases in enrollment rates for girls (41.7% to 58.3%), the proportion of sick individuals who managed to receive health care for their illness (54.9% to 68.4%) and access to HH taps providing clean drinking water (35% increase) [57].
[55] Mallett, R.; Slater, R. Funds for Peace? Examining the Transformative Potential of Social Funds. Stability: International Journal of Security and Development (2013) 2 (3) 49. Funds for Peace? Examining the Transformative Potential of Social Funds. The 13 programmes were: the National Solidarity Programme in Afghanistan, the Community Empowerment and Local Governance Project in Timor Leste, the Nepal Poverty Alleviation Fund, the Community-Based Reintegration Assistance for Conflict Victims (BRA-KDP) in Indonesia, the Northern Uganda Social Action Fund (NUSAF), the GoBifo project in Sierra Leone, a community driven reconstruction programme implemented by the International Rescue Committee (IRC) in Liberia, the Tuungane programme in the Democratic Republic of Congo (DRC), the Autonomous Region in Muslim Mindanao Social Fund project in the Philippines, the KALAHI Comprehensive and Integrated Delivery of Social Services project in the Philippines, the Yemen Social Fund for Development, the Ethiopian Social Rehabilitation and Development Fund, and the Nigeria Community Based Poverty Reduction Project.
[56] It should be noted that this study felt the lack of baseline data for SFD hampered the quality of the evaluation.
[57] ESA Consultores International, 2003, ‘Yemen Social Fund for Development: 2003 Impact Evaluation Study – Final Report’ Report for the World Bank and World Bank 2006b ‘ Republic of Yemen Social Fund for Development Project’. Implementation Completion Report, 25 June.

While CDD remains appealing and demonstrates and ability to promote inclusive development[58], the evidence supporting it is mixed. There is a growing body of evidence that CDD does not systematically deliver on all the desired outcomes and more modest ambitions are calld for[59]. CDD/ Reconstruction (CDD/R) programmes – aim to empower local communities to directly participate in development activities and to control resources to do so – thereby improving socio-economic wellbeing, governance, and social cohesion at a local level. CDD/R is context driven, but is generally implemented as a standard model. While goals and ambitions may be high, the global evidence base on CDD/R is mixed and results more modest.
[58] Evidence on outcomes of an inclusive societies approach (GSDRC Helpdesk Research Report 1235) This looks at 80 studies.
[59] Bennett, S and D’Onofrio, A Community-Driven Development in Conflict-Affected Contexts: Revisiting Concepts, Functions and Fundamentals. Stability (2015) 4 (1) 1-18.

Ambitious design does not always deliver on wider system reforms. A 5 country rigorous impact evaluation from CDD/R in conflict affected countries[60] concluded that, as currently designed, implemented, and evaluated, CDD/R delivers tangible economic outcomes more than it generates social changes related to governance and social cohesion. However, the economic effects are found in just a few studies. Moreover, CDD/R programming is better at producing outcomes directly associated with the project rather than broader changes in society[61],[62]. Areas that need addressing include: the relatively short timelines of CDD/R projects; the small size of block grants; the limited reach of the projects; the menu restrictions on CDD/R programming; the limitations of social infrastructure; the theory of change; the quality and intensity of social facilitation; the way in which communities are conceptualized; and how community institutions build on existing institutions and relate to the state[63],[64]. This mixed evidence base also extends to the gender impacts of CDD[65].More modesty in setting CDD/R goals, and more honesty in monitoring delivery and evaluating impact is called for.
[60] Afghanistan, Democratic Republic of Congo (DRC), Aceh (Indonesia), Liberia and Sierra Leone.
[61] King, E. A critical review of community-driven development programmes in conflict-affected contexts. International Rescue Committee (IRC), London, UK / Balsillie School of International Affairs, Waterloo, Ontario, Canada (2013) 55 pp.
[62] Bennett, S.; D’Onofrio, A. Beyond critique: Revised approaches to community-driven development. An inception paper. International Rescue Committee, New York, USA (2014) 34 pp.
[63] King, E. A critical review of community-driven development programmes in conflict-affected contexts. International Rescue Committee (IRC), London, UK / Balsillie School of International Affairs, Waterloo, Ontario, Canada (2013) 55 pp.
[64] Bennett, S and D’Onofrio, A Community-Driven Development in Conflict-Affected Contexts: Revisiting Concepts, Functions and Fundamentals. Stability (2015) 4 (1) 1-18.
[65] Browne, E. Gender in community-driven development (GSDRC Helpdesk Research Report 1079). Governance and Social Development Resource Centre, University of Birmingham, Birmingham, UK (2014) 9 pp. This concluded: - Elite capture is a significant concern. The evidence is clear that ‘uncontrolled’ CDD will not necessarily benefit women, the poor and other disadvantaged groups. - Women’s participation is a central problem as they do not usually have the time and/or confidence to contribute to village planning processes. - To reach women and other disadvantaged groups, CDD needs to have explicit targets for them or mandatory participation requirements. Programmes with an explicit gender strategy are more likely to impact on women’s empowerment than programmes without clear gender equality goals. - Programmes which allow women-only space appear effective in enabling women’s voice and developing projects that respond to women’s needs. - CDD programmes struggle to change attitudes and norms around women’s social position. They are often successful at engaging women in projects, but fail to make significant changes in the long-term. - Examples of positive gender outcomes are improved women’s participation in village-level meetings and processes; personal empowerment and voice; women’s access to services; increased skills and independent income. The literature does not present evidence on whether gender inclusion strategies make CDD programmes more effective, as this is not usually included in evaluation outcomes.

Microfinance: Globally mixed
Microcredit has spread rapidly since its beginnings in the late 1970s, but whether and how much it helps the poor is the subject of intense debate. However, the evidence from the microfinance literature on the development impact of access to credit is mixed at best often depending on country contexts[66] and is sometimes negative [67]. The early enthusiasm about microcredit in the 1990s and early 2000s was fuelled by mostly anecdotal evidence and descriptive statistics about dramatic economic and social benefits[68]
[66] See: IMF paper on the links between financial inclusion and economic stability here: http://www.imf.org/external/pubs/ft/wp/2015/wp1522.pdf
[67] Financial Inclusion and Inclusive Growth: A Review of Recent Empirical Evidence. Asli Demirguc-Kunt Leora Klapper Dorothe Singer. Policy Research Working Paper 8040. World Bank, April 2017.
[68] See: Banerjee, A., E. Duflo, R. Glennerster and C. Kinnan. 2015a. "The Miracle of Microfinance? Evidence from a Randomized Evaluation." American Economic Journal: Applied Economics, 7(1): 22-3. Beck, T. 2015. “Microfinance – A Critical Literature Survey.” IEG Working Paper 2015/4. Attanasio, O., B. Augsburg, R. de Haas, E. Fitzsimons, and H. Harmgart. 2015. "The Impacts of Microfinance: Evidence from Joint-Liability Lending in Mongolia." American Economic Journal: Applied Economics, 7(1): 90-122. Kaboski, J. P. and R. M. Townsend. 2011. “A structural evaluation of a large-scale quasi- experimental microfinance initiative.” Econometrica, 79, 1357–406. Morduch, J. 1998. “Does microfinance really help the poor? Evidence from flagship programs in Bangladesh.” Working Paper, Stanford University. Morduch, J. 1999. “The Microfinance Promise.” Journal of Economic Literature, XXXVII: 1569-1614. Pitt, M. M. 1999. “Reply to Jonathan Morduch’s “Does microfinance really help the poor? New evidence from flagship programs in Bangladesh.”” Mimeo, Brown University.

Microcredit itself alone is unlikely to be transformational in lifting people out of poverty as it’s not usually used for microenterprise but financial inclusion, ie. introducing people (and their money) into the formal financial system, has its own intrinsic value. Skeptics fear that microfinance is displacing more effective anti-poverty measures or even contributing to long term poverty via over indebtedness. The evidence tells us that interventions do need to be country specific.

More rigorous impact evaluations in recent years have drawn much more modest conclusions. For example, a rigorous randomised evaluation of the "traditional" micro-lending model was undertaken in India[69]. The findings suggest that access to microcredit has important effects on household expenditure patterns and the creation and expansion of businesses, but no effect on health, education, women’s decision-making, or average monthly expenditure overall, at least in the short term. It is possible that impacts on education, health, or women’s empowerment would emerge after a longer time, when the investment impacts (may) have translated into higher total expenditure for more households. However, at least in the short-term, microcredit alone does not appear to be a recipe for changing education, health, or women’s decision-making. This same study showed that microfinance can be a more positive experience for women where programmes, along with providing credit, also develop women’s skills and knowledge[70].
[69] The Miracle of Microfinance? Evidence from a Randomised evaluation. Abhijit Banerjee, Esther Duflo, Rachel Glennerster. American Economic Journal: Applied Economics. March 01, 2014
[70] Specifically where: - the programmes which target the most vulnerable women are empowered through access to financial services and skills to become co-contributors to their family and community - programmes assist women to develop skills and knowledge, and thereby raise their self-esteem, their social capital, and therefore their reputation in the wider community - financial and economic management experience is cumulative, and has a key role in improving beneficiaries’ self-confidence, their households’ level of support, and positive wider community sentiment over a longer period of association with micro-finance institutions - Where programmes fail to integrate these themes, programme participants may be more vulnerable to negative experiences and outcomes such as loss of family and community support or social status they previously held.

Evidence from Yemen

SFD had external quantitative and qualitative evaluations at the end of each Phase[71] to examine its effectiveness in terms of poverty targeting; community consultations and participation; efficiency in terms of coverage; and outcomes attributable to SFD interventions in the areas of education, health, water, rural roads and microfinance (which then accounted for c.70% of SFD’s investments).
[71] At the end of each Phase in 2003, 2006 and 2009 at the end of each Phase.

Two institutional assessments focused on SFD’s indirect contribution to national public/private implementation capacity, both through the transfer of ‘expertise’ and co-operative arrangements for implementation and policy development. SFD’s operations have reached about 25% of Yemen’s 40,000 villages[72] and more than 50% of the rural population[73]. SFD’s ability to work in difficult areas was attributed to its clearly defined work procedures, employment of local staff and its close relationship with communities and local authorities[74]. SFD is viewed as trying to raise the quality standard of development initiatives as well as the capacity of the national public administration (e.g. by continuously measuring the efficiency of interventions as part of a results-based management approach, targeting investment through the use of data and objective indicators, a participatory approach to decision making regarding projects and responsive- ness to beneficiary needs)[75]. A 2008 study[76] showed that SFD had efficient and transparent procurement procedures and was working to support national strategies rather than a separate approach[77]. SFD costs were at least 20 per cent lower than the education ministry and its projects implementation units. SFD has also promoted capacity development and good governance among NGOs[78].
[72] SFD Management Information System, Jul. 2013.
[73] Based on the 2004 Yemen Population Census, 73 per cent of Yemen’s 19.3 million population live in rural areas.
[74] M. Jennings, ‘DFID Yemen Social Fund for Development – Institutional Evaluation SFD Evaluation 2009’, Final Institutional Evaluation Report, Contract No. CNTR 200808562, The Recovery and Development Consortium: Maxwell Stamp PLC, the Post-Conflict Reconstruction Unit, The University of York and COWI, 2009.
[75] Ibid.
[76] Ministry of Education, Republic of Yemen and KfW Entwicklungsbank, ‘School Construction Costs in Yemen Cross-Sector and Multi-Institutional Assessment Study’, Draft Report on Findings SEF No. 1992 70 182, Prepared by GET German Education and Training GmbH, 2008.
[77] M. Jennings, ‘DFID Yemen Social Fund for Development – Institutional Evaluation SFD Evaluation 2009’, Final Institutional Evaluation Report, Contract No. CNTR 200808562. The Recovery and Development Consortium: Maxwell Stamp PLC, the Post-Conflict Reconstruction Unit, The University of York and COWI, 2009.
[78] M. Jennings, Institutional Analysis of Social Fund for Development, Republic of Yemen, London: DFID, 2006.

The institutional assessment noted that SFD could remain functional when a crisis occurs[79]. During Yemen’s 2011 economic and political crisis, SFD was able to continue its operations with implementation of 82% of its projects across 300 districts (90% of the country)[80]. SFD’s diverse funding sources and approaches helped, using not only contractors but contracting with the community. With the crisis, SFD prioritised the labour-intensive cash-for-work and water projects putting cash into local peoples’ pockets and using local materials.
[79] Ibid. For example, it increased its investment in the Hadhramaut Governorate following the 2008 floods and loss of life. Similarly, it introduced a labour-intensive programme to create employment in local public goods projects as a response to rising food prices during the global food crisis.
[80] SFD Management Information System quoted in Lamis Al-Iryani, Alain de Janvry & Elisabeth Sadoulet (2015) The Yemen Social Fund for Development: An Effective Community-Based Approach amid Political Instability, International Peacekeeping, 22:4, 321-336.

Social Protection/Labour Intensive Public Works: Strong
Key findings confirmed SFD’s capacity in its LIPW programmes at targeting poor and deprived communities and at meeting their priority needs[81]. In treated communities, 74% households had at least one member participating in LIWP - a productive safety net approach in mitigating the impact of economic shocks. More aggregate benefits went to the poor and there a decline in intra-community inequality. Income gains were used to increase staple food consumption, reduce levels of indebtedness and protect loss of sustainable assets to cope with the crisis. There was improved access to water where projects focused on water availability[82].
[81] S. Christian, A. de Janvry, D. Egel and E. Sadoulet, Quantitative Evaluation of the Social Fund for Development Labour Intensive Works Program (LIWP), Berkeley, CA: University of California, 2013. DFID funded.
[82] Lamis Al-Iryani, Alain de Janvry & Elisabeth Sadoulet (2015) The Yemen Social Fund for Development: An Effective Community-Based Approach amid Political Instability, International Peacekeeping, 22:4, 321-336

The latest impact evaluation of the SFD found that almost 70 percent of its funds benefit the poorest three income deciles, and an impact evaluation of the SFD LIWP[83] found “statistically significant program effects on food consumption, debt repayment and durable goods ownership,” and that “the LIWP program played a role in cushioning targeted communities from the economic shock of 2010–2011, averting possible longer term consequences related to selling off assets and increased debt, and positive impacts of the LIWP created infrastructure on water availability. However, it should be noted that this evidence is pre-conflict.
[83] The evaluation was funded by the U.K. Department for International Development, conducted during 2011–2013 by the University of California Berkley and RAND Corporation.

A more recent review of LIPW[84] in SFD concluded overall, LIWP has positive short term benefits for beneficiaries. In the longer term, the assets created are of generally good quality. However, there are technical, recording and process issues with the programme implementation which need to be addressed. Most related to quality issues. Data accuracy and implementation of quality and targeting standards and protocols varies greatly across governorates, suggesting that some compliance issues exist at branch office level[85]. However, benefits were found to be unequally distributed across participants as the crisis had attracted participation of households that would have normally self-selected out of enlisting for workfare. Wages set on a piece-rate basis, created greater rewards for workers involved in more skill-intensive tasks. There was no detectable impact on animal asset ownership, consumption of higher value foods and ownership of goods such as clothing and household utensils.
[84] Highlights of findings and conclusions of SFD ‘Labour intensive Public Works Programme’ (LIWP) Sharon Beatty and Khalid Al Dubai, 21 September 2017. The LIWP is implemented by SFD in eight governorates: Amran, Sana’a, Ibb, Dhamar, Mukulla, Hajja, Hodeida, and Raymah. Of these 8, this study selected 4 for inclusion in the sample: Amran, Sana’a, Ibb, and Dhamar. The evaluation selected these 4 governorates as they have sufficient numbers of “completed” projects which also include the most common LIWP interventions. The other 4 governorates were excluded because either they had not yet reported at least 2 completed projects by the time the study was being designed, or, in the case of Mukulla, security concerns prevented its selection.
[85] Labour intensive Public Works Programme (LIWP) Sharon Beatty and Khalid Al Dubai, 21 September 2017.

Community led Development: Mixed
SFD is viewed as having evolved into a ‘model’ nationwide organisation, flexibly extending a participatory, community led development models across Yemen particularly to rural and remote areas. SFD’s demand-led approach, pro-poor resource allocation on a nationwide basis, use of verified results as a basis for decision making, participatory processes, transparency principles at all levels and well-developed procurement systems have allowed it to contribute to the promotion of solid systems of governance that underscore state building. However, in a deeply entrenched patronage system like Yemen, this has not been problem free. The Parliament, where the majority of its members are elite community leaders, has several times reluctantly ratified SFD loans as they have been seen as a threat to their patronage role in their constituencies. While SFD has gained recognition by communities and development organisations, this has often not been the case among elites and central government officials.

Four factors are argued[86] to have been essential in enabling SFD to implement its development interventions effectively:
[86] Lamis Al-Iryani, Alain de Janvry & Elisabeth Sadoulet (2015) The Yemen Social Fund for Development: An Effective Community-Based Approach amid Political Instability, International Peacekeeping, 22:4, 321-336
- Ownership: A demand-driven approach allows the establishment of direct links with communities and the creation of community ownership of SFD projects.
- Trust: SFD’s political neutrality has been established through objective and transparent resource allocation procedures. Such perceived neutrality has earned SFD the trust of populations and continued access to the most difficult places in spite of tribal conflicts and insecurity.
- Flexibility: A flexible mode of funding allows SFD to respond to communities’ changing needs and to sustain projects in spite of crisis conditions.
- Relevance: The quality and importance of its interventions for the lives of beneficiaries has given SFD visibility, recognition and support among stake- holders, the government and donors.

Microfinance: Mixed
A 2014 review of existing evidence of microfinance showed that the impact is mixed, not up to date and reliant on SFD’s own assessments. SFD reported a positive impact on micro finance beneficiaries[3]. Its assessments (in 2003, 2006 and 2009) suggests this increased people’s income, improved their living standards, empowered women and created more job opportunities for communities.  SFD (2008) that conducted a market study on women reported that most of women microfinance clients are engaged on a very small scale of activities, most of them are home based enterprises. The chances for working outside are limited. However Aliriani (2002) reported that microfinance has reached only to a few poor people. Reasons for this include lack  of  experience,  economic instability, culture barriers, scattered population & inadequate infrastructure. This was reinforced by an IFC study (2007) suggests a promising market for microfinance in Yemen but dependent entirely on the education of clients, loan facilitation and finally training and consulting clients. There are a number of areas that could improve operationally. Alshami et al (2013) proposed a conceptual framework in the role of Malaysian and Yemeni Microfinance on the poor wellbeing and provided guidelines on how to improve the sustainability and outreach of MFIs. In another paper the World Bank (2013) reported that Yemen lags in innovation comparing to other regions.
[3] Alshebami and Khandare (2014). Microfinance_in_Yemen_Challenges_and_Opportunities, International Journal in Management and Social Science, Vol.2 Issue-12 https://www.researchgate.net/publication/299283487_Microfinance_in_Yemen_Challenges_and_Opportunities

SWF

Cash transfers: Limited
Yemen-specific evidence on the impacts of CTs is limited. The quality of design and implementation, local context and the presence and impact of complementary services and benefits are all important predictors of success and, to date, these have not been evaluated in Yemen. Given the limited evidence base, the fact that the SWF is currently not functioning as originally set up, and much of the evidence is prior to the latest conflict, findings should be used cautiously.

The European Commission funded an independent evaluation of SWF in February 2012[87]. It concluded that CTs do reach the beneficiaries in Yemen, however not always in the right amount. The more remote and rural areas, the more difficult it was to reach beneficiaries through advanced bank and/or post office systems. In these places cashiers are instructed to transmit cash to the beneficiaries. The SWF estimated that at least 70% of beneficiaries receive their money through cashiers. The 30% are those living in urban areas and receive their money in the post office or the bank. The study also found a number of operational areas where SWF could benefit from efficiency and reform, such as the operational estimate budget and human resources management policy. A recent study from 2012 concluded:[88]
[87] See: https://ec.europa.eu/europeaid/sites/devco/files/evaluation-of-eu-cooperation-with-yemen-vol-ii_en_0.pdf
[88] Transforming Cash Transfers: Beneficiary and community perspectives on the Social Welfare Fund in Yemen. Thabet Bagash (Interaction in Development), Paola Pereznieto (ODI), and Khalid Dubai (Interaction in Development). ODI, December 2012.
1. Health shocks pushed people into vulnerability and poverty. Despite the Social Welfare Law exempting beneficiaries from payment for social services – this was not the case in practice The high costs of medicines and operations forces people to sell assets or take on debt.
2. Awareness of the programme and its operations was low for beneficiaries and non-beneficiaries alike. Community leaders were key in sharing information but this raises risks of elite capture.
3. The cash transfer has a low purchasing power but was viewed as better than nothing with impacts varying. In 2012, the cash was equivalent to $56 per quarter for a family of 6. Beneficiaries and non-beneficiaries would like to see the value increase but agree it is better than nothing. Perceptions were that it had limited but positive impact, which varied depending on the context and on vulnerability[89].
  [89] For example, HHs count on the cash to pay for essential services (in Hodeidah mainly water and electricity), the money was said to enable extra spending capacity when the transfer coincided with special occasions or times of need (Ramadan) and the beneficiary card is mostly used as a guarantee to borrow money or buy goods. Some widows said that the cash contributed a little to their independence and decreased reliance on men. People from marginalised groups felt cash assistance made them feel they were being recognised as being part of the community.
4. There is demand for scaling up SWF coverage. There are many who had applied for the scheme but not yet been processed and there are also those who are eligible but who have not accessed the SWF for various reasons, as well as a large number of poor individuals and families who do not fit the SWF’s categories or its criteria for cash assistance.
5. SWF is a safety net and given current coverage and transfer levels would have limited impacts on poverty at a national scale. In 2012, some 4m HHs were considered poor. This number has increased during the current crisis. There is a need to address the urgent crisis now while looking to build pathways for financing and sustaining the broader SP system in Yemen.

The 2013 the Yemen National Social Protection Monitoring Survey (NSPMS) showed that at least 70% of SWF beneficiaries depended on cash transfers to purchase food and strengthen their livelihoods, cash assistance prevented vulnerable households from resorting to negative coping strategies, and social cash transfers helped beneficiaries to improve their access to basic social services, including health, nutrition, water and sanitation, and education.

The Q1 review of the World Bank/ UNICEF support to SWF beneficiaries in January 2018 identified a number of key challenges and their mitigation:
1. Limited capacity of service providers. Some local consultancy firms have exhibited limited capacity particularly in terms of beneficiary verification and grievance redressal. To address this, UNICEF needed to expand its capacity to provide hands-on support to these service providers. UNICEF also is exploring working through INGOs with expertise in managing similar operations and will also rebid to approach more competent service providers and will continue to engage a wide network of social workers with previous experience with CT beneficiaries that exist in all districts.
2. Identity verification gaps. The payment process requires that beneficiaries provide one additional document of identification (such as a national ID card, electoral card, passport, student ID, or disability ID - in addition to the SWF beneficiary card). It was determined that cross-checking identity verification was required as the SWF beneficiary card does not include adequate security features. About 90 percent of beneficiaries on the SWF list were verified during Q1 payment and more are expected to be verified during Q2 payment. However, there are many reported cases of beneficiaries who do not have the required documents. To address this issue, UNICEF is currently preparing for the use of community validation of identity with support from INGOs. It is expected that the process of validating beneficiary identification will help in further cleaning up the national program database.
3. Engaging the Social Welfare Fund (SWF). To date, UNICEF’s collaboration with SWF has included: approval for UNICEF to use the SWF beneficiary list; UNICEF backup of the cleaned beneficiary list on SWF server at YemenNet; engaging volunteer social workers in the field facilitation process; and information sharing and collaboration in resolving some access challenges at the national level. It is anticipated that UNICEF will start engaging SWF at the technical level to ensure that they are engaged in activities that complement payment and delivery processes and can be used to strengthen the SWF in the future; as well as maintain access support functions at the national level. Additionally, the clean list of beneficiaries after completing identity verification will be transferred back to the SWF database.

Contracted TPM reviewing the Q1 SWF payments showed that:
- A total number of 1.33 million households received first Q payment of 1.58 planed/expected (84%).
- Of these, 44% were direct females recipients.
- 83% of surveyed female recipients and 93% of the male reported they used the CT for food, medicine and repayment of debt.
- 79.5% of the beneficiaries received their cash within the first visit to the payment centre.
- 85.7% of the local actors and leaders interviewed believed the project helps the Yemeni people.
- 97.6% of beneficiaries reported they received the right amount of cash entitlement.

Figure 1: Geographical distribution of SWF beneficiaries (based on Q1 payments made in Jan 18)

Source: World Bank Presentation to Development Partners, January 2018

Endnotes