Type of Review: Project Completion Review

Project Title: UNDP Strategic Partnership Phase II - South Sudan component

Date started: 1st July 2009	Date review undertaken: 1st June 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
DFID committed to make a contribution of £15 million to the SPII programme over a period of two years (July 2009 – March 2012). This support was provided through the DFID Sudan Office, while the SPII programme was set up as national programme, with one unified management and funding structure. However, with the declaration of independence of South Sudan on 09 July 2011, the SP framework was split between both the countries with focus on supporting governance and rule of law in South Sudan. / A first tranche of £5.0 million was disbursed in November 2010, half of which was spent in South Sudan. Later, in December 2011, a separate funding arrangement was signed with UNDP South Sudan and the commitment for South Sudan was reduced from £5.0 million to £2.5 million, which was released in the same month. Thus in total £5 million was disbursed and spent for the SP-II programme in South Sudan. / The first iteration of the Strategic Partnership, which began in 2005, was initially devised as a method of the UK providing programmatic support to a UNDP that DFID perceived as under-performing at the time. However by the time the SPII began, the support provided by the UK was almost exclusively financial.

What were the expected results?
The Strategic Partnership was a mechanism for providing support to UNDP across a range of programmes. As such the expected results were very broad based. According to the logframe the intended impact of the project was: / Strengthen governance and rule of law within the overall framework of supporting peace in South Sudan. / The intended Outcome was: To strengthen democratic governance and equitable delivery of public services through capable, accountable and responsive government, State and local levels, resulting in a reduction in poverty. / The objectives of the SP II as a funding vehicle were: / Provide strategic support to the UNDP Governance and Rule of Law Programme / To provide a more predictable resource base, which would allow UNDP and its partners to move away from ad hoc project-oriented interventions to a more integrated and strategic programmatic approach / Promote development effectiveness through better strategic coordination and the simplification and harmonization of procedures and reporting between UNDP, the government counterparts and funding partners / The focus of UNDP’s governance and rule of law programme in South Sudan was twofold: / Support to processes of democratic governance: the main elements of UNDP’s support included: (1) capacity development of GoSS and civil society actors to administer, finance and participate in free and fair elections as part of a broader democratization agenda; (2) increase accountability mechanisms through strengthening the capacities of South Sudan Legislative Assembly (SSLA) as well as of the 10 state assemblies to implement standard parliamentary procedures and oversight functions with a special focus on the empowerment of women and potential women’s leaders; (3) capacity development of political parties, civil society and media to enhance participative processes and empower diverse communities, especially women, to enable them to efficiently access government goods and services. / Support to decentralization: the main objective was to support the process of devolution of power through decentralization as stipulated in the CPA and to support equitable and gender-sensitive wealth distribution from central to local levels to maximize the development impact at the community level. This included: (1) strengthening policy coordination & target setting at state level; (2) strengthening the financial legal framework for resource mobilization; (3) strengthening local processes for effective planning and public expenditure and (4) strengthening institutional capacities for data collection, conflict and gender sensitive policy analysis, and evidence-based planning and budget execution.

What was the context in which UK support was provided?
The Strategic Partnership (SP) framework was originally created in late 2005 as a two-year co-financing partnership between UNDP, the Government of National Unity, the Government of Southern Sudan, the Government of the Netherlands, the UK Department for International Development (DFID) and the Danish International Development Agency (DANIDA) in support of the UNDP Governance and Rule of Law Programme in Sudan. / According to DFID staff members interviewed for this PCR, at the time the original agreement was made few development organisations were operating in South Sudan and UNDP was the only organisation with the capacity to undertake the work required on governance and rule of law. However, it is reported by DFID staff members that UNDP was at that time underperforming in its role. Faced with a lack of alternatives DFID suggested the Strategic Partnership arrangement as a way of providing more support for UNDP as well as bringing the Government of Southern Sudan to the table and working cooperatively. / The framework underwent an external evaluation in mid-2007 and, following the review’s recommendation, the original framework period 2005-2007 was extended until June 2009 and the Swedish International Development Agency (SIDA) joined the SP in 2008. / A second phase of the programme (II), and the subject of this review, was agreed covering the period between 1st July 2009 and March 2012. The focus of the second phase was primarily on UNDP’s rule of law programme. / The UNDP SP II was set up as a national programme, with one unified oversight, management and funding structure. With the South Sudan independence on 9 July 2011, the SP Steering Committee decided to split the SP framework into two separate frameworks for the two countries. In July 2011, the only agreements on SP that were active were DFID and Govt. of Netherlands, however, post-independence, with the split to independent structures, DFID contributed £2.5 million to the South Sudan programme whereas the Netherlands decided to withdraw their support.

## Section A: Detailed Output Scoring

Output 1: Institutions, systems and processes of democratic governance strengthened
Output 1: final score and performance description: B / Indicators and Results: / It should be noted that although UNDP is able to claim all of the results below, the results that are under indicators 1.1, 1.2 and 1.3 were not funded by the SP. They were UNDP activities funded outside of the SP. / % of State / National parliamentarians with increased knowledge of their role and responsibilities (disaggregated by state and gender) (Target = 100%) / Results: Partly achieved. UNDP conducted training of national parliamentarians but the impact of this training on increasing knowledge of parliamentarians is unclear / Eleven trainings were organized following the April 2010 elections for the legislative assemblies at the national and state levels to orient them on their legislative, executive oversight, and representational functions. A total of 606 members of the legislative assemblies (including 159 women) attended the training. No information exists as to the impact of this training. / UNDP also supported the national Ministry of Parliamentary Affairs to hold the fifth Speakers Forum. Members of both the SSLA and 10 SLAs attended the forum. The forum discussed and provided inputs on the contentious issues in the draft interim constitution as well as other governance challenges facing South Sudan in the run up to and immediately after the declaration of independence. / Number of media entities enabled to report on government business and decision-making (Target = 20) / Results: Partly achieved. UNDP conducted training of journalists but the impact of the training on their ability to report on government business and decision making is unclear. / 140 journalists from Southern Sudan were given training. 12 media houses were provided with professional media journalists to mentor the process. UNDP reported positive changes including strengthened reporting capacities and network formation. / Level of capacity of 10 state-level committees and Southern Sudan High Committee (SSHC) to conduct peaceful and credible election (Target = 10 Committees and SSHC enabled to carry-out their functions without external support) / Results: Achieved. / National Elections Commission set up a fully functional South Sudan High Committee and also 10 State Committees in the South. The functioning of the committees was critical for the conduct of the election as evidenced by the outcome of election. The elections were assessed as; peaceful and the conduct of polling administered satisfactorily in 70% of the areas (EU Observation Mission). / Number of CBOs enabled to undertake civic and voter education (Target = 25) / Results: Achieved. / For elections a total of 46 NGO grantees were supported, which included 35 small grantees, 6 medium grantees and 5 conflict mitigation grantees. / For referendum, support was extended for 149 NGOs, which included 133 small grantees, 9 medium grantees, 5 innovative grants and 2 conflict mitigation grants. / Additional activities undertaken with SP funding under Output 1: / Although these activities are not directly related to the DFID indicators they were funded under the SP and do make a legitimate contribution to Output 1 and the Outcome of the SP. / 2009 / Under the Good Governance and Equity in Political Participation project UNDP focused on strengthening the capacities of women leaders and institutions impacting on women’s political participation. According to UNDP “the major outcome of the project in Southern Sudan is increased gender sensitivity and in women’s awareness of policy issues”. / 2010 / 606 members of the Southern Sudan and State Legislative Assemblies (159 women) received induction training after the April 2010 general elections. One key result of the training was the increased capacities of the legislative assemblies to review and discuss the 2011 annual work plans and budgets presented by the State Ministries of Finance. / In four out of the ten states (Central Equatoria State, Eastern Equatoria State, Upper Nile and Western Bahr- el-Ghazal), the legislative assemblies were able to approve the 2011 work plans and budgets before the end of 2010. / 2011 / Support to the Office of the President in enhancing its capacity to implement the Government of South Sudan policy, as well as enhancing the human and institutional capacity of the Office to support the President in achieving his mandate.
Final results: / Activities against the indicators in this output were funded from outside the SP. Judging solely on these indicators, UNDP has delivered some progress towards Output 1 with 2 of the indicators being achieved and 2 being partially achieved. On the basis of this, the overall progress towards this Output is therefore a B. Since the activities were undertaken outside of the SP framework, the successes cannot be considered strictly as an SP result, however they contribute to achievement of the overall Output statement and the Outcome. / There were other activities funded under the SP that contributed to this output but that was not part of the original logframe or the SP, such as support to the Office of the President. So although they may be judged to contribute to Output 1 as a whole and to the Outcome of the SP, they do not contribute specifically to DFID’s stated indicators. / The fact that UNDP as a whole achieved successes under some of the indicators, though not through SP programme highlights both a strength and a failing of DFID’s SP with UNDP. The strength is that because the activities relating to the indicators were already being undertaken by UNDP using bi-lateral funding, it was possible to channel the SP funding to other activities that lacked resources. The failing is that it appears neither UNDP nor DFID responded to the situation by altering the logframe accordingly and considering a revised strategy. / It is of concern that UNDP is able to report on the quantitative outcomes of activities but there is little information available on the qualitative impact making it hard to assess some parts of the indicators. For example for indicators on building capacity of parliamentarians and the media there is information on the number of training sessions run but nothing on the impact this has had on attendees. Poor reporting by UNDP contributes to the confusion surrounding this Output. In its 2010 SP Annual Review UNDP reports that its two main national programmes were under this output - the support to the electoral process in Sudan and the support to the Southern Sudan Referendum – but these were funded outside of the SP framework. These indicators were also included in UNDP’s revised SP II framework for South Sudan. / Impact Weighting (%): 35% / Revised since last Annual Review? Y / During the last Annual Review there were four outputs. The fourth output has been removed as the programme was split into Sudan and South Sudan and as a result the impact weighting has been shifted to approximately equally distribute the weighting among three outputs. / Risk: Medium / Revised since last Annual Review? N

Output 2: National/sub-national/state/local levels of government expand their capacities to manage equitable delivery of public services
Output 2: final score and performance description: B / Indicators and Results: / Number of CBOs influencing government decision-making processes on women’s issues (Target = 35) / Results: Not assessed. / UNDP reports that this indicator falls outside of their own framework and therefore there are no results to report, in the last annual review it was recommended that this indicator should be removed from the logframe although this change was never made. / The number of state budgets prepared through consultation and are ready for presentation to the SLAs for approval (Target = 10) / Results: Achieved. / All ten states completed their 2011 Annual Work plans (AWPs) and budgets. UNDP specialists provided support to the State Ministries of Finance (SMOF) in the preparation of the Appropriation Bills that were presented to and consequently passed by the State Legislative Assemblies. / Number of states that include payroll cleaning activities in their Annual work plan and budget (Target = 5) / Results: partially achieved. / Two states – Central Equatoria and Northern Bahr el Ghazal included payroll cleaning activities in their 2011 budgets and work plans (which were compiled in 2010). A number of other states are also implementing payroll cleaning activities, but were not included in the work plans and budgets. / Number of counties enabled to plan budget (Target = unspecified) / Results: Achieved. / In 2011, support was provided to the State Ministries of Local Governments and counties to finalize the 2011 budgets. As a result, 79 counties had their 2011 Budgets completed in time with the accurate amount and uses of County Development Grants (CDGs). / Additional activities undertaken with SP funding under Output 2: / Although these activities are not directly related to the DFID indicators they were funded under the SP and do make a legitimate contribution to Output 2 and the Outcome of the SP. / 2009 / The main focus under this output was support to decentralization, as stipulated in the CPA, and was focused around training. UNDP strengthened the capacity of 10 Budget Sector Working Groups in the strategy and planning of their Budget Sector Plans. A workshop was held to ensure that budgets were aligned with state and county level budget planning; / Four interns from Harvard University were assigned to different Budget Sector Working Groups to assist the MoFEP in drafting the budgets. / 2010 / Referendum Task Force established, providing technical advice and support to the Office of the President on referendum-related matters / GoSS Priority Core Governance Functions action plan developed / Rapid Capacity-Placement Initiative (RCPI) rolled out: 93 UNV recruited and placed in government institutions at GoSS and State level / Preparation of the Southern Sudan Development Plan initiated / 2011-2013 Budget Sector Working Group planning and budgeting exercise initiated and guidelines for the planning exercise developed / 2011 Budget Sector plans developed and approved / Aid Information Management System installed and populated with relevant donor data / Quarterly Donor/GoSS Fora held / National Baseline Household Survey Report for Southern Sudan finalized and published / Southern Sudan MDG Report finalized and launched / 2010 plans and budgets for all states finalized and approved by the State Legislative Assemblies / Draft 2011 plans and budgets finalized for all states, out of which 50% were approved by the State Legislative Assembly (Central Equatoria, Eastern Equatoria, Upper Nile, Northern Bahr el Ghazal and Western Bahr el Ghazal) / State Revenue Collection strengthened in Northern Bahr-el-Ghazal and Lakes States: / State Revenue Authority established in NBeG / Bill for establishment of a State Revenue Authority passed in Lakes State and a Revenue Task Force has been set-up tax collection increased by 300% in NBeG State / 14 low cost housing units were completed in five states (Central Equatoria, Eastern Equatoria, Jonglei, Northern Bahr el Ghazal and Western Bahr el Ghazal) by the end of 2010 / 8th Governor Forum held from 26-30 October 2010 in Juba, bringing together the Governors of all 10 States of Southern Sudan / All 74 counties drafted their 2011 plans and budgets / One Commissioners’ Forum held in each state, with the participation of Commissioners, County administrators, technical staff, traditional leaders, Ministry representatives and other stakeholders. / 2011 / Supported the Ministry of Finance and Economic with an embedded cadre of senior advisors assisting the Ministry in budgeting and planning / Three regional workshops and a conference in Juba to consult for the South Sudan Development Plan / Installation and training in use of the Aid Information Management System (AIMS) / Support to the preparation, printing and launching of the 2010 Statistical Yearbook / Support to the 2011 Governors’ Forum / Organisation of a study tour to Ghana for three state governors and undersecretaries from the Office of the President and Ministry of Parliamentary Affairs to gain better understanding of decentralization and fiscal arrangements / Provision of advisors at state level to assist in planning budgeting and financial management and completion of Annual Work Plans / Provision of planning specialists to support in drafting of state plans for the integration and reinsertion of returnees Northern Bahr El Ghazal, Western Bahr El Ghazal, Warrap, Central Equatoria and Eastern Equatoria / Two consultancies undertaken in the Office of the Presidential Advisor on decentralization / Support to urban planning in the states / Through the Local Government Recovery Project support provided to the formulation and implementation of policies and guidelines for improved local governance / Training of 84 local government officers in three-week Training of Trainers session on Public Financial Management
Final results: / The key activity under this output was the provision of up to 125 UNVs in government institutions at both national and state level. UNDP staff members were also embedded as programme advisors in government institutions. As part of the review process senior staff from some of these government institutions were interviewed with regard to the impact of the UNDP advisors. Some were extremely positive about the support provided, for example the Director for Labour and Public Service in Jonglei State listed numerous specific achievements attributable to the UNDP advisor and commended the on-going mentoring of staff provided by the advisor. However in several cases the government interviewees complained that the UNDP advisors did little more than act as an additional member of staff in the ministry, carrying out tasks that were assigned to them by the Ministry but not building the long-term capacity of the institution or its staff by providing mentoring or on-the-job training. In many cases it was concerning that the advisors seemed to be little more than glorified administrators, for example ensuring that the institutions’ publications were well presented but having little influence on the content or the policy around them. / According to one donor representative, budget cuts meant that there were more regional and national advisors and fewer international advisors than originally planned. This was problematic because it is more difficult for a national UNV to take a hard line with the institutions it is supporting and to pass on difficult messages. The same person claimed that many of the UNVs, in their late 30s, were too young to be advisors or to be taken seriously. The above criticisms notwithstanding, UNDP should be commended for providing such a degree of support at the state level. / Possibly one of the greatest successes under this output was the support to the Governors’ and Commissioners’ Forums that provided the opportunity for genuine decentralised politics to flourish. However, the Governors’ Forum has been criticised for being driven by an agenda set by the offices of the President and the Vice President. / In many cases it is unclear which of the achievements can be specifically attributed to UNDP and the SP. For example indicator 2.3 refers to payroll cleaning activities and in the SP Annual Report 2011 the UNDP cites the implementation of the electronic payroll system in two states as an SP success. However the introduction of the payroll systems was carried out by another organisation under the Joint Donor Office’s Capacity-building Trust Fund (CBTF) and UNDP advisors only assisted with the implementation. Such collaboration is an example of two complementary DFID-funded programmes working together for the best results for the beneficiary; however it highlights the difficulty in ascertaining exactly which activities were undertaken through SP funding. / It is concerning that UNDP reports that indicator 2.1 falls outside of their framework and therefore they are unable to report on it. This is an issue that was picked up in DFID’s last Annual Review of the SP and at that time the recommendation was made to remove it from the logframe. This recommendation was not acted upon. / Impact Weighting (%): 35% / Revised since last Annual Review? Y / During the last Annual Review there were four outputs. The fourth output has been removed as the programme was split into Sudan and South Sudan and as a result the impact weighting has been shifted to approximately equally distribute the weighting among three outputs. / Risk: Medium / Revised since last Annual Review? N

Output 3: Rights upheld and protected through accountable, accessible and equitable Rule of Law institutions
Output 3: final score and performance description: C / Indicators and Results: / 3.1 Number of counties with functioning courts in South Sudan (Target = 78) / Result: partially achieved. / UNDP has supported the Judiciary of South Sudan in the establishment of 39 county courts across all ten states. It has contributed to the planning of 10 high courts, one in each capital of the ten states. / Under the SP UNDP also undertook the construction and rehabilitation of the Raja County Court and Yambio High Court. A high court was constructed in Bor, in part using SP funding. / UNDP supported the development of four-year action plan (2011-2014) for the Judiciary of South Sudan, which was incorporated into the South Sudan Development Plan. The action plan provides strategic direction and allows for better coordination to strengthen the functioning of the high and country courts, as this has subsequently enabled the development of a comprehensive capacity development plan for judges and support staff. / 3.2 Number of counties with a functioning police infrastructure (Target = 40) / Result: Unknown. / UNDP has been unable to provide any results against this indicator despite repeated prompting and despite police construction of police infrastructure being an SP activity. / 3.3 Number of people accessing Justice services through Justice Confidence Centres (JCCs) (Target = 500,000) / Result: Substantially underachieved in relation to the target of 500,000. However in this instance it may be that the wording of the indicator is not exactly as intended. The population of South Sudan is only 9 million so it is unrealistic to expect that 500,000 people would be accessing the JCCs. Perhaps a more appropriate indicator would have been “500,000 people with access to the JCCs”. / In total about 2,500 people have used the JCCs in 2011. The Juba JCC has been providing legal aid clinics by giving general legal advice and providing legal information including conducting mediation. / Additional activities undertaken with SP funding under Output 3: / Although these activities are not directly related to the DFID indicators they were funded under the SP and do make a legitimate contribution to Output 3 and the Outcome of the SP. / 2009 / Training in awareness of legal rights and providing legal assistance to 208 police officers, 68 CSO representatives, 57 lawyers and 31 traditional chiefs / Monthly rule of law forums held in nine locations / Quarterly rule of law forums held at GoSS level / Capacity development for the Ministry of Legal Affairs and Constitutional Development including facilitating 26 Ministry legal counselors on a two week course in common law in Kampala. / Construction of a two story law library in Juba / In collaboration with other UN agencies establishment of 9 Special Protection Units / Road safety campaign initiated to support community policing: march held, performances given, 300 traffic control police officers trained (10 from each state), equipment including computers for managing road safety data provided. / 2010 / One training manual was developed in December 2010 for the training of Traditional Authorities which incorporates human rights standards. This standardized training. Manual will be used for further training of Traditional Authorities / Customary law study tour for 10 persons conducted to both Mozambique and Lesotho in 2010 / Construction of customary law research centre in Rumbek / Recruitment of consultant for research on customary law ongoing / 10 trainings for traditional authorities completed / construction works for the judges’ residence of the Court of Appeal Judge for the Greater Upper Nile (Malakal) Circuit been completed and handed over to the Judiciary in February 2010 / Renovation and construction works on the High Court in Yambio with 2 new holding cells was completed in June 2010 and the Judiciary has since moved into the building / Significant improvements were made in 2010 towards in ensuring the compliance of prisons in Southern Sudan with minimum prison standards / UNDP has completed the construction of four prisons in four states including Jonglei – phase 1&2, NBeG, Lakes, Central Equatoria / Construction of five prisons is ongoing in five states including Jonglei, Western Equatoria, Central Equatoria, Upper Nile, and WBeG / UNDP has also provided training to 630 Police Officers on different topics including Special Protection, Critical Incident Management, Basic Police Training, Asset Management and Finance / 10 Human Rights state offices supported with a laptop, Zain modem, office desk and chair / 20 Human Rights monitors trained on computer applications / Provision of basic equipment (20 computers, 20 chairs and desks) and supplies to Human Rights Commission / Human rights monitoring database developed to monitor rights violation and reporting. / 2011 / Through the component of the Support to Police and Prisons Services project against which SP contribution was applied, UNDP supported: the rehabilitation and/or construction of police facilities; the institutional capacity building of the Police Service; and community based support to Police Service. This included: Three payam police stations rehabilitated/constructed, furnished and equipped; nine Special Protection Units (SPUs) constructed and received office equipment; specialized training for Police officers in logistics and asset management, personnel registration, community policing, and criminal investigation / Construction of Bor High Court. Completed in November 2011 / 23 human rights awareness trainings conducted in nine field locations for CSOs and personnel of rule of law institutions / Small grants of $15,000 each given to 4 CSOs to operate Justice and Confidence Centres providing legal information and advisory services to the public. Around 3,800 people have benefitted from information provided / 56 rule of law fora conducted across nine states. 1725 rule of law actors reached. Served to identify key issues and challenges in the rule of law and justice sector / Rule of Law officer collocated at the Human Rights Commission and seven officers advising at state level offices / 27 trainings delivered using the customary law training manual developed by UNDP / Customary law resource centre constructed in Rumbek.
Final results: / The results under Output 3 fall short of the stated indicators. It is concerning that in the case of indicator 3.2 UNDP is unable to provide any information on results, although this is one of their own indicators. In the case of indicator 3.3, poor wording has created an unrealistically high target. This should have been spotted by both DFID and UNDP at an earlier stage. / Numerous other activities have been completed under Output 3 but it is concerning that many of these appear to oriented around events and numbers rather than achieving a genuine improvement in a given area. A good example would be the 2009 road safety campaign. It is difficult to see how a march and a performance with music and poetry could possibly contribute to improved road safety in South Sudan. Furthermore, providing traffic control training to 10 police officers from each state appears to be a tokenistic gesture of inclusion rather than a rational decision, given that the vast majority of traffic police are based in Juba. / Similar comment can be made about the infrastructure projects. The UNDP Annual Report 2011 for the SP indicates that the High Court in Bor, completed in November 2011, was ready for hand-over to the local authorities in February 2012. However when the reviewer visited the court building in June 2012 it had not yet been handed over or used, and deterioration due to lack of caretaking was already evident. UNDP staff explained that the lack of use of the court is a result of the building not yet being certified for use by the local authorities. They anticipated it would be late July at the earliest before certification would take place. Furthermore the lack of access to the court was of great concern; it is built in a field away from the main road and currently the only way to access it is by 4x4 or on foot. In times of heavy rain it will be almost completely inaccessible. It should however be noted that the local authorities in Bor expressed great satisfaction with this a tangible output produced by UNDP. / Another organisation working on rule of law issues throughout South Sudan commented on similar lack of planning with some of UNDP’s police stations and Special Protection Units, citing cases of facilities that had been built in areas with poor access and little or no water supply, meaning that they remained unstaffed and ultimately abandoned. / The finessing of results in some of UNDP’s reporting is concerning. For example, UNDP reported to DFID that it “has contributed to the foundation of 10 high courts” however on further investigation it is clear that this consisted of visiting four potential sites and preparing architectural drawings and advertising the Invitation to Bid. To call this a “contribution to the foundation” is a generous and somewhat misleading description of the progress made. / A more substantive critique of the approach under Output 3 is that it relied too heavily on working with authorities and there was very little engagement with civil society. For rule of law institutions to be accessible, equitable and accountable civil society must be equipped to understand, engage with and challenge them. In the UNDP programme of work under Output 3 the civic engagement component appeared to involve little more than the training of local chiefs, with no guarantee that the information would trickle down. The Justice Confidence Centres exist to provide consultations to members of the public but are not proactive in disseminating information. / Impact Weighting (%): / Revised since last Annual Review? Y / During the last Annual Review there were four outputs. The fourth output has been removed as the programme was split into Sudan and South Sudan and as a result the impact weighting has been shifted to approximately equally distribute the weighting among three outputs. / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results
Has the logframe been changed since the last review? Y / The logframe has changed since the last Annual Review because that review used the pre-independence logframe, which included activities in the north. / When the SPII began, South Sudan and Sudan were one united country, therefore the entire programme was run from Khartoum and reporting was made to the DFID office in Khartoum. When South Sudan seceded in July 2011 SPII split into two separate programmes for Sudan and South Sudan. At this time new logframes were created. / In the course of this review it has become clear that there has been a great deal of confusion as to which logframe was being used in the post-independence South Sudan programme. DFID staff members claim that they agreed a revised logframe with UNDP in late 2011 however UNDP staff members appeared not to have seen the logframe and say they were never presented with it. As a result, in some cases UNDP have not measured progress against the DFID indicators. / 1.2 Final Output score and description: / The final Output score for this project is a B which means overall the Outputs moderately did not meet the expectations. / Output 1 and 2 moderately did not meet expectations and output 3 substantially did not meet expectations.
Direct feedback from beneficiaries / Although the ultimate beneficiaries of the SP should be the people of South Sudan for the purposes of review the beneficiaries may be understood as being the government institutionsthat were supported in the SP. / Most interviewees were grateful for the support provided by the programme although many expressed a degree of doubt as to the value of the technical advisors. / In South Sudan responding to the beneficiaries’ stated needs while not indulging requests for capital “statement” projects is often a difficult balance to strike. In Bor some of the officials interviewed claimed that the money spent on providing UNDP advisors to local government would have been better spent on building more facilities for the government, yet the High Court that UNDP had completed eight months earlier was still unused and local authorities had failed to provide the access route to the court that UNDP claims was promised. Other officials interviewed claimed that local authorities don’t need advisors; they need capacity building. When questioned further, “capacity building” in this context was understood to be training over an extended period. One official cited the three months of training that the state revenue collectors had undertaken at a training facility in Uganda as the single most important factor in increasing revenue collection in his state. Unfortunately this training was not funded by the SP.
1.4 Overall Outcome score and description: B / The anticipated outcome according to the DFID logframe is: / To strengthen democratic governance and equitable delivery of public services through capable, accountable and responsive government, State and local levels, resulting in a reduction in poverty. / UNDP presented the following responses to the Outcome Indicators: / Outcome Indicator 1: Level (%) of knowledge and understanding of the political system among citizens (target 60%) / A survey was conducted to measure citizen’s knowledge about electoral process. The statements from International Observers show that, though civic education was well-presented with clear messages, it was too little and too late to make a real contribution to voter understanding of the complex and unfamiliar electoral process. / In the case of the referendum a survey was conduct and almost three-quarters (74.8%) of the sample have correct knowledge regarding the starting date and purpose of the referendum that took place on 9th January 2011. Also over 90% of the sample surveyed registered to vote in the referendum. / At the baseline only 20% of those surveyed showed a basic understanding of the electoral system and the above results would suggest improvements in this understanding. Some of the activities that UNDP have undertaken may very well have contributed, but we should be cautious when looking at these results. The measures described here; purpose and starting date of the referendum as well as choosing to vote do not tell us nearly enough about citizens understanding of what is a complex political system. More assessment is needed to test comprehensive understanding of the political system. / Outcome Indicator 2: % of citizens who have confidence in Rule of Law institutions (75%) / UNDP plans to conduct comprehensive survey in 2012 to document information on the indicator. / Outcome Indicator 3: % of citizen satisfied with local public services in target areas (Over 65%) / UNDP plans to conduct comprehensive survey in 2012 to document information on the indicator. / Only one of the outcome indicator can be assessed. UNDP have not yet collected the information that will allow assessment of two out of the three indicators. But as can be seen from Section A of this PCR, there were dozens of activities that were not part DFID output indicators that contributed to the achievement of the Outcome undertaken using SP funding. In fact the activities related to the DFID indicators represent only a very small portion of all of the activities undertaken with SP funding. Therefore the overall results of outputs of the SP are greater than would it would appear using the logframe indicators alone The lack of a theory of change also means that for some of these other activities there is little explanation as to why they were undertaken and how they fit into the result chain rational. / 1.5 Impact and Sustainability / Sustainable impacts include: / Systems and structures put in place at national, sub-national and local levels for planning and budgeting have become adopted as key Government processes. These processes are no longer entirely dependent on donor support. / Governor’s Forum which is the only annual event that brings together the key Government officials from across South Sudan (the Executive, State Governors and Ministers) and key partners, has continued to be considered as the key event where decentralization, security, resource allocation, rule of law and other aspects of governance are discussed. The Governor’s Forum is part of the Government’s annual work plan though might need minimum external support. / The Referendum Task Force formed and supported through the SP (Support to Office of the President Project) was instrumental in the preparation for the conduct of referendum, through organizing experience sharing visits countries that have conducted referendum in the past, and also documenting the lessons learned from the referendum processes, will inform future electoral processes in South Sudan. / Rule of Law Forums established at states level have continued to serve as a local mechanism that bring stakeholders together to address rule of law issues. While UNDP still provides minimum coordination support, the culture of information sharing, tracking of issues and application of rule of law has been expanded and strengthened at the state level. / Infrastructure projects such as the police posts, the library in the Ministry for Justice and the High Court in Bor will serve local communities for many years to come.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / As a flexible fund spread across numerous different projects it was unlikely that the SP was ever going to overspend. Indeed, when DFID chose in November 2011 to halve the amount of funding that it had previously planned to commit (£2.5 million instead of £5 million) activities were simply removed from the programme. / 2.2 Key cost drivers / The major cost drivers included the following: / Inflation in South Sudan / Limited availability of project inputs in the local market and the necessity to import materials / Limited local capacity resulting in a dependence on international experts for delivery of project activities / 2.3 Was the project completed within the expected timescale: Y / As with budget (see 2.1), because the SP was somewhat open-ended in terms of its ambitions there was no specific end goal, therefore staying within the timescale was not a challenge. It is important to remember that the SP was not a project; it was a funding mechanism that existed to fund an open-ended number of activities so long as the money lasted. UNDP reports that the SP activities were completed nine months before the agreed end date of the SP period.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / According to interviews with DFID staff members, the SP was designed in the context of an under-performing UNDP. The model for the purpose of the SP still holds true; UNDP continues to undertake activities in the realm of governance and rule of law yet in many of the activities the substantive impact is unproven the UNDP monitoring and evaluation system has not provided the information required to adequately assess progress against many of the indicators. UNDP would benefit from closer coordination with donors and with the Government of South Sudan to ensure that the activities that it is carrying out are relevant and effective / Activities undertaken as part of the SP were impacted by changes in evidence in the following manner: / Increased insecurity in some of the states negatively impacted on the speed with which some of the projects could be completed. / Separation of South Sudan resulted in the splitting of the SP framework. This has contributed to the challenge described under the response to Question 2 above. / Delay in releasing funds by donors during late 2010 early 2011 resulted in delayed implementation. / 3.2 Set out what plans are in place for an evaluation. / The SP II will be subject to a UNDP evaluation in 2012, assessing the effectiveness of the SP as funding mechanism as well as progress made towards achieving the supported programmatic outcomes.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / According to the Framework Agreement between UNDP and the Government of the UK, UNDP is solely responsible for the administration of DFID financing covered by the Framework Agreement and carries out administration in accordance with its financial regulations, rules and directives. / 4.3 Climate and Environment Impact / The SPII was designed before climate and environmental impact were part of the considerations in the planning process.

5. Value for Money
5.1 Performance on VfM measures / The SP projects were implemented through existing UNDP programme management structure at national, state and county levels so no additional structures were required to be put in place. At all levels, UNDP-funded staff were embedded within Government institutions, sharing Government facilities and services. / Value for money analysis is a requirement for any procurement in accordance with UNDP procurement rules and regulations. While there is always competition to get the least cost, it is also a requirement to determine whether the project input being procured meets the purpose of the project, can be delivered in a reasonable time, and the input meets quality requirement. / XXXX to add following Lydia’s response / 5.2 Commercial Improvement and Value for Money / The commercial practices undertaken through the SP project resources followed UNDP procurement procedure. / This review did not look in detail at UNDP’s procurement processes. Work is being planned by DFID’s commercial advisor to explore these issues in greater detail as part of the Multi-lateral Aid Review follow up. / 5.3 Role of project partners / All SP activities were carried out by UNDP apart from construction. / 5.4 Did the project represent Value for Money : N / The total budget for the SP programme activities in South Sudan was US$50 million. An extra US$4.5 million was budgeted for M&E. Management costs between the Sudan and South Sudan programmes have not been disaggregated in the budget information available, they amount to a total of US$10.8 million, it may be estimated that the South Sudan programme accounts for half of this; $5.4 million. / The UK’s contribution was approximately $7.8 million. / Considering that it is difficult to establish exactly what was achieved under the SP and considering that UNDP is unable to provide results against several of DFID’s indicators despite having a $4.5million budget for M&E, it must be considered that the project did not represent value for money.

6. Conditionality
6.1 Update on specific conditions / N/A / No Financial Aid was directly given to a partner government.

7. Conclusions
The Strategic Partnership may be evaluated by two criteria: / Its success as a funding vehicle / Its success in achieving programmatic aims. / In the first regard the conclusion must be that the SP failed. It has been said many times by interviewees during the review process that the SP was “neither strategic, nor a partnership”. Indeed many of the UNDP staff who were interviewed spoke of the SP as a “flexible fund”, seemingly with no understanding of the SP’s original purpose. / DFID must shoulder some of the responsibility for the failure of the partnership by failing to remain engaged. With just two Southern Sudan-based staff at the time the SPII began in 2009 DFID’s resources were over-stretched and the responsibility for engaging with and monitoring the SP was handed to the Joint Donor Office (JDO). Despite doing commendable work, the JDO did not have the same authority as the donors themselves and therefore was not able to hold UNDP to account in the same way that a donor would have been able to. / The theory behind the first phase of the SP in 2005 was that it would bring donors, UNDP and the Government of Southern Sudan together to work on governance and rule of law projects strategically. However, according to senior UNDP staff, while the GoSS had ownership at project level of many UNDP projects it never had any ownership of the SPII arrangement, and government representation at Steering Committee meetings was only nominal. Many interviewees during the review process have commented that Steering Committee meetings focused more on administrative issues than programmatic or strategic issues. Since these meetings were the most important opportunity for donors and GoSS input to the SP it is concerning that they were not used for strategic purposes. One donor representative interviewed said that it felt like the SP was simply a UNDP vehicle. / However, in the role of a flexible fund the SP was highly successful, enabling funds to be shifted from one programme to the next according to need, reducing the administrative burden between UNDP and the donors. One example would be when DFID decided to make available US$10 million to be spent on UNVs, the SP funding that had previously been intended for that programme was able to be moved to another programme where there was a shortfall. Although the fund was set up as a strategic partnership, by the end of its lifespan it had become, de facto, a flexible pool. While the donors are not happy with this outcome they must share some of the responsibility for allowing it to happen. / Lessons Learned from SPII as a Funding Vehicle / The original decision to set up a “strategic partnership” was taken for the purpose of supporting an under-performing UNDP. If the original intent had been adhered to UNDP would have benefitted from DFID’s support and DFID may have had greater confidence in the SP. In future if DFID sets up an SP it must maintain engagement and commitment to enable the partnership to meet its maximum potential. / In many ways UNDP treated the Strategic Partnership mechanism as a flexible pooled fund. In this context the SP provided UNDP with a vehicle to move funds between projects as and when they were needed without UNDP repeatedly having to return to donors with funding requests. As such it was successful in lowering the administrative burden. / If a Strategic Partnership is to involve the government it must be ensured that the government representatives at Steering Committee meetings are sufficiently senior and empowered to take decisions. / For a Strategic Partnership to succeed Steering Committee meetings must be held regularly and must focus on programmatic issues, not merely administrative issues as this is the key opportunity for all partners to input to the process. In the case of the SPII, Steering Committee meetings were held at most twice a year, which was insufficient. / The DFID advisor tasked with over-seeing the SPII had far too many other duties to commit sufficient time to overseeing the SP. To maintain engagement in a Strategic Partnership of this scale DFID must commit at least 50% of one staff member’s time. / Despite the JDO having competent staff to oversee the SP it was not a sufficient substitution for DFID’s direct involvement. An intermediary such as the JDO cannot wield the same influence as the donor itself. / With regard to the second criterion, the SP’s success in achieving its programmatic aims, this is more difficult to measure, largely due to poor reporting and poor communication. / The first point that is crucial to note in regard to this review is that although the majority of DFID’s logframe indicators are the same as the indicators in UNDP’s own logframe, UNDP appeared to be unfamiliar with the DFID logframe when it was presented at the beginning of the review process and took approximately three weeks to provide very brief responses against the indicators. / Considering that DFID was the sole donor remaining in the post-independence South Sudan SP, agreeing a logframe between the two organisations should have been a simple matter. However it appears that there was a failure to reach a consensus in this regard. As a result, one of the DFID indicators (2.1) actually falls outside of UNDP’s entire work plan. This anomaly was flagged up in the last DFID Annual Report on the SP and a recommendation was made to remove the indicator however this recommendation was not acted upon. / In other cases activities were undertaken by UNDP but not funded by the SP, while numerous activities were funded under the SP that were not in the DFID logframe. This could be viewed as an advantage; one of the SP’s strengths should have been that it was sufficiently flexible to alter its activities according to need rather than simply slavishly adhering to indicators. However during the course of this review it has become clear that DFID had little knowledge or oversight of the activities that were taking place under each output. One donor representative commented that, “It felt like UNDP were running the partnership and didn’t take donor input seriously. We would only receive annual funding plans a day before the meeting.” So although the flexibility of the SP was advantageous, it was not managed responsibly. / With regard to programmatic aims, is important to remember that the SP was not a programme. It was a funding mechanism for UNDP to undertake a series of projects that fell within the scope of governance and rule of law. As such its objectives are somewhat ill-defined. DFID’s logframe outlined a series of indicators, but these represent only a fraction of the activities that could have been, and were, covered under the DFID agreed outcome of “strengthen democratic governance and equitable delivery of public services through capable, accountable and responsive government, state and local levels”. Activities funded under the SP included, for example, town planning, a road safety campaign and support for Governors’ and Commissioners’ forums amongst many others. All of these activities, if carried out well, could have been legitimate contributions to governance and rule of law even though they were not specifically identified activities in DFID’s logframe. / The broad outcome and the similarly broad outputs of the SP were drawn from UNDP’s own Country Programme Action Plan (CPAP). The three SP Outputs in the DFID logframe correspond directly with the wording of the CPAP, therefore reporting on the SP should simply have been a matter of drawing out which activities had been funded by the SP. However UNDP’s reporting was extremely poor and in many cases it was difficult to ascertain exactly which activities were carried out using funds from the SP. For example the 2011 SP Annual Report lists the Commissioners’ Forums as an activity but then at the end of the paragraph it states that the forums never took place due to lack of funds. In the 2010 Annual Report some activities were reported then it is stated that these activities were not part of the SP. Unpicking exactly which activities were and were not funded as part of the SP over the three years is an almost forensic task. / This poor reporting of the SP is not a phenomenon restricted to the review. A donor representative who attempted to monitor the activities of the SP said that: “Getting information out of UNDP was difficult and it was always late”. Another donor complained that at the meetings “UNDP themselves could not show us the successes. We left with a feeling that we didn’t know what had been achieved and what the goals were.” / Lacking a clear theory of change and with poor reporting it is difficult to ascertain exactly what the SP set out to achieve, what activities were funded under the SP, and whether these activities contributed to improvements in governance and rule of law. However, this confusion notwithstanding, during the course of this review some broader successes can be identified: / Support to decentralisation initiatives – The South Sudan Legislative Assembly chose decentralisation as a system of governance at independence. By placing much of its support at state level and building the capacity of local governments, UNDP has supported these decentralisation initiatives. / Induction training for parliamentarians after independence – UNDP used SP funding to provide support to a fledgling government many of whose members had little or no experience in national government. / The Commissioners’ and Governors’ Forums – These forums provide the opportunity for genuine decentralised politics to flourish. / The provision of legal aid via the JCCs – Although the numbers attending the JCCs have been modest to date they are the first example of legal aid being made accessible to the wider population. / The law library in the Ministry of Justice – The library is a well-equipped and well-used central resource. / Support provided to the Human Rights Commission – Established in just 2009 the HRC has become prominent within government and has recently launched a three-year strategic plan. / All senior staff members from partner organisations consulted as part of this review process were glad to see the end of the SP. While UNDP regretted the loss of what it viewed as a flexible funding mechanism, it was acknowledged that administrating the SP was more cumbersome than the benefits it brought and was not worth the damage that it caused to relationships between the organisation and donors. Some donors that had previously put funding into the SP have subsequently funded specific UNDP governance and rule of law programmes on a bilateral basis. / On the part of the donors in general, and DFID in particular, there is a sense of relief at having reached the end of a programme that was increasingly dysfunctional and that repeatedly failed to deliver clear results. / Lessons Learned from SPII’s Programmatic Work / The SP spread itself too thinly over too many different programmes to have any significant impact in any particular area. A narrower remit would have enabled keener focus on the outcome, better oversight and clearer results. / No records appear to exist as to UNDP and DFID agreeing to a change in logframe. If a logframe is changed partway through a programme it must be agreed by both parties and the agreement must be well documented. / DFID must align its indicators with the wider programme it is supporting. In this case one of DFID’s SP indicators did not even fall within UNDP’s programme of work therefore they were entirely unable to report any activity on it. / A stronger theory of change should have been identified for each of the SP Outputs, which would have provided indication as to the activities. / The substantive benefit of activities must be evaluated alongside the quanitative achievements. For example, UNDP is able to report on the numbers of people who took part in various training but there is little information available as to the genuine increase in understanding of the participants. Both DFID and UNDP must ensure that mechanisms are in place to evaluate the qualitative value of such activities. / Actors in the Rule of Law field that are bilaterally funded by DFID have complained that there is little cooperation or coordination from UNDP. DFID should ensure that organisations that it is funding in the same field are working in cooperation with one another. / Too many of the SP’s activities focused on supporting government institutions and although this is necessary in a fledgling country it was done almost to the exclusion of introducing rule of law principles to civil society. The training of chiefs and the setting up of JCCs is not sufficient in this regard. Lessons should be learned from the highly successful CPA-dissemination campaigns that took place throughout Southern Sudan that showed how complex and legalistic documents could be explained to a widespread and largely illiterate audience. / Advisors need to be of sufficient calibre and experience to genuinely build the capacity of institutions that they are working with. Mid-term evaluations of the SP, government counterparts and other actors working in the field of governance and rule of law have criticised the low level of capability, experience and commitment of some of the UNDP advisors. Despite the challenges, strong efforts must be made to ensure that extremely skilled advisors are found for field-based positions. / Better consideration needs to be given to infrastructure projects. An unused high court, an abandoned police station and an incomplete training centre are three extremely expensive SP-funded infrastructure projects that have been encountered just in the course of this review. In all cases a failure to communicate and cooperate sufficiently with the local authorities appears to be at the heart of the buildings’ failures.

8. Review Process
This review was conducted by Lydia Stone, an independent consultant. / The review and write-up was conducted over 14 days throughout June 2012. It is accompanied by an aide memoir that provides further information on lessons learned from the Strategic Partnership. / The consultant undertook a field trip to Bor to witness SP activities at state level. / A literature review was conducted that included: / UNDP annual reports of the Strategic Partnership / DFID annual report / Baseline values for CPAP indicators / DFID monitoring mission final performance review / SP results framework / Interviewees included: / Mervyn Patterson Senior Governance and Conflict Advisor DFID / Sonia Warner Senior Governance Advisor DFID (formerly in Khartoum office during SP inception) / Hamish Falconer Programme Manager DFID / Line Urban Senior Governance Advisor Joint Donor Office / Ronald Sonneman Embassy of the Netherlands / George Conway Country Director UNDP / Amanda Serumaga Team Leader, Governance & Rule of Law Unit UNDP / Evarist Twimukye Chief Technical Advisor, Support to Economic Planning UNDP / Francis Luwangwa Project Manager, Support to Development Planning & PFM UNDP / Mandisa Mashologu Team Leader, Poverty Reduction & MDGs Unit UNDP / Guyson Adi’kobaa Programme Analyst, Poverty Reduction & MDG Unit UNDP / Obiora Anene State Coordinator – Jonglei State UNDP / Charity Mahowe Revenue Specialist – Jonglei / Ministry of Finance UNDP / Nicholas Jonga Statistician – Jonglei Ministry of Finance UNDP / Abdul Wurie Development Planning Specialist – Jonglei Ministry of Finance UNDP / Kartik Sharma Rule of Law Officer UNDP / Mary Jervas Yak Deputy Minister of Finance & Economic Planning Government of South Sudan / Aquilla Maluth Man Minister of Finance and Economic Planning Jonglei State Government / Johnson Simon Lul Director General of Ministry of Labour and Public Service Jonglei State Government / Philip Jack Boldit Director General, Ministry of Finance and Economic Planning Government of South Sudan / Jacob Aligo Lo-Lado Minister of Finance and Economic Development Central Equatoria State Government / Eric Pelser Team Leader Safety and Access to Justice Programme