Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Unlocking the potential of groundwater for the poor in Africa (UPGro)
Programme Value: £8m (+ £2m NERC and £2m ESRC)		Review Date: November 2017
Programme Code: 203774	Start Date: 10/12/2012	End Date: 31/03/2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A	A+
Risk Rating	Low	Low	Low	Moderate	Moderate

Summary of programme
DFID is contributing £8million to support research that will unlock the potential of groundwater for the poor in Africa (UPGro). The Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC) are providing £2million each, giving a programme total of £12million. NERC is also providing in-kind resources and systems to commission and manage the research calls and related procurement throughout the life of the programme. The programme will run over seven financial years from December 2012 to March 2020 and is open to UK and non-UK researchers.

UPGro delivers the knowledge and information required to better access and manage groundwater resources to enhance water security for the 300 million poor people without access to improved water in Sub-Saharan Africa, and maximises the potential role groundwater can play in Africa’s economic development.

Summary of progress and lessons learnt since last review.
In response to recommendations of the 2016 UPGro Annual Review:
- Logframe indicators and targets were thoroughly reviewed and updated by the Programme Coordination Group (PCG) and a subgroup of the Programme Executive Board (PEB) and are reported against in this report.
- Catalyst projects are uploading data to relevant NERC and ESRC data centres.
- Gender is addressed specifically in logframe revision and the Knowledge Exchange Strategy has been updated to make gender explicit.
- The logframe review ensures early career researcher definitions are consistent across different activities, to enable future collation of data.
- Programme Executive Board have worked with the PCG to ensure that the UPGro Ambassadors were in place and able to meet the Consortia Principal Investigators (PIs) at a face-to-face meeting in London on 24th October.
- The PCG and the programme management and governance in general have been reviewed by a NERC mid-term review process. Confirmed that the PCG is well established and functioning efficiently.
- Collaboration and learning from other programmes - Future Climate For Africa (FCFA), REACH (improving water security for the poor) and SHEAR (Science for Humanitarian Emergencies And Resilience) – to strengthen research uptake and participation of southern partners: UPGro/FCFA ovelap paper has been drafted. Regular contact made with FCFA and REACH teams and calls with ESPA (Environmental Services for Poverty Alleviation) Impacts Team

Summary of recommendations for the next year
The Knowledge Broker will make the visibility and capacity development of UPGro Early Career researchers a high priority in 2018, as part of a wider Young Water Professional initiative that is planned for the Rural Water Supply Network (RWSN). Knowledge Broker, with on-going review by the PEB.

PCG to continue to manage the relationship with the Ambassadors. The role will be discussed with the Ambassadors to work out good win-win plans. PCG, with regular and on-going review by the PEB.

On-going learning from other programmes to strengthen research uptake and participation of southern partners: Continued collaboration with FCFA and REACH in particular, including uptake of the recommendations of the planned review of the impact of the UPGro, REACH and FCFA programmes. DFID, NERC and KB/PCG. Ongoing.

Based on responses from stakeholders within a NERC-led UPGro mid-programme review:
Where possible, the programme secretariat should be the main contact between the projects regarding all aspects of post-award funding queries and if this is not possible, the programme secretariat should be informed on funding assurance and reporting requests so that the secretariat can liaise with the lead project PI and PCG to ensure that all requests are met to deadline. All parties. Ongoing.

Programme Coordination Group (PCG) to target UPGro early career researcher group and encourage direct contact between them at the project and programme level. Develop coordinated training for this group as well as those in African organisations. PCG. Training plans to be agreed by March 2018. Otherwise ongoing.

Funders to consider data management of ODA initiatives and large interdisciplinary projects. NERC is currently reviewing its whole data management process and this programme will fall part of the revised process. DFID and NERC. To be reviewed regularly by the PEB.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents

Unlocking the Potential of Groundwater for the Poor (UPGro), is a seven-year international research programme (2013-2020) which is jointly funded by UK’s Department for International Development (DFID), Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC). During the programme over 130 of the world’s best researchers from 43 organisations across Africa and Europe have been or currently are focused on improving the evidence base around groundwater availability and management in Sub-Saharan Africa. The goal is to ensure that the hidden wealth of Africa’s aquifers benefit all citizens and the poorest in particular. UPGro projects are interdisciplinary, linking the social and natural sciences to address this challenge.
.
Water resources are critical to economic growth and social development. A study on groundwater in Africa has shown that there is possibly 20 times more water available as groundwater compared with that available in lakes and rivers[1]. Groundwater provides most of the domestic water supply in parts of rural Africa and supports poverty reduction through access to clean drinking water and irrigation[2]. It is estimated that groundwater provides water for domestic supplies and livestock for more than 100 million people and is the source of drinking water for 75% of Africa’s population (although this varies in proportion by country/sub-region)[3]. Ensuring availability and sustainable management of water resources has been enshrined in the UN Sustainable Development Goals (SDGs) under SDG 6. In 2015, 6.6 billion people, or 91 per cent of the global population, used an improved drinking water source, versus 82 per cent in 2000. Despite that improvement, an estimated 663 million people were using unimproved water sources or surface water that year. Groundwater has the potential to provide an improved source of drinking water for those in SSA who are currently without access.
[1] MacDonald et al. 2012. Quantitative maps of groundwater resources in Africa. Environ. Res. Lett. 7. 024009
[2] Hunter et al. 2010. Water Supply and Health PLoS Med7 (11): e1000361
[3] UNECA African Climate Policy Centre 2011 Management of Groundwater in Africa including transboundary aquifers: Implications for meeting MDGs, livelihoods goals and climate change adaptation. Working Paper Number 6.

With increasing pressures on water resources, the potential pressure on groundwater as the solution to the water security challenge in Africa is high. As the population grows, water security in SSA will become increasingly important and demands on groundwater are likely to surge. Poorly managed water resources will constrain opportunities for development, including better services and livelihoods for poor people. Despite the importance of groundwater in meeting water security needs for poor communities in Africa, there remain big challenges to realise this potential, including substantial knowledge gaps[4].
[4] MacDonald AM, Bonsor HC, Calow RC, Taylor RG, Lapworth DJ, Maurice L, Tucker J and Ó Dochartaigh BÉ. 2011. Groundwater resilience to climate change in Africa. British Geological Survey Open Report, OR/11/031. 25 pp.

Without addressing some of these core gaps in the evidence and data, it will be hard to identify and manage the full implications of increased groundwater use. UPGro is funding high quality environmental and social research to address these issues. The programme aims to deliver robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa. All research supported under UPGro will deliver outputs that can be used by policy makers and other stakeholders to inform effective decision-making and planning. The UPGro programme has two phases, the initial phase (2013-2015) comprised 15 ‘Catalyst’ projects that investigated different aspects of how the use and understanding of groundwater in Africa interacts with socio-economic conditions. Phase II was launched in 2015 and comprises five ‘Consortium’ research projects, which will run until 2019-20 and are undertaking detailed research on several aspects of ground water in Sub Saharan Africa (SSA). The table below provides further details on each project and a brief explanation of their area of research.

#	Consortium Projects (2015-2019)
	Project Title	Area of Research/Problem statement
1	Gro for GooD: Groundwater Risk Management for Growth and Development	To design, test and transfer a novel, interdisciplinary and replicable Groundwater Risk Management tool to improve governance transformations to balance economic growth, groundwater sustainability and human development trade-offs.
2	Grofutures: Groundwater Futures in Sub-Saharan Africa	To develop the scientific evidence and inclusive groundwater management processes by which groundwater resources can be used sustainably for poverty alleviation in Sub-Saharan Africa (SSA).
3	BRAVE: Building understanding of climate variability into planning of groundwater supplies from low storage aquifers in Africa	To develop water demand scenarios to inform the modelling of water resources and availability in future years. This work will be based on current domestic, agricultural and productive use needs and will be set within the context of the current impacts on existing needs and demands.
4	T-GroUP: Experimenting with practical transition groundwater management strategies for the urban poor in Sub Saharan Africa	To investigate the social, technical and political changes needed to make the shift towards sustainable urban groundwater management. Using “Transition Management theory” to find radically new and collaborative ways of using and managing urban groundwater.
5	Hidden Crisis: unravelling current failures for future success in rural groundwater supply	To achieve a more complete understanding of how to keep water flowing from boreholes, reducing waste and improving water services for Africa’s poorest communities, reducing wasted investment by water users, charities and tax-payers due to water point failure.

Additionally, the UPGro-funded Africa Groundwater Atlas and Literature Archive (http://www.bgs.ac.uk/africagroundwateratlas/index.cfm) continue to prove to be an invaluable resource for African groundwater researchers.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

2017 Highlight(s)
- Kenya Water Act 2016 influenced to allow more innovative models for rural water services (most of which are groundwater dependent). The policy influencing that led to the Kenya Water Act changes and Fundifix success story (see film here ) started under earlier ESRC and DFID grants, was taken to the next level by UPGro (Gro for GooD Catalyst & Consortium grant) and then brought to fruition by a combination of UPGro and REACH (improving water security for the poor), another DFID-funded programme.
- Emerging International Standard on Water Point Functionality from the Sanitation & Water for All (SWA) partnership is drawing on Hidden Crisis early findings.
- Hand-pump accellerometers to monitor use behaviour within Gro for GooD led to a process of inferring groundwater height based on monitoring of the frequency of vibrations from wells during pumping – a potentially game-changing discovery for groundwater mapping globally. Achieved international publicity through the BBC (see story here) and the Economist ( see article here )for the work on these ‘Smart Handpumps’.
- Inadequate consideration of groundwater in Sustainable Development Goal (SDG) 6 monitoring has been brought to the attention of UN-Water and UPGro has pathway to influence future Unicef and WHO Joint Monitoring Programme (JMP) and Global Environmental Management Initiative (GEMI) methods through the International Association of Hydrogeologists (IAH) and the Groundwater Solutions Initiative for Policy and Practice (GRIPP).
- White Volta Basin Plan : Groundwater and stakeholder engagement introduced to planning process by the BRAVE project. Partners are optimistic that they can continue to use this relationship to influence future policy on groundwater extraction in the county and guide further research being undertaken by the Water Resources Commission and Water Research Institute in Ghana during the development of the plan.
- Significant contributions to documents and decisions by national and international decision-makers, including UNICEF, The World Bank, Sanitation & Water for All, and the Governments of Uganda, Ethiopia and Burkina Faso.
- Catalyst projects were successful with African- and female-lead author papers, and although the Consortia projects have not met the African-lead targets, papers accepted or submitted in 2017 will exceed these targets. Women researchers have been in active authorship positions.
- BRAVE project have launched radio extension programme in Burkina Faso and Ghana as a way of communicating with a wide audience on practical groundwater and agricultural issues.
- Water users – particularly women - are being involved in the research process, helping guide the research direction and contributing to co-creation of knowledge.
- School Water Clubs have been established at three secondary schools in Kwale County through an outreach programme offered by the Gro for GooD project and local partners including the BASE Titanium mine.
- Africa Groundwater Atlas (see here ) continues to prove to be an invaluable resource for African groundwater researchers. Visits to the website are not captured in the log frame though have increased by 60% from 2524 visits between August 2015 and September 2016 to 4259 visits between October 2016 and September 2017.

Annual outcome assessment
The outcome for the UPGro programme is: “Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa”. The programme is assessed as being on track to meet its outcome targets, despite some initial start up delays. Progress against the outcome indicator milestones is good with all milestones being achieved and in most cases exceeded. The table below and the related narrative sections that follow provide a detailed illustration and description of progress against each milestone.

OUTCOME		INDICATOR		Baseline (2014)	Reported for 2016	Milestone 2017	Progress 2017
Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa	O.1	Use of evidence by other researchers: Citation of UPGro research in briefing papers, working papers and conference proceedings and peer-reviewed articles and book chapters. (Self-citations are included so that collaboration is not discouraged)
			Catalysts	7	32	90	117
			Consortia	-	as above[5]	L:20 / M:35 / H:50	41
	O.2	Use of evidence by national decision-makers: Number of National Sector Performance Reports, Joint Sector Review reports or other key reports, strategies and plans that directly or indirectly reference UPGro research.		0	2	3	7
	O.3	Use of evidence by international decision-makers: Number of key international documents, such as JMP, GLAAS, UN World Water Development Report that directly or indirectly reference UPGro research.		0	1	1	3
	O.4	Use of evidence contributing change: Number of stories of changes to groundwater use that have affected the poor in Sub Saharan Africa, which were influenced by UPGro or where UPGro research has influenced policy, the institutional framework, practice, groundwater monitoring and research.		0	1	3	10
[5] Note that the 2016 figure didn’t include self-citations and combined the catalysts and consortia into a single figure

Key points
- Both Catalyst and Consortia studies met the 2017 citation milestone. The most cited UPGro paper (36) to date is: Sorensen, J. P. R.D.J. Lapworth,D.C.W. Nkhuwa, M.E. Stuart, D.C. Gooddy, R.A. Bell, Chirwab, M. Chirwa, J. Kabika, M. Liemisa, M. Chibesa, S. Pedley (2015) “Emerging contaminants in urban groundwater sources in Africa” Water Research, Volume 72, 1 April 2015, Pages 51-63 doi:10.1016/j.watres.2014.08.002
- Hidden Crisis work has made significant contributions to documents and decisions by national and international decision-makers, including UNICEF, The World Bank, Sanitation & Water for All, and the Governments of Uganda, Ethiopia and Burkina Faso.
- Gro for GooD continues to be influential in Kenya, and by securing the REACH (improving water security for the poor) programme, Oxford and partners spreading their ideas and influence to Ethiopia and Bangladesh.
- BRAVE and GroFutures are making tangible impacts on water resource monitoring and planning in West and East Africa, particularly through engagement with the White Volta Basin Authority (BRAVE) and Dodoma Urban Water Supply and Sewage Authority (GroFutures).
- The Catalyst studies continue to deliver academic, policy and field-implementation outcomes – notably the Road Recharge catalyst, which is being taken up across Ethiopia, other African countries and is being introduced in Bangladesh. One catalyst project has received significant additional funding from the NWO (Dutch Scientific Council) under the programme on Inclusive Roads, for continuation and up-scaling Of the other eight, three have received small additional funding to continue parts of the project and one has received a research award as grantees under the Global Resilience Partnership (USAID, Rockefeller Foundation and SIDA) over up to $1 million: http://www.globalresiliencepartnership.org/teams/roads-water-livelihoods/ and http://www.globalresiliencepartnership.org/water/#winners
- The Catalyst Grant mechanism has provided a good opportunities for building collaboration and partnerships among African and European researchers from different disciplines and with local, national and international stakeholders. Catalyst Projects published at least one article on their research topic and as a result, 18 articles on groundwater issues in Africa were published in various International Journals.

Overall output score and description

An overall rating of A+ is proposed. For research (40%), outputs moderately exceeded expectations, for capacity development for UPGro early career researchers (10%) outputs met expectations, for research into action (25%) outputs moderately exceeded expectations and for participation and influence of research for groundwater users (25%), outputs substantially exceeded expectations. This is an improvement on the A rating awarded in previous years, reflecting largely an improvement in the demonstrable uptaking of UPGro research, influencing stakeholders – as exemplified in the cases of the Kenyan Water Act and of the ground-breaking discover of inferred water table height from hand-pump handle vibrations, within the Gro for Good project.

Key lessons
The Knowledge Broker adds value to the work of the researchers and for future similar programmes, the timing of establishing this aspect should be carefully considered. This may particularly be the case if there is an initial ‘Catalyst Phase’.

Key actions
- Programme Executive Board (PEB) to understand the effectiveness of the new due diligence process, admin implications for the project research teams and to feed into cross DFID/RCUK learning, where appropriate. Ongoing.
- PEB needs to agree and programme most effective use of remaining funds for the UPGro budgetary contribution to the combined UPGro/FCFA/REACH impact review, to be commissioned in early 2018.
- PEB to communicate to researchers the results of the mid-term UPGro review: November/December 2017.
- PEB, Knowledge Broker and PIs to continue to work at achieving publication and presentation targets for African female researchers. Ongoing.
- The Knowledge Broker to work with the UPGro Ambassadors to facilitate better ways of working with individual research consortia and to ensure all parties derive maximum benefit from this resource. Ongoing.
- DFID CEW team to work together with the Knowledge Broker to develop impact stories and communication products. Ongoing.

Has the logframe been updated since the last review?
In response to the 2016 Annual Review recommendations, thresholds to Outcome 1 were raised due to better than expected citation rates. Most changes were made at the Output levels, in particular Outputs 1 and 2. Across the log frame in both targets and reported figures, Catalyst research has been separated from the Consortia, and the wording of many indicators was clarified to show that the reported figures were cumulative totals. Output 1 has been clarified to better capture what the programme was actually doing (e.g. the many presentations, posters and abstracts being presented at conferences).

Output 2 (Early Career, Female and African researchers) has been amended in response to the 2016 Annual Review recommendation, which found that the metrics were too difficult to measure because of the dynamic nature of the teams - so they were changed from absolute numbers to percentages. Also the disaggregation was changed to include consideration of African women, not just Early Career. This is incentivise the profile raising and capacity development of all African women in the programme, not just the junior ones.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

OUTPUT 1		INDICATOR		Baseline (2014)	Reported for 2016	Milestone 2017	Progress 2017
Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated	1.1	Peer-reviewed papers: Cumulative number of peer-reviewed articles in journals,book chapters.
			Catalysts	2	15	15	17
			Consortia	-	3	15	16
			TOTAL	2	18	30	33
	1.2	Conference presentations: Cumulative number of presentations (oral or poster) at international academic, policy or practice conferences disaggregated by project: KB/At/Am = Knowledge Broker, Atlas Team, Ambassador
			Catalysts	44	67	60	77
			Consortia	-	54	90	115
			KB/At/Am	2	7	15	15
			TOTAL	46	128	140	206
	1.3	Peer-reviewed papers (interdisciplinarity): Cumulative number of papers where the authors are from different disciplines and/or the paper Combines social/policy and physical/natural sciences.
			Catalysts	1	5	6	5
			Consortia	-	1	5	8
			TOTAL	1	6	11	13
	1.4	Peer-reviewed papers (author representation): Cumulative no. of papers with lead (first or second) authors are:
	Catalysts		[1.4.1] Female	0	6	6	6
			[1.4.2] African	2	5	5	6
			[1.4.3] African female	0	2	2	2
	Consortia		[1.4.1] Female	-	2	7	7
			[1.4.2] African	-	0	5	1
			[1.4.3] African female	-	0	2	0
	1.5	Data: Number of DMPs in place and being satisfactorily implemented		-	5	5	5
	1.6	Dissemination: Cumulative number of research document downloads from UPGro website, RWSN websites and Africa Groundwater Atlas.		1,122	2,454	5,500	6,859

Key Points
- 13 peer-reviewed Consortium papers have been published since October 2016, some as pure UPGro and others contributing African evidence to larger global studies on fossil groundwater, water security and groundwater monitoring. Whilst the majority of the academic outputs so far have been from the physical sciences, there have been some interdisciplinary papers that connect the groundwater science to wider issues around groundwater use, management or role in climate resilience and water security.
- 2 papers were published from Catalyst studies and will probably be the last from the direct funding. However, a significant amount of ‘catalyst research’ is continuing in different forms.
- UPGro researchers have been actively presenting their work at conferences and events to both academic, policy and practitioner audiences.
- The Catalyst projects were successful with African- and female-lead author papers, and although the Consortia projects have not met the African-lead targets, papers that have been accepted or submitted in 2017 are expected to exceed these targets. Women researchers have been in active authorship positions in these.
- There have been 6859 cumulative research document downloads from the UPGro website and other platforms that disseminate UPGro publications (e.g. NORA), which meets the 2017 milestone. Although visits to the Africa Groundwater Atlas website are not captured in the log frame, visits to the homepage of the Atlas have increased by 60% from 2524 visits between August 2015 and September 2016 to 4259 visits between October 2016 and September 2017. This follows several successful promotional campaigns, including at the IAH Congress in Montpellier (Sept 2016) and the RWSN Forum in Abidjan (November 2016). The UPGro website (upgro.org) is the gateway to the programme, and is also a management tool which is updated on a regular basis to provide a comprehensive store of materials emerging from the programme and links to organisations, articles and events where UPGro is visible. From November 2016 – October 2017, there were 53 posts, which were also broadcast through UPGro and RWSN twitter and LinkedIn and other social media. The UPGro twitter account still only has limited reach (223 followers) so UPGro tweets are also sent out via the RWSN account (1,031 followers) and the Knowledge Broker team leader (1,619 followers). The Knowledge Broker team currently relies on unpaid ‘organic’ social media coverage, but in 2018 consideration will be given to setting a small social media advertising budget to increase this.

Figure 1: monthly total page views and visitor to upgro.org May 2015 - 5Oct 2017 (source: Wordpress analytics)

The all-time top 10 of visitor countries to upgro.org is:

1	UK	6	Germany
2	USA	7	India
3	Kenya	8	Ethiopia
4	Netherlands	9	Spain
5	Switzerland	10	France

Other dissemination and outreach platforms include:

Platform	Followers	Cumulative Posts (Oct 2017)
UPGro.org (Wordpress site/blog)	34[6]	177
ResearchGate (UPGro Project Page)	106	18
Twitter (UPGro)	223	166
Twitter (RWSN)	1031	749 (mostly RWSN-related)
RWSN LinkedIn Group	3883	n.d. (mostly RWSN-related)
RWSN Facebook Group	2009	n.d. (mostly RWSN-related)
RWSN Sustainable Groundwater Development	1066	2495[7]
[6] Subscribers who are notified of news items on the UPGro website
[7] Discussion group mainly focusing on practice groundwater issues worldwide, but generally in Africa

- An UPGro YouTube channel[8] was launched in July 2016 and videos stored there have been viewed 2767 times; it also provides links to UPGro-related videos hosted by UPGro partners.
  [8] https://www.youtube.com/channel/UCTv5uGIhSsEiZ2ktSTn3jhA
- 500 USB sticks containing all the publically available UPGro publications and information were produced in March 2017. By the end of the reporting period 460 had been distributed by the Knowledge Broker at face-to-face events including: REACH Annual Workshop (Naivasha, Kenya); SDC Global Programme Water Peer Review (Bern, Switzerland); WEDC Conference: UPGro session (Loughborough, UK); International Mining, Minerals & Groundwater Conference: UPGro session (Livingstone, Zambia); SIWI World Water Week: RWSN exhibition stand & session (Stockholm, Sweden). An offline version of the Africa Groundwater Atlas has also been distributed on a USB stick at some of the events listed above.
- At the end of 2016, UPGro had an exhibition stand and a side event at the 7th RWSN Forum in Abidjan, which was used as a platform by UPGro projects and the Atlas to promote and disseminate materials (also see Output 3).

Summary of responses to issues raised in previous annual reviews (where relevant)

PEB (Programme Executive Board) to continue to monitor the new logframe, ensuring indicators and targets remain appropriate and agree approach on study for logframe impact indicators, commissioning if appropriate (Lead: PEB. Target Date: monitoring ongoing, approach on indicators: March 2016)	Completed. Log Frame indicators and targets were thoroughly reviewed and updated by a subgroup of the PEB and the PCG continued to refine these following the meeting and are reported against in this report.	The targets and milestones will continue to be monitored, reviewed and adjusted as necessary by the PEB. / DFID CEW is planning over the next year to commission a multi-programme (REACH/UPGRO/FCFA) impacts review, framed around water security.
Ensure catalyst projects upload data to NERC and ESRC data centres (Lead: RC Data centre lead. Target Date: March 2017)	Completed. The NGDC has been the lead data centre funded through UPGro, however social science data should go to UKDS. Only 2 (Non-Consortia) Catalysts generated new data, the remainder relied on collating existing data.	None required.

Recommendations
1. Programme Executive Board (PEB) to understand the effectiveness of the new due diligence process, admin implications for the project research teams and to feed into cross DFID/RCUK learning. Ongoing.
2. PEB needs to agree and programme most effective use of remaining funds, including the UPGro budgetary contribution to the combined UPGro/FCFA/REACH impact review, to be commissioned in early 2018.
3. PEB to communicate to researchers the results of the mid-term UPGro review: November/December 2017.
4. PEB, Knowledge Broker and PIs to continue to work at achieving publication and presentation targets for African female researchers. Ongoing.

Output Title	UPGro early career researchers equipped with the skills to collaborate and communicate their work in the wider context of poverty and groundwater science and governance
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

OUTPUT 2	INDICATOR	Baseline (2014)	2016[9]	Milestone 2017	Progress 2017
	International events: Cumulative % of Early Career (EC) researchers from each project giving at least 1 presentation research findings at international conferences. (disaggregated by sex and nationality)
	[2.1.1] % of all EC Researchers	0	17%	30%	28% 
	[2.1.2] % of female EC researchers	0	20%	30%	38% 
	[2.1.3] % of African EC researchers	0	11%	30%	18% 
	[2.1.4] % of African female EC	0	11%	30%	11% 
	Training, coaching and mentoring: Cumulative % of Early Career (EC) UPGro researchers receiving training or systematic coaching and mentoring (disaggregated by sex, nationality).
	[2.2.1] % of all EC Researchers	0	46%	30%	51% 
	[2.2.2] % of female EC researchers	0	46%	30%	54% 
	[2.2.3] % of African EC researchers	0	61%	30%	72% 
	[2.2.4] % of African female EC	0	67%	30%	78% 
	Knowledge sharing: Cumulative number of UPGro Early Career (EC) that have actively participated in at least one international knowledge sharing event, such as a PCG workshop/webinar; (disaggregated by sex and nationality).
	[2.3.1] % of all EC Researchers	0	ND	30%	50% 
	[2.3.2] % of female EC researchers	0	ND	30%	54% 
	[2.3.3] % of African EC researchers	0	ND	30%	74% 
	[2.3.4] % of African female EC	0	ND	30%	78% 
[9] Not reported in 2016 due to change in Indicator

Key Points
- GroFutures organised a successful training workshop on Analysis of Long-Term Groundwater Records at Sokoine University of Agriculture, Tanzania, in February 2017 involving 24 EC researchers.
- T-GroUP has supported a further 22 MSc and BSc students from UNESCO-IHE and Makerere University, Uganda.

Summary of responses to issues raised in previous annual reviews (where relevant)
The Programme coordination group (PCG) capacity building theme as set out in the workplan does not specifically mention gender. The PEB should ensure disaggregation by gender is included and strengthening of women early career researchers is included in the PCG work plan and monitoring (Lead: PEB. Target Date: April 2016)	Addressed & Ongoing. Gender addressed specifically in Log Frame revision. / Knowledge Exchange Strategy updated to make gender explicit.	The Knowledge Broker will make the visibility and capacity development of UPGro Early Career researchers a high priority in 2018, as part of a wider Young Water Professional initiative that is planned for the Rural Water Supply Network (RWSN).
PCG to ensure early career researcher definitions are consistent across to enable future collation of data (Lead: PCG. Target Date: April 2016)	Completed. This was included in the Log Frame review: / “Early careers” (EC) refers to researchers with either / <5 years post-PhD experience; or / <10 academic experience, after Bachelors or Diploma without a PhD. / An EC at the beginning of the programme (1 Jan 2015), or whenever they joined their UPGro project, remains an EC for the duration of the programme. / Only Consortium projects are considered. / ‘African’ refers to nationality/citizenship, not location. E.g. a Ghanaian EC team member located in the UK counts, but a British EC team member located in Ghana does not.

Recommendations

The Consortium Coordination Group working with individual research consortia and the Knowledge Broker to consider opportunities to improve the percentage of female early career researchers involved with UPGro. CCT/KB to report to the PEB on progress. Ongoing.

Output Title	Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub-Saharan Africa (SSA)
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

OUTPUT 3		INDICATOR	Baseline / (2014)	Progress Reported in 2016	Milestone 2017	Progress 2017
Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub Saharan Africa (SSA)	3.1	Involvement in research: Cumulative Number of stories of SSA stakeholders involved in the development of the research plans and the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management.	0	6	L: 5 / M: 7 / H: 20	14  (M)
	3.2	Briefing materials produced: Cumulative Number of policy and practice briefing materials and syntheses produced by UpGro research projects.	15 Catalyst project + 1 overall Catalyst flyer / UPGro leaflet / UPGro pull-up banner	11	L: 15 / M: 20 / H: 25	29  (H)
	3.3	UPGro (co-)organised events: Cumulative Number of UPGro project events/sessions with policy-makers, practitioners and change makers where research findings are presented.	Africa:/ Intl: 1 UK: 2	10	L: 15 / M: 20 / H: 25	25  (H)
	3.4	Decision-making processes: UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings).	0	6	5 / At least 1 processes or events per project	+14 

Key Points
- BRAVE have tapped into IRC’s well established “Learning Alliances” in Burkina Faso and Ghana to engage stakeholders and extend that to district levels so that there is co-creation of knowledge and practical tools that benefit both researchers and local stakeholders.
- UPGro teams have been actively engaging the governments of Kenya, Tanzania, Ethiopia, Malawi, Uganda, Ghana, Burkina Faso, and Niger, and demonstrating success in getting ideas and evidence taken up.
- At the end of 2016, UPGro had a large presence at the 7th RWSN Forum in Abidjan, Cote d’Ivoire, as a Bronze Sponsor and with an exhibition stand; multiple sessions and presentations in the main programme; supporting an Africa Groundwater Network training day (in French); and a full-day on African groundwater. The Forum was attended by over 450 participants from civil society, development partners, government and private sector and was completely French/English bi-lingual. There were 283 participants from 27 Sub-Saharan Countries. The Forum was organised by the Skat Knowledge Broker team. It is the largest event on rural water supply globally and is held every five years.
- In 2017, the University of Zambia invited UPGro to run a full-day special session on African groundwater science and use, at their international conference on Mining, Minerals and Groundwater. The 3-day conference was opened by the President of Zambia who explicitly talked about the importance of groundwater to Zambia’s economy and society. This was followed by a keynote presentation by UPGro Ambassador, Dr Callist Tindimugaya.
- UPGro (Knowledge Broker/T-GroUP) was invited by the Swiss Water Partnership (SWP) to be part of a well-attended interdisciplinary groundwater session at Stockholm World Water Week. In recent years, groundwater issues have been neglected and previous attempts to get a session on the topic, by both SWP and RWSN partners (UPGro, Skat, UNICEF, WaterAid) had not been successful. The SWP is looking to continue to promote groundwater issues.

Summary of responses to issues raised in previous annual reviews (where relevant)
5. PEB should work with PCG to ensure UPGro Ambassadors in place in time to be effective and maximise impact (Lead: PEB. Target Date: August 2016)	Addressed & Ongoing. This was included in the Log Frame review. Ambassadors meeting face-to-face in London on 24th October.	PCG to continue to manage the relationship with the Ambassadors. The role will be discussed with the Ambassadors to work out good win-win plans.

Recommendations
1. The PCG to work with the UPGro Ambassadors to facilitate better ways of working with individual research consortia and to ensure all parties derive maximum benefit from this resource. PCG, plus KB and DFID. Ongoing.

DFID CEW team to work with all parties (Knowledge Broker, Consortium Coordination Group and individual research consortia) to better facilitate engagement with DFID Country offices and other relevant DFID Departments as appropriate. DFID, PCG and KB. Ongoing.

Output Title	Current and potential groundwater users participate and influence the UPGro research and are presented with the findings
Output number per LF		4	Output Score	A++
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

OUTPUT 4		INDICATOR	Baseline / (2014)	Progress Reported in 2016	Milestone 2017	Progress 2017
Current and potential groundwater users participate and influence the UPGro research and are presented with the findings	4.1	Groundwater users engaging with researchers: Cumulative number of stories where users have participated and influenced the methodology and results of the UPGro research (stories should highlight participation of women and of the poor)	0	Catalyst: 1 Consortia: 5	At least 10	Catalyst: 1 Consortia: 13 
	4.2	Reporting of research progress and findings to water users: Cumulative number of face-to-face events and activities that give feedback on the research progress, findings and practical implications to the groundwater users that are/were the target of the research.	0	0 / (3 not reported last year)	5	12
	4.3	Media coverage in UPGro countries: Cumulative number of programmes or articles on UPGro work in local media (radio, newspapers, TV). Blog posts not included due in unknown reach/impact	2 articles in UK/Int.	8 / (+15 Int.)	10	12 / (+ 31 int.)

Key Points
- BRAVE have launched their radio extension programme in Burkina Faso and Ghana as a way of communicating with a wide audience on practical groundwater and agricultural issues.
- Water users – particularly women - are being involved in the research process, helping guide the research direction and contributing to co-creation of knowledge.
- School Water Clubs have been established at three secondary schools in Kwale County through an outreach programme offered by the Gro for GooD project and local partners including the BASE Titanium mine.
- TV and newspaper articles stimulated by UPGro work and activities were published in Kenya, Tanzania and Burkina Faso
- Gro for Good achieved significant international publicity through the BBC and the Economist for the work on Smart Handpumps[10]
  [10] Co-developed under an earlier grants and taken further with REACH

Summary of responses to issues raised in previous annual reviews (where relevant)

As for output 1. PEB (Programme Executive Board) to continue to monitor the new logframe, ensuring indicators and targets remain appropriate and agree approach on study for logframe impact indicators, commissioning if appropriate (Lead: PEB. Target Date: monitoring ongoing, approach on indicators: March 2016)	Completed. Log Frame indicators and targets were thoroughly reviewed and updated by a sub-group pf the PEB and refined further by the PCG and are reported against in this report.	The targets and milestones will continue to be monitored, reviewed and adjusted as necessary by the PEB. / CEW is planning over the next year to commission a multi-programme (REACH/UPGRO/FCFA) impacts review, framed around water security.

Recommendations
1. DFID CEW team and NERC to work together with the Knowledge Broker to develop impact stories and communication products. DFID, NERC, KB. Ongoing.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers originally identified for UPGro include research staff costs, costs of equipment and consumables, and travel and subsistence. These have not changed since the programme was approved and NERC assess these as part of the grant review process to ensure costs are kept down.

The Moderating Panel for the consortium round scrutinised the requested costs of the consortium grant proposals and decided that the costs for each of the 5 projects awarded were fully justified, i.e. all the resources requested (e.g. staff time, equipment and field costs) were required to deliver the stated programme of work. Any significant future variations to the project plans will have to be agreed by the PEB, who will take VfM into account.

Over the lifespan of the programme management costs are expected to be approximately 4% of the total cost and are an in kind contribution from NERC in addition to NERC’s cash contribution. This figure remains true.

VfM performance compared to the original VfM proposition in the business case
The original UPGro Business Case identified the following key elements of VfM:

- Leveraging of Research Council funds.
- Use of well-developed RCUK systems into which there has been considerable investment.
- Competitive research calls to identify and fund the highest quality research.
- Value for money guidance at the peer review and panel stages.
- Wired link between research and impact to ensure UPGro delivers benefits for poor people through research uptake in developing countries.

These have not changed and the UPGro programme continues to deliver good results against all criteria.

The programme leverages resources from both the Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC), which are DFID’s co-funding partners who continue to provide additional pro-bono resources to ensure the effective and smooth management of all activities. This is particularly relevant for the administration and management of all research calls and associated activities, such as peer reviewing of proposals, financial management and supervision of contracting / granting arrangements with all implementing partners. The linkages between research and impact are delivered through a joint effort between DFID, NERC and ESRC and all impact strategy plans agreed at the Programme Executive Board (PEB) level.

Furthermore, the programme aims to deliver strong value for money against the following five criteria of: economy, efficiency, effectiveness, cost-effectiveness and equity. This is currently achieved as follows:

- NERC exerts pressure for economy (minimising input costs) through close scrutiny of budgeted and actual costs of each grant. Where it is possible to identify unit costs that are comparable between projects (for example, in travel budgets or day rates of senior staff), NERC provides guidance on what is reasonable and what is excessive. NERC reviews budgets and expenditures (at application and peer review) and will ask grant holders to reduce high costs;
- Efficiency (maximising research outputs in relationship to budget inputs) is a function of ensuring that research grants are of high quality. Stiff competition due to the heavily over-subscribed nature of the scheme; due diligence assessment of the delivery capacity of contracted researchers; and clarity (between DFID, ESRC and NERC) and transparency (between NERC and applicants) regarding the purpose and priorities of the UPGro programme all help to ensure that efficiency is maximised;
- Effectiveness (the translation of research outputs into outcome) and cost-effectiveness (the ratio between inputs and impact) is hard to judge at this point. Assessment of the likely impact of the UPGro programme to date suggests that this research is likely to be effective in (i) helping to shape our understanding of groundwater issues across an number of countries and contexts in Africa and (ii) exerting a positive influence upon practice (programmes and policies). A separate, cross-programme impact review for UPGro, REACH and FCFA (Future Climate For Africa) is currently being commissioned, to be undertaken in 2018, investigating the impact of these programmes on improved water security for Africa.
- Since the Business Case was approved, DFID has introduced equity as a fourth dimension of its approach to framing VfM. UPGro’s strategy to include non-UK researchers from Sub-Saharan countries as key partners in the research, will help to ensure a good performance on this dimension of VfM.

Assessment of whether the programme continues to represent value for money(VfM)
A mid-programme review, led by NERC in 2017, stated that: ‘The main conclusion from the responses to the UPGro questionnaire and other sources of evidence available for the mid-term review of UPGro is that UPGro is meeting the programme objectives and is good value for money.’

This programme is assessed as continuing to deliver good VfM. The use of the robust RCUK peer review systems for competitive research calls has delivered high quality research, demonstrated by the emerging outputs of the catalyst research projects and the calibre of the consortium research teams. The costs of the consortium projects were scrutinised as part of the standard RCUK assessment process, including the use of moderating panels.

The management of the programme presents some innovative elements and has been structured with the aim of delivering the highest possible level of outputs, whilst keeping costs down and thus ensuring high VfM. This was inspired partly by lessons learned from other programmes co-funded by DFID, NERC and ESRC, which involved a more structured and cost-heavy management set-up. The model used for UPGro is lower cost, with the Programme Co-ordination Group (PCG) costing 500 k over the project lifetime and the Knowledge Broker services totaling £86,000 per year, which is significantly lower than those incurred by other programmes of a similar size and scope. This represents good VfM.

A programme coordination group (PCG) was established to integrate the 5 consortia to ensure that the outcomes of the programme are greater than the sum of its individual parts, and to enable efficient engagement with the funders and the knowledge broker, while enhancing the link between research and impact.

Quality of financial management
NERC ensures good financial management at the level of individual grants through a combination of pre-conditions imposed at procurement stage (institutions receiving grants which are not already eligible for RCUK funding have to have passed the RCUK recognition process and its due diligence checks) and ongoing annual reporting requirements, as set out in the RCUK-standard terms and conditions attached to grant awards.

NERC contracts are concluded with a lead institution: this institution assumes responsibility for ensuring good financial management (and avoiding project-level under- or over-spend) through any ‘sub-contracts’ with other project partners. In addition, a range of processes and safeguards are in place to ensure value for money is assured throughout the application, review and award granting process:

- At the application stage value for money (VFM) is a stated assessment criterion in the scheme specification and applicants are required fully cost all elements of their proposed research and provide detailed justification for each item of expenditure. Peer reviewers and panel assessors are asked to consider VFM as part of the grant assessment and is one of the factors which panel members consider when making final funding recommendations.
- At the award contract stage all costs are subject to detailed scrutiny by the NERC Secretariat. Any unjustified or excessive costs may be removed from the budget.
- Grants are only held by institutions which have passed RCUK recognition processes, which include checks on financial management and capacities. Details of the information organisations are required to provide as part of the Due Diligence process.
- Grants are contracted with RCUK standard T&Cs which include financial management and reporting requirements. In addition, the RCUK-wide Funding Assurance Programme conducts checks at an institutional level (see NERC’s annual report and accounts - http://www.nerc.ac.uk/latest/publications/strategycorporate/annualreport/annualreport/ ).
- Where awards have contracted project partners the NERC contract is with the host institution. The host institution will set up ‘sub-contracts’ with any partner organisation. The host organisation will thus take the financial responsibility of tracking partner spend and the risk of any overspend or default.

Finally, following a review of the programme spending profile and performance, it was observed that up to the date of this annual review, all payments and disbursements were made in accordance with the original schedule and the spending profile is reflecting the expected forecasts. During the initial start-up of the programme there had been some challenges with ensuring the sub-contracting of second tier implementing partners satisfied DFID and RCUK strict standards and this caused some delays. However these issues have now been resolved and, as already outlined, the programme is now meeting agreed spending targets and forecasts.
Date of last narrative financial report	24 October 2017
Date of last audited annual statement	N/A – NERC is a UK Research Council and part of HMG

E: RISK (½ page)

Overall risk rating: the risk level for the programme was reviewed in accordance with the latest Smart Rules guidance on risk, which now spreads risk levels across four levels and six categories and was assessed as Moderate.[11] The table below provides a description of how we assessed risk against each of the six categories now included in the Smart Rules:
[11] Revised risk levels under the SMART rules are: minor, moderate, major, severe.

Risk table
Risk category	Risk Analysis and description	Risk level
External context	The external context for this project is generally favourable and the broader area of research well developed and mature. Conducting research in country specific contexts will always entail a degree of risk, which will vary from country to country. The programme is operating in potentially difficult contexts (e.g. Kenya, Nigeria, Niger Ethiopia), which present some challenges and could affect the delivery of activities for some projects. This issue is being tackled at two levels: i) the project level where each consortium is following the security procedures and ‘duty of care’ guidelines employed by each research institution and ii) the programme level where the PEB has revised the risk associated with each proposal and periodically reviews any changes in circumstances that may affect the work and/or safety of any of the research team involved.	Moderate
Delivery	The risk related to the delivery chain for this programme is low. This is mostly due to the streamlined and simple structure of the programme, which involves a first layer of consortia (5 in total) that are led by at least one UK or European research institution and a second layer of sub-contracted service providers/institutions, mostly based in SSA. Because of the granting arrangements employed by NERC all second layer delivery partners and service providers are accounted for and are requested to sign agreements that meet RCUK and DFID standards. Non-UK or other unrecognised institutions funded under such arrangements are required to gain full RCUK recognition before contracts can be issued and funding can commence and full due diligence checks are in place to complete these checks. In order to ensure compliance, NERC operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The NERC risk assessment strategy also recognises this as an important ssue in the current research funding environment.	Moderate
Operational	Ensuring high levels of transparency and strict standards with the sub-contracting of second tier implementing partners has resulted in low levels of risk in the delivery category but has had an impact on the programme operations both in terms of delays and morale among consortium members. The programme has developed an approach to overcome this challenge and ensure mitigation of any impacts on the programme. More specifically, they have realised that they need to ensure the project PIs build sufficient time into proposals to allow for appropriate contracting of second tier partners and contractors. The Research Councils are also in discussion with Higher Education Institutions to improve collaborative working practice that ensure better financial management of ODA grants and sub-contracts. This risk was initially ‘Major’ but has been downgraded to Moderate given the actions undertakne over the last reporting year.	Moderate
Safeguards	UPGro is a research programme and as such it involves intrinsically low levels of risk in this category. Its subject matter which aims to attain environmental sustainability in the use and management of water resources is a further guarantee that all the standards and environmental safeguard principles are adhered to. Social and environmental safeguards are also guaranteed through the manadatory principles that all UK and EU based research instutions must follow in order to retain their ISO accreditations and respect EU funding rules.	Minor
Fiduciary	The fiduciary risk associated with the granting /contracting of both layers of suppliers and partners is managed by NERC in accordance with the strict rules set by RCUK and has been revised in full to ensure it satisfies DFID due diligence requirements. To this date there have been no reported issues in this area and NERC remains confident of its level of oversight and ability to intervene in case of any repoted incidents.	Moderate
Reputational	Reputational risk for this programme is very low. All research proposals have been thoroughy reviewed and scrutinised in line with the strict standards imposed by the UK Research Councils and are implemented by internationally recognised research institutions. The subject matter of the research is uncontroversial and there is very little scope to generate outputs that may have an adverse impact on any specific group of stakeholders in partner countries. On the contrary, the research funded under UPGro is expected to deliver substantial benefits to government agencies and local communities alike, by producing evidence that can significantly improve the management and availability of water resources for economic and social development purposes.	Minor

Overview of programme risk
Through peer review and expert advice the NERC only give grants to institutions recognised as bona-fide research institutions through due diligence checks, and on the condition that those institutions and award holders are willing to adhere to NERC terms and conditions.

In general, only accredited UK institutions are eligible for NERC Research grants. Non-UK or other institutions funded under this scheme are required to gain full RCUK recognition and were required to undergo a due diligence process before contracts can be issued and funding awarded.

Outstanding actions from risk assessment
- On-going learning from other programmes to strengthen research uptake and participation of southern partners.
- PEB needs to agree and programme most effective use of remaining funds, essentially the budget for the independent mid-term review.
- The programme will need to ensure that its indicators, metrics, milestone sand associated definitions are regularly reviewed to ensure that they are fit for purpose.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Consortia are now on track to deliver within planned timescales having made-up the initial 5-6 month delays in consortia start up caused by changes to DFID’s due diligence requirements. Spending levels are also now back on track and in line with agreed schedule.

Performance of partnership (s)
UPGro is co-funded by NERC and ESRC, which provide contributions of £2 million each to the total £12m programme. NERC additionally provides in-kind support in the form of the Programme Secretariat that is responsible in major part for the implementation. The programme is overseen by a Programme Executive Board (PEB), chaired by Professor Declan Conway (LSE). Skat Foundation are contracted to perform the Knowledge Broker role.

In terms of managing and administering the programme UPGro follows a clear and structured division of labour between its funding partners. The NERC Secretariat manages the portfolio of funded scheme awards. The same team manage communication with award holders from the application stage, granting successful awards and then throughout the course of the funded project. As such good working relationships have been established and continue with our community of award holders.

All live projects are required to submit biannual reports via the knowledge broker. These report on project progress and provide an opportunity to highlight emerging findings and flag up where there has been evidence of research impact or uptake. The NERC team pick up on any issues which require action from the reports and raise any significant impact stories to our Communications team and DFID.

The Secretariat is also responsible for dealing with ad hoc issues raised by award holders. The NERC finance team is responsible for the financial management and oversight of scheme awards. Where no-cost extensions are awarded this does not impact upon the profiling of award spend or DFID payments. In the case of a no-cost extension, the award profile remains the same: the extension affects the final reconciliation payment only which will be delayed according to the amount of the extension. DFID payments will remain in line with the original profile; NERC will manage the slight variation in final reconciliation payments within its own accounting systems.

Asset monitoring and control
N/A the programme does not have any material assets that require monitoring.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable. There have been no changes to established partnership principles. A detailed description of the functioning of the partnership between DFID, NERC and ESRC has been provided in the relevant sections above. It should also be noted that UPGro is a multi-country programme and does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The importance of water security remains unchanged since the initial design of UPGro and the challenges are recognised in the Global Goals. It is reasonable to assume that the benefits of UPGro work will increase over time, as research findings emerge and are taken up by implementing partners.

Uptake is being tracked as part of the logframe reporting over the lifetime of the programme. The performance of the catalyst projects and dissemination of emerging results including some media uptake, awards and use in national planning provides an assurance of quality of UPGro research and interest to key audiences.

The revision of the logframe with the Knowledge Broker and research consortium allowed updating of the impact indicators and output/outcome levels in line with a better understanding of the planned main research phase. This provides a stronger basis for ongoing M&E. This ongoing process will be supported by the independent mid-term review, which is currently being discussed and planned by the PEB and should take place at some point during the next FY (2018-19).

Furthermore, since the 2016 review the UPGro Programme Coordination Group (PCG) has produced and published a “Knowledge Exchange Strategy” for the programme. This strategy builds on the PCG Programme Management Plan and incorporates the four priority themes for the PCG: i) science integration, ii) knowledge exchange, iii) capacity strengthening and iv) data management.

The Knowledge Exchange Strategy is also divided into three key activity areas: a) Internal Knowledge Exchange (incorporating science integration and capacity strengthening), b) External Knowledge Exchange, and c) Data Exchange and will be accompanied by annual work plans, which will outline and cost a detailed set of activities for each area.

The PCG is working closely with the UPGro Knowledge Broker, the consortia research teams, the UPGro Ambassadors, and the National Geoscience Data Centre to achieve the aims and objectives defined in this strategy.

On gender issues, the programme has a clear potential to achieve good results and generate positive change. Research clearly shows that improved access to groundwater disproportionately improves the lives of women, due to the predominant burden on them to undertake the job of water collection and of the job of child care etc. where illness results from access to low quality water sources.

An example of this can be seen in the Hidden Crisis project, which involves women from water point committees in each community/village in the process of mapping out the water points across the village and record the history of performance and management of each water point. However, so far evidence of such examples is weak and sparse and the programme will need to improve the way in which he monitors impact of programme activities on gender issues. This should be underpinned by a clear action plan, which should also help the refining of indicators on gender disaggregated data under output 2.

Monitoring progress throughout the review period
Over the past year the Knowledge Broker, in consultation with the consortium, has led a revision of the UPGro logframe and data collation processes. This has been discussed and approved by the PEB and based on a trial reporting process run with the catalyst projects last year. The DFID SRO led this review with input from NERC, ESRC and the Knowledge Broker, who provided a report against the revised logframe.

NERC led a light-touch mid-term review of programme in September 2017. This was to get a qualitative assessment on whether the programme is meeting its objectives and to gain feedback on the effectiveness of the commissioning processes and management structures. This is one part of a two-part review, part 2 being a broader review involving a number of DFID and NERC funded programmes in the water sector. This second part will be commissioned in the coming few months.

This Annual review has been shared with NERC and ESRC and will be discussed at the next PEB meeting in November 2017.