BUSINESS CASE
ASIA REGIONAL TRAFFICKING PROGRAMME 2011 – 2015

STAGE 1 – SCOPE

Executive Summary

Overview

- A four year regional programme that aims to reduce the number of women and girls from being trafficked and to protect the rights of women and girls who migrate for work from Asia.
- It will reduce the number of women and girls who are trafficked by 10% (60,000) within the four year programme period.

The Need

Asia has the highest prevalence of trafficking victims.[1] 80% of those trafficked are women and girls, most of whom are coerced and exploited in the sex industry, garment sector or domestic work. Trafficking has harmful devastating life-long psychological and physical effects on the victims, who often lack appropriate information, are denied access to services or the ability to exercise voice or choice to escape coercive or harmful situations.
[1] 3 per 1000 inhabitants compared to 1.8 per 1000 inhabitants globally. (UNODC)

South Asia has the second worse gender equality measures in the world[2]. They are the poorest, most vulnerable and have little choice or control over their own lives. Fewer than 35% of women in South Asia are in paid work[3], compared with 60.5% in Sub-Saharan Africa. Social exclusion in Asia is an added dimension of trafficking risk and vulnerability – most of the women and girls trafficked are from low castes, tribes, ethnic or religious minorities.
[2] World Economic Forum Global Gender Gap Report 2007; Economist Intelligence Unit Women’s Economic Opportunity Index 2010 UNDP Human Development Report: Gender Related Development Index & Gender Empowerment Measure 2009 Report
[3] International Labour Organization, Key Indicators of the Labour Market database 2009

This programme will help deliver DFID’s transformative Vision for Girls and Women and tackle one of its key priorities to Prevent Violence Against Women and Girls. It will also contribute to the other priority pillar promoting Women & Girls’ Economic Empowerment through better wages, working conditions and remittances from safe labour migration and alternative economic opportunities if have the option to work closer to home and avoid the risks of trafficking.

Human trafficking is one of the largest profit-making illegal industries in South Asia[4]. Trafficking is illicit & often ‘invisible’; it relies on coercion, deception, vulnerability, poverty and low status of women & girls. It is fuelled by corruption, collusion, lack of political will and government capacity to effectively tackle trafficking through protective laws and effective justice & criminal systems and ineffective cross-border monitoring and cooperation. The low status of women is fuelled by discriminatory policies, attitudes and practices towards women and girls.
[4] Human trafficking is estimated to generate US$32 billion globally a year, according to UNODC

Definition of Trafficking:

The definition of trafficking used for this programme is the internationally agreed Protocol to Prevent, Suppress and Punish Trafficking in Persons, Especially Women and Children[5]. The term includes recruitment, transportation, harbouring human beings by threat, use of force, coercion, abduction, fraud, deception or abuse of power for the purpose of exploitation. The definition of exploitation includes, at a minimum, sexual exploitation, forced labour or services, slavery or practices similar to slavery. There are internationally agreed indicators for all of these elements.
[5] The term “trafficking” refers to the recruitment, transportation, transfer, harbouring or receipt of persons, by means of the threat or use of force or other forms of coercion, of abduction, of fraud, of deception, of the abuse of power or of a position of vulnerability or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purpose of exploitation. Exploitation shall include, at a minimum, the exploitation of the prostitution of others or other forms of sexual exploitation, forced labour or services, slavery or practices similar to slavery, servitude or the removal of organs. Source: Protocol to Prevent, Suppress and Punish Trafficking in Persons, Especially Women and Children, supplementing the United Nations Convention against Transnational Organized Crime (article 3 (a). This supplements the Palermo Convention Against Transnational Organised Crime. Key references & guiding principles for the programme will be based on Internationally or regionally ratified instruments & agreements, including ILO & Human Rights Conventions, SAARC Convention, Colombo Process.

Intervention Summary and Expected Results

The first phase of the programme (Year 1) will focus on Design & Inception:

- Inception / pilot programmes that could be scaled up or replicated
- Design of full Business Case, Theory of Change and Evaluation Framework
- Evidence Paper

The second phase (Years 2-4) is full implementation of the programme and could support interventions such as:

- Integrated approaches that interrupt the trafficking chain - linking prevention protection and prosecution
- Improving cross-border collaboration between countries
- Innovative partnerships between governments, the private sector, recruitment and labour migration authorities NGOs, community-based organisations, trade unions, international, regional anti-trafficking organisations and donors that have not worked collaboratively in the past.
- Changes in anti-trafficking policies, laws and prevention approaches that show how they will reduce the incidence of trafficking.
- Participation and voice of trafficked women and girls to guide and inform the programme throughout its lifecycle.
- Community-based pilots that can be replicated or scaled up.
- Best practice models of operational research and impact evaluation that show a clear chain of results from the intervention to the number of women prevented from being trafficked.
- Potential for innovation and use of new technologies to prevent trafficking

A selected set of interventions will be chosen that have the potential to demonstrate impact and results in the limited time frame and scope of this programme, but should also contribute to wider public goods of knowledge, policy and practice to tackle trafficking in women and girls.

Focus Countries:

India, Bangladesh, Nepal will be the focus countries of origin or transit, but the programme will also include destination countries within and outside of the region, e.g. Gulf States, Middle East, Europe, Pakistan, Malaysia.

Funding: Funding available is £3m but potential for increasing this if a case can be made in outer years. £.5m needs to be programmed in the first year in a design & inception phase (2011/12)

Sectors:

Women and girls in Asia tend to be trafficked into three sectors: the sex industry, domestic work and the garment sector, sometimes working in several sectors.

Since most of the anti-trafficking investment to date has focused on sex trafficking, this programme will use its limited resources where there are currently significant gaps in investment and evidence, but where vulnerability and risk is extremely high - namely the garment and domestic work sectors. All stakeholders consulted to date agree that this is where DFID is likely to make the most valuable contribution and where impact is more likely to be felt.

Strategic Case

A. Context and need for DFID intervention / Human trafficking is one of the largest profit-making illegal industries in South Asia[6]. Consequently, Asia has the highest prevalence of trafficking victims.[7] 80% of those trafficked are women and girls – unsurprisingly, as South Asia has the second worse gender equality measures in the world[8], which make women and girls more vulnerable to exploitation. Fewer than 35% of women in South Asia are in paid work[9], compared with 60.5% in Sub-Saharan Africa. Trafficking has devastating life-long psychological and physical effects on the victims, and constitutes a serious violation of human rights. / DFID’s Business Plan and Structural Reform Plan reflects a core commitment to lead international action to empower girls and women and to prevent violence against girls and women, including through piloting new approaches. / DFID’s Strategic Vision for Girls and Women[10], launched in March 2011 states that the benefits of investing in girls and women are transformational – for their own lives and for their families, communities, societies and economies, and that empowering girls and women will have multiplier effects for economic growth and achieving all of the MDGs. This programme will contribute to this Vision, which seeks to ‘strengthen results’, ‘encourage innovative approaches’ to preventing of violence against women, empower women economically and ‘work with partners in new and different ways to deliver transformational outcomes for girls and women’. / Combating human trafficking is a key priority for the Coalition Government. Home Office Minister Damien Green stated in June 2010 ‘it is a shocking brutal form of organised crime with men, women and children being abused in the sex industry, forced labour and domestic servitude’. Secretary of State Mitchell stated DFID’s commitment to tackling the drivers of organised crime through its development programmes at the launch of the Strategic Defence & Security Review.[11]. He called for “greater co-operation between the UK’s development, diplomatic and military efforts and an “integrated approach” between government departments and international partners to tackle threats to international stability and security. / Despite investments in anti-trafficking programmes by governments, international agencies and NGOs in the past few decades, there is little hard evidence of the material impact this has made on the incidence of trafficking. There are some inherent problems in collecting data (i.e. how to determine the size of the ‘potential pool of trafficking victims); and there are also very few impact evaluations of large-scale interventions. Strategies and approaches to trafficking address prevention, protection and prosecution, but little evidence of attempts to integrate these strategies, nor is there evidence of wider ambitions that trafficking prevention could contribute to transformational change in the lives of women and girls in source or host countries. Also, the links between labour migration, forced & bonded labour and trafficking – particularly their gender dimensions - have not been well understood. / DFID has some history of funding anti-trafficking programmes in South East Asia, West Africa and Central Asia from 1999 - 2009. Partners included the International Labour Organisation, International Organisation for Migration, UNIFEM, Save the Children, Anti-Slavery International and World Vision. Reviews of these projects revealed some useful lessons[12]. Programme objectives included: building capacity to combat trafficking; advocacy & awareness raising; modelling community-based participatory pilot interventions for prevention, withdrawal and reintegration of victims. Until now, there has been no further funding for anti-trafficking programmes, however, there is an active network of UK NGOs that engage regularly with DFID and the Home Office on UK-related trafficking issues that have been consulted in early stages of design of this programme. / Most of the international, national and local investments and interventions have focused on trafficking in the sex industry. In most countries, there are laws in place, though little political will, capacity or resources to have significant effect in practice. The SAARC Convention[13] on Preventing and Combating Trafficking of Women and Children for Prostitution, whilst a useful starting point, has been widely criticised for lack of implementation or monitoring, nor showing tangible results. Also, it focuses primarily on sex work and doesn’t address other areas of trafficking. / The Colombo Process is another relevant mechanism focused on regional cooperation around labour migration policies and approaches involving annual meetings of labour & migration ministers from Afghanistan, Bangladesh, China, India, Indonesia, Nepal, Pakistan, Vietnam, Sri Lanka, Philippines and Thailand. Ministers met most recently in May 2011 and adopted the Dhaka Declaration which sets out commitments of principle between countries on labour migration, which include addressing the specific needs and concerns of vulnerable groups of migrant workers, especially women, domestic workers, low-skilled and low-wage workers. No mention is made of trafficking, but it has a strong focus on safe migration and protection of migrant workers. The International Organisation on Migration provides a secretariat function from Dhaka and supported development of new legislation on trafficking in Bangladesh. / IOM, ILO, UNODC, UN.Gift, the trade unions, the Institute for Human Rights and Business, Fair Labour Association in partnership with large multinational apparel companies and private sector recruitment agencies, amongst others, are delivering promising initiatives in this area. / The ILO adopted a new Convention on Decent Work for Domestic Workers in June 2011, which sets international labour standards for domestic workers for the first time. Domestic workers organisations have been instrumental in getting agreement of governments, employers and workers organisations. This provides a significant opportunity to tackle trafficking of adolescent girls and women in domestic work, as a legal framework that protects rights, terms and conditions of work will enable violations to be prosecuted and offers increased opportunities for protection, monitoring and scrutiny of domestic labour migration and recruitment. / There are a few results-based evaluations of anti-trafficking interventions – most of which are in the security & justice sector, focusing on prosecution, punishing & ‘rescuing’ of trafficking victims. Smaller-scale community based prevention, awareness-raising and reintegration programmes tend to be small-scale, and have lacked rigorous evaluation. Most initiatives fail to demonstrate results beyond specific project objectives, but strong advocacy efforts by NGOs appear to have had some influence on policy makers at national level. / There are few examples and limited investment of efforts to prevent trafficking of women and girls into forced, coercive or bonded labour in sectors such as the garment industry or domestic work, where there is a high prevalence of trafficking. These sectors are arguably where the most hidden and harmful bonded labour practices often occur, yet largely neglected by the international community. / The consequences of DFID not intervening are: a) more women and girls will be trafficked in South Asia; b) evidence-based approaches for catalytic and innovative approaches to trafficking will be lost; c) the opportunity to demonstrate the value of transformational approaches to violence against women and girls will be missed; and d) DFID will lose the opportunity to become actively involved in an area squarely addressing its current strategic objective of investing in girls and women.
[6] Human trafficking is estimated to generate US$32 billion globally a year, according to UNODC
[7] 3 per 1000 inhabitants compared to 1.8 per 1000 inhabitants globally. (UNODC)
[8] World Economic Forum Global Gender Gap Report 2007; Economist Intelligence Unit Women’s Economic Opportunity Index 2010 UNDP Human Development Report: Gender Related Development Index & Gender Empowerment Measure 2009 Report
[9] International Labour Organization, Key Indicators of the Labour Market database 2009
[10] “A new strategic vision for girls and women: stopping poverty before it starts”, DFID 2011
[11] ### Royal College of Defence Studies on 16 September 2010
[12] DFID Internal Note: Trafficking – investing in prevention in source countries (2009). Lessons include: treating trafficking as part of wider poverty reduction & development activity; district & provincial administrations can be effective advocates for national policy change; community level interventions make a sustainable difference; microfinance can be effective; projects work best when they are part of a comprehensive programme; ILO has a comparative advance in delivery.
[13] South Asian Association for Regional Cooperation

B. Evidence underpinning intervention / At least 2.5 million people are estimated to be trafficked per year[14]. Human trafficking is one of the largest profit-making illegal industries in South Asia – UNODC estimates criminal activity through trafficking generates US$32 billion globally a year.[15] / Trafficking is a fundamental violation of human rights and has devastating psychological and physical effects on the victims and their life prospects. It is driven by poverty, vulnerability and gender inequality. It is estimated that eighty percent of those trafficked are women and girls, according to the Global Report on Trafficking in Persons 2009[16]. Fifty percent of these are estimated to be under the age of 18.[17] There are often cross-border health implications to trafficking, including HIV/AIDS: it is estimated that one newly trafficked girl once infected with HIV has the potential to generate 108 new infections each year[18]. Orphans and children affected by conflict have higher risk of trafficking because of their vulnerability, lack of family protection, information and exposure to risk.[19] / 95% of victims of trafficking are said to experience physical or sexual violence during trafficking. It is estimated that 90% of victims trafficked into EU member states end up in the sex industry, but because data on forced labour such as domestic work is hidden, this figure is most likely exaggerated. Less than 5% of domestic workers globally are paid a minimum wage, most domestic work is unregulated and unprotected by national law; women and girls often subjected to sexual abuse, long hours, arduous physical labour, lack of choice or voice and restricted mobility. / Most countries have ratified the International Protocol to Prevent, Suppress and Punish Trafficking in Persons, with binding provisions in domestic law, although in many countries – including South Asia - these are not comprehensive enough, nor is there adequate political will, resource or capacity to monitor or ensure these are implemented in practice. / Trafficking is directly linked with internal or cross-border migration. Trafficking victims may be kidnapped, tricked or coerced, but most often they migrate for economic reasons - legally and/or illegally with their consent, but end up in exploitative situations of forced or bonded labour in debt, without freedom of movement or access to sources of help, information or communication. Even if they are ‘rescued’ from trafficking situations, the possibilities for a return to a ‘normal life’ are extremely rare. Women who end up in sex work face stigma, exclusion and rejection by their families and communities. Poor families may send their children abroad for work as a survival strategy, even knowing that they might be exploited, so may be reluctant to punish or prosecute recruiters / traffickers. / Most countries do not comply with minimum standards for the elimination of trafficking because they lack political will, resources and/or capacity to deal with it effectively. There are limited efforts on the part of government authorities to combat either internal or cross-border trafficking through criminal prosecution, conviction or punishing traffickers, and inadequate systems to protect victims of trafficking. Governments that promote labour exports rarely put in place measures to protect their citizens from exploitation and abuse once they leave the country. / Most anti-trafficking strategies and initiatives fail to take an integrated approach that include prevention, protection, prosecution, nor do they address the core drivers and enablers of trafficking. Also, the views and experiences of victims of trafficking are rarely sought in the formulation of anti-trafficking strategies and policies, but could and should be a critical part of the solution. / See attached Annex II for further evidence and background. / Trafficking in Asia – focus countries / Asia has the highest prevalence of trafficking victims[20]. In South Asia, 150,000 people are estimated to be trafficked within South Asia each year. It is estimated that 25,000 Bangladeshi and 15,000 Nepali women and children from poor and vulnerable households are trafficked to India annually. However, the accuracy of data should be treated lightly: because it is criminal and illegal, it takes place under the radar and only certain types of trafficking is reported or recorded. / The focus countries of origin for this programme will be India, Nepal and Bangladesh, but the programme will also include destination and transit countries within and outside of the region e.g. Gulf States, Europe, Pakistan, Malaysia. See Attached Annex II for more information on trafficking in each country. / Trafficking approaches / programme areas: / The underlying drivers of trafficking include high unemployment, poverty, social exclusion, gender inequality, corruption, crime and poor governance in sending, receiving and transit countries in Asia. / Most anti-trafficking programmes tend to focus in three areas: Prevention, Protection and Prosecution. These include: / Improving legal and justice systems: ensuring laws and policies adequately protect women and girls from trafficking, and that they are put into effect, with monitoring and redress systems in place; / Improving cross-border collaboration between countries; supporting the implementation of the SAARC convention on trafficking / providing alternative economic opportunities and livelihoods for women and girls, including microfinance, small enterprise and vocational training / working at community level to raise awareness of the risks of unregulated migration, improve access to information and choices for women and girls at risk of trafficking, support for victims of trafficking / managing corruption and inefficiencies in identifying and prosecuting traffickers by working with police and border agencies / support safe migration strategies and improve recruitment practices with private sector partners, trade unions & governments / support host governments and employers of trafficked women and girls to improve living and working conditions of trafficked women and/or support their return home / There is strong evidence that traffickers use the internet, mobile phones and other technologies to promote and organise their ‘trade’, but there are also some examples of new technologies such as tracking and information systems and mobile phones used to prevent, protect, find traffickers or empower victims of trafficking to get help or information. / Evidence on what works / There are a small number of projects that have proven evidence of success. One project, using an independent impact evaluation, took an innovative approach that combined victim rescue with the police, victim aftercare, including provision of economic empowerment opportunities and capacity building prosecution institutions. The evaluation found that the prevalence of commercial sexual exploitation of children had decreased by approximately 72% in the area over the course of the project[1]. / Despite significant investment and a wide range of international, national and local institutions working on trafficking, there is still not a great deal of rigorous evaluation of what works. One of the biggest challenges has been the lack of coordinated effort by different actors involved, and the lack of integration in what they do, resulting in inadequate responses to tackling the supply chain of trafficking. The definition of trafficking is also a major challenge – interpreted by different countries in different ways, which means the nature, scale and treatment of the problem are poorly conceived internationally, regionally and nationally. / There have been a few meta-evaluation studies on anti-trafficking work – all of which conclude that there is a dearth of credible evidence on the impact and effectiveness of anti-trafficking initiatives. A recent global study[21] of anti-trafficking initiatives included three international, two regional and nine national anti-trafficking initiatives, and highlighted common themes, patterns and approaches to evaluation in this sector. It found overwhelmingly that anti-trafficking initiatives are not sufficiently targeted or evaluated for impact, significantly limiting progress in efforts to tackle trafficking. See attached Annex III for further evidence and background on this study and evidence from a range of anti-trafficking approaches.
C. Partnerships / Potential partners and types of partnership will be explored in Stages 2 and 3 of the Business Case. A number of potential partnerships are listed below. Ideally, the programme will support consortium arrangements between international, national, regional and local institutions to complement areas of expertise, generating multi-sectoral, multi-disciplinary relationships with a strong results and evaluation focus. / International / Regional Garment Sector / Institute for Human Rights & Business, ILO, IOM, ITUC, UNGlobal Compact, ILO, UN.GIFT, IOM; EC, SAARC, Geneva Global; Verite, Fair Labour Association, Humanity United, Nike Foundation, Novo Foundation, along with . Key multinationals in apparel sector, Ethical Trade Initiative (ETI); EC, Global Alliance Against Trafficking of Women (GAATW), Women Working Worldwide, RAGS, Anti-Slavery International. / Domestic work / ILO, IOM, International Domestic Workers Network, ITUC, UNWomen, US State Dept, European Commission, GAATW, UNGift, WIEGO (network of academic & women’s organisations working in the informal economy), Women Working Worldwide, Nike Foundation / Other potential partners / UK Government partners – SOCA, Home Office, FCO. / UNICEF, ECPAT International; International Justice Mission, Stop the Traffik, Anti-Slavery International, Migrant Helpline, Save the Children, Human Trafficking Centre, Dalit Freedom Network, Nimbus, Salvation Army, Terre des Hommes, Made by Survivors, Concern / National / Local institutions National & local partners - national government ministries / departments (covering labour, migration, gender, organised crime, recruitment); trafficking survivors networks, civil society organisations; private sector organisations (e.g. Chambers of Commerce), employers; trade unions, research and policy advocacy institutions such as Centre for Social Research in India; media & ICT agencies.
D Operational Research / Impact evaluation / Operational Research and Impact Evaluation will be a critical dimension of each intervention that receives support. A Theory of Change for the programme overall as well as for each intervention should draw on baseline data where available, development of counter-factuals and independent mixed methods of research to assess impact and results and to draw lessons on what works and why; how to assess value for money and the potential for initiatives to be scaled up or replicated. This should contribute to the global public knowledge for the field of trafficking, and improve the design, impact and monitoring of strategies for long-term impact. / The Design and Inception Phase of the programme will enable programme design to be developed alongside the evaluation approach. This will include: / Developing a Theory of Change, / Evaluation & Monitoring Framework / Impact Evaluation design should include: developing a method of comparing different approaches, drawing conclusions about generalisability of the findings and counterfactuals. / Establishing a Steering Committee for the evaluation to ensure the independence of the evaluation, that quality standards are met, and its value for the future. / Evaluation questions will be developed after Phase 1 but might include: / What are the key enablers of trafficking and where can the trafficking chain most effectively be blocked or interrupted? What are the best ways to do this? / How can laws and policies on trafficking, labour migration and labour standards better protect women and girls in practice? How do these laws interact with each other? / What are the key political levers and incentives that can unlock political will and better use of resources to prevent trafficking? / How can the voices and experience of trafficked women inform anti-trafficking strategies? / What are the most effective ‘combinations’ of integrated strategies to tackle trafficking? / Partners for this exercise might include London School of Hygiene & Tropical Medicine; US State Dept, International Centre for Research on Women (ICRW), Global Alliance Against Trafficking of Women; RRMRU (Dhaka-based, link RPC on migration funded by RED); IDS; 3ie; Harvard Kennedy School of Governance; Coffey International, others (to be identified)
E. Impact and Outcome / Results Chain / The intended overall Outcome for this programme is to reduce the incidence of trafficking for garment and domestic work among adolescent girls and women from Bangladesh, India and Nepal. / Key Outputs will include improving the evidence base on strategies and approaches that are likely to yield the greatest impact; a clear theory of change that identifies critical paths in the trafficking chain that disrupt opportunities for corruption, coercion, deception and extreme exploitation; safe labour migration and recruitment policies and practices; improved awareness, protection and working conditions of women and adolescent girls working in garment and domestic sectors in the three countries; empowerment of women and girls to reduce the risk of trafficking, and promoting viable economic alternatives if they choose not to migrate for work. / A Draft Logframe is attached which will be amended after the Inception/Design Phase (Annex 2). / The first phase of the programme will support Inception Projects to test approaches, build new partnerships and a robust Evaluation Framework for designing and delivering an effective results and impact-based programme. This is set out in the Management Case – (B) Design Issues below.
[14] UN Office on Drugs & Crime, FAQs, 2010.
[15] Human trafficking is estimated to generate US$32 billion globally a year, according to UNODC
[16] UN Global Report on Trafficking in Persons, Feb 2009, UN.Gift & UNODC
[17] ‘Now Public: A Fundamental Assault on Liberties – Human Trafficking” Feb 2009
[18] Grey et al 2001, Powers et al 2008
[19] Varouhakis, M., 2002, July 26, "Trafficked Women Are Victims," Global Outlook, Centre for Research on Globalisation
[20] 3 per 1,000 inhabitants compared to 1.8 per 1,000 inhabitants globally
[1] International Justice Mission Cebu Field Project: Overview and Findings Report. April 2010. Project was supported by the Gates Foundation and Nike Foundation. Both foundations are keen to role out this approach.
[21] “Feeling Good about Feeling Bad: A Global Evaluation of Anti-Trafficking Initiatives” by Global Alliance on Trafficking in Women, 2010.

Appraisal Case

Determining Critical Success Criteria (CSC) / Critical questions the programme will seek to answer are set out above in the Evaluation and Monitoring Section above. Critical Success Criteria will be revised and improved in Stages 2 and 3 of the Business Case development but proposed as follows: / CRITICAL SUCCESS CRITERIA WEIGHTING / Integrated approaches that interrupt the trafficking chain - linking prevention protection and prosecution 5 / Improving cross-border collaboration between countries on monitoring 4 / Public-private partnerships that improve recruitment and labour migration policies and practices 4 / New and innovative partnerships between key stakeholders that have not collaborated effectively in the past (including governments, the private sector, recruitment and labour migration authorities, NGOs, community-based organisations, trade unions, international, regional anti-trafficking organisations and donors) 3 / Changes in anti-trafficking policies, laws, monitoring and implementation practices that show how they will reduce the incidence of trafficking. 4 / Participation and voice of trafficked women and girls to guide and inform the programme throughout its lifecycle. 5 / Community-based prevention programmes and reintegration of trafficked women and girls that show long-term potential for change and can be replicated or scaled up. 3 / Best practice models of operational research and impact evaluation that show a clear chain of results from the intervention to the number of women prevented from being trafficked. 5 / Use of innovation and new technologies to prevent trafficking and protect migrant workers from abuse and forced labour 4
B. Feasible options / Issues & Options / There are a range of feasible options for the Asia Regional Trafficking Programme in relation to target group, geographical focus and partnerships. / B1 Target Group / Analysis of trafficking interventions and consultations with the key UK, international and country-based stakeholders so far point to significant gaps in investment and evidence in garment sector and domestic sectors, strongly endorsing a DFID focus in these areas. Sex work will be included where appropriate (women may end up doing sex work if they are trafficked for other types of work). / The options are to focus on: / Garment sector / Domestic work sector / Garment sector & domestic work / Given the complexity of the issues, number of countries, stakeholders and taking a ‘whole value chain’ approach, it might make most sense to limit the focus of this programme. However, we propose Option (c) for the Inception / Scoping phase of the programme to identify where the most promising results & impact might be found. / B2 Geographical Focus / India, Bangladesh & Nepal as countries of origin and transit and destination. Include also key destination countries in the Gulf States, Middle East & Europe. / Focus on India as country of origin and destination from women & girls trafficked from Nepal and Bangladesh as well as between states in India (particularly relevant for domestic work) / Focus on Bangladesh as a country of origin and destination for women and girls trafficked from Nepal and India (particularly relevant for the garment sector) / We would propose option (a) for the Inception Phase in order not to limit the process of identifying promising initiatives and partners, and ensuring that we build on existing work (e.g. Abu Dhabi Dialogue, IHRB in Bangladesh, Jordan) garment sector agreements and new commitments to improve working conditions and migration of domestic workers. A narrower set of countries is likely to be selected for the Implementation Phase. / B3 Partnerships / Delivery Channels / DFID will not specify partners during the Inception Phase, but a list of potential partners has been set out above, and a wide group of key stakeholders have already been consulted and have expressed enthusiasm for DFID’s ambition to foster / catalyse new partnerships and expand existing ones. The Full Business Case will set out options for partnerships and delivery channels based on results of the Inception Phase.
Theory of Change / Will be developed once sectors, geographical focus, partnerships have been agreed. This will need to take into account a range of factors, including: / Migration flows

3.	Key Elements of Financial Case

As part of the Asia Regional allocation, DFID’s FCPD has confirmed an allocation of £3 million under the governance and security pillar and against the Human Trafficking offer outlined in the Asia Regional Operational Plan. / 2011/12 £0.5 million 2012/13 £0.75 million / 2013/14 £0.75 million 2014/15 £1 million / The resources available in the first year will: / finance consultancy support in full business case design and / finance the initial phases of a small number of inception / pilot projects. / The bulk of the resources will be programmed in year two based on the results of pilot / inception projects in the first year. Options for programming include using some or all remaining funds to scale up one or more of those pilot initiatives, or alternatively re-tender against amended criteria. / Depending on the scalability of the work supported and the results achieved, it may be desirable to increase the funding allocated to this pillar. / Value for Money / The funds will directly support a reduction of trafficking through the pilot programmes, and by improving the evidence base, building the capacity of justice and security systems, improving recruitment practices, labour migration and labour monitoring systems, the programme aims to change the environment in which human trafficking occurs. / The findings from one impact evaluation states that anti-trafficking activities focused on security and justice have ‘a two-fold impact: specific oppressors are no longer free to perpetrate abuses and, perhaps even more significantly, their arrests and charges serve as a powerful warning to would-be perpetrators, preventing future crimes so that young girls are never abused’. / Relevant to work on trafficking and the links with labour migration and labour standards, DFID’s Responsible and Accountable Garment Sector (RAGS) Challenge Fund and its Retail Business Innovative Facility (RBIF) are demonstrating value for money and cost benefits of supporting initiatives that improve working conditions and responsible labour practices, especially for women and girls. This programme should benefit from this work. / Unit costs: / The Inception / Design Phase will identify potential projects and partners that have the capacity to deliver the objectives of the programme. Allocation of resources will depend on the number of projects supported, the length of each project, and the size and scale of ambition in each. / This £3m programme aims to prevent trafficking of 60,000 women and girls – amounting to unit costs of around £50 per woman/girl at risk of trafficking. The average prosecution case for a trafficked woman is around £250 in South Asia, so this is a challenging and ambitious programme. However it is hoped that a good theory of change with a results-based framework will demonstrate impacts for specific women with innovative and catalytic partnerships that have long-term strategic impacts.

4.	Key Elements of Management Case

The Design & Inception Phase will inform the full implementation of the programme. The Management Case will be outlined in Stages 2 & 3 of the Business Case, but at this stage, considerations: for the management of the programme should include: / The size of budget is relatively small and investment of appropriate staff time and administrative and management investment will need to be proportionate. / Trafficking is a complex issue and there are multiple international as well as national stakeholders that will need to be consulted and engaged if DFID is to demonstrate its added value and support catalytic, innovative and transformative interventions. / This is a ‘flagship’ programme for DFID: the only trafficking programme we are investing in, and as such there will be strong interest and scrutiny by key stakeholders in the UK, globally and in Asia. As trafficking is a key element of UK’s commitment to tackling Organised Crime, there is strong interest from FCO & Home Office and SOCA. / A. Broad Options / Options for management of the programme might include: / Management in-house throughout the programme with additional project management support / Management in-house for the first phase (2011 – 2012) and out-sourced from start of Second Phase. / Monitoring & impact evaluation components could be independently commissioned with a single delivery partner or sub-contracted by the management agency.
B. Design Issues / The programme will be delivered in two phases: / The first phase (July 2011- Aug 2012) would focus on design, piloting & establishing a monitoring & results-based evaluation framework for the programme. It would involve: / Design of Business Case Stages 2 & 3 (with support of consultancy) / Contracts issued for 3-5 ‘Inception’ programmes that will inform Phase Two and/or identify promising approaches that could be scaled up or replicated – at least one agency covering garment sector, another domestic work. / A consortium of international, regional & national research, evaluation & monitoring institutions will be contracted to develop a coherent evaluation framework for the programme, Theory of Change and indicators for monitoring success and results. It will also propose how evidence and knowledge will be managed and shared in a way that contributes to the global public ‘good’ of knowledge in this field. / Evidence Paper commissioned to examine legal, policy, institutional and implementation issues around girls and women migrant workers trafficked in the garment and domestic work sectors. (Terms of Reference available if needed). This will be delivered in partnership with the Harvard Kennedy School of Government. / Time frame and process set out below and key outcomes set out below: / 1 Two Calls for Proposals sent out with Critical Success Criteria & key outcomes expected / ‘Promising Inception Projects’ (demonstrating promising approaches that could be scaled up or replicated in the Implementation Phase) and / b) Evaluation Framework, Theory of Change, Results Indicators (ideally a Consortium) Aug 2011 / 2 Bids assessed by a Steering Group and 3-6 Accountable Grants or MOUs awarded Sept 2011 / 3 Evidence Paper delivered Sept 2011 / 4 Results of Inception Projects shared & reviewed Mar 2012 / 5 Evaluation Framework agreed Mar 2012 / 6 Decisions on key partners, priorities and results agreed for Implementation Phase Mar 2012 / 7 Stage 2 & 3 Business Case drafted and approved April 2012 / 2. Design of the second Implementation Phase (2012 – 2015) will be set out in Stages 2&3 of the Business Case once the Evidence Paper has been drafted, initial results of the Inception Phase have been digested, and the Evaluation Framework and Theory of Change is agreed.
D. Monitoring and Evaluation / The programme will need to address Monitoring & Evaluation in two phases: Inception phase 2011-12, full implementation 2012 – 2015. Options could be: / An independent agency with expertise in Impact Evaluation identified to monitor & evaluate results and delivery with implementation partners. / Management Agency for Phase 2 sub-contracts Impact Evaluation component, and manages overall results, including Monitoring & Evaluation.
E. Risk Assessment / Detailed risk assessments will be carried out in Stages 2 & 3 as the scope of the programme is developed further in Inception Phase.