 Evidence for Action to Reduce Maternal and Neonatal Mortality in Africa (E4A)

Business Case

October 2011
Acronyms

ARH	AIDS and Reproductive Health
AU	Africa Union
AUC	African Union Commission
CARMMA	Campaign to Accelerate Reduction in Maternal Mortality in Africa
CoIA	Commission on Information and Accountability
CSO	Civil society organisation
DHS	Demographic and Health Survey
E4A	Evidence for Action to Reduce Maternal and Neonatal Mortality in Africa
EmOC	Emergency obstetric care
FEWS	Famine Early Warning System
GAVI	Global Alliance on Vaccines Initiative
GHS	Ghana Health Service
GFATM	Global Fund for AIDS TB and Malaria
HA	Health Adviser
HDRC	Human Development Resource Centre
ICPD	International Conference on Population and Development
IHP+	International Health Partnership+
IPU	Inter Parliamentary Union
LSHTM	London School of Hygiene and Tropical Medicine
LiST	Lives saved tool
MDTF	Multidonor trust fund
MH	Maternal Health
MMR	Maternal mortality ratio
MNH	Maternal newborn health
MNCH	Maternal, newborn and child health
MNM	Maternal newborn mortality
NMR	Neonatal mortality ratio
NPV	Net present value
NSDS	National Statistical Development Strategies
PEA	Political economy analysis
PLG	Project Leadership Group
PMNCH	Partnership for Maternal, Newborn and Child Health
PPD	Partners in Population and Development
RCOG	Royal College of Obstetricians and Gynaecologists
RH	Reproductive health
RMHA	Regional Maternal Health Adviser
RMNCH	Reproductive, maternal, newborn and child health
RMNH	Reproductive, maternal and newborn health
SOWC	State of the World’s Children
TLG	Technical Leadership Group
TSU	Technical Support Unit
UNGA	United Nations General Assembly
UNSG	United Nations Secretary General
WRA	White Ribbon Alliance

Intervention Summary

Title: Evidence for Action to Reduce Maternal and Neonatal Mortality in Africa

What support will the UK provide?

The UK will provide £20 million from August 2011 to March 2016.

Why is UK support required?

Over the past two years, there has been unprecedented attention to the high maternal and newborn mortality rates. Globally $40 billion has been pledged. The UN Secretary General has launched the Global Strategy for Women’s and Children’s Health and a Commission on Information and Accountability (COIA) has been established. The latter has developed a set of recommendations to improve data and increase accountability that have been widely accepted. The UN Secretary General’s flagship High Level Side Event at the 2011 UN General Assembly re-affirmed commitment to the Global Strategy by Heads of State, foundations and private companies.

Building on the Secretary of State’s commitment to the Global Strategy and his participation as a Commissioner, this project will contribute to implementing the Commission’s recommendations and sustain the international momentum at country level. The project will capture and generate evidence on women and newborns dying in childbirth such as who, where, why, and how many. The data will be made available to planners, policy makers, clients, civil society, politicians and others. Advocacy and accountability mechanisms will be supported. Service delivery inadequacies will be highlighted and progress celebrated.

Maternal mortality is the most off-track MDG and progress on maternal and neonatal[1] mortality in most African countries has stalled[2][3]. Approximately 50% of all maternal deaths worldwide occur in sub-Saharan Africa[4][5] with national rates of neonatal mortality the highest in this region[6]. Women in sub-Saharan Africa have a 1 in 13 lifetime risk of dying during pregnancy or childbirth compared to 1 in 4100 in industrialised countries[7]. The region also has the highest maternal mortality ratio among developing regions at 640 deaths per 100,000 live births. There has been little progress on reducing neonatal deaths in Africa, with the smallest reduction in rates (1%/year) globally between 1990 and 2009[8]. Up to one quarter of all under five deaths in Africa occur in the first month of life[9].
[1] Newborn and neonatal both refer to the first 28 days of life and are used interchangeably
[2] 2UN Non-Governmental Liaison Service.  MDG% The Most off Track of All MDGs – Recommendations for the ACP-EU Joint Parliamentary Assembly.  http://www.un-ngls.org/spip.php?page=article_s&id_article=2381
[3] World Health Organization.  Countdown to 2015 decade report (200-1010): Taking Stock of Maternal, Newborn and Child Survival (2010).
[4] http://www.who.int/making_pregnancy_safer/topics/maternal_mortality/en/
[5] Hill K, Thomas K, AbouZahr C et al.: Estimates of maternal mortality worldwide  between 1990 and 2005: an assessment of available data. Lancet 370(9595), 1311–1319 (2007).
[6] http://www.unicef.org/health/index_maternalhealth.html
[7] http://www.unicef.cz/download/MaternalMortality_D7341Insert_English.pdf
[8] Oestergaard, M.Z, Inoue, M, Yoshida, S et al .  Neonatal Mortality Levels for 193 Countries in 2009 with Trends since 1990: A Systematic Analysis of Progress, Projections and Priorities.  PLOS Medicine (2011) volume 8, issue 8
[9] Ibid

Weak political commitment and weak accountability, both underpinned by lack of data, are major contributory factors to the slow progress in reducing maternal and newborn mortality[10]. Maternal mortality reduction in countries across the world has always been associated with increased political focus and use of good data[11][12][13]. Where political will has been lacking, some countries such as Indonesia and Honduras have used evidence to generate the necessary commitment as well as inform strategy[14]. In Africa, where data is generated it is often not in an accessible form for policy makers and advocates. Accountability mechanisms are usually not strong[15].
[10] Ibid
[11] Commission on Information and Accountability for Women’s and Children’s Health.  Keeping Promises, Measure Results (Advanced Copy).  United Nations. (2011).  http://www.who.int/pmnch/media/membernews/2011/20110620_commission_on_accountability/en/index1.html
[12] Lerberghe, W. and DeBrouwere, V.  Of Blind Alleys and Things that Have Worked: History’s Lessons on Reducing Maternal Mortality.  Safe Motherhood Strategies, A Review of Evidence (2001).  http://www.jsieurope.org/safem/collect/safem/pdf/s2929e/s2929e.pdf
[13] Shiffman, J., 2007. Generating political priority for public health causes in developing countries: Implications from a study on maternal mortality. Centre for Global Development Brief.
[14] Human Development Network.  Koblinksky, M.A (editor).  Reducing Maternal Mortality:  Learning from Bolivia, China, Egypt Honduras, Indonesia, Jamaica and Zimbabwe.  World Bank (2003)..
[15] Claasen M and Alpin-Lardies C 2010 Social Accountability in Africa-Practitioners Experiences and Lessons, IDASA-ANSA Africa

What are the expected results?

In six countries (Sierra Leone, Ghana, Nigeria, Tanzania, Malawi, Ethiopia) the project will
- Put neglected EVIDENCE to work by the use of powerful communication – especially through reviewing and acting on the experience of every single maternal and newborn death.
- Raise the profile of maternal health such that each and every maternal death is unacceptable through country and regional ADVOCACY campaigns
- Secure ACCOUNTABILITY mechanisms for maternal and newborn health backed by sound data as part of the COIA activities in 6 countries –including transparency mechanisms for all stakeholders that include civil society groups and the creation of an easily accessible website featuring key information on maternal and newborn mortality.
These three core activities will be based on robust alignment and harmonisation activities ensuring that national and regional activities such as CARMMA, the Maputo Plan of Action and country maternal health roadmaps are strengthened by E4A.

Expected results in the six countries include at least a 400% increase in media reports on performance of maternal and neonatal health, at least three countries with greater than 50% of quality maternal death audits systematised, six countries will have active national advocacy campaigns on maternal and neonatal mortality reduction and will have had parliamentary debates on MNH; there will be evidence based planning in 100% of health facilities in targeted districts with evidence fed into annual/health sector reviews across all six countries. All countries will report to the COIA on resources for RH (international and domestic), there will be a 50% decrease in stock outs of essential drugs and at least a 10% increase in skilled birth attendance. Access to life saving quality emergency obstetric care will consequently increase, leading to a reduction in maternal and neonatal mortality. Given the leveraging effect on other resources, the project is considered to be very good value for money.

How will we determine whether the expected results have been achieved?

An integrated monitoring and evaluation strategy will be embedded within project activities in all countries. Measurement will include evidence availability and use of improved data, quantity and quality of advocacy activities, functioning of accountability mechanisms, drug availability, use of data in sector reviews, extent to which the data is used in national and local planning and resource allocation. The extent and attribution of advocacy and accountability activities will also measured to improve the evidence base of these activities. For best value for money, some indicators will be measured in all countries whilst in-depth research will adopt case study methodology. The specific indicators for each country and research protocols will be developed during project inception.

### Strategic Case
Context and need for DFID intervention

The global burden of maternal and newborn deaths and lack of progress in tackling this problem is borne disproportionately by sub-Saharan Africa.[16],[17] Approximately 50% of all maternal deaths worldwide occur in sub-Saharan Africa[18],[19] with national rates of neonatal mortality the highest in this region [20]. Women in sub-Saharan Africa have a 1 in 13 lifetime risk of dying during pregnancy or childbirth compared to 1 in 4100 in industrialized countries.[21] The region also has the highest maternal mortality ratio (MMR) among developing regions at 640 deaths per 100,000 live births. There has been little progress on reducing neonatal deaths in Africa, with the smallest reduction in rates (1%/year) globally between 1990 and 2009[22]. Up to one quarter of all under five deaths in Africa occur in the first month of life[23].
[16] World Health Organization 2010. Trends in Maternal Mortality: 1990-2008 (http://whqlibdoc.who.int/publications/2010/9789241500265_eng.pdf)
[17] http://www.unicef.cz/download/MaternalMortality_D7341Insert_English.pdf
[18] Hill K, Thomas K, AbouZahr C et al.: Estimates of maternal mortality worldwide between 1990 and 2005: an assessment of available data. Lancet 370(9595), 1311–1319 (2007).
[19] http://www.who.int/making_pregnancy_safer/topics/maternal_mortality/en/
[20] http://www.unicef.org/health/index_maternalhealth.html
[21] http://www.unicef.cz/download/MaternalMortality_D7341Insert_English.pdf
[22] Oestergaard, M.Z, Inoue, M, Yoshida, S et al . Neonatal Mortality Levels for 193 Countries in 2009 with Trends since 1990: A Systematic Analysis of Progress, Projections and Priorities. PLOS Medicine (2011) volume 8, issue 8.
[23] Ibid

There is unprecedented international agreement around reasons for high MMR and NMR, but there is a gap in implementation at Regional and National Levels. The majority of these maternal and newborn deaths are completely avoidable. The global evidence indicates a number of core strategies that are critical to reducing maternal and neonatal mortality, including: skilled birth attendants; referral networks; reliable supplies of equipment and drugs; physical access to services; supervision and regulation; and community engagement[[][24].
[24] DFID 2010 Improving Reproductive, Maternal and Newborn Health: Burden, Determinants and Health Systems, Evidence Overview.

Why then has so little progress been made over the last 25 years? There is a growing consensus (as evidenced in the Global Strategy For Women’s and Children’s Health[25] and the Commission on Information and Accountability for Women’s and Children’s Health[26]) that a lack of political will and focus, weak governance and a lack of effective accountability mechanisms at all levels has underpinned poor progress in this region. Underpinning the lack of commitment to action to reduce MNM is the poor public awareness of the scale of the problem and lack of accessible evidence to inform public opinion and advocacy. The political and health systems failures to address MNH, reflects the lack of real value placed on the lives of women and children.
[25] United Nations Secretary-General. Global Strategy for Women’s and Children’s Health, The Partnership for Maternal, Newborn and Child Health (2010) http://www.who.int/pmnch/topics/maternal/201009_globalstrategy_wch/en/index.html
[26] Commission on Information and Accountability for Women’s and Children’s Health. Keeping Promises, Measure Results (Advanced Copy). United Nations. (2011). http://www.who.int/pmnch/media/membernews/2011/20110620_commission_on_accountability/en/index1.html

Galvanising the links between evidence, advocacy and accountability is now the most compelling opportunity for catalysing change. Insufficient attention has been paid to the power of data, in the hands of advocates and decision-makers, for bringing political pressure to bear for improvements in health service delivery. This includes the use of data to improve management, planning, monitoring and accountability of health services. Decision makers and managers cannot plan effective responses to poor health outcomes if they do not have access to robust data. A health system cannot be accountable to users without access to credible transparent data and advocates cannot influence the political environment without recourse to sound evidence. Experience from other parts of the world, including Europe and the US[27] as well as Honduras[28] suggests these issues are not hard to address. Using the power of evidence to catalyze commitment to action, inform action, and hold all stakeholders to account for health outcomes represents an enormous opportunity to make a difference in the region.
[27] Lerberghe, W. and DeBrouwere, V. Of Blind Alleys and Things that Have Worked: History’s Lessons on Reducing Maternal Mortality. Safe Motherhood Strategies, A Review of Evidence (2001). http://www.jsieurope.org/safem/collect/safem/pdf/s2929e/s2929e.pdf
[28] Shiffman, J., 2007. Generating political priority for public health causes in developing countries: Implications from a study on maternal mortality. Centre for Global Development Brief.

History shows that mortality can be reduced rapidly if evidence can be put into action. Historical experience in countries of the global north, for example Sweden, as well as more recent examples in low income countries has shown that reduction in maternal mortality can be achieved relatively quickly (a halving in ten years has occurred in many settings). The preconditions for change include the use of effective advocacy, deploying sound evidence and information to inform and influence public opinion, and holding policy-makers publicly accountable[29]. This resulted in politicians, policy makers and senior managers providing the necessary inputs and giving sufficient managerial attention to reduce maternal mortality. Additional resources were provided, legislation enacted, new policies adopted, midwife production increased, professional accountability enhanced, and referral systems improved[30].
[29] Wim Van Lerberghe and Vincent De Brouwere 2001 Blind Alleys and things that have worked: history’s lessons on reducing maternal mortality, Studies in Health Services Organisation and Policy, 17, 2001
[30] Ibid

More recently, evidence from the Asia region, specifically Sri Lanka, Malaysia and Indonesia [31][32], shows that reduction in maternal and newborn mortality is possible in poorly-resourced settings. Analyses of success stories reveal the importance of multiple drivers. These include better management of resources to improve access to quality services and an enabling political environment with strong civil society involvement. This has been shown to be necessary to create a political climate which holds decision-makers accountable for failures in the health system. An effective approach to accelerated reduction of MNM, therefore, needs to work strategically across the three areas of evidence, advocacy and accountability.
[31] Ibid
[32] Bullough C, Meda N, Makowiecka K, Ronsmans C, Endang L. Achadi, Hussein J Current strategies for the reduction of maternal mortality  BJOG: an International Journal of Obstetrics and Gynaecology September 2005, Vol. 112, pp. 1180–1188

The time is politically right at the international level for this intervention: The Political and Institutional Landscape. The rapidly changing political and institutional landscape over the past 12 months, characterised by the launch of the United Nations Secretary General’s (UNSG) Global Strategy for Women’s and Children’s Health, marks a unique political opportunity backed by significant new resource commitments. Under the UNSG Global Strategy, USD $40 billion has been pledged to translate policy commitment into practice on the ground. This provides an unprecedented opportunity for major new projects, programmes and strategies to build on an International momentum and forge effective collaborations with traditional and non-traditional actors, to achieve “more health for the money”, through maximising the effectiveness of existing resources.

The Global Strategy places accountability at the very heart of the new landscape for women’s and children’s health. To identify optimal arrangements for global reporting, oversight and accountability a UN Commission on Information and Accountability (CoIA) has recently been set-up, led by WHO. The recommendations place added emphasis on strengthening information systems, including death registration, and on national and international independent review processes to monitor commitments and results. Effective public advocacy that places pressure on, and demands accountability of, policy-makers and decision-makers at every level of health system delivery combined with sound infrastructure and improving the context and culture of data use, are necessary in order to strengthen information systems. The role of civil society will be critical in the development of legitimate accountability mechanisms.

Following the AU Summit in 2010, momentum within the African region has mirrored international momentum, with the Campaign for Acceleration of Maternal Mortality Reduction (CARMMA). The AU was represented on the CoIA and this project will play a role in supporting the AU to align with the CoIA to maximise African ownership of both processes.

Why DFID Intervention is justified
In its Business Plan (2011–2015) DFID places the health and status of women and their newborns high on the national and regional policy agenda. This intervention will directly support DFID’s 2015 targets for safe deliveries and maternal and newborn lives saved and contribute to tracking core indicators as laid out in the Framework for Results. The intervention is directly relevant to the UK’s two strategic priorities of: preventing unintended pregnancies and ensuring pregnancy and childbirth are safe for mothers and babies.

DFID has been at the forefront of support to the CoIA. This project is strategically positioned to provide independent technical support to country efforts to implement recommendations of the Commission. This will not only complement DFID’s global and country strategies in MNCH, but will add the missing piece that has the potential to accelerate the trends for declining MMR and set the conditions for transformative change.

### The Feasibility of Intervening[33]
[33] Information in this section reflects evidence gathered from 3 out of the 6 selected countries during the design phase.

Feasibility at Country Level

The E4A Design Group of experts felt that 6 countries was the maximum number where this approach could realise the desired change within the budget available. A smaller number could have been chosen, but this would have reduced the overall collective impact and risked not including a sufficiently representative range of country situations.

Country selection was based on a range of factors. Criteria were developed to help guide the selection, including the strength of DFID investment in health, political will, burden of mortality, civil society engagement and the consortium’s expertise and experience across each country. Countries were scored for each criterion out of 3 and then totalled. Ethiopia, Tanzania, Malawi, and Sierra Leone scored highest in their respective subregions and were included. Nigeria was added because it has by far the highest mortality burden and the generation of political will was felt to be key to accelerating progress. Ghana was included because of the wealth of data already available and the presence of strong consortium partnerships and donor support. Whilst Nigeria may be among the most challenging, Ghana may be a country where the approach would add value yet can be more easily demonstrated.

Summary of Selection Scoring[34]
[34] A more detailed breakdown of the scoring within each criteria is available upon request. Multiple data sources were used.

CRITERIA	West & Central				North East		East				South
	SL	DRC	Ghana	Nigeria	Ethiopia	Sudan	Tanzania	Rwanda	Kenya	Uganda	Malawi	Zambia	Zim	Moz
Strength of DFID Investment in Health	2	2	2	2	2	1	1	2	3	1	3	2	3	2
Consortium strength - Evidence	2	1	3	2	3	1	3	1	2	3	3	1	2	2
Consortium strength – Advocacy & Accountability	1	1	1	1	1	1	3	3	3	3	2	2	1	1
External Linkages eg H4	3	2	1	3	3	1	2	3	2	3	1	3	1	3
Political Will	3	2	3	1	2	1	2	3	2	1	3	3	2	2
Openness of Civil Society	1	1	3	1	2	1	3	2	1	3	2	3	1	2
Burden of MH	3	2	1	3	3	2	3	2	1	1	3	2	1	1
SUM	15	11	14	13	16	8	17	16	14	15	17	16	11	13

All countries proposed have high levels of maternal and neonatal mortality and include 3 out of the 4 highest burden maternal mortality countries in Africa (see table below). Three countries (Sierra Leone, Nigeria and Ethiopia) are considered fragile states, with potential to transition into more stable states. In all countries delivery of MNH services is fragmented and underperforming in relation to available resources, leading to inequitable delivery of care and insufficient coverage and quality. All countries have policy frameworks supporting the use of data for management and decision-making, but all have weak information, planning and accountability systems which result in less than optimal management and utilisation of existing resources for health.

Maternal and Neonatal Mortality Rates in Six Countries of Focus

	Sierra Leone	Ghana	Nigeria	Ethiopia	Tanzania	Malawi
Maternal Mortality Ratio (per 100,000 live births) (2008 figures)[35]	970	350	840	470	790	510
Neonatal Mortality Rate (per 1000 live births (2009 figures)[36]	49	26	39	35	34	30
[35] World Health Organization 2010. Trends in Maternal Mortality: 1990-2008 (http://whqlibdoc.who.int/publications/2010/9789241500265_eng.pdf)
[36] World Health Organization. World Health Statistics (2011). WHO http://www.who.int/whosis/whostat/EN_WHS2011_Full.pdf

In all 6 countries there are advocacy groups and networks campaigning for improvements in maternal and neonatal health. Nonetheless, efforts are ad hoc, localised and have not achieved the scale necessary to have optimal impact in making users’ and women’s voices heard and to hold decision-makers and service providers to account.

The intervention will work with existing systems, bodies and structures to ensure that in-country capacities and resources are maximised to improve the responsiveness of health systems to meet the needs of women and their children. Political, institutional, economic, social, and conflict context appraisals for the three case study countries, where scoping visits were undertaken, indicate a strong feasibility of intervening, as summarised in the table below:

Country	Situation and Feasibility of Intervening
Nigeria	One in 10 maternal deaths worldwide occur in Nigeria yet only 2% of the global population live there. It is one of the few countries in the world that has seen no significant decline in neonatal mortality. The decentralized structure favours intervening at the state level. Initially focus will be on selected Northern states where the burden of MN deaths is high, strategic opportunities with DFID investments and other MNH programmes exist, and where there is a high degree of political will to improve MNH outcomes. Examples of the use of evidence for transformational change will be used to instigate debate and action on the unacceptability of MN deaths in the intervention states and beyond. Strategic partnerships will be developed with other States to facilitate cross-state learning and to advocate for the replication and implementation of similar effective efforts to reduce MN deaths. This will be supported by targeted interventions at the Federal level through a national advocacy campaign linked to national and sub-national accountability mechanisms.
Ghana	Although maternal mortality estimates vary significantly depending on the source and methodology used, a recent maternal health survey in 2007 suggested it was one of the major causes of death among women in Ghana[37]. In July 2008 the President of Ghana declared maternal mortality a national emergency and announced free national health insurance membership for pregnant women. / Ghana has already begun to develop a data based management culture, although there are weaknesses in the system at sub national level. There is a need to harmonize and strengthen the numerous overlapping and at times incomplete data analysis and dissemination efforts in the country and to effectively translate evidence into action. However, accountability mechanisms are extremely weak and skewed towards donors rather than citizens. / The political, social and institutional analysis indicates a strong potential to strengthen the use of timely and reliable evidence to mobilise change to improve maternal and newborn health, through coordinated advocacy and accountability efforts. This includes strengthening use of existing data to inform decision-making and planning and packaging data in formats that can be used by advocacy groups to hold the health system accountable for delivery of quality services.
Malawi	Infant and under five mortality rates in Malawi have declined over the past 15 years. These indicators have been better than average for least developed countries and Malawi is on track to reach MDG4 by 2015[38]. Despite this Malawi has one of the highest maternal mortality ratios in the world and is off track in achieving the MDG 5 target. There is expressed commitment to scale up and intensify efforts to accelerate progress on MDGs 4 and 5 and a wealth of recent evidence with which to generate targeted plans and programmes[39], however in practice, evidence is rarely used for decision-making. The worsening political and economic situation in the country poses particular challenges for Malawi and threatens progress towards MDGs 4 and 5. Economic hardship through escalating costs of living, punitive taxes, and fuel and electricity shortages will hit poor and at risk populations the hardest, including mothers and children. The international community is being called upon by Malawian civil society to ensure that the lives of the 75% of Malawians who live on less than $1 per day are protected during this political and economic crisis. Within this context, focus will be placed on monitoring public expenditure, particularly resource allocation towards MNH services and the use of evidence based advocacy to expose and help remove various barriers in health service utilization.
[37] Ghana Health Service et al 2009 Ghana Maternal Health Survey 2007. (Although estimates vary significantly depending on the source and methodology used)
[38] National Statistics Office. Malawi Demographic and Health Survey (2010) Preliminary Report. Measure DHS, ICF Macro. Calverton, Maryland, USA (http://204.12.126.218/dhs/pubs/pdf/PR4/PR4.pdf)
[39] The Emergency Obstetric Care survey has just been released and the 2010 DHS final report is due by the end of February.

Feasibility of Intervening at Regional Level
The regional landscape is changing fast and there is a need to ensure that regional efforts are connected with country programming and the international agenda. There are critical players at regional level with whom an intervention can form strategic linkages at national and sub-national levels. These include potential to work with CARMMA in branding and messaging to support national campaigns, and with the AU to align the Maputo Plan of Action with MDG 4 and 5 indicators. The project will form a critical link in feeding country learning through regional bodies and networks, such as the Partnership for Maternal, Newborn and Child Health (PMNCH), to strengthen harmonisation of efforts, and maximise use of resources. Through working at both country and regional level, there is a unique opportunity to support regional learning for greatest impact, in line with the recommendations of the CoIA.

Consequences of Not Intervening

Not intervening increases the likelihood that accelerated reduction in MNM will not occur in the focus countries as health systems remain unresponsive with decision makers and managers continuing to work in an evidence vacuum with no effective internal pressure (through performance management) or external pressure (advocates and civil society, opposition parties and media) to hold them to account. In addition, existing investments in MNH will not reach their full potential as the fundamental disconnect between evidence, advocacy and accountability, identified as being critical to improving the responsiveness of health systems[40] and necessary to improving MNH outcomes is currently not addressed in a comprehensive manner. The overall risk is that if current investment is not optimised then achievement in improving MNH outcomes will be significantly below Global targets.
[40] Commission on Information and Accountability for Women’s and Children’s Health. Keeping Promises, Measure Results (Advanced Copy). United Nations. (2011). http://www.who.int/pmnch/media/membernews/2011/20110620_commission_on_accountability/en/index1.html

B Impact & outcome

The project will result in better maternal and neonatal health services in six countries through generating political commitment and improving efficiency from greater use of evidence. Country implementing partners will work with the public and private sector as well as civil society. International and regional accountability frameworks will also be strengthened.

Impact
Maternal and neonatal mortality will decline in the six intervention countries.

Outcomes
Maternal and newborn health services will be better planned and managed by acting on evidence of need.

Sector monitoring and evaluation capacity will be improved. Evidence will be captured, analysed and made accessible to planners, managers, advocates and policy makers. Accountability systems and advocacy activities will be supported to urge politicians and decision-makers to take action on the evidence available.

The following outcome level indicators apply to all six countries:

- Number of facilities with reliable supplies of reproductive health drugs in the 6 countries (selected from a list 14 essential drugs)
- Human resource for health plans that have specific costs projected for MNH
- Health facility managers use evidence for better management

There are many case studies in which working with parliamentarians[41], using community score cards[42], advocacy[43] at various levels and other processes have resulted in beneficial change, but the evidence of attributable results is still not strong. Where advocacy and better data has led to improvements in service delivery the results chain is context specific[44]. This project, working across a representative group of different country contexts, will build an evidence base for this approach through integration of a strong monitoring and evaluation component. It will help to establish the relative impact of different strategies in different contexts (see management case for more details).
[41] World Health Organization. Parliamentarians Take Action for Maternal and Newborn Health, Hague. WHO (2009) http://whqlibdoc.who.int/hq/2009/WHO_MPS_09.02_eng.pdf
[42] World Bank. Social Development Notes: Participation and Civic Engagement, The Community Score Card Process in Gambia, No. 10 (2005). http://siteresources.worldbank.org/INTPCENG/Resources/CSC+Gambia.pdf
[43] Women and Children First (UK): Advocacy Update. http://www.wcf-uk.org/images/stories/docs/AdvocacyUpdate_2011_July.pdf
[44] USAID. Promoting Accountability for Safe Motherhood, The White Ribbon Alliance’s Social Watch Approach. Health Policy Initiative (2010). http://www.whiteribbonalliance.org/Resources/Documents/HPI-WRA-Promoting-Accountability-for-Safe-Motherhood.pdf

# 2. Appraisal Case

A. Determining Critical Success Criteria (CSC)
The design of this project began in late 2009. After concept note approval in 2010 and an international competitive tender, a design and implementation contract was awarded to an Options UK led consortium, primarily made up of UK academic institutions. Criteria for selection included the quality of consortium organisations and their personnel, the quality of partner organisations, project strategy and value for money.

For this Appraisal, the following success criteria were agreed for the detailed design phase:
Critical success criteria
CSC	Description	Weighting (1-5)
1	Timely, reliable and useful evidence on factors contributing to maternal and newborn deaths	5
2	National and regional advocacy campaign uses evidence to leverage and sustain action through broad civil society engagement	5
3	Data used to hold decision makers to account to meet national commitments on MNH services and outcomes through managerial and political engagement and Commission for Information and Accountability processes	4
4	Feasible and flexible approach to rapidly scale up evidence, advocacy and accountability activities.	4
5	Capacity strengthened at country and regional level to respectively provide and coordinate accurate, regular reporting by countries that is aligned to the Global Strategy	3

An option considered at concept note stage, but not taken forward, was to fund through multilaterals. At the time, promising UN initiatives were confined to harmonising monitoring and evaluation and there was little appreciation for the power of harnessing advocacy and accountability. The landscape and international MNH agenda has changed considerably since the PCN was developed and a multilateral option is reconsidered below.
B. Feasible options
The intervention seeks to address context-specific and information-related systemic gaps in the delivery of MNH programmes in six African countries (Ethiopia, Ghana, Malawi, Nigeria, Sierra Leone, and Tanzania) which undermine their performance and sustainability.

Three options (plus the counterfactual) have been identified, summarised in the table below: The options vary in their degree of emphasis on project independence and advocacy.

Documented progress by many countries that have reduced maternal mortality has been context specific[45]. However, historical analysis of maternal mortality reduction indicate that it has always been associated with increased political focus and use of good data[46]. Case studies suggest no country has achieved a significant reduction without it[47]. The evidence is therefore circumstantial but compelling. Option-specific evidence is highlighted for each option appraisal. In all cases, the most will be made of existing data, and additional data will be collected where it is lacking.
[45] Shiffman 2007 American Journal of Public Health, May 2007, Vol 97, No 5
[46] Wim van Lerberghe and Vincent De Brouwere 2001 Blind alleys and things that have worked: history’s lessons on reducing Maternal mortality, Studies in Health Services Organisation and Policy, 17, 2001.
[47] Whilst there is no reference that concludes this definitively, case studies investigating significant maternal mortality reduction (referenced in this BC) document the need for increased political will and strong data.

Summary of Options

Option	Title	Description
1	Strengthening government planning and reporting systems through better use of data	Working from within the health sector, and through existing funding channels, building capacity for data collection and analysis and strengthen planning and sector reviews to incorporate recommendations from evidence
2	Contribution to international response around RMNH	Supporting multilaterals at different levels to implement the recommendations to measure and report on agreed indicators through national review commissions, improve vital registration, strengthen resource tracking
3	Direct support to national structures and civil society	Significant overlap with options 1 and 2, but with an added emphasis on advocacy and independent watchdog function at country level
4	Alternative use of resources	No investment in better evidence and its use

Option 1: Strengthening government planning systems through better use of data
Five of the 6 selected countries receive DFID budget support and have established sector wide approaches. The focus will largely be at country level and implementation will be through the health sector.

What will be done?
Regional level: Strengthening the AU to monitor and report back on Maputo Plan of Action target achievements, aligned to MDG and Global Strategy reporting frameworks. Country level: Working with facilities, districts and national level to capture existing data, analyse it and inform planning. Data sources could include labour ward registers, maternal and newborn death audits, existing sentinel site vital registration, and mortuaries. Analysis will compare cause of death and contributory factors and identify service delivery inadequacies. Planning processes will be strengthened to adopt a more rigorous review of progress, highlighting deficiencies and informing evidence-based resource allocation and management decisions.

How it will work
The theory of change for this option is that strengthened availability and use of evidence and data within the health sector will result - through evidence based decision making and better performance management - in a more responsive health system with improved availability of inputs (drugs, midwives, ambulances), leading to lower mortality. Funding will be through sector or general budget support in 5 countries. In the 6th country (Nigeria) funds will be channelled through an implementing partner, preferably a funding arrangement that is already established to strengthen information systems and planning. Technical assistance will be embedded within the health sector at various levels. Resource allocation and improved management will be influenced through existing accountability mechanisms such as annual reviews, planning guidelines, sector meetings. Any new or invigorated accountability mechanisms encouraged by the Global Strategy process will be supported. Ranking and comparisons will be used (largely between states/districts but also between countries if useful), as will rewards for better results.

Evidence
A study: ‘Do Health Sector-Wide Approaches Achieve Results?’ by the Independent Evaluation Group (2009 IEG Working Paper 2009/4) examined SWAp experience in 6 countries, including 3 of the Evidence for Action countries (Ghana, Tanzania and Malawi). IEG concluded that Health Swaps have been largely successful in putting in place critical tools and processes for improved sector coordination and oversight. To some extent outcomes have improved, a finding also supported by the DFID Impact Evaluation of the SWAp in Malawi[48], but outcome attribution to SWAps is unclear. Institutional support has concentrated on procurement and financial management at the expense of M&E capacity building and use, with M&E systems remaining very weak.
[48] Pearson M 2010 Impact Evaluation of the Sector Wide Approach (SWAp), Malawi, HDRC and UKAID

Option 2: Contribution to international response around RMNH
Crucial momentum and consensus is being reached in implementing the Global Strategy through accountability. The CoIA recommendations will be formally adopted in September 2011 at the United Nations General Assembly (UNGA). A Workplan is being drafted to implement the recommendations. This option will be anchored at international level (Secretariat is based in WHO Geneva). A mechanism for direct support to countries through a pooled mechanism/challenge fund may be developed.

What will be done
To date the focus of the Commission has been largely on the international arena rather than supporting countries to implement the recommendations The Secretariat with the mandate to implement the recommendations will be supported to lead the process. At international level resources will be tracked and progress at country level monitored. There will be regional alignment of indicators and reporting systems. Countries will strengthen national review systems, as well as scale up vital registration (with additional support from others) and improve routine data collection. Death audits within a confidential enquiry system will be expanded. Resources will be tracked from external sources as well as domestic resources allocated to a) the sector, and b) reproductive, maternal, newborn and child health. National health accounts will be strengthened to supplement tracking arrangements. There would be very limited support for civil society groups and domestic accountability beyond national review commissions.

How it will work
International scrutiny from international reporting arrangements, as well as improved data availability, will exert influence on governments to allocate more resources more efficiently, leading to improved management, greater input availability and lower mortality. Funding would largely be through a multidonor trust fund, managed by a multilateral, to contribute to the maternal and newborn parts of the COIA Workplan. DFID would have to take a lead role in establishing this. Implementation will be largely through UN agencies. We would expect some earmarking to maternal and newborn health as well as to the 6 priority countries we have identified. In-country, the additional information gathered on service delivery performance and resource allocation at national level will serve a strengthened national review mechanism.

Evidence
The CoIA drew on the collective wisdom of its working group members, many of whom are the leading authorities in their field, and used the available evidence to inform their recommendations. The Commission’s report, however, is unsighted on in-country political economy analysis. In order to simplify and harmonise implementation of the recommendations, a pooled funding arrangement makes managerial sense. Although the MAR ranked WHO as weak, they have very successfully managed such an arrangement for decades with the Polio Eradication Initiative. However, such mechanisms often take a long time to become operational. Additionally, the capacity of multilaterals to work with civil society and influence the political economy is recognised to be limited.

Option 3: Direct support to national structures and to civil society
A specific initiative that will implement many of the CoIA recommendations at country level. Data sources will be improved and a political economy lens will be used to focus on those issues and organisations which will effect greatest change. It will systematically ensure that action results from evidence through support to advocacy as well as accountability.

What will be done
In addition to strengthening the AU’s monitoring and reporting role, the project at regional level will also work with civil society organisations to reinforce accountability messages internationally. As with option 1 above, at country level, evidence will be captured and analysed on maternal and newborn mortality to inform planning. Accountability mechanisms (such as national commissions) that emerge from the CoIA recommendations will be supported and fed with evidence that is accessible and easily understood. The evidence will also inform advocacy activities and the capacity of advocates will be strengthened to bring service delivery gaps into the public domain.

How it will work
In addition to improving data capture as indicated above, this option focuses more on strengthening its availability and use by multiple actors through two routes. Firstly, capacity building for CSOs, to support more effective civil society advocacy and empower citizens to hold providers and policy makers to account, will result in political commitment for adequately resourced, responsive health systems. Secondly (as Option 1) - capacity building of government systems to use evidence and data more effectively within the health sector will support strengthened managerial accountability and evidence based decision-making. Both prongs combined will lead to more responsive, capable, accountable MNH services and lower mortality.

Empowering civil society with evidence will enhance system responsiveness by giving service beneficiaries increased voice in decision-making. Service delivery inadequacies will be exposed. Planners, managers and senior officials will be supported to improve performance but, crucially, they will be given increased impetus through advocacy and public opinion to ensure the inputs and information are available to save maternal and newborn lives. In each country a strong understanding of the local context will inform navigation of the political landscape to design and implement coordinated advocacy strategies around which civil society organisations will coalesce.

Evidence
The use of data, including at the subnational level, communicated through advocates and champions led to increased attention and action in Honduras, Sri Lanka, Malaysia, and Indonesia[49][50][51]. These are country examples in which advocacy has played a crucial role in shaping a political environment conducive to safe motherhood programmatic success and where reduction in maternal mortality has resulted from use of evidence and advocacy. This has happened in a range of country contexts, underlining the need to tailor the interventions accordingly.
[49] Shiffman et al 2004 The emergence of political priority for safe motherhood in Honduras, , Health Policy and Planning 2004 19(6):380-390
[50] Bullough C, Meda N, Makowiecka K, Ronsmans C, Endang L. Achadi, Hussein J Current strategies for the reduction of maternal mortality  BJOG: an International Journal of Obstetrics and Gynaecology September 2005, Vol. 112, pp. 1180–1188
[51] Shiffman 2003 Generating political will for safe motherhood in Indonesia, , Social Science and Medicine 56 (2003) 1197-1207

Comparative summary of options

All options have common characteristics, components and risks. This table highlights the differences.

Emphasis, approach	Option 1: Health systems, esp planning	Option 2: International response	Option 3: Direct support
Main implementing mechanism	MOHs	MDTF, H4	Country based institutions, selected based on merit.
Source of evidence	Largely public facilities, but also community. Emphasis on strengthening routine information systems	As Option 1, though more focus on vital registration	Public and private facilities, innovative data sources, strengthening routine information systems
Accountability	Through capacity building of MOH, and national accountability system (CoIA)	As for Option 1, plus support for international oversight	As for Option 1, but also strengthened accountability at local level and through support to CSOs
Advocacy	None	Modest, often quiet diplomacy. possibly some NGO support through H4	Core component, emphasis on supporting advocacy at all levels
Strengths	Ownership, improved capacity of government systems	UK seen to strongly support Global Strategy and CoIA (SoS a Commissioner)	Flexibility to work with the best organisations, advocacy to bring weight of public opinion and strengthen accountability, improved capacity of government systems
Weaknesses	Risk that commitment to reducing MNM remains weak and management does not improve.	Risks lack of focus at subnational level; evidence may remain shallow and not reveal required context specific improvements. / Will take significant time to set up. High transaction costs.	Risk of limited ownership of data by host government

The direct impact on climate change/environment and the quality of evidence of each option is rated in the table below:

Option	Evidence rating	Climate change and environmental category
1 (SWAp)	Limited	C
2 (International response)	Medium	C
3 (Direct support)	Medium	C
4 (Do nothing)	Limited	C

Social Impact

The underpinning basis of this project is to meet the health and survival needs of the poor and most vulnerable women and newborns. Maternal and newborn mortality are among the most inequitable MDG indicators – 99% of maternal deaths occur in low income countries[52]. The proportion of women dying of maternal causes increases consistently with increasing poverty[53][54]. A 55-country analysis of Demographic Health Surveys in the mid-1990s found that women in the richest quintile were 5.2 times more likely to give birth with a doctor, nurse or midwife than in the poorest quintile[55]. Additionally, investing in women’s health may have a greater impact on child health than income-generation interventions[56].
[52] World Health Organisation 2009 World Health Statistics 2009, World Health Organisation, Geneva
[53] O’Donnell 2007 Access to health care in developing countries: Breaking down demand side barriers. Cadernos de Saude Publica 23 [12]: 2820-2834
[54] Graham WJ et al, 2004 The familial technique for linking maternal death with poverty. Lancet 363 (9402): 23-27
[55] O’Donnell 2007 Access to health care in developing countries: Breaking down demand side barriers. Cadernos de Saude Publica 23 [12]: 2820-2834
[56] McGillivray, 2011, Dutta & Lawson Health Inadequacy and Development, , UNU-WIDER,.

A thorough analysis of the cause of maternal and newborn deaths will identify the factors impeding improvements in MNH services. The project will highlight these issues and will reach out to relevant ministries though its advocacy activities.

The project will strengthen voice, responsiveness and accountability in delivery of MNH services in 6 countries, in order to achieve better quality of care and increased coverage to poor and vulnerable groups. Advocacy, supporting parliamentarians, working with media, and better evidence based planning will provide the incentives and technical empowerment to respond to the health needs of poor women and newborns. A coordinated advocacy strategy will be facilitated in each county, adopting lessons from the AIDS response in South Africa[57]
[57] Mobilising and Mediating Global Medicine and Health Citizenship, IDS Citizenship DRC Working Paper 324, 2009.

The poorest women use health services the least and are more likely to die in silence at home. With better access to information on where they are and why they do not use health services, coupled with stronger accountability measures, managers will be more incentivised and knowledgeable to identify how services can better meet their needs. Use of score cards and community enquiry will strengthen local accountability and the voice of poor women. Constructive community dialogue will be facilitated, drawing on international best practice (for instance, White Ribbon Alliance use of public hearings in Orissa, India). Not all approaches will be used in any one country and strategies will be tailor-made to fit each context.

Evidence and advocacy will be used to influence gender imbalances that have the greatest impact on MNH. Issues will be context specific, but will likely include delaying early marriage and changing decision making around use of maternal health services. Verbal autopsies will provide case studies of the underlying determinants of maternal health, highlighting how the status of women is contributing to maternal mortality. Various channels will be used such as media, the church, and traditional authorities to disseminate case study findings and expand their impact far beyond the individual village. Allying with programmes that invest in women and girls, particularly their health, education and income, will be key to raise their bargaining power and status within households, including nutritional status as under nutrition is often intergenerational[58]. The project will seek to shift attitudes on the status of women as well as using evidence to demonstrate the extent of MNM – shifting attitudes that this matters, as well as how bad it is.
[58] Ramachandran 2006 Women and Food Security in South Asia: Current Issues and Emerging Concerns, , UNU-WIDER Research Paper 2006/131

There are many examples where advocacy and accountability approaches have achieved results[59], but the extent of impact and which works better in various contexts is unclear. Strong monitoring and evaluation will help to quantify relative contribution to outcomes to strengthen the evidence base.
[59] Empowerment and Accountability: DPC Introductory Note, Annex 3, Jan 2011.

Political impact

Many African states are characterised by weak participation and accountability. Even those with democratic systems often have weak democratic institutions, a lack of transparency, top-down political governance, and superficial citizen participation in decision-making processes[60]. Recently African governments have increasingly sought to reduce the space for CSOs and advocacy organisations have been hardest hit by laws and regulations[61]. CSOs also lack the coordination mechanisms and leadership needed for strategic alliance building. As a result civil society networks and platforms are underdeveloped[62]. The fragmented nature of CSO activities at country level for maternal health has been confirmed during the design process in 3 of the intervention countries (summarised above in the Strategic Case).
[60] Claasen M and Alpin-Lardies C 2010 Social Accountability in Africa-Practitioners Experiences and Lessons, IDASA-ANSA Africa
[61] Godsater A and Soderbaum F 2010 Civil Society in Regional Governance in Eastern and Southern Africa
[62] Ibid

National and regional policy makers lack the knowledge and analysis of poverty issues because research is often limited or of poor quality or there is lack of meaningful access. Even when data is collected, it is often not presented to stakeholders in a way that meets their needs. African citizens do not know about their governments’ commitments and the extent to which they are being honoured – a pre-condition to any form of citizen-led accountability[63]. Free media and access to information can enable citizens to monitor the states’ activities, enter into dialogue and influence political outcomes[64]. Where data is available it is often not used to hold governments to account[65] as citizens and CSOs often do not have the skills and knowledge to process, analyse or use complex information, and or have limited advocacy capacity.
[63] Social Develop Direct 2011 Inputs for the design of a regional empowerment and accountability programme in Africa
[64] CommGAP 2007 ‘Communication for good governance’, Communication for Governance and Accountability Program, World Bank, Washington DC
[65] Darch C and Underwood P 2010 ‘Struggles for Freedom of Information in Africa’, in Freedom of Information and the Developing World: The Citizen, the Sate and Models of Openness, Chandos Publishing, Oxford

Not surprisingly then, the limited capability, accountability and responsiveness of governments has meant that increased civil rights alone have not resulted in better outcomes in many countries. For maternal health service delivery, political resolve has been a more important underlying factor for change. Success has often been achieved by the availability and accessibility of data, the active engagement of civil society and professional groups, and focusing events that capture the public’s attention[66]. In applying these lessons learned, this project will counter the marginalisation of CSOs and assist them to promote citizen-led accountability. It will generate the required political will for change through strengthening civil society capacity and unity, providing information and evidence to a variety of stakeholders in a form that is accessible, and funding events that highlight the plight of pregnant women and newborns. Mechanisms will be established for providers and policy-makers to be answerable for their actions. Ultimately more accountable management of health services will mean better health outcomes and the potential for closing the equity gap. Using both long and short routes of accountability, this project seeks to systematically support and engage with a) direct mechanisms for citizen feedback, b) organisations that represent citizens’ views, and c) formal accountability mechanisms. Using mobile and web based technology, rapid feedback of service delivery inadequacies will be placed in the public domain. Formal accountability mechanisms such as parliaments and national review commissions (one of CoIA’s recommendations – see below) will be strengthened. Civil society organisations will be mobilised for unified action to coalesce behind a single overarching message and banner. Political economy analysis in all countries will inform the design and implementation of interventions in practice (and will be regularly updated). Such analysis will enable an understanding of vested interests and the potential for resistance as well as identifying the champions, coalitions for change and entry points for action.
[66] Shiffman J 2007 Generating Political Priority for Maternal Mortality Reduction in 5 Developing Countries, American Journal of Public Health, May 2007, Vol 97, No 5

This project is very timely given the international focus on accountability for maternal, newborn and child health. An unprecedented process with global ambition has been taking shape over recent years, culminating in the launch of the UN Secretary General’s Global Strategy for Women’s and Children’s Health in September 2010. G8 commitments and other pledges to 2015 total $40bn, and a Commission on Information and Accountability (CoIA) has been established to ensure pledges are kept and the objectives of the Global Strategy are realised. DFID’s Secretary of State is a Commissioner and the Commission’s work has been widely accepted by African governments. The challenge now is ensuring that momentum is maintained and African countries deliver on their commitments, monitored through accountability mechanisms. This project will align itself with a common multiagency Workplan to implement the Commission’s recommendations. It will demonstrate the UK’s commitment to the CoIA and support its implementation in 6 countries, including 3 of the top 4 with the highest burden of maternal mortality in Africa.

At the regional level, the emergence of regional institutions provides new opportunities for policy engagement and there are various examples of civil society dialogue, though the channels for interaction are generally weak[67]. Various organisations have begun to generate robust research and use information to build networks and influence decision makers. For example, CSOs in East Africa successfully collaborated in supporting a multicountry Caravan that coincided with the AU Summit in July 2010[68].
[67] Godsater A and Soderbaum F 2010 Civil society in regional governance in Easter and Southern Africa
[68] FEMNET 2011 Narrative Report to DFID

DFID’s Africa Regional Plan recognises that regional cooperation is key to managing scarce resources and addressing health, among other priorities. The Plan commits DFID to work with the AU and other regional institutions to strengthen governance and accountability. The regional level has the potential to reinforce country based project activities and there are a number of promising initiatives by both the AUC with its on-going Campaign for the Reduction of Maternal Mortality in Africa (CARMMA), and by regional CSOs such as the ranking of African government expenditure on health by the African Public Health Alliance. Given the AUC’s mandate to monitor maternal and newborn health commitments among member states, the inception phase will assess how the project can support AUC’s leadership and coordination in aligning with the COIA and maximising the role of regional CSOs in maternal and newborn health.

An assessment of other regional initiatives outside the health sector will inform how best to work with them. Examples include supporting national and regional parliamentarians to debate decisions taken at the AU, and working with the Afrobarometer network to a) extract Afrobarometer data on survey responses to relevant health questions and b) facilitate data dissemination and communication activities targeting CSOs, media and policy makers. Other collaborative opportunities include the Sate of the Union which seeks to catalyse African citizenship to track their own government’s progress against its AU commitments, including the Maputo Plan of Action; and the Southern African Trust which brokers improvement in relationships between CSOs and governments for pro-poor policy development.

Impact on Climate Change and the Environment
There are unlikely to be major direct climate change or environmental impacts of the project. There are two main direct effects that the programme may have on the environment:

- The release of carbon emissions from air travel during technical support, monitoring and evaluation, as well as from increased vehicle use from data capture and more frequent supervision.
- Clinical Waste generated as a result of increased clinical activity from improved coverage

The project will attempt to minimise environmental impact using teleconferences wherever possible and increasing the number of country based members of Technical Support Units. Carbon emissions from flights will be offset using a reputable international scheme. Health services will ensure that clinical waste generated will be disposed of responsibly in accordance with good practice.

Environmental health issues, such as water and sanitation, and indoor air quality from stoves, might affect maternal and newborn deaths. Climate change impacts on broader health could also have a longer term effect on general health. However such effects are likely to be minor compared with the immediate concerns of the availability of MN health services[69].
[69] For instance, 30% of child mortality is due to neonatal conditions versus 17% due to diarrhoea: WHO 2009 Global Health Risks: Mortality and burden of disease attributable to selected major risks, WHO
#### Theory of change
Better access to data will impact on maternal and newborn health indirectly through multiple routes. At the political level robust evidence will provide definitive credible indicators made widely accessible that measure the severity of the problem to empower many actors. Accountability mechanisms will be informed by unequivocal data, advocates will use accepted figures, and political champions will be able to reinforce messages and broker solutions. At the technical level, policy and strategy consensus will be facilitated/confirmed, the case for more resources more easily articulated, prioritisation better informed, and accountability of health professionals strengthened.

The evidence used will largely be captured from existing sources, but some primary data may need to be collected if existing data is considered to be insufficient. The lack of evidence of the problem that perpetuates MNM invisibility is mainly linked to lack of accessible data by those who need it. Commonly, data is available in labour ward registers, partial vital registration, mortuaries, HMIS, but not captured and/or analysed in a way that is useful to mangers, advocates and politicians.

The use of data will be substantially strengthened by a) better systems for international accountability against agreed benchmarks, and b) a national coordinated advocacy campaign to highlight service delivery inadequacies and celebrate improvements in health outcomes. A thorough analysis of the local political economy and institutional bottlenecks will inform country advocacy strategies. Advocacy campaigns will be tailored to the local context and the type of engagement with accountability processes will be shaped by local accountability structures. Outside the health sector, targets for advocacy will vary by country, but are likely to include central ministries, Cabinet, Parliamentarians, local/federal government, traditional and church leaders, and donors. Where evidence suggests solutions lie outside the health sector, interventions (including their evaluation) will focus in these sectors. The Theory of Change diagram below is for the recommended Option (3), Options 1 and 2 do not include all steps shown but follow the same general change process.

Inadequate and Recommended Communication Networks for Strategy Development and Implementation

Source: Based on figures 3 and 4 in Bullough et al, 2005, p.1185[70].
[70] Bullough, C et al,. 2005 REVIEW: Current strategies for the reduction of maternal mortality, BJOG Vol 112, pp. 1180-1188

Evidence to be generated, where information is currently lacking, will include eg. tracking outcomes and inputs over time and geography by type of facility; provider performance; causal factors of mortality; quality of care; media content analysis; resource tracking; community perceptions of quality and access; frequency of stock outs of tracer drugs; disbursement of budgets from national to region and district. Robust information collated from existing data sources (ie DHS, HMIS, etc) as well as the generation of new evidence where there are gaps (eg verbal autopsies, facility based death audits) will be made available through a national web-based evidence hub and disseminated to civil society and advocacy networks through locally appropriate media. Innovative approaches such as use of mobile phone media to rapidly report systems failures will be used. Initiatives will work within key strategies in each country on evidence generation, quality, use and capacity building efforts, particularly the National Statistical Development Strategies (NSDS) which each of the six countries has developed.

Evidence capture and analysis will be continually undertaken to inform national and local strategies. The emerging consensus on a new approach with these characteristics (illustrated above) places a high priority on the use of evidence to leverage changes in service-delivery. The crux of the approach involves systematising the effective use of information through a focus on its production and effective dissemination. Institutional collaboration will vary depending on country context and could include national statistical offices as well as ministries of health and academic institutions.

Sustainability

The project strategy will focus on institutional capacity building at three levels, complementing NSDSs and building on training already being conducted in-country: 1) research and training institutes – to build cadres of professionals skilled at data capture, analysis and communication; 2) CSOs and the media – to build skill base within the CSO community and media outlets in knowing where to access data and how to effectively use it in campaigns, reporting, and for accountability; and 3) strategic government stakeholders and providers to build the skill base in using data for decision making, management and delivery of services.

Inputs will be in the form of:
- tools and methods for evidence collection (where there are gaps), analysis and accountability (eg. medical audits, community score cards; mapping and policy tracking, mobile data capture);
- customised training packages for key stakeholder groups in data use (eg. Journalists);
- curricula development with research institutes for training of cadres of M&E officers, where such courses exist.
- Data management training (eg in updating and managing web based information portals);

Project achievements such as more domestic commitment to MNH should minimise post project erosion of gains. The CoIA is a global process that will contribute to sustained momentum in commitment to MNCH. The project will work in partnership with those agencies already strategically committed to the above capacity building inputs such as the Health Metrics Network. Some inputs will have a sustained impact beyond the life of the project such as curriculum and tools development. Others will require longer term support to ensure that capacity development efforts are institutionally sustained in line with NSDS goals and objectives. The most likely mechanism for this will be within the CoIA and IHP+ processes in which harmonised M&E has a central focus with links to on-going funding channels through the UN as well as GFATM and GAVI.

Additional Evidence Base

The project will address the identified systemic gap in the generation, transmission and communication of information for decision-makers. The approach is consistent with lessons learned from famine early warning systems (FEWS) [71] which shows us that while a sound evidence-base is essential for effective decision-making and planning, data alone is not sufficient to change attitudes of policy-makers and opinion-leaders to ensure appropriate release and utilisation of resources, and quality of and access to services. Multiple relationships between government and civil society (including advocacy groups, civil society networks and the media) working together are necessary to drive change.
[71] “The Famine Early Warning Systems Network (FEWS NET) was established in 1985 by the USAID to improve the emergency response capability in Africa, disseminate information and increase food security. One of its main objectives is to provide timely and rigorous early warning and vulnerability information on emerging and evolving food security issues. Its main activities are focused on monitoring and analysing relevant data and information in terms of its impacts on livelihoods and markets to identify potential threats to food security.” Website www.fews.net. Quoted from http://www.un-spider.org/guide-en/3204/famine-early-warning-systems-network-fews-net.

The change desired is making maternal and newborn mortality a political priority whereby political leaders consider an issue to be worthy of sustained attention, and back up that attention with the provision of resources and holding senior managers accountable. Political priority concerns the agenda-setting phase of the public policy process in which problems rise to the attention of policy makers. Issues are more likely to emerge on national policy agendas when they have acquired the status as a serious problem (as opposed to one of the many lower priority conditions existing in a country), ii) policy communities have generated consensus on workable solutions, and iii) political windows have opened, creating opportunities for advocates to link these three streams[72]. Consensus on workable solutions is important in order to present credible policy alternatives to politicians. The first, problem status, is acquired when the problem is one of only a handful of issues that receives major attention and this is achieved through a) indicators that provide evidence of the magnitude of, and change in, severity of a condition; b) focussing events such as natural disasters, crises and forums which give public visibility; and c) feedback to policy makers on performance deficiencies[73]. Political entrepreneurship ie activism by influential individuals and groups that can seize political windows and create or capitalise on opportunities, is often a critical factor[74]. The international community is not without influence. State preferences are often created in the process of transnational interactions[75]. In maternal health there are a variety of UN agencies, foundations, international NGOs and bilaterals active at international and country levels. There are many examples in health where international policy networks have influenced national policy to varying extents[76].
[72] Kingdon JW 1984 Agendas, Alternatives and Public Policies. Little, Brown & Co.
[73] Ibid
[74] Shiffman J et al 2004 The emergence of polical priority of safe motherhood in Honduras. Health Policy and Planning: 19(6): 380-390.
[75] Finnemore M 1996 National interests in international society. Ithaca, NY: Cornell University Press.
[76] Ogden J et al 2003 The politics of ‘branding’ in policy transfer: the case fo DOTS for tuberculosis controle. Social Science and Medicine 57: 179-88

Shiffman[77] applied the above framework to a number of developing country case studies, which revealed remarkable consistency. All achieved progress in maternal health within very different contexts. The most striking of which was Honduras[78], lowering its maternal mortality by 40% from 1990-1997. The credible indicator was obtained through an in-depth maternal mortality study in 1990 which revealed a level that was four times higher than health leaders previously believed. The results shocked health officials and was widely publicised in the media. Focusing events comprised the International Conference on Safe Motherhood in 1987, subsequent regional maternal health priority-setting meetings, and the ICPD in 1994. Senior Honduran representatives actively participated in all of these. Entrepreneurship behind the scenes by mid-level health officials made the issue an ongoing priority, but also proactively promoted action on safe motherhood in all regions of the country. The development of credible policy alternatives was achieved through a strong and cohesive technical working group. The raised national priority also influenced an increase in donor support. Combined efforts resulted in expansion of infrastructure, concentration in areas with the highest mortality (using good data), increase in nurses by 66%, collection of data by community leaders on women of reproductive age, organisation by health centres of community groups to support educational programmes, development of clinical guidelines. Access and utilisation to maternal services increased markedly with institutional deliveries rising from 45% to 61%, with larger increases in rural areas.
[77] Shiffman J, 2007 Generating Political Priority for Maternal Mortality Reduction in 5 Developing Countries, American Journal of Public Health May 2007, Vol 97, No. 5.
[78] Shiffman J et all 2004 The emergence of polical priority of safe motherhood in Honduras. Health Policy and Planning: 19(6): 380-390.

In India[79] credible studies in the 1990s suggested the persistence of high maternal mortality, but it was the power of a few key focusing events, facilitated by advocates and political entrepreneurs, that created political prominence. The first was a White Ribbon Alliance organised march to the Taj Mahal, the second was the hosting of the World Health Day when the Prime Minister met with directors-general of WHO and UNICEF. Later, the Prime Minister expressed deep concern over India’s very high maternal mortality rate. Extensive dialogue resulted in a national consensus on an intervention strategy providing workable solutions. Evidence on the problem as well as programmatic successes continued to be generated. State governments were engaged and civil society organisations worked with the media and parliamentarians, promoting accountability at various levels. The political window arrived with the 2004 parliamentary elections, after which spending on health increased, with maternal mortality reduction as a core priority. Many challenges remain, but the appearance of maternal mortality reduction on the national political agenda has improved its prospects.
[79] Shiffman J Ved RR 2007 The state of political priority for safe motherhood in India, 785-790 BJOG

Although in another differing context, the Indonesian maternal health policy and service delivery transformation process shows remarkable similarities. Sound evidence, focussing events, clear policy alternatives, and advocate activism stressing accountability within a national campaign, resulted in skilled birth attendance doubling in 10 years and maternal health rising from near obscurity to national prominence[80]. The history of maternal mortality reduction in developed countries has strong parallels. As far back as the mid-1700s Swedish authorities were using data to promote action to prevent avoidable maternal deaths[81]. Data was indicating that skilled attendance at birth was reducing deaths. By 1861 40% of births were attended by certified professional midwives and by 1900 it was 78% when the MMR reached 228/100,000 without antibiotics, transfusions and caesarean sections. It was a combination of technical advances and policy environmental factors largely generated by concerns of the medical establishment[82]. As the graph below shows, the USA and England and Wales lagged behind with accelerated progress only starting in the 1930s, despite information on the policy solutions being available since 1900. In the UK local authorities who spent very little on maternal health, and competition between doctors and midwives in both countries was pervasive. Mortality reduction was accelerated through the use of better information from confidential enquiries and the action of pressure groups causing maternal mortality reduction to be a political priority[83]. In the UK committees were formed to create policy consensus and a focusing event, the 1938 Conference, gave rise to a comprehensive Mothers’ Charter. In Sweden the concern of health professionals was sufficient for policy change, but in many other countries legislation was only introduced and funds made available after pressure mounted from civil society. Information was essential, but not enough. The commitment to act on the information was just as important, where advocacy and accountability played a key part[84].
[80] Shiffman J 2003 Generating political will for safe motherhood in Indonesia. Social Science & Medicine 56 (2003) 1197-1207
[81] Lerberghe WV & Brouwere VD Of Blind Alleys and Things that Have Worked: History’s Lessons on Reducing Maternal Mortality
[82] Ibid
[83] Lerberghe WV & Brouwere VD Of Blind Alleys and Things that Have Worked: History’s Lessons on Reducing Maternal Mortality
[84] Ibid

Maternal Mortality from 1870 to 1993 (Sweden, US and England & Wales)[85]
[85] Ibid

Maternal mortality rates in our intervention countries are much higher than many of the case studies above (see Strategic Case above), with considerably more scope for reduction. With significantly more resources being channelled to maternal and newborn health, both within DFID and from other sources, we need to ensure it is well used. Data generated will both inform where it should be allocated as well as provide feedback on how it has been used. This fits with the DFID focus on results, and the call more widely to demonstrate the impact that additional funding has made.

C Appraisal of Options

Closing the gap in the availability of context-relevant evidence while simultaneously addressing accountability weaknesses ensures that information produced will be used appropriately. Were the project to focus exclusively on evidence collation the impact on service delivery and therefore outcomes may be reduced in accordance with reduced accountability (due to the absence of civil society empowerment and community voice). The intervention prioritises six African countries which differ markedly in their local context (socioeconomic, economic, geographical, political). Although the project anticipates this in design, its value-for-money depends on the extent to which the various components of the project interact with the context to achieve desired outcomes.

Given the limited availability of information on maternal mortality and lack of direct attributable evidence of the specific impact that evidence has had on improving maternal mortality the appraisal has not been able to generate specific numbers regarding the number of deaths averted or cost effectiveness of the intervention. E4A will directly contribute to enhancing this evidence base in due course. However, it is anticipated that through raising awareness and highlighting specific areas of concern, E4A will enhance the efficiency of pre-existing spend on MNH in the 6 countries. Direct information on spend on MNH proved to be problematic to gather. As a result data on MNH in the 6 countries in question was gathered by collecting the following information:

Data on donor spend on maternal, newborn and child health in the 6 countries from 2007 and 2008 taken from Pitt et al (2010)[86]. Taking the average of these two years and conservatively assuming that 40% of this spend was on child health, information on donor spend on maternal and newborn health was estimated[87].
[86] Pitt, C, G. Greco, T. Powell-Jackson and A. Mills (2010), Countdown to 2015: Assessment of Official Development Assistance to Maternal, Newborn and Child Health 2003-2008, The Lancet, 376, 1485-1496
[87] G8 methodology for separating women’s and children’s health spend assumes 40% goes to child health since children are 15% of the population and women 25%.

Comparing this with data on external resources for health in 2009 in the 6 countries as a percentage of total expenditure on health, gathered from World Health Organisation[88], led to an estimate of total spend on maternal and newborn health shown in the table below.
[88] WHO 2011 World Health Statistics page 132

Annual Spend on Maternal and Newborn Health, $ Millions[89]
[89] Total spend on MNH is estimated, based on calculations as per explanatory bullet points above, using Pitt and WHO references cited.

	Annual Donor Spend on Maternal and Newborn Health	External Spend % total spend 2008	Total Annual Spend Maternal and Newborn Health
Ethiopia	85.1	39.5%	215.4
Ghana	30.5	14.3%	213.0
Malawi	39.1	99.1%	39.5
Nigeria	87.9	4.9%	1793.1
Sierra Leone	11.8	20.4%	57.8
Tanzania	67.8	56.5%	120.0
Total	322.2		2438.8

The figure of annual total MNH spend of approx $2.4 billion assumes that the ratio of external resources on all areas of health is equal to the ratio of external resources to maternal, newborn and child heath. There is no precedent for this assumption, but it is used as it is very conservative, given the donor focus on MNH.

With total average spend of £4m per annum, E4A represents 0.27%[90] of total annual spend on MNH in the 6 countries. Thus for MNH to represent a cost effective use of resources it would need to enhance the overall efficiency of annual spend by at least 0.27%. This is very likely to take place because MNH spend is currently both allocatively and technically inefficient. Here are some examples of these inefficiencies, taken largely from the intervention countries and highlighting inadequacies in resource allocation and managerial effectiveness.
[90] Based on Exchange Rates as of 21st June 2011, £1: $1.62

Allocative inefficiency

- Resources not being allocated to geographical areas of need instead being focused on urban as opposed to rural areas and as a result low risk pregnancies have the most intervention and monitoring while high risk receive significantly less[91]
  [91] Skilled birth attendance in rural and urban areas dramatically different in all 6 countries, for instance R:U: Ghana 43:84; Ethiopia 3:45; Nigeria 28:65 (Source: http://apps.who.int/ghodata/)
- Resources not going to most cost effective interventions, which are family planning and emergency obstetric care
- Some inputs present eg health worker, but limited equipment or blood supply for clinical intervention[92][93]
  [92] Ministry of Health and Social Welfare 2007 Tanzania Service Availability Mapping 2005-2006
  [93] Independent Review Team 2008 Ethiopia Health Sector Development Programme III Mid-Term Review Final Report
- Sub-optimal allocation of resources to senior staff and not enough task shifting - increasing responsibility and tasks to 'lower' cadres (much more feasible and cost effective but often not done due to unfounded doctor resistance)[94]
  [94] WHO 2006 Working Together for Better Health, World Health Report, WHO

Technical Inefficiency

- Poor resource flow  - resulting in salaries sometimes not being paid and limited non-salary expenditure for facilities/ cleaning /drugs/ power/ fuel[95]
  [95] For example, shortage of fuel for ambulances and supervisory visits is a widespread problem in Sierra Leone
- Weak management / lack of accountability resulting in poor staff motivation and poor quality services[96]
  [96] See, for instance, COWI, Gilroy, EPOS 2007 Joint External Evaluation of the Health Sector in Tanzania 1999-2006
- Stock outs of essential medicines and supplies[97]
  [97] Safe Motherhood Working Group 2009 Preliminary Results from the National EmOC Baseline Assessment
- Lack of quality control / adherence to protocols eg no intermittent presumptive therapy in pregnancy for malaria / management of elevated blood pressure etc- resulting in poor outcomes[98]
  [98] Liverpool School of Tropical Medicine/RCOG 2009 Making it Happen baseline survey
If one conservatively assumes that E4A enhances the efficiency of MNH spend by 0.4% in only the 3rd, 4th and 5th years of the project, and utilising a discount rate of 10%, the Net Present Value (NPV) is £332,000. Lowering the discount rate to 5% raises the NPV to £1.32m. At a discount rate of 12% the NPV becomes zero. Increasing the efficiency impact of E4A to 0.6% in years 3, 4 and 5, raises the NPV to £8.8m.
Changing the overall impact of E4A to allow it to raise efficiency of spend by 0.4% for 2 years after the project has finished significantly increases the NPV to £9.2 million utilising a discount rate of 10%. Maintaining this assumption of E4A impacting on the efficiency of spend for 2 years after the project has finished, the NPV becomes negative when the discount rate is quadrupled to 40%. This sensitivity analysis demonstrates that E4A represents value for money and is a sound investment of taxpayers’ funds.
Discount rates should reflect the value that society attaches to present as opposed to future consumption i.e. the opportunity cost of capital in the country in question. HMT recommends for UK based projects a discount rate of 3.5% be applied. Given that there are more pressing immediate needs in developing countries, and that interest rates are typically higher than in UK, a discount rate of 10% was chosen for this analysis. A higher discount rate was not used as it would reflect too high a preference for current over future consumption.
D. Comparison of options
Options compared for achievements regarding Critical Success Criteria
CSC	Weight	Option 1		Option 2		Option 3
		Score	Score (w)	Score	Score (w)	Score	Score (w)
1	5	4	20	4	20	5	25
2	5	1	5	3	15	5	25
3	4	3	12	5	20	4	16
4	4	3	12	3	12	5	20
5	3	4	12	5	15	4	12
Totals			61		82		98

#### Option 1, Strengthening Government Planning and Reporting, involves working within the health sector, strengthening the planning cycle by providing data on MN mortality and the reasons behind the unacceptable levels. Planners will be assisted to factor this into their sector plans. This option maximises ownership and will be in line with the sector wide approach, but does not tackle institutional inertia and political commitment. In essence it will be business as usual with better information, yet limited incentives to take the action required. The major risk is that any change will be cosmetic without stronger accountability.
#### Option 2, Contribution to the International Response, puts the UK government directly behind implementation of the Global Strategy’s Workplan to implement the Commission’s recommendations. The recommendations are likely to make a significant difference to the political visibility of MNH at country level. All three options within this BC will support the Workplan, but this option puts all our support in the UN basket. This has two major drawbacks: a) a multidonor trust fund will take too long to set up and will be DFID transaction heavy; and b) the Workplan will focus on accountability, but will be lacking significant civil society challenge. As with Option 1, the risk is that change will be small and incremental and not involve the step change in political will and attention that is required.
#### Option 3, Direct Support to National Structures and Civil Society, will have the largest impact on the inefficiencies described above largely due to the additional advocacy component. Data on mortality, publicised case studies, and service delivery inadequacies will be frequently in the public and technical domain. MN mortality will be the forefront of the political agenda and allocative and technical inefficiencies will be highlighted as causal factors contributing to unacceptable health outcomes. This option seeks to repeat the successes of other countries that have dramatically reduced MN mortality in a relatively short period of time, often within a resource constrained environment. This is the recommended option.

E. Measures to be used or developed to assess value for money
The cost benefit analysis for E4A rests on the premise that the project will enhance the efficiency of pre-existing spend on MNH. While specific cost-effective metrics are hard to develop due to the lack of specific information on MNH spend, the high levels of allocative and technical inefficiency existing at present in MNH spend suggest that this is likely to take place.

Evidence that E4A has represented value for money can be determined by the extent to which the highlighted measures of allocative and technical inefficiency improve in the 6 countries, and the overall level of political attention devoted to MNH. While attributing any change to E4A will be problematic due to the host of other initiatives going on, project evaluation will establish in more detail the cost-effectiveness of E4A and will be used as a guide for future funding decisions.

If E4A has no impact on the political discourse in the 6 countries regarding the urgency of action on MNH then it would no longer represent value for money. It is likely that E4A will have a varying degree of impact across the 6 countries. Drawing on the impact evaluation subsequent value for money assessments will seek to tease out this distinction between progress achieved in the 6 countries and assess whether overall E4A has represented value for money.

3 Commercial Case

A. Statement of procurement/commercial requirements for intervention

Intervention title	Evidence for Action to Reduce Maternal and Neonatal Mortality in Africa

Sub-project	Options Consortium activities: generation of evidence, advocacy, strengthening of accountability
Procurement route	Direct

Sub-project	Evaluation Oversight
Procurement route	Direct

The project will collaborate at international level, support Africa regional level and specifically operate in 6 countries in Africa. Multilateral organisations will be among the collaborators, but any support will be in kind and no indirect procurement will take place.

The range of skills and knowledge in this multisectoral (public, civil society, academic) project requires the skills and expertise from a range of organisations. In order to achieve coherence, maximise synergies and economies of scale, and minimise transaction costs for DFID, project implementation has been contracted to a consortium. The management agent (MA) will manage all consortium sub-components. The procurement process had to identify an MA that could mobilise the requisite technical and operational skills, innovation, institutional linkages and cost savings.

Given the emphasis within the project on evidence, data capture and analysis, the MA will have strong evaluation skills and a separate robust evaluation would be duplicatory. However, external oversight is required to ensure objectivity and quality assurance in evidence generation and measuring results.

B. How does the design use competition to drive commercial advantage for DFID?

The project has been design led since the expertise in evidence generation and advocacy lies with the consortium partners. The project has been tendered as a ‘design and build’ contract through an open OJEU process. The TORs specified the project objectives:

a) develop and operationalise a tailored methodology that provides evidence on maternal and newborn (MN) mortality for context specific planning;
b) support the actions of MN health advocates at regional, national and sub-national levels in the generation and use of mortality data;
c) strengthen accountability mechanisms at all levels for progress on MN health

In order to maximise the range of potential suppliers and the effectiveness of the project, neither the countries nor the detailed approaches were specified in advance. Of the four bids received, two stood out strongly and were invited to present. Options was selected as MA based on the quality and track record of the organisations and personnel involved, their value for money, technical understanding and sound methodology.

The Human Development Resource Centre will be used to support oversight of monitoring and evaluation.

C. Market response
The technically demanding nature of the TORs and the range of expertise required meant that consortia were likely to form. We are confident that the winning bid includes the global leaders in the field, and organisations with the capacity to manage and deliver results.

D. Cost drivers

The key cost drivers are as follows:

Staff
International staff, mostly short term, technically supporting implementation, providing guidance, overseeing capacity building, collaborating with international organisations
National staff within the selected implementing partner institution to implement activities

Partner organisations
Civil society organisations and academic institutions implementing project activities such as advocacy and accountability events, capacity building, data analysis and dissemination, as well as equipment, overhead costs

Travel and subsistence
International and local travel to, and within, the 6 countries, as well as key regional and international events

Costs will vary between countries and will be higher where infrastructure is poor. The country implementing partners will be selected during the inception phase. Partner effectiveness will be assessed alongside costs and a balanced approach taken. DFID will be involved in this process to ensure VFM is achieved, through use of appropriate criteria. We will combine support functions with implementing partners such as sharing office space. Open reporting of activities, funded by DFID and others, will minimise risks of double funding.

We will use existing CSOs, with various funding sources, which will be mobilised to work together to achieve results greater than their individual contributions. Accountability activities will involve UN organisations (collaboration mentioned above) engaged in similar work to achieve cost effective synergies and cost sharing.

The contract will be constructed such that 45% of costs will be invoiced quarterly according to achievement of actual expenditure milestones and 55% invoiced based on delivery of KPIs, for which the timing will vary (see contract management below). The MA will provide information on fees and expenses that account for each output/milestone cost with details of how fee rates are constructed, including the overhead, salary and profit margin making up each fee rate.

E. Procurement process

A Project Concept Note for the project was approved in January 2010, following extensive consultation with stakeholders internationally, and health advisers at country and headquarters on regional added value to make a difference in maternal mortality in Africa. Improvement of data and its use was identified as a high priority. A project design group was convened incorporating procurement, health, epidemiology/data, economic, research, and social development/governance disciplines. Nine EOI were received in response to the OJEU notice and 4 bids were received. They were appraised by the group and the contract awarded to Options.

F. Contract management

The MA will report to DFID on performance against key performance indicators (KPIs), linked to delivery phases, which will be objectively verified. The M&E plan will include all KPIs and those tracked more frequently will include routinely monitored data. Most KPIs will be aggregated and some country-specific, depending on context. Any significant constraints will be highlighted. KPIs will be derived from log frame indicators, which will be confirmed during the inception phase. They will be in aggregate form on a quarterly basis for overall project and contract management, but there will be more detailed six monthly updates, project discussions and an annual review. Reports will be reviewed by the DFID project manager, country advisers, and Leadership Group (see below).

The six monthly/annual reviews of outputs will monitor whether achievement is on track and deliverables are being produced. There is a contract break from inception to implementation when we determine outputs and payments. The MA will be incentivised to meet the agreed outputs/deliverables in the logframe as part of the milestone payment criteria that will be agreed before the implementation contract is awarded. The inclusion of KPIs in the reporting requirements will give clear visibility of both what is being achieved and how other deliverables are progressing. The reporting itself will also be a deliverable. The contract includes Section 2 Clause 29 Payment to cover non-payment based on unsatisfactory completion of the deliverables.

Options will use DFID terms and conditions and follow these in contracting with the sub-contractors, adapting them as necessary to make them applicable to the subcontractor. This will assure that all partners will work in pursuit of common goals under the same terms and conditions. The contract has the option of a 2 year extension based on satisfactory performance. Any cost extension will be up to 50% of the original contract amount. Any contract changes will require justification and amendment request which will be approved by both PrG and the Project Manager. The abovementioned review process will inform the management of change throughout the contract life.

The Management Case outlines oversight arrangements. The Project Manager is the Regional Maternal Health Adviser, based in the Africa region, and already supporting HAs in the 6 countries as well as liaising with the AU. The RMH Adviser will be supported by the DFID Project Leadership Group spanning the full range of expertise required for project implementation.

4 Financial Case

A. How much it will cost?

The expected cost of the project is £19.8 million over 5 years plus design costs of £0.2m. The annual breakdown is as follows:

2010/11	2011/12	2012/13	2013/14	2014/15	2015/16
£200,000	£1,700,000	£5,000,000	£4,800,000	£4,700,000	£3,600,000

Allocation is as follows:

Design	£200,000
Options implementation	£19,300,000
Reviews, M&E oversight	£500,000
(See Monitoring and Evaluation in the Management Case for details)

B. How it will be funded: capital/programme/admin

It will be funded 100% from programme, and has been budgeted for in the Operational Plan for ARD, but will extend one year beyond the current Operational Plan period. Further approval from HMT is also required, as the project will extend beyond the SR10 settlement. DFID departments may want to provide additional resources to this project and there is flexibility to accommodate this – see Commercial Case.

C. How funds will be paid out

The management fee for the contract and for the core costs has already been agreed. Funds will be disbursed via a contract between DFID and Options UK and between DFID and the Human Development Resource Centre (HDRC) for monitoring and evaluation oversight. Payments will be disbursed 3 monthly in arrears for 45% of the contract value, and 55% will be disbursed in arrears when KPIs are achieved. Forecasts will be updated regularly based on detailed monitoring of project implementation.

If the project is terminated early through no fault of the MA, DFID will reimburse the suppliers for any costs that have already been incurred, or that will be necessarily incurred and the supplier cannot avoid or recover (including reasonable costs associated with project run down).

The HDRC will be reimbursed upon receipt of satisfactory reports after inception phase, for each annual review and end of project evaluation.

D. How expenditure will be monitored, reported, and accounted for

Options UK will submit a quarterly detailed certified statement of reimbursable expenditure and show evidence of acceptable performance against KPI. There will be stringent tracking of unit costs and inputs to outputs to ensure funds remain secure and provide VFM. The level and projected costs of short-term and long-term personnel and TA work will be based on an agreed annual workplan.

Options will submit Annual Audited Accounts signed by the Finance Officer on behalf of the implementing partners and certified by their auditors.

5 Management Case
## A. Oversight
The DFID Project Leadership Group
DFID will establish a Project Leadership Group (PLG) to oversee implementation of the E4A project and set strategic direction of the project. It will be chaired by the ARD Regional Maternal Health Adviser and supported by the ARD MDG Programme Manager. PLG membership will comprise a multisectoral team similar to the E4A Design Group:

Core members:
- ARD Regional Maternal Health Adviser
- ARD Regional MDG Adviser for Africa
- Two country health advisers (rep West Africa and East Africa) from the 6 countries
- ARD Programme Manager
- Representative of the ARH team in PRD to ensure coherence with broader policy developments and links to the CoIA
- Representative from RED

Attendance from the following as needed:
- Regional Economic Adviser for Africa
- Regional Social Development Adviser for Africa
- Regional Governance Adviser for Africa
- Regional Statistics Adviser for Africa
The PLG’ functions are to:
- Review and approve six-monthly project updates and monitor implementation of annual review recommendations
- Review and approve annual reviews and the project completion report
- Review and approve payment against KPIs whose delivery coincides with 6-monthly meetings
- Decide on substantive changes to annual project plans, M&E plan, log frame and project direction
- Review and approve M&E outputs, with the guidance of external M&E peer review
- Ensure coordination and collaboration with other DFID research, projects and international organisations
The MA will report to the PLG, which will meet on a six-monthly basis, and the E4A Project Director (Options UK) will attend when required. In the unlikely event that significant changes are urgently required, the Regional Maternal Health Adviser has the mandate to make decisions on behalf of the PLG, but will make every effort to consult Core PLG members by email and phone.
Regional level work is important but small scale and will be overseen by the Regional Maternal Health Adviser supported by PLG members who are working with regional organisations. This oversight function will include consultation with regional stakeholders such as UN regional offices, AU, and regional advocacy organisations.
At country level, oversight will be provided by the Country Steering Group which will be chaired by the relevant government authority and involve all key stakeholders such as the DFID, Ministry of Health, academic institutions, advocates, parliamentarians, and other development partners. The country DFID Health/MDG Adviser will be a key link between the PLG and country level activities as well as between the project and the local DFID operational plan. The Management Agent is required to work closely with all of these stakeholders and all will be consulted during annual reviews. If sector policy requires, country Steering Committees could be integrated into another mechanism provided effectiveness is not compromised.
Enhancing the voice of the beneficiaries is a central component of this project. Their voice will be heard at the local level through direct accountability activities and represented at higher levels through the project’s advocacy and national accountability support.
## B. Management
The project will be managed by the Regional Maternal Health Adviser who will be in frequent contact with the Options E4A Management Team. Financial reports, compliance and administrative functions will be managed by the DFID Programme Manager in the MDG ARD Team. Implementation management by Options will be at multiple levels:
Consortium
Options will lead a consortium of organisations comprising research departments of four major universities, Immpact, the Centre for International Health & Development, the Centre for Global Health, Population, Poverty, and Policy and the London School for Hygiene and Tropical Medicine, with advocacy and accountability experts from the White Ribbon Alliance and Advocacy International. Options has good experience of leading consortia for multi-year, multi-country and multimillion pound programmes and is well positioned to lead this consortium.
Project Management
Led by the Options Project Director, an E4A Management Team will be responsible for implementing the project, including coordinating activities, managing the consortium, procurement oversight, quality assurance, and for the overall assessment of progress against the logical framework indicators. It will also be responsible for dissemination of evidence, for producing six-monthly progress reports and an Annual Report specifying progress against the log frame in advance of the AR.
Technical Management
The Management Team will report to the Technical Leadership Group (TLG) comprising experts from within the consortium, each with a supportive thematic responsibility. Reporting to the DFID PLG, the TLG will:
- work with the E4A Management Team to ensure overall progress towards the project’s objectives
- advise on evaluation design
- advise on strategic options
- provide regular leadership advice for the scoping of assignments
- directly contribute technical support to country-level activities.

Country & regional level management
In each country, the E4A project will establish a Country Team, hosted within a local institution. The configuration of technical support at the regional level will be defined during the inception phase following a mapping and assessment of regional opportunities to add value to existing evidence, advocacy and accountability frameworks. For each Country/Regional Team, a Technical Support Unit will be established, each led by a member of the TLG. The TSUs will be a virtual group comprising TLG and country based experts and stakeholders. It is envisaged that country-based TSU membership will increase during the project.
Managing links with other projects
In each country the Country Team and TSU will ensure synergy and complementarities with projects being implemented by DFID country and regional offices as well as those of other development partners. Leveraging of resources will be a key strategy employed to ensure value for money.
Opportunities will be maximises for shared impact with DFID’s project Preventing Maternal Death through Unwanted Pregnancy (PMDUP) within which Options has a discrete consultancy support role. Opportunities to build institutional networks by working alongside the proposed regional programme of support for empowerment and accountability (supporting Afrobarometer, the State of the Union Initiative, the Southern Africa Trust and possibly others) will also enable this intervention to gather weight behind issues and campaigns around MNH in order to advocate for change and achieve greater results. Support to the AUC will be in accordance with other DFID assistance such as the current African Union Governance and Capacity Programme (2011-2012).
The DFID Health Services Team plan to provide £3m to WHO (from an existing Aid Effectiveness and Accountability Programme) to support leadership in implementing the COIA Workplan. This adds to pledges by Norway and Canada on the same. E4A’s focus at regional and country level provides strong complementarity to COIA secretariat support. The Management Agent will sign an MOU by December 2011 with WHO to agree responsibilities and coordination arrangements in implementing the COIA Workplan.

DFID Project Management
Technical Leadership Group
DFID Country Office
In-country Steering Group
E4A Management Team
Country Teams
WHO Global Strategy Agenda for Action
Technical Support Units
DFID Project Leadership Group
Regional activities
E4A Organogram
C. Conditionality

Not applicable.

D.	Monitoring and evaluation

A detailed monitoring and evaluation (M&E) strategy will be designed during the six-month inception phase of the project.

Team

Within the Options Consortium, the London School of Hygiene and Tropical Medicine (LSHTM) will coordinate M&E activities in collaboration with the country M&E teams. Given the differing yet complementary skills of the consortium partners (i.e. economic analysis, qualitative and quantitative evaluations and research, impact studies, etc), the consortium will draw upon the expertise of all the evidence partners in the design and implementation of the M&E strategy in each country. Importantly, LSHTM will also incorporate key political, accountability and advocacy analysis and studies into the strategy through the involvement of both domestic and international experts. This will allow the project to fully investigate and report on pathways and linkages between evidence, through advocacy and accountability and the impact on key outcome measures.

Approach
Whilst numerous case studies exist, there is very little robust evaluation and research on the effectiveness and direct impact of advocacy and accountability efforts in influencing change. Concerted efforts will be placed on detailing how advocacy and accountability initiatives will be monitored, evaluated and researched. This will be an important addition to the evidence base on how advocacy initiatives deploy evidence to leverage and sustain action and how data can be used to better inform project direction and learning and to hold decision makers to account to commitments and targets on maternal and newborn health. Specifically, the strategy will incorporate experimental design, political and economic analysis and qualitative studies among other approaches, to help to identify important factors that influence whether advocacy and accountability initiatives have been successful.

As part of this analysis, particular attention will be paid to the areas where current levels of evidence are not strong. These include:
- the cost effectiveness of advocacy efforts for maternal and newborn health
- detailed case studies of what works in terms of advocacy and accountability, their attribution, and how contextual factors affect impact on maternal and newborn survival
- causal chain analysis detailing mechanisms for change including specific elements of advocacy and accountability actions

The specific indicators for each country, research protocols and evaluation questions will be developed during project inception. The framework for this will be based on the project’s theory of change model - focussing on the key evidence, accountability and advocacy levers for better access to services and a more responsive health system. Pathways to these levers converge on increased demand for change, more political commitment, more evidence-based decision making and more use of evidence within accountability structures. Below are some evaluation questions that will be included.

Overall questions
- What are the critical ingredients that create pace for change?
- What is the balance of efforts that have together effected change?
- Which ingredients have been less crucial?
- Do the results represent value for money and are there unintended benefits that need to be considered?
1. Questions on demand for change
- What is the public priority on this issue? Is voting affected?
- Is there a consistent voice for change in the media?

2. Questions on political commitment
- Are there high profile parliamentarians who speak on this issue?
- Is there political momentum around the continuing death toll?
What do state actors find valuable about relationships with non-state actors and what are the incentives to engage and respond?

3. Questions on evidence-based decision-making
- Are national health sector decisions made on the basis of evidence?
- Do local data affect decision-making at regional and distract level?

4. Questions on use of evidence in accountability structures
- Does the COIA operate well based on recently collected evidence?
- Is local level evidence used to hold services and decision makers to account?

Multidisciplinary teams including political analysts, epidemiologists and social scientists with long experience in evaluation of complex interventions will collaborate in this effort.

Organisation

A balance will be struck in terms of maximising use of the technical expertise within the Consortium, objectivity in evaluation and value for money. A semi-independent[99] evaluation with additional external oversight is proposed:
[99] Although a consortium member, the LSHTM will not be part of project implementation in order to maintain distance and independence

- Whilst LSHTM will lead the development of the M&E Strategy and conduct selected studies and facilitate cross country learning, M&E activities will be integrated within the work of the country teams and technical support units.
- As per DFID’s policy[100], the project will make use of existing country capacity and expertise for evaluation functions. In each country a technical M&E review group, made up of local technical experts, will critique the M&E strategy and recommend improvements tailored to the local situation.
  [100] Building the Evidence for Reduce Poverty. The UK’s policy on evaluation for international development, July 2009, DFID
- Where possible independent data sources (e.g. Demographic and Health Surveys) will be used to evaluate the effect of the intervention or at least provide supporting evidence on plausibility. Rigorous evaluation designs will be put in place where possible to determine whether observed changes are attributable to the project.

The national platform approach proposed by Victora and colleagues (2011)[101] will be adopted. This is based on continuous monitoring of different levels of indicators; gathers additional data before, during, and after the period to be assessed by multiple methods; and uses a variety of analytical techniques to deal with problematic biases in the data. E4A will build on, and/or collaborate with other evaluations by partner and donor supported projects, with rigorous quality assurance standards adhered to. The inception phase will be used to maximise harmonisation opportunities, particularly with national activities linked with the recommendations of the COIA.
[101] Victora et al 2011 Measuring impact in the Millennium Development Goals era and beyond: a new approach to large-scale effectiveness evaluations, Lancet 2011: 377:85-95

Given the strong technical capacity of the LSHTM and collaborating partners, a full external evaluation will not be good value for money. However, the Human Development Resource Centre will be contracted directly by DFID during the inception phase to peer review and quality assure the development and implementation of the M&E strategy. In collaboration with the local technical M&E review group, the external reviewer will review research questions, protocols, and data collection tools, ensure objectivity and technical quality of data collection and analysis, confirm/assess progress during annual reviews, quality assure evaluation findings and M&E outputs, and assist with the project completion report process. DFID will provide overall oversight through its PLG and close monitoring by the Project Manager.

Components

The following components will be included:

A routine monitoring plan.
The monitoring plan will be developed in line with the outputs specified in the logframe and in accordance with the specific components underlying the theory of change. Monitoring will as far as possible utilise routine health information systems, but ad hoc data capture at baseline and subsequent regular intervals may be necessary when routine data are unavailable. Certain types of data capture (for example MNH messages by type of media) will be on-going while other data will be captured at baseline, mid-term and at the end of the project (such as percent of facilities effectively implementing quality audits or accountability mechanisms established at country level). The baseline will incorporate qualitative data to capture the voice of stakeholders and civil society with a stake in evidence, advocacy and accountability. Six-monthly summary reports will be submitted against the annual workplan, KPIs and log frame, using a common template, and will inform annual reviews.

Outcome and impact evaluation.
A rigorous evaluation of outcome and impact will be built into the project at the design stage. Although there is little doubt that evidence, advocacy and accountability are essential to achieve sustained reductions in maternal and neonatal mortality, the impact of the project on the quality and use of MNH care and mortality will depend on a number of extraneous factors which may be beyond the control of the implementers. Constraints in terms of human resources, or difficult geographical access, for example, will influence the overall impact of the intervention, even in a context where women’s voices are being heard and decision-makers and service providers are held to account. Although attributing a specific outcome to the project may not always be possible, a multitude of studies will be conducted to examine a single phenomenon in an effort to help solidify linkages between DFID support and stated measures in the logframe.

To determine the size of effect attributable to the project, implementation will need to be phased over time using a stepped wedge design and/or randomly allocated across districts so that changes resulting from the project can be separated from those unrelated to the intervention. Only variables implemented in targeted areas will be measured and compared to non-intervention areas to avoid contamination by countrywide interventions. Operations research will also need to be put in place to document the mechanisms through which the various components of the project impact on health service quality and use and health outcomes in order to inform further scale-up and replication in other contexts. Specific attention will be paid to identifying and tracking key contextual factors. Determining the direct impact of addressing structural/external factors in reducing MNM will be challenging. Qualitative studies using stakeholder enquiry and interviews will assess the combined effect in helping influence the broader challenges outside the health sector.

Dissemination of evidence
Evidence from 1 and 2 above will be disseminated to project partners, and national and international policy makers to maximise uptake and impact of the findings and promote transparency. Results will be published through DFID channels, project web-pages, presentation at conferences and publication in peer reviewed journals.

4. Engagement
This will include a stakeholder analysis of key players such as WHO, UN, Civil society, the International Initiative on Impact Evaluation (3ie), and the Network of Networks on Impact Evaluation (NONIE). A similar process will be undertaken in each country. The engagement plan will feature an in-depth validation of how the underlying principles of evaluation will be applied in the E4A project - namely
- Usefulness
- Cost-effectiveness
- Accuracy
- Credibility
- Impartiality
- Transparency
- Ownership and Alignment
- Harmonisation
- Mutual accountability

E. Risk Assessment
See below for a full project risk analysis table. Key risks around political and technical commitment are already partly mitigated by the Global Strategy/CoIA process. Technical risks include capacity challenges to address service delivery inadequacies such as health workers or supplies. The involvement of country Health Advisers, links to a steering committee and maintaining pressure through advocacy will provide incentives for the capability and resources to be reallocated. Low service utilisation of poor women despite quality improvements will be monitored and will inform policy, plans and donor programming. A risk assessment for each country will be developed during the inception phase.

Risk	Probability	Impact	Mitigation
Political Risk
Lack of political interest or commitment to reducing Maternal and newborn mortality and a reluctance to reallocate resources for MNH services.	Medium	Medium	CONSORTIUM: The purpose of the project is to mitigate this risk. Accountability strengthened by the project will be reinforced by the UNSG’s Global Strategy/CoIA.
Political instability undermines potential for impact, particularly in fragile states.	Medium	Low	CONSORTIUM: Options’ experience in fragile states, including Nigeria and Sierra Leone, includes procedures for monitoring political unrest, and maintaining the focus of key stakeholders on the intended impact of the project as long as it is safe to operate.
Advocacy messages create conflict and tension with governments rather than constructive dialogue.	Medium	Medium	CONSORTIUM: The Options Consortium was built specifically with this in mind. Our partners are skilled at developing constructive dialogues with government. Success will be celebrated. UN commitment to implementing the CoIA recommendations will support constructive engagement. In-country Steering Committees will guide the project on how far to challenge inadequacies.
Institutional Risk
Inadequate numbers of skilled health workers available particularly at the sub-national level to deliver evidence-based MNH services.	High	Medium	CONSORTIUM: Supporting and working through the health sector and partners, will influence HR policy and strategy (esp retention, deployment and workforce planning).
Inadequate capacity to develop performance appraisal tools and processes for stronger managerial accountability	Medium	Medium	CONSORTIUM/DFID: The project will work with other reform and DP supported interventions to strengthen performance appraisal systems and prioritise implementation in the health sector.
Limited number of effective accountability groups capable of holding government and health professionals accountable.	Medium	Medium	CONSORTIUM/DFID: The project approach includes identifying and implementing a strategy to provide technical support to existing active groups to enhance their effectiveness if needed.
Weak capacity in Government to capture, analyse and interpret data threatening sustainability of the project.	High	Low	CONSORTIUM: All country operational plans will include capacity building component delivered by our evidence experts to strengthen capacity. This will be linked to National Statistical Develop Plans and health sector M&E strengthening plans. Where sustainable capacity strengthening is required beyond 5 years project will identify other partners to continue support.
The country based evidence that is needed is far greater than project resources available.	Medium	Medium	CONSORTIUM: Funds will not be available to conduct large surveys. However, all countries have on-going intiatives that capture and analyze data. Project TA will facilitate an evidence network that ensures the data that is collected is robust and credible, it is triangulated with complementary sources, and its use is maximised.
Insufficient independent media outlets	Medium	Low	CONSORTIUM: During country assessments, suitable media outlets will be identified, and if they are deemed to be insufficient, advocacy strategies will explore use of alternative communication channels.
Sensational and irresponsible reporting – raising issues but counterproductive	Low	Low	CONSORTIUM: Training and close working with media to ensure responsible reporting – avoid sensational reporting.
Country assessments identified lack of capacity in critical advocacy skills such as branding and effective messaging.	Medium	High	CONSORTIUM: The project will deliver strategically targeted communications and branding support. It will provide technical support to create of templates; messaging and context specific communications strategies to build ready to use material to jump start efforts where the weak link is branding and communications. Longer term capacity and skills development will be delivered to enable sustainability.
Lack of local ownership and internal drive for this effort.	Medium	Medium	CONSORTIUM: The project will recruit experienced local teams; within credible well respected host agencies with existing internal drive and determination to improve MNH outcomes. The local teams will build alliances and identify synergies and strategic opportunities to catalyse change in focus outputs. Existing relationships with consortium members to National and regional networks across the region and within the focus countries are already strong and these will be further developed and built on to add maximum value.
Project impact ends when the project ends – a lack of sustainability.	Low	Medium	CONSORTIUM: The project will develop context specific sustainability strategies to ensure that over 5 year life of the project capacity is developed in the key focus areas in country and across the region. The project will also develop, where appropriate, strong networks of experts across the region to support and progress skills development, strengthen peer review and support and build lasting regional expertise.
Accountability efforts by civil society threaten to demotivate and demoralise providers who, with inadequate supervision and resources, will resent feeling under greater scrutiny. Tensions between health workers and community can create a blame culture among providers.	Medium	Medium	CONSORTIUM: The project aims to avoid blame and shame approaches and use positive deviance to highlight good practice and learning to counterbalance examples of poor performance and outcomes.
Perception of the outcome and outputs of this project among stakeholders will be confused; with expectations that this project is primarily focused on research and data collection.	Low	High	CONSORTIUM: Early implementation of clear and targeted communications strategy among key regional and national stakeholders; to include early newsletter and other written and branded material to raise profile of this project and articulate its purpose effectively. The purpose of this effort will also be to ensure that potential opportunities for collaboration and partnership are identified early on.
Economic Risk
Governments and donors cannot meet their spending commitments towards reducing MDG 5 given the current economic climate.	Medium	Medium	CONSORTIUM/DFID: The project approach to strategically integrate evidence, advocacy and accountability will be used to support efforts to maintain pressure on governments and donors to keep spending commitments in place. The project will work strategically with other groups who share this aim and are already working to hold them to account. It will liaise with accountability mechanisms under the UNSG’s Global Strategy/CoIA.
Accurate measurement of resource allocation to RH at National and District Level is hindered by lack of transparent systems for budgeting and resourcing	Medium	Medium	CONSORTIUM: In each country the project will prioritise working with Development Partners and other existing projects and groups that are focused on governance and budget tracking in order to build on existing progress made in these areas. The UN will be leading on this (CoIA recommendations) and Options will play a supportive role with other partners.
Social Risk
Poor women and children do not use the evidence-based services.	Medium	Medium	CONSORTIUM: The data systems will be strengthened to collect data on who is accessing services to highlight whether poor women and children are using the services. The information will be used to inform policies and strategies to increase utilisation of poor women to services.
Political complexity and the nature of power relationships means that raising voice alone may not translate into increased accountability. For example, raising demand without formal avenues of engagement and response can lead to weak personal and patronage driven responses.	Medium	Medium	CONSORTIUM: The project will navigate the political landscape and design appropriate approaches for voice and accountability that are driven by the context and actors.
Conflict Risk
Conflict either re-emerges or intensifies in post conflict or on-going situation. Countries particularly at risk: Nigeria, Sierra Leone.	Low	High	CONSORTIUM: The project maintains information channels with security networks and emergency procedures to minimise the risk of disruption to activities. Advocacy activities aim to maintain priority for maternal and child health issues even in the event of political upheaval.
Overall risk level	Medium	Medium	CONSORTIUM: risks will be continually monitored and updates will be included in every report. DFID: will ensure effective internal communication to take timely action. Links to DFID in-country offices will be strong to assist with problem solving and mitigation.

F. Results and Benefits Management
The logframe below is indicative at this stage. It needs to be flexible to include the reality and situation within the 6 countries as well as to respond to the emerging Workplan for implementing the CoIA recommendations. The inception phase will enable CoIA alignment, as well as measure baselines and confirm milestones and targets. Each level of operations (regional and each country) will have a nested logframe which will be aggregated into the consolidated project logframe. Extent of nested LF alignment with project LF will be specified after the inception phase. Baselines and targets are only given for 3 countries (Ghana, Nigeria, Malawi) which were visited during the design phase (the design budget was insufficient to visit all 6). After 6 months implementation (the inception phase) targets and baselines for all indicators for these 3 countries will be confirmed. The targets and indicators for the remaining 3 countries will be drafted after 6 months and finalised after 1 year. Finalisation of the nested and project log frame with all indicators and targets will be a contractual deliverable by the Management Agent.
.