Type of Review: Annual Review

Project Title: International Partnership for African Fisheries Governance and Trade (PAF)

Date started:	2011	Date review undertaken: October 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
DFID supports the International Partnership for African Fisheries Governance and Trade (PAF) which is based in the New Partnership for African Development (NEPAD) Planning and Coordinating Agency (NPCA) in Midrand, South Africa. The Programme aims to support an emerging political cadre in defining processes that will strengthen Africa’s capacity to consider, determine and implement responsive reforms in fisheries governance and trade. / DFID support is directed at the governance, management and implementation of the Programme through the NPCA. This involves: / the development of a Comprehensive African Fisheries Reform Strategy; / support to countries in integrating fisheries into the Comprehensive African Agriculture Development Programme (CAADP); / operation of a policy Think Tank[1] which supports the high level Conference of African Ministers of Fisheries and Aquaculture (CAMFA); / increasing African Voice in policy decisions, and / a West African Pilot Project (WAPP) to pilot policy options in Sierra Leone and Ghana. / The funding from DFID agreed in 2009 was £6,936,000 over six years. A new Memorandum of Understanding was signed in October 2011 to cover the period until 2014. This created a Special Purpose Vehicle (SPV) within the NPCA to allow additional funding from other sources. DFID is providing £4.8 million during the second period.
[1] The Think Tank process is one of dialogue, discussion, learning and sharing between a number of stakeholders from government, industry, academic institutions and international organisations.

What are the expected results?
The expected impact of the Project is that African fisheries resources contribute sustainably to inclusive growth. The indicators and milestones for this are: / Indicator 1: National/regional governance reforms enable wealth generation from fisheries providing economic, social and environmental benefits to the Africa region, its nations and the African people. / The milestone for the end of the project is: Reforms yield tangible economic (surplus over costs) and welfare benefits in fisheries of at least 4 Africa states. / Indicator 2: National and regional economic growth is facilitated through integrated trade in fish and fish products. / The milestone for the end of the project is: Trade-related measures implemented in at least 4 African states require effective resource governance. / Indicator 3: Fisheries Sector contributing to CAADP. / The milestone for end of project is: CAADP Compact targets of 6% agriculture contribution to GDP increasingly met by fisheries in at least 4 African countries. / The Outcome of the Project is National, regional and international fishery policy reform is guided by a Comprehensive African Fisheries Reform Strategy (CAFRS). / The CAFRS is being developed by PAF as an output of the intervention. The Indicators for this are: / Indicator 1: CAFRS adopted and used to guide reform in at least 5 African states. / The milestone for the end of the project is: CAFRS becomes de facto guide to fisheries reform. / Indicator 2: Lasting African / non-Africa partnerships facilitate innovation in the analysis and resolution of reform processes / The milestone for the end of the project is: NEPAD takes forward long-term strategy cementing Africa/non-Africa partnership. / Indicator 3: Increasing recognition of a coherent “African voice[2]” on effective reform [3]at international fora. / The milestone for the end of the project is: NEPAD takes forward a coherent African voice, with sustained inputs from international partners. / Indicator 4: Regional Economic Integration (REI) on fisheries policy informed by CAFRS. / The milestone for the end of the project is: RECs playing an incremental role in sub-regional and Africa regional fisheries strategy and reform.
[2] The African Voice discussed here refers to a coherent African approach to fisheries policy that is able to influence the global fisheries policy debate.
[3] What constitutes “effective reform” will be decided by the CAFRS as it evolves.

What is the context in which UK support is provided?
Fisheries and aquaculture make crucial contributions to the global wellbeing and prosperity. Today, fish constitutes an important source of nutritious food and animal protein throughout the world. In addition, the sector provides livelihoods and income, both directly and indirectly, for a significant share of the world’s population. Fish and fishery products are among the most traded food commodities worldwide, with trade volumes and values reaching new highs in 2011 and expected to carry on rising, with developing countries continuing to account for the bulk of world exports. / However, many fish stocks are biologically fully or over-exploited with only 12.7% being not fully exploited[4]. Those that are biologically fully exploited are capable of generating greater economic benefits if fisheries are managed such that resource rents[5] are generated. In Africa the majority of fisheries are poorly managed and the lost contribution of the fisheries sector to economic growth is estimated to be as high as $2 billion per year. / Although more than 10 million Africans depend upon fish and fisheries for their livelihoods and 30% of the population for its nutrition and food security, current and future benefits are threatened by this mismanagement. This is likely to be further affected by climate change in the future in that the distribution of species, biodiversity and biomass are likely to change - especially in fisheries where safe biological limits have been reached or exceeded. Compounding this mismanagement, and resulting from it, is that the potential of fisheries development is often ignored in wider economic planning and was largely overlooked in the Comprehensive African Agriculture Development Programme (CAADP) process. As a consequence fisheries development is often poorly supported by governments and donors. / The PAF project aims to support an emerging political cadre in defining processes that will strengthen Africa’s capacity to consider, determine and implement responsive reforms in fisheries governance and trade. DFID’s role in this process is to support the African Union/NEPAD to facilitate a Pan-African participatory process of research, dialogue, and lesson learning which moves towards the design and implementation of a Comprehensive African Fisheries Reform Strategy with broad Ministerial backing. An important part of this process is to develop more economically rational ways of managing the fishery such that resource rents from the fishery are realised. This will often require a reduction in fishing effort and the allocation of rights within the fishery. It will generate winners and losers. Key to this process will be how rights are allocated within the fishery, the distribution of the economic benefits generated from resource rent capture, and the institutional reforms that are needed to make such changes fair and sustainable. PAF will develop and test appropriate approaches, and generate the supporting evidence base, that are able to move fisheries to a more economically rational footing which generates sustainable economic growth and welfare benefits. / Linked to this, and merged with it in 2010, has been the establishment of the West African Pilot Project (WAPP) which was set up to inform PAF’s work.
[4] FAO (2012) State of World Fisheries and Aquaculture. FAO, Rome.
[5] The resource rent is the surplus value after all costs and normal returns have been accounted for.

## Section A: Detailed Output Scoring

Output 1: Strategy component: A Comprehensive African Fisheries Reform Strategy (CAFRS ) developed
Output 1 score and performance description: / The Output score is: A+. The output has moderately exceeded expectation. Generally this output is being delivered according to the milestones and the policy reform momentum which has been developed has exceeded expectation.
Progress against expected results / Indicator 1.1: Strategy for reform of fisheries (including aquaculture potential and research needs) developed and agreed by ministerial task force / Milestone: Policy Working Groups established and contributing to CAFRS development by end year 2. Roadmap for Strategy Development Process developed by quarter 2, 2011. / Progress: The PAF sponsored Conference of African Ministers of Fisheries and Aquaculture (CAMFA) of September 2010 detailed some key areas of strategy for the development of African Fisheries. In 2011, the 18th Session of the AU Assembly of Heads of State endorsed CAMFA as its policy organ responsible for fisheries. CAMFA provided the basis of the Comprehensive African Fisheries Reform Strategy (CAFRS). CAFRS is an evolving strategy which is being built on a foundation of evidence, stakeholder engagement and policy dialogue - much of this provided through Working Groups that have been established (see below). / To guide the CAFRS, PAF has facilitated the development of a wider Pan-African Fisheries Policy Framework (AFPF) which will lay down the guiding principles for the Reform Strategy. A Roadmap for taking this process forward was agreed in March 2012. In June 2012 PAF held a Think Tank meeting in Abidjan to develop the AFPF and validate CAFRS broad framework with a number of different stakeholders. At this meeting it was agreed that the final of CAFRS would be validated in November 2012 and would be presented back to CAMFA in 2013. / To internalise the Policy and Strategy, PAF has developed a collaboration with the AU-IBAR to take this work forward in association with FAO, the World Bank and WWF. The planned Pan-African Fisheries Reform and Coherence Mechanism will coordinate the development of the CAFRS. This is a key part of internalising the policy reforms within African Union (AU) institutions. The Mechanism will, in large part, be the technical arm of the African Union which takes the work of the CAMFA forwards after the planned for end of PAF in 2014. It will be a CAMFA Secretariat based in African Union Inter-African Bureau for Animal Resources (AU-IBAR). The Global Environmental Facility (GEF) has been approached, and has committed to fund this mechanism. It is particularly interested in mainstreaming the CAFRS into the CAADP process. / Working Groups on Governance, Illegal Fishing, Trade, Aquaculture and Investment have been formed and are operational. The Trade Working Group was operated through Marketing Information And Technical Advisory Services For The Fisheries Industry In Southern Africa (INFOSA) with overheads funded by the Norwegian Embassy, in Pretoria. It came to an end at the end of 2011. As a follow-up to a previous Steering Committee meeting, it was reported at the 5th PAF Steering Committee (April, 2012) that the Trade Working Group will be reconstituted with the Rural Hub (a Technical Organisation of Economic Community of West African States (ECOWAS) as the new host. Some of the activities will be shared with the Fisheries Commission for Central West Gulf of Guinea (FCWC). / The Working Groups are contributing to the wider understanding of the CAFRS process. They have been particularly helpful in the development and implementation of the post-CAADP Compact National Fisheries Investment Plans and demonstrating how these can add value to, support, and in-turn are supported by, the CAADP process. In March 2012 a PAF Working Group retreat took place in South Africa to increase alignment of Working Group activities with the CAADP. This has led to closer links between the Working Groups and the development of Post-Compact investment interventions in some of the countries. / A key facet of the project has been the use of Think Tanks. They have provided a valuable mechanism for engagement, sharing ideas and learning lessons. The Think Tank meeting held June 2012 on the “Formulation of a Pan-African Policy Framework and Comprehensive African Fisheries Reform Strategy” is an example of how a diversity of ideas and experience can be brought together to inform a way forward. This workshop also highlighted the need to widen the policy framework and include such components as mainstreaming climate change in African fisheries development. In the lead-up to the next CAMFA, planned for in 2013, this process would provide a valuable means to evaluate the current policy-related evidence from the different Working Groups and contribute to the analytical report outlined under Indicator 2.2 below. / Summary: / Overall this milestone is being well delivered and represents a very significant stage in the development of the foundations for the reform process. The majority of the Working Groups are working well and generating evidence that can support the policy reform process. / Indicator 1.2: AU ministerial task force established, supported by NEPAD-based policy Think Tank / Milestone: Ministerial task force established and agreement reached on at least 3 policy areas relevant to CAFRS by early 2012. / Progress: The Ministerial task force was established as CAMFA in 2010 and endorsed by the 18th Session of AU Assembly of Heads of State in 2011. In February 2012 a NEPAD/AU-IBAR workshop on partnership coordination and policy coherence in the Fisheries Sector in Africa was held in Nairobi. At the PAF Steering Committee meeting in April 2012 it was recommended that: / a tripartite framework and coordination mechanisms be established between the African Union Commission (AUC), the NEPAD Planning and Coordinating Agency (NPCA) and the African Union Inter-African Bureau for Animal Resources (AU-IBAR); and that / a post-CAMFA workshop be held between AUC, NPCA, Regional Economic Councils (RECs) and the Regional Fisheries Bodies (RFBs). This was held in September 2012 in Johannesburg. / As mentioned under 1.1 above, the Pan-African Fisheries Reform and Coherence Mechanism will give rise to the internalisation of the PAF into the AU-IBAR and this will be the technical secretariat to the ministerial task force. This currently manifests itself through PAF and the Think Tank process is a means of gaining stakeholder (such as government fisheries staff, academics, consultants, and policy makers) support for, and input to, major policy and strategy changes. The PAF Think Tank has been established for some time and it is designed to: / facilitate debate around different policy proposals; / translate existing and new knowledge into policy options and promote their uptake; / develop and articulate the “African voice” in fisheries international policy; and / co-ordinate the Working Groups and other PAF institutions to foster coherence across the different activities and outputs. PAF staff have regularly engaged with other AU staff during 20011/12 to identify how PAF will become the CAMFA Secretariat, how this will operate and to identify resources for funding. / As regards the three policy areas identified in the milestone, agreement has been reached on the following: / The importance of fully internalising the fisheries reform in the CAADP process if it is to be effective. Of the 40 countries that have signed CAADP compacts, 21 include fisheries in their strategies. / The importance of fisheries in the economic growth of the countries of Africa and the need to reflect this in the policies and plans of the countries concerned. This has started with economic valuations of fisheries in Angola, Gabon, Congo DR, Congo Republic, Cameroon, Sao Tome and Principe, and Equatorial Guinea presented to ministers in Cameroon in September 2012. / The reform process needs to change the way fisheries are developed and this means making difficult decisions about who wins and who loses. It also requires major long-term structural reform that requires substantial sector investment. The World Bank has responded to this with large-scale investment in Ghana and Sierra Leone but with reform triggers built into the funding mechanism. / Summary: / The milestone is well advanced and CAMFA is now an accepted African institution within the AU system. The foundations have been laid for a sustainable role for PAF as the Secretariat to CAMFA within the AU. Whilst the project is moving ahead to generate policy guidance it should also ensure that the policy process is evidence-based and that policy should balance the social, economic, environmental and political needs of African fisheries. / Indicator 1.3: NEPAD structures and processes facilitate the development and political adoption of CAFRS. / Milestone: Trust attracts sustainable funding; NEPAD internships / Progress: It was originally planned that the PAF would develop into a Trust. This has changed and a Special Project Vehicle (SPV) within the NEPAD Planning and Coordination Agency (NPCA) is now in place with a ring-fenced budget and budgetary control mechanism. The DFID funding under the PAF, has leveraged additional funding from other donors. Recent funding sources are shown in the table below: / PARTNER AMUNT OF FUNDING (US$) OUTCOMES / Swedish International Development Cooporation Agency (SIDA) through the Food and Agriculture Organisation (FAO) US$207,000 Fisheries Governance reforms / African Union Commission US$50,000 Coordination mechanism for Regional economic Communities (RECs) and Regional Fisheries Bodies (RFBs) / African Union Inter-Agency Bureau for Animal Resources (AU-IBAR) US$270,000 Comprehensive African Fisheries reform Strategy (CAFRS) / Convention for the Conservation of Marine of Antarctic Marine Living (CCAMLR and UK Foreign and Commonwealth Office US$85,000 Training for African members of the CAAMLR on Port State Measures Agreement / German International Development Agency (GIZ formerly GTZ) US$50,000 Assessment of feasibility on eco-labelling in African fisheries / Africa Caribbean Pacific (ACP) Fish II (EU-funded) US$255,000 Joint development of Regional Fisheries Management Plans for Central Africa (Gulf of Guinea) / Icelandic International Development Agency (ICEIDA) US$40,000 To support an International Institute for Fisheries Economics and Trade (IIET) held in Dar es Salaam in June 2012. / Other Possible Funding: / In addition it is likely that the SIDA funding through FAO (a MoU for this was signed in October 2012) will increase by an additional $600,000. This work is to support the development of CAFRS. / Following a recommendation from CAMFA to establish the Pan-African Fisheries Reform and Coherence Mechanism, NEPAD, AUC, World Bank, FAO and World Wildlife Fund (WWF) developed a project with US$25 million funding from GEF and $US123 million from the World Bank to finance fisheries investments in Mauritania, Comoros, Tanzania and Mozambique. This was agreed in October 2011. The GEF/World Bank commitment is dependent on PAF handling the Post-Compact formulations. / Furthermore, the EU has just approved funding for a joint project by the WorldFish Centre, NPCA and AU-IBAR on “Improving Food Security and Reducing Poverty through intra-regional Fish Trade in sub-Saharan Africa”. A total of €5.5 million has been earmarked for this project of which €800,000 will support the PAF Trade Working Group. / At the PAF Steering Committee meeting in April 2012 it was agreed that a NPCA Fisheries Strategy for PAF after 2014 would be developed to provide a framework for future funding. This is complemented by the NEPAD FAO Fish Programme (NFFP) which now has a workplan that is harmonised with that of PAF. / Internships / Internships within NEPAD provide the opportunity for young African people to gain experience in PAF and to learn about pan-African approaches to fisheries policy. These have proved useful for PAF. Young people who have completed internships are starting to take the messages of the reform process back to their countries to build momentum for change. PAF currently has three recent graduate interns who are involved the Think Tank process. Lessons learnt from PAF’s experience of internships have informed NPCA’s policy on interns more generally and, in 2012, NPCA approved a new policy on the use of internships for the wider organisation. / Summary: / The PAF is now a sustainable institution and is starting to receive additional funding from a number of different sources. Much of this has been directly leveraged by DFID’s support for PAF. As the policy process moves forward there is a need to ensure that the evidence for the policy implications for the reforms extends beyond the economic and include the social, environmental and political economy. / Recommendations: / Recommendation: Given the flexible and opportunistic nature of the project in shaping policy, and the importance of keeping track of what the project does and does not do in any one year, and to ensure that the change process is clearly documented, it is recommended that NPCA develop a quarterly reporting system to clearly demonstrate what has been achieved in each quarter. / Recommendation: Given the need to ensure that the policy changes proposed under the CAFRS do generate pro-poor impacts, it is recommended that PAF adopts the World Bank’s Poverty and Social Impact Analysis approach to strengthen the evidence base around the proposed policy reforms by promoting a systematic understanding of the poverty and social impact of those reforms. / Recommendation: Given the potential importance of climate change to the fisheries in Africa, PAF should develop a plan for fully incorporating climate change into the emerging policy framework and CAFRS. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low/Medium/High Low / Revised since last Annual Review? No

Output 2: Governance component: Potential benefits of African fisheries in pro-poor economic and social growth better understood and shared
Output 2 score and performance description: / The Output Score is B: the Output moderately did not meet expectation. Whilst much has been achieved under this Output the analytical study integrating the Working Group data under Indicator 2.2, which was designed to provide continent-wide figures for the wealth and growth potential of fisheries, has not been produced. This study is very important for both combining evidence sources and informing policy. There have also been delays in drafting the five pilots which so far include Ghana and Sierra Leone. / Progress against expected results / Indicator 2.1: Fishery Governance Policy Working Group active and sharing advice on change and growth potential / Milestone: Grant renewed or re-awarded on annual basis for Phase 2 / Progress: The Governance Working Group has been primarily concerned with: developing the economic valuations of the different fisheries in Africa; identifying lessons in governance; building capacity in economic valuation methods at the national administration levels; and, identifying priorities for development within the different regional fisheries committees. The grant for the Working Group was renewed in August 2012 on the recommendation of the NEPAD Steering Committee. The use of funds is agreed by the Steering Committee and monitored against audited annual accounts. / The Working Group has done much to inform a rational economic approach to fisheries and to build economic analysis capacity. It will now need to translate that learning and skill development into policies guidance that can inform CAMFA in 2013. / Summary: / Overall this milestone has been achieved. / Indicator 2.2: Recognised continent-wide figures for wealth and growth potential of fisheries (including aquaculture, inland systems and IUU compliance) / Milestone: Analytical study integrating WG data completed in Year 2 and published in at least 3 documents/papers. / Progress: Whilst the project has been very busy in generating reports on specific issues these have not been brought together into a single analytical report. Bringing the different lessons learnt, knowledge gained and key sources of evidence around the efficacy of these different components of the project still remains important to inform the policy process and would provide a valuable “state of the art” report for CAMFA in 2013. It would also provide an opportunity for ideas and experiences to be shared through the Think Tank process before the 2013 CAMFA meeting. These findings should also be summarised in policy briefs that can reach a much wider audience. / In 2010 the Governance Policy Working Group undertook an initial economic valuation of African fisheries resource rent based on the point of first sale. This was found to be in the order of US$2 billion/year. But, this needs to be complemented by further country level valuations. / One of the lessons learnt from pilot projects in Ghana and Sierra Leone is that the knowledge in government administrations on fisheries economics is very limited. As a result, the Governance Working Group has conducted training for administrators on economic valuations of fisheries. For example: / in November 2011 a training session was conducted for the seven coastal states (Sao Tome & Principe, Congo, DRC, Gabon, Cameroon, Equatorial Guinea, and Angola) of the Economic Community for the Central African states (ECCAS); / in March 2012 training was conducted for the member states of the Lake Victoria Fisheries Organisation (LVFO) (Tanzania, Kenya and Uganda); and / training has also been conducted in the relevant ministries in Ghana (March 2012) and in Sierra Leone (April 2012). / In July 2012 a Think Tank event was held jointly with the University of Dar es Salaam and the International Institute for Fisheries Economics and Trade (IIFET). This event achieved three main outputs. It: / confirmed the value of African fisheries; / agreed to develop strategies to improve the equitable distribution of benefits from the fisheries sector; and / agreed on the need to further strengthen the capacity of country experts in the field of fisheries economics. / Regional economic assessments to inform policy formulation process have been launched and are ongoing. The assessments are being conducted in the West, Central, East, Southern and North Africa. / A forum involving Regional Fisheries Bodies (RFBs) and Regional Economic Communities (RECs) was organised by PAF and held in September 2012, Johannesburg. This REC -Regional Fisheries Bodies Coordination mechanism agreed a number of strategies which will enhance the coherence of fisheries with the regional integration agenda as well as improve the accountability of the RECs within the framework of CAADP. / Since then the Working Group has completed economic valuations in seven coastal states: Angola, Gabon, Congo DR, Congo Republic, Cameroon, Sao Tome and Principe, and Equatorial Guinea. These were presented to Ministers in Cameroon in September 2012. / Summary: / The work towards this milestone is well developed but has not fully delivered. This work now needs to continue to extend the valuations to other countries and to come to a more definitive Africa wide valuation. In addition, the evidence needs to be shared with a wide diversity of stakeholders in forms that are suited to the audiences. / Indicator 2.3: Pilot-scale activities based on best practice and wealth-based reform models developed, validated and contributing to CAFRS / Milestone: proposals for pilots in at least 5 fisheries drafted by the end year 3 and informing CAFRS by 2013.
Progress: At present two pilots have been funded: in Sierra Leone and Ghana. In November 2011 NPCA signed a MoU with the Sierra Leone Ministry of Fisheries and Marine Resources for US$1.4m to support a fisheries reform strategy under the West African Pilot Project. A further US$1.4 m has been provided to Ghana to enable PAF to provide support to the Ghanaian Fisheries Commission to enhance its capacity. Support was provided in preparatory work leading to the signing of the Financing agreement by the World Bank in March 2012 for US$53.8m and PAF involvement in this process has done much to leverage this additional funding. PAF also facilitated the development of a subsidiary agreement between the West Africa Sub-Regional Fisheries Commission and Ghana which was signed in April 2012. This will provide for an exchange of lesson learning across the region. / Three others pilots have been identified but full proposals have not been prepared yet. These are for: 1) deep sea shrimp fisheries in Senegal; 2) a cross border shrimp stock in Nigeria/Cameroon, and 3) small pelagic between Cameroon and Gabon. / The two ongoing pilots have already started to inform the CAFRS process in a number of ways: / economic valuation of fisheries is necessary to stimulate interest in national governments and to move fisheries to an appropriate level on the policy agenda; / that integration of fisheries reform needs to be incorporated into the CAADP process if it is to be sustainable; / policy reform is not an easy process as it often requires some people losing opportunities in the fishery; / leveraging finance against reform helps that reform to occur more effectively; / reform requires substantial capacity building at the national level to understand the underlying principles of the reform process and to put it into practices; / reform is a learning process for NEPAD as well as for the country administrations; and / reforming policy processes requires a flexible and opportunistic approach and does not always go as originally planned. / While these may seem to be obvious statements their acceptance in past fisheries policy has been limited and these represent significant shifts in the policy process. Perhaps the most significant of these in terms of the theory of change is that capacity for policy change at the level of national institutions is less than expected and that a greater level of emphasis has been needed in building this. / In the last 12 months the pilot work has revolved around extending the front-loading design and coordination work of the two ongoing pilots. The country teams have also been involved in stimulating cross learning such as taking the Sierra Leone Minister of Fisheries and his staff to Namibia in June 2012 to learn how fisheries management and development reform has taken place there. Subsequently a bilateral cooperation agreement between the two ministries was drafted to cover cooperation in the following: 1) rights-based fisheries, 2) revenue generation and full economic recovery, 3) quota system skills, 4) territorial monitoring control and surveillance, and 5) fisheries legislation. It is envisaged that this will lead to positive changes in the situation in Sierra Leone in the future. / Summary: / The work to achieve this milestone is well on the way but has been delayed, in part by problems beyond the projects control. / Recommendations: / Recommendation: Given that the intended impact of this project is to achieve inclusive growth, and that a wealth based approach has the likely outcome that there will be winners and losers from this in terms of access to the benefits from the resource in the future (due to down-scaling of fishing capacity), and that major reforms are likely to most adversely affect the more marginalised in the sector, PAF should draw up a plan to: / understand the likely effects of reforms on the more marginalised and poorer groups in the fishery and in ancillary services against a baseline of the current situation; / provide evidence to the CAFRS process on how these adverse effects can be minimised; Identify how wealth realised from the fisheries as a result of the reforms can be redistributed to facilitate livelihood adjustment for the losers; / initiate a process of analysis to understand how climate change will affect wealth creation and distribution; and / identify and promote ways for these adaptation strategies to be incorporated into the reform process. / Recommendation: Recognising the need to input as much evidence as possible into the policy process, and acknowledging the diversity of work that has been done across the project so far, it is recommended that: / The NPCA facilitates a process which draws together the learning from the different Working Groups and Pilot Projects, and enables this to be discussed in a wider Think Tank forum. / An analytical study report be prepared and agreed in advance of CAMFA next year. / Policy guidance is developed for CAMFA based on this. / An informing and influencing strategy for dissemination of project learning is developed and implemented. An important part of this will be the production of a series of policy briefs to share the evidence and implications of that evidence more widely and to link into DFID country offices where the pilots are being implemented / Recommendation: Given the importance of ensuring the quality of the evidence for policy that is generated by the PAF in the development of the Comprehensive African Reform Strategy, it is recommended that such evidence is peer reviewed in appropriate published journals. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low/Medium/High Low / Revised since last Annual Review? No

Output 3: Illegal fishing component: Knowledge and experience of tools systems and policy requirements to tackle illegal fisheries production and trade in place and shared
Output 3 score and performance description: / The Output score is: A: Outputs met expectations. In reality performance under indicator 3.2 exceeded expectations and those under 3.3 were below expectation. / Progress against expected results / Indicator 3.1 SIF (Stop Illegal Fishing) policy working group active and engaging stakeholders into the SIF network by 2010 / Milestone: Grant renewed or re-awarded on annual basis from Phase 2. / Progress: The grant was renewed in August 2012. / Indicator 3.2: Successful activities in SADC under previous project on illegal fishing emulated in other African sub regions contributing to CAFRS / Milestone: At least three shared actions to develop regional cooperation on Illegal, Unreported and Unregulated (IUU) fishing by 2012. / There have been a number of shared actions which have taken place. Some of these are outlined below. / In the Southern African Development Community (SADC) region, capacity of the SADC Secretariat was in 2011 strengthened to implement the Regional Fisheries Strategic Plan, the operationalisation of the Illegal Fishing Task Force and the Regional Monitoring, Control and Surveillance (MCS) Centre. / Building on past work in Stop Illegal Fishing (SIF) where a Capacity Needs Assessment methodology was developed and used in six countries, SIF now has a SIF/PEW pilot project with Seychelles, Kenya, Tanzania, Mozambique and possibly Comoros (verbally agreed but still to get on paper) to implement a project on enforcement actions. / Following the first workshop in Sierra Leone, SIF coordinated a new workshop on National and Regional Solutions to IUU Fishing in May 2012. This brought together people from Liberia, Guinea, FCWC and Sierra Leone to work on a regional agreement. / In February 2012 the combined IUU vessel list was developed to support countries across Africa to identify vessels that have been shown to engage in IUU fishing. This followed on from direct requests from countries and CAMFA to create this facility. Information is now available on the SIF website and regularly updated. / Members of the SIF network participated in 30th Session of the FAO Committee on Fisheries (COFI) held in Rome from 9th to 13th July 2012. Members of the SIF network supported the African Members of COFI to prepare an Africa Group Statement on IUU fishing that was presented by the Minister of Investment, Natural Resources and Industry of the Seychelles, the Hon. Peter Sinon under the agenda item on combating IUU fishing. Working Group staff were also able to run morning briefing sessions for the African delegates to increase their awareness of key policy issues and to ensure a common African voice reflecting a regional approach and regional coherence in terms of fisheries policy and approach to strategy at COFI. The African Statement was supported by ten African COFI Members, many of whom also supported the Statements of other African countries and added extra support and information to the Statement. In relation to the Port State Measures Agreement, which will provide a coordinated response to IUU fishing, seven African countries have signed the Agreement and are now working towards ratification. SIF had supported the negotiations of the Agreement that culminated in inclusion of Article 21 (Requirements of Developing States). This is progressively building a sense of agreement across African decision makers and assisting the engagement in wider global debates. / In July 2012 SIF and the Commission for the Conservation of Antarctic Marine Living Resources (CCAMLR) held a second meeting on flag and port state measures in Cape Town. This was totally funded by CCAMLR and more than 20 Africa countries and Regional Fisheries Management Organisations were present. / Information on illegal fishing in Liberian waters was presented at the 7th International Forum on Illegal, Unreported and Unregulated (IUU) Fishing, 2‐3 February 2012 in Chatham House in London, by the NPCA’s Senior Fisheries Adviser and discussed by the meeting. This is part of an ongoing process of raising the profile of IUU fishing at a global level to increase buy-in and coordinated action. / Collaboration was started in August 2012 with FCWC and Nigerian navy to develop and Regional Strategy against illegal fishing in the Gulf of Guinea. / Summary: / The milestone has been substantially exceeded and is contributing significantly to the success of the project. / Indicator 3.3 Risks on non-compliance in fisheries and trade assessed, contributing to 2.2 and CAFRS / Milestone: Study completed by in Year 2. / Progress: Although there have been a number of studies produced these have not been compiled into a single document under indicator 2.2. (See note under recommendations in output 2.). These documents have informed a wider debate on IUU fishing and raised the profile more generally. The Stop Illegal Fishing website (http://www.stopillegalfishing.com/) is now a major source of information and news that is used by the countries in Africa. / Summary: / This milestone has not been completed and should be moved ahead before the next CAMFA meeting in 2013.
Recommendations: / Recommendation: It is recommended that the SIF Working Group develop and agree a plan with NPCA, before the end of November 2012. The plan should cover how the assessment of the risks of non-compliance in fisheries and trade will be carried out. It should be implemented to feed into Indicator 2.2. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low/Medium/High Low / Revised since last Annual Review? No

Output 4: Trade and market access component: innovative and equitable approaches to investment and trade in African fishery products explored and exchanged
Output 4 score and performance description: / The Output score is: B (the output moderately did not meet expectations) for this output because progress on two of the milestones is limited. It is important to note however that the dates for completion of these milestones have not been reached yet. The situation is likely to improve significantly when the new Working Group institutional measures start to take effect. / Progress against expected results: / Indicator 4.1: Fishery Trade Policy Working Group active and engaging stakeholders including small scale operators into the trade network by early 2010 / Milestone: Grant renewed or re-awarded on annual basis from Phase 2. / Progress: In September 2011 the grant was transferred from INFOSA to FCWC as discussed under 1.1 above. In addition PAF have entered into dialogue with the Rural-Hub to establish an ECOWAS trade observatory to study regional trade trends and bottlenecks in technical and policy trade areas These are existing institutions that are well functioning and with wider support from the region. / Indicator 4.2: Demand-led trade studies and pilot activities commissioned and informing CAFRS / Milestone: At least 3 major regional trade studies or shared actions completed and published by 2013, informing CAFRS / Progress: The milestone for this does not mature until 2013 and progress is reported here for indicative purposes. INFOSA implemented a basic study on regional trade mapping but this did not go far enough. In August 2011 GIZ and the AU looked at developing a strategy for wider ECO-labelling in Africa. PAF chaired the group looking at fish. Since then the EU has approved a Euro 5.5 million project to be implemented by the WorldFish Centre, AU-IBAR and PAF which should contribute significantly to this Output. The role of the PAF, through the Working Group, will be to carry out research into cross-border movements of fish, identification of trade constraints and the implementation of the Think Tank process on trade issues. / It is recognised by PAF that the three regional trade studies need to be completed and the new institutional arrangements should allow that to begin in the next few months through FCWC and the Rural Hub in Senegal. / This output concerns investment as well as trade. The Fisheries and Aquaculture Investment Partnership, which is supported by the Investment Working Group under PAF, has done a number of studies on investment in fisheries enterprises around the world. These are in line with the wider output but not covered by specific milestones. They provide a useful and easy to read product which can be used to share lessons learnt and to stimulate private sector investment in African Fisheries. These are available on http://africanfisheriesinvestment.org. The Partnership also completed a study of public-private partnership arrangements for four fish receiving stations in Sierra Leone as part of the CAADP Post-Compact interventions. This was complemented by the Aquaculture Working Group conducting a feasibility study for Aquaculture investments. It has provided a much stronger awareness of the issues surrounding the need for investment in small-scale enterprises and has begun to stimulate interest in greater investment in small-scale fisheries operation. Furthermore, PAF has developed a programme memorandum to establish the Equity Fund for Fisheries and Aquaculture. A number of partners including the International Finance Corporation (IFC), and the African Development Bank have expressed interest whilst ECOBANK has expressed willingness to be the Fund Manager. / Summary: / The output has been delayed because of institutional issues. These have now been resolved and the output needs to move ahead quickly if it is to stay within the time frame of the milestone. / Indicator 4.3: Common African Position on Regional and international trade contributes to African voice. / Milestone: Common position on fisheries access agreements and associated trade adopted by 2012. / Progress: The PAF Think Tank Meeting and the training workshop on fisheries access agreements held in June 2012 cemented the functional working relationship and collaboration between AU-IBAR and NPCA. At the Think Tank held in Abidjan in June 2012 there was increased common thinking on access agreements and under the general policy concerns around the “Scramble for Africa” there is increased caution over trade in fish. Linked to this, and at a more global level, in October 2011 PAF, DFID and the Chinese Ministry of Agriculture conducted the final formulation mission for the Africa-British -China Trilateral Cooperation in Agriculture and Fisheries. This is likely to have implications for China’s involvement in fisheries in Africa and provides a process for agreed principles for cooperation. The World Bank’s PROFISH and PAF will undertake the joint study of the Scramble For Fish in order to generate information which will guide Africans during negotiations of the Foreign Fishing Agreements. This is all providing a stronger African position on fisheries access agreements which will help in national negotiations as well as facilitate regional cooperation. / Summary: / Whilst there is some movement towards delivering this output milestone there have been delays which now need to be overcome.
Recommendations: / Recommendation: Recognising the importance of trade measures to realising the full economic benefits for fisheries in Africa and appreciating that this Output has been delayed substantially in its implementation, it is recommended that PAF: / urgently review how recently established project initiatives (such as the NEPAD FAO Fisheries Project) which have complementary components could contribute to the implementation of this output and strengthen its contribution to the development of CAFRS. / draw up a plan to fully deliver this project assigning responsibilities to specific institutions and defining realistic delivery dates. This plan should be drafted and presented to DFID for consideration by the end of November 2012. / Recommendation: Recognising: 1) the importance of investment in the small-scale enterprises in Africa to comply with the reform process, to take up new growth opportunities in the sector and to enable some groups to leave the fishing industry where current fishing levels are too high, and 2) that there are limited avenues for that to occur at present, it is recommended that an additional indicator be included under this output. This should address the availability of investment finance for both enterprises that wish to enhance their compliance with the reforms in the sector and those that wish to leave the sector and engage in alternative livelihoods. This change should be included and costed in future workplans. . / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low/Medium/High Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: The overall score for the project is A: the outputs met expectation. / 1.3 Direct feedback from beneficiaries: / The positive feedback from donors has been in the form of financial support for the PAF. SIDA specifically requested that FAO, in planning its fisheries programme for Africa, work with NEPAD to ensure compatibility between the two programmes. Likewise, the EU funding on trade was linked to the PAF to ensure compatibility with PAF’s work. The World Bank funding of fisheries projects is done in partnership with the PAF and uses the reform process of the PAF as a guide for investment. More and more funders are seeing the PAF as a viable mechanism to work with and one which reflects greater participation by African partners and African views on development within the sector. / A brief email survey was implemented as part of the Annual Review. Nineteen people involved in working with the project were contacted. The feedback was generally very positive. Some of the key comments are summarised below: / the PAF has raised the profile of the importance of fisheries to national and regional fisheries development in ways that had not been done before; / it has increased investment in the sector from both national governments and donors; / the PAF’s development of FishNet - the African network of fisheries expertise - has supported the engagement of African expertise in fisheries research and development to a greater degree than before; / the PAF has been flexible in implementation, which has allowed “lessons learnt” and “feedback” processes to take their course; / the PAF project, and its host NEPAD, had contributed immensely in facilitating the integration of fisheries into the CAADP; / the PAF has had significant impacts on national and regional fisheries policy formulation through capacity development and Think Tank events and the issues of climate changes adaptation and other natural disasters, sustainable environmental managements, wealth creation etc., now being integrated in national and regional fisheries policies; / as a result of PAF there is an increasing trend on the continent towards the development of regional policy initiatives for coherence and regional integration.
1.4 Summary of overall progress / The overall progress of the project must be considered in the context of dealing with quite radical policy and institutional change in an area which has traditionally been very challenging and across a wide array of different partners with varying levels of capacity to respond. PAF is not only concerned with developing a common policy and strategy for fisheries reform but also generating the evidence to support that reform. It plays an important role in convincing governments, often with little understanding of fisheries, of its potential, generating a common African Voice on what the reforms should be, and gaining support from development partners to invest in those reforms. This has to be done at a certain distance from the policy processes which are essentially national in nature and which operate within the timeframe of national governments. In addition, the project has to build the reform process into the ongoing CAADP process and to build sustainable institutions to ensure its continuation. These would be major challenges for any project, but to gain policy coherence across disparate countries in Africa has been a real and important achievement. / In the light of those constraints it can be said that the project has been very successful in building the momentum for policy reform in fisheries in Africa. / It has also been very successful in leveraging additional funds from a number of different partners which has started to fund different aspects of the policy reform process. DFID’s role in funding the collaborative process which drives the PAF and which has been so successful in generating the additional funding remains crucial to maintaining the momentum for policy reform. / However, some aspects of the project have not gone as well as expected due in part to the complexities of managing a diverse array of activities through a multitude of partners. In addition, the project has changed its institutional arrangements part-way through to become a SPV in NPCA which meant adopting a new set of administrative and management systems. The legal, administrative and financial constraints associated with working with many partners have presented organisational problems but also learning opportunities. This has been a necessary process to get buy-in from national governments, regional development groups and African experts. / In the main it has achieved most of its milestones at this stage of the project. It is aware of the short-falls that have occurred and plans to address these in the coming months. The budget is 23% under spent as of the end of April 2012. A six month no-cost extension is recommended to complete the outstanding work following a review by DFID of a costed workplan..
1.5 Key challenges / There are a number of challenges for the project as follows: / The project is dealing with a complex policy environment which has inherited a poorly managed fishery which is not achieving its potential, which will be affected in the long-term by climate change and which has significant associated distributional issues. / The work towards Output 4 (trade and investment) has been slower than expected due to institutional constraints. These are in the process of being resolved and should be completed in coming months. / Working with the Regional Economic Communities has been slower than expected because the technical capacity of the RECs is rather low in relation to fisheries. This has required more work in raising awareness and building skills. / Likewise at the national level there is a lack of awareness amongst economic planning ministries of the importance/potential of the fisheries sector. Getting fisheries into the CAADP process has not always been straightforward because the true potential of the sector has not been realised and as a consequence its priority has tended to be low. / The legal, administrative and financial procedures that have to be followed to put agreements in place for much of the work to take place has been slower than expected due, at least in part, to capacity weaknesses in NPCA itself. Likewise, the monitoring of expenditure across numerous costs centres and agencies has been complex. / Under the West Africa Pilot Project the support goes through; 1) the Working Groups and 2) the Governments. Capacity short-falls have led to delays in both cases. / The challenges demonstrate the realities of working in such a complex policy environment and have emphasised the need for the project to adopt a flexible and opportunistic approach. It has responded to this very well. Because of this complex and challenging environment PAF need to make sure that they report very clearly what they are achieving against the logframe. / In addition to implementation challenges is the challenge of developing a policy direction for African Fisheries at the same time as generating the evidence to support that policy. Changes brought about by the reform process will doubtless lead to economic improvements in the fisheries of Africa but over a considerable time scale. The reform process also needs to understand and generate evidence of the complex social issues that such policy reforms will generate. The engagement of the SIDA funded FAO work on fisheries will complement the economic aspects of the PAF work and this needs to feed into the Pilot Projects, the policy debate and the CAFRS. / Recommendations: / Recommendation: It is recommended that the PAF work closely with the NFFP to ensure that wider social and environmental issues are covered by the research into possible policy reforms and that appropriate measures are taken to minimise adverse effects.
1.6 Annual Outcome Assessment / The project is well on its way to achieving the Outcome milestones for the end of project. The reform process is widely endorsed through the Conference of African Ministers of Fisheries and Aquaculture which is now the de facto fisheries policy body of the African Union. The broad CAFRS framework is being used to guide the formulation of Post-Compact National Fisheries Investment Plans and to guide the inclusion of fisheries into the wider CAADP process. Experience from PAF’s work is also being used to inform an African Voice on fisheries which is being expressed at global fora. / PAF has developed both short-term and long-term partnerships with African and non-African institutions. The internalisation of PAF into a technical unit in NPCA has already occurred. PAF has established relationships with a number of RECs and Regional Fisheries Bodies which have laid the foundation for long-term collaboration. The FishNet network of expertise, which has been generated and supported through the PAF Aquaculture Working Group, has linked a wide number of African fisheries experts across the continent and encouraged a sharing of information and ideas. PAF has also secured funding agreements with a number of international funding/implementation agencies such as the World Bank, SIDA, EU, DFID, and FAO. / The evidence for PAF presenting a coherent African Voice emerging from the policy dialogue of the project is increasing. PAF represented African fisheries at Rio, COFI, Chatham House and UNCLOS. PAF also has a role of representing African fisheries at the Global Partnership on Oceans and on the Steering Committee of the World Bank’s global Profish initiative and that of the private sector Allfish initiative. / As regards the REC’s involvement in the fisheries reform, this has been more successful in recent months with ECOWAS establishing Regional Fisheries Working Groups during a meeting in Benin in August 2012, supported by PAF. PAF’s valuation of fisheries in central African states has raised the awareness in ECCAS of the importance of fisheries and this is expected to affect other RECs in similar ways as the fishery resource valuations progress. / At the Impact level it is uncertain if the project will be able to demonstrate tangible economic and welfare benefits in four African states by the end of the project as these can take time to generate. However, it is recommended that the project initiate steps to measure changes in social, environmental and economic parameters that will be able to provide this knowledge. / Changes in trade-related resource governance are likely to emerge from an increased uptake of trade related initiatives such as certification through the Marine Stewardship Council, Eco-labelling, and IUU-trade measures. This will require a no-cost extension of six months to materialise. / Awareness of the actual and potential role of fisheries in the CAADP Compact target of increasing agriculture’s contribution to GDP by 6% has already increased with 21 countries out of 40 with post-Compact initiatives including fisheries. The extent to which fisheries will be able to increase productivity between now and the end of the project is unclear given the time required to introduce the reforms.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / The project is currently 23% (approximately £1.37 m) under-spent on its projected expenditure up to April 2012. The reasons for the short fall are outlined under the key challenges in 1.5 above. The projections by PAF staff are that some of this short fall will be regained during the second and third quarters of 2012 but that a no-cost extension of six months would ideally be needed to address the delayed implementation beyond March 2014. / 2.2 Key cost drivers / PAF is essentially a knowledge management and policy process project. This requires the generation, analysis, sharing and use of knowledge to inform and institutionalise policy reform. Key cost drivers in that process are the cost of funding research through the Working Groups, operating the Think Tanks and other workshops to develop and share information and knowledge, and complementing and building capacity at national and regional levels. / 2.3 Is the project on-track against original timescale: No / Many of the planned for activities and achievements are on schedule but some are delayed, particularly those related to the Trade Working Group under Output 4. The PAF team have asked for a six month no-cost extension to cover outstanding issues and this is recommended by the Annual Review.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Given the nature of the project there is an ever increasing level of knowledge which is designed to inform the policy reform process. Some elements have started to clarify policy assumptions and others to stimulate discussion around new policy directions. The valuations of fisheries in the ECCAS region have clearly informed the national government of the potential economic value of those fisheries to national growth and this has started to influence policy in those countries - 21 countries now have fisheries in their CAADP Post-Compact investment plans. / However, it is likely that the evidence to demonstrate the practical and sustained wide-spread effectiveness of Wealth-Based Fisheries Management (which is one of the major policy proposals of the project) in the context of very diverse African fisheries will take many years to become available. Whilst there can be little doubt that the application of more economically rational approaches to fisheries management will generate higher economic returns, the distributional aspects of those returns and the consequences for the poor, are less clear. There is a need to build an increasing understanding of, and stronger consensus around, how such fisheries management approaches will operate within the complex and multidimensional aspects of African fisheries as part of the wider economic development process and associated political economy. Clearly a cautious approach needs to be adopted to policy guidance until that context specific evidence is available. The guidance should indicate a direction of change rather than be prescriptive about what that change should actually be unless clear evidence is there to support it. / Whilst evidence may be slow to emerge, the real value of CAFRS and PAF for African fisheries in the medium-term, and a central part of the theory of change, lies in the process which has been adopted. This process has been built on dialogue and supported by practical experience, leading to increased understanding and agreement around common ideas, approaches, actions and principles. This has built a momentum for change, a commitment to collaboration, a sharing of experience and knowledge, and is evolving a shared African Voice. There is increasing evidence that this collaboration is having positive effects e.g. in IUU fishing. / That process is increasingly recognising the place of the fisheries sector within the wider development context which sees fisheries as only one, albeit important, part of the livelihoods of people and one aspect of national economies. In response PAF recognises that fisheries reforms need to occur within the context of the reform process of CAADP and this also needs to address the wider issues of the Millennium Development Goals. The work of the Governance Working Group on the economic valuation of fisheries has helped governments to realise the economic potential of their fisheries. The work of the Working Group on Finance and Investment in Fisheries and Aquaculture has demonstrated the need for innovative and appropriate investment approaches and mechanisms that can assist the small-scale fisheries - these can also contribute to the wider economic development of fishing communities. It is now engaging with different funding agencies to initiate a process of direct investment in the sector. / In addition, the CAFRS process cannot evolve in isolation to the wider fisheries policy framework at the global level. It needs to understand how it will accommodate key global policy frameworks such as the Code of Conduct for Responsible Fisheries and the Ecosystem Approach for Fisheries and Aquaculture. The engagement of the FAO in partnership with PAF raises the opportunity for the importance of climate change, disaster risk management and ecosystem approaches to fisheries development to contribute to that policy debate. The recent development, through FAO, of the International Guidelines on Securing Sustainable Small-Scale Fisheries, also needs to be taken into account in the policy and strategy process. The linkages between CAFRS and these wider fisheries policy frameworks may be an area which needs to be addressed through the Think Tank process and to feed into the next CAMFA. / Recommendation: It is recommended that the PAF reviews the relevance of existing and emerging policy frameworks in fisheries and develops guidance on how these can be combined with the CAFRS. A process for carrying this out should be developed and submitted to DFID before the end of November 2012. / Recommendation: It is recommended that the PAF identify ways in which the International Guidelines on Securing Sustainable Small-Scale Fisheries can be incorporated into the CAFRS. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation of the project is planned for 2013 and the Terms of reference for that will be developed as part of this Annual Review.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The Risk Rating at the last Annual Review was Low and this does not require revision. / 4.2 Assessment of the risk level / The key risks are that it will not be possible to measure impact in terms of effect of reforms on tangible economic and welfare benefits in fisheries, or the contribution of fisheries to the 6% increase agriculture productivity in the life of the project. These seem rather optimistic given the time it will take to generate the evidence of policy change. It is recommended that measures be put in place to monitor changes in these benefit flows as soon as possible. / A second risk in that the work under Output 4 is further delayed and progress on this should be reported upon regularly to DFID.
Risk of funds not being used as intended / The project has several layers of auditing which is done within countries and regional institutions, and at the NPCA level. Such audits are reviewed by the Finance Department in NPCA and submitted to the NPCA Steering Committee. There are different levels of expenditure authority across the project and the expenditure is guided by both a work plan and a Manual of Procedures approved by DFID. In addition all donors contributing to the project have their own auditing procedures which can cross reference expenditure. / Although these procedures are in place it would provide invaluable guidance to NPCA have a Fiduciary Risk Assessment carried out on the project. / 4.4 Climate and Environment Risk / Given the excessive level of fishing in the fisheries around Africa, the main environmental outcome of the project is likely to be a positive improvement in the biomass and biodiversity of fish stocks as a result of reduced fishing effort. In addition, the engagement of the FAO in partnering the project will increase the focus on ecosystem approaches and climate change adaptation in the fishery. / The potential effects of climate change on African fisheries are poorly understood but reducing fishing effort is likely to build greater resilience into both the stocks and the fisheries. / One cause of possible concern is the increased spread of disease in fish through aquaculture expansion and the movement of live fish between countries. The Aquaculture Working Group has been active on preparing disease control guidelines to limit this.

5. Value for Money
5.1 Performance on VfM measures / As the project was designed before the current Business Case approach no VfM criteria are defined in the Project Memorandum. / However, a key element of VfM is the approach which is adopted for funding the activities. DFID funds are able to leverage considerable amounts from other donors to allow much more to be done than in the DFID project alone. Key to this has been the partnership with the World Bank which has been supportive in funding National Fisheries Investment Plans based on the reform process. / This leverage has created a level of development momentum which is now a major driver of the project which is having a snowball effect on other inputs and initiatives. This is results in a policy process which is moving faster and more widely than could have been reasonably expected. / 5.2 Commercial Improvement and Value for Money / The PAF manual of procurement procedures is designed to ensure value for money on procurement as well as ensure that correct procedures are followed. Much of the work has been done by African experts and institutions thus building up experience, and knowledge locally, and reducing costs. The supply market for these experts has been expanded considerably during the Project and it is likely that quality of delivery is improving. / The supply market for the international skills needed for the project is limited given the nature of the work and therefore competition has been low. / 5.3 Role of project partners / The overall PAF institutional structure within NEPAD has changed (in October 2011) since the last review and PAF has transformed into a Special Purpose Vehicle (SPV) within the NEPAD Agency. A PAF Coordinator has now been recruited and the SPV has a stand-alone bank account and will be audited separately. This transition has invariably led to delays in procedures and the development of new systems which have had follow-on effects on delays in the Project’s implementation. / Consultancy companies involved in the work seems to be appreciated and their role continues to be important. The increased use of African expertise has helped to generate a local perspective, build skills, reduce costs and stimulate cross-learning. / The institutions involved in the Working Groups seem to have delivered as planned apart from in the case of the Trade Working Group where INFOSA has now been replaced. / 5.4 Does the project still represent Value for Money : Y/N / Yes. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None

7. Conclusions and actions
The project is an important and valuable initiative for DFID to be involved in. It has the potential to have major and lasting impacts on the policy process and policies across the continent. It addresses the needs of a large number of poor people engaged in fisheries and aquaculture across the continent and has the potential to improve food and nutrition security as well as support economic growth. It is also generating evidence which may have much wider implications about fisheries development and management in the rest of the world. / The momentum which the process has developed has the potential to lead to greater policy coherence in fisheries, to raise the priority of fisheries up the policy agenda, and to adopt a level of cross-continent collaboration which has not been seen before. / To achieve that it needs to ensure that the evidence for policy change is available from a number of sources and is combined in analytical ways that address the social, economic, environmental and political economy aspects of the sector in the African context. Without that level of discussion, analysis and agreement there is a danger that the policy process may move in directions which may be difficult to sustain in the long-term. The Think Tank process provides an opportunity to achieve that discussion, analysis and agreement and the growing partnership with other agencies, projects and institutions provides an opportunity for considerable coherence across polices and policy frameworks. More needs to be made of this. / In terms of the deliverables of the project, operating in a complex policy environment has meant that the approach has had to be both flexible and opportunistic. This it has done well and has made the best use of the opportunities that have arisen. However, this may have shifted the focus of the work such that some things have not always been done according to plan. The transformation of PAF into a Special Project Vehicle has provided an opportunity to internalise PAF in the AU on a sustainable basis but has introduced short-term delays in administration as procedures are put in place. / The Logframe for the project seems to have sometimes not helped to provide a clear direction and some of the milestones could be usefully reformulated (such as the milestones for indicators 2.1, 3.1 and 4.1) . It may also have generated unrealistic expectations by suggesting that tangible economic and welfare benefits will be visible by the end of the project and these will take some more years to achieve. / Specific actions are as follows: / The periodic reporting from the project is often unclear and it is difficult to see what has been achieved when. The project should develop a simple reporting format which relates to all the logframe indicators and which is replicated at the Working Group level for reporting purposes. This should be developed and agreed with DFID by end of November 2012 and used for the next reporting period (December 2012) and for subsequent quarters. All of the sources for indicators need to be updated given the increase in the number of processes and activities that are underway and which are providing the evidence for progress towards milestones. The project is unlikely to achieve the Impact milestones in terms of economic and welfare benefits but PAF should put in place measures to monitor changes in those against a baseline. / The Logframe requires some revision in the milestones and the addition of an indicator under Output 3 to reflect the work on investment. This should be amended alongside the updated sources for each indicator by the end of November 2012. Given the potential importance of climate change to the fisheries in Africa, PAF should develop a plan for fully incorporating climate change into the emerging policy framework and CAFRS. / Given the need to ensure that the policy changes proposed under the CAFRS do generate pro-poor impacts, PAF should adopt the World Bank’s Poverty and Social Impact Analysis approach to strengthen the evidence base around the proposed policy reforms by promoting a systematic understanding of the poverty and social impact of those reforms. / To assist NPCA in budgeting, forecasting and monitoring its own financial procedures, DFID should increase scrutiny of the programme (i.e. though the log-frame and a revised risk assessment – in place by end November 2012), consider if a more in-depth analysis of financial practices is needed to more closely ‘follow the money’ though the delivery chain, and provide increased support to the programme via an independent financial consultant The exact actions used for more in-depth scrutiny of practices will be determined following the outcome of the revised risk assessment and the needs indicated. Increased support via a financial consultant should consist of no more than 10 days and aim to ensure stricter compliance with the DFID MoU and embed accurate and timely financial reporting. This should be completed prior to the end of the current financial year) / The Think Tank process of shared knowledge and experience is critical for both the development of appropriate policies and for generating a truly Africa Voice. This needs to be made much more use of in the remainder of the project. / PAF should draw up a plan to: 1) understand the likely effects of reforms on the more marginalised and poorer groups in the fishery and in ancillary services, 2) provide evidence to the CAFRS process on how these adverse effects can be minimized, 3) explore how wealth realised from the fisheries as a result of the reforms can be redistributed to support the people displaced/disadvantaged from the fishery or ancillary services and 4) identify and promote ways for these adaptation strategies to be incorporated into the reform process. / In the lead up to CAMFA in 2013 a more formal, participatory and structured approach to the policy guidance process should be adopted. This includes analysis, dialogue, discussion and agreement on policy advise and should be implemented and documented in the lead-up to CAMFA in 2013. NPCA facilitates a process which draws together the learning from the different Working Groups, enable this to be discussed in a wider Think Tank forum and for policy guidance to be developed for CAMFA, and that an analytical study report be prepared and greed in advance of CAMFA next year. This should link into the analytical study proposed under indicator 2.2. / Given the importance of ensuring the quality of the evidence for policy that is generated by the PAF in the development of the Comprehensive African Reform Strategy, it is recommended that such evidence is peer reviewed in appropriate published journals. / The SIF Working Group should develop and agree a plan with NPCA, before the end of November 2012, on how the assessment of the risks of non-compliance in fisheries and trade will be carried out and that this be implemented to feed into indicator 2.2. / PAF should urgently review the partnership arrangements for Output 4 (trade) with the view to partnering with a wider diversity of institutions (including the recently agreed support project structures such as the FAO Fisheries Project) for enhanced delivery and draw up a plan to fully deliver this Output assigning responsibilities to specific institutions and defining realistic delivery dates. This plan should be drafted and presented to DFID for consideration by the end of November 2012. / An additional indicator should be included under Output 4 which addresses the availability of investment finance for both enterprises that wish to enhance their compliance with the reforms in the sector and those that wish to leave the sector and engage in alternative livelihoods. This change should be included and costed in future workplans. / PAF should work closely with the NFFP to ensure that wider social and environmental issues are covered by the research into possible policy reforms and that appropriate measures are taken to minimise adverse effects. / PAF reviews the relevance of existing and emerging policy frameworks in fisheries and develops guidance on how these can be combined with the CAFRS. A process for carrying this out should be developed and submitted to DFID before the end of November 2012. / PAF identify ways in which the International Guidelines on Securing Sustainable Small-Scale Fisheries can be incorporated into the CAFRS. / Given the delays that have occurred in the project’s delivery (largely outside of the project’s influence), and the slower rate of disbursement, the project should be given a no-cost extension of six months to complete its work. However, this should be contingent upon the delivery of a revised log-frame (as per previous recommendations) and a more detailed budgeted plan to cover the remainder of the project with the new end date, by the end of November 2012. Forecasting needs to be provided on a monthly basis with forecasts on upper and lower achievement/cost levels. / An evaluation of the project should occur in 2013 to coincide with CAMFA. Core questions for this evaluation will be drawn up in Terms of reference to accompany this Annual Review.

8. Review Process
The review was undertaken by an independent consultant contracted through the CEIL PEAKS Call Down Framework. It was completed as a desk study in the UK with phone and email correspondence with project partners. The main sources of information for the Review were from reports and websites, and discussions with key staff in PAF, the World Bank, some of the Working Groups and with the DFID advisers in London. / Documents used in the review include: / The DFID 2011 Annual review / Cunningham S., Neiland A., Arbuckle M., and Bostock T. (2009). Wealth-Based Fisheries Management: Using Fisheries Wealth to Orchestrate Sound Fisheries Policy in Practice. Marine resource Economics, Vol .24, pp271-287. / DFID (undated) International partnership for African Fisheries Governance and Trade: Programme Memorandum. / Bene C. (2011). CAADP and Fisheries Policy in Africa: are we aiming for the right reform? Future Agriculture Consortium (www.future-agricultures.org) / Various quarterly reports from the Project. / PAF Annual Workplan April 2012-March 2013. / Presentations made at the CAMFA meeting in 2010. / The report on CAMFA 2010. / Minutes of the African Union Fisheries Coordination Meeting held in Johannesburg September 2012. / World Bank Project Appraisal Document for a strategic partnership for African Fisheries : proposals for An African Fisheries Reform Mechanism / A report of the NEPAD PF Working Group Retreat held in, Johannesburg, March 2012. / Proceedings of the 5th Steering Committee meeting of PAAF, Kenya, April 2012. / Draft report of the Proceedings of the Think Tank Meeting on the Formulation of a Pan-African Policy Framework and CAFRS - June 2012. / Economy and fishing in Cameroon - an economic valuation. / Economy and fishing in Gabon - an economic valuation. / An email request for opinions on the progress of the project was sent to 19 different stakeholders. The report was reviewed by the CEIL PEAKS management team prior to submission. A full Quality Assurance process was not undertaken due to the very tight reporting turnaround time.