## Intervention Summary: iFUSE - The Investment Facility for Utilising Specialist Expertise
What support will the UK provide?
DFID will provide £3.48 million to an outsourced facility (iFUSE) for the provision of specialist expertise on a non-profit basis, to assist partner developing countries in implementing investment climate (IC) reforms. It will operate from November 2011 to 31 March 2015. / The objective of iFUSE is to provide partner countries and DFID country programmes with the option to access an additional source of specialist expertise on a wide range of IC issues to contribute to the delivery of DFID poverty objectives on a demand-driven basis. / iFUSE will manage requests for support from developing country partner governments and DFID IC country programmes and match them to the best qualified sources of expertise within participating UK Other Government Departments, both substantive Whitehall Departments and subsidiary bodies (referred to as OGDs). The programme may expand after the first year of operation, to include, for example, specialists of professional bodies (such as the Institute of Civil Engineers). / iFUSE will provide deployment support to experts and pay full costs of assignments .It will also facilitate knowledge exchange between partner developing country officials and UK officials, through activities including experience-gaining visits and attachments into OGDs by partner developing country practitioners.

Why is UK support required?
There is robust evidence that a good IC is key to growth and long term poverty reduction. UK government and professional body expertise on IC is currently under-utilised and used in only an ad hoc manner to support developing countries. OGDs often receive requests from developing countries for specialist advice which they cannot respond to due to staffing and budget constraints and they do not systematically organise their expertise by IC reform area. / iFUSE will expand the use and increase the efficient deployment of specialist IC expertise, support development objectives, and provide greater value for money for the end users – UK’s partner governments in developing countries. It will facilitate deployment of more expertise by operating an effective pooling system and by providing resources to reduce budget pressures on supplying OGDs. The programme will be run and managed by a private contractor with DFID oversight.

What are the expected results?
The outputs of the iFUSE programme are: / High quality advice in specialist IC reform areas, in response to DFID partner government or DFID programme requests. / Knowledge exchange activities including experience-gaining visits, twinning arrangements and/or developing country practitioner attachments into OGDs. / The outcome of these outputs will be an improvement in the delivery and implementation of IC reforms in developing countries both where the expertise is utilised directly and in general due to the likely increased choice in available expertise. / The end results of IC reforms that specialist expertise will help deliver are: / Increased firm productivity and investment, / more jobs, improved employment and growth prospects in developing countries, / increased consumer welfare from better and more products and services at more competitive prices.

List of Acronyms

CSC	–	Critical Success Criteria
DANIDA	–	Danish International Development Agency
DFID	–	Department for International Development
EU	–	European Union
GRD	–	Growth and Resilience Department in DFID
HMG	–	Her Majesty’s Government
HMT	–	Her Majesty’s Treasury
IC	–	Investment Climate: the wide range of factors that determine whether
 investors will invest in a country.
ICT	–	DFID’s Investment Climate Team, housed in GRD
IDB	–	Inter-American Development Bank.
iFUSE	–	Investment Facility for Utilising Specialist Expertise
MA	–	Management Agent, the private contractor that will run iFUSE on
DFID’s behalf after a competitive bidding process.
MOU	–	Memorandum of Understanding
OGDs	–	Other Government Departments (including subsidiary UK
Government bodies) that will provide experts for the iFUSE
programme as needed.
OJEU	-	Official Journal of the European Union
PD	–	DFID’s Policy Division.
TA	–	Technical Assistance.
ToRs	–	Terms of Reference.
VfM	–	Value for Money
WDR	–	The World Development Report (a World Bank publication)
Business Case for: iFUSE - The Investment Facility for Utilising Specialist Expertise

Strategic Case

A. Context and need for DFID intervention / A good investment climate (IC) is key to growth and long term poverty reduction. World Bank analysis shows a strong correlation between higher growth rates and a better IC. The analysis shows that a better IC leads to higher levels of productivity (WDR 2005) which leads to higher growth rates. / Separately, World Bank Research papers[1] reach similar conclusions. Escribano, A. and Guasch, J.( 2005) estimate that reducing unnecessary red tape and improving infrastructure account for over 30 percent of productivity in Central American countries Guatemala, Honduras, and Nicaragua and that “IC matters enormously”. Klapper et al find that “empirical evidence suggests that greater ease in starting a business and better governance are associated with increased entrepreneurial activity”[2]. / David Dollar et al, analysing over 1000 manufacturers in India find that net fixed investment is four times higher for firms in good IC environments as compared to firms sampled from poor IC environments[3]. Additional evidence includes: / A recent World Bank study (2010) on the impact of business climate reform on firms’ entry for 100 countries including in the Sub-Saharan Africa region, indicating that reducing costs and time for business entry leads to more firms entering the market. However, the depth of entry reforms is critical: at least a 40% reduction in costs of entry is needed to have an impact on key results. / A WB study (2007) on the impact of simplifying business registration through electronic procedures in Guatemala, Sri Lanka and Jordan, found an increase in business registrations of more than 20% in all three countries after the full implementation of the modernisation plans / Aghion et.al (2008) established that the elimination of the License Raj - a system of central controls regulating entry and production activity in India's manufacturing sector - led to 6% increase in the number of new firms, after controlling for other factors such as trade liberalisation and labour market laws. / UNDP, with financial support from Australia, provided technical and other support to the Vietnamese Parliament in drafting and implementing a new Enterprise Law. Enacted in 2000, by 2003 the new Enterprise Law had already resulted in the registration of 55,000 new businesses, an increase of more than 350%. / A cross country study (Eifert 2009) based on doing business data between 2003 and 2007, shows that a 10-day reduction in days to register a business is associated with an increase of investment rates by 0.3% in relatively poor countries, and in countries with relatively better policies. / DFID recognises the importance of the investment climate: work with and in support of the private sector to achieve wealth creation and poverty reduction objectives is a Ministerial and corporate priority as set out in DFID’s new strategy for supporting private sector development[4]. Improving the IC is a key element of this strategy and is recognised as such in DFID’s Business Plan, which commits DFID to develop new programmes on IC and property rights. DFID operations bear this prioritisation out in practice - according to country office results frameworks 24 out of 27 DFID country offices running wealth creation programmes have plans to continue or begin IC programmes. / IC reform requires significant specialist expertise that is often in scarce supply in many DFID partner countries, and therefore requires external inputs. The objective of iFUSE is to provide partner countries and DFID country programmes with the option to access an additional source of specialist expertise on a wide range of IC issues, to contribute to the delivery of DFID poverty objectives on a demand-driven basis. Aside from supporting specialist deployments to developing countries, iFUSE will also support officials from partner countries to share and gain knowledge through experience-gaining visits to UK counterparts, as well as inward attachments or twinning arrangements with practitioners in UK Other Government Departments including substantive Whitehall Departments and subsidiary bodies such as the Better Regulation Executive (referred to collectively as OGDs throughout this document). / Vibrant demand for specialist IC advice already exists. Several OGDs (e.g. Office of Fair Trading, Ministry of Justice, HM Revenue and Customs) have indicated that they receive frequent requests from developing country governments to provide specialist support or knowledge exchange on a wide range of IC issues. Those governments look to the UK as an authority on such issues. Despite wishing to do so, OGDs are not always in a position to respond favourably due to budget and staffing constraints. DFID country offices primarily make use of consultancy expertise to help deliver their objectives and have confirmed, in consultations, that they would welcome additional, alternative specialist resources from OGD practitioners and professional bodies (such as the Institute of Civil Engineers). / iFUSE will facilitate the provision of additional supply. OGDs are experiencing substantial resource reductions as a result of an HMG-wide fiscal tightening. One of the first areas being cut in many cases is Departments’ international engagement. Before the current budget-constrained environment, supply was constrained by a Department’s human resources and the lack of systems for effectively pooling OGD expertise. But in a constrained budget environment iFUSE will facilitate the deployment of specialist expertise that would otherwise not be accessible, both by creating an effective pooling system and by relieving budget pressures on supplying OGDs. / An example illustrates both of these points: during the 7 months period between April 2010 and November 2010, the Office of Fair Trading received and rejected 11 requests for support from developing countries (out of which 6 were for short term assistance) due to a lack of funding. Requests for support (for example, on cartels, mergers and consumer protection) came from a range of countries including India, Namibia, Morocco, China and South Africa. / The specialist expertise to be provided offers unique added value that can help improve delivery of DFID objectives. Specialist OGD practitioners are likely to have more hands-on and up-to-date knowledge of best practice and technical issues, as well as stronger experience of public sector policy making and reform implementation in core IC areas, than many private consultants. A successful programme will provide more alternatives in the use of technical expertise and drive up the quality of expertise in areas where iFUSE expertise exists due to increased competition and the use of peer practitioners. iFUSE may result in more expertise being deployed rather than substituting for consultancies that would have happened regardless. / Experts will be largely expected to deploy to developing countries and will require air transportation which has a carbon emissions effect. This impact could be largely minimised by the commitment of the UK Government to offset all emissions arising from official and Ministerial air travel[5] . Similarly, a rise in knowledge exchange opportunities for partner government officials is likely to generate an increase in carbon emissions. It is recommended that iFUSE procedures include arrangements to use UK HMG standard carbon offsets (see footnote 5). / iFUSE also offers an opportunity to strengthen the cooperation among OGDs - a DFID corporate objective, enhancing coordination and the overall ability to deliver on joint objectives and strategies, as well as increasing opportunities for mutual learning as well as increased value for money (see below). / iFUSE will fund, on a non-profit basis the following types of activity: DFID IC programme design, monitoring or implementation support, programme reviews and evaluations; similar activities for partner government institutions in developing countries directly; and knowledge exchange activities for developing country government staff such as twinning arrangements, experience-gaining visits and inward attachments linking UK specialists and developing country partners. Other technical inputs that clearly support partner governments to deliver IC reform will also be eligible but must demonstrate their eligibility.
B. Impact and Outcome / The outputs of the iFUSE programme are: / High quality advice and assistance in a range of specialist IC reform areas, to be delivered by iFUSE in response to DFID partner government requests; and / Knowledge exchange activities for developing country government staff. / The outcome of these outputs will be an improvement in the delivery and implementation of IC reforms in developing countries both where the expertise is utilised directly and in general due to the likely increased choice in available expertise. / iFUSE will enhance the impact of DFID’s IC work in developing countries, which is: / Increased firm productivity, / Increased investment, / more jobs, improved employment prospects, / Increased consumer welfare from better and more products and services at more competitive prices, / Stronger long term growth prospects in DFID partner countries. / The likely consequences of not intervening through iFUSE will be: / OGD expertise to support developing countries continues to be in scarce supply and deployed in an ad hoc manner. / An asset that could play a more prominent role in helping deliver DFID UK poverty objectives in developing countries will remain under-utilised and deliver fewer benefits than it could otherwise. / DFID IC programmes and partner governments have less choice of expertise, lower competition and lower quality than would have been possible if DFID had intervened.
[1] Escribano, A. and Guasch, J., 2005,  World Bank Policy Research Working Paper 3621. http://papers.ssrn.com/sol3/papers.cfm?abstract_id=755070
[2] Leora Klapper, Anat Lewin, Juan Manuel Quesada Delgado (2009) “The impact of the business environment on the business creation process”. World Bank Policy Research Working Paper No: 4937 Available at: http://www.businessenvironment.org/dyn/be/besearch.details?p_phase_id=168&p_lang=en&p_phase_type_id=6
[3] David Dollar et al (2002): IC and economic performance: firm level evidence form India
[4] See DFID’s May 2011 publication on work with the private sector at: http://www.dfid.gov.uk/Media-Room/News-Stories/2011/Mitchell-Harness-dynamism-and-energy-of-private-enterprise-in-international-development/
[5] To meet this commitment, a Government Carbon Offsetting Facility (GCOF) was developed in November 2007 to help offset government travel emissions in a simple, cost-effective way. The Facility covers government air travel emissions from 1 April 2009 to 31 March 2012 and applies all the public sector.

Appraisal Case / A. Determining Critical Success Criteria (CSC) / Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / 1 Knowledge transfer improves the quality of DFID and partner government IC programmes because it is applicable (specialist, informed, high quality) and relevant to developing country contexts. 5 / 2 Expanded pool of specialist expertise available to DFID and partner governments enhances competition and increases overall quality of expertise. 4 / 3 Knowledge transfer is led by demand from DFID programmes and partner governments and is provided in a timely fashion. 4 / 4 Assignments set out clear measures of success and follow up arrangements 4 / 5 Environmental impacts and opportunities of each assignment are adequately addressed prior to deployment 3 / Evidence from assessments undertaken over the last 20 years points towards four key elements for successful provision of technical assistance or capacity building[6]: / specialists need a strong understanding of the developing country context to provide effective advice. / supply-led assignments tend to be less effective than demand-led assignments. / it is critical that short term advisory support is provided quickly to seize opportunities in government cycles or local political economy developments. / assignments need clear measures of success and adequate follow up to ensure real change is delivered. / Other lessons from similar initiatives include: the importance of preparation and training for deployed experts; the importance of adaptability and flexibility as a criterion for selecting candidates, on equal footing to technical expertise; and the need to have a large pool of suitable experts to increase responsiveness. These global lessons inform the CSC for assessing the added value of iFUSE. The CSC on competition and overall quality is based on economic theory that under certain conditions[7] additional suppliers increase competition for a good or service and that increased competition raises product or service quality. Although the literature remains inconclusive on its general applicability,[8] in the case of iFUSE, the market structure in the status quo of privately provided specialist expertise is relatively simple: one consumer (DFID) paying market prices, and several private sector suppliers supplying at market prices. In these simplified conditions, it is more likely that increased competition from iFUSE will raise service quality. / The environmental CSC is included to reflect the fact that, iFUSE will be able to draw on UK Government expertise on climate change issues to increase the preparedness of individual IC experts to address climate change risks and opportunities through their specialist advice on IC, where appropriate.
B. Feasible options / Entry point / The entry point for assessing options can be either: / different interventions for delivering IC improvements / different options for the design of the proposed programme, / a combination of both of these or / a single appraisal of the added value of the proposed intervention. / We assess each of these in turn: / Assessing different interventions will not add enough value: the premise of iFUSE is that OGD IC expertise, an existing asset, is being under-utilised for UK international development objectives. The solution is to improve its utilisation rate through an efficient mechanism (the proposed iFUSE programme). Other interventions that look to increase other sources of supply of specialist expertise will not accomplish this and so would not be directly comparable and would still leave the OGD asset under-utilised for UK development objectives. / Assessing different design options also has limited value: It would take months of study to get estimates for how much spare capacity will develop for different OGDs and what form this will take (short or long term), as well as how demand will develop from partners and country offices, and how demand or supply would vary depending on what the programme funds. The costs of investigating these issues would be high and likely produce inaccurate results anyway. The programme is not high risk enough to justify the additional steps and costs and a course correction has already been built into the proposed design after the first year of operations in case it is needed. / A combined appraisal of different interventions and different design options would be more complex still and not justified by the relatively simple, moderate risk programme. / We therefore have opted for a straight-forward approach, assessing the value added of this intervention against the option of not establishing iFUSE (which is the counterfactual). This is more in line with the programme's moderate risk and simple structure. The programme builds on what currently happens in an ad hoc manner and provides structures and systems to improve delivery. It does not innovate a new approach. / Delivery Methods: In House versus Outsourcing / iFUSE operations require the performance of a range of professional tasks and responsibilities, including ongoing engagement with OGDs, partner governments and (potentially) professional bodies to address demand for and manage the supply of expertise and knowledge exchange; proactive management of the pool of expertise; knowledge management and dissemination services; technical and logistical support to individual experts deployed; and financial and project management. This range of functions requires full time dedicated expertise with specific skills which are not core competencies of Growth and Resilience Department (GRD) and its Investment Climate Team (ICT) who lead on IC. The only choice for delivering iFUSE is therefore an outsourced private contractor - the Management Agent (referred to throughout this document as the MA). / Proposed Options / Two options are considered in this appraisal: / Establish a new outsourced facility called The Investment Facility for Utilising Specialist Expertise (iFUSE). / Maintain the status quo, characterised by private consultancies providing technical assistance resources, with only ad hoc use of OGD specialist expertise in developing countries. / Under Option 1, iFUSE will be established to facilitate the use of specialist expertise from key OGDs and (potentially) professional bodies (such as the Institute of Civil Engineers) on a non-profit basis to support DFID’s objectives for improving the IC in developing countries. / The programme will begin by funding short term advisory expertise for assignments of 20 days or less each (to avoid protracted contract negotiations with OGD Human Resource Departments for releasing specialists for an extended period and accepting the contingent liability). Short knowledge exchange visits or long term inward secondments of developing country practitioners into OGDs will also be funded. iFUSE will be responsible for ensuring that support is provided, when demanded, in technical areas of IC including, for example: / Commercial Law, regulations and requisite procedures (e.g. firm entry and exit). / Commercial justice such as contract enforcement, alternative dispute resolution mechanisms. / Industry sector specific law, regulation and licensing. / Natural resources regulations, procedures and governance. / Cross Border trading procedures and logistics facilitation. / Trade facilitation, including ‘deep integration’ issues arising from preferential agreements. / Business-friendly taxation. / Financial sector regulatory reform and supervision. / Competition policy and market development. / Land legislation, registration and transfer of title processes. / General Government interface with business: processes, procedures, IT systems. / Business environment reform advocacy. / Infrastructure development and public private partnerships, / Other World Bank ‘Doing Business’ indicator areas. / The details of the programme’s operation can be found in the Management Case. / Theory of Change / The problem the intervention is designed to address is the scarcity of specialist expertise to support reforms to improve the poor IC in developing countries. / Poor IC is typified[9] by excessive red tape, poor enforcement of rules, uneven regulation and uncompetitive markets which makes doing business slow, costly and unpredictable, and hampers business productivity, innovation, investment, job creation and economic growth. Broadly, IC reform tackles these problems with the following theory of change leading to outcomes and impacts. / A successful IC reform reduces the monetary or time costs of doing business, increases the predictability of the rule of law governing business operations, facilitates the use of otherwise dormant assets or promotes fairer and more competitive markets. / Firm savings enhance productivity by giving firms more time or money to increase production. Increased predictability allows firms to make better plans for the future. Newly active assets allow firms to leverage additional finance. More competitive markets improve efficient resource allocation and promote innovation and enhanced productivity. / All these effects encourage firms to increase investment. / Increased investment allows firms to expand, hire more workers with more stable and better quality jobs and improve and increase production of the goods and services they offer and to do so at more competitive prices, increasing the efficient allocation of resources. / Increased stable employment improves employed people’s livelihoods and has both a direct and indirect impact on poverty. Competitive pricing reduces price distortions that can have a negative impact on the poor. / iFUSE is expected to enhance and strengthen this theory of change by providing more high quality IC specialist inputs. Its own theory of change is as follows: / IFUSE provides a structured approach to identifying and managing supply of relevant specialist IC technical expertise. / This generates a richer pool of knowledge and expertise to meet partner countries’ technical needs that can be accessed quickly, increasing its relevance and effectiveness. / More choice of expertise leads to greater competition. This will enhance overall technical quality of expertise available. / Knowledge exchange opportunities (such as developing country partner government officials’ experience-gaining visits or short term inward attachments to practitioners in the UK) enhance expertise on IC reform of in-country implementers and policy makers. / Improved overall quality of expertise both from knowledge exchange and expert deployment enhances the quality of IC reforms. / The theory of change for IC reform improves and strengthens as a result of iFUSE inputs leading to strengthened impacts of the IC reform theory of change: more investment, more jobs and stronger economic growth. / Key assumptions and underpinning evidence: / The assumptions for the IC theory of change have been broadly assessed in the Strategic Case showing medium strength evidence that IC reform has positive impacts on measures that lead to higher growth and more jobs. For the iFUSE theory of change: / From 1 to 2: The expertise can be adapted to developing country contexts. / This can be managed to some extent with appropriate training and increasing developing country exposure, filtering for relevant expert competencies and through capturing learning from other contexts (e.g. the European Twinning Community) as well as the programme’s own lesson learning. It is also highly likely that many senior practitioners in core OGD departments already have some, or in some cases substantial, developing country experience. / The evidence assessment is strong given the ample ability to provide training and support and use lessons learnt to ensure expertise can be adapted. / From 2 to 3: The expertise supplements or enhances or substitutes for existing technical assistance effectively and can be delivered at speed and to meet demand. / Evidence from experienced managers in OGDs who manage pools of specialist expertise indicates, that pooling systems do improve the speed of delivery of expertise. These managers also indicate that peer to peer advisory support from current practitioners can be more effective than that provided by private consultants because it has additional legitimacy (learner is more open to learning and therefore implements more). Specialist practitioners are peers and this fosters respect and empathy because practitioners can relate better to both technical content and practical realities facing their counterparts and are more likely to be up to date with best practice and the latest innovations. There are also possible spill-over benefits in the form of informal peer to peer networks as a result of the engagement between specialists and developing country practitioners. But no hard empirical evidence appears to be available to support this. Nevertheless, the advice of current practitioners through iFUSE will be at least as good as that provided by more generalist private consultants and there is no evidence or strong argument to refute this proposition. / The evidence assessment for this assumption is rated as medium given the strong qualitative evidence from existing managers of pools of experts but it is lacking the rigorous assessment that would make it strong evidence. / Similarly, the evidence that increased supply will increase quality of services provided is not strongly supported by evidence of market behaviour as it depends on how rents are captured (see the beginning of the Appraisal Case). But because of the nature of DFID’s position as a single consumer, paying market prices (an HMT requirement), iFUSE should incentivise improved quality or lower prices. / At 4: The knowledge exchange visits positively affect the quality or amount of reform implementation / There is evidence that knowledge exchange visits can be valuable lesson learning experiences for public sector practitioners.[10] But this is based on perception surveys rather than objective empirical data. For this reason evidence assessment is medium. / From 3 and 4 to 5: The increase in quality of reforms makes a discernable difference to the quality, effectiveness or sustainability of reforms delivered. / Evidence for the benefits of technical assistance in general is provided by the World Bank and Danida (see footnote vi). The World Bank’s 2005 study found that technical assistance (TA) for enhancing the institutions/rules of the game was more effective for the IC than for general policy. The IMF have found that their TA has provided significant enhancement in technical capacities[11] and a similar conclusion is reached by an Inter-American Development Bank (IDB) study[12] that also concludes that TA is higher value for money than pure investment financing. There are many other positive external reviews of specific programmes by other donors[13]. / In terms of the added value of OGD specialist TA making a discernable difference on reforms vis-a-vis standard TA, the evidence in point b. indicates that specialist practitioner assistance can be at least as good as traditional technical assistance channels and suggests anecdotally potential added value. The proposition that it provides additional benefits does not have rigorous evidence backing and will need to be tested by the proposed programme monitoring. / In summary, the evidence that the programme will have clear benefits is medium strength given the evidence that the specialist technical assistance can provide benefits and lead to delivery of change; the evidence that the programme will have higher quality is anecdotal (based in part on the specialist nature of OGD expertise) and will need to form part of the programme assessment. / From 5 to 6: The improvement in reforms makes a discernable difference to the theory of change for IC and contributes a noticeable difference to the benefits received by final beneficiaries. / The analysis in point d. applies here. There is medium evidence that the programme will have positive impacts on the IC but there is little empirical evidence that the practitioner expertise will have greater benefits not covered under current interventions and so its evidence assessment is weak. But the evidence is medium strength in that its benefits are at least as good as what is currently available. / Summary of Relevant Information and Evidence of Impact / Good evidence that we have identified a need. Demand from partner governments for specialist UK Government IC advisory expertise exists and DFID country offices have provided feedback that they would welcome an additional source of technical assistance. / Good evidence from OGDs that relevant expertise is available and that financial resources to match demands to an adequate supply of expertise are constrained. / Good evidence that the intervention will lead to a positive impact on the theory of change in IC. / The evidence that it will be an improvement over existing interventions is weak and untested, although there is a strong chain of logic and anecdotal evidence that suggests it is a strong possibility. / But the evidence is good that it can be as least as good as existing interventions. / The appraisal will focus on potential value for money gains of the programme compared to the status quo. / Climate and Environment Relevance of Options / Will the success of the intervention be affected by climate change or the environment? / Since it involves the deployment of expertise, the main effect on the programme is likely to be from natural disasters that slow or prevent deployments. But these would affect a large number of DFID operations and would not be programme specific. / Will the intervention contribute to climate change or environmental degradation? / It will contribute carbon emissions for each contract that requires air travel, which will likely be most of them. The key unknown is whether the programme will contribute additional carbon emissions or would largely substitute for existing emissions from other sources of technical assistance deployment. And whether the additional carbon emissions are significant enough to require additional measures beyond the use of Government Carbon Offsets. This will remain largely unknown until the programme is operational so the proposed approach is to track programme progress and build steps into iFUSE design to limit impact as necessary (eg. potential use of virtual equipment to substitute for travel for short assignments). / Could the intervention help tackle climate change or build resilience to it; could it help improve the environment or its management? / Although the bulk of impact will be indirect (IC improvements will lead to more business activity which may separately lead to substantial environmental effects) and will depend on the specific areas of IC where expertise is deployed, iFUSE could, where relevant, aim to provide expertise that also ensured that more environmentally sustainable outcomes are delivered - versus the status quo. Given UK experience in providing climate change advice, the likelihood of this additional qualitative benefit could be high. / Proposed climate assessment categorisation for iFUSE is low risk, medium potential opportunity / Appraisal of Options 1 (iFUSE) and 2 (Status Quo) / An objective appraisal in favour of Option 1 must show that Option 1’s net benefits exceed those of the status quo Option 2. / Benefits / In the previous section we established some potential additional benefits that OGD expertise may bring over and above the current sources of expertise: / Quicker identification and deployment of specialist IC expertise due to the use of pre-existing pools of specialist practitioners rather than consultants. This has a cost saving (calculated below) and an additional value if rapid deployment can take advantage of rapidly evolving political situations to enhance impact, particularly in fragile states. / OGD experts may be more effective at providing high quality policy-relevant advice and at transferring knowledge. This is due to the strong experience with government policy making and more up to date knowledge of the hands-on application of good practice, as well as at transferring knowledge due to a stronger ability to relate to their counterpart’s challenges, / The establishment of a strong informal peer network between OGD experts and developing country counterparts that could further enhance quality and sustainability in the delivery of reform. / The expected expansion of the supply for specialist IC expertise is likely to increase competition and to raise the overall quality of the totality of IC advisory services to developing countries / The opportunity for OGD staff to gain or strengthen their own developing country exposure could be classified as an additional, albeit incidental, benefit for the UK Government (HMG). / The only potential negative benefit is additional carbon emissions to the extent that iFUSE increases the overall use of technical expertise. Although we are unable to say with confidence the extent to which this is likely to be a factor, we are confident that this can be minimised as set out in the environmental assessment of options. / The one benefit of the status quo that iFUSE does not have, in which private sector consultants dominate specialist service provision, is the private sector perspective to reform efforts. Although OGD expertise is not devoid of private sector perspectives, private consultants are likely to have more sophisticated or deeper private sector perspectives vis-à-vis average OGD expertise. This could enhance the efficiency or effectiveness of reform, but we are not in a position to test its validity or strength due to a lack of evidence specific to IC. / As stated earlier in this appraisal, there is more anecdotal than quantitative evidence to test and back up these assumptions. This, together with the long and complex interactions of the casual chains, makes it very hard to provide a quantification of these benefits, let alone obtain their net present value. / Costs / The costs of Option 1 (iFUSE) and Option 2 (the status quo) can be categorised as follows / transaction costs: the identification of the assignment, the search for the relevant and available expertise, the contractual negotiation and the assignment monitoring / services costs: the cost of delivering the assignment / environmental costs / These costs are quantifiable, given a specific set of assumptions which is set out together with the calculations below. Sensitive commercial information for the calculations and the calculations themselves are in a restricted annex. / Given that we have a measurable set of costs but there are very significant challenges to measuring the benefits, we have opted for a more manageable analysis of the costs and benefits which entails: / a form of cost effectiveness analysis. / a qualitative comparison of the net benefit between the two options. / a final appraisal judgement weighing quantitative cost effectiveness against qualitative net benefits. / Cost effectiveness analysis / Option 1 - Establish a new outsourced facility which manages the demand and supply for specialist, technical assistance: iFUSE / iFUSE is designed to provide expanded supply of specialist expertise – and potentially higher quality advice – to improve the IC in partner countries. Requests for support are envisaged to come directly from partner governments or through a DFID country office. / Key assumptions in our analysis are: / Matching supply and demand is managed by the MA. / To allow like-for-like comparisons, the bulk of requests for specialist expertise come from country office programmes. As in the status quo, DFID country offices initiate requests for support on their IC programmes to ensure relevance and need and make a final decision on the choice of expert. (In practice we expect partner governments to initiate a substantial number of requests as well.) / MA provides logistic as well as technical support to the deployment of expertise, including covering the cost of incidentals; / Full costs are paid for deployed experts, including daily rates, travel and incidentals, all form part of the appraisal and are paid fully by iFUSE, given HM Treasury rules[14]. / Transaction costs / Processing the deployment of short term specialist technical assistance through iFUSE is expected to be shorter than under the status quo, therefore reducing the transaction costs. This is because pools of experts will already be available from the participating OGDs and the OGD affiliation provides an immediate quality filter without requiring a call for CVs and a trawl through many of them. Likely transactions costs, per short-term assignment, are as follows: / DFID staff Advisory time – up to 5 days: includes writing the ToRs (2 days), choosing the specialists (1 day), monitoring the consultancy (2 days). / Other DFID staff time, up to 1 day – country office staff plays some role to contact the contractor on the logistics of the consultancy but procurement, drafting and negotiating the contracts would be handled by the MA. / MA management fee, including administration costs, staff time and overheads – up to 15% of the value of the contract. A lower figure is likely to be negotiated as part of the procurement process. / Recipient developing country Government officials’ time – up to 2 days / OGD officials’ time – up to 1 day, on the assumptions that the bulk of the transactions are undertaken by the MA but that each OGD will need some staff time dedicated to managing the supply of expertise / Service Costs / These are made up of the ‘daily rate’ of OGD staff and incidentals costs, for an average assignment of 12 days. / The key cost-reducing driver in terms of service costs is that the full cost ‘daily rate’ of OGD staff is lower, and by a significant margin, than the daily rate of a private consultant. We assume that flight costs and incidentals (hotels, subsistence and visas) will be the same under iFUSE as under the status quo, despite the fact that in practice the MA may be able to exploit some economies of scale. / Given these assumptions, the average costs per assignment under iFUSE are estimated to be about £13,897. / Option 2: Maintain the status quo. / Under the status quo, partner governments procure private consultancy services directly or through DFID country offices. As is the case for Option 1, significantly more information is available about procurement through DFID country offices than there is about procurement from headquarters. For simplicity, we present the analysis of costs on the basis of country office procurement. This means in practice: / - demand for specialist expertise is identified by partner governments and DFID in country. / - DFID’s country office takes on the responsibility to deliver short term technical assistance, through private consultancy services such as call down contracts for the procurement of consultancy services. / - the DFID office invests a significant amount of staff resources in the process of identifying and contracting suitable consultants. / Transactions Costs / We estimate the transaction costs per assignment of the status quo as follows (with DFID estimated costs expressed in terms of the opportunity cost of staff time): / DFID staff advisory time up to 8 days: includes writing the ToRs, sending out requests for expertise, evaluating CVs, interviewing candidates, choosing the specialists, monitoring the consultancy. We expect this to take an extra 3 days compared to iFUSE because expertise needs to be evaluated and assessed for suitability and quality while OGD experts will already have a well defined quality standard by virtue of being affiliated to OGDs and their personnel quality standards. / Other DFID staff time, up to 5 days – country office staff usually directly involved in the procurement, drafting and negotiating the contracts. / Resource centre staff time, up to 10 days to identify the potential consultants from a pool of ‘associates’ and conduct logistics and contracting– / Management fee for the resource centre, paid for by DFID centrally. / Recipient developing country Government officials time – up to 2 days / Service Costs / These are made up of the consultancy fees and incidentals costs, for an average assignment of 12 days. The consultancy fee is the average daily rate for a senior consultant. / We estimate the status quo average costs per assignment as £19,868. / The average cost efficiency savings of Option 1 over Option 2 are therefore estimated to be £5,971 per assignment, or 30% of the average assignment cost under Option 2. / Sensitivity analysis / A sensitivity analysis was undertaken by modifying key assumptions, such as / - Demand for support: the original assumption is that there could be up to 80 assignments per year, on the grounds of existing demand from the Office of Fair Trading (assumed to apply equally to at least 7 other OGDs). Demand was increased by 50% and reduced by 50% respectively to see how the results would change. / - Management and administrative fees under iFUSE: during contract negotiations the indicative management and administrative fee of 15% would be reduced by 2 percentage points. / - Use of staff and partner staff times, to see if the results are robust regardless of whether iFUSE results in faster deployments with lower staff resource inputs. / - estimated fees paid to resource centres that currently play a role in supporting DFID offices in recruiting private consultants. / - the average daily rate of private consultants, as it is possible that for highly specialised inputs the daily rate could exceed by 50% the average rate assumed. / In the best case scenario for Option 1, with high demand for iFUSE expertise as compared to highly specialised, more expensive private consultancy services which take a longer time - an additional cost of staff time - to identify consultants, the cost efficiency savings generated by iFUSE could amount to just over 50% of the costs under the status quo. The average assignment costs for Option 1 and Option 2 would be £12,080 and £24,416 respectively. / In the worst case scenario for Option 1, with low demand for iFUSE expertise as compared to average private consultancy services and costs and identical staff time implications as the status quo, iFUSE is 0.7% more expensive than the status quo. The average assignment costs for Option 1 and Option 2 would be £16,592 and £16,460 respectively. / Balance of costs and benefits / Based on the cost effectiveness analysis, the average Option 1 iFUSE assignment is likely to cost about 30% less than the average Option 2 assignment, the status quo. Even under the worst case scenario, Option 1 and Option 2 cost essentially the same. / But, crucially too, the qualitative benefits of Option 1 indicate that iFUSE specialist expertise would add benefits that the status quo lacks, as set out in the theory of change, including the potentially higher quality advice (partly related to increased competition) and more effective knowledge transfer (related to the peer status of experts). These are all likely to positively affect the overall quality and success of IC reforms. / Conversely, the main benefit of the status quo is a pure private sector perspective that can enhance efficiency and relevance of reform efforts to constraints faced by developing country businesses. Meanwhile, iFUSE’s assumed negative impact on the environment can be offset using accepted government procedures (see footnote 5). / In conclusion, the overall net benefits are likely to vary depending on the demand for specialist expertise and on the actual costs of equivalent private specialist expertise – as demonstrated by the sensitivity analysis. But overall, based on the range of additional potential benefits, as well as cost efficiency improvements robust to sensitivity analysis, there is a high degree of confidence that iFUSE will provide additional positive net benefits that will exceed the status quo. / Delivery Risks, Appraisal and Challenges Analysis (Economic, Social, Political, Institutional, Environmental, Fragility/Conflict, Corruption) / The bigger risks and challenges to the successful implementation of this intervention are primarily political and institutional, although the risks related to the inherent fragility of some countries are particularly acute as well. These risks are typical for IC interventions. / For the most part the risks and challenges faced by status quo private consultancy expertise are exactly the same. For example, the risk that policy advice does not translate into effective administrative/regulatory changes which have a positive impact on growth and poverty reduction (iFUSE is likely to do better than the private consultancy status quo on this as set out earlier but the risk still remains) . The main risk is the potential lack of developing country and development experience of some OGD practitioners. This could result in a poor inclusion of: / social issues, including poverty focus and gender sensitivity, and the additional challenges these bring to achieving broad impact, / political and institutional issues, underestimating or not understanding how weak political and institutional systems add to the challenges of successful IC interventions. / corruption issues - under-appreciating its extent, its effects and how it undermines an assignment. / the links between environmental sustainability and IC reform. Dealt with elsewhere in this business case. / the heightened challenges including a faster pace of change and reduced access to information and mobility in fragile states. / The Management Case sets out how this additional risk will be managed.
C. Narrative of Relative Merits of the Intervention Against Critical Success Criteria / Knowledge transfer improves the quality of DFID and partner government IC programmes because it is applicable and relevant to developing country contexts / iFUSE fares both well and potentially poorly under this criterion. / It fares well because: / OGD practitioners have the peer status and practical experience to impart relevant specialist IC knowledge in a policy making environment, which can be of greater value than the status quo. / The links and networks that assignments generate may result in a higher level of ongoing support for partner countries IC programmes which further improves the quality or sustainability of delivery. / It could potentially fare poorly because of the risk outlined above: the low level of developing country experience of some OGD practitioners - noting that many practitioners are likely to have some experience[15]- may reduce the applicability and relevance of engagement below the status quo despite the positive benefit. However this risk can be managed with appropriate management systems (see management case). / Expanded pool of expertise available to DFID and partner governments enhances competition and increases the overall quality of expertise. / Compared to the status quo, iFUSE will increase the pool of expertise available as DFID country offices and partner governments will be able to access both OGD and consultancy expertise instead of just the latter. We expect the additional expertise to drive up the quality of consultancy expertise although there is a risk of crowding out some private sector provision should the programme grow substantially. Overall we assess that iFUSE will result in an improvement in the status quo provided this risk is properly mitigated (see management case). / Knowledge transfer is led by demand from DFID programmes or partner governments and is provided in a timely fashion / The current status quo is assessed to already be demand-led. The iFUSE programme will be designed in this way as well but the iFUSE programme is expected to increase the timeliness of deployments due to the specificity of expertise and the establishment of managed pools of experts, provided these are efficiently used and managed. / The assignments set out clear measures of success and follow up arrangements / As technical assistance assignments under the status quo are usually undertaken in the context of broader aid programmes, it seems to be a good assumption that DFID country offices already invest a significant amount of time on follow-up. iFUSE, in performing a knowledge management function, can ensure not only that clear and consistent measures of success are included in every assignment but that lessons are learnt across a diverse range of programmes as the number of assignments grows, as to which measures of success are most effective in transforming outputs into outcomes. / Environmental Implications of each assignments are adequately addressed prior to deployment / DFID will ensure that, in the context of iFUSE procedures, there will be a provision to draw on the necessary expertise to ensure that potential climate change concerns of each individual assignment are adequately taken into consideration prior to deployment, so that each individual expert is aware and prepared to tackle these during deployment as relevant, to ensure the programme remains relevant. This is an improvement over the status quo where DFID/partner governments would have less control over and most importantly fewer ways of increasing the climate change skills of the consultant hired. / Appraisal Result and Rationale / This appraisal finds that the proposed iFUSE programme will offer improved cost efficiency, more qualitative benefits and therefore greater net benefits versus the status quo, and an improvement in the five critical success criteria compared to the status quo provided that, in two of the criteria, key risks are proactively managed. This appraisal indicates that Option 1 (the iFUSE programme) should be approved and funded.
E. Measures to be used or developed to assess value for money / Key value for money measures and performance metrics, whose indicators will be developed by DFID and the MA during iFUSE inception and will be used thereafter to report on performance will be: / Cost per assignment / Cost per assignment as a percentage of average short term private sector consultancy assignment cost. / MA cost as a percentage of total deployment costs per year compared to the equivalent measure for resource centres. / Evidence for the generation of peer networks in evaluation surveys and analysis. / Speed (in days) of deployment from TORs submittal compared to private consultancies. / Level of satisfaction with assignments by DFID country office and partner government recipients and comparative analysis with private sector consultancies. / Change in level of satisfaction and cost of private sector consultancies before and after the start of the iFUSE programme (if feasible). / Measures to determine poor value for money are as follows: / On average, lower satisfaction with assignments by DFID country office and partner government recipients of OGD expertise than private sector consultancies. / Costs per iFUSE assignment that equal or exceed average short term consultancies. / Costs of MA as a percentage of total deployment costs per year that equal or exceed the equivalent measure for resource centres. / VfM Summary: iFUSE and the 3 Es / The iFUSE option will deliver value for money by limiting the administrative costs of the programme to a reasonable percentage of total budget, reducing the cost of inputs (advisory expertise), increasing competition and sources of supply which should drive up the quality of expertise and potentially, through additional benefits that are difficult to quantify, having a greater impact on IC reform than the status quo. Detail is as follows: / Economy: purchase of inputs – will be based at current cost rates in other Whitehall Depts. Costs cannot be reduced below these as this would be anti-competitive so a limit is already in place but the appraisal shows a lower input cost than the status quo and therefore an improvement in economy. / Efficiency: turning inputs into outputs – Administrative cost control will be built into the contract with the MA to safeguard a minimal level of efficiency. The other key measure will be the quality of technical expertise and feedback mechanisms from developing country partner governments and DFID country offices. But the theory of change suggests that iFUSE will promote higher quality and therefore improve efficiency. / Effectiveness: outputs to poverty outcomes: Very much dependent on the IC theory of change. With higher technical assistance quality from iFUSE expertise, there is a probability of more effectiveness but this is extremely difficult to quantify. / Cost Effectiveness: inputs for impacts: The appraisal case contains a cost effectiveness analysis which shows a clear improvement to the status quo. But the difficulty with directly measuring impacts makes quantifying in terms of final impact very difficult.
[6] See for example: “ Building Effective States, Forging Engaged Societies: Report of the World Bank Task Force on Capacity Development in Africa” (2005) World Bank, available at http://siteresources.worldbank.org/EXTAFRDEVOPRTSK/Resources/acdtf_report.pdf Or “Guidance Note on Danish Support for Capacity Development “ (2006) by Danida available at http://www.oecd.org/dataoecd/43/16/40986702.pdf
[7] notably whether rents can still be extracted.
[8] See a quick literature review and some evidence . Crespi, John M and Marette , Stéphan (2006) “Quality and Competition: An Empirical Analysis across Industries” Working Paper 06-WP 420 March Centre for Agricultural and Rural Development Iowa State University available at http://ageconsearch.umn.edu/bitstream/18426/1/wp060420.pdf#
[9] Investment climate reform also includes infrastructure improvements and financial sector development which are not explicitly referred to in this theory of change.
[10] See for example Nick Axford; Matt Jonas; Vashti Berry; Vicky Green; Louise Morpeth (2010) Can study tours help promote evidence-based practice in children's services? European Journal of Social Work, Volume 13, Issue 4 December 2010 , pages 523 - 543 available at: http://www.informaworld.com/smpp/ftinterface~content=a920991228~fulltext=713240930~frm=section
[11] See IMF’s independent evaluation at: http://www.ieo-imf.org/news/pr/pr0501.html
[12] IDB study on technical assistance available at: http://ideas.repec.org/p/idb/ovewps/0109.html
[13] Such as the 2001 Review of the Commonwealth Secretariat’s Assistance to Member States with Investment Promotion and Negotiations in the Extractives Sectors
[14] HMT rules state that when one government department provides a service to another department full costs must be recovered to ensure fair competition.
[15] This is likely to be the case especially for OFT, HMRC, UKTI and BIS officials

Commercial Case - Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / DFID is expecting to procure directly the services of the Management Agent (MA) and provide the necessary funds to pay for the operation of iFUSE on a strictly reimbursable basis – in accordance with standard contract terms. iFUSE would manage a range of responsibilities set out in the Management Case. / DFID will initiate a ‘restricted OJEU’ competition for the provision of professional management services, as agreed with DFID’s Procurement Group.
B. How does the intervention design use competition to drive commercial advantage for DFID? / iFUSE is designed to improve Value for Money for DFID by tapping into an under-utilised source of specialist IC technical expertise in developing countries from OGD practitioners. The Appraisal Case sets out in detail how iFUSE would improve on the cost effectiveness of the status quo and potentially increase quality of services due to increase choice of expertise providers to drive commercial advantage for DFID. / The prospective MA bids will be assessed on the basis of delivering the expected services for the lowest budget at sufficient quality. As it is pointed out in the section below, we believe there will be enough interest by a significant number of small and larger providers that a competition will effectively lower the costs of MA services to DFID. / It is possible to define specific project objectives for the supplier of management services (the MA), notably that: / 100% of deployments adhere to agreed deployment date, / the vast majority of deployed experts provide positive feedback on the quality of the logistical support provided, / both OGDs and DFID country offices and developing country partners are fully aware of the existence of the programme; / there are a reasonable minimum number of deployments each contracting year. / In the first year we would expect the MA to be particularly flexible to operational change should the programme be delivering below an acceptable standard. A variable percentage could be paid to the MA for each successful secondment. This will ensure that there is a positive incentive to meet the demand that the specialist technical assistance is aimed to provide. Any contract issued will be under standard DFID terms and conditions and will be fully compliant with DFID policies on staff travel. / DFID and the MA will define, during the inception, key milestones on economies of scale due to increased demand for services, and link these to management fees.
C. How do we expect the market place to respond to this opportunity? / There is a buoyant market for the provision of the type of services relating the management of iFUSE, both at small business and larger supplier level. We would therefore expect a significant number of private providers to express an interest in the competition. / The market of reference is the UK, especially given the needs to negotiate agreements with OGDs whose headquarters are in the UK. Unlike many of the developing country markets where DFID country offices source their services suppliers, the UK market for management services provider is expected to be very large and diversified. Moreover, the services requested – related to project management, financial management and logistics support management – are general and widely available. There should be a range of providers available to compete for the tender to ensure there are no restrictions to the competition between suppliers. / The opportunity will also be attractive because it will involve managing a network of UK Government Department specialists, thus providing an opportunity to the winning contractor to build networks and relationships which may prove commercially valuable in the future. / To conclude, the scale of the project, the relative lack of technical complexity of the services required and the expectation that the market is very well developed and would be attractive suggest that the competition could deliver strong value for money through procurement.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / A key cost driver will be travel costs which rise the more ad hoc and short notice travel plans become. One benefit of setting up iFUSE is that it might drive transport costs down through structured management of the demand and supply for services. This is expected to partly offset sudden increases in oil prices which are outside of iFUSE’s control. / A second key cost driver is the administrative costs iFUSE will pay in transferring money from DFID to an OGD to fully cover the costs of each assignment. The MA will be asked to develop systems to streamline the payment process.
E. What is the intended Procurement Process to support contract award? / DFID’s Procurement Group has advised that most appropriate intervention with the market would be engagement with the EU Restricted Directive. This entails: / Advertising for the provision of services, through dissemination of ToRs to initiate restricted competition led by 3 to 4 technical questions to identify bidder shortlist. / Limited bidding by 3 to 4 successful shortlisted suppliers. / Formal procurement process followed thereafter with a key initial requirement for bidders to produce a full workplan. The winning contractor should be chosen and the contract awarded no later than 11th of November 2011. / A 6 week inception phase to put systems, documentation and a specialist database together before delivery of the service commences by January 2012.
F. How will contract & supplier performance be managed through life of intervention? / The MA Contract will include objective key performance measures fully under the supplier’s control. Objective, reasonable metrics will clearly define steps to contract termination. / Monthly activity reports and Quarterly progress reporting to DFID including risk monitoring as well as independent verification measures will be put in place. / Annual reviews and independent evaluation will provide ongoing monitoring to ensure effective service delivery.

Financial Case
A. How much it will cost / DFID will provide £3.48 million over 4 fiscal years, from November 2011 to 31 March 2015. Money is available within GRD/ICT programme budget and this allocation has been approved by the Policy Division Director and is available. / Pending a successful completion and a positive outcome of an external review at the end of the scheduled iFUSE programme in March 2015, more funds could be made available to extend the life of iFUSE but would need to be approved as part of the next HMG spending review period and would require an updated business case. / HMT delegated authority approval will not be needed for iFUSE as HMT has advised that the programme is not contentious and is too small in monetary terms to require their approval. HMT were consulted on the iFUSE model and indicated on 13 July 2011 that they were content with it.
B. How it will be funded: capital/programme/admin / This is programme expenditure as the beneficiaries of the intervention are DFID partner governments. The total budget currently allocated for iFUSE is £3,480,000 and is projected to be disbursed as follows: / 2011/12 – £ 180,000 / 2012/13 – £ 600,000 / 2013/14 – £1,000,000 / 2014/15 – £1,700,000
C. How funds will be paid out / Payment will be on a strictly reimbursable basis. Programme performance metrics will be developed by DFID and the MA during the inception phase to ensure the MA is incentivised to provide value for money. The contract will include milestones linked to payments – where appropriate – to closely manage and quality control MA performance, and an exit clause will be included should performance prove unsatisfactory. Otherwise, payment will be made at regular intervals depending on the volume of services provided.
D. How expenditure will be monitored, reported, and accounted for / Financial statements (on a monthly basis in the first six months and quarterly thereafter) will be required along with a yearly external audit where the annual audited accounts are presented to DFID. / - Possible databases, tracking systems and knowledge assets developed by the MA may revert to DFID for internal use in a different or follow-up programme. / - Administrative costs should not exceed 15% of total programme budget to ensure value for money. / - As the work will be contracted out, payment to the MA will be made in arrears. There should, therefore, be no need to return unused funds to DFID at the end of the project. / - Costs of audit, operational reports and quality assurance tracking will be borne by the iFUSE budget within the 15% administrative cost maximum. Review and evaluation costs will similarly be borne by iFUSE out of its budget. See Management Case for evaluation plans.

 Management Case

A. Oversight / An iFUSE oversight body will be established, The Oversight Committee (“The Committee”), which will include the MA, one or more representatives from DFID (including potentially DFID country offices), OGD representatives and (possibly) developing country partner governments. DFID will chair and convene it with administrative assistance from the MA. The Committee will provide, by consensus, a strategic oversight role, assessing performance, opportunities and challenges and recommending change, especially as a result of evaluations and eventually in the consideration of possible extensions to the life of the programme beyond its expected close. The Committee will also verify that appropriate procedures are in place to ensure: / responsiveness and efficiency in meeting requests for support. / effectiveness in providing relevant and excellent quality support. / lessons learnt are fed back into processes and procedures. / It is envisaged that The Committee will be relatively light touch and informal. It will meet every 4 months in the first year of iFUSE operations and bi-annually thereafter, with the option for 2 meetings in the early part of the programme, at the start and at the conclusion of the inception period. / Participation / UK OGDs expected to supply specialist expertise include: / UK Department for Business, Innovation and Skills (BIS) / Better Regulation Executive (BRE) / Local Better Regulation Office (LBRO) / Her Majesty’s Revenue and Customs (HMRC) / Her Majesty’s Treasury (HMT) / Office of Fair Trading (OFT) / Competition Commission (CC) / Ministry of Justice (MoJ) / Intellectual Property Office (IPO) / UK Trade and Investment (UKTI) / Financial Services Authority (FSA) or equivalent. / Land Registry (LR) / Scottish Enterprise (SE) / Infrastructure UK (IUK) / Department for Transport (DoT) / Other bodies with relevant IC experience to be agreed by DFID. / Indicative Timeline / Business Case Approved -17 August 2011 / Contract Award -11 November 2011 / MA Mobilisation and inception begins -21 November 2011 / IFUSE IMPLEMENTATION STARTS -15 January 2011 (assumes inception progress stops for 1 week in December.) / First evaluation begins (completed) -15 January 2013 (end Feb 2013) / Possible Expansion (subject to evaluation) - 15 April 2013 / Second evaluation begins (ends) -15 January 2015 (end Feb 2015) / Programme closes unless extension is recommended - end March 2015 / An external evaluation will be completed after 12 months and no later than 15 months from the date that iFUSE implementation begins. / Subject to the results of the first evaluation, iFUSE may expand its operations. The evaluation will recommend any changes to iFUSE operations and the feasibility of expanding the programme while remaining on a non-profit basis such as to: / Facilitate and manage medium to long term assignments by OGD staff of more than 20 days duration each and potentially long term outward secondments of OGD staff into partner governments or DFID programmes. / Expand beyond OGDs the list of entities supplying specialist IC expertise, to include for example, professional bodies (such as the Institute of Civil Engineers). / The winning contractor should demonstrate competency to provide support to all potential aspects of the programme and will make recommendations for change in light of the findings of all evaluations. Any decision on expansion of operations or extension of the programme’s lifespan will be made by DFID in consultation with “The Committee”. / The risk matrix and the Log-frame may need to be updated to reflect revised expectations as a result of agreed changes to the programme from the findings of evaluations. No other major changes to this business case are envisaged. / As the sole funder of iFUSE, the responsibility for taking final decisions in relation to iFUSE operation, and to ensure the MA meets the contractual obligations, rests with DFID’s Investment Climate Team (ICT), to which the MA will report directly. / Further Programme Extensions / DFID’s Procurement Group have advised that subject to satisfactory performance, evaluation findings and the recommendations of The Committee, iFUSE, and therefore the management contract, may be re-tendered or extended for 2 calendar years beyond the duration of the original management contract. A further extension of up to 50% of the value of the original contract beyond these 2 years additional years can also be negotiated. Any extension will be at the sole discretion of DFID.
B. Management / As the sole funder of iFUSE, ICT is responsible for engaging the MA through a competitive tender and maintaining the contractual relationship. The programme will be delivered by the MA through the following activities and outputs for which they will have responsibility: / Liaise with OGDs to identify specialists and establish a pool of specialists; / Develop and manage individual Memoranda of Understanding (MoUs) with participating OGDs which set out the terms and conditions for their participation; / Manage the pool of expertise to be deployed on a short-term, demand-led basis to support developing country partner objectives, including establishing and managing an up to date system for storing details of the specialists available by IC theme. / Manage and prioritise requests for expertise from partner governments, DFID programmes and other bodies and ensure they meet pre-determined eligibility criteria. / Establish, maintain and manage a reporting feedback system to track the quality of expertise deployed, information exchange and accumulate experience of knowledge transfer to improve programme functioning and DFID knowledge on an ongoing basis. / Support and facilitate short knowledge transfer for partner government officials, through site visits, inward attachments or twinning arrangement visits of developing country delegations to the UK; subject to set criteria. / Provide logistical and technical support to ensure specialists are ready to transfer knowledge to a developing country environment (facilitating transport, visas, hotels). / Paying for travel and incidental costs and full OGD salary costs of technical support. / Develop a system using existing, standard software packages to store financial and operational information for the programme and accumulate and disseminate knowledge on programme performance and lessons learnt. / Disseminate information and actively promote the existence of the programme and lessons learnt and best practice (including through an annual workshop for DFID, OGDs and as practicable recipient governments). / Reporting to DFID on programme performance, key performance indicators and the strategic relevance of the programme. / DFID’s ICT will monitor and manage the MA’s performance for results based delivery. A set of quantitative metrics that measure MA performance will be included in the contract, developed with the MA during the inception phase and monitored regularly through the MA tracking system and monthly reports. These will include at the output level: / the number of assignments completed (assessed against demand); / the number of assignments completed on time; / the amount of funding disbursed; / the geographic coverage of the assignments ; / the percentage of end of assignment reports rated ‘very good’ or ‘good’ by recipients. / the total number of deployment days, broken down by OGD; / feedback questionnaires from deployed experts to assess the effectiveness of the technical and logistical support provided by the the iFUSE MA; / annual light touch questionnaires to DFID staff (to determine programmes profile, assess emerging demands / determine course correction). / A proportion of the management fee to the MA will be linked to performance. Details will be determined and finalised during the inception phase. A monthly activity report will enable DFID to spot early signs of poor performance. More detailed quarterly reports will enable careful consideration of performance against demand and the constraints faced by suppliers. / Very poor value for money will be measured by, among other indicators: iFUSE deployment times exceeding the status quo, assignment and management costs exceeding those under the status quo, low deployment rates, a majority of deployment reviews rated unsatisfactory, a shallow and stagnant overall pool of expertise. / Unexpected success would include a large number of requests for deployment, a larger than expected number and total days of deployments and near perfect deployment reviews. Specific metrics for failure and success will be developed by the MA with DFID support and finalised during inception. / Management of the programme within the ICT will be the responsibility of the property rights advisor. The economic advisor will provide advisory support and the programme officer will provide management and budgetary support.
C. Conditionality / iFUSE does not provide funds directly to partner governments, and therefore issues around conditionality do not apply.
D. Monitoring and Evaluation / Evidence and lessons learnt / The appraisal sets out key elements for successful technical assistance[16] and notes that there are many evidence sources that demonstrate its benefits. The major lessons set out in this business case will be incorporated into iFUSE design and operations. / Monitoring and evaluation plans / The MA will be responsible for adopting the monitoring and evaluation plan steered by The Committee. The MA work plan developed by the MA with ICT consultation and approval will explain how each Log-frame milestone and target will be delivered. / For effective monitoring, the MA will capture information for assessing performance in a timely, effective and efficient way. Some of the key rigorous targets at outputs, outcome and impact level are provided in the iFUSE log-frame which may be updated during the inception phase by DFID and the MA. As iFUSE will be entirely demand-led, some degree of flexibility will be required so that realistic targets, particularly at the output level, can be adapted to changing demand patterns. The MA will be responsible for setting out a lessons learning strategy to enhance the effectiveness of iFUSE during implementation. / Beyond monthly activity reports, the MA will be responsible for producing a quarterly narrative on progress, inclusive of a risk monitoring report. Expected data to be collected at the outcome level includes: / end user assessments of assignments or user satisfaction surveys (to assess the quality and effectiveness of the advisory expertise provided); / the inclusion of specific targets for the provision of high quality specialist advice within the performance management systems of OGDs. / Annual performance reviews - against Log-frame outputs and main outcomes - will be undertaken internally by DFID. Details for the first external evaluation – which could be lead by a senior DFID or OGD adviser – are set out in Section A ‘Oversight’ of this Management Case. / A second external evaluation (to be completed by end of February 2015) will include an impact assessment and will determine whether iFUSE, and the related management contract, should be extended beyond its completion date. Further reviews and evaluations will be completed during the project extension beyond the original contract length to assess performance and make further future recommendations on the life of the programme. The project completion report will be completed when it is decided to end iFUSE operations.
E. Operational Risk Assessment / Risks Probability of occurring Likely impact / 1. OGDs cannot supply most suitable and experienced staff due to resource and staffing constraints. Medium - expected to rise above medium as administrative budgets fall. Medium to high / 2. OGDs use iFUSE to reduce their budget constraints. Medium – as above Medium to high / 3. Service/performance of MA is poor quality. Low to Medium Medium / 4. Insufficient demand for iFUSE expertise to justify costs of the programme (eg admin as % of total programme expenses rise to 20% or more). Medium High / 5. Partner governments are less responsive than expected to the advice provided Low to Medium Medium / 6. iFUSE provision of UK specialist expertise is seen as a form of tied aid Low to Medium Low to medium / 7. Demand for iFUSE services creates perception of unfair competition and potentially displaces private sector provision of services. Low to Medium Medium / 8. Deployed personnel has limited ability to adapt to transfer knowledge Low Low / 9. Tensions arise between OGDs, country offices, partner governments and DFID HQ due to contrasting interests or incentives. Low High / iFUSE carries the potential for significant (Medium) risk, especially with regard to both the supply of demand for specialist IC expertise. Recommendations for mitigation are as follows: / 1. Supply is too low due to resource and staffing constraints: The sizeable squeeze on public sector administrative and programme budgets may constrain supply despite the existence of iFUSE. In order to mitigate this risk, iFUSE will comply with HMT protocol that full costs should be recovered for all assignments. If constraints on supply are related to staffing rather than financial, iFUSE will explore with OGDs alternative methods of advisory delivery (including virtual meetings) and will need to remain flexible to adapt its services to address binding constraints on OGD resources. / 2. Use of iFUSE to reduce budget pressures: There are likely to be increased pressures to use it as a way to provide more opportunities to OGD staff who have seen career options reduced and therefore that iFUSE is used in areas or activities outside of its original objectives. The key mitigation mechanism is a clearly worded MoU with each supplying Department, clear eligibility criteria for each reimbursable assignment that the MA approves and strong management by the MA and oversight by DFID. / 3. MA poor performance or specialist poor performance affects quality of iFUSE delivery. / The former can be managed through a performance-based contract with clear measures of failure related to MA performance, as set out earlier in the management case. But the MA cannot be contractually responsible for the quality of the professional expertise provided, because it has no formal responsibilities over it. This risk can be managed by setting out in the MoUs between DFID and OGDs clear responsibilities for the delivery of high quality services by the OGDs, including: / Stating that advisors represent the UK or their professional body and must ensure high professional standards to safeguard their organisation’s reputation. / Ensuring feedback on deployments is given to line managers and The Committee. / Capturing the lessons learnt from each assignment, identifying problem areas and addressing them during the pre-deployment stage of each assignment. / 4. Insufficient demand for iFUSE expertise to justify costs. This will be dealt with through the monitoring of MA and programme performance with clear metrics for programme failure and closure (or retendering) a core part of the contractual arrangement with the MA. The MA will be tasked to promote and communicate iFUSE to help generate demand. / 5 and 8. Less responsiveness of recipients to specialist expertise, and lack of contextual understanding: If recipients are less responsive to specialist expertise, this will most likely be to due to some OGD practitioners lacking developing country contextual knowledge– although many will have this knowledge. For those that don’t, risk mitigation will be part of the iFUSE design:, demand-led assignments with training provided on country characteristics prior to deployment, specific training on fragile states, climate change and gender aspects of IC reform where relevant, as well as procedures to ensure recruitment includes criteria for flexibility, adaptability and knowledge of developing country contexts. Feedback on assignments will determine other reasons for poor recipient responsiveness and a flexible iFUSE design will allow the programme to respond to any new, emerging risks. / 6. Perception of tied aid: Given its initial UK Government focus, this is a significant risk. To mitigate this perception the provision of specialist expertise will be strictly demand-led. The MA will ensure that all requests articulate the added value of iFUSE over other options and, encourage requesters to consider other options if added value is unclear. Programme expansion will potentially open up supply from non-UK bodies to also negate this perception. iFUSE will be designed to ensure it complies with the International Development Act. / 7. Unfair Competition and Private Sector Displacement. There is possibility - more so if the iFUSE becomes open to professional bodies - that the use of non-private expertise to provide services currently provided primarily by private consultants might raise concerns of unfair competition. But iFUSE operations will remain fair and legal provided that they only reimburse employment costs and expenses for services provided on a non-profit, non-commercial basis. If iFUSE were to experience a very significant demand for its services and related expansion of its activities, there could be some risk of crowding out private sector provision. At present, this seems unlikely, but will be monitored with appropriate mechanisms if the programme expands. / 9. Tensions between stakeholders due to contrasting interests or incentives. To manage this risk the MA will need to ensure that it employs a clear communications strategy with all stakeholders and a plan for expectations management, and ensure MoUs address and resolve the main potential incentive conflicts. DFID will use the Implementation Committee as a forum to address major conflicts in a transparent manner and will do so while retaining decision-making authority over the programme.
F. Results and Benefits Management / Programme results will be monitored against the programme Log-frame. The programme will be subject to Annual Reviews that will assess progress against the Log-frame, and a Project Completion Review which will assess benefits against the Log-frame targets. Evaluation details to track benefits have been included in the monitoring and evaluation section.
[16] See for example: “ Building Effective States, Forging Engaged Societies: Report of the World Bank Task Force on Capacity Development in Africa” (2005) World Bank, available at http://siteresources.worldbank.org/EXTAFRDEVOPRTSK/Resources/acdtf_report.pdf Or “Guidance Note on Danish Support for Capacity Development “ (2006) by Danida available at http://www.oecd.org/dataoecd/43/16/40986702.pdf