Business Case and Intervention Summary

Intervention Summary

## Title: Palestinian Programme Strategic Intervention Fund

What support will the UK provide?
The UK will provide £1 million to finance at least 12 small projects over 4 years which will support work by the Department for International Development and our partners to improve the lives of Palestinian people and contribute towards the Middle East Peace Process. The Strategic Impact Fund will be used to strengthen the evidence base for DFID and partner programmes, improve DFID’s influencing ability with donors and the wider community, and support innovation to drive improvements in project delivery and value for money.

Why is UK support required?
Much of our work supporting Palestinians within the Occupied Palestinian Territories (OPTs) and in the near region is carried out in partnership with, and through others. Policy influencing is a major element of our work. DFID has previously developed a key comparative advantage in its ability to support small but strategic and influential interventions that generate new evidence, promote innovation and leverage results via policy change and programme responses. Many partners are hampered by bureaucracy and cumbersome procedures which hinder the speed and flexibility needed to support small-scale, rapid interventions which can take advantage of windows of opportunity or address new risks to stability. Organisations which are capable of doing this work often do not have the capacity or finances available to carry out the intervention when needed. An ability to support a range of strategic interventions would enable the programme to maintain maximum flexibility, resilience and leverage more impact in order to deliver greater development outcomes.

What are the expected results?
The project will help DFID and its partners to deliver high quality programmes which will improve the lives of Palestinian people and contribute to a two state solution, as measured by year on year improvement in the Palestinian Programme portfolio quality score. This will be achieved through the generation and use of new evidence, new pilot studies and new ways of working, with at least 75% of interventions in these fields meeting or exceeding expectations in delivering strategic impact. The project will produce at least: / 6 high quality studies which strengthen the evidence base for DFID, Palestinian Authority and other partner projects, ensuring projects stay relevant and effective in a fast-moving political and economic environment, and leading to better value for money and reduced risks to project delivery / 3 pilot projects that assess and develop innovative approaches to project delivery and which are taken forward by DFID/other partners to increase the returns on investment / 3 influencing activities which bring together key development actors working to support Palestinians in order to improve harmonisation and coordination of development activity and leverage development outcomes beyond that which a single actor can deliver alone.

BUSINESS CASE

Strategic Case

A. Context and need for a DFID intervention / Context / The Israeli-Palestinian conflict is rooted in the 1947 plan to partition the then British Mandate Palestine into Arab and Jewish states, the subsequent establishment of the state of Israel in 1948 and the ensuing war which displaced hundreds of thousands of Palestinians as refugees. The 1967 Arab-Israeli war led to Israel’s occupation of the West Bank and Gaza Strip, and annexation of East Jerusalem. UK policy (in line with international law and significant international consensus) is that the Occupied Palestinian Territories (West Bank, Gaza, East Jerusalem) or ‘OPTs’ constitute the land that should – as a result of negotiations between the parties – form the basis for a future Palestinian state. The UK’s ultimate goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. DFID’s Operational Plan for OPTs seeks to support that goal, by focusing on i) reducing poverty, and ii) supporting the development of a peaceful Palestinian state and society. / The entrenched and highly unpredictable nature of the Israeli-Palestinian conflict and the impact of Israeli occupation mean the situation in the Occupied Palestinian Territories (OPTs), and for Palestinian refugees in the region, is very fragile. There have been two violent Palestinian uprisings against the occupation, and Israel has suffered periods of bombings and rocket attacks against its cities. An escalation of violence in 2009 led to significant numbers of deaths and destruction in Gaza. In recent years the internal Palestinian scene has been dominated by the conflict between the Fatah and Hamas factions, which saw Hamas taking control of Gaza by force in 2007. The Hamas/Fatah reconciliation agreement announced in May 2011 is yet to be implemented, adding another degree of uncertainty to the internal political situation. / There have been various internationally sponsored attempts over many decades to resolve the conflict by negotiating a ‘Two-State Solution’, most notably the Oslo Accords of 1993. Most recently, the Quartet have called for an immediate resumption of meaningful talks. But trust is very low between the parties, with each side accusing the other of unilateral action (the Palestinians for seeking recognition via the UN in September 2011, Israel for its continued building of illegal settlements within the OPTs). Prospects for peace thus remain uncertain. / Economic conditions in the OPTs are closely tied to political developments as a result of the ongoing conflict and occupation. Israeli movement and access restrictions in the West Bank, incursions, and its almost complete control over Area C (60% of the West Bank), East Jerusalem and the Gaza Strip act as major impediments to economic development. For example, the IMF estimate that if there is significant easing of movement and access restrictions, growth in the OPTs will be at 7-10% per year 2012-14, whereas if the status quo is maintained (line B), growth will be under 4%. The Palestinian Authority (PA), has very limited control over its income, given the unpredictable nature of aid flows (37% of its income in 2010), and the fact that tax revenues (41% of its income in 2010) are transferred to the PA via Israel, which collects on the PA’s behalf. Both sources of finance are vulnerable to political leverage (for example in response to Hamas/Fatah reconciliation, and Palestinian action at the UN). Political change thus could lead to either rapid deterioration or continued improvements in conditions in the OPTs. The situation in Gaza is particularly fragile and a future humanitarian crisis cannot be ruled out. Our development support is likely to need to respond to major changes in the political and operating environments over the course of the next four years. / Need / Both DFID’s business plan for 2011-15[1] and the recently published Humanitarian and Emergency Response Review[2] note the need to improve the coherence and performance of UK aid in fragile and conflict-affected countries like the OPTs. Under the OPTs operational plan, the majority of the Palestinian programme resources will be concentrated on fewer, larger projects focused on strategically targeted areas. This will include handing over the lead in certain sectors to others as appropriate. / However, to maintain the ability to respond effectively to the changing political and humanitarian situation on the ground, and to continue to deliver development objectives effectively, we have identified the need for a mechanism capable of supporting targeted inventions aimed at addressing emerging risks, opportunities and issues within and across projects, which cannot be easily incorporated into our ongoing projects or carried out by others. These interventions fall into three main areas: strengthening the evidence base for DFID and partner projects; supporting innovation and improving DFID’s influencing ability with donors and the wider community. These are therefore logically best addressed by an overarching Business Case addressing these three areas in a strategic, planned way rather than by ad hoc, individual interventions. / a) Strengthening the evidence base / The availability of statistics is relatively good in the OPTs with a World Bank Statistics Capacity Building Indicator score of 71/100 compared with an average score of 58/100 for the Middle East and North Africa. The Palestinian Central Bureau of Statistics (PCBS) has a comprehensive programme of surveys and censuses which use internationally recognised methodologies. However, there is a general lack of strategic analysis in relation to the large amount of available statistics in the OPTs. / In addition, as set out in the context section above, unpredictable and sudden changes in the political environment can have a significant impact on development programmes. An ability to fund focussed research on the impact of these changing situations on project delivery would build resilience into DFID and partner programmes, ensuring development projects stay relevant and effective in a fast-moving political and economic environment. For example, changes in the Israeli access regime to Gaza announced in June 2010 could impact very significantly on our policy and programme delivery. Being able to commission an ad-hoc survey of the impact of the restrictions enabled us to ensure programme direction remained appropriate and effective - leading to better value for money and reduced risks for projects. / b) Supporting Innovation / The operating environment in the OPTs and the near region is constantly evolving. The Palestinian team and our partners needs to be able to meet these new challenges, as well as maximise new opportunities. During the course of projects we often find out about innovative work being done by others which we could support to both complement and strengthen our own programmes and inform the development of new programmes. A mechanism such as the Strategic Impact Fund would provide the opportunity to pilot new ways of working in low risk way, evaluating lesson learnt and improving skills to strengthen future programme development. The fund will be used not only to support innovation within DFID-funded programmes, but also to support other and multilateral partners in assessing and implementing innovative ideas that will leverage our programme results and increase the returns on DFID and others investment. New ways of working, for example, could range from partnerships with the private sector, to supporting partners to be innovative in their approach to a problem. Further details of this is given in the impact and outcome section. / c) Influencing / There are a wide range of development actors in the OPTs including approximately 80 donors and international agencies, numerous NGOs (including approximately 1500 Palestinian NGOs), the Palestinian Authority (PA) and other state bodies. A local aid coordination secretariat and donor cluster forums are in place to try and coordinate the flow of aid and activity of donors, multilaterals, and international NGOs and local NGOs, and to align these with the Palestinian National Plan (PNP) developed by the PA. / In designing business cases for each of our major projects, we look to join up and coordinate with partners working in the field where possible. Despite these efforts, the sheer volume of development activity, the challenges of different timeframes and project processes of different organisations, and the additional resources required to manage complex work of coordination means that opportunities for harmonisation and joint working are often missed resulting in duplication of effort. For example earlier this year, three UN agencies all released a report on the economic situation in the OPTs within days of each other. Material of this type is of high value to donors and the PA as an evidence base for both programmes and influencing work with partners – consistent and joined up messages from the UN agencies would have supported a coherent influencing strategy much more effectively. Improved coordination will ensure projects are meeting an unmet need, that donors, the PA and partners are working together effectively , and that the aims of the PNP are achieved. / Effective influencing is key to maximising the impact of our programme. Our statebuilding work in particular depends on aligning interests and incentives between DFID, the Palestinian Authority and other donors to ensure maximum progress on institutional reform. However, as DFID’s policy paper on influencing strategies recognises, successful influencing is often born of unique and unrepeatable contexts and opportunities and the ability to seize opportunities and take risks. A strategic impact fund would provide us with the resource and ability to do this effectively, enabling us to effectively leverage soft power to deliver greater impacts and improving value for money. / Why DFID? / Much of our work in the OPTs and the near region is carried out in partnership with large multilateral organisations, such as the European Union or UN agencies. Multiple layers of bureaucracy and cumbersome procedures mean many of these organisations lack the speed and flexibility needed to support small-scale, rapid interventions which can take advantage of windows of opportunity or address new risks to stability. Organisations which are capable of doing this work often do not have the capacity or finances available to carry out the intervention when needed. An ability to support a range of interventions would enable the programme to maintain maximum flexibility and resilience. This type of work also informs our own programmation and has significant impact in taking forward UK lobbying priorities.
B. Impact and Outcome / The overall impact of the project will be to improve the quality of DFID’s and partners’ work in the OPTs, ensuring that resources are used to deliver a high quality programme which improves the lives of Palestinian people and contributes to a two state solution. High quality means good value for money, sustainable impacts, meets clear needs and achieves programme aims. This will be measured through an improvement in the Palestinian programme portfolio quality score over the four year life span of the project. / The outcome will be the generation and use of new evidence, pilot studies and ways of working to strengthen the impact of DFID's work in OPTs. The strategic impact of each intervention in achieving this outcome will be assessed at evaluation stage, with a target of at least 75% interventions meeting or exceeding expectations. Illustrative impacts of each area of intervention drawing on evidence from previous Palestinian programme funds are set out below: / Strengthening the evidence base / New evidence will be used and disseminated to others to ensure projects stay relevant and effective in a fast-moving political and economic environment and leading to better value for money and reduced risks to project delivery. For example, a Palestinian Programme fund paid for a short and low cost household survey to see if the reduction in restrictions on blockade on Gaza announced by Israel in June 2010 had improved the lives of Palestinians living in Gaza. The survey found that there had been little impact – this meant that we had up-to-date information to use in our dialogue with Israel, and DFID and the wider donor community had clear facts to use when designing new projects. Evidence of this kind ensured the team could explain clearly why decisions were made, help increased transparency, show better value for money, and improved communications with both parliament and the wider public. / Supporting Innovation / Pilot projects that will assess and develop innovative approaches to project delivery and are taken forward by DFID/other partners to increase the returns on DFID/donor investment. For example, in June 2010, we supported the Palestinian Investors Conference in Bethlehem which successfully brought together the Palestinian private sector and over 1000 Arab and Western investors. Several major investment announcements were made including $500 million (including $20 million from DFID) for the provision of affordable housing in the West Bank. / Influencing / Influencing activities will bring together key development actors to improve harmonisation and coordination of development activity in the OPTs and leverage development outcomes beyond that which we can deliver alone. For example, in May 2008 the UK hosted the Ad Hoc Liaison Committee (AHLC) in London and the costs of this were met from a previous Palestinian Programme fund. The AHLC is a high level donor meeting which is valued by participants as it is the only forum where Israel and OPT’s both attend, where development assistance and its role in the political process is highlighted, and constraints emphasised. By hosting the meeting, DFID was able to ensure a concerted effort to make donors pay out committed development funding to the PA and provide indicative figures of support for the new year improving the predictability of aid flows. / . ,
[1] “Improve the coherence and performance of British international development policy in fragile and conflict-affected countries”
[2] “Improve the coherence of and links between our development and humanitarian responses in fragile and conflict-affected situations”

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / There are three possible options: / 1. Not to have a fund, and not to undertake any small projects. / 2. Small short-term projects funded ad hoc from administrative funds or programme funds, with each piece of work treated as a separate project. / 3. Various small short term projects (with either restriction or no restriction on the type of intervention) funded from money set aside for such a purpose, with clear selection criteria for funding.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Medium / 2 Medium / 3 Medium / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A - high potential risk/opportunity; B - medium/manageable potential risk/opportunity; C - low /no risk/opportunity; or D - core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 C B / Overall, the climate and environment impact associated with establishing the SIF are judged to be neutral. The generic overall risks and opportunities presented by SIF in terms of climate/environment aspects are detailed in Section C. Options 2 and 3 all require a summary sheet to be prepared for each individual intervention, and this would present an opportunity to consider the climate/environmental implications of the intervention. On this basis, levels of climate/environment safeguards would be similar for both options. Under Option 3 however, a designated Project Officer would be involved, which will help ensure consistency in the implementation of climate/environment screening and safeguards from design to project end. / Under all options (except the ‘counterfactual’ Option 1) there is the opportunity to fund strategic climate/environment related analysis and interventions that could help achieve and sustain broader Palestinian Programme aims. This is particularly pertinent to research/analysis and interventions relating to climate change as a cross-cutting issue: as this is a significant, emerging and evolving threat that the Palestinian Programme as a whole will have to grapple with in order to achieve and sustain programme impact. SIF funding of climate/environment interventions could also help encourage other donors/partners to invest or expand activities in this area. / .
C. What are the costs and benefits of each feasible option? / Since Option 1 is the counterfactual, the costs, benefits, risks and opportunities of Options 2 and 3 will be assessed in comparison with Option 1. / 1. Costs / The costs of Options 2 and 3 are as follows: / Project cost: £1m on small projects. For Option 2 this could come from administration or programme funds, although it is expected that the majority would come from programme funds given that the administration budget is limited and benefits would not just be to DFID. For Option 3 it will all come from programme funds. / Staff time: Option 3 will require 10% of a project officer in London to manage the fund, plus advisory time to design and implement the interventions. This is considered to be significantly less than Option 2, which for the same number of projects would require much greater project officer and advisory time on design given the need to write separate Businesses Cases for each project. / Partner costs: it is possible that other partners would need to contribute, but it is impossible to estimate the value of this. The partner costs would be the same under both Options 2 and 3. / The overall cost of Option 3 would therefore be lower than Option 2 for the same number of small projects. / 2. Benefits / Compared to the counterfactual, both Option 2 and 3 have similar benefits derived from allowing a large number of small projects. These common benefits will be outlined below, where the quantification is based on Option 3. There is then a discussion of to what extent the size of these benefits will differ between the two. / Summary of benefits table / Stage 1 / Description of who benefits, and how and when they benefit Stage 2 / Quantification Stage 3 / Monetary value / a) Portfolio quality: DFID OPTs benefits from its large projects being better designed and implemented. Contribute to increase in portfolio quality score from 74% to 80%. To be determined in project evaluation. / b) Influencing and coordination: DFID strengthens its influence across the donor and wider community By 2014 there will have been at least 3 specific influencing activities which bring together different actors. To be determined in project evaluation. / c) Strengthened project design and delivery: partners benefit from improved evidence base resulting from analysis and pilots identifying innovative approaches to project delivery By 2014, 6 studies will have changed DFID, donor or Palestinian Authority programmes in a recognisable way, and at least 3 pilots will have been scaled up To be determined in project evaluation. / a) Portfolio quality / If operated effectively, small projects can be complementary to the wider business plan strategy, providing a flexible resource to underpin the effectiveness of larger projects and enable them to remain responsive to changes on the ground. In particular, the large projects in the DFID Palestinian Programme will benefit in the following ways: / Better designed: the studies will provide a better understanding of the context and need for intervention, while pilot studies can enable different approaches to be tested prior to full-scale implementation. / Better implemented: studies during implementation can enable the project design to be adjusted to ensure that it remains relevant despite changes in the environment. Studies and coordination activities can also be used to influence stakeholders that are important to the project’s success. / The best quantitative indicator of this benefit would be the change in portfolio quality score of the DFID OPT programme compared to what would have happened without the SIF (tracked at the Impact level). The portfolio quality score is based on the extent to which DFID projects are achieving their objectives, and so is able to capture the extent to which projects are realistically designed and effectively implemented. It therefore does not measure the extent to which project objectives are the most relevant. Assessing to what extent an improvement in the score can be attributed to the SIF will require interviews with project teams to understand the impact of each SIF project alongside other factors. This is planned as part of the project evaluation. Given that the office has a wider objective to improve its portfolio quality score, we can at this stage only state that the project will contribute towards this improvement. / The monetary value of the benefit can only be calculated afterwards once the impact on individual project scores has been determined. For those projects which have a Net Present Value (NPV) estimate, a percentage increase in the NPV can be made depending upon the impact on the project score and on any other evidence of the project’s impact. This is also planned as part of the project evaluation. / b) Influencing and coordination / A recent DFID internal document states: “Influencing interventions…are key to DFID’s success as a world leader in development. They allow DFID to leverage change that would not be possible under a traditional costed development intervention alone and act as aid multipliers when used in conjunction with other resourced interventions”.[3] The quantitative indicators of this benefit at the Outcome level are that by 2014, 3 influencing activities will have taken place which enable DFID to strengthen its influence across the donor and wider community. Given the diverse aspects to coordination this is probably the best indicator available. / By bringing together key development activities these will be designed to improve harmonisation and coordination of the development activity, resulting in additional benefits including: / Reduced duplication of effort: resulting in cost savings. / Reduced transaction costs: for instance, as the PA is able to deal with a group of donors at once rather than individually. / The monetary value of reduced duplication of effort and reduced transaction costs is very difficult to measure and should probably not be investigated as part of the project evaluation / c) Strengthened project design and delivery / The same DFID internal document recognises that the provision of evidence and analysis is an important form through which DFID can influence national policy in both formal and informal settings to deliver improvements in delivery. The SIF will support the strengthening of programmes of the Palestinian Authority, international community and Palestinian civil society through providing evidence and analysis from all three outputs: analytical studies; pilots; and coordination activities (discussed above) which can be used to disseminate and discuss evidence and pilots. / The quantitative indicator of this benefit is that at the Outcome level by 2014, 6 studies will have changed DFID, donor or Palestinian Authority programmes in a recognisable way, and at least 3 pilots will have been scaled up. The monetary value of this benefit depends upon the exact impact that the studies have on programmes, and the return of the new scaled-up projects. DFID has commissioned a literature review on the rate of return to research, which finds that the information requirements are very high.[4] In order to monetise the benefits of research three questions need to be addressed: did the research influence decisions (the Attribution Problem); did the change lead to the observed outcome (the Identification Problem); and can the benefits of the outcome be quantified (the Measurement Problem). However, despite the difficulties, it is of wider value to DFID to try to assess the value of the benefits from the SIF in order to inform DFID’s wider policy on the value of such funds in country offices. The project evaluation will therefore look at a sample of these to estimate a range of potential values. / Comparison of benefits between Options 2 and 3 / The benefits will be higher for Option 3 for the following reasons: / Flexibility: Option 3 would allow interventions to be undertaken at short notice given the streamlined design and approval process compared to a Business Case, and because funding forecasts would only need to be made for the fund as a whole and so it would be easier to be flexible while spending annual allocations. Such flexibility would allow the small projects to respond strategically to in-year challenges and opportunities, thereby increasing the benefits compared to Option 2 in terms of portfolio quality, influencing, innovation and coordination. / Coherence: For Option 2 it may be difficult to have complementary projects, as availability of funds and staffing resources could vary over the life of the project. A fund would allow for continuity from year to year, with a designated Project Officer overseeing the approval process and implementation of the interventions. / In addition, the lower transaction costs of Option 3 compared to Option 2 is likely to mean that there would be many more small projects under Option 3. / 3. Risks / The key risks to Options 2 and 3 are: / Substitution of financing: SIF 4 funding simply substitutes for alternative sources of external financing for projects, meaning that DFID bears the costs for benefits that would have been realised without DFID intervention. Details of how this risk will be minimised through rigorous scrutiny of the need for DFID funding and availability of funding from other sources is set out in the management case. Having a dedicated project officer as in Option 3 will enable greater consistency of scrutiny across all projects. / Lack of strategic fit: SIF 4 becomes a convenient fund for small stand-alone projects of limited strategic value. That could also put the programme’s tight focus in the context of limited human resources at risk. Tight management has avoided this in previous iterations of SIF (1, 2 and 3) and this will be reinforced by the Programme Steering Group’s vetting role for SIF 4 (the PSG is the main forum for verifying that the Palestinian Programme team is fulfilling its programme management obligations in order to deliver its Operational Plan). This risk will be lower for Option 3, as a designated project officer will be able to maintain close oversight on strategic fit across all projects. / Innovative project design results in failure to deliver outcomes: Innovative pilot projects are by nature high risk as they will adopt new and potentially untested approaches to project delivery. However, the reward to risk ratio is high, as the small size of the pilots means the financial costs of failure are low, while the potential rewards are high if the pilots are successful. Risks can be mitigated through rigorous scrutiny of project proposals through the summary form and by the project steering group, and careful monitoring of the pilot throughout the life of each project. / Environmental and climate change. The rapid design and implementation of potential SIF funded projects presents a risk that climate/environment screening could be overlooked or inadequate within the time available. It will be important to ensure that within overall SIF management arrangements that adequate resources (financial and human) are built in to undertake rapid climate/environmental screening and monitoring of interventions. As far as is possible, priority will be given to recruiting nationals or consultants based in the region/country so that air travel and associated carbon emissions can be minimised. / Key risks identified in the management of the project are detailed in section B of the Management case / Opportunities / Value for money: As set out in detail in the strategic case and benefit analysis above, SIF 4 provides an opportunity to improve value for money by: developing innovative approaches to maximise project outcomes relative to costs; providing evidence to ensure our projects remain appropriate and effective in a changing environment; leveraging input from others to deliver greater impact and reducing duplication. One of the focus for SIF interventions will be identifying effeciencies, for example through alternative delivery models for United Nations Relief and Work Agency services in Palestinian refugee camps. Lower transaction costs under Option 3 (by reducing the need for separate project management, implementation and monitoring arrangements) means this option is likely to deliver greater value for money. / Relationship building: By increasing the scope for engagement, joint working and coordination with partners, SIF 4 will enable us to strengthen our relationships with key partners, including the Palestinian Authority, NGOs and other donors, building trust and contacts to lay the foundation for greater joint working in future. It will also enable us to build relationships and test the capabilities of new partners, whom we would not otherwise have the opportunity to work with, expanding our reach within the OPTs both in influencing and when developing and delivering future projects. / Responding to conflict and working in fragile states: The analytical studies and pilot projects conducted through the SIF will enable us to develop greater knowledge and understanding of effective working in a conflict environment – one of the key priorities identified in the DFID vision. Being able to conduct innovative pilot studies will provide a safe context in which to take risks and test the boundaries of what works when dealing with conflict situations. Dissemination of evidence and findings from studies will support broader understanding of the factors driving conflict and how we can measure progress in an uncertain and fragile environment / Use of SIF funds to undertake climate/environment related intervention: Given the fragile and degraded nature of the Palestinian environment and the significant and emerging threat of climate change exacerbating this situation, SIF funds could be used to undertake strategic research or pilot projects regarding potential impacts of climate change and environmental degradation on broader programme aims. The SIF funding modality therefore provides the possibility of undertaking such crucial climate analysis and activity in a timely and effective manner in order to achieve and sustain programme impact and encourage other partners to invest/expand work in this area. This is particularly relevant for climate change where new data/information, technologies and potential impacts are emerging constantly, and there is a need to analyse and respond in a fairly rapid manner. This opportunity will help the broader Palestinian programme to comply with the DFID commitment to make all development ‘climate and environment SMART’; / 5. Comparison of costs and benefits / Option 3 would seem to be preferable to Option 2 in that not only does it have lower costs, but also is very likely to have higher benefits. / It has not been possible to monetise the benefits of Option 3 and so it is not possible to compare the benefits and costs in a quantitative way. If Option 3 is able to achieve the targets in the logframe there is a good chance that the benefits will outweigh the costs, but there is insufficient evidence to say this with certainty.
D. What measures can be used to assess Value for Money for the intervention? / Since the design of the interventions is not yet known, it is impossible to specify unit cost measures in advance. However, the selection criteria will include the need for each intervention to have at least one unit cost to measure economy and one unit cost to measure efficiency. How the design maximises cost effectiveness will also have to be justified. / The evaluation of the project will include a calculation of the Internal Rate of Return.
E. Summary Value for Money Statement for the preferred option / Option 3 would seem to be preferable to Option 2 in that not only does it have lower costs, but also is very likely to have higher benefits. / It has not been possible to monetise the benefits of Option 3 and so it is not possible to compare the benefits and costs in a quantitative way. If Option 3 is able to achieve the targets in the logframe there is a good chance that the benefits will outweigh the costs, but there is insufficient evidence to say this with certainty.
[3] DPC Policy Discussion Paper: Evaluating Influencing Strategies and Interventions.
[4] Sen, K. (2010) Literature Review on Rates of Return to Research. Report written for DFID.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The fund will support a variety of interventions over four years to support the Palestinian programme to effectively meet its goals. Procurement mechanisms will be used as appropriate to the type of supplier: / Multilateral organisation (eg UN agencies) – Memorandum of Understanding or Administration Agreement (where DFID has agreed one with the organisation) / Non-governmental organisation (eg Oxfam) – Accountable Grant / Not-for-profit organisation (eg universities, think tanks) – Contract / Consultancies - Contract / If a consultancy is needed, the work will be commissioned in line with standard procurement procedures in an appropriate and proportionate way based upon the estimated value of the project, and expenditure budgets will be drawn up that reflect value for money.
B. How does the intervention design use competition to drive commercial advantage for DFID? / It is expected that any work commissioned will not be of such a value and on a time scale that will allow DFID to significantly drive a commercial advantage, but all appropriate actions will be taken to ensure value for money and transparency. Robust terms of reference will be drawn up that sets out our clear expectations of the supplier and agreed expenditure budgets drawn up that adhere to DFID policies and standards in terms of costs such as flights, subsistence etc. For longer interventions (up to four months) breakpoints can be built into the project to look at progress and to see whether further funding is appropriate. / For interventions over £25,000, but under the Official Journal of the European Union (OJEU) limit , which is currently £101,323, the Departmental Procurement Officer (DPO) will set up a limited form of competition which is transparent, using proportionate effort to ensure value for money. If the contract is over the OJEU limit the DPO will follow DFID guidance on the procurement of goods and services using the appropriate OJEU procedure, and allowing sufficient time for the process. We will also look at recruiting suppliers through framework agreements that DFID has to reduce cost of the recruitment process and the time needed to carry it out. / Where appropriate DFID will look at working closely or sharing work with a partner organisation to improve value for money. DFID has good working relationships in-country with a range of multilateral and non-governmental organisations, as well as other donors and private sector companies which it can draw on help drive competitive advantage
C. How do we expect the market place will respond to this opportunity? / In general, it is expected that there will not be a large number of bidders for each project, due to the short length and low value of the projects and the level of specialised knowledge needed. However, where interventions are put to tender there will be a robust transparent competition. Where appropriate for the nature of the intervention, we will invite in-country organisations to join the bidding process – this would have the added advantage of local knowledge, greater value for money and adding to the local economy.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The main cost drivers are labour costs and availability. Consultants or organisations will need to have comprehensive knowledge of Palestinian issues, experience of working in the region and where necessary, the appropriate contacts to be able to carry out the work. This means that there will be only a few people or organisations which would be suitable, and availability to do the work when required could reduce the number of suppliers. The OPTs are considered a fragile state with an unstable political situation and this has an impact on security and the ability to move around, particularly access to Gaza. Not all suppliers are happy working in this environment, so again, reducing the pool of possible suppliers. / These issues can be mitigated to some extent by drawing up robust but not restrictive terms of reference, and inviting a large a pool as possible of potential bidders to bid (by drawing on personal contacts, DFID framework agreements and relevant suppliers).Supplier costs can be reduced by using daily rates as laid out in framework agreements
E. What is the intended Procurement Process to support contract award? / This is dependent upon the value of the contract, but the appropriate DFID guidance will be followed to ensure a clear competitive process. For projects above the OJEU limit (currently £101,023) the tendering process will be open and the appropriate OJEU procedure used – this will probably be for the larger longer interventions lasting several months. Most interventions will be short and low cost, and a supplier will be selected through a less bureaucratic competition appropriate to the cost of the intervention. For example, for a short intervention costing less than £25,000 and a short lead time of one month – the process may be asking consultants with the appropriate expertise and availability to tender. At all times the need to get something done quickly will be balanced with the need for an effective project which delivers efficiently and meets DFID standards. / As the intervention will normally be small and with a limited number of outputs (e.g. a report) the terms of reference laying out DFID’s requirements can be kept fairly simple and straight forward. Separate terms of reference will be drawn up for each intervention which will also include a need for the partner to report on the impact and sustainability of the intervention at an appropriate time after the end of the intervention.
F. How will contract & supplier performance be managed through the life of the intervention? / The designated Project Officer will keep in close contact with the supplier to ensure all is going well with regular catch-up meetings and breakpoint reviews (where built into the intervention design). The outputs will be assessed as appropriate before the intervention is closed and payment made. The the outputs should include a final financial report on expenditure signed off by an authorised person in the supplier’s organisation, and a report on the impact of the intervention.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / As there will be a range of potential interventions with a number of service providers, the appropriate mechanism for the partner will be used. These include Accountable Grants with non-governmental organisations; MOUs or administration agreements (if appropriate) with multilateral organisations; and contracts with consultants or academic institutions. In all cases the relevant DFID guidance and standard procedures for each mechanism will be followed. / In working with multilateral or non-governmental organisations there is less opportunity for competition, but each intervention must meet the selection criteria for funding and be approved by the Programme Steering Group (PSG)
B. Value for money through procurement / The intervention will have met selection criteria and be approved by the Programme Steering Group. One of the criteria will be value for money i.e. will the project effectively deliver the expected output within the resources provided. Value for money will also form part of the terms of reference for the intervention which will be used to select the most appropriate service provider. / For interventions over £25,000 the appropriate procurement procedures will be undertaken including drawing up robust terms of reference, allowing time for an appropriate and transparent tendering process, or if over £101,323 then using the appropriate OJEU procedure, and agreeing a cost-effective budget. Our relationship with our partners will be open and based upon clear deliverables to enable DFID to both achieve the best value for money and maintain a strong working partnership. Where appropriate DFID will look at working closely or sharing work with a partner organisation to improve value for money.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / £1 million has been allocated to this project which is expected to last for 4 years (until the end of the expected term of the current administration and in line with the Palestinian programme Operational Plan). This will provide enough time to be able to plan ahead as necessary (for example to be able to undertake an annual review on a certain issue for several years) and for the fund to have a real impact on the Palestinian programme. £1 million will provide sufficient funding to support a range of interventions in each year of different values and length, reduce the concern that there will not be funding available for an intervention and ensure funding will be available throughout the life of the project. / The Palestinian programme is focussed on three areas (known as pillars): building the institutions needed for a viable Palestinian state; private sector growth; and protecting the vulnerable. For 2011/12 there have been bids of £140,000 for projects to the end of the current financial year, so the profile at present is / 2011/12 - £140,000 / 2012/13 - £286,000 / 2013/14 - £287,000 / 2014/15 - £287,000 / Each financial year the programme pillars will be expected to put in bids for the projects they would like to be funded for that year. This means ongoing, close control will be needed to ensure forecasting is up to date and that the budget profile on ARIES is correct especially for projects approved at short notice. / There will not be a fixed amount for each year which cannot be exceeded, but there will be a target for each year to ensure that the funding is spent across the term of the project and that there is not a rush at the end to find interventions – this may need to be revisited in view of the call on funds. The ideal situation in financial terms would be to have steady flow of interventions across each year of the project, as this would enable staff resources and spending to spread evenly across the life of the project. This will probably not be the case as the implementation of interventions will be dependent upon changes in the political and/or humanitarian situation in the OPTs. If it appears that there is no demand for the project funds (perhaps due to a long term stabilisation in the peace process), the project could be closed early. / Up to £20,000 of funding will be held in the final year to support an evaluation study of SIF 4 – further details are provided in Section D of the Management case.
B. How will it be funded: capital/programme/admin? / The project will be funded from programme costs, as this is the most appropriate source of funding. Programme funding allows for a wider variety of projects and a range of funding mechanisms.
C. How will funds be paid out? / This will depend upon the mechanism used for the intervention. In line with DFID guidance this will be in arrears (if possible), with the possibility of 10-30% of the final funds withheld until the strategic impact of the intervention has been assessed in a follow-up report. For some interventions the receipt and acceptance of a report will be the trigger for payment.
D. What is the assessment of financial risk and fraud? / As the project is a series of relatively low value, short interventions each of which will be closely managed, the financial risk of the overall project is low, as is the risk of fraud. In line with DFID guidance payments will be made in arrears once the outputs have been delivered. Partners, such as non-governmental agencies, consultancies or multilaterals, will be chosen carefully with good financial accountability a key requirement. Terms of reference will be robust to ensure that the partner is aware of how much work and to what standard will be needed to be done to ensure the outputs are delivered.
E. How will expenditure be monitored, reported, and accounted for? / Partners are required to provide financial reporting as one of the outputs of the intervention. For consultants, academic institutions etc the budget (fees, travel costs, subsistence and incidental expenses) will be discussed and agreed before signing the contract. Receipts will be needed with the final invoice to cross check expenditure is as agreed in the contract. / For the project overall there will be a spreadsheet to monitor spend on the project overall allowing accurate forecasting on ARIES, and providing up-to-date figures. This spreadsheet will be cross-referenced with ARIES to ensure payments have gone through and accruals and pre-payments recorded as appropriate.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The SIF will have a structured approach to which interventions are funded by applying the same set of selection criteria to each (including value for money). Although the projects will be short in duration and low cost, they would only receive clearance if the case put to the Programme Steering Group (PSG) clearly demonstrates that they will have a high impact. / Management of the fund will be carried out by DFID Palestinian Programme staff. External management by, for example, a consultancy would not provide value for money or the flexibility required to ensure the project meets its objectives. DFID staff are better placed to decide whether or not an intervention is necessary and would add value to the Palestinian programme. Due to the context in which the Palestinian programme operates there may be a greater need for interventions at one point of the project’s lifespan than at another. There is likely to be range of partners who would be managed through different mechanisms; for example an intervention with an NGO would be through an Accountable Grant and one with an UN agency would be through a Memorandum of Understanding. / The project will be managed by the London based B2 Project Officer, and overseen by the London based B1(D), with support from London- and Jerusalem-based advisers and other staff in Jerusalem as necessary. / Interventions can be proposed by any member of the Palestinian team, or by partners in Whitehall or in-country. The first step will be for the designated Project Officer to complete a summary form outlining the proposed intervention and showing how the project meets the selection criteria (at annex A). If SIF Project Officer is content the project meets the selection criteria (to be drawn up by the PSG), they will present this to the PSG for approval. The PSG will ensure the intervention fits with the current political or humanitarian situation and programme need, is value for money, and there are minimal risks for non-completion. The PSG will also ensure that there are the appropriate staff resources available for the intervention to be implemented and will keep oversight of the number of interventions in operation at any one time - a number of small interventions could take up substantial resources if they are not carefully managed. / The intervention will be signed off by the Deputy Head of DFID Jerusalem as Chair of the PSG and who has the level of delegated authority to do so (up to £1.5 million for a new project funded from programme funds). If the intervention was designed by DFID, there will then need to be a commissioning process (appropriate to the value of the project) to find an implementing partner. In line with advice from FCPD each intervention will have its own logframe which will be based upon the common impact and outcome identified in the overarching business case logframe, and will be used in the monitoring and evaluation of the project. / The designated Project Officer for the intervention will provide oversight and liaison with the partner organisation as appropriate to meet DFID standards during the course of the project. Although the interventions may be short and of a lower value than the projects DFID usually funds, adherence to correct DFID procedures is vital to ensure transparency and value for money. / As the OPTs are considered a fragile state and the situation on the ground can change rapidly, this could mean that a project may need to be suspended or ended early (with an agreed exit strategy). This decision will be taken by the PSG.
B. What are the risks and how these will be managed? / As the SIF 4 fund projects will operate across the scope of the Palestinian programme, risks identified in the country-level risk register will be relevant. The risk register is monitored and reviewed quarterly by the Programme Steering Group, with mitigation actions in place to be activated when appropriate. / Using a Strategic Impact Fund could help reduce the risk for the whole Palestinian Programme, for example, through ‘testing the water’ for a large proposed project, investigating the extent of need and looking at how the UK can best provide support, and piloting innovative ways of working. / A risk assessment will be done for each intervention based on the OPTs risk matrix as part of the selection criteria, which the Programme Steering Group will take into account when they decide to approve an intervention or not. Risks looked at will include whether the organisation has the expertise to carry out the project, that the project length and value are appropriate to produce the expected outcome, and that the operating environment is favourable for work to be done (for example it is safe for consultants to go to Gaza if that is what is required). / Although there is the possibility that the immediacy for an intervention to be done may outweigh other considerations, the need to meet selection criteria and go through an approval process will mitigate this.
C. What conditions apply (for financial aid only)? / Each intervention will need to meet the rigorous selection criteria and be approved by the Programme Steering Group, but no conditionality will be put on individual interventions once underway. It is expected that due to the short nature of the interventions this will not be necessary unless in exceptional circumstances where the political situation is changing rapidly or there is the possibility of conflict, and the conditionality is for reasons of security or safety.
D. How will progress and results be monitored, measured and evaluated? / Monitoring / Projects are expected not to last more than four months, and the financial reporting and other documentation will be proportionate to the size of the intervention and in line with DFID standards. / Proposals will be submitted in a standardised Project Proposal Form (at Annex A) along with an logframe based on the overarching business case logframe impact and outcome and information from the Project Proposal Form. This includes a section on monitoring, in which the implementing partner will outline the following: / One strategic impact of the project – this is defined as “the longer term effect or anticipated policy shift or other change the project is expected to contribute towards. This will assessed no later than six months after the main work has been completed. 10% to 30% of the funding will be withheld until the strategic impact has been assessed and a report delivered. / Main outputs – this is defined as “the products and/or services delivered” through the intervention. / The implementing partner will produce a follow up note no later than six months after the project is completed (or sooner as appropriate) outlining whether or not the project has a strategic impact, as defined by the indicators. They will use the following scale to assess the impact: / Description Scale / Substantially exceeded expectation 1 / Moderately exceeded expectation 2 / Met expectation 3 / Moderately did not meet expectation 4 / Substantially did not meet expectation 5 / The assessments will be made no later than six months after the completion of work as the monetary value of the benefits from an intervention can only be calculated after the intervention has ended, and only after a period of time will it be possible to see the benefits of the whole project (eg a pilot study has led to a larger project being undertaken, an influencing activity has led to real changes on the ground). / Implementing partners’ report will also include qualitative case study material to explain the score they have given. The SIF Programme Officer will quality assure the scoring to ensure the assessment is an accurate reflection of progress made, and to ensure moderation of the scores. / The overall logframe will include an aggregate of these scores using the DFID portfolio quality assessment scoring methodology. This score will be used in the logframe at the Outcome level. The overall Portfolio Quality Score for the whole OPTs programme will be the indicator used at the Impact level. The milestones and targets in the logframe will be reviewed annually to ensure they are being met, and an Annual Review completed. / Evaluation / The individual projects will not be evaluated however there will be a light desk study evaluation of the overall SIF at the end of the four years, including an assessment of the value of the benefits from the SIF in order to inform DFID’s wider policy on the value of such funds in country offices. This will be used to complete the Project Completion Report at the end of the project in March 2014. Some of the budget will be held back for this study in case it is not possible to do this in-house (no more than £20,000). This study will use the evaluation questions set out in the framework below: / Strategic Evaluation Questions / Relevance / Was the selection of the project to be implemented based on consultation? / How were beneficiaries involved in the design of the projects? / Effectiveness / Did the projects achieve their objectives, in terms of strengthening the evidence base, strengthening influencing across donors and the wider community or through successful innovative pilots? / Efficiency / Were the projects achieved on time and were cost-efficient? / Impact / What has happened as a result of the projects, have they been scaled up or taken forward? / What real difference have the activities made to beneficiaries? / Sustainability / What steps have been taken to ensure that benefits of the projects have continued after the project has ended? / What were the major factors which influenced the sustainability? / How have coordination mechanisms been strengthened as a result of the work? / Coverage / How were projects selected? / What are the reasons why some projects were turned down? / Coherence – strategic level policies / Were the projects consistent with the broader policies in the country eg. developmental and trade policies? / To what extent did other policies and programmes affect the delivery of the SIF? / Co-ordination – operational level / How well have the implementing partners worked together with other partners in the country?
Logframe / Quest number of logframe for this business case: 3216497

Annex A – Intervention Summary Form

Intervention Information
Intervention title
Name of Implementer
Which main area does this address? Only tick one	Statebuilding		Wealth Creation			Poverty & vulnerability
Time Frame
Total estimated budget		Amount requested from DFID

Proposal
Explain briefly the context and the need for this intervention
Methodology
How will you conduct the work including details of the methodology?

Monitoring and Evaluation
What is the potential strategic impact of the project?
This is the longer term effect or anticipated policy shift or other change the project is expected to contribute towards. This will be assessed 6-12 months after the main work has been completed.

What are the main outputs of the project? This is the products and/or services delivered

Please set out how you will monitor and evaluate the project?

Risk
What are the risks associated with this project and how will you manage these?
Description of Risk	Likelihood / (H/M/L)	Impact / (H/M/L)	How are you managing these risks?

Detailed Budget
Please provide full details of the budget

Value for Money
How does the project design maximise cost effectiveness?

Unit cost to measure economy		Unit cost to measure efficient

Logframe

Please insert completed logframe showing how the intervention will contribute towards the overall impact and outcome set out in the SIF 4 overarching logframe.

Assessment
After the work is completed you will be expected to produce a follow up note assessing whether or not the project has had a strategic impact – this will be based on the impact report produced by the implementer (one of their outputs as per the terms of reference) an appropriate time after work has been completed. The assessment should be based on the information you have already identified in section 4.
As well as a quantitative assessment based on the scale below you also need to provide qualitative case study material to explain the score you have given.
Description	Scale
Substantially exceeded expectation	1
Moderately exceeded expectation	2
Met expectation	3
Moderately did not meet expectation	4
Substantially did not meet expectation	5

.