## SCALING UP ACCESS TO
## CONTRACEPTIVE COMMODITIES IN NIGERIA

DFID NIGERIA
HUMAN DEVELOPMENT TEAM
16 July 2011

## SCALING UP ACCESS TO
## CONTRACEPTIVE COMMODITIES IN NIGERIA

Contents	Page

Acronyms	3
Clarification of terms	4
Intervention Summary	5
1. Strategic Case	8
2. Appraisal Case	22
3. Commercial case	33
4. Financial Case	38
5. Management Case	39
6. Log frame	43
7. Annex 1: Population Growth Projections 2010 - 2100	46
8. References	47

Acronyms
CIDA	Canadian International Development Agency
CPR:	Contraceptive Prevalence Rate
CLMS:	Central Logistic Management System
CYP:	Couple Years of Protection
DALYs:	Disability Adjusted Life Years
DFID:	The UK Government’s Department for International Development
FACE:	Fund Authorisation and Certificate of Expenditure
FP:	Family Planning
FMOH:	Federal Ministry of Health
HERFON:	Health Reform Foundation of Nigeria
LGAs:	Local Government Areas
LMIS:	Logistic Management Information System
LTA:	Long-term Arrangements
MDAs:	Ministries, Departments and Agencies
NDHS:	National Demographic Health Survey
NPHCDA:	National Primary Health Care Development Agency
NPopC:	National Population Census
NSHDP:	National Strategic Health Development Plan
PATHS2	Partnership for Transforming Health Systems 2 (DFID)
PRRINN	Partnership for Reviving Routine Immunisation in Northern Nigeria (DFID)
PHC:	Primary Health Care
PSB:	Procurement Service Branch
QALYs:	Quality Adjusted Life Years
RH:	Reproductive Health
RHP:	Reproductive Health Policy
RHCS:	Reproductive Health Commodity Security
RHCST:	Reproductive Health Commodity Security Assessment Tool
STI:	Sexually Transmitted Infection
TBA	Traditional Birth Attendants
TFR:	Total Fertility Rates
UNFPA	United Nations Population Fund
USAID	United States Agency for International Development
VVF:	Vesico Vaginal Fistula
VFM	Value for Money
Clarification of terms

Couple Years Protection (CYP) is the volume (quantity) of contraceptives provided expressed in CYPs. CYP is an estimate of the number of years (or fractions of a year) of protection provided by each unit of contraception. It can be used to report across different methods of contraception. Each unit of FP service delivery is multiplied by that method’s conversion factor to calculate the expected duration of contraception provided. E.g. 500 freely provided male condoms = 1 CYP; 100 sold male condoms = 1 CYP; an IUD insertion = 5.5 CYPs; a 5-yr implant = 3.5 CYPs; tubal ligation (sterilisation) = 12.5 CYPs, etc.

Disability-adjusted life year (DALY) extends the concept of potential years of life lost due to premature death to include equivalent years of “healthy” life lost by virtue of being in states of poor health or disability (3). One DALY can be thought of as one lost year of “healthy” life, and the burden of disease can be thought of as a measurement of the gap between current health status and an ideal situation where everyone lives into old age, free of disease and disability.
### Social marketing. Social marketing is the use of commercial marketing techniques to achieve a social objective. Social marketers combine product, price, place, and promotion to maximize product use by specific population groups. In the health arena, social marketing programs in the developing world traditionally have focused on increasing the availability and use of health products, such as contraceptives or insecticide-treated nets. Different models of social marketing have been used in developing countries with varying levels of donor funding. While some of the models rely heavily on donor support, others include built-in exit strategies that depend on the commercial sector to ensure sustained product supply.

Reproductive Health Commodity Security. Contraceptive security exists when people are able to choose, obtain and use the contraceptive supplies they want. Achieving that requires a full supply of contraceptives at the end user level of the supply chain (service delivery points and communities).
### Total market approach (TMA) A total market approach brings together all parties interested in providing reproductive health/family planning and other health services. TMA emphasizes equity and growth of the whole reproductive health/family planning market by ensuring delivery of high-quality products and services in a range of prices aimed at specific populations, determined through market segmentation. In addition to stimulating supply, TMA focuses on generating demand among underserved population groups through various social marketing and communication approaches.

Method Mix. Women’s preferences for spacing versus limiting their total number of births influences their choices of contraceptive methods. Those wanting to stop childbearing are likely to use one of the most effective methods while those wishing to postpone a birth choose among short-acting reversible methods.[1] It is well documented that a family planning programme must offer the full range of methods to all women[2].
[1] Ibid
[2] Contraceptive Method Mix (1994) Geneva: World Health Organisation.

Intervention Summary
What support will the UK provide?
UK Aid will provide £18 million (£3 million a year for 6 years) / Period of funding : 6 years (2011-2017)

Why is UK support required?
What need is the intervention trying to address? / Investment in modern family planning is one the most cost-effective ways of improving maternal and new-born health and provides economic benefits to women and households.[3] [4] / This initiative will purchase and distribute a range of contraceptives, providing the equivalent of 1 million Nigerian couples with modern family planning each year for 6 years. United Nations Population Fund (UNFPA), the leading UN agency supporting reproductive health in Nigeria, will be responsible for ensuring access to reproductive health commodities to public health facilities. / Nigeria currently has a modern contraceptive prevalence rate (CPR) of only 10%. This is well below the Sub-Saharan Africa average (18%)5. Family planning commodities in Nigeria’s public health sector are unavailable or unreliable. Regular stock outs are commonplace. Nigeria’s latest Demographic and Health Survey (2008) showed that almost six out of ten married women who want to use contraceptives do not have access to them[5]. / Ensuring women and girls have the ability to choose whether, when and how many children they have is a priority for the UK Government. The Secretary of State for International Development, Andrew Mitchell said: “DFID will now have an unprecedented focus on family planning, which will be hard-wired into all our country programmes.”[6] DFID’s Global target is to provide 10 million couples with family planning services by 2015. / There is strong evidence that family planning contributes to reducing maternal mortality by delaying the first pregnancy and reducing the number of births. Thus reducing the number of times a woman is exposed to the risk of mortality[7]. Family planning also increases birth intervals. This has been shown to have a positive effect maternal and child health outcomes, as well as the wider family and household[8] [9]. / It is estimated that more than 30,000 Nigerian women die in child birth – representing more than 10% of all maternal deaths worldwide. Nigeria is the most populous country in Africa with a population of over 158 million[10], a growth rate of 3.2% which means that the population will double in 22 years. Total fertility rate is 5.7, with rates as high as 8.7 in the North of Nigeria (Sokoto State)[11]. / Although Nigeria has a national system to purchase and deliver contraceptives to health facilities, this system has failed to deliver timely or adequate contraceptive stocks to clinics and places where women can access. This is largely due to lack of funding for contraceptives, lack of skills of health workers and poor logistics management. As a result, most of the improvements have been made through donor partners and UNFPA. This programme will complement government and other partners in these efforts. / What will DFID do to tackle this problem? / The proposed intervention will centrally purchase family planning commodities, through UNFPA. This will provide contraceptive protection to 1 million Nigerian couples annually. This is part of a coordinated initiative with the government of Nigeria, civil society and other development partners. / These commodities will be provided free across all public health facilities. By providing commodities to public facilities and reaching rural health clinics, this will ensure contraceptives reach girls and women most in need. It is estimated that this programme has the potential to reduce maternal deaths by approximately 1255 women each year. This DFID procurement is estimated to be approximate 50% of the total current demand for contraceptives in the public sector for Nigeria in 2011[12]. The programme will work closely with government (MDG Office), the UN, USAID, civil society and others to advocate for additional resources for family planning commodities and services. The Federal Government has agreed to commit $3 million to UNFPA for contraceptive procurement in 2011 and also to remove user fees for family planning in public facilities. With UNFPA support commodities will be ordered, procured, stored and distributed to the place of need through existing Federal, State and LGA systems. This is an important step forward, as there has been minimal Nigerian government financing of contraceptives for at least the past 10 years. DFID, along with UNFPA, USAID, CIDA and other development partners, including local influential CSO’s like HERFON will continue to advocate for sustainable increases to Federal Government funding commitment to family planning commodities. / The programme is designed to complement the work of DFID’s other health programmes. PATHS2 and PRRINN-MNCH will both support logistics and supply chain; service delivery improvement, monitoring as well as working with girls, women and communities to influence the demand and uptake of use family planning commodities.
[3] Cleland J, Bernstein S, Ezeh A, Faundes A, Glasier A, Innes J. 2006. Family planning: The unfinished agenda. Lancet. 368 (9549) pp.1810-27.
[4] Singh S, Darroch J, Ashford L, Vlassoff M. Adding it up: the benefits of investing in sexual and reproductive healthcare. UNFPA: Cuttamacher Institute; 2009.
[5] NPopC, 2008 NDHS
[6] DFID 2010, Andrew Mitchell: Speech at World Population Day.
[7] Stover J, Ross J. How contraceptive use has reduced maternal mortality. Maternal Child Health J.2009; 14: 687-695.
[8] James Trussell and Anne R. Pebley: The Potential Impact of Changes in Fertility on Infant, Child and Maternal Mortality. Studies in Family Planning Vol. 15, No. 6 (Nov. - Dec., 1984), pp. 267-280
[9] John Stover and John Ross. How Increased Contraceptive Use has Reduced Maternal Mortality; Maternal and Child Health Journal Volume 14, Number 5, 687-695, DOI: 10.1007/s10995-009-0505-y
[10] NPopC, 2006 National Population Census
[11] National Planning Commission. Nigeria Demographic and Health Survey (NDHS) 2008. Abuja: National Planning Commission.
[12] JSI forecasting

What are the expected results?
As a result of this support, 1 million couple years of contraceptive protection will be made available in the public health system across Nigeria each year for 6 years. DFID’s Global target is to enable at least 10 million more women to use modern methods of family planning by 2015, contributing to a wider global goal of 100 million new users. Nigeria will therefore be a major contributor to this target. An important indicator that the project will monitor will be the availability of a mixed choice of contraceptive commodities, and the prevention of stock-outs seen in previous years. / DFID, through UNFPA will contribute to Nigeria’s National Goal of increasing contraceptive prevalence rate from 10% to 30% by 2015. The goal of Nigeria’s Reproductive Health Policy 2010 is to see a 2% annual increase in CPR. / Using internationally recognised tools to convert the Couple Years Protection into the likely impact, this intervention in Nigeria is estimated to avert more than 7,500 maternal deaths by the completion of the 6 year programme in 2017. / How will we determine whether the expected results have been achieved? / Nigeria’s contraceptive logistics system run by the FMOH produces quarterly reports related to distribution of contraceptive commodities. Contraceptive prevalence will be measured through Demographic and Health Surveys conducted every 5 years, and Multi-Indicator Cluster surveys undertaken once in the intervening years. DFID will undertake annual reviews against log frame indicators.
	Strategic Case / A. Context and need for DFID intervention / Scaling up access to contraceptive commodities for women is a Nigerian government priority and a DFID priority. Nigeria’s National Strategic Health Development Plan[13] places a high priority on family planning. The National Reproductive Health Policy 2010 goal is a 2% increase in CPR annually. The DFID Business Plan of June 2011 states; “….we will double our impact in terms of the number of maternal and newborn lives saved, and enable 10 million couples to access modern methods of family planning over the next five years”[14]. This programme makes a significant contribution towards this global effort. / High Unmet Need / Utilisation of modern contraceptives in Nigeria is low, at only 10% and yet unmet need is high (20%); even within those regions of Nigeria where the status of women is low and social barriers to access is high. Total contraceptive prevalence rate (CPR) in Nigeria, including traditional methods is 15%[15]. / Some explanations for low CPR in Nigeria include: / Lack of service availability / Perceived social disapproval or lack of social acceptability. / Perceived health risk and side effects. / Figure 1 Total Contraceptive Prevalence Rates / There is strong anecdotal evidence and accepted perceptions within Nigeria that “religious” barriers prevent contraceptive uptake. However, other populations and states with strong religious traditions actually have substantially higher rates (Italy 60%, Egypt 60%, Iran 74%) (Figure 1). Nigeria is low (15%) by Sub-Saharan Africa standards (23%) and significantly lower than the average for all less developed countries (52% excluding China)[16]. / Fig 2. Contraceptive Prevalence Rate by State (Demographic and Health Survey 2008) / Figure 2 shows the large regional differences in CPR with some states having the lowest rates in the world (0.2% in Jigawa). Other states, such as Lagos, with a contraceptive prevalence rate of 27%, is seen as high in Nigeria, but is only just about the average for a sub-Saharan African country.
[13] Government of Nigeria. National Strategic Health Development Plan Framework. Jan 2011.
[14] Choices for Women: planned pregnancies, safe births and health newborns; The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world. DFID, 2010
[15] National Planning Commission. Nigeria Demographic and Health Survey (NDHS) 2008. Abuja: National Planning Commission.
[16] Choices for Women: planned pregnancies, safe births and health newborns; The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world. DFID, 2010

Figure 3 Contraceptive Prevalence Rate by zone / The high demand for family planning stretches across Nigeria. The chart below shows that, despite fewer numbers of family planning users in the North, demand (number with unmet need) remains proportionally as high as the South. One of the important reasons of high unmet need is the lack of commodity availability in the public services.[17] State governance programmes suggest low incentives for state government to procure contraceptive commodities, given that the formula for allocating government resources is heavily based upon population size. Political, together with cultural and religious reasons, may present barriers to government financing. / Figure 4: The Mountains of Un-met need in Nigeria (Engender Health 2010) / (MWRA – married women of reproductive age)
Maternal Mortality. / Federal Government statistics it is estimate that more than 30,000 Nigerian women die each year as a results of maternal mortality (Maternal Mortality Rate 545 per 100,000 live births) – representing more than 10% of all maternal deaths worldwide. Family planning (FP) contributes to lowering maternal mortality by reducing the number of births and, thus, the number of times a woman is exposed to the risk of mortality. It also changes the ages at which women give birth, and increases the intervals between births thereby reducing high risk pregnancies[18], [19]. Primary and secondary research shows strong evidence that family planning may reduce maternal deaths by up to 30%[20]. / Abortion in Nigeria is only legal to save a woman’s life – and yet 760,000 abortions are estimated to be performed each year with approximately 60% of those as unsafe abortion.[21] / Improving access to family planning may reduce the number of women and girls who resort to unsafe abortions for unintended pregnancy. / Unsafe abortion burden (number of unsafe abortions and rate) 760,000 (total number of abortions in 2006) / 25% of women experience serious complications Source: Reducing Unsafe Abortion, Guttmacher Institute, 2008. / Unwanted Pregnancy And Induced Abortion In Nigeria: Causes And Consequences. Bankole et al 2006 / Numbers of women treated for complications from unsafe abortion (per year) 52% 2002-3 / 142,000 women treated annually Source: Henshaw et al, 2008 / Guttmacher Institute 2008 / Family planning and inequalities / The Demographic and Health Survey of 2008 shows that higher levels of educational status, wealth, and urban locations are associated with higher use of family planning. CPR is also directly related to the availability of family planning commodities. Thus girls and women who have lower education and higher levels of poverty also have the most limited access. (Reproductive Health Commodity Security Assessment Tool 2008).
[17] Nigeria Demographic and Health Survey, 2008. Demographic and Health Surveys
[18] James Trussell and Anne R. Pebley: The Potential Impact of Changes in Fertility on Infant, Child and Maternal Mortality. Studies in Family Planning Vol. 15, No. 6 (Nov. - Dec., 1984), pp. 267-280
[19] John Stover and John Ross. How Increased Contraceptive Use has Reduced Maternal Mortality; Maternal and Child Health Journal Volume 14, Number 5, 687-695, DOI: 10.1007/s10995-009-0505-y
[20] Mulligan J. et al. Interventions to reduce unintended pregnancy, Structured Review, DFID 2010.
[21] Ipas in Nigeria, 2008. Available at: http://www.ipas.org

Figure 5: Contraceptive Prevalence Rate by Education of mother / Figure 6: Modern Contraceptive Prevalence by Wealth Quintile (Nigeria DHS 2008)

Population growth and family planning / Nigeria is the most populous country in Africa with a population of over 158 million[22], a growth rate of 3.2% which means that the population, given current trends, will double in 22 years. / Population growth is almost entirely due to differences in fertility – The number of children a woman produces has a greater impact on population growth than if she lives for 35 or 70 years. As fertility drops, the main driver behind population growth is unmet need for family planning[23]. / In Nigeria, the total fertility rate is 5.7 – A figure which hides huge regional and rural/urban differences. Teenage pregnancy is high in Nigeria. Nearly one quarter (23%) of young women age 15-19 have given birth or are currently pregnant. Of the total population of Nigeria, 42% are below the age of 15. Additionally, reducing adolescent fertility is particularly important for maternal and child health, but also it reduces population growth, regardless of whether overall fertility is reduced. / Political and traditional leaders recognise the immense challenge of rapid population growth and its relationship with unemployment, food scarcity, and other societal challenges[24]. However, to date, there are no public Government position statements or political or strategic commitments to address this. / Figure 7: Fertility by Zone (Demographic and Health Survey)
[22] NPopC, 2006 National Population Census
[23] Bongaarts J. Population policy options in the developing world. Science 1994; 263 (5148): 771-776.
[24] Statement from Leaders at the Nigeria Family Planning Conference 2010.

A recent estimate from the UN Population Commission projects that Nigeria’s population will rise from today’s estimated 158 million to 730 million by 2100 (See Annex 1). Three projections were made that consider the range of possibilities with respect to pace of fertility decline. For Nigeria, the projections are: / Figure 8: UN Population Commission – Projections of Nigeria’s population (2011) / Low Case Scenario Medium Case / Scenario High Case Scenario / 2010 158 158 158 / 2050 348 390 433 / 2100 505 730 1024 / 2050 population estimates show between 348 million (more than double the 2010 population) and 433 million (nearly tripling in size). By 2100, the range is even more dramatic: between 505 million (more than a tripling) and over 1 billion (which would be more than a six-fold increase). These projections are based upon current trends and various fertility rate scenarios. / Family planning service provision and financing / Figure 9: Contraceptive utilisation by provider (DHS 2008)

Both the public sector and private sectors are important providers of family planning commodities in Nigeria – each providing a different method mix. Of all methods, approximately 60% is provided by the private sector; however this figure is quite heavily influenced by the large proportion of condoms which are delivered outside of the public sector (i.e. social marketing). Regular stock outs of contraceptives in the public sector mean that the private sector is the only option available to the majority of the population. / Despite the wide ranging evidence and policy commitments being in place in Nigeria, there has been consistent lack of funding for family planning commodities – and to date there is no earmarked budget allocation for these commodities at Federal or State level. A few states have integrated family planning into their essential drug packages – however few states have financed these commodities on any scale. Given the lack of state government commitment, combined with the cost advantages of centralised pooled procurement, UNFPA has coordinated efforts to undertake large scale procurement, and distribute these commodities through the Government’s Reproductive Health Commodities Logistics System. / Advocacy efforts to address this situation have resulted in government commitment of $3 million for family planning commodities through UNFPA. Although this is a positive step forward, this funding allocation appears to be a one-time commitment rather than a regular Federally-mandated budget allocation to family planning. In addition, the Government of Nigeria issued a policy directive in March 2011 that user fees be removed for family planning commodities and services. This is an important step in removing barriers to access – and is in line with other policy directives. However, these commitments are yet to be realised. Estimates from the Reproductive Health Logistics Management System show this commitment would only met a 50% shortfall for 2011 only. / In 2010, UNFPA, Federal and State Government and other partners convened a high-level Family Planning Conference with included representatives from the Sultan of Sokoto, religious and traditional leaders, academics, Senators, Ministers, community groups and development partners. The conference marked a strategic and leadership change of direction. However, despite the beginnings of positive discussion on family planning, financial commitments were not met. While sustainability is desired, it is likely that external financing for family planning will be needed for at least the next 5 years until Federal financial commitments and procurement systems can be implemented effectively. / Commodity Procurement in Nigeria / UNFPA is the only Agency providing contraceptives to public health facilities in Nigeria. UNFPA is the procurement agent for the Federal Ministry of Health and works directly with the Family Health Division, together with a USAID funded programme (JSI-Deliver) to make annual estimates of contraceptive requirements and develop a detailed procurement plan for government and all partner contributions. UNFPA obtains low prices and discounts through its strong bulk buying position both individually and with other UN agencies, its market knowledge developed over long periods, and its technical knowledge of the ingredients of commodities, its production costs and sources, and branding opportunities for suppliers. The public plus private sector (mostly social marketing) is known as the family planning total market.

Contraceptive Commodity procurement projection need for the ‘total market’ / Figure 10: Social marketing (private sector) forecasts / 2011 2012 2013 2014 2015 / Condoms $5,680,550 $6,379,159 $6,852,881 $7,361,783 $7,908,477 / Injectables $3,336,606 $4,446,976 $5,000,182 $5,622,207 $6,321,611 / IUDs $21,630 $47,432 $52,175 $57,393 $63,132 / Implants $243,750 $213,459 $256,151 $281,775 $309,939 / Pills $2,380,950 $1,886,975 $2,028,875 $2,181,446 $2,345,490 / Emergency Contraception* $489,841 $351,758 $403,369 $462,554 $530,422 / Cycle Beads* $14,400 $14,400 $14,400 $14,400 $14,400 / TOTAL: $12,187,912 $13,340,160 $14,608,034 $15,981,557 $17,493,471

Figure 11. Public sector procurement forecasts and Couple Years of Protection

	2011		2012	2013	2014	2015	2016
Condoms	Costs ($)	$3,104,674	$3,501,191	$3,916,545	$4,351,306	$4,806,235	$5,308,678

	Quantities (piece)	114,340,925	128,944,108	144,241,031	160,252,688	177,007,105	195,511,428
	CYP	228,682	257,888	288,482	320,505	354,014	391,003
Injectables	Costs ($)	$2,983,325	$3,364,344	$3,763,464	$4,181,232	$4,618,379	$5,101,184

	Quantities (ampoules)	2,882,439	3,250,574	3,636,197	4,039,837	4,462,201	4,928,679

	CYP	576,488	650,114	727,239	807,967	892,440	985,736
IUDs	Costs ($)	$72,009	$79,424	$87,171	$95,271	$103,752	$112,988
	Quantities (piece)	208,118	229,549	251,939	275,350	299,861	326,555
	CYP	1,144,649	1,262,520	1,385,664	1,514,425	1,649,235	1,796,050
Implants*	Costs ($)	$167,474	$184,708	$202,735	$221,581	$241,300	$262,773

	Quantities (piece)	8,249	9,098	9,986	10,915	11,886	12,944
	CYP	28,871	31,843	34,951	38,202	41,601	45,303
Pills	Costs ($)	$3,697,408	$4,169,626	$4,664,279	$5,182,043	$5,723,826	$6,322,252

	Quantities (cycles)	9,062,274	10,219,671	11,432,056	12,701,085	14,028,985	15,495,715
	CYP	129,461	145,995	163,315	181,444	200,414	221,367
Total	Costs ($)	$10,024,890	$11,299,293	$12,634,194	$14,031,434	$15,493,491	$17,107,875

	CYP	2, 108, 151	2, 348, 360	2, 599, 651	2, 862, 543	3, 137, 704
							3,442,459
	CYP to be contributed by DFID Grant of £3m yearly =$4,800,000	1,009,400	997, 595	987, 662	979,244	972, 084	965,859

Links with other development partners: / There is excellent communication and coordination between the various partners and government on contraceptive procurement planning – much of this led by UNFPA in collaboration with the Family Health Division of the Federal Ministry of Health. Together the various approaches toward family planning have resulted in a Total Market Approach – where the public and private sector work together to promote family planning – and complement one another’s approaches. / The success of the programme outlined in the business case depends on the programme working closely with other development partners, government and other DFID funded programmes. / The key partners working on family planning provision include: / the Gates Foundation who run an Urban Family Planning Programme in 5 Nigeria cities (Ibadan, Ilorin, Abuja, Zaria and Benin City). This programme does not include procurement of commodities. / USAID has an important programme that works with government and UNFPA on procurement and supply chain management (JSI Deliver). USAID has not procured any contraceptives for the public sector. USAID is also working with the private sector and social marketing of contraceptive commodities. / CIDA has just begun a new $21 million 5 year maternal and child health programme, working with UNFPA, UNICEF and WHO under the auspices of the UNH4. This programme will disburse Canadian $9 million over the next 5 years for a variety of drugs, commodities and equipment for maternal and child health and this will include contraceptives. / UNFPA has committed core funding to work alongside this initiative – and has support from the new Executive Director of UNFPA. / Links with other DFID Programmes: / It is intended that this initiative will explicitly work with other DFID programmes in Nigeria. This has been incorporated into PRRINN and PATHS 2 logframes. / PATHS2 (Partnership for Transforming Health Systems) is DFID Nigeria’s main Health Systems Strengthening Programme. It currently works on National Policy within the Federal Ministry of Health and various National Agencies – as well as within 5 states (Lagos, Jigawa, Kano, Kaduna and Enugu). PATHS2 has a component of its work specifically considering issues of service delivery and within this, logistics and supply chain management. PATHS2 will directly complement the work on this initiative, though working with UNFPA to ensure an effective supply chain nationally – but specifically within the states it operates, ensuring work on training of health staff, demand creation, supply chain, forecasting as well as monitoring and evaluation is effective. Through the PATHS2 programme in 2010, £3 million of family planning commodities were procured using UNFPA systems. Throughout Nigeria today, the only family planning commodities available in the public sector were procurement through DFID/PATHS2. / PRRINN-MNCH (Partnership for reviving routine immunisation in Northern Nigeria – Maternal Newborn and Child Health) Is currently working on health sector governance and service delivery issues in 4 northern states. It is a partnership between DFID and the Government of Norway. The focus of their work is on maternal and child health, particularly at the primary health care level. This has included ensuring family planning becoming an integrated part of primary health service delivery – this has included: / Integration of family planning advice and support during ANC and Routine Immunusation care. / Ensuring family planning as part of post-abortion care. / Advocate for family planning commodities to be included as an essential drug in FMNCH / Monitoring the distribution and supply of family planning commodities; particularly in the primary healthcare setting. / During the 2010 Mid term review of PRRINN MNCH findings included: / Commodities in stock in all facilities visited. (Larger centres had a full range available and averages of 14 women per day receiving commodities.) / Staff are trained to provide manual vacuum aspiration (MVA) and family planning as part of the care package. / Community volunteers were knowledgeable about birth spacing, the benefits and were able to discuss with women in private settings / PRRINN MNCH will directly support this programme (as stated in their logframe) by including family planning modules into the training of health workers; advocating with State and LGA leaders for contraceptive commodities to be included as essential drugs; forecasting contraceptive commodity needs at State and LGA levels; reporting stock-outs; using community volunteers and health staff to stress the importance of family planning as part of the wider maternal and reproductive health needs of women. / ENR (Enhancing the National Response to HIV) is an HIV programme supported by DFID. It uses a social marketing approach, and within its procurement is mainly condoms (200 million pieces per year), and also a full method mix of family planning commodities. The approach used is social marketing – and this enables our work to take a total market approach. / HERFON (Health Reform Foundation of Nigeria) is a Nigerian foundation that operated nationwide as an advocacy group for health reform and transformation. This group was actively involved in the 2010 Family Planning conference – and are leading advocates in Nigeria for scaling up the countries efforts in maternal and child health. / Consequences of not intervening / The status quo is currently a situation of high un-met need for family planning, low contraceptive prevalence rate, regular stock outs of contraceptive commodities – reliance on the private sector for those who can afford – and unplanned pregnancies for those who cannot. The cost of not intervening can be measured in women’s lives and costs to the economy. Every year, up to eight million girls and women suffer pregnancy-related complications and roughly 350,000 die Girls and women in 6 countries are at highest risk: more than 50% of maternal deaths occur in India, Nigeria, Pakistan, Afghanistan, Ethiopia and the Democratic Republic of the Congo.

B. Impact and Outcome / Theory of Change / There is strong evidence that if girls and women use family planning commodities (i.e. increased CPR -Contraceptive Prevalence Rate) then they will reduce the number of children they give birth to, there will be fewer unplanned pregnancies and the space between children’s births will be greater (see orange boxes). There is also strong evidence that these changes result in a number of positive changes including reduced maternal mortality and morbidity as well as healthier children.

Achieving an increased CPR in Nigeria can be achieved relatively easily initially in Nigeria just through the procurement of contraceptive commodities owing to the extremely low stock levels and high unmet need. To enable there to be a sustained increased CPR, there will need to be proactive advocacy efforts (pink box) with government and other leaders (traditional and religious). There has been minimal investment by government in family planning commodities for the last 10 years. The recent commitments ($3 million) and current momentum needs to be maintained in order to leverage government resources. As CPR increases, there will need to be a deliberate effort in a number of areas (Blue boxes) such as logistics and supply chain, training of health staff, strengthening of health facilities and demand creation in communities (See risk tables on page 41). Advocacy efforts by UNFPA, other development partners and Nigerian Health Associations, will be put into ensuring government adequately supports these areas. In addition, support for these activities such as supply chain and demand creation is integrated into DFID’s other health systems strengthening programmes and the programmes of other development partners. / At the community level, there are many barriers that prevent women and girls getting access to services, including family planning services. Other DFID programmes in education, growth and governance support this empowerment. Education of girls is a central point of this work. Given the lack of availability of family planning services for some years, it is likely that incrementally increasing supply will on its own increase acceptability and demand. / Impact / The programme will provide into Nigeria’s public health system family planning commodities for 1 million couples each year for 6 years (a total of 6 million CYP). As a result, the programme will reduce the number of maternal deaths by at least 1255 each year for the next 6 years. The programme will contribute the Nigeria’s ambitious goal of increasing contractive prevalence rate by 2% each year from the current level of 10%. / International literature has shown that through improving the utilisation of family planning commodities, there are wide ranging benefits to women, their family and the society as a whole. Many of these will not be measured in this programme – such as improvement in school enrolment, nutritional status, women’s empowerment etc / Outcomes / Direct attribution: 1 million Couple Years of Protection of family planning commodities provided each year for the next 6 years. / The logical frame work and the programme performance matrix will provide the bench mark for monitoring project progress and evaluation. / Sustainability: / UNFPA has an advocacy strategy to ensure investment by the Nigerian Government in family planning. Forecasting organisations and published literature suggest that as commodities become available, demand for services will increase. This programme deliberately proposes a flat line in funding – with the explicit intention of government and others incrementally increasing their proportion of funding year on year to meet demands.

Appraisal Case

A. Determining Critical Success Criteria (CSC)

Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention.

CSC	Description	Weighting (1-5)
1	QUANTITY: UNFPA capacity to procure large quantities (and Value for Money): measured in Couple Years of Protection) – and impact on national contraceptive prevalence rate (CPR).	4
2	COVERAGE AND EQUITY: State capacity to provide wide geographical coverage across the whole of Nigeria, including rural areas.	5
3	COVERAGE AND EQUITY: State and LGA capacity to provide commodities to those populations most in need including lowest wealth quintiles and adolescent girls.	5
4	QUALITY: UNFPA, State and LGA capacity to ensure continuity of supply of an appropriate range of commodities (measured in prevention of stock outs in public health facilities)	3
5	INSTITUTIONAL: Ability to strengthen existing systems and/or does not undermine existing systems.	2
6	SOCIAL: Awareness of sensitivity of family planning and appropriate ways of working.	2

B. Feasible options

Option	Title	Description
1	Centralised procurement of family planning commodities using Nigeria’s current system for the public sector	UNFPA currently leads contraceptive procurement efforts for the public sector in Nigeria; UNFPA pool funds from government and partners to ensure a coordinated approach to forecasting, decisions on method mix, procurement, storage, distribution, management and monitoring. / In this option, DFID would provide funds to UNFPA to rapidly scale up the availability of family planning commodities to the public sector throughout Nigeria. This effort would be supported and complemented by UNFPA, government and other partners to ensure an effective supply chain, training of health workers and demand creation. / This approach would complement the current social marketing work within the private sector and support the total market approach which values of both the public and private sector. / Contraceptives procured for the public sector will be branded and marked as Free and not for sale. This will prevent leakage to the private sector and ensure that the cost of commodities does not become a barrier for women. / This option would work explicitly with DFID’s existing health systems programmes, particularly the service delivery components of PATHS2 and PRRINN-MNCH as well as the logistics and supply components of PATHS2. It would also complement the current work with the Gates Foundation as well as USAID (particularly the TSHIP programme through the Alliance for Reproductive and Maternal Health). / This option would collaborate with state governments in their forecasting and supply chain work, complemented by work of DFID programmes and other development partners.
2	Decentralised state based procurement of family planning commodities	Ideally, family planning commodities should be an integrated part of a comprehensive essential package of drugs and commodities procured by state governments. This option would prevent any risk of another parallel vertical, centrally led initiative – and empower state governments to take leadership in family planning services. / Nigeria has 36 states plus the FCT and therefore this option would be highly complex unless focussed on a few selected states. This option would be best if integrated within DFID’s existing PATHS2 and PRRINN programme and have a potential impact on 8 states. The scale and impact of this approach would be substantially lower than option 1. Significant technical assistance for individual procurement across all 36 states would be required. This is expensive and requires substantial logistic support. There are currently no zonal arrangements (capacity nor storage) for the procurement of these drugs and commodities in Nigeria.
3	Scale up of social marketing	DFID is already investing significantly in the social marketing of family planning commodities. / This option would require contracting out social marketing services to a private contractor. Currently the Society for Family Health is the only nation-wide social marketing firm in Nigeria. / This option would limit Nigeria’s approach to provision of family planning commodities to a mainly private sector approach. USAID is already planning to scale up some social marketing of family planning work. International experience shows that increasing coverage and quality of family planning services requires a total market approach.
4	Do nothing	The resources could be applied to other activities.

Social Impact

This programme has been designed to promote the availability and accessibility of a range of family planning commodities to girls and women who wish to use these services – including the poor, rural and uneducated. Removal of user fees may reduce barriers to access. Another key barrier will be ensuring the commodities are available, and become integrated with other services.

Another critical barrier concerns that of traditional and cultural beliefs, particularly in the north of Nigeria. Early marriage is also closely linked to early fertility, and 15% of girls 15-24 had already had a birth before they turned 15 (Jigawa, Zamfara, Yobe, Jigawa, Kaduna and Kano). There are significant social and cultural norms across Nigeria and childbearing illustrates these differences. For example, 65% of girls start childbearing before they leave their teenage years in Katsina – and yet only 3% in Edo state (DHS 2008). Early childbearing has consequences for individual girls in relation to high risk of HIV infection, limited opportunities[25].
[25] Lloyd C. and J. Young (2009) New Lessons: The Power of Educating Adolescent Girls. Population Council

Figure 12: The results of women and girls being in control of their fertility[26]
[26] Guttmacher Institute (2009) Adding it Up. New York: Guttmacher Institute

Outcome	Reason
Improved women’s education	Girls can stay in school and finish their education
Increased female labour force participation	Family sizes smaller, giving women increased flexibility to work
Increased political participation	Women have more freedom to participate in society
Higher status for women	Women are not always pregnant and have increased control over their lives
Increased family well-being	Mother has survived to care for her family
Increased child well-being	More time and income for each child

In the long term, there are additional potential societal benefits:

Outcome	Reason
The amount needed to spend on the public health sector is lower	Healthier mothers & babies, and slowing fertility means reduced numbers of people seeing health care
The amount needed to spend on the public sector education, water and sanitation is lower	Slowing fertility means reduced numbers of students, and people needing water and sanitation services.
Improved productivity and higher income, greater savings and investment	More people in working age population with fewer children to support
Potential for faster economic growth	Working population has fewer children to support
Reduced pressure on natural resources	Fewer people to be sustained by the land

Impact on climate change and the environment:

Some research suggests that family planning is associated with lower carbon emissions.[27] However, there is very limited evidence (from observational studies) which quantifies any reduction and can isolate this from other confounding variables. As the human population grows so does the demand for energy; as more energy from fossil fuel is used, more greenhouse gases are produced.
[27] Wheeler D and Hammer D The Economics of Population Policy for Carbon Emissions Reduction in Developing Countries. Centre for Global Development Working Paper 22. 9 November 2010.
Carbon emission reductions from spending $1 million on various interventions[28]
[28] Wheeler D and Hammer D The Economics of Population Policy for Carbon Emissions Reduction in Developing Countries. Centre for Global Development Working Paper 22. 9 November 2010.

In the table below:

the quality of evidence for each option is rated as either Strong, Medium or Limited,
the likely impact on climate change and environment is categorised as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.

Option	Description	Evidence rating	Climate change and environment category (A, B, C, D)	Comments
1	Centralised procurement of family planning commodities using Nigeria’s current system for the public sector	Medium	C	This option could possibly have a positive impact on climate change and environment.
2	Decentralised state based procurement of family planning commodities	Medium	C	As above – however the scale will be lower than option 1
3	Scale up of social marketing	Medium	C	This option could possibly have a positive impact on climate change and environment.
4	Do nothing	Medium	C	Not known.

C. Appraisal of options

Value for money for family planning interventions

Increasing modern family planning coverage is a highly cost effective intervention[29] [30]. Estimates for meeting family planning needs for 818 million women in developing countries would cost:
[29] Ibid.
[30] Singh, S., Darroch, J.E., Ashford, L.S., Vlassoff, M., 2009. Adding it up: The costs and benefits of investing in family planning and maternal and newborn health. New York: Alan Guttmacher Institute, UNFPA.

- $ 28 to avert an unintended pregnancy
- $ 3050 to save the life of a woman or newborn
- $ 62 to save a DALY (women and newborns combined)

Putting this in the context of other common health care interventions in developing countries they demonstrate that such a cost-benefit figure represents relatively good value for money:

Intervention	Cost per DALY saved in US$
Insecticide-treated bed nets	13-20
Malaria prevention for pregnant women	29
Tuberculosis treatment (epidemic situations)	6-60
Modern contraceptive methods	62
Antiretroviral therapy (Africa)	252-547
BCG vaccination of children	48-203
Oral rehydration therapy	1268
Cholera immunisation	3516

Furthermore the Guttmacher Institute in 2009 demonstrated that in Sub-Saharan Africa, providing modern contraceptives, would more than pay for itself, saving $1.30 in the cost of maternal and newborn care for each dollar invested.

Using the MSI Impact calculator – and applying this to the contraceptives to be procured under this programme, it has shown that for each £1 invested in family planning in Nigeria, the benefits are around £26. These are estimates have been determined using data on current demand for family planning commodities and could vary over time.

Estimated Reproductive Health Impact for 6 Year Nigeria Contraceptive Programme

Impact Measures		Year 1	2	3	4	5	6	Total
CYPs		1009400	997595	987662	979244	972084	965859	5911844
Unintended pregnancies averted		210516	208054	205983	204227	202734	201436	1232950
Unintended births		153086	151296	149789	148513	147427	146483	896594

Maternal deaths		1286	1271	1258	1248	1238	1230	7531

Unsafe abortions averted		21975	21718	21502	21318	21163	21027	128704
DALYs averted		248935	246023	243574	241498	239732	238197	1457958
Total cost savings (GBP)		25,567,866	25,268,848	25,017,248	24,804,022	24,622,661	24,464,983	149,745,628

The MSI Impact Calculator: Methodology and assumptions

The MSI Impact Calculator is one of the methodologies being used by DFID to calculate the impact family planning programmes worldwide. Full details of the methodology are contained within The MSI Impact Calculator: methodology and assumptions by Nick Corby, Tania Boler and Dana Hovig 2009. Each country has been provided with a coefficient which has been derived from the best data available for each country – usually Demographic and Health Surveys together with UNICEF Multi-indicator Cluster Surveys. The accuracy of the coefficients is dependant upon the quality of the data. In Nigeria, the DHS, although not perfect, is considered to be the best data available.

Couple Years of Protection (CYP) is a commonly used measurement of family planning performance. It is calculated by multiplying the number of each contraceptive method given to clients by a corresponding conversion factor. This yields an estimate of the duration of contraceptive protection provided. One full CYP is the equivalent of one year of protection from unintended pregnancy for one couple.

The conversion factor differs for each method of contraception. For example the conversion factors used by MSI equate 100 male condoms paid for by the client and 500 free male condoms to one CYP. These differences reflect how many estimated units of that method are typically needed to provide one year of contraceptive protection per couple. They also reflect estimated effectiveness, wastage and frequency of intercourse.

These conversion factors offer only a limited indication of family planning performance for a number of reasons. For example, these conversion factors do not reflect regional or national estimates of wastage for condoms or frequency of sexual intercourse. Furthermore, they do not account for method substitution. A particular distribution programme may simply cause people to replace on contraceptive method or supplier for another and not necessarily increase the overall use of contraception. In addition, these factors do not reflect the cost effectiveness of different programmes. They also ignore whether a particular programme is reaching poor or marginalised groups.

Full details on the formula used to derive pregnancies averted; deaths averted etc are contained within The MSI Impact Calculator: methodology and assumptions by Nick Corby, Tania Boler and Dana Hovig 2009. Over and above those indicators within the table above, the MSI tools can also calculate environmental impact per CYP.

Option 1: UNFPA centralised procurement of family planning commodities using Nigeria’s current system for the public sector.

UNFPA NEGOTIATED UNIT COSTS OF CONTRACEPTIVES (as at June 2011)
Contraceptive Type	Cost USD	UOM
Male Condoms	3.91	Gross
Female Condoms	0.6	Each
Implanon	19.6	Set
Jadelle	21.0	Set
Exluton	0.4340	Cycles
Microlut	0.4570	Cycles
Microgynon	0.333	Cycles
Medroprogesterone Acetate. Exclude Needle	0.7700	Vial
Noristerat	1.3	Ampoule
Syringe Options
Soloshot IX Syringe	0.0750	Each
Syringe 2ml disposable, plastic 21G x 1.5 inch	0.0350	Each
Discard-it Syringe 2ml vial Ned. 21g x 1.5 inch	0.1210	Each

The system currently in place for the procurement of family planning commodities is through centralised pooled procurement through UNFPA. This mechanism enables price advantages through bulk purchases internationally. This option has the capacity for large scale up and potentially huge impact. There is a reproductive health logistics system in Nigeria which moves the commodities from the port to facilities through a network of stores in Lagos, states and local governments and then on to facilities and communities. States are supported to forecast their needs and are an integral part of the process. Stock outs are monitored through the public system in this option – and while this is weak, it is something being strengthened by DFID’s current programmes (especially PATHS2 and PRRINN-MNCH).

All family planning commodities in the public sector are free. Therefore the family planning commodities in the programme will be branded and clearly marked free (not for sale). Cost as a potential barrier is therefore removed with this option.

There are significant advantages of this approach in terms of scale and coverage. Some more ‘conservative’ states that have been unwilling to procure FP commodities themselves have been willing to draw down from centralised procurement. A disadvantage of this approach is that FP commodities are procured separately from other commodities which should be considered an integrated part of a package of essential services. In some states DFIDN’s PATHS2 and PRRINN programmes have been working with state governments to create budget lines for all essential drugs and family planning has been part of this. Slow progress is being made. This centralised approach does not need to undermine state ownership as long as states are kept explicitly involved in forecasting, distribution and monitoring. Budget lines for family planning could be used for additional family planning commodities and added to the central procurement budget pool.

Option 2: Decentralised state based procurement of family planning commodities

Nigeria has 36 states and the Federal Capital Territory. To reach the impact proposed by this initiative under this option would require support and technical assistance to all 37 entities. In addition, fiduciary risk would be high as many state based procurement systems are unable to procure, distribute and manage supplies in a timely manner. This option would not allow for economies of scale.

Ideally family planning should be procured as part of an integrated package of essential drugs. States are supposed to have budget lines for essential drugs – however, many do not disburse on this budget line and therefore there are regular stock-outs of most essential drugs at the primary health care level. Therefore this approach, while the most decentralised, state owned and integrated approach – it is likely to be unable to achieve the results and impact required.

Option 3: Scale up of social marketing

DFID currently has a large social marketing programme throughout Nigeria that provides condoms and other contraceptives through the private sector. Each year DFID procures 200 million condoms which are socially marketed. The programme also procures family planning commodities that people buy at a subsidised rate from private providers.

This option would be to massively scale up this work to meet the unmet need. However cost barriers, despite the commodities being subsidised, are a risk particularly toward reaching those most at need including the lowest wealth quintiles.

There is evidence that social marketing together with free public sector provision of family planning commodities complement each other well. A single market approach (i.e. just social marketing or just public sector free) approach is less efficient and has greater risk than a total market approach – where the various sectors reinforce results in one another. It is possible that USAID may provide additional resources for socially marketed family planning – further reinforcing the need to DFID to complement the public sector side of the market.

Support for this approach could potentially undermine Nigeria’s Reproductive Health Logistics system, and reduce responsibility / public sector for government in provision of family planning.

Costs (Dollars) of social marketing commodities[31]
		Commodity	Shipping & Handling
Duofem or Comb3 OC		1.03	0.097
Depo Provera		11.03	0.09
Jadelle		21	1.82
IUCD		0.49	0.075
Cyclebeads		0.99	0.8821
Cost (British Pounds)
Condoms	0.0113		0.0016
[31] UN

In addition to the costs above, are those of the social marketing.

Option 4: Alternative use of resources/ Do nothing

Under this option, resources would be channelled into other programmes and interventions, some of which would be less cost-effective and higher risk.
D. Comparison of options

The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention.
CSC	Description	Weighting (1-5)	Option 1		Option 2		Option 3		Option 4
			UNFPA Centralised procurement of family planning commodities using Nigeria’s current system for the public sector		Decentralised state based procurement of family planning commodities		Scale up of social marketing		Do nothing

		Weight	Score	Weighted Score	Score	Weighted Score	Score	Weighted Score	Score	Weighted Score
1	QUANTITY: Capacity to procure large quantities (and Value for Money): measured in Couple Years of Protection) – and impact on national contraceptive prevalence rate (CPR).	4	5	20	3	12	4	16	0	0
2	COVERAGE AND EQUITY: Capacity to provide wide geographical coverage across the whole of Nigeria, including rural areas.	5	5	25	3	15	4	20	0	0
3	COVERAGE AND EQUITY: Capacity to provide commodities to those populations most in need including lowest wealth quintiles and least educated.	5	5	25	3	15	2	10	0	0
4	QUALITY: Capacity to ensure continuity of supply of an appropriate range of commodities (measured in prevention of stock outs in public health facilities)	3	4	12	4	12	4	12	0	0
5	INSTITUTIONAL: Ability to strengthen existing systems and/or does not undermine existing systems.	2	5	10	2	4	2	4	0	0
6	SOCIAL: Awareness of sensitivity of family planning and appropriate in ways of working.	2	4	8	5	10	3	6	4	8
Totals				100		68		68		8

The options appraisal above showed Option 1 – centralised procurement of family planning commodities to be the most appropriate option to explore.
E. Measures to be used or developed to assess value for money / Value for money will be assessed by reviewing: / Unit costs of commodities procured (will be assessed annually). / Couple years of protection procured and distributed each year / Contraceptive prevalence rates for all women, the poorest 40% and young women aged 15-19 (measured through the Demographic Health Survey [DHS] and Multi-indicator Cluster Survey [MICS] – both co-financed by DFID through other programmes) / Number of women using family planning (DHS and MICS) / Number of unintended pregnancies prevented (calculated from CYP) / above are standard indicators from within DFID’s Framework for Results for improving reproductive, maternal and newborn health in developing countries.) / Using a DFID accepted impact calculator – such as the MSI Impact tool, estimates will be made annually of the maternal deaths averted and DALYs saved. / Figure 2: Diagrammatic Representation of the Impact of Family Planning (from the MSI Impact Calculator) / Miscarriages averted / (15% of all pregnancies) / Births averted / (Pregnancies x (1-probability miscarriage–probability abortion) / Abortions averted / (Pregnancies x (1 - prob. miscarriage) x probability abortion) / CYPs / (FP method x CYP conversion factor) / Pregnancies averted / (CYPs x Guttmacher ratio) / Maternal Deaths averted / (births x MMR ÷100,000) / Infant Deaths averted / (births x IMR ÷ 1,000) / Eco footprints averted / (births x eco footprint) / Carbon footprints averted / (births x carbon footprint) / Costs saved / (Maternal deaths x mat death cost) + / (Infant deaths x inf death cost) + / (Unsafe abortions x 40% x PAC cost) / Unsafe abortions averted / (Abortions x unsafe AR ÷ AR) / DALYs saved / (CYPs x PSI DALY coeff ÷ PSI CYP:DALY convertor) / DALYs from maternal morbidity & mortality, unsafe abortion, child health due to inadequate birth spacing / Costs saved per £1 invested / (costs saved ÷ cost of delivering services) / Family Planning Methods

Commercial Case for Option 1.

   Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / UNFPA is the UN Agency with the mandate to promote reproductive health activities in member countries all over the world. It works with nations, civil societies, communities, households and individuals to enhance a state of complete physical, mental and social well being in all aspects of the reproductive system. UNFPA is the lead development partner working with collaborating with the Federal Ministry of Health and the States to support family planning services in public health facilities in Nigeria. It does this through advocacy and policy dialogue, supporting Federal and State government to create the necessary policy environment for sustainable development in reproductive health, strengthening systems and structures for efficient reproductive health delivery, building institutional and personnel capacities, and ensuring efficient and timely provision of supplies and equipment. It also helps communities to raise their demand for reproductive health commodities and facilities. / UNFPA leads on sexual and reproductive health rights (SRHR) and supports countries to use population data for policies and programmes to reduce poverty. It has a critical role on MDG5 (maternal health) and supporting role on MDG6 (HIV/AIDS) and MDG3 (gender equality). All three of these interventions are priority areas for DFID Nigeria. The DFIDN Operational Plan 2010 – 2015 includes a large scale up to help Nigeria in its push to meet MDGs 5 and 6, and MDG 3 initiatives. They also chime with DFID’s strategy for Women and Girls. / DFID’s Multi-lateral Aid Review (MAR) 2011 concluded that UNFPA’s strengths were building strong partnerships with civil society, partner countries and other agencies. UNFPA has a good track record on procurement with a strategy to consider VFM related principles. UNFPA has strengthened its oversight and financial resource management, with flexibility to respond to country needs. However, Evaluation culture and global level results chains are week. / The efficient procurement process of the UNFPA HQ and the vast experience gathered over the years, together with the quantum of contraceptives procured for countries all over the world, places it in the best position to handle this intervention. In addition, UNFPA as the lead UN Agency on reproductive health has comparative advantage in carrying out interventions in reproductive health especially contraceptive services. The Federal Government recognizes the vantage position of UNFPA, its achievements in promoting maternal health, support in national development including conduct of national census, achievements in interventions in reduction of maternal mortality and morbidities such as Vesico Vaginal Fistula etc. Their partnership with UNFPA goes back over 25 years and this strong partnership has helped to promote more effective government health systems – the ordering, procuring, storing and distributing FP commodities to help avoid stock-outs is a recent example. / B. Value for money through procurement / The procurement policy for UNFPA entails sourcing of contraceptives, medical supplies, equipment and logistic support through its Procurement Services Branch (PSB) in Copenhagen. The process is transparent and uses international competitive bidding processes. Competition itself does not ensure value for money. However, UNFPA has a comparative advantage in the procurement of commodities because of the substantial use of long-term agreements (LTA), continuous pre-qualification of potential suppliers for medical and pharmaceutical items, and crucially, excellent knowledge of the cost and international quality standards required for all the ingredients in the commodities it buys regularly. Another strength compared to other UN agencies is that UNFPA procurement is conducted in small highly specialised markets. Therefore international competitive bidding and the vast experience of the UNFPA HQ ensures that good quality products are obtained at the most competitive prices. The prices obtained by UNFPA will be regularly assessed and benchmarked by the DFID Project Manager and Commercial Adviser. UNFPA has assured DFID that it uses market surveys to regularly benchmark the prices it obtains. / UNFPA’s procurement capability was last assessed by DFID’s Procurement Group in 2008. The findings were positive. An updated assessment is planned but there appears to be no evidence to suggest performance has deteriorated. DFID Nigeria will regularly assess UNFPA’s management of this through the MoU to ensure that value for money is maintained. / UNFPA is also ISO certified as complying with best practice in the field in 2008. It is the only UN agency currently holding this certification. UNFPA’s current head of procurement was appointed in 2010. He plans to accelerate collaborative buying with other UN agencies, consistent with the “One UN” approach.

C. Clearly state the procurement/commercial requirements for intervention (through UNFPA) / The funding model requires payment of the grant to the UNFPA HQ for transmission to the Country Office. The majority (93%) of the funds committed to UNFPA under this programme are for contraceptive commodity procurement – with support costs (app. £100,000) associated with staffing in UNFPA and commodity logistics support. UNFPA HQ will manage the fund on the behalf of the UNFPA Country Office. Note that UNFPA will charge the minimum administration fee of 7% as agreed in the DFID/UNFPA Framework Arrangement of 1st November 2007. The UNFPA central procurement systems have been assessed as value for money by DFID Procurement Group, and will require regular assessments by DFID Procurement Group to ensure that value for money is maintained. / The UNFPA Country Office will undertake commodity forecasting each year in collaboration with the national government and other partners. The Federal Government of Nigeria has committed to use UNFPA for procurement of public sector commodities since their partnership began over 25 years ago and there is no indication of this partnership dissolving soon. In addition, Canadian CIDA has a programme with UNFPA to also fill part of the funding gap. / UNFPA has a strong and well established relationship with the federal and state ministries of health and civil society organisations, all of whom will collaborate with UNFPA to implement the programme, maintaining strong supply chains and logistics, creating demand, monitoring and obtaining quality assurance with the help of their USAID funded partner John Snow Incorporate – technical experts in supply and quality control of storage and distribution chain.
D. How does the intervention design use competition to drive commercial advantage for DFID? / The procurement of contraceptives and any other items will be carried out by the UNFPA Procurement Unit in Copenhagen with collaboration of the Commodity Security Branch UNFPA HQ. This will be in accordance with a procurement plan agreed with DFID Nigeria. The procurement process is based on international principle of transparently fair and open international competitive bidding, offering economies of scale and volume discounts as it supports contraceptive procurement for UNFPA worldwide. Thus quality is assured and the prices are about the best globally. Prices will be regularly monitored by DFID Nigeria. / In liaison with the RHCS Forecast sub-committee, the contraceptive commodity requirement for the country to be funded by the project is determined. The contraceptive order is submitted by the UNFPA Country Office to the Procurement Unit in Copenhagen which carries out the procurement process on the behalf of the Country. All necessary documents and waivers for importation and clearance of the commodity are handled by the UNFPA Country Office in collaboration with the FMOH and other relevant government agencies. Global forecasting of future requirements and analysis against historical trends are collected to produce an annual procurement plan and early warning to potential suppliers of likely needs. Global pricing and trends are also analysed. / UNFPA’s procurement policies, practices, systems and management are judged to be capable of delivering the programme to the required standard. Risks are mainly related to stock-outs and that UN management charges will neutralise the best prices obtained through UNFPA’s purchasing power. / DFID’s investment will be channelled through UNFPA delivered through a Memorandum of Understanding (MoU) with funds released in advance (but not too much in advance of need) as agreed in the MoU. The MoU will be supported by the addition of specific delivery requirements related to UNFPA’s obligations to ensure fast, effective management and sustained supply of quality products at best prices.
E How do we expect the market place will respond to this opportunity? / UNFPA experience is that companies manufacturing bulk volumes of contraceptives will respond enthusiastically to the demand for commodities created by the DFID Programme and will bid for the opportunity to supply them. The consistent procurement of contraceptives from the Grant of £3 million annually for six years and the likely sustained increase in contraceptives use in Nigeria thereafter will lead to increased production of contraceptives with possible reduction in unit prices thereby stimulating further increase in utilization. UNFPA is very confident that its markets will respond to the opportunity. DFID Nigeria accepts that UNFPA does not routinely experience difficulty in sourcing its products, and that the opportunity to pre-qualify to supply bulk products is forecast to give incentives for markets to bid competitively for pre-qualification.
F. What are the key underlying cost drivers? How is value added to the accessibility of FP commodities and how will we measure and improve this? / The key cost driver for this programme is the mix of commodities procured together with the unit costs of the commodities. / Essentially the principles of demand and supply will interplay to influence the services. This will include the availability of products, popularity of products, quantum of requests received, the brand of the products etc. / To improve targeting of additional resources for contraceptives procurement, distribution and delivery, the analysis of cost drivers are important in order to get the best results in terms of impact on the MDGs. / Good distribution methods will significantly reduce unit costs of commodities; increase use of family planning programmes; increase quality of product and service, and promote contraceptive use. There will be potential from the programme funds to help the federal government to develop the capacity to examine unit costs and value for money in a systematic manner. All of these types of measures can provide an effective way to improve the use of resources in the sector. / Providing the contraceptives free at the point of use as a form of price subsidy will reduce the direct cost of purchasing contraceptives, while investing in effective distribution channels will reduce management and travel costs at all government levels. / How cost-effective are expenditures on distribution? A common conclusion is that inadequate physical access to supplies and services is one of the predominant causes of unmet need. Therefore bulk procurement of contraceptives, high quality logistics and distribution to facilities should greatly enhance people’s access to contraception. / The evidence is a little clearer for measures of quality, such as the range of method choice, private versus. public provision, waiting times and the quality of family planning counselling services. Contraceptive discontinuation is strongly affected by the range of contraceptive methods available to users. A mix of methods is found to address needs of couples, and a lack of access to a method mix that meets needs leads to decline in service utilization. Several studies have likewise shown that contraceptive use rises with greater method choice and increases in quality. / Other demand side drivers are supported by the NDHS data, which suggests that major barriers to contraceptive use include lack of knowledge about family planning methods, socio-cultural issues and concerns about health effects, all of which are addressed by promotional activities. Examining data from studies20 suggest that exposure to promotional messages through community and traditional structures, television, radio and print media has great potential to increase contraceptive use. / Measuring unit costs of activities undertaken and supported by the programme will be deployed to create the platform to exert cost control measures. Also efforts will be made to periodically examine unit costs, track costs and identify anomalies. At each Annual Review DFID Nigeria will build in a VFM clause to the Terms of Reference.
H. How will UNFPA manage contract and supplier performance through the life of the intervention? / The contract and supplier performance will be managed through the UNFPA management system as integral part of the UN system in Nigeria. DFIDN will ensure that UNFPA’s terms of reference contain clear and comprehensive reporting lines to us. We will need more than simply data on purchase orders. We will require demonstrable evidence that would survive physical checks that UNFPA are consistently managing supplier performance, including that of consortia members, and achieving programme outcomes. DFIDN will ensure UNFPA’s management performance forms a significant component of monitoring reviews. / UNFPA has confirmed that it operates vendor performance measurement processes, to ensure that all contract requirements and technical specifications are met, identify performance problems early and find solutions with all involved parties. Information on performance influences future sourcing choices. UNFPA also operates supplier communication processes to strengthen its relationships with its key markets.

Financial Case

A. How much it will cost / The cost of DFID’s investment is £18 million pounds sterling over 6 years. This will be disbursed in annual instalments as determined in the MoU between DFID and UNFPA. / According to UNFPA in partnership with the Family Health Department of the FMOH, Nigeria needs $11 million to $16 million worth of contraceptives annually in the public sector for the next five years following current consumption pattern. The Federal Ministry of Health is expected to contribute about $3 million annually. This leaves the country with serious funding gap. UNFPA is expected to support Nigeria with about $2 million annually during the project period. UNFPA therefore requires support to assist in bridging the funding gap for contraceptives in Nigeria. UNFPA along with its partners DFID, USAID, CIDA will be pushing hard for over the next few years for the Federal Government of Nigeria to assume greater responsibility in the provision of contraceptives to its citizenry. / Projected Public Sector Funding gap (US$) (source: USAID-Deliver programme) / GAP
C. How funds will be paid out / Project fund will be channelled to UNFPA Headquarters and then released to the Country Office in Nigeria annually. Funds will be accessed annually based on approved work plan and accompanying FACE and released for project implementation either directly to the Country Office. Monitoring of project activities and financial expenditures will be carried out in line with UNFPA’s management procedures. Annual programme and financial reports will be prepared and submitted to DFID.

Management Case

A. Oversight

UNFPA Country Office Abuja will exercise functions as the Implementing Agent. Monitoring and Evaluation through the Log Frame and Programme Performance Matrix as attached.

B. Management

The project will be managed through the existing management structure of UNFPA in the country. The Country Office will be responsible for the overall management of the project in the country and will use the zonal offices to coordinate activities in the states. One programme officer (logistician) will be recruited to assist with the coordination of project activities.

Technical assistance will be provided when needed by the UNFPA sub-Regional and Regional Offices in Dakar and Johannesburg respectively. In line with the principle of aid effectiveness, the project will be implemented with national and state governments to ensure ownership. UNFPA will collaborate with the FMOH at the national level and the SMOH at the state levels.

Appropriate documentation, Memorandum of Understanding (MoU) concerning the project will be signed by UNFPA and DFID by their designated representatives. In addition, DFID and UNFPA will sign documents concerning the disbursement of and accounting for funds through the UNFPA headquarters.

Federal, State and LGA government partners will review the UNFPA programme reports and documents line with procedures as part of the review of the national RH project. This will afford the national government the opportunity to monitor the progress and performances achieved in the project. The UNFPA Country Office will collaborate with partners in the national RHCS Technical Working Group chaired by the FMOH to determine forecast of contraceptives requirements, produce shipping plans. The Country Office of UNFPA thereafter collaborates with the Procurement Unit of UNFPA Headquarters to place orders for contraceptives and deliver them to the national warehouse.

Maximising coordination with other donor programmes

UNFPA will be invited to DFID’s monthly health programme managers meeting. This will ensure there is regular communications with other DFID programmes (particularly given the important links with PATHS2 and PRRINN/MNCH), and enhances linkages into current DFID issues. UNFPA also regularly attend the monthly health donors coordination meeting held at UN House.

C. Conditionality

Not applicable, as the programme does not involve financial aid to government.

D. Monitoring and Evaluation

There are no plans in this programme to spend monitoring resources on evaluating its effectiveness; however resources will be needed to monitor implementation, such as the procurement and supply chain process (and other blue boxes in the theory of change.)

UNFPA will be responsible for developing a monitoring framework that will be approved by DFID during the first 3 months of the programme.

The programme will require data on supply chain, reaching beneficiaries, demand creation, primary health care effectiveness and staff skills. Some of these aspects are already being monitored through other programmes e.g. JSI-deliver on supply chain, and PATHS2 and PRRINN on staff skills. PATHS2 and PRRINN-MNCH will supply the required data (such as service delivery data) to UNFPA on the states where they are working (Lagos, Kano, Kaduna, Enugu, Jigawa, Yobe, Katsina and Zamfara). UNFPA will need to assess where there are gaps in monitoring and advice PRRINN and PATHS2.

A number of critical indicators in this programme will be collected by the Demographic and Health Survey in 2013.

DFID will conduct annual reviews that UNFPA will be part of, using external consultants to ensure independence. This annual review will assess the programme against the log-frame of the programme and assess value for money of the intervention.

DFID, UNFPA and other partners will join the programmes Joint Annual Review undertaken by the Federal Ministry of Health – and further monitoring of programme implementation will be imbedded into this review.

The project shall also be monitored according to the UNFPA’s guidelines. Periodic monitoring visits to Federal, State and LGA PHC departments, warehouses and service delivery points will be undertaken by UNFPA’s partner JSI. There will be quarterly monitoring and supervision of the project in all states coordinated by the FMOH with reports routinely submitted to the FMOH and to the management project team in UNFPA. The project will support Technical Review meetings at state levels monthly to coordinate and monitor the project activities in the states. Similarly, there will monitoring and coordinating activities in the LGAs coordinated by the FP team in the LGAs.

Quarterly reports will be provided to DFID in a format agreed with UNFPA and DFID.

E. Risk Assessment

Risk	Impact on results	Likelihood of happening	How DFID will manage the risk?
Government / other key stakeholders not prepared for scaling up family planning in Nigeria.	High	Low	Nigeria has had times in its recent history where there has been significant resistance to family planning. Owing to the engagement of traditional and religious leaders together with political leaders in debates around family planning, the resistance has been massively reduced. DFID, USAID and UNFPA all have programmes that are specifically working on ensuring these leaders are kept engaged in these debates. HERFON – a Nigerian Health Reform Foundation (also funded by DFID) was involved in running the recent successful family planning conference. Through the Health Donor Partners Group that also includes high level official s from MOFH, it the intention is to keep up the push on the Federal Government to invest more in FP services. At State level, UNFPA with its CSO advocates will continue to lobby for more State resources.
Health services are too weak at the primary and community level to deliver family planning services	Medium	Low/ / Medium	DFID has two major health systems programmes – and is working towards developing replicable models to strengthen Nigeria’s weak primary health care services. DFID is also working with Federal Government and the National Primary Health Care Development Agency on strengthening PHC. It is hoped that a Health Bill will soon be passed which will provide a significant boost to PHC – but even without this, family planning services are relatively basic and can be delivered even by relatively weak health service
Logistics management system fails to ensure commodities are moved from port to facilities at the right time in the right amounts	Medium	Medium	Logistics systems in Nigeria are weak. USAID through its DELIVER project (along with JSI) is specifically working on Nigeria’s reproductive health logistics system. DFID’s PATHS2 programme is also working on Federal and State government logistics systems more generally across Nigeria. In addition, CIDA has a new programme working with WHO and UNFPA which includes strengthening of existing government logistics systems.
The incorrect method mix is procured leading to stock outs of some commodities and for other going to waste.	Low	Low	Owing to the extremely low supply of commodities in the past, the method mix provided to facilities has been more based on what is available rather than what is needed. Work will be done, through UNFPA and the Government of Nigeria to continuously assess method mix requirements.

F. Results and Benefits Management

The programme will increase in the availability of family planning commodities in the public sector. The CYP (Couple Year of Protection) will be used to estimate the impact of the programme on maternal and child health.

This will be measured and managed through routine quarterly strategic reports drawing on performance against log-frame indicators to assess impact and results, and from the quarterly monitoring and supervision mentioned in Section D above.
PROJECT NAME	ACCESS TO FAMILY PLANNING COMMODITIES IN NIGERIA
Super Goal	Indicator 1		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)
Improved maternal health	Maternal Mortality Ratio	Planned	545 (per 100,000 live births)		409		275		136
		Achieved
			Source
			Demographic and Health Survey (DHS) 2008. Future DHS conducted in 2013 and 2018. MICS Surveys 2011 and 2016
IMPACT	Impact Indicator 1		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)
Women and men have access to a mix of quality contraceptives and use them	Contraceptive Prevalence Rate (modern)	Planned	9.7 (2008)		15 (20 = national target)		17.5 ( 26 = national target)		20 (30 = national target)
		Achieved
			Source
			DHS and MICS as above
	Impact Indicator 2		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)
	Number of states with a CPR of less than 15%	Planned	24 (2008)		20 states		15 states		10 States
		Achieved
			Source
			DHS and MICS as above
	Impact Indicator 3		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)
	Adolescent (< 19 yrs) birth rate	Planned	126 (2008)		120 (114 = national target)		117 (102 = national target)		114 (90 = national target)
		Achieved
			Source
			DHS and MICS as above

OUTCOME	Outcome Indicator 1		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)	Assumptions
Adequate quantities of appropriate mix of quality contraceptives procured and distributed	Couple Years of Protection (CYP) of commodities procured with DFID funds and distributed to public health facilities	Planned	1 million (2011 after programme approval)		1 million	1 million	1 million	1 million	1 million	6 million	*Targets based on contribution toward National Strategic Health Development Targets. The programme assumes National targets are over-ambitious. * Contraceptive prevalence rate increases are associated with maternal and infant mortality reductions (although not causal). *Concurrent substantial increase in quality and accessibility of child and maternal health services are required. However this intervention alone may reduce maternal mortality by at least 10% (as calculated from MSI standard indicator tool).
		Achieved
			Source
			Contraceptive Logistics Management System Assessment Report (annual)
	Outcome Indicator 2		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)
	Proportion (%) of service delivery points in 12 select states providing at least 3 methods of modern contraceptives	Planned	14% (2007)		15%	20%	25%	35%	50%
		Achieved
			Source
			Contraceptive Logistics Management System Assessment Report (annual)
OUTPUT 1	Output Indicator 1.1		Baseline		Milestone 1 (2012)	Milestone 2 (2013)	Milestone 3 (2014)	Milestone 4 (2015)	Milestone 5 (2016)	Target (2017)	Assumption
Effectively managed national contraceptive supplies and logistical management system	Proportion (%) of service delivery points in 12 select states with NO Stock outs of contraceptives for more than 7 consecutive days in 3 months	Planned	30% (2007)		32%	37%	42%	47%	52%		It is assumed that: * as supply increases, demand increases. * user fees in public services will be removed in line with new national policy. * correct contraceptive methods will be procured based on previous demand and survey information. * current trend toward greater cultural and religious acceptance toward contraceptives is maintained.
		Achieved
		Source
				Contraceptive Logistics Management System Assessment Report (annual)
						RISK RATING
						Medium
INPUTS (£)	DFID (£)			Govt (£)	Other (£)	Total (£)				DFID SHARE (%)
	£18 m			Not known		£18 M				100% (50% of all public sector contraceptive commodities)
INPUTS (HR)	DFID (FTEs)

OUTPUT 2

IMPACT WEIGHTING (%)

INPUTS (£)

INPUTS (HR)

ANNEX 1.

Population growth projections 2010-2100, using the UN Medium variant
DFID BAR and selected other countries.

Country	2010 Pop Estimate (m)	2025 Pop Projection (m)	2050 Pop Projection (m)	2100 Pop Projection (m)	2005-2010 fertility rate	Contraceptive Prevalence rate %	Unmet Need for FP %	2010-2100 Pop Growth Factor
Africa
DRC	66	95.4	148.5	212.1	6.07	21	24	3.21
Ethiopia	83	110	145.2	150.1	4.60	15	34	1.81
Ghana	24.4	33.4	49.1	67.2	4.34	24	35	2.75
Kenya	40.5	59.1	96.9	160.1	4.80	39	26	3.95
Liberia	4	5.8	9.7	16.5	5.42	11	36	4.13
Malawi	14.9	24.2	49.7	129.5	6.00	41	28	8.69
Mozambique	23.4	32.4	50.1	77	5.11	17	18	3.29
[Niger]	15.5	26.2	55.4	139.2	7.19	11	16	8.98
Nigeria	158.4	229.8	389.6	729.9	5.61	15	20	4.61
Rwanda	10.6	15.8	26.0	42.3	5.43	36	38	3.99
Sierra Leone	5.9	7.9	11.1	14.2	5.22	8	28	2.41
Somalia	9.3	14.2	28.2	73.0	6.40	15		7.85
South Africa	50.1	53.7	56.8	54.5	2.55	60	14	1.09
Sudan	43.5	60.8	91.0	127.6	4.60	8	26	2.93
Tajikistan	6.9	8.50	10.8	11.7	3.45	38		1.70
Tanzania	44.8	70.9	138.3	316.3	5.58	26	22	7.06
Uganda	33.4	52.3	94.3	171.2	6.38	24	41	5.13
Zambia	13.1	21	45	140.4	6.20	41	27	10.72
Zimbabwe	12.6	16.7	20.6	21.8	3.47	60	13	1.73
Asia
Afghanistan	31.4	47.6	76.2	110.8	6.62	19		3.53
Bangladesh [32]	148.0	175.2	194.4	157.10	2.38	56	17	1.06
Burma	48.0	53.2	55.3	46.9	2.08		19	0.98
[China] [33]	1341.3	1395.3	1295.6	941.0	1.64	87	2	0.70
Kyrgyzstan	5.3	6.3	7.8	9.3	2.70	48	12	1.75
India [34]	1224.6	1459.0	1692.0	1550.9	2.73	56	13	1.27
Nepal	30	37.7	46.5	45.0	2.95	48	25	1.50
Pakistan [35]	173.6	220.6	274.9	261.3	3.65	30	25	1.51
Other Areas
Occupied Palestinian Territories	4	6	9.7	14.9	4.65	50		3.73
Yemen	24.1	36.7	61.6	99.0	6.10	28	39	4.11
UK	62	67.6	72.8	75.7	1.83	82		1.22
Total, BAR countries, excluding India	1109.2	1495.2	2187.3	3259.7
[32] Bangladesh’s projected population peaks in 2050 at 194 million
[33] China’s projected population peaks in 2025 at 1395 million
[34] India’s population peaks in 2060 at 1718m
[35] Pakistan’s population peaks in 2065 at 285 m Key Documents: - Nigeria: Demographic and Health Survey – National Population Commission 2008 - National Strategic Health Development Plan; Federal Ministry of Health 2010. - Choices for women: Planned pregnancies, safe births and healthy newborns: The UK Framework for Results for improving reproductive, maternal and newborn health in the developing world. - The MSI Impact Calculator: Methodology and assumptions : Nick Corby, Tania Boler and Dana Hovig 2009

Note: China, Niger and UK included for illustrative purposes – not DFID BAR countries Sources: CPR and Unmet need for FP, from UNFPA – SOWP report 2009; all other data UN World Population prospects, 2010 revision: http://esa.un.org/unpd/wpp/index.htm.