## A1 Goal, Purpose, Risk
Project Completion Report (reviewed August 2010)
ARIES Project Code | 104186
ARIES Project Description
A1: Goal, Purpose, Risk
Goal
Goal statement | Significant positive changes in selected institutions leading to effective management of public resources and stronger formal accountability
Indicator 1 | Improved accountability and effective use of public resources
Target (if any) | No target
What progress was made? | C4C supported 8 Issues Based Projects (IBP) overall, with support to 5 continuing into the Extension Phase. One IBP, the Northern Nigeria Water Governance Initiative, made notable progress against this indicator achieving sustained improvements in water management in 6 northern States, including improved accountability and more effective use of public resources. Key achievements of other IBPs relate to policy advocacy (detailed under Purpose level evidence). Policy advocacy achivements might ultimately facilitate improved accountability and effective use of public resources, but within the lifetime of the programme did not directly impact on these aspects of change.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Goal Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Purpose
Project Purpose | Government and non Government actors in C4C focal sectors replicate improved ways of working for setting policy and managing resources
Indicator 1 | Formal agreements between supply and demand partners to work together on an identified issue, using an IBA
Target (if any) | Three formal written agreements between supply and demand side partners
What progress was made? | Formal written agreements between supply and demand side partners in all 5 Extension Phase IBPs
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Recognised change champions
Target (if any) | Four initiatives with change champions that are identified by partners
What progress was made? | All 5 Extension Phase IBPs have identified change champions
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Documented, socially inclusive change strategies in the new initiatives
Target (if any) | Three initiatives with a full set of change strategy documents (change strategies include workplan, budget, communications straregy etc.)
What progress was made? | All 5 IBPs have a full set of Change Strategy documents
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | Actors apply IBA
Target (if any) | Three or more instances of IBP members applying an IBA outside existing IBPs but within focal sectors
What progress was made? | At least 3 of the 5 Extension Phase IBPs report applying an Issues Based Approach outside C4C IBPs
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Were Purpose Assumptions realised? If so, to what degree, and what was the effect on the project? | The C4C Log Frame was rewritten for the 18 month extension phase. There are 3 assumpions: 1. Drivers of Change analysis - that institutional change will have structural impact - is correct, 2) political sensitivities do not lead to voice suppression, 3) Macro-economic factors (oil price, global financial crisis) do not unduly distort supply of public funds. In the Extension Phase, the 5 remaining C4C IBPs were either not working on issues where these assumptions directly apply, or their activities were yet to attain the profile where these concerns would come into play.
What evidence is there that achievement of the Purpose contributed or continues to contribute to the realisation of the Goal? If it has done so or is doing so, to what degree? | The C4C Log Frame was re-written for the final 18 month Extension Phase partly because the previous Purpose was unrealistic. The revised Purpose is realistic and achievable - and that has been beneficial for IBP planning - but there is now a gulf between the Purpose and the Goal. C4C's revised purpose indicators focus wholly on administrative targets which are fully achieved. However, these provide no basis on which to highlight let alone analyse outcomes and impact. Key C4C Extension Phase Purpose level achievements are: the Gender Affirmative Action (GAA) IBP achieved an effective and influential coalition of key gender actors at national level focused on women's political participation and the setting up of the Gender Technical Unit in the National Assembly; the Climate Change (N-CAN) IBP achieved an effective working relationship between national CS actors and National Assembly members on climate change, resulting in the passage of the national Climate Change Commission Bill and a strong Nigerian negotiating team on international climate fora; all IBPs contributed to openning up space for civil society to engage constructively with Government at national level, and great efforts were made to mainstream gender and disability across IBPs. These achievements contribute in a small way towards achievement of the C4C Goal.
What is the evidence that the achievement of the Purpose can be attributed to progress made in delivering the Outputs? | C4C Purpose level targets and indicators focus on administrative processes relating to IBPs, and are largely the same as the indicators for Output 2. As these targets and indicators do not focus on achievement, they provide no basis on which to judge the collective impact of delivering the Outputs.
Purpose Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Project Purpose Score | 3
Purpose Justification | C4C supported 5 IBPs in its Extension Phase. The Project Completion Review (report available) scored these: Gender Affirmative Action 1-2, Climate Change 1-2, Constitutional Reform Dialogue Mechanism 3, Action on Disability 3, and Accountability 5. 3 represents the average of these IBP scores.
Risk
Project Risk Rating or latest Overall Risk Score. | Low
Was the Project Risk Rating revised since the last review? | Yes
If Yes, why was this? | C4C Purpose level targets and Indicators are all adminstrative processes fully within the control of the project. The Project Risk rating has therefore been reduced from High to Low.
If new risks have emerged since the last review, click the '+' box on the left-hand side and list them in the appropriate boxes.
Risk Recommendation 1
If more Recommendations need to be made click the '+' box on the left-hand side.
Logframe, DSOs, Cross-Cutting Markers
Logframe revised since the last review? | Yes
If Yes, why was this? | The Log Frame was completely revised in March 2010, with the revised Log Frame used for managing the programme in the 18 month no cost extension phase
Logframe Recommendation 1 | DFID should exercise greater vigilance in approving Log Frames ensuring that they are fit for the range of purposes they are required to fulfil. This Log Frame is useful for administering project inputs, but provides no basis to record or analyse C4C's achievements, the changes it has succeeded in bringing about or the challenges it has faced.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
DSOs revised since the last review?
If Yes, why was this?
DSO Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Cross-Cutting Markers revised since the last review?
If Yes, why was this?
CCM Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Consensus by C4C, DFID and partners of the features required for successful implementation of IBPs
Has the Impact Weight been revised since the last review? | Yes
If Yes, why was this? | Log frame rewritten since last review. All Outputs changed.
Current Impact Weight (%) | 25%
Has the Risk been revised since the last review? | Yes
If Yes, why was this? | Log Frame completely revised in March 2010
Current Risk | Low
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator | Synthesis of success factors and features of Issues Based Approach (IBA)
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Synthesis document
What progress was made, including numbers | Synthesis document produced in April 2010.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Agreement on what is an Issues Based Approach and how it works
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Agreement on findings of the Synthesis document
What progress was made, including numbers | Agreement on Synthesis findings by IBP partners.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Output Performance for Output 1 | 3
Impact Weighted Score | #VALUE!
Justification for the Score | The IBA, as defined by C4C, focuses on demand and supply side players coming together to find solutions, on an issue people feel the need to do something about, and which if resolved can lead to positive change. It is evident from C4C's own experience that success is critically to do with how well this is done. The experience of successful C4C IBPs indicates that critical success factors include involving the right players (motivation, complementary skills etc..), time to nurture effective partnerships where these do not already exist, effective use of political intelligence and analysis, a clear theory of change. These, and other aspects of HOW, are not fully brought out in C4C's synthesis of IBA success factors.
Output 1 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Improved ways of working (ie. Issues based Approach) tested and validated by C4C IBPs
Has the Impact Weight been revised since the last review? | Yes
If Yes, why was this? | Log frame rewritten since last review. All Outputs changed.
Current Impact Weight (%) | 45%
Has the Risk been revised since the last review? | Yes
If Yes, why was this? | Log Frame completely revised in March 2010
Current Risk | Low
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator | Partnership: active engagement between demand and supply side players
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | All 5 IBPs "active"; shared workplans, clear supply and demand side roles and responsibilities, and deliver on workplans
What progress was made, including numbers | All 5 IBPs have workplans, including demand and supply side roles and responsibilities. 2 out of the 5 have fully delivered on their workplans.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Inclusiveness: socially marginalised voices respresented in issues
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 4 IBPs: marginalised groups say that they have access, opportunity and control in IBPs
What progress was made, including numbers | This has been partially achieved. C4C has made efforts to involve women and disabled people in all IBP Steering Committees. There is particularly positive feedback from disabled individuals involved in the GAA and CRDM Steeering Committees.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Effectiveness: achievement of IBP Outcomes
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | At least 4 out of the 5 IBPs score an equivalent of 1 or 2 using DFID's ARIES scoring systen.
What progress was made, including numbers | 2 IBPs (N-CAN and GAA) has scored an equivalent of 1 or 2. " (CRDM and ARPWD) have scored 3, and 1 (Ac) has scored 5.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Output Performance for Output 2 | 3
Impact Weighted Score | #VALUE!
Justification for the Score | The core C4C IBA was common to all IBPs (demand and supply side players coming together on an issue of mutual interest) - but some IBPs worked well, and others did not. C4C staff took a "hands off" approach to supporting IBPs ( in order to promote ownership and avoid donor imposed agendas). This worked well for IBPs building on pre-existing CSO campaigns, with highly competent, experienced and motivated demand and supply side partners. It worked less well for IBPs which needed more support - and was particularly challenging when seeking to support IBPs working on "toxic" issues, with massive vested interests, no history of demand and supply players working effectively together and no trust. C4C staff, highly competent in many areas, had no previous experience of facilitating innovative partnership working and no capacity building support in this area of their work.
Output 2 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Actors in focal sectors better understand improved ways of working (ie. Issues Based Approach)
Has the Impact Weight been revised since the last review? | Yes
If Yes, why was this? | Log Frame completely revised in March 2010
Current Impact Weight (%) | 30%
Has the Risk been revised since the last review? | Yes
If Yes, why was this?
Current Risk | Low
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator | Success stories shared
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | At least 5 communications training sessions for colaitions on messages and delivery mechanisms for key actors delivered
What progress was made, including numbers | C4C has delivered communications training to all IBPs. IBPs all have as their an agreed Result area, indicators and milestones on lesson learning and sharing, and all have held or plan to hold reflection events.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Best practices shared
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | At least 5 round tables convened bringing actors around the table to share best practices
What progress was made, including numbers | C4C has convened round table sessions on the IBA for media, Government, the private sector and young people.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Actors promote IBA
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Three or more instances of actors in IBPs driving the promotion of the IBA outside existing IBPs, but inside focal sectors.
What progress was made, including numbers | Gender Affirmative Action, Climate Change and Disability IBPs all report applying an Issues Based Approach to other initiatives
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Output Performance for Output 3 | 3
Impact Weighted Score | #VALUE!
Justification for the Score | C4C has devoted considerable time, resources and support to encourage IBPs to learn and disseminate lessons. Much of this material focuses on marketing the core elements of the C4C IBA (demand and supply side players coming together) which is not unique to C4C, and is not getting to the core of why some C4C IBPs work and others do not.
Output 3 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 4 is required, click on the '+' sign to the left of this worksheet
If Output 5 is required, click on the '+' sign to the left of this worksheet
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 6
Impact Weighted Score | #VALUE!
Justification for the Score
Output 6 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 7
Impact Weighted Score | #VALUE!
Justification for the Score
Output 7 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 8
Impact Weighted Score | #VALUE!
Justification for the Score
Output 8 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 9
Impact Weighted Score | #VALUE!
Justification for the Score
Output 9 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 10
Impact Weighted Score | #VALUE!
Justification for the Score
Output 10 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-10-16
Impact Weighting (must = 100) | #VALUE!
Total Impact Score | #VALUE!
Output Risk | #REF!
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant | X
Donor partners
DFID staff
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | C4C supported partner organisations to work together through an Issues Based Approach. The IBA, as defined by C4C, focuses on demand and supply side players coming together to find solutions, on an issue people feel the need to do something about, and which if resolved can lead to positive change. This core C4C IBA was common to all 8 C4C IBPs - but some IBPs worked well, and others did not. Success was critically to do with how well partners were able to use this opportunity. 3 IBPs were very successful. 2 of these built on long standing CSO campaigns and involved highly competent motivated partners. In the 3rd (Northern Nigeria Water) (which was in its 4th year of operation when taken on by C4C) project staff had spent the first 2 years of the programme bringing together demand and supply side partners, nurturing partnerships, ownership and new ways of working and overcoming a history of mistrust. C4C staff took a "hands off" approach to supporting IBPs (in order to promote ownership and avoid donor imposed agendas). This worked well for IBPs building on pre-existing CSO campaigns, with experienced partners. It worked less well for IBPs which needed more support - and was particularly challenging when seeking to support IBPs working on "toxic" issues, with massive vested interests, no history of demand and supply players working effectively together and no trust. C4C staff, highly competent in many areas, had no previous experience of facilitating innovative partnership working and no capacity building support in this area of their work.
Working with Partners Recommendation 1 | The IBA concept remains valid. Its potential was most fully demonstrated by the Water IBP, which was also the most successful IBP in terms of achieving positive progress towards the programme purpose/goal. Further exploration of lessons to be learned from Water (and its sister programme Wudil Water) may be useful to inform future DFID programming
If more Recommendations need to be made, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | One clear lesson emerging from the Water IBP is that it is critical for programme staff to have time and skills to nurture effective partnerships to drive change. C4C’s experience demonstrates that committing resources and pushing for results too quickly undermines longer-term effectiveness and value for money.
Working with Partners Recommendation 3 | In programmes seeking to promote innovation and new ways of working, staff need senior advisory support (in the role of critical friend) and good quality technical assistance to develop their skills in facilitating innovative and effective partnerships to drive change, and developing context specific theories of change.
2. Best Practice / Innovation | C4C made considerable efforts to mainstream gender and disability across their IBPs, particularly supporting the involvement of women and disabled people in the Steering Committtees of all IBPs. This experience was described as "wonderful" by individuals involved.
Best Practice / Innovation Recommendation 1 | C4C's experience demonstrates that the importance of leadership and monitoring in encouraging disability and gender mainstreaming - and provides a model that DFID could usefully apply to other project initiatives.
If more Recommendations need to be made, click the '+' box on the left-hand side.
3. Project Management | The C4C project team placed great emphasis on due diligence in their dealings with IBPs - focusing on effective systems for plannng, monitoring, financial management and reporting. However, DFID's initial requirement of Log Frames for all IBPs contributed to difficulties in IBP management. Log Frames had the effect of projectising support to embronic partnerships, committing tranche funding and raising partner expectations. This made withdrawal from poorly functionning IBPs very difficult. Additionally, the team struggled with defining appropriate indicators and milestones for advocacy initiatives. Too many indicators focused on activities, and provided no basis on which to judge quality, impact or value for money.
Project Management Recommendation 1 | Voice and accountability planning needs to pay careful attention to appropriate outcome, impact and quality indicators, a challenging area of work where practice is evolving. Project staff are likely to require technical assistance.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Project Management Recommendation 2 | Voice and accountability programmes require flexibility in planning frameworks and financial management. DFID should recognise this and ensure that Programme Officers are exposed to the realities of V and A planning and financial management (eg. through participation in reviews) and can work with project staff to develop appropriate and accountable systems.
Project Management Recommendation 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Evidence: Key documents
Quest No.
C4C and IBP Quarterly reports - Extension Phase
C4C 2009 Annual Review
C4C 2010 Annual Review
Evidence Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions were attached to this project, was disbursement suspended at any point because of the conditions?
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Sustainability
Comment on the likelihood of the benefits arising from this project being sustained beyond the end of project, and any challenges to sustainability.
Sustainability Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## E Recommendations
E: Recommendations
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Purpose
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Risk
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Logframe
R1 | DFID should exercise greater vigilance in approving Log Frames ensuring that they are fit for the range of purposes they are required to fulfil. This Log Frame is useful for administering project inputs, but provides no basis to record or analyse C4C's achievements, the changes it has succeeded in bringing about or the challenges it has faced. | DFID
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Cross-Cutting Markers
R1 | 0
R2 | #REF!
R3 | #REF!
A2: Outputs
R1.1 | 0
R1.2 | 0
R1.3 | 0
R2.1 | 0
R2.2 | #REF!
R2.3 | #REF!
R3.1 | 0
R3.2 | #REF!
R3.3 | #REF!
R4.1 | #REF!
R4.2 | #REF!
R4.3 | #REF!
R5.1 | #REF!
R5.2 | #REF!
R5.3 | #REF!
R6.1 | 0
R6.2 | #REF!
R6.3 | #REF!
R7.1 | 0
R7.2 | #REF!
R7.3 | #REF!
R8.1 | 0
R8.2 | #REF!
R8.3 | #REF!
R9.1 | 0
R9.2 | #REF!
R9.3 | #REF!
R10.1 | 0
R10.2 | #REF!
R10.3 | #REF!
B: Scoring
R1 | 0
R2 | #REF!
R3 | #REF!
C: Knowledge Sharing
Working with Partners
R1 | The IBA concept remains valid. Its potential was most fully demonstrated by the Water IBP, which was also the most successful IBP in terms of achieving positive progress towards the programme purpose/goal. Further exploration of lessons to be learned from Water (and its sister programme Wudil Water) may be useful to inform future DFID programming | DFID
R2 | One clear lesson emerging from the Water IBP is that it is critical for programme staff to have time and skills to nurture effective partnerships to drive change. C4C’s experience demonstrates that committing resources and pushing for results too quickly undermines longer-term effectiveness and value for money. | DFID
R3 | In programmes seeking to promote innovation and new ways of working, staff need senior advisory support (in the role of critical friend) and good quality technical assistance to develop their skills in facilitating innovative and effective partnerships to drive change, and developing context specific theories of change. | DFID
Best Practice / Innovation
R1 | C4C's experience demonstrates that the importance of leadership and monitoring in encouraging disability and gender mainstreaming - and provides a model that DFID could usefully apply to other project initiatives. | DFID
R2 | #REF!
R3 | #REF!
Project Management
R1 | Voice and accountability planning needs to pay careful attention to appropriate outcome, impact and quality indicators, a challenging area of work where practice is evolving. Project staff are likely to require technical assistance. | DFID
R2 | Voice and accountability programmes require flexibility in planning frameworks and financial management. DFID should recognise this and ensure that Programme Officers are exposed to the realities of V and A planning and financial management (eg. through participation in reviews) and can work with project staff to develop appropriate and accountable systems. | DFID
R3 | 0
C: Other Comments
R1 | 0
R2 | #REF!
R3 | #REF!
C: Evidence
R1 | 0
R2 | #REF!
R3 | #REF!
D: Conditionality
R1 | 0
R2 | #REF!
R3 | #REF!
D: Sustainability
R1 | 0
R2 | #REF!
R3 | #REF!
Additional Recommendations arising
R1
R2
R3