Business Case and Intervention Summary

Intervention Summary

## Title: School Feeding - Supporting access to primary education for vulnerable children

What support will the UK provide?
As part of DFID Sierra Leone’s wider education programme, this intervention will improve access to primary education in the most vulnerable communities across the country. In order to increase enrolment and retention in school, particularly for girls, the preferred option for intervention is to support the UN’s World Food Programme to deliver an expanded school feeding programme in line with the Government of Sierra Leone’s Education Sector Plan (ESP). / How much funding does the UK expect to provide? / £5 million / Period of funding? / Over three academic years: October 2011-June 2012, 2012/2013, 2013/2014.

Why is UK support required?
What need are we trying to address? / The decade-long civil war in Sierra Leone ended in 2001 leaving behind a shattered country. The education sector particularly suffered, with the death and displacement of key personnel, the collapse of systems and the destruction of schools and colleges. Over the past ten years there has been significant progress in rebuilding the sector, one consequence of which has been the doubling of enrolment into primary schools to 1.4m children in 2010. / While enrolment has seen significant expansion, a major challenge is how to then retain those children once in school. An estimated 240,000 children of primary school age are out of school[1] and that figure may well be an under-estimate. Drop out rates are exceptionally high with only 47% of girls and 64% of boys entering primary school being able to complete all 6 grades.[2] Not only is this an extremely inefficient use of scarce national resources, but by failing to educate almost half of the country’s children to primary level, the prospects for a literate, healthy, prosperous and stable Sierra Leone are undermined. / The main reason for such high drop out rates is poverty. Immediately after the war, primary school fees were abolished, in theory making education free of charge. In practice, however, the majority of parents still continue to pay for their children to go to school in both direct and indirect costs (charges for extra lessons, fees for exam results and registration etc.). These charges and fees are often the only way unpaid or community-employed teachers can maintain themselves, but they do place a considerable additional burden on households resulting in many children dropping out or not enrolling at all. Traditionally, poorer households have focused their limited resources on educating their sons rather than their daughters, resulting in the far higher illiteracy rates amongst girls and women. / With 75% of the Sierra Leonean population living on under $2 a day, economic shocks seriously impact household expenditure on basic services, including education. The 2008 food crisis, like previous periods of economic stress, saw increasing numbers of children dropping out of school across the developing world as poorer families were forced to de-prioritise education.[3] Fuel and food prices in 2011 have already exceeded the levels of 2008[4] and are threatening to have a similar impact on households in Sierra Leone, undermining progress and further exacerbating the high drop out rates, particularly for girls. / A school feeding intervention is in effect a social transfer of around 10% of household expenditure per child. Take home rations for families may equal up to 50%. Given the rising cost of food and the existing $17 per child per year in education costs, this intervention would reduce household expenditure on food, allowing families to continue investing in core basic services such as education. / The aim of this intervention is therefore two fold: to improve school enrolment and retention; and act as an education and social safety net in the most vulnerable communities. / What will we do to tackle this problem? To address these needs, the DFID programme will have two elements. The first element (2011-1214) will support the World Food Programme (WFP) to reach 400,000 of the most vulnerable children in Sierra Leone, providing a hot meal each school day. The beneficiaries were identified through a comprehensive vulnerability assessment that WFP undertook in late 2010, identifying the 56 (of 150) chiefdoms across the country with the worst education, gender, food security and poverty indicators. In addition, DFID assistance will support a pilot of take home rations for 1,500 girls in two chiefdoms with particularly poor gender ratios in education. If the pilot is successful this will be scaled up to 3,500 girls in 2012. These measures will help to boost enrolment and retention within schools by changing the incentives around education for children and poorer households. / In the Poverty Reduction Strategy Paper (An Agenda for Change 2008-2012) and the Education Sector Plan 2007-2015, the Government of Sierra Leone (GoSL) has made universal primary education a key priority for the education sector. It has identified school feeding as a main mechanism to raise enrolment and completion. In the second element (2012-14) of the intervention therefore, WFP and its delivery partners will work with the local and national authorities in a transition to a more Government-owned and managed school feeding programme. / Who will be implementing the support we provide? / The implementing partner will be WFP which has an existing school feeding programme which currently reaches 250,000 children in Sierra Leone. DFID will support WFP to scale up this programme and fully implement the recommendations in the 2009 WFP evaluation, particularly on targeting and monitoring. WFP will work with four Non-Governmental Organisations (NGOs) in delivering the programme: PLAN International, World Vision, AfriCare, and Catholic Relief Services. These partnerships allow the school feeding to be more closely monitored and supervised than WFP would be able to do alone. The NGOs are also able to ensure that the school feeding and other local education and community projects are mutually reinforcing. / WFP works with the Ministry of Education, Science and Technology (MEST) School Feeding Coordination Unit and its representatives at the District level as well as District Councils who have responsibility for many aspects of primary education. The school feeding programme is also part of the wider UN-GoSL Joint Vision for Sierra Leone. / Are any other donors supporting this or similar programmes? / This is the only national school feeding programme in Sierra Leone. Over the three academic years in which DFID will provide support (2011/12, 12/13 and 13/14) the total cost for WFP school feeding programme is £15,897,000 of which DFID’s contribution constitutes 31%. In addition to DFID funds for 2011/12, Irish Aid (£1.7m), the UN Joint Vision Fund (£610,000) and a contribution from the World Bank will meet the needs for this academic year. For subsequent years, similar contributions are expected and on the basis of funding in previous years’ programmes, WFP expects that the existing programme can be sustained through other donor funding and then expanded with DFID funds.
[1] Education in Sierra Leone: Present Challenges, Future Opportunities, World Bank 2007, p. 48
[2] Education Sector Plan 2007-2015, Government of Sierra Leone, 2001, p.23
[3] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.2
[4] World Economic Situation note 35: Summer Turbulence, DFID (internal document), September 2011, p.4.

What are the expected results?
Based on experience from similar contexts, WFP expect enrolment to increase by 8% and completion to increase by 10% each year in schools receiving school feeding. In a stable economic environment this would equate to at least 30,400 additional years of education attributable to DFID although the real figure is likely to be much higher because of the role of school feeding in preventing increased drop out rates due to economic pressures. Reliable data is scarce so this will be assessed in the yearly evaluations. Also during the life time of the project 29,700 children will complete primary school supported directly by DFID. These results will contribute substantially to the DFID Sierra Leone’s Operational Plan targets. / DFID will be supporting 110,000 children each year for three years. In addition, the piloting of the take-home initiative is also expected to see the retention and completion rate of the 1,500 (and potentially 3,500) beneficiaries rising from 47% to 95%. / Given the uncertainties caused by lack of reliable data, an analysis of just the additional enrolment expected demonstrates that this intervention represents good value for money with a Present Value Benefit of £11m on the investment of £5m. / By indirectly transferring around 10% of household expenditure per beneficiary child, the School Feeding Programme would also constitute a social protection mechanism that would extend to 110,000 children and their families in the poorest chiefdoms across the country – potentially reaching up to 400,000 indirect beneficiaries a year. / Take home ration packs that feed a family of 5 will directly benefit a further 17,500 people. / WFP aims to procure 10% of the total food requirement (7,200 metric tonnes per year) locally through the Purchase for Progress (P4P) initiative with direct benefits for smallholder farmers’ groups and boosting local food production and stimulating economic activity. This supports wider GoSL agricultural growth plans and is a key requirement for a sustainable nationally-managed school feeding programme in future years. Small scale production and unreliable supply make this aspect a challenge but WFP has successfully increased its local produce over the past two years from nothing to 370 tonnes, so the target of 720 tonnes is a significant but achievable increase. / The programme will have a thorough baseline established in 2011 and an independent evaluation each subsequent year.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Context / The decade-long civil war in Sierra Leone displaced hundreds of thousands of people and disrupted the lives of many more. The provinces had been neglected in terms of service provision, including education, before the conflict and the war then compounded this with the destruction of schools and colleges, particularly in the North and East. A generation either missed out on education entirely or had their schooling interrupted or truncated. The whole system of training and replacing qualified civil servants for the Ministry, teachers and school inspectors broke down as the reach and capacity of the central Government deteriorated. / Since the war ended in 2001, GoSL has made good progress in re-building this shattered education system. The abolition of primary school fees, school construction programmes, support from development partners and political support for education have all had an impact: / Primary enrolment has more than doubled to 1.4 million; / Education spending as a share of the Government’s recurrent budget has been around 20% consistently since 2009; / The number of primary schools has increased from 4,261 in 2005 to 5,930 in 2010. / In common with other countries experiencing rapid expansion in education, however, Sierra Leone’s fragile education system has struggled to expand enrolment at the same time as ensuring retention and good quality education for all. There are three main challenges facing basic education at the current time: Sector capacity; quality of education; and retention and completion in primary schools. / Sector capacity: The sector as a whole is characterised by a lack of trained personnel and weak supervision and performance management systems. MEST, for example, has been carrying over 200 vacancies but has lacked the experienced candidates and money to fill them. Around 40 senior positions have recently been filled but the Ministry’s capacity remains weak at both central and District levels. The impact of this is seen in the continual implementation delays and problems on Ministry-managed programmes such as the Education for All Fast Track Initiative (EFA-FTI) and the Swedish aid grants. Data collection and analysis remains very weak which impedes sector planning and prioritisation. UNICEF has funded a capacity development strategy for education which will analyse the gaps and means for addressing them. If MEST demonstrate clear ownership and drive behind this initiative, DFID will consider supporting this strategy during the Operational Plan period. / Another aspect of the sector capacity is the teacher corps. With the expansion of schools and the legacy of the war, up to 40% (8,000) of current primary school teachers are unqualified and untrained. With lengthy Government procedures and low and sporadically paid salaries, the great majority of new teachers graduating from teacher training colleges leave the profession within four years.[5] Many of the trained teachers opt for urban schools as do most of the 25% of primary school teachers who are women.[6] This has a significant impact on the quality of education and girls’ participation in rural areas. DFID will work with UNICEF and MEST on a parallel intervention to support the professionalisation of the teaching corps. / Quality of education: In terms of the quality of what children are actually learning in school, there is very limited data available. A study on numeracy found that the mean score for simple addition tests for boys and girls in Sierra Leone in Grade 3 was 56% and 53% respectively. This compared to 74% for both boys and girls in Liberia and 70/67% in Ghana.[7] Small scale literacy assessments indicate similar concerns. To begin to address these issues, there is a need for more evidence and data. A nationwide reading and numeracy learning assessment is therefore planned for late 2011 through the EFA-FTI. In parallel DFID will fund another intervention looking at school and classroom management and accountability. This will focus heavily on teacher training, looking at improving the way reading is taught and the use of child-centred teaching methods as well as how children and schools are supported and encouraged by the community. / Access: While there are concerns around the education system and the quality of the education provided, this intervention will focus on the third major challenge, that of access. The results from this intervention will therefore contribute to several of the DFID Sierra Leone Results Framework indicators for education, notably: / - Number of girls and boys surviving to grade 6 in Primary School (proxy for quality) / - Numbers of girls and boys enrolled in primary school in Grade 1-6 / It will also exceed the 2014/15 target in DFID’s Result Framework for Sierra Leone of 16,800 additional children completing grade 6 in vulnerable communities due to nutritional support programmes. / Despite the expansion in primary enrolment over recent years, only 47% of girls and 64% of boys finish all 6 grades of primary school. There is considerable geographical disparity in the overall rate, with the Northern Province rates dropping to 47% for boys and 29% for girls, while Kono District in the Eastern Province has rates as low as 42% and 22%.[8] These figures indicate both the scale of the overall challenge in Sierra Leone but also the specific problem facing girls, particularly in rural areas. / Although this programme will not be exclusively focused on girls, they are likely to benefit most from the programme given the higher drop out rates. The targeted take home rations, however, will focus only on girls in particularly marginalised areas. DFID’s overall goal is for every girl and every boy to have access to a good quality education but girls face gender-specific obstacles to enrolling, remaining in school and learning effectively. One aspect of this will be tackled through another DFID intervention by providing water facilities and separate latrines for girls and boys in up to 2,000 primary schools as well as a menstrual hygiene campaign. Educating girls also has additional developmental benefits which in the longer term will benefit the next generation of both boys and girls. Evidence shows that: / At the individual level, an educated girl is likely to increase her personal earnings potential, be more likely to delay marriage and pregnancy, and be more likely to access health support leading to lower rates of maternal mortality.[9] / At the family and community level, more educated girls have fewer, healthier, and more educated children. Investments in girls’ education can reduce the incidence of poverty at a community level. [10] / At the wider societal level, more educated girls lead to improvements in national economic growth, an increase in female leaders, and lower levels of population growth and the subsequent reduction of pressures of climate change.[11] / Whilst the quality of the education received is a key factor, where nearly half of all children are dropping out of primary school, the medium to long term prospects for a healthy, prosperous and stable Sierra Leone are seriously undermined. A system which has high enrolment but also such high drop out and repetition rates is also hugely inefficient for the resource-strapped Government of Sierra Leone. / Although there are a number of factors contributing to the high drop out rates, a recent study found that the major underlying factor is poverty: ‘for the 80% of the poor living in rural communities, education is not a priority and households are often faced with the choice between putting food on the table and sending their child to school’.[12] School fees were formally abolished in 2001 but putting a child through primary school is still a costly investment for a household. In Sierra Leone, around 75% of the population live on less than $2 a day, and 57% on less than $1 a day. In the context of this level of poverty, the direct and indirect costs to education have been estimated at $17 per child per year.[13] Over 60% of households report paying charges for registration and exam results and around half of households report having to pay for sports lessons, Parent-Teacher Association fees, obligatory ‘gifts’ to the teacher and extra lessons.[14] / The willingness to invest in sending the household’s children to school is dependent on the balance of benefits and costs. Indications are that the value attached to education is still relatively low, especially in rural areas, with a third of children reporting their parents had a negative attitude to education.[15] This is seen as linked to the extremely high rates of adult illiteracy with 74% of women and 55% of men illiterate. In rural areas the rate increases to 89% and 73% respectively.[16] The high drop out rate means that many children fail to reach a functional level of literacy, which contributes to the perpetuation of this inter-generational poverty trap. / The balance of education costs and benefits for households is precarious and, in a country as poor as Sierra Leone, it is especially vulnerable to economic shocks. Over the past 18 months food and fuel commodity prices have risen above the ‘crisis’ level of 2008 which triggered a global response.[17] There has been little focus on the impact of the current crisis, but in Sierra Leone, the consequences for poor people are clear: / Food item Price increase Food item Price increase / Rice (imported) 14% Eggs 36% / Rice (local) 12% Bread 37% / Groundnut oil 41% Sugar 23% / Bongo (dried fish) 80% Cassava 16% / Source: Understanding commodity prices in Sierra Leone, Ministry of Finance and Economic Development, GoSL, May 2011. / Of household expenditure, spending on food constitutes 41%, rising to 53% in rural areas and significantly more for low income households.[18] Such price rises have a major impact on household budgets and priorities. Like previous economic shocks, the food price crisis in 2007/08, followed by the global recession, saw many households in developing countries reduce expenditure on education and reduce the number of meals the family consumes, leading to significant impacts on school retention and the cognitive abilities of young children.[19] The potential impact of this is compounded in Sierra Leone where an estimated 1.8 million people (35% of the population) are already undernourished, the highest proportion in West Africa.[20] / This intervention will provide an incentive for children and households to invest in education (element 1) and enhance the Government’s ability to manage and sustain the programme (element 2). It will both improve the enrolment of children into school and improve the retention and completion rates of those within education. / The policy context / The global level / Sierra Leone is committed to achieving MDG 2 to ensure that all children can complete a full course of primary school and MDG 3 on eliminating gender disparity in primary and secondary education. The Government of Sierra Leone’s own analysis indicates that it is unlikely to meet the targets by 2015,[21] but, together with its development partners, it remains committed to making significant progress over this period and continuing to do so until the objectives are met. / DFID priorities DFID’s Business Plan 2011-2015 commits DFID to continue its efforts towards the achievement of the MDGs, including education. Recognising the role of women in development, it also pledges to undertake new programmes to help to increase the number of girls completing primary and secondary education. DFID’s Gender Vision has a similar theme, with the ‘progression of girls through secondary school’ as one of the four key pillars to achieve transformation in the lives of girls and women. / DFID Sierra Leone’s Operational Plan 2011-2015 has a strong emphasis on helping Sierra Leone achieve progress on the MDGs, including MDG 2 and MDG 3. The MDG pillar in the Operational Plan comprises of interventions in health, water and sanitation and education. These programmes have been designed to maximise the synergies between the sectors and track the subsequent results. For example education, particularly of girls, has long term benefits for reproductive and child health. Likewise providing clean water, vaccinations and deworming campaigns can increase school participation and attainment. School sanitation can also both reduce ill health and improve girls’ attendance. This intervention fits within the wider DFID programme of support to improve the life chances for all Sierra Leoneans. / The DFID Sierra Leone 2011-15 education programme is being developed but the impact and overall design was agreed through the Bilateral Aid Review process, culminating in the Operational Plan. It will have two main themes initially: improving quality of education through teacher training and management and school development and accountability; and promoting access to education. This intervention will form a substantial element of the latter area of work, seeking to get children into school and enable them to complete primary school, particularly girls and those in poor areas. Tackling what they learn whilst they are there is the focus of the other theme. In 2012/13, DFID will look to support MEST strengthen its processes, capabilities and structures through technical assistance. This will complement WFP’s work to build the capacity within MEST to manage the school feeding programme. / This intervention is also relevant to another of DFID’s objectives, namely economic growth and wealth creation. Under the first (and preferred) option set out below, the intervention will procure 302 tonnes of foodstuff each year, part of the 702 tonnes WFP aims to locally procure annually for the school feeding programme. / National policy / The Government of Sierra Leone has set out its objectives within the Poverty Reduction Strategy Paper (PRSP), An Agenda for Change 2008-2012. One chapter focuses on the need to expand and commercialise the agricultural sector, to which the local procurement for school feeding would contribute. In the chapter on human development, the PRSP highlights the challenge of access to education: ‘Some 30% of children of primary school-going age are still out of school. Many of those who eventually access schooling do not complete. Getting all children to access and finish schooling are phenomenal challenges which should be addressed effectively’.[22] To address this strategic priority, the PRSP identifies WFP’s contribution through school feeding and calls for its expansion: / ‘In the medium term, the Government will extend school feeding programmes to other schools in all districts. In addition take-home ration given as incentive for increasing attendance rate for girls will be promoted. Schools located in the most vulnerable settlements would be targeted as a matter of priority. The extension of the School Feeding Programme for Sierra Leone will improve the health of the children and have a positive impact on the access, retention and eventually the overall quality of education in the country.’[23] / At the sector level, MEST’s strategy is detailed in the 2007-2015 Education Sector Plan (ESP). Achieving universal primary education and completion is a key priority for the sector and while the ESP flags recent increases in enrolment, it also notes the high drop out rates and numbers of out of school children as major sources of concern. To tackle this, it sets out a number of strategies including enforcement of legislation, making primary school mandatory, improving school infrastructure and reducing the teacher/pupil ratio. To address the illegal fees being charged, there are two major initiatives which will have an impact on this area. Firstly, the teacher verification process currently underway should ensure that the Government teachers’ payroll is clean and that teachers in schools receive salaries. The other is DFID’s proposed intervention supporting school and teacher accountability through working with School Management Committees and Parent-Teacher Associations as well as piloting community report cards and supporting MEST’s school supervisors and inspectors. The ESP also explicitly states MEST’s priority to expand school feeding to ‘not only encourage the children to access school but to stay without absenting themselves for lack of food. This [will] help to improve primary completion’.[24] / While school feeding is a clear policy choice for the Government of Sierra Leone, the recent economic shocks have led it being seen both as an education tool and also as a social safety net. In May 2011, GoSL asked donors to support the expansion of safety nets to mitigate the impact of the food and fuel price rises. The World Bank undertook to investigate the options for a long-term safety net programme but such a mechanism is unlikely to be established in the next two to three years. In the short term, the options for scaling up safety nets are limited to school feeding and cash for work schemes. / The Government’s draft National Policy Framework for Social Protection outlines the need for increased focus on mechanisms that support access by vulnerable women, infants and children to health and education. It specifically mentions school feeding and the need to ‘ensure a uniform application of such programmes across all districts, using criteria that ensure that the most vulnerable are targeted.’[25] The WFP targeting methodology provides this type of national framework and while it focuses at the level of vulnerable chiefdoms rather than individuals, it does ensure that there is consistency across the country. / Peace building: The lack of affordable and accessible basic services outside the capital, including education, was identified as one of the underlying causes of the civil war. Rebuilding the education system country-wide to give children and youth greater opportunities and a sense of social inclusion and responsibility was therefore a key recommendation of the Truth and Reconciliation Commission’s report.[26] Although the situation has improved significantly over the last decade in terms of service provision, the educational indicators still reflect disparities between the capital and the more remote provinces where the conflict began. For example, the Northern and Eastern Provinces have lower rates of female enrolment, lower exam pass rates, and pupil/teacher ratios are around 50% higher than in the Southern and Western Provinces.[27] / This intervention will work nationwide but will be focused on the most marginalised chiefdoms and those with the lowest rates of education participation. It therefore fits within the wider DFID strategy to expand basic service provision across the country and in doing so reduce the geographical disparities and strengthen the state-citizen relationship. / Evidence base / There is robust evidence for the wide ranging benefits for the individual and society in improving the level and quality of education, particularly for girls: / Economic impact / Studies have revealed that adding one year to the average number of years schooling of the population can add 0.3% or more to the economy’s growth rate.[28] After allowing for the costs of achieving such an increase, this is equivalent to an economic return of 20% or more. / Private returns (lifetime income differential) on completing primary education is estimated at around 26% for low income countries while the social return (benefits of having an educated individual in society) are around 21%.[29] / Health impact / A one year increment in a mother’s education leads to a 9.5% reduction in mortality of children under 5.[30] / Women in Sierra Leone with no education give birth to almost twice as many children as women who have been to secondary school (5.8 births, compared with 3.1 births) and uneducated teenagers (15-19 years old) are three times as likely to have begun childbearing as those with a secondary or higher education.[31] / Every extra year of schooling for a mother reduces the risk of having stunted children by 5%.[32] / Children’s nutritional status is negatively affected by women’s low status when they ‘tend to have weaker control over household resources, tighter time constraints, less access to information and health services, poorer mental health, and lower self-esteem.’[33] Girls’ education is crucial to breaking this cycle. / Estimates of GDP lost to malnutrition range from 2–3% in many countries to 11% in some Central American countries.[34] / The National Audit Office report in 2010 on DFID’s Bilateral Support to Primary Education, also noted that the presence of school feeding programmes strongly correlated with high attendance in primary schools.[35]
B. Impact and Outcome that we expect to achieve / The impact of this intervention would be to improve the life chances of vulnerable children through increased lifetime income and improved health and healthier offspring that result from additional years of education. / With 240,000 primary school-aged children out of school and the risk of an increased drop out rate because of the increasingly difficult economic environment, this intervention will target up to 110,000 of the poorest children in Sierra Leone to ensure that they are drawn into primary school and enabled to continue studying once there. / The outcomes are: / to increase the primary completion rate of boys (64%) and girls (47%) within the targeted schools (rate of increase dependent on the option); / to raise primary school enrolment within the targeted communities; / to build the capacity of the Government of Sierra Leone and MEST to plan, manage a deliver an education-focused safety net scheme; / Provide a social protection mechanism for 110,000 children and their families, potentially indirectly supporting 400,000 people each year. / to improve the economic rationale for education in low income households. / Intervention Results Chain / Input / - Funding £5m / - 2,016 tonnes of food / - Personnel time for delivery and monitoring / Process / Outcome / Output / Impact / - 110,000 children receive daily hot meal at school / - 1,500 girls receive take home ration / -GoSL capacity to manage programme strengthened / - Completion of primary school increases by 10% / - Enrolment increases by 8% / - GoSL takes over delivery for x% schools / - Increased local food supply / - Increased lifetime earnings / - Improved maternal and child health / - Increased literacy rate / - Increased economic growth in agriculture / -Food procured (90% international, 10% local) / - Food distributed to schools / - Training GoSL staff / - Pilot Take Home Rations
[5] Addressing Challenges at a Time of Rapid Change; The 2010/11 Education Sector Review Report, June 2011, Government of Sierra Leone, page 45
[6] Ibid. p. 40
[7] Making the grade: Assessing literacy and numeracy in African countries, DIME, World Bank, 2010.
[8] Education Sector Plan 2007-2015, Government of Sierra Leone, 2007, p.140
[9] Gender inequality, income and growth: are good times good for women, Dollar David and Roberta Gatti, World Bank, Gender and development working paper series, number 1, 1999, http: //www.worldbank.org/gender/prr, Returns to Investment in Education: A Further Update, G. Psacharopoulos. and H. Patrinos, Policy Research Working Paper No. 2881, World Bank, 2002.
[10] Growing Up Global: The Changing Transitions to Adulthood in Developing Countries; National Research Council (NRC)/Institute of Medicine, 2005 and Moving Forward With Girls’ Education in the World Bank: The Changing Context and What It Means for the Future. World Bank 2007
[11] The Economics of Population Policy for Carbon Emissions Reductions in Developing Countries, D. Wheeler and D. Hammer, Working Paper 229, Centre for Global Development, 2010.
[12] Barriers to Education: The Out-of-school Children of Sierra Leone, UNICEF, 2008, p. 29
[13] Primary Education in Sierra Leone: The State of Quality & Access, Evaluation Unit, Institutional Reform and Capacity Building Project, Ministry of Finance, GoSL, 2009
[14] Service Delivery and Perception Survey, Center for Economic & Social Policy Analysis, Sierra Leone, 2007, p18-19.
[15] Barriers to Education: The Out-of-school Children of Sierra Leone, UNICEF, 2008, p. 31
[16] Demographic and Health Survey 2008, Government of Sierra Leone, 2008, p. 36
[17] World Economic Situation note 35: Summer Turbulence, DFID (internal document), September 2011, p.4.
[18] Understanding commodity prices in Sierra Leone, Ministry of Finance and Economic Development, GoSL, May 2011.
[19] Education for All Global Monitoring Report 2010, UNESCO, pp. 166-167
[20] State of Food Insecurity in the World 2010, UN Food and Agriculture Organisation, p.17
[21] Millennium Development Goals: Progress Report 2010, GoSL, 2010, p. 11
[22] An Agenda for Change, GoSL p. 79
[23] An Agenda for Change, GoSL p. 80
[24] Education Sector Plan 2007-2015, Government of Sierra Leone, 2007, p.23
[25] National Policy Framework for Social Protection (draft) GoSL, 2011
[26] Witness to Truth: Report of the Sierra Leone Truth and Reconciliation Commission, Volume 2,2004. http://www.sierra-leone.org/TRCDocuments.html pp. 21, 99.
[27] Education in Sierra Leone: Present Challenges, Future Opportunities, World Bank 2007, p. 73
[28] Do Better Schools Lead to More Growth? Cognitive Skills, Economic Outcomes, and Causation, Hanusek and Woessman NBER Working Papers 14633, National Bureau of Economic Research, 2009, Table 14; see also Gender inequality, income and growth: are good times good for women, Dollar David and Roberta Gatti, World Bank, Gender and development working paper series, number 1, 1999, http: //www.worldbank.org/gender/prr
[29] Returns to Investment in Education: A Further Update, G. Psacharopoulos. and H. Patrinos, Policy Research Working Paper No. 2881, World Bank, 2002, Table 2, p. 14
[30] Increased educational attainment and its effect on child mortality in 175 countries between 1970 and 2009: a systematic analysis, E. Gakidou et al, The Lancet, vol. 376, September, 2010.
[31] Demographic and Health Survey 2008, Government of Sierra Leone, 2008, p. 55
[32] State of Food Insecurity in the World 2010, UN Food and Agriculture Organisation. 2010, p. 22
[33] The importance of women’s status for child nutrition in developing countries, Smith et al/IFPRI, 2003, cited in The neglected crisis of undernutrition: DFID’s strategy, DFID, 2010, p. 19
[34] Repositioning nutrition as central to development: a strategy for large-scale action. World Bank. 2006, cited in State of Food Insecurity in the World 2010, UN Food and Agriculture Organisation, p. 32
[35] DFID: Bilateral Support to Primary Education, National Audit Office, 2010, p.42

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / DFID Sierra Leone’s education programme will comprise several interventions tackling different aspects of the education system. This holistic approach will ensure that progress in basic education will be broad-based and can be sustained. In parallel to this intervention, DFID is developing a programme on teacher training and management and a programme to improve learning outcomes and accountability in schools. There will also be an intervention to expand water and sanitation facilities to primary schools under DFID’s Water and Sanitation Programme. DFID’s strong support to the Free Health Care Initiative (FHCI) and the provision of bednets has improved the treatment and prevention of common diseases which keep children from school and impact early cognitive development such as diarrhoea and malaria. / This proposed intervention, for which £5m has been allocated under the Operational Plan, focuses on access to education. The objective is to ensure that children in vulnerable communities enrol and complete primary school by changing the cost-benefit relationship of education to households. While seeking to expand school participation, the intervention is also designed to safeguard gains already made in the face of rising food costs. In order to do this, two primary options have been identified one based around food inputs and one on cash inputs. / For all potential interventions, the high risk of corruption and mismanagement in Sierra Leone needs to be a paramount consideration. The 2011 DFID Fiduciary Risk Assessment found the risk was ‘High’ in three social sector Ministries, including MEST. This risk can be managed by good design of programmes, particularly in the choice of partners and ensuring sufficient safeguards and adequate monitoring are in place but this does raise the complexity and costs of interventions. / OPTION 1: SCHOOL FEEDING / Intervention / The UK would support the UN’s World Food Programme (WFP) to scale up its existing school feeding programme. It would also pilot and potentially scale up a sub-component focused on increasing girls’ completion through take home rations. The intervention would involve WFP in working with MEST’s School Feeding Coordination Unit to increase capacity with a view in the medium term to transferring the programme to GoSL ownership. Given local supply constraints 10% of total requirements will be procured locally, the rest of the foodstuffs would be purchased on the international market. / Cost: The cost would be £5m over four years. / The rationale / The international evidence on the beneficial impact of school feeding on enrolment and attendance is strong, especially when combined with other interventions aimed at improving access and quality of education.[36] In Sierra Leone, school feeding would be complemented by and enhanced through DFID and other interventions in the sector. For example, UNICEF fund an annual de-worming campaign amongst school children, a modality widely acknowledged as a cost effective way to increase cognitive abilities and improve school attendance.[37] Likewise, DFID’s provision of water and sanitation facilities, support to the FHCI, training 8,000 teachers and work on school accountability and management will cover many of the same chiefdoms as the school feeding. WFP’s NGO implementation partners also run a number of projects in the areas in which they are delivering school feeding which will maximise the impact of the school meals. For instance, PLAN runs an integrated community and education development programme which supports teachers and School Management Committees, identifies and supports vulnerable children and improves school environments. Another major programme which is relevant is the national early childhood health and nutrition programme supported by USAID and Irish Aid which recognises the importance of nutrition in early childhood to subsequent educational attainment. / On school feeding itself, there is considerable comparative evidence about the results possible. In Kenya a randomised control trial saw school meals increase attendance by 30%, while an evaluation of the Global Food for Education initiative, delivered by the WFP in 38 countries, saw a rise in enrolment of 10% for boys and 12% for girls.[38] A review of 18 recent evaluations and random control trials on school feeding also pointed to increased attendance of 4-6 days per academic year.[39] Predictably, the impact of school feeding is greater in low income countries, where the food provided has greater value to households and children.[40] / Although nutrition in early childhood (pre-school) is the crucial period for cognitive development, some studies have shown that better nutrition of primary school children is linked to improved concentration and performance in tests.[41] While school feeding may contribute to better nutritional status, factors outside the school – health, hygiene and other sources of food – are also key determinants. The evidence for school feeding directly raising educational achievement is generally limited, hence DFID’s holistic approach under the MDG programme pillar to address health, WASH and other determinants and to work closely with partners such as USAID and Irish Aid on early childhood nutrition. / School feeding is also often deployed as a social safety net as well as its direct impact on education outcomes. School feeding, on average, provides a transfer of up to 10% of household expenditure per beneficiary child through the value of the food provided.[42] This is particularly significant given that many families will have more than one child benefiting from school feeding. The ratio increases further if take-home rations are used. In the case of Sierra Leone, piloted take home rations are designed to feed a family of 5 for a month, potentially representing 50% or more of a low income household’s monthly expenditure.[43] In the light of the current economic pressures on households in Sierra Leone, school feeding can reach a large number of households, providing significant support through explicit (in the case of take-home rations) and implicit (though school meals) transfers. / For a social safety net to be effective it needs to correctly identify and target the poorest and most vulnerable people in the country. A household approach can be more accurate but due to risks of stigmatisation, migration and the complex and costly logistics, school feeding is often targeted at whole geographical areas. This means every child in those schools will benefit whatever their household income level. Evidence suggests, however, that school feeding that focuses on a relatively low proportion of the total number of children in education (WFP in Sierra Leone would target 35% of primary children) and concentrate this assistance in the poorest areas, limits the ‘errors of inclusion’ i.e. feeding wealthier children.[44] / Recent World Bank analysis indicates that overall such school feeding programmes are progressive in their targeting compared to scholarships but not as effective as conditional cash transfer programmes in ensuring benefits are focused on those in the lowest income brackets.[45] The chart below reflects the effectiveness of targeting through different social transfer modalities by income quintile of beneficiaries, with Q1 being the poorest households and Q5 the wealthiest: / Source: Redistributing Income to the Poor and the Rich: Public Transfers in Latin America and the Caribbean, Lindert et al., 2006, p. 71. / WFP Sierra Leone commissioned an independent evaluation of its current school feeding programme in 2009. One of the recommendations of this evaluation was for a more rigorous focus on targeting and monitoring.[46] Previously school feeding in Sierra Leone had been targeted at individual schools which created distortions and migration of pupils to those schools in the area that were receiving the food aid.[47] This inevitably led to WFP food allocations being insufficient for the rapidly expanding schools. The evaluation therefore recommended a shift to targeting at the chiefdom level to minimise the pull factor and allow for better planning of resources. A comprehensive vulnerability mapping exercise was undertaken in September 2010 by WFP in conjunction with local and national authorities. The exercise identified those chiefdoms most in need of support through local consultations and the use of gender and education data and other vulnerability indicators such as access to markets and social services and poverty levels. This exercise has provided WFP with a sound targeting strategy and will allow them to quickly scale up the existing programme to other vulnerable areas. / Source: WFP, Sierra Leone, 2010. / As mentioned earlier, there is a high level of fiduciary risk in Sierra Leone, recently confirmed by the DFID 2011 Fiduciary Risk Assessment. Large quantities of food being transported to remote locations through a school feeding programme represent an opportunity for theft and misuse. The 2009 evaluation of WFP’s work identified the risks involved in food distribution and storage. In response, WFP have overhauled their mode of operations. They shifted from their previous policy of commercially-contracted transport delivering food to a system whereby food is managed and delivered to schools through three (four in 2011/12) international NGOs who store the food in their District warehouses and then distribute to the schools. These international NGOs have higher overhead costs than local NGO or commercial partners but they give a greater degree of assurance on avoiding misuse of the food. The NGOs also liaise closely with chiefdom and school authorities in terms of storage and stock control and provide a closer level of engagement with School Management Committees and communities involved in the school feeding than WFP would be able to maintain nationwide. / Another step WFP have taken to reduce their risk portfolio is to use bulgur wheat as the staple food stuff in the school feeding. Bulgur wheat is accepted by the school children but it is not a preferred food source in communities and therefore has a much lower market value in Sierra Leone than rice or cassava. By reducing the incentive for theft by using bulgur wheat, WFP have been able to reduce leakage of school feeding stocks on to the commercial market. / While there is considerable evidence internationally about school feeding, the evidence is limited in Sierra Leone. The 2009 evaluation of WFP’s work noted that school feeding had encouraged ‘war-affected parents to enrol children, in particular girls, in primary education’.[48] Random inspections of school registers by the evaluation team also found ‘an overall increase in enrolment, regularity of attendance and retention’ since school feeding had started, although these increases were not quantified in the report and the lack of regular impact monitoring in the WFP programme was highlighted as a flaw.[49] This intervention would help to address this particular issue and more broadly strengthen the evidence base by supporting a comprehensive baseline study in late 2011 and annual evaluations of impact on enrolment, attendance and completion in each subsequent year of the programme timeframe. / Sustainability / Sustainability of school feeding is a major challenge for programmes around the world. Sierra Leone, like many other countries, does not seek an exit strategy for school feeding but rather a transition to a nationally owned and financed system, acting as an education intervention, a scalable safety net and a boost to local agricultural production. The Government of Sierra Leone has confirmed this intention in both the PRSP and Education Sector Plan. / Over the last 45 years, WFP has successfully handed over school feeding programmes to national authorities in 31 countries although it should be noted these are all now middle (and even high) income countries with greater administrative and financial resources than Sierra Leone possesses.[50] The cost of the current school feeding programme is beyond the capacity of GoSL to fund or MEST to administer in the short term. This intervention would support this transition over the medium term which would begin with WFP supporting MEST in producing a National School Feeding Policy. This document would set out the timeline for the transition and the milestones along the way which would see MEST’s financial and management contribution increase. / MEST has already stated that it would like to directly administer school feeding to 25% of the 1,600 schools WFP has identified in its expanded school feeding programme in 2012, rising to 50% of schools in 2013. This would entail much the same role as the NGOs currently play for WFP – MEST would take delivery of WFP food in its own storage facilities, manage the distribution to schools, monitor implementation and report back to WFP and the National School Feeding Committee. It is unlikely that MEST would have the resources to be able to achieve these targets but the announcement shows intent and, with WFP’s support, this capacity can be increased. More realistic targets are needed however and WFP will not handover food for distribution until it and its donors are content with the controls in place. / International experience suggests that a successful transition involves mainstreaming school feeding into national policies and plans, national financing and national implementation capacity.[51] While Sierra Leone has included an expanded national school feeding programme as an objective in several national policies, there is little detail on implementation. This would be produced in the first year of the intervention leading into the second main element of the programme to focus on building Government capacity at the central and local level to increasing ownership of school feeding. On financing, GoSL’s contribution may be minimal in the short term given other financial constraints. Nevertheless an increasing role will be identified in the transition strategy even it this is in-kind support to the school feeding programme. MEST’s administrative capacity to run such a programme is also currently very limited. MEST’s School Feeding Coordination Unit, like many others in the Ministry, currently consists of one officer. There are, however, 2 MEST school feeding monitors in each District who work closely with WFP on their existing programme. / WFP’s commitment and track record globally in helping such transitions was highlighted in the DFID Multilateral Aid Review (MAR) assessment of WFP that noted that it is ‘increasingly tackling sustainability in preparation for handover to governments e.g. school feeding’.[52] However, these transitions do not happen quickly and it has taken many years even in middle income countries with capacity and resources. Given the constraints of MEST, WFP are realistic that the full transition will not happen in the project lifetime but are confident that much greater ownership and oversight can be built over this period, particularly in terms of national policy, District-level delivery and monitoring and in-kind support. DFID’s proposed technical assistance to MEST and the recently completed Capacity Development Strategy for the education sector will help more broadly to professionalise and strengthen MEST. / Local procurement is also a key factor in establishing a sustainable national programme. Local procurement reduces a country’s expensive dependence on imported food for school feeding, reduces transport costs and helps to stimulate the rural economy by providing market access to farmers. WFP’s plan to procure 10% of the total food requirement locally through the Purchase for Progress (P4P) project would see an increase from 370 tonnes purchased in 2010/11 to 720 tonnes in 2011/12 onwards. If further food of the right quality and price is available this could be expanded in later years, although the current target is considered ambitious. / Institutional partnership / Delivery of any programme in Sierra Leone is constrained by the limited number of reliable partners with nationwide reach. WFP is one such partner who can effectively procure and distribute goods on such a scale. The fact that WFP has existing programmes and partnerships that can be scaled up quickly is a major advantage for this option. This is important for delivery against the Results Framework but also given the immediacy of the food price rises. / Channelling resources through MEST for school feeding would increase national ownership but given their very limited capacity and a ‘high’ fiduciary risk rating from a recent DFID assessment, the risk to delivery would be too high at this stage. Funding WFP to deliver while supporting a transition to greater GoSL ownership and collaboration at the District level, as outlined above, is the most realistic option for a partnership on school feeding. / WFP achieved a ‘strong’ rating in the MAR. The main MAR report focused largely on the humanitarian emergency food aid component of WFP’s work but highlighted some key organisational strengths: / WFP delivers results at scale in humanitarian and fragile contexts.  / It has a strong corporate emphasis on costs/efficiencies coupled with business model improvements. / Drives cost control with delivery partners; and it seeks value for money through local procurement and cost-efficient delivery tools / WFP has demonstrated good partnership behaviour over the last two years: improvements can be seen at country and global levels. / Since 2007 WFP has carried out significant reforms of its strategic direction, operational tools and its results, financial, programming and HR systems.[53] / Sierra Leone was one of the ten countries visited by the MAR team during their research and so there is additional material on WFP’s performance in country[54]. During the field visits the MAR team found that WFP’s ‘investment in poverty and vulnerability mapping was a key strength’ and that WFP generally was responsive to challenge and criticism, citing WFP Sierra Leone as having redesigned their programme after the findings of the late 2009 evaluation. The MAR team also welcomed the local procurement of food stuffs from smallholders in Sierra Leone. The team reported that cooperation with the UN Food and Agricultural Organisation was stronger in Sierra Leone than elsewhere and that WFP was ‘managing to balance the need to control the delivery of food while allowing increased government ownership’. The independent 2009 evaluation of WFP’s work also noted that WFP had helped strengthen ‘working relationships between WFP and national counterparts’[55] / The country level research of the MAR identified generally weak results frameworks and an inconsistent drive for programme efficiency and cost reductions in WFP programmes. In Sierra Leone the reforms in WFP taken in response to the late 2009 evaluation were a positive signal of the need to improve efficiency and reduce costs although sustaining this momentum would need to be monitored. The results framework will be strengthened for the whole of WFP’s school feeding programme through the DFID intervention by ensuring that a comprehensive baseline and annual evaluations take place. The logframe has been designed accordingly. / OPTION 2: CONDITIONAL CASH TRANSFER / Intervention: / The UK would support an international NGO to establish and operate a conditional cash transfer programme. Families of targeted primary school pupils would receive a quarterly cash transfer in exchange for 80% school attendance. The Ministries of Social Welfare and Education would need to take a substantial role in the targeting and monitoring the intervention. Given the high operating cost in Sierra Leone, the project would reach the households of up to 14,000 children. / Cost: The cost would be £5m over four years. / The rationale / There is a robust and increasing body of evidence from a number of countries that conditional cash transfers (CCTs) have generated significant gains in access to education and other social services.[56] They can alleviate poverty in the short term and build human capital in the long run. CCTs generally provide a regular cash payment to targeted households on condition that some or all of the household members maintain a verifiable set of behaviours. In education this often revolves around minimum school attendance. / CCTs were pioneered in Latin America and evaluations there showed substantial impacts. In the Bolsa Familia scheme in Brazil, for example, beneficiaries were found to be 63% less likely to drop out of school and 24% more likely to advance an additional year.[57] A CCT scheme under Pakistan’s Punjab Education Sector Reform Programme, increased enrolment rates for girls aged 10-14 by 11%.[58] A review of the evaluations and random control trials conducted on education-focused cash transfer programmes found enrolment rates increased in both primary and secondary education by between 4 and 18% as well as consistently raising attendance rates and reducing drop out rates.[59] The same review concluded, however that there was no evidence that CCTs actually raised educational attainment.[60] Any such intervention would therefore focus on enrolment and retention rather than the quality of learning. / Like school feeding, there is a strong safety net element to CCTs. The substantial impacts in behavioural change that CCTs have demonstrated have generally required a substantial incentive to the household. International experience has established a recommended input range of 25-30% of the monthly household expenditure for a cash transfer programme.[61] This would provide a substantial easing of the economic strain for low income families, especially given the recent rises in fuel and food prices affecting Sierra Leone, the latter hitting the poorest families hardest. The relative cost of the inputs, however, does limit the beneficiary numbers and the complexity of CCTs makes them difficult to scale up or down quickly in times of economic shock or recovery. / CCTs are particularly strong in their targeting potential. If done well, this type of intervention can target individual households, allowing for a greater focus on the most marginalised and vulnerable in society. For an education CCT this might allow a specific intervention focused on girls, children with disability, orphans or others at a disadvantage in the education system. / Within the envelope of £5m for demand-side access to education, such a CCT programme could potentially make a real difference to the education prospects of the 13-14,000 targeted children and wider benefits for the households in which they live. However, by selecting individual households and girls, such a CCT programme would risk creating jealousy and stigma against the beneficiaries. In Sierra Leone there is already evidence of a backlash against girls receiving scholarships under other programmes by their resentful male peers with sexual violence and rape seen as a punishment for this “unfair” distribution of benefits.[62] Ensuring sufficient community sensitisation and regular close monitoring to prevent such a response would be a major challenge in running such an intervention in Sierra Leone. / While there is a strong evidence base showing the impact CCTs can have on education indicators, they are complex instruments to establish and run. Until recently CCT programmes were usually implemented in stable, middle income countries. Expansion of the modality into fragile states has begun but in-kind transfers (food aid, agricultural inputs etc) have tended to predominant in these environments. This is still the case in Sierra Leone where there are a number of practical challenges that would need to be overcome in setting up a CCT programme. These include: the safety and security of transporting large amounts of cash around on a predictable timetable; availability of delivery partners with local experience in delivering such an intervention at scale; inadequate data to properly target the intervention; and limited Government capacity to engage and oversee the programme. While none of these are insurmountable and CCTs have been shown to work in fragile contexts, it would delay implementation while such capacity was built up. The limited number of beneficiaries would also reduce the value of such an intervention to the DFID education Results Framework, although there would be wider benefits to the targeted household health and nutrition. / Sustainability / The capacity of the Government to manage a national CCT or safety net process is very limited. Any intervention would need to be implemented by a non governmental actor and would require significant input to building up the Government’s financial management, infrastructure, staff capability and structures to take on the management in later years. Given the limited number of beneficiaries and the relatively high cost, this would be a very expensive mechanism for the Government to maintain and difficult to justify in terms of its limitation to 13,500 of the 1.4 million children in primary school. Further expansion through Government resources is extremely unlikely given the size of the budget. A CCT programme may be effective in the short term but it is difficult to see how it could be sustained after the end of the intervention’s funding. / Institutional partnership / As indicated there is a lack of obvious partners with the capacity and experience to run this programme immediately. An international NGO could mobilise expertise from elsewhere and utilise their existing networks but this is unlikely to give nation-wide coverage in the short to medium term. MEST has not yet been able to demonstrate the degree of fiduciary risk control and organisational capability to make them an option. The recent MEST initiative to pay a share of the fees for all girls in junior secondary school has been characterised by low levels of disbursement and late and partial payments. Similar delays and bottlenecks have been seen in MEST’s management of the resources in the pooled Education Sector Support Fund. / In addition to MEST’s limited capacity, there is also an issue over the principle of CCTs for primary education. The Government of Sierra Leone has made primary school mandatory and, in theory, free of charge. Effectively rewarding a relatively small number of children for complying with the law may be a difficult issue for GoSL. MEST’s preference would be that any such CCTs focus on secondary and tertiary education, which already consume 60% of MEST’s recurrent budget (as opposed to 22% for primary) and cater for a much smaller segment of the population than that in primary schools. Given that Government leadership would be very important for this type of intervention, this dichotomy may present a further challenge. / At the request of the Government of Sierra Leone and in agreement with other donors, the World Bank is investigating the options for a longer-term safety net programme, which would be national in scale and sustainable. This work is only in the initial stages but any recommendations would likely include significant support to the GoSL institutional lead agency (most likely the Ministry of Social Welfare) to manage or at least oversee the proposed scheme. Investing in MEST to develop and manage a similar scheme may prove duplicative in the medium term. / Given the immediacy of the food prices crisis and the relatively small number of beneficiaries that could be reached through a CCT intervention, this intervention would struggle to deliver impact on the scale and timeframe required. / OPTION 3 ‘DO NOTHING’ / Intervention: The UK would not invest in an education safety net to protect and promote enrolment and retention. / Cost: £0m. / Option 3: / If DFID chose to do nothing in this area, it is unlikely that the few other donors in education in Sierra Leone would make up the gap. The World Bank does not have an IDA programme but does manage the Fast Track Initiative grant of $14m. These funds have been fully allocated but the programme has consistently underperformed and finishes at the end of 2011. Given previous grant performance Sierra Leone’s prospects for a further FTI grant are in some doubt and passing resources to a UN agency for implementation is not a preferred modality for the FTI. The Swedish Government’s education programme closes in 2012 and, like the FTI grant, resources have been fully allocated for the remaining months. The Japanese and German Governments have small programmes in technical and vocational education while UNICEF has its programme funding committed to other aspects of education. A UN fund and Irish Aid have provided funds to school feeding but this will not cover the existing 250,000 beneficiary programme let alone a scale up. The World Bank may provide additional resources through a social protection envelope for school feeding but this is unlikely to be sufficient for significant expansion. The World Bank is looking into longer term safety nets but, like DFID, sees school feeding as the only viable option in the short term. / Without a DFID intervention, and given that there is unlikely to be any large scale cash transfer scheme established in the next 2-3 years, the school feeding programme would struggle to maintain its coverage of 250,000 children. Discussing a potential DFID contribution has also prompted WFP to build in a far greater emphasis on baselines and evaluations as well as working with Government to identify and work towards milestones on transitioning to national ownership. Without a DFID intervention WFP would lack the resources for these two crucial elements for sustainability and results. / Even in times of relative economic stability, completion rates are very low in Sierra Leone and 30% of school aged children are out of school. In the context of record food prices, past experience points to both these indicators being likely to deteriorate as poor households de-prioritise education and other social spending. Girls would suffer disproportionately in this scenario. Without a properly targeted and scaled up safety net programme through school feeding (or cash transfers), enrolment, attendance and completion rates in primary schools in poor areas will reduce at a time when Sierra Leone needs to be consolidating and strengthening its education sector towards reaching the MDGs. / There would also be a reputational risk of DFID, the largest bilateral donor in Sierra Leone, failing to respond to the Government’s call for donor support to mitigate the impact of the food price crisis.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Medium / 2 Medium / 3 N/A / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 n/a n/a / The climate and environmental impact of both options is low. / For the school feeding option, food will be sourced mostly internationally and will have to be transported to Sierra Leone and distributed locally to schools, with some carbon footprint although this is considered to be small. Some food may be sourced locally through increased local agricultural development. This may have some impact on the local environment although the amounts WFP targets for purchasing are still very small. WFP coordinates its work with the Agricultural Business Centres as part of the Smallholder Commercialisation Scheme. These centres train smallholders on minimising the environmental impact of farming as well as soil conservation and thus impacts should be minimised. / For the Cash Transfers option, there are no direct climate and environment impacts.
C. What are the costs and benefits of each feasible option? / Option 2, cash transfers, is a feasible option but has drawbacks, especially in terms of the numbers of beneficiaries compared to school feeding. On average education-focused cash transfers results in 4-18% increases in enrolment. Many of the higher end increases were seen in CCT programmes in Asia and South America, whereas results from Africa have tended to be towards the lower end of the scale.[63] Taking a mid-point of this range, a CCT-derived 11% increase in enrolment in Sierra Leone is comparable to the expected increase from a school feeding programme (8%). Both interventions would have other benefits, especially at the household level for cash transfers and take home rations. The lack of education and poverty data in Sierra Leone makes it difficult to estimate the potential impact such benefits would have. Also given the main objective of this intervention to improve enrolment and retention in schools. The primary prism for analysing benefits of the options therefore is enrolment and extra years of education. / The conditional element of the cash transfer intervention would be the girl beneficiary’s 80% attendance rate at school, verified by the school. In line with DFID experience, the per-beneficiary cost of £8 per month, amounting to 30% of the average Sierra Leonean household expenditure,[64] is within the 25-30% range identified by Save the Children UK’s research.[65] Although CCTs can provide high impact, the programmes are expensive at cost per beneficiary. Given the unit cost, the programme could reach around 13,500 beneficiary children a year over the three years compared to the 110,000 each year reached by the school feeding programme option. The beneficiaries for CCTs however are wider than just the children targeted as it is the household which would receive the transfer. The average household size is 6 people in Sierra Leone so the beneficiaries of the cash transfer could reach as high as 67,500. / Benefits Costs / Option 1 School Feeding 110,000 direct beneficiaries per academic year for school meals / 17,500 direct beneficiaries per year for take home rations. / Up to 400,000 indirect beneficiaries per academic year (for three years) / Household expenditure 10% (50% for take home rations) £5m total cost / Cost (school feeding) per direct beneficiary £15.15 per year / Cost per beneficiary (direct and indirect) £3.16 per year / Sub Saharan Average per beneficiary cost of WFP school feeding: £12.60.[66] / Option 2 Cash Transfers 13,850 direct beneficiaries, per academic year (for three years) / 55,400 indirect beneficiaries per academic year (for three years) / Household expenditure 30% £5m total cost / Cost per beneficiary (direct) £120 per year / Cost per beneficiary (direct and indirect) £18.05 per year / Given the need for a large-scale programme to provide a form of national safety net to protect and promote enrolment and completion of primary education, school feeding is the preferred option. School feeding can be scaled up rapidly, can cover up to 35% of children in school and is aligned with Government policy. / Option 1: School feeding-Supporting access to primary education for vulnerable children: Economic Appraisal / DFID Sierra Leone’s school feeding programme is a component of its wider education programme. The main objective of this programme is to improve access to primary education in the most vulnerable communities across Sierra Leone. The programme is also aimed at improving on enrolment and retention in schools especially for girls. / Incremental costs / The total DFID investment will be £5 million over three academic school years (2011/12-2013/14). DFID’s funding will provide around 31% of the total funding for the school feeding programme and the remainder being provided by the other donors including Irish Aid and the UN Joint Vision Fund. The table below provides a breakdown of costs over the three years: / £ millions 2011/12 2012/13 2013/14 Total / DFID SL School feeding programme 2.0 2.0 1.0 5.0 / The DFID support is aimed at expanding WFP’s existing school feeding programme, to providing pupils in the most food insecure, poor and educationally disadvantaged areas with a hot meal everyday of the school year. A component of the intervention is also to support a pilot to increase girls’ completion rates in two chiefdoms with a very high gender disparity. This programme will be managed by WFP and delivery is been done through three NGOs; PLAN International, World Vision and AfriCare. / Incremental Benefits / The programme is expected to deliver benefits in three ways: / Increase enrolment and completion rates of beneficiaries / Increase incomes of beneficiaries / Specific benefits associated with educating girls. / A major challenge for the education system in Sierra Leone is getting children enrolled in schools and also retaining those already in schools. This is an issue in particular for poor families. To address this problem, the Government abolished school fees for primary education thus making primary school education free. However, the evidence suggests that the other costs associated with educating a child such as transportation costs, lunch costs and exam fees are still impacting on the expected uptake of education and on retention rates. / The DFID schooling feeding programme will save parents the costs of providing lunch meals to their children and will result in a reduction in the overall costs of sending their children to school. The evidence from other WFP school feeding programmes implemented in countries with a context similar to Sierra Leone’s, show that these programmes lead to an annual increase in enrolment rates in schools by 8% and in completion rates by 10%. It is thus assumed that the DFID programme will lead to increased enrolment and completion amongst pupils benefiting from the programme at similar rates. / As enrolment, retention, and completion increase, this is expected to impact on improved educational attainment. It follows therefore that as workers gain more skills the higher their earning potential. The evidence shows that an extra year of primary education results in a 9% increase in average income. / The evidence from Sierra Leone also confirms this trend as the 2004 household survey found that those with a Grade 5 education were earning 5% more than those who left school at grade 4. Also those who left school at Grade 6 were earning 14% more than those who left school at Grade 5. Taking the median, it is thus assumed that the DFID school feeding programme will lead to a 9% increase in earning of the beneficiaries for each additional year of schooling. / The increased enrolment from the programme was calculated as well as the future income uplifts for the beneficiaries of the programme. The following additional assumptions were made in calculating these benefits: / Enrolment only increases in the first year of the programme even though the programme runs for three years. / Each additional school year provides 9% of additional earnings for the beneficiaries in line with the evidence from other countries and in Sierra Leone. / The benefits are accrued over 25 years even though the programme runs for three years. It is assumed that if beneficiaries leave school at age 16 they will have a working life span of approximately 25 years given that the life expectancy in Sierra Leone is on average 45 years. / The project would yield other indirect benefits such as health benefits that could not be monetised. It is assumed that the benefits of this programme could be much higher if these indirect benefits are factored into the calculations. / As DFID’s contribution will also go towards a pilot school feeding programme for girls aimed at increasing their completion rates, there are the extra benefits associated with providing education to girls. The research on the benefits of educating girls finds that this impacts on future personal incomes as well as on incomes and productivity of economy. Further benefits also expected include improvement in health and reduction in fertility which evidence shows also has benefits to the economy. The specific benefits of the Take home ration for girls are also calculated in terms of increased enrolment and income uplifts using the same assumptions outlined above. / The benefits are discounted at 3.5% which is the recommended rate in the HM Treasury’s Green Book. These benefits are also apportioned according to DFID’s share of funding to support the school feeding programme. DFID’s contribution is approximately 31%. / Balance of costs and benefits / The table below shows the balance between costs and benefits including their present values after discounting. This shows a cumulative net present value benefit of the programme will be £6.2 million, with benefits occurring over a 25 year period. This produces a benefit cost ratio of 0.8. The cumulative benefits will be much higher if the indirect benefits are monetised and factored into the calculations. / £ millions Total programme / Costs 5,000,000 / Present Value (PV) Costs 4,865,878 / Benefits 17,247,185 / Present Value Benefits 11,069,145 / Net Present Value (NPV) 6,203,267 / Risk and uncertainty / From the table below, it can be seen that on reducing the rate of salary uplift for an extra year of education from 9% to 5% the project is no longer worthwhile as it yields a negative cumulative net present value. The implication is that if the average return on the incomes for an extra year of schooling in Sierra Leones falls to 5% or below, the project will not produce the results and benefits outlined above. However, reducing the rate to 7% the project will still yield a positive net present value. / On increasing the rate of return from 9% to 14%, the project yields a positive cumulative net present value, making the investment worthwhile. The net present value of the project triples to £18.1 million. This implies that as rate of return on getting an extra year of education increases above 9% the expected cumulative benefits will also continue to increase. / £ millions Salary uplift rate (5% ) Salary uplift rate (7%) Salary uplift rate (9%)* best estimate Salary uplift rate (14%) / Costs 5,000,000 5,000,000 5,000,000 5,000,000 / PV costs 4,865,878 4,865,878 4,865,878 4,865,878 / Benefits 7,009,771 11,614,078 17,247,185 35,830,951 / PV benefits 4,500,701 7,455,158 11,069,145 22,989,552 / NPV - 365,177 2,589,280 6,203,267 18,123,674 / Conclusion / The economic appraisal suggests that the programme will offer good value for money as the project yields a positive net present value. The main benefits are expected in the form of increased enrolment, retention and completion rates, increased personal incomes and the associated benefits of educating a girl child. / The net present value of the monetised benefits will be £6.2 million, at our best estimate. However, sensitivity analysis suggests that the programme will not represent value for money if the rate of income uplift reduces to 5%. This suggests that the project must be monitored closely and implemented within the agreed timeframe in order to realise the expected results and benefits. / The project would also yield other indirect benefits such as health benefits that could not be monetised. Benefits from completion rate increases are difficult to estimate at this point given the lack of data. The benefits of this programme would be much higher if these indirect benefits are factored into the calculations. / Several simplifying assumptions have been used in the analysis, which mean that the results have limitations and caveats, and should only be used as a decision making tool.
D. What measures can be used to assess Value for Money for the intervention? / At the input level: / Unit costs of school feeding and take home rations per beneficiary will be monitored during / the programme. / The average cost per beneficiary for a WFP school feeding programme in Sub Saharan Africa is around $20.40/£12.60.[67] The cost in Sierra Leone in 2011/12 will be $27/£15.15. This is in part due to the current high fuel and food prices on the international and local markets and partly due to the poor road and infrastructure conditions in the country. While WFP will seek to bring this rate down, the global price of food stuffs is the major variable and clearly beyond their control. WFP is already operating in the country and has the procurement, storage and distribution networks that will also avoid the high start up fees of beginning a new intervention. / Following the 2009 evaluation, WFP restructured its operation, cutting down its number of sub-offices, reducing its transport fleet and reducing the number of expatriate staff. This dealt with many of the legacy issues stemming from the humanitarian mode of operation during and after the war.[68] WFP had moved to commercially hired transport to deliver the food from WFP warehouses to schools. While this was cheaper it failed to provide sufficient checks and balances on stock control and losses. To remedy this, WFP has contracted four NGOs to act as the delivery arm of the operation, taking delivery of stocks and then disbursing them to schools. As these are international NGOs the overhead costs are more expensive than local commercial companies but the degree of supervision and monitoring is substantially enhanced. / WFP will procure 90% of its food required through an international competitive tendering process that should guarantee the best value for money available at the time of purchase. Where local purchasing is possible in terms of quantity, quality and price, WFP will pursue this option, the target is 10% of total needs a year. A review of relative costs of local and international purchasing will be included in the annual WFP reports to DFID. / At the outcome level: / Data limitations pose some challenges for rigorous value for money assessments, so the preferred intervention option of school feeding, will include funding for a thorough baseline of the targeted chiefdoms in late 2011 with evaluations in 2012 and 2013. The programme will track for both school feeding and the take home rations: / Enrolment numbers / Attendance in school / Completion rates / Some of these will also be monitored by other DFID programmes, such as the school water and sanitation programme, as well as other programmes ongoing in the country such as de-worming to track and compare cost-effectiveness of results. / At the Impact level: / Extra years of education result in benefits over a considerable time, particularly in terms of lifetime increases in income and reproductive health. This programme is unable to track such impacts but the approach will be validated by the results from the periodic Demographic and Health Survey data if it continues to show positive correlation between the level of education and health and income indicators. The next survey is due in 2013.
E. Summary Value for Money Statement for the preferred option / £ millions Total programme / Costs 5,000,000 / PV costs 4,865,878 / Benefits 17,247,185 / PV benefits 11,069,145 / NPV 6,203,267 / The economic appraisal suggests that the programme will offer good value for money as the project yields a positive net present value. The main benefits are expected in the form of increased enrolment, retention and completion rates, increased personal incomes and the associated benefits of educating a girl child. / The net present value of the monetised benefits will be £6.2 million, at our best estimate. However, sensitivity analysis suggests that the programme will not represent value for money if the rate of income uplift reduces to 5%. This suggests that the project must be monitored closely and implemented within the agreed timeframe in order to realise the expected results and benefits. / The project would also yield other indirect benefits such as health benefits that could not be monetised. Benefits from completion rate increases are difficult to estimate at this point given the lack of data. The benefits of this programme would be much higher if these indirect benefits are factored into the calculations.
[36] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009
[37] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, pp 27
[38] Vermeersch, Christel 2002 and US Agricultural Service 2003, cited in What Works in Girls’ Education, Herz and Sperling, 2004, p. 54
[39] School feeding for improving the physical and psychosocial health of disadvantaged students, Kristjansson et al, 2007, p.38
[40] School feeding for improving the physical and psychosocial health of disadvantaged students, Kristjansson et al, 2007, p. 11
[41] For example School feeding for improving the physical and psychosocial health of disadvantaged students, Kristjansson et al, 2007, pp 29-30, 38
[42] School feeding for improving the physical and psychosocial health of disadvantaged students, Kristjansson et al, 2007, p. 14
[43] Understanding commodity prices in Sierra Leone, Ministry of Finance and Economic Development, GoSL, May 2011.
[44] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.15
[45] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.15
[46] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, p.10
[47] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, p.52
[48] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, p.10
[49] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, pp.32, 40
[50] Feed Minds, Change Lives: School Feeding: Highlights and New Directions, World Food Programme, 2009, p.12
[51] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.34
[52] Multilateral Aid Review: Assessment for World Food Programme, DFID, February 2011 (unpublished)
[53] Multilateral Aid Review: Ensuring maximum value for money for UK aid through multilateral organisations, DFID, March 2011
[54] UK Multilateral Aid Review – Country visit findings – WFP, DFID 2011 (unpublished).
[55] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, p.10
[56] Cash Transfers, DFID Evidence Paper, 2011
[57] Veras, 2007, cited in Cash Transfers, DFID Evidence Paper, 2011 , p.24
[58] Chaudhury 2008, cited in cited in Cash Transfers, DFID Evidence Paper, 2011, p. 24
[59] The Impact of CCTs: What we Know and What We Are Not Sure About, Ribas et al., Poverty in Focus, IPC, 2008., pp.12-13
[60] Ibid.
[61] Cash Transfers, DFID Evidence Paper, 2011, p.65
[62] Barriers to Education: The Out-of-school Children of Sierra Leone, UNICEF, 2008, p. 38
[63] Cash Transfers, DFID Evidence Paper, 2011, p.25
[64] Integrated Household Survey, Statistics Sierra Leone, 2004, http://www.statistics.sl/household_surveys.htm
[65] Cash Transfers, DFID Evidence Paper, 2011, p.65
[66] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.60
[67] Rethinking School Feeding: Social Safety Nets, Child Development, and the Education Sector, Bundy et al, World Bank, 2009, p.60
[68] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, p.11

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / This intervention would use a standard Administrative Agreement with the UN’s WFP. WFP is the world’s leading delivery agent for school feeding and currently implements the only significant school feeding programme in Sierra Leone. They are best placed to deliver this intervention.
B. Value for money through procurement / From the 2011/2012 academic year until 2013/14, WFP will provide an on-site, hot, nutritious mid-day meal for 400,000 primary school children every school day. Additionally 1,500 girls will receive a monthly 15 kg take home food package, sufficient for a family of five. This may increase to 3,500 in 2012 pending the evaluation findings of the pilot. / The total annual commodity requirement for this operation is 7,200 metric tonnes with a cash value of approximately US$ 8,640,000 (the proposed DFID contribution would constitute 28% of this). WFP’s procurement will be 90% through international tendering and 10% local procurement through the Purchase for Progress (P4P) initiative. / For international purchasing, the procurement policy of WFP is to purchase from pre-qualified suppliers through a competitive bidding process. Competitive bidding guarantees that the best possible prices are obtained and that the purchase is carried out transparently. This process entails an analysis of the cost of the commodity as well as the cost of transport and handling up to delivery to WFP warehouses in country. / For the 10% local procurement, this should equate to nearly 2,100 tonnes over the next three years. The DFID share of this would be around 900 tonnes. The P4P scheme is being piloted by WFP in 21 countries and seeks innovative ways to support local smallholders, acquire local staples and collaborates with other actors on agricultural development. The approach requires that WFP criteria on price, quantity and quality are met. / In Sierra Leone a P4P Programme Advisory Group (PAG) has been established including the Ministry of Agriculture, Food Security and Forestry (MAFF), the UN Food and Agricultural Organisation, the International Fund for Agricultural Development, USAID, the National Federation of Farmers of Sierra Leone and the NGOs CARE, Catholic Relief Services, Concern Worldwide and World Vision. The 2009 evaluation found the objectives and justification for the P4P project to be ‘sound’ but recommended that the programme be better linked to other agricultural interventions aiming to improve rural livelihoods and conditions.[69] In response WFP have increased cooperation with 12 farmer smallholder organisations and the 125 EU/MAFF-supported Agricultural Business Centres. WFP will evaluate its whole P4P initiative in 2011 and 2014. / Local purchasing helps to provide the foundation for a sustainable, nationally-funded school feeding programme and by providing a reliable purchaser, enables smallholder farmers’ groups to expand food production. WFP has already made steady progress on local purchasing over the past 3 years, despite the low level of commercialisation and the generally small scale of the farms. In 2009, 162 metric tonnes of rice was purchased from local farmers in four pilot districts - Koinadugu, Tonkolili, Kono and Kenema. This was expanded to 259 tonnes of rice in 2010 which was supplemented with another 110 tonnes of Pigeon Peas, Cassava cereals (Gari), palm kernel oil, fortified blended food. The 720 tonnes a year that WFP now seek to purchase is an ambitious target given the state of supply but they believe it is realistic. Should local production expand more significantly and given that the value and quality remains sound, WFP could further expand local purchasing. / While the amounts locally procured are relatively small and the administrative burden is greater than for bulk international shipments, the Purchase for Progress scheme broadens the benefits of the school feeding to the local and national economy. By reducing reliance on expensive international food sources, it should also help the Government of Sierra Leone manage and finance the school feeding programme in future years.
[69] World Food Programme, Sierra Leone - Decentralized evaluation, Fawzi El-Solh et al, August 2009, pp. 45-46

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The UK will provide £5,000,000 over the next three years. / £ millions 2011/12 2012/13 2013/14 Total / DFID SL School feeding programme 2.0 2.0 1.0 5.0 / The funds in this programme are largely for bulk purchasing of food stocks which are predictable. Regular contact will be retained with WFP to ensure accurate monthly quarterly and monthly forecasts are provided.
B. How will it be funded: capital/programme/admin? / The £5m will all come from the programme RDEL budget.
C. How will funds be paid out? / In order to respond to the food price rises and safeguard and extend educational gains in the most food-insecure areas of Sierra Leone and fit with the academic year cycle, the funds will be spent: / - £2m paid in October 2011 / - £2m paid in August 2012 / - £1m paid in August 2013 / WFP needs to have contributions in advance in order to be able to procure food on the international market. Delivery can then take several months. Given this, the first tranche will be paid immediately. This will allow WFP to order replenishment supplies for its existing food stock which will be heavily drawn down from September with the expansion to 400,000 beneficiaries.
D. What is the assessment of financial risk and fraud? / In general there is a high financial and fraud risk in Sierra Leone. This intervention will reduce these risks by channelling resources through a UN agency (WFP) which has better fiduciary controls than the Ministry of Education (rated as high risk in the recent DFID Fiduciary Risk Assessment). WFP has also improved their operations to reduce waste and misuse by conducting a comprehensive targeting exercise to ensure that school feeding targets the most vulnerable localities. They have also contracted 3 international NGOs, soon to be expanded to 4, to oversee the distribution and monitoring of foodstuffs to the schools. This follows an internal review which highlighted the risks of depending on contracted local commercial transport companies. / WFP and its partners will also work with the local and national authorities to increase their capacity to plan and monitor school feeding in advance of an increased role in programme delivery.
E. How will expenditure be monitored, reported, and accounted for? / WFP will provide annual audited financial statements and six monthly statements of expenditure alongside narrative reports. A final programme report six months after the end of the project will account for all funds received.

Management Case

A. What are the Management Arrangements for implementing the intervention? / This intervention will be overseen by the Project Officer and Education Adviser in the Millennium Development Goals Team, DFID Sierra Leone. / WFP is accountable to its donors and the Government of Sierra Leone, specifically the Ministry of Education’s School Feeding Coordination Unit. / Beneficiary accountability is provided through the local School Management Committees who are an integral part of the intervention at the community level. Their views and feedback will be given to evaluators and fed through the NGO delivery partners and MEST school feeding monitors. / DFID will manage the programme through an Administrative Agreement with WFP, setting out the terms and conditions of the funding. Underpinning this agreement is the project document from WFP and the agreed logframe. DFID will engage with the WFP office in Sierra Leone and, where necessary, the regional or headquarters offices either directly or through relevant DFID officers in London or Rome. / All school feeding activities within the country are coordinated by the National School Feeding Coordination Unit in the MEST. The National Coordinator is Freetown based with two monitors in each of Sierra Leone’s 13 Districts. These officers provide the link to the MEST District Education Offices as well as the District Councils, particularly their Education Committees that manage devolved education functions. / At the national level a School Feeding Technical Committee will be set up between WFP, relevant Government bodies and NGOs to ensure harmonisation, coordination and that best practice is shared. It is anticipated that this body meets on a quarterly basis. WFP will also ensure that the school feeding programme is coordinated with the Small Holder Commercialisation Programme (SCP) through the Secretariat situated in MAFF. / At the local level, coordination bodies will be formed in each District to oversee school feeding implementation, compromising of NGO delivery partners, District Council representatives, MEST officials and WPF officers. These bodies will report to the central Technical Committee and play a key role in ensuring that the targeting, delivery and monitoring of school feeding proceeds smoothly. They are likely to also meet quarterly. / WFP will manage the grant and be responsible for its full and timely implementation. WFP will provide the vulnerability assessments, targeting, procurement and technical assistance for the programme. It has contracted four international NGOs to store WFP food in their District warehouses and then distribute it to the schools. The four NGOs are Africare, Plan, World Vision and Catholic Relief Services. These partners are already operational in delivering school feeding in 12 of the 13 Districts and have the capacity to scale up. The NGOs also provide the routine ongoing monitoring of the distribution and work with the communities and local authorities to ensure that the school feeding is compatible and complementary with any other local interventions. / Within WFP, the programme is managed by a team covering WFP’s health, nutrition, and education interventions and is supported by sub-office programme teams in the regional hubs of Magburaka and Kenema.
B. What are the risks and how these will be managed? / Risk Mitigation Probability Impact / 1 The level of fiduciary risk is generally high in Sierra Leone WFP was chosen as a reliable partner with good financial management systems. It will work with MEST to build their capacity but control of resources will rest with WFP during the lifetime of this project. L M / 2 Theft of food After the 2009 evaluation, WFP contracted four international NGOs to manage the distribution and provide a closer supervision role than WFP was able to achieve. This arrangement will be kept under review with MEST and WFP officials conducting spot checks and monitoring visits. The choice of bulgur wheat as the main element of school feeding also reduces the incentive for theft given its low market value. M L / 3 Rising international commodity prices affect the tonnage WFP can purchase and therefore the beneficiaries it can reach. WFP will seek to maximise value for money and the local procurement should help to mitigate international price fluctuations. Nevertheless, if prices do continue to rise WFP will either look for more donor funding or reduce the number of beneficiaries. In either case, DFID’s attributable results will be reduced. DFID will maintain a regular dialogue with WFP on its procurement needs and budget implications through the quarterly education partners’ meeting. M H / 4 Lack of MEST capacity undermines national ownership and long term sustainability. Given the experience WFP has had in enabling a transition from donor-funded and WFP-delivered school feeding to nationally owned and resourced programmes, it is unrealistic to expect Sierra Leone to make this transition in anything less than a decade, despite this aim being the stated policy of the Government. Nevertheless, there is a risk that MEST fails to provide the staff and resources to begin to build this in-house capability during the life time of the intervention. The transition strategy that WFP draws up with MEST needs to be realistic and have clearly identified milestones. During the Operational Plan period DFID also expect to support MEST in wider reform and strengthening following the analysis provided in the UNICEF-funded 2011-2015 Education Sector Capacity Development Strategy. H M / 5 Weak data collection systems undermine ability to demonstrate results Government systems for collecting and analysing data are weak, particularly at the central level. WFP will therefore undertake its own baseline in those targeted districts in 2011, although it will build on the (currently unverified) national school census work of 2010. This data will be the basis for the annual evaluations of progress against the targets in the logframe. Schools will be assisted in keeping accurate records by the INGO partners. M M
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / Project monitoring and reporting will take place on a number of levels: / School level: School Management Committees or Food Management Committees will oversee the daily preparation of the school meals and report to the relevant delivery NGO when there are issues or concerns. MEST School Feeding Monitors will also visit each site twice a term to monitor behaviour, use and the impact of school feeding within the school. WFP has supported the monitors to set up this schedule of visits and has donated 11 motorbikes for this purpose in 2009/2010 and is currently considering a request for an additional 13 to support the remaining Districts (not included under this project). / District level: the School Feeding coordination bodies will receive reports from the NGO and Government monitors as well as feedback from the communities through their Councillors. / National level: WFP, NGOs and Government agencies in the School Feeding Technical Committee will regularly meet to discuss progress and, where necessary, resolve problems in delivery. These discussions will be informed by reports from Districts and supplemented with periodic WFP field visits. / Reporting on the project will be done through the WFP Standard Project Report on an annual basis with a short narrative interim report on a six-monthly basis. WFP will present its activities, spending and results to DFID and other partners during the DFID Partners’ Quarterly Education Review. / In addition to WFP’s own monitoring, DFID will undertake at least two field visits a year to monitor the intervention’s implementation. / On evaluation, the DFID contribution will support WFP to better track the impact of the whole of its school feeding programme. This will be done through the baseline study in 2011 and then evaluations on a yearly basis thereafter. These will be contracted out by WFP to independent consultants, costing in total $120,000. The results from these evaluations will verify the milestone data used in the programme logframe updates. / For the take home rations pilot, PLAN (the implementing partner of WFP) will evaluate the initiative in 2012. The results of this evaluation will then inform whether WFP scales up its support to 3,500 girls in areas with particularly low rates of girls’ participation and completion in primary education. / The results of the intervention will be managed through the logframe. This will be updated annually after WFP’s programme impact review and supplemented by 6-monthly narrative reports on progress and quarterly presentations to DFID. Results from the intervention will be fed into the DFID Sierra Leone Results Tracker which is updated quarterly, in this case by the Project Officer and Education Adviser. / The project has annual milestones and reviews but demonstrating the impact of a project on enrolment, retention and completion in schools requires several years to be sure of the modality and counterfactual. This programme, spread over three academic years, will ensure that WFP has the time to fully evaluate the results and demonstrate outcomes and impact.
Logframe / Quest No of logframe for this intervention: 3196886 / Given the scarcity of data in Sierra Leone, a full baseline has been built into this programme. This will be completed during the six month inception period and then the current logframe will be revised and the indicators and milestones adjusted where necessary.