DFID Uganda

Sustaining Nutritional Assistance in Karamoja

Full Business Case

October 2011

Intervention Summary

## Title: Sustaining Nutritional Assistance to Karamoja

What support will the UK provide?
The UK will provide £2,751,250 in financial year 2011/12 only.

Why is UK support required?
Up to 650,000 people in the north-eastern region of Karamoja are facing food insecurity. Delayed and haphazard rains during 2010 and the delayed start of rains in 2011 led to lower harvest yields in 2010 and delayed planting in 2011. The migration of pastoralists and herds from neighbouring countries worse affected by the Horn of Africa food crisis has put additional serious pressure on the limited grazing and water resources available to the people of this region. In May 2011 rates of malnutrition in children under five exceeded 12% Global Acute Malnutrition and 2% Severe Acute Malnutrition in half of the districts in the region. / The Ugandan Ministry of Health and its development partners are addressing the situation through a range of health, water & sanitation and nutrition-focused interventions to prevent loss of life and the deterioration of health and nutrition status. These activities are undertaken alongside livelihoods and resilience-building activities supported by a range of UN and other partners. The primary non-governmental implementers of nutrition interventions in Karamoja are WFP and UNICEF. / Due to the stressed food security conditions set out above, estimates of numbers in need of these programmes have increased by about 30% from the initial calculations used by WFP and UNICEF in their programming. Consequently both WFP and UNICEF face immediate shortfalls in required funding for the period August 2011 – January 2012, and longer-term shortfalls for UN financial year 2012.

What are the expected results?
Global and severe acute malnutrition rates maintained within safer levels across Karamoja, helping to bring down child mortality rates and avoid over 1,000 preventable child deaths. / 22,300 vulnerable people provided with supplementary feeding until March 2012 / 6,912 malnourished children under 5 provided with therapeutic feeding until March 2012 / 30,000 households – about 180,000 people – assisted with access to safe water and better sanitation between now and March 2012. / Improved district-level systems for the implementation and coordination of nutrition assistance.

Contents

List of abbreviations

1 STRATEGIC CASE
A Context and need for DFID intervention	5
B Impact and outcome	8

2 APPRAISAL CASE
A Feasible options & theory of change	10
B Evidence base	12
C Costs and benefits	14
D Value for money measures	17
E Value for money statement	18

3 COMMERCIAL CASE
A Selection of funding mechanism and partners	19
B Value for money through procurement	19

4 FINANCIAL CASE
A How much will it cost?	21
B How will it be funded?	21
C How will funds be paid out?	21
D How will expenditure be monitored, reported, accounted for?	22
E Monitoring and reporting of expenditure	22

5 MANAGEMENT CASE
A Management Arrangements	23
B Risks	24
C Conditionality	24
D Monitoring and evaluation	24

Logical Framework	Annex 1

List of abbreviations

DALY	Disability Adjusted Life Year
DFID	UK Department for International Development
GAM	Global Acute Malnutrition
MAM	Moderate Acute Malnutrition
NGO	Non-Governmental Organisation
NUSAF2	Second Northern Uganda Social Action Fund
OCHA	Office for the Coordination of Humanitarian Affairs
OTC	Outpatient Therapeutic feeding Centre
PRRO	Protracted Relief and Recovery Operation
SUN	Scaling Up Nutrition
SAM	Severe Acute Malnutrition
SFP	Supplementary Feeding Programme
TFP	Therapeutic Feeding Programme
UNICEF	UN Children's Fund
UN	United Nations
VHTs	Village Health Teams
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme

Business Case

Strategic Case

A. Context and need for a DFID intervention / What is the food security situation in northern Uganda? / The 2011 Horn of Africa crisis at this stage has had a moderate and localised impact on Uganda. The country has not so far experienced the humanitarian crisis faced by its neighbours. However UN OCHA have estimated that up to 650,000 people in the north-eastern region of Karamoja are facing food insecurity.[1] / Delayed and haphazard rains during October-December 2010 and the delayed start of rains in 2011 led to lower harvest yields in 2010 and delayed planting in 2011. The migration of pastoralists and herds from neighbouring countries worse affected by the crisis has put additional serious pressure on the limited grazing, water and public service resources available to the people of this region. [2] [3] / Given the above, the situation in Karamoja remains of concern. At the moment, it is not clear whether the expected harvest will be enough due to delayed and erratic pattern of rains. Close and continuous monitoring and assessment of crop and livestock is being undertaken by partners. Should a sudden dry spell or crop diseases occur these may seriously affect crops at critical stages and, thus, significantly lower the coping capacity of the population. / In addition, water scarcity associated with the drought may exacerbate the high malnutrition rates. Shortages of safe drinking water, which are common even in normal times in Karamoja, continue to increase the risk of water-borne disease from high usage of unsafe sources. The threat of another widespread cholera epidemic in the region, as was the case in 2010 and early 2011, remains a concern. In addition, the burden of childhood illness is high in Karamoja which risks compounding the nutrition situation. Therefore, in addition to high impact nutrition interventions, access to safe water and interventions including the promotion of sanitation and hygiene to reduce the burden of diarrhoea will prevent further exacerbation of the situation. / Impact on nutrition / The nutritional status of the population in the Karamoja region of Uganda is of serious concern. In May 2011, rates of malnutrition in children under five were 12.8 % Global Acute Malnutrition (GAM) and 2.8 % Severe Acute Malnutrition (SAM) in half of the districts.[4] “Pockets” of high malnutrition rates are increasingly being detected, such as in the district of Nakapiripirit (20% GAM compared to 12% in December 2010 and 9% in May 2010) and Kotido (14% GAM in May 2011 compared to 7% in December 2010 and 10.8% in May 2010). / The analysis of the related nutrition and health indicators denotes high rates of disease burden among children 6-59-months: up to 55% in Amudat and 77% in Abim and Kotido were reported with malaria or diarrhoea or acute respiratory diseases in the 2 weeks previous to surveillance round.[5] Regional Child Mortality figures remain stable compared to December 2010 and May 2011. In terms of adequate feeding practices in the communities and families, the coverage is low – less than 30% of children are exclusively breastfed up to the age of 6 months and nutritious foods such as beans or groundnuts are rare in children’s diet. / From January to May 2011, 4,320 cases of severe malnutrition were admitted into 66 therapeutic feeding sites supported by UNICEF throughout the region. This represents 42% of the estimated 10,337 annual caseload. A total of 1,163 cases were admitted in April alone. While the numbers are comparable to those seen in April 2010, the overall higher level of malnutrition registered in the May 2011 surveillance round is worrying. The increase in admissions puts additional pressure on the staffing and supply capacity of the sites as well as requires intensified coordination with agencies operating nutrition-related programs such as supplementary feeding by WFP. Between August 2011 and March 2012 the estimated SAM caseload to be reached with lifesaving interventions is 6,912. / Undernutrition has immediate as well as long term and societal effects. As well as a leading cause of child mortality, undernutrition leaves long term consequences such as preventing brain and cognitive development. This means children are less likely to enter school and less able to learn and perform in school. Adults who were undernourished as children earn less and contribute less to economic growth. Undernutrition is estimated to reduce GDP growth by 2-3%[6]. / Identification and treatment of acute malnutrition according to the Integrated Management of Acute Malnutrition approach provides an entry point to preventative malnutrition services such as counselling on infant feeding, an important intervention for preventing children from slipping back into malnutrition once discharged from the programme. Opportunities for action on the diseases associated with malnutrition are also offered through linking children and their caretakers with existing health services such as HIV counselling and testing. Particularly pertinent for Karamoja is the link with WASH. / What is being done? / The Ugandan Ministry of Health and its development partners are addressing the situation through a range of health, water & sanitation and nutrition-focused interventions to prevent loss of life and the deterioration of health and nutrition status. These activities are undertaken alongside livelihoods and resilience-building activities supported by a range of UN and other partners. / The primary non-governmental implementers of nutrition interventions in Karamoja are WFP and UNICEF. The UN is targeting support to pregnant and lactating mothers, and children from the ages of 0-5. / Within WFP’s 2011-15 Country Programme: / Livelihoods and resilience-building interventions, including activity in Karamoja to increase community and household resilience to food insecurity through improving livelihoods. DFID is already funding these programmes which reach 75,000 households across the region, and WFP assess that this work has already significantly helped many communities to cope better with the current conditions. / Within WFP’s 2010-12 Protracted Relief and Recovery Operation (PRRO): / Support to extremely vulnerable households in Karamoja, including targeted food distributions with micronutrient-fortified commodities; sensitisation on care practices; community-based supplementary feeding programmes and support to therapeutic feeding, to treat moderately or severely malnourished children. / Within UNICEF’s 2011-14 Country Programme: / Provision of therapeutic feeding sites to treat severely malnourished children, including support for better nutrition practices, training health workers, and conducting tri-annual nutrition surveillance. / Water, sanitation and hygiene interventions, including access to safer water and sanitation facilities, the promotion of safe hygiene practice and work to prevent disease outbreaks. Recent analysis has concluded that water scarcity and disease (particularly diarrhoea) are significant causes of increased malnutrition levels among children. / Due to the stressed food security conditions set out above, estimates of numbers in need of these programmes have increased by about 30% from the initial calculations used by WFP and UNICEF in their programming. Consequently both WFP and UNICEF face immediate shortfalls in required funding for the period August 2011 – January 2012, and longer-term shortfalls for UN financial year 2012. / In late July, as part of their broader Horn of Africa appeal, WFP identified a need for $5.2m for the remainder of 2011. This includes $1.2m for the Protracted Relief & Recovery Operation and a further $4m for activities under the Country Programme. In discussion, they identified a further $500,000 required for the PRRO for the period Jan-March 2012. UNICEF issued an appeal in July for immediate needs in Karamoja totalling $896,000 for nutrition and $1.55m for WASH. So far Japan has made a firm commitment to the WFP Country Programme appeal, worth $500,000; a planned contribution from Germany will help cover outstanding requirements for targeted food distribution under the PRRO. / How do we know this is effective? / There is good evidence of nutrition-related interventions in the health sector[7]. DFID’s 2009 strategy on The Neglected Crisis of Undernutrition concluded that “sound nutrition can bring profound benefits in terms of survival, health, education, economic growth, poverty reduction and empowerment. It is a foundation for the attainment of the MDGs and an investment in the future”[8]. It reviewed the evidence on effective interventions, and found that among direct interventions, “breastfeeding promotion, complementary feeding, vitamin A and zinc supplementation and management of severe acute malnutrition showed most promise for reducing child deaths and the future disease burden related to undernutrition. / The strategy noted that in addition to the right direct interventions, “leadership and strategic capacity are essential ingredients for advancing the national nutrition agenda” – an effective response often requires changes to be made to the national strategic approach to nutrition issues. / There is moderately strong Uganda-specific evidence about the effectiveness of existing WFP and UNICEF programmes, demonstrating that the UN’s nutrition programming has helped in previous years to keep GAM rates below 10%. This is examined in more detail in the appraisal case below. / What is the international and national policy context? / Based on the evidence that shows how improved nutrition affects improved health, wealth and well-being, the international community agreed that a broad framework and partnership for collective action was needed and consequently nutrition stakeholders from governments, donor agencies, civil society, the research community, the private sector, intergovernmental organizations and development banks developed a Framework for Scaling up Nutrition[9]. / Uganda is an “Early Riser Country” under the SUN process, which is based on the principle that international assistance will be aligned to country-led plans and priorities and countries will lead their own efforts to scale up nutrition. DFID offices in the “Early Riser Countries” have agreed to use the global SUN process to help galvanise stronger national commitments to tackle undernutrition. / As part of this agenda, Uganda has launched a Nutrition Action Plan 2010-15 (NAP) with a budget of around $70 million. This plan incorporates many elements of the draft Food and Nutrition Bill, which is yet to be passed by Parliament. The National Planning Authority is currently leading on the NAP and it is in the process of making the Uganda Food and Nutrition Council and its Secretariat functional. The Council and the Secretariat will provide an institutional home for nutrition. However the plan is not yet being funded and is not yet operational: we will engage with WFP and the Government of Uganda to identify ways to accelerate this process. / Why should DFID intervene now? / This Business Case adds detail to the decision taken in principle by the Secretary of State for International Development on 11 August 2011, that the UK should contribute to the UNICEF and WFP nutrition appeals for Karamoja. / This decision took into account that the response to the UN’s appeal for new funds for Karamoja has so far been limited – only Japan and Germany have made additional commitments, and this will meet only part of the estimated shortfall. Given the critical requirements of other parts of the Horn of Africa, it is likely that most new resources will be directed towards emergency needs elsewhere. Should the shortfall remain unfunded, consequences would include: / A reduction or break in the provision of nutritional assistance to the most vulnerable groups in Karamoja; / Increased likelihood of a renewed need for emergency food distribution in the region, which could require a higher level of financial commitment from donors including the UK and would be a set-back to the strategy of building resilience; / Further worsening of GAM levels, remaining beyond targets under DFID Uganda’s Country Operational Plan; / Failure of development partners to support Government of Uganda development of a Nutrition Action Plan which will improve future response. / DFID has to date focused its resources in Karamoja for 2011-15 on WFP’s implementation of the Second Northern Uganda Social Action Fund (NUSAF2), which is working to build resilience through community-led projects and cash/food transfers to improve livelihoods opportunities. This reflects a commitment to help the region move away from cyclical reliance on expensive and unsustainable emergency food aid. The approach is proving successful: so far in 2011 74,210 households have enrolled in the programme, 1,330 sub-projects have been approved, and 73,876 households have received either food or cash transfers in return for their work on these projects. WFP assess that the reduced need for emergency food aid in Karamoja (compared for example to neighbouring regions of Kenya) is in part attributable to this intervention. / However the most vulnerable groups in the region continue to rely on the various levels of “safety net” currently provided by WFP and UNICEF. The increased demand for these interventions in 2011 has created a risk that existing programmes cannot be sustained to the end of the year. Without these “safety nets” in place, the integrated approach to undernutrition risks failing, which would make a renewed need for emergency food aid more likely.
B. Impact and Outcome that we expect to achieve / The outcome of this intervention will be to maintain global acute malnutrition within DFID’s target threshold of 10% on average across all districts of Karamoja, and severe acute malnutrition within 2.5%. / At the impact level, this will help to reduce under-5 mortality rates in Karamoja to below 160 per 1,000 live births, and to reduce crude mortality rates in the region below 1 per 10,000 people per day. / These outcome and impact targets are in line with the DFID Uganda Results Framework, developed alongside the 2011-15 Country Operational Plan.
[1] WFP Horn of Africa update, WFP Regional bureau ODRK. July 13 2011 Phase 2 - moderate/borderline food insecurity
[2] Eastern Africa Drought Humanitarian report no.1, 29 March 2011. OCHA
[3] Karamoja region food security situation analysis, June 2011. HSU Karamoja
[4] MoH/UNICEF/ACF surveillance round report May 2011
[5] DHOs/UNICEF/ACF surveillance report May 2011
[6] DFID (2009) The neglected crisis of undernutrition: Evidence for Action. London: DFID.
[7] Bhutta, Z. A., Ahmed, T., Black, R. E., Cousens, S., Dewey, K., Morris, S. S., Sachdev, S. P. S., & Shekar, M. (2008). What works? Interventions for maternal and child undernutrition and survival. The Lancet. Series: Maternal and child undernutrition 371, 417-440.
[8] DFID (2009), The neglected crisis of undernutrition: Evidence for Action. London, DFID
[9] Scaling Up Nutrition – a Framework for Action See: http://www.unscn.org/files/Announcements/Scaling_Up_Nutrition-A_Framework_for_Action.pdf (accessed 03.03.2011)

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The theory of change for this intervention is based on extensive evidence from existing UN nutrition programmes in the Karamoja region. Global and severe acute malnutrition will be reduced by providing supplementary and therapeutic feeding to those who need it the most; preventing disease outbreaks (particularly diarrhoeal diseases among children) through safe water and better sanitation; and helping districts to recognise the warning signs of malnutrition and respond accordingly. In turn, this will help to drive down the number of preventable childhood deaths in the region. / Option 1: The ‘Do Nothing’ Counterfactual / Reject the proposal from UNICEF and WFP. Re-programme £2.75m elsewhere. / We judge that this would result in UNICEF and WFP maintaining August 2011 levels of nutritional support in Karamoja over the 8 months to March 2012, compared to the increased levels of coverage they could reach with DFID support. / Option 2: Contribution to WFP and UNICEF Uganda / The option described here is assessed to be the only feasible one in this context for achieving the outcome and impact above, since it would be inappropriate to put in place new arrangements for this short-term assistance. This was the option approved in principle by the Secretary of State for International Development on 11 August 2011. / The activities described here are those which have been prioritised by the existing providers of nutritional assistance in the region, UNICEF and WFP. / In line with the theory of change above, DFID funds will be used to achieve three outputs: / 1. Malnourished children and individuals receive appropriate treatment and care / Under this output, WFP will provide community-based supplementary feeding to children and others suffering from moderate acute malnutrition, and UNICEF will provide therapeutic feeding to those suffering from severe acute malnutrition. The programme will aim to achieve coverage of 80% of those who meet these criteria – a level judged feasible given the difficulties of access in Karamoja and the staffing and resource constraints of districts and other implementing partners. / WFP will use funds to procure food commodities (cereals, pulses, corn soya blend, oil and sugar) to cater for the supplementary food needs of the targeted moderately malnourished children/individuals and contribute to the rehabilitation of the severely malnourished children in the UNICEF supported Therapeutic Feeding Programme. Furthermore related costs such as transport, storage and warehousing costs and payment of partner costs will also be met from the contribution. / In addition WFP will undertake complementary activities such as community mobilization and sensitization, nutrition and health education, promotion of backyard vegetable gardens, creation and support of community support groups such as parental care groups, and the creation and support of parental groups to promote good health and nutrition practices. / UNICEF will use funds to support the procurement of therapeutic supplies to ensure “zero” stock-outs on items used for treatment of severe acute malnutrition This will be combined with strengthened logistics and an end-user monitoring system. / UNICEF will also provide technical support, coaching, mentoring and supervision of 373 health workers in 66 supported sites to ensure provision of quality care in therapeutic feeding programmes. The programme will support the establishment of 2 more Outpatient Therapeutic Centres (OTCs) at HC II (1 in Kaabong and 1 Moroto, two health centres in extremely hard to reach areas). UNICEF will mobilise 2,968 village health teams in the catchment areas of the health facilities for case identification, referral and follow up. / UNICEF will intensify support at community level for the promotion of nutrition, health and hygiene practices, through the use of VHTs, women groups and other informal networks; and will train 210 health workers in the Uganda national comprehensive Infant and Young Child Feeding (IYCF) package in all the 7 districts of Karamoja, with 30 health workers selected in each district.[10] / Finally, this contribution will enhance programme monitoring and co-ordination by facilitating regular joint WFP/UNICEF, partner and district monitoring and support supervision and monthly coordination meetings as a way of promoting harmony between the SFP and TFP. Issues discussed in the monthly meeting will feed into the Karamoja regional quarterly nutrition and health coordination meetings and other meetings related to the implementation of the Ministry of Health’s integrated management of acute malnutrition (IMAM) strategy. / 2. Safe water facilities, sanitation and hygiene practices are provided and promoted in health centres, schools and rural communities / The present coverage of safe water in Karamoja varies from 30 – 40% with a high reliance on unsafe and unprotected water sources. In addition, sanitation coverage is very low, resulting in a very susceptible environment for multiple health risks including diarrhea and epidemics such as Cholera and Hepatitis E. / This output will be led by UNICEF’s WASH team. DFID-funded activities will provide access to safe water to an additional 30,000 households and health centres in the most affected areas, and re-establish access to improved drinking water sources through regular chlorination, operation and maintenance of water points, including boreholes. Household water treatment will be focussed on families with malnourished children and distributed through the integrated management of acute malnutrition programme. / UNICEF will also use UK funds to provide adequate sanitation facilities to children in schools and people at health centres. This will include the construction and rehabilitation of household and communal latrines in the affected communities whose health and hygiene has been affected by drought; by supporting latrine construction with provision of building materials and sanitary digging kits; and constructing latrines at health facilities. / Finally UNICEF will promote safe hygiene practices in rural communities, school and health centres including hand washing practice. This part of the programme will include the provision of critical commodities to promote hygiene practices such as soap distribution to each household and school child alongside hygiene promotion messages. / 3. Communities and districts are better able to obtain and analyse timely, frequent and quality data on nutritional vulnerability and to take action accordingly / At the local level in Karamoja, the nationally-led response to undernutrition can be improved through better training of village health workers and local staff in health facilities, more reliably to identify cases of acute and chronic malnutrition and to provide appropriate referral and follow-up. / Under this programme, UNICEF will provide refresher training for 140 health workers, 7 district surveillance focal persons and 7 district health officers on the food and nutrition security assessment (FNSA) methodology; and support supervision and data collection, interpretation and report writing for one round of the FNSA in all the 7 districts of Karamoja; / The programme will also support monthly field monitoring for Community vulnerability system (CVS) targeting the 200 VHTs and 80 health workers, and support district based monthly analysis for CVS data. / 2,100 children under five will be screened for malnutrition and referred to care as needed: 300 in each district.
B. Assessing the strength of the evidence base for each feasible option / Global economic evidence / Sanitation and hygiene promotion are the two most effective interventions for controlling endemic diarrhoea and are the most cost-effective public health intervention (approximately US$3 per DALY averted for hygiene promotion and US$11 for sanitation promotion) ranking higher on this basis than any other form of health intervention (e.g. combating malaria, tuberculosis and HIV/AIDS)[11]. Prüss-Üstün et al. (2008) estimate that the global savings from the combination of improved domestic water supply and sanitation in rural and urban areas is US $8 for every US $1 invested. / In addition to diarrhoea prevention, better access to safe sanitation and water frees time for more productive use, such as increased production, improved education levels or more leisure time. Evidence shows that for a six-person household, the time savings amount to 30.4 and 91.25 hours saved per individual per year, for improved access and piped water respectively[12]. / Uganda-specific evidence / The treatment of acute malnutrition was traditionally facility based. However, past experience from facility based SFP/TFP has shown that facility based models have not been effective due to limited coverage, accessibility, distances from patients, low health staffing levels and also other competing needs and obligations at household level. These challenges have often resulted into poor performance of programmes. / Community based interventions have been designed to address these gaps and also promote both existing health worker and community participation and involvement. Uganda recently rolled out a model for the integrated management of acute malnutrition, comprised of four components: community outreach, in-patient therapeutic care (ITC), out-patient therapeutic care (OTC) programmes and supplementary feeding programmes. The community outreach component involves early identification of malnourished individuals at community level to enable early detection and referral and to increase the number of cases that can access quality and timely treatment. The WFP community based SFP is designed to fit within this framework to address the challenges highlighted above. / Recent monitoring reports on food security in Uganda indicate that community-based SFP reaches up to 20,000 children on average per month as opposed to 6,000 in 2008 before the roll out of the community-based approach. Improved community and health worker involvement has resulted in improved awareness and empowerment. Capacity development (training of health workers and community support groups - VHTs, mother groups) has shown positive response in terms of promotion of good health and nutrition practices. Creation of outposts/outreach sites closer to communities has increased access to other complimentary health services such as immunization, de-worming and health education. It has further reduced distances moved by clients to access supplementary feeding services and improved reporting on performance of the programme. / WFP’s current strategy draws on the findings of the end-term-evaluation of its previous PRRO. This found that general distributions, supplementary and therapeutic feeding played a critical role in keeping GAM rates below 10%. However, it noted with concern the increased malnutrition rates in return areas once food assistance stopped, and indicated the importance of developing an appropriate phase-out strategy. It found that village health teams needed additional training on nutrition to improve their ability to refer patients.[13] An earlier DFID evaluation of the UN’s joint nutrition programmes in north and north-eastern Uganda found similar conclusions.[14] / DFID’s completion review of WFP’s emergency operations in 2008-10, which included support for supplementary feeding, concluded that the programme had made a significant contribution to stabilising and preventing a more serious deterioration in the overall food security situation and nutritional status. It also noted that the community based distribution approach for supplementary feeding is new to Karamoja and warranted further systematic evaluation in order to identify its utility, cost effectiveness and lessons learned. / In early 2011 Makerere University School of Public Health produced an independent review of UNICEF’s IMAM operations, to underpin plans to scale up the approach. This found that the level of IMAM training in health facilities was high, the medicines and supplies for IMAM were available in most facilities most of the time, and adherence to IMAM treatment procedures was considered reasonably high. It also identified weaknesses to be addressed, including a shortage of skilled personnel in IMAM facilities, weak referral mechanisms at all levels, inadequate data management and analysis, and limited support supervision and commitment from districts. / The proposed treatment of children with severe acute malnutrition is in line with the national guidelines on integrated management of acute malnutrition as well as global WHO/UNICEF recommended approaches. / Option Evidence rating / 1 Strong. Nutritional indicators will worsen / 2 Strong. Existing interventions will be sustained, whose costs and benefits have been measured extensively through impact evaluations. / Climate and environment relevance of options / The programme may have an indirect positive impact on the environment. As part of prevention activities within the community based supplementary feeding programme (CBSFP), community members, caregivers, and mother support groups are sensitized and trained on proper food preparation, hygiene and proper waste disposal methods which promote safe environment. However, this programme does not directly address environment or climate change and is judged to be low risk and low opportunity (category C). / WFP supports other programmes such as the NUSAF2 livelihoods programme, also funded by DFID, that more directly address environmental conservation and climate change. / Option Climate change and environment risks and impacts, Category (A, B, C, D) / 1 C / 2 C
C. What are the costs and benefits of each feasible option? / Option 1: The ‘Do Nothing’ Counterfactual / Costs / 6,912 cases of severe malnutrition not provided with lifesaving interventions resulting in morbidity and mortality. 30,000 additional households without access to safe water facilities and 15,000 additional people and 2,500 children without access to sanitation services. These are the current costs of inadequate sanitation facilities in Karamoja. / In the absence of the proposed nutritional services, around 504 additional MAM children are likely to die in eight months. Similarly, in the absence of the proposed nutritional services, 638 additional SAM children are likely to die. / Benefits / In theory, £2.75m can be reprogrammed to other parts of the DFID Uganda portfolio or returned to the centre. In practice, there are no competing alternative uses of the funds within DFID Uganda priorities at this point. / Option 2: Support WFP / UNICEF proposals / Costs / The total financial cost of the programme is £2.75m, allocated as set out in the financial case below. Since the programme will be administered by UNICEF, WFP and their NGO partners, the additional resource costs in terms of DFID staff time will be negligible. / All costs will be incurred in the period to March 2012, with both expenditure and activity complete by the end of the UK 2011/12 financial year. / The main cost driver for nutrition programming is food costs, representing about 61% of total costs for these activities. WFP are well placed to obtain best value through good knowledge of suppliers and bulk purchasing procedures. / The main cost of the WASH program (78%) is for rural water supply infrastructure (new water points). There is uncertainty over the sustainability of this new infrastructure as we do not know at this stage whether the Government of Uganda will be allocating additional resources for maintenance of the water points. This is an assumption within the programme which DFID will monitor closely with UNICEF. / Benefits / The health benefits from nutrition and WASH interventions stem from: (a) savings to households and public institutions with a reduction in the use of medical care; (b) income from productive activities to households through the reduction of adult sick days; (c) income from productive activities to households through the reduction of child sick days; and (d) added output over a lifetime through reductions in mortality. / The calculation of benefits also comes with significant externalities. These are: (1) the cost savings to households going from high cost water sources to lower cost sources; (2) time savings to households (particularly women) who spend less time gathering water and devote more efforts to productive activities; (3) business value-added for firms that could not be established or expanded due to existing water supply constraints; (4) health benefits through the reduction in diarrhoea and malaria. / This appraisal case focuses on (2) and (4) only in response to DFID guidance on proportionality[15]. / (i) Nutrition component. / The proposed interventions will provide nutrition services, over an 8 month period, to 22,500 moderately acute malnourished (MAM) children per month; and 5,530 severely acute malnourished (SAM) children. For the severely malnourished, death rates with 70% intervention effectiveness are almost halved, from 30/100 to 18.45/100[16]. For the moderately malnourished, with 70% intervention effectiveness, death rates are more than halved - from 5 to 2.2 per 1000 per month[17]. As a result, the proposed nutrition interventions are likely to avert 1,143 child deaths in eight months (around 143 deaths per month) or produce 37,719 healthy years of life (DALYs)[18]. The cost per DALY for these interventions is £14, which is highly cost-effective[19]. / (ii) WASH component. / The expected stream of benefits arising from the WASH intervention is comprised of the following: / Time saving to households (particularly women) who spend less time gathering water and devote more efforts to productive activities / Health benefits arising from fewer cases of diarrhoea. / Valuing time saved from more water points / The opportunity cost of fetching water can be estimated by monetising person-hours spent fetching water. The loss formula is / Tsfw/Twork x Yh; / where Tsfw is time spent to fetch water; Twork is total normal working day time; Yh is average daily household income. / 1.5[20]/8 x 3,907[21] = UGX 735 / Therefore, if 30,000 additional households are served with a convenient water point by the end of the 8-month intervention period (thus eliminating the 1.5 hours per day spent fetching water) the time saved is worth UGX 22 million daily (in 2009 prices). This is a very conservative estimate, since benefits are likely to be accumulated beyond the life of the programme itself; these have not been valued since the lifespan of water points is at this point uncertain. Converted into US$ using an exchange rate of 2,030 UGX = $1 the time saved by constructing more water points serving 30,000 additional households is estimated to be worth $10,837 per day. / Estimating savings to household medical bills / The annual estimated economic benefit from reduction in health costs per household is computed as follows: / Hh x Sshare x 12; / where Hh – total household monthly expenditure in health related services; Sshare – share of sanitation related ailments in total monthly household expenditure in health services. / 1,704[22] x 0.2[23] x 12 = 4,090 / We therefore multiply the reduced health costs per household of 4,090 by the number of households served (30,000) and suggest that over UGX 122 million or US$60,000 is saved per annum, assuming that sanitation related ailments are 100% eradicated. / The aggregate benefits of the nutrition and WASH components are summarised below: / Stage 1 / Who benefits, how and when Stage 2 / Quantification Stage 3 / Monetary value / The nutrition component ensures 80% of children in Karamoja with severe malnourishment receive appropriate treatment between August 2011-March 2012. 1,143 child deaths averted / 37,719 healthy years of life (DALYs)[24] saved Value of averting deaths not monetised. / Cost per DALY = £14. / The WASH component ensures 30,000 additional households are provided with safe water facilities by March 2012. Time saved by constructing more water points serving 30,000 additional households = 5,625 hours per day. / Health savings assuming that sanitation related ailments are eradicated $10,837 per day or around $2.63m over 8 months through time saved. / US$ 60,000 per annum healthcare savings, or around $40,000 over 8 months. / Sensitivity analysis / The intervention builds on existing UNICEF and WFP programmes, making it unlikely that any of the key assumptions about implementation will change over the 8-month period. One factor which could alter the numbers of malnourished people in Karamoja is rainfall. The proposal given to DFID was dated August 2011 and is based on rates of malnutrition from January to May 2011. The SAM caseload between August 2011-March 2012 is an estimation. / It is possible that rainfall is more favourable to the Karamoja region in the last quarter of 2011 and water is not as scarce as expected. Even if we halve the numbers of MAM and SAM children, resulting in 11250 MAM and 2,765 SAM, the intervention still averts 571 deaths and saves 18,843 DALYs. The cost per DALY is still highly cost-effective at $46 (£29).
D. What measures can be used to assess Value for Money for the intervention? / Evidence of the economy of inputs and efficiency of implementation through WFP and UNICEF can be collected by monitoring unit cost information as follows: / Unit cost of nutrition interventions per severely and moderately malnourished child / Unit cost per new borehole or per pit latrine, including cost per beneficiary / WASH costs per household, to include promotion of good hygiene behaviour, sanitation facilities, and water points maintenance. / Cost per DALY saved through nutrition interventions. / Comparison with costs in other countries / According to a study carried out by WashCost[25] / In Burkina Faso: Total expenditure on traditional pit latrines (TPLs) in rural and peri-urban areas ranges from 1-4 US$ per capita per year. Total expenditure on VIP latrines in peri-urban areas ranges from 4-22 US$ per capita per year (7 US$ is the median) / In Ghana: Total expenditure in rural areas (only VIP) ranges from 2-10 US$ per capita per year / In Mozambique: Total expenditure on traditional pit latrines in rural areas ranges from 0.30-2.5 US$ per capita per year. Total expenditure on slab latrines in rural areas ranges from 0.5-2.5 US$ per capita per year
E. Summary Value for Money Statement for the preferred option / The economic appraisal set out above has estimated the incremental benefits of the proposed intervention (Option 2) over and above the do nothing counterfactual. / For the investment in WASH of £907,000, the benefit-cost ratio is 2:1. / The nutrition component adds 37,719 DALYs on top of this, at a cost of between £14 and £29 (well within the value for money threshold of £300 per DALY, calculated from GNI per capita).
[10] Health workers to be selected should be from the supported Therapeutic feeding programs. Already 1 round of training on IYCF through district budget support ongoing targeting about 150 health workers
[11] Laxminarayan, R., Chow, J., and Shahid-Salles, S.A. (2006) Intervention Cost–Effectiveness: Overview of Main Messages. Chapter 2 in “Disease Control Priorities in Developing Countries (2nd Edition)”. Edited by Dean T. Jamison et al World Bank, Oxford University Press.
[12] Evaluation of the Costs and Benefits of Water and Sanitation Improvements at the Global Level, Guy Hutton and Laurence Haller
[13] WFP, Protracted Relief and Recovery Operations project document, Rome, 2009
[14] Attawell, Kathy, Evaluation of joint UN emergency health, nutrition and HIV/AIDS programme in North and North Eastern Uganda, DFID, August 2007
[15] Refer Para 66 of How to Note: Writing a Business Case (August 2011)
[16] hhtp://www.who.int/nutrition/topics/malnutrition/en/index.html; Under-five mortality rate for severe acute malnutrition ranges between 30% to 50%
[17] Malnutrition and Mortality - the use of epidemiological tools in conflict-affected populations; hhtp://conflict.Ishtm.ac.uk/page_139.htm
[18] We assume 1 child death averted is equal to 33 DALYs (WHO).
[19] Cost effectiveness is defined as cost per DALY < GNI per capita which is £300 (2009)
[20] According to the Uganda National Household Survey 2009/10, rural Ugandans spend 26 hours per week on ‘care labour activities’ (= 3.7 hrs per day). This includes collecting firewood and fetching water (including travel time), construction of own dwelling/farm building, milling and other food processing for the household. Following a similar economic appraisal of a watsan programme by DFID Mozambique (PRONASAR), we assume that 1.5 hours per day are spent fetching water alone.
[21] Source: Uganda National Household Survey 2009/10. Average monthly household income for rural Northern Uganda was UGX 117,200. We convert this to a daily figure (dividing by 30) to get 3,907.
[22] Source: Uganda National Household Survey 2009/10. Mean Consumption Expenditure per capita per month in rural Northern Uganda is 28,400, of which 6% is allocated to health. Therefore monthly spend on health is 1,704.
[23] We assume that a fifth of the spending on health is for diarrhoea treatment and treatment for other water-borne diseases.
[24] We assume 1 child death averted is equal to 33 DALYs (WHO).
[25] WashCost: Research conducted by WASHCost has highlighted just how little is known about what communities invest in toilets, sanitation and hygiene. The analysis of costs and service levels is providing the best available data based on expenditures of governments, programmes and households – as illustrated with findings from rural and peri-urban areas and small towns in Ghana, Burkina Faso and Mozambique.

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / Both WFP and UNICEF are particularly well placed to manage these interventions. They have a strong track record and ground presence in Karamoja, and are engaged with national policy processes. They have already developed a coordinated, integrated approach to undernutrition with the support of the UN Resident Coordinator’s Office. No other agency or NGO is judged to be able to combine these functions of delivery and advocacy in a similar way. / WFP has a strong comparative advantage in the delivery of food commodities at scale in Karamoja where it has an established field presence. Furthermore, WFP has a growing global role in hunger and nutrition advocacy and is therefore well placed to design and implement effective nutrition programmes whilst building capacity / UNICEF Uganda works to help the Government of Uganda to meet its obligations under the UN Convention on the Rights of the Child, through a new "Country Programme of Cooperation" (currently running from 2010 to 2014). The UNICEF Moroto Office is responsible for operations in the Karamoja region. At the national level, UNICEF is working with the Ministry of Gender Labour and Social Development, Ministry of Health and Ministry of Water on a transition/handover plan for coordination functions of the child protection, nutrition and WASH clusters / Both UN agencies will work through a network of NGOs as implementing partners on the ground, which will provide the local and thematic expertise required. / DFID will put in place Memoranda of Understanding (MoU) with both agencies for the implementation of this intervention, using existing standard DFID MoU templates. This will include provision for the payment of indirect costs to agencies based on pre-negotiated standard rates.
B. Value for money through procurement / WFP has selected partners through a competitive process whereby a request for proposals is advertised at regional level. Proposals received from interested organisations are screened for a number of factors including technical abilities to implement IMAM activities. / WFP’s process involves a first level of evaluation at district level by the field team and district health authorities while the second level evaluation is done at Kampala level. The organisation selected then signs a tripartite field level agreement with WFP and district. The agreement outlines the obligations of WFP, partner and the district. / WFP together with partners and district counterparts conducts mid-term reviews to assess programme performance against the set objectives. Furthermore, at the end of the contract period, WFP in collaboration with the districts conducts partner performance reviews in line with the obligations defined in the field level agreements. The results of these two reviews inform the decision to either renew a contract through an old partner or search for a new partner through a call for proposals. / UNICEF will use a similar competitive contracting process for WASH activities. Therapeutic feeding activities will be implemented through NGOs who hold a standard Programme Cooperation Agreement.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total cost of the activities in this programme will be £2,751,250 between August 2011 and March 2012. / The approximate allocation of funds to outputs of the programme will be as follows. Overhead and organisational costs are included within these totals: / Output Amount (£) % of total / Malnourished children and individuals receive appropriate treatment and care 1,711,441 62 / Safe water facilities, sanitation and hygiene practices are provided and promoted in health centres, schools and rural communities 907,397 33 / Communities and districts are better able to obtain and analyse timely, frequent and quality data on nutritional vulnerability and to take action accordingly 132,412 5 / Total 2,751,250 100 / The division by implementing partner will be: / Partner Amount £ sterling % of total / WFP 1,241,875 45 / UNICEF 1,509,375 55 / Total 2,751,250 100 / Funds will be paid in a single instalment (see section C below), so there are no issues around accurate monthly forecasting for DFIDU.
B. How will it be funded: capital/programme/admin? / The programme will be funded from the DFID Uganda programme resource budget, and has been budgeted for in the Operational Plan for DFID Uganda.
C. How will funds be paid out? / Funds will be paid in one instalment to WFP and UNICEF, made in November 2011. This will be a payment in arrears for activities from August 11, and in advance for the four months to March 2012. Given the short-term nature of this intervention it would be inappropriate to make an advance payment for the quarter to February and then a single additional payment for the month of March 2012.
D. What is the assessment of financial risk and fraud? / UK funds will be held and managed by UN agencies who have adequate financial management capacity in Kampala and on the ground in Karamoja. DFID has worked previously with both UNICEF and WFP without experience of funds being misused or diverted. / We judge the financial risk attached to this intervention to be low.
E. How will expenditure be monitored, reported, and accounted for? / Both UNICEF and WFP will submit formal final progress reports, including full financial information on income and expenditure, to DFID within 2 months of the end of the programme in March 2012. This reflects the emergency nature of the intervention and the short term funding being provided by DFID. / The DFID Programme Manager will meet WFP and UNICEF officials for an update on progress and spend at regular points throughout the programme (at least every 3 months, currently planned for November 2011 and February 2012).

Management Case

A. What are the Management Arrangements for implementing the intervention? / DFID Uganda will provide oversight of the project. The B1D Programme Manager will meet WFP and UNICEF representatives at least every three months to review progress, spend and any issues with implementation. He or she will be supported by the Health Adviser and Social Development Adviser. / WFP / The programme is implemented in all the 7 districts in Karamoja region in partnership with two non-governmental organizations (NGO’s): Andre Food Consult (AFC) for South Karamoja, and Community Action for Health (CAfH) for North Karamoja. At the district level, WFP works closely with the District Health Office and targeted health centre staff. Within the community, implementing partners have trained community volunteers and village health teams (VHTs). The district authorities identify and support in the training of VHTs involved in the programme. Once trained, the VHT’s are able to identify, screen and refer moderate/acute malnutrition (MAM) cases for further screening and treatment by health and partner staff. / The SAM cases identified by VHTs are referred to UNICEF supported therapeutic treatment centres for treatment and later discharged into the SFP for follow-up. WFP supports TFP clients (in third phase) and one caretaker per patient. TFP discharges are admitted into SFP for two months for further support and follow-up. This is to prevent re-admissions to the TFP as much as possible. / To reduce distances to and from health centres - which can often prevent beneficiaries from attending facilities for treatment - outposts have been created closer to communities. WFP delivers food to the main health facilities and the partner manages the distribution from the health centres to outposts/outreach sites closer to communities. The community volunteers also participate in food distribution and other community related activities such as sensitization on health and nutrition issues. / UNICEF / District administrations are the main partners to spearhead the implementation of the interventions at district level, to ensure proper ownership, oversight, and sustainability. / Current partners in nutrition (Action Contre la Faim and Concern Worldwide) will be involved in supporting districts for the treatment of severe acute malnutrition and capacity development of health workers; CESVI for community mobilisation and ACTED for the implementation of the community vulnerability surveillance system. / Similarly the WASH program will partner with International/National NGOs including C&D, CESVI, IRC and ACF alongside government to build on their experience in their areas of operation and expertise in order to promote sustainability. / UNICEF has Project Cooperation Agreements with these implementing Partners and these work with local district administrations in the framework of the cooperation agreement between UNICEF and Government of Uganda.
B. What are the risks and how these will be managed? / Overall this is assessed as a medium risk programme. Although there is good evidence about the activities proposed, and our level of confidence in implementing partners is high, the nature of the working environment in Karamoja will remain very challenging. Renewed insecurity, drought or flooding all risk reducing the outcome of the programme overall. / Description of risk Probability Impact Mitigation strategy / Insecurity caused by intertribal cattle raids, or poor road condition caused by flooding, limits access by partners to parts of the region. Medium Medium Tolerate. WFP, UNICEF and their partners are experienced under these conditions. / Increasing food and fuel prices lead to high operational costs, resulting in necessity to scale down implementation plans. Medium Medium Tolerate. Budgets reflect current high prices, and the short-term nature of this programme will limit the possibility of very significant unexpected increases. / Drought and disease outbreaks lead to increased needs for vulnerable people or difficulty in implementing safe water access. Medium Low Tolerate. Although this may increase the level of need, its impact on the programme’s ability to achieve the results set out already will be limited. / Other institutions involved – Ministry of Health, district governments – do not perform effectively in expected roles. Low High Treat. The programme will help strengthen district capacity, and DFID will continue to push WFP and UNICEF to cooperate effectively with central institutions on nutrition issues.
C. What conditions apply (for financial aid only)? / Not applicable to this programme.
D. How will progress and results be monitored, measured and evaluated? / Monitoring / WFP and UNICEF will provide routine monitoring of output indicators in the logframe. The targets in the DFID logframe have been discounted by around 10% from targets set out in WFP and UNICEF proposals and used in the appraisal above, to ensure realism. The sensitivity analysis included in this Business Case demonstrates that even underachievement by 50% would still represent value for money. / Outcome indicators will be measured through ACF/UNICEF nutritional surveillance reports, which are carried out on a quarterly basis. / WFP / WFP has 5 sub-offices in the Karamoja region, which provide a strong monitoring function “on the ground”. In addition monitoring is conducted by partners and district health technical staff. Partners consolidate monthly progress reports from supported outposts/outreaches for the health centres and submit one report to the WFP field office. This information is entered into WFP’s web-based Programme Database by WFP field monitors who work closely with the partner and with district health teams. From the database, monthly and quarterly reports are generated, which will be shared with DFID. / WFP has organised mid-year programme reviews at regional level to check the overall progress of the programme, share best practices and challenges as well as address key issues affecting the smooth operation of the programme. / UNICEF / Through UNICEF’s Zonal Office in Moroto for Karamoja region, UNICEF staff will continuously monitor progress and interact with implementing partners to take corrective actions if required. This will be done through field visits, meetings and reports submitted to UNICEF by implementing partners. Programme quality assurance will also be conducted on a quarterly basis for all implementing partners and districts (this includes financial spot checks). / The monitoring system for this project is based on the UNICEF/Government of Uganda Country Programme monitoring framework. As part of this framework, UNICEF, working with the local government authorities, will develop a district monitoring plan in collaboration with NGO implementing partners. / Evaluation / There is no independent evaluation planned for this programme, given its short-term nature, the relatively low financial commitment, and the strength of existing evidence on nutrition interventions in the region and more widely.
Lograme / Quest No of logframe for this intervention: 3231357