DFID Zambia

Tackling Maternal and Child Undernutrition in Zambia

Business Case

October 2011

Table of Contents

Glossary

Malnutrition: an abnormal physiological condition caused by deficiencies, excesses or imbalances in energy, protein and/or other nutrients.

Undernutrition: when the body contains lower than normal amounts of one or more nutrients, i.e. deficiencies in macro-nutrients (food) and/or micro-nutrients. Undernutrition encompasses stunting, wasting and deficiencies of essential vitamins and minerals (collectively referred to as micronutrients).

Stunting: refers to short stature (or low height for age) and is an indicator of long-term nutritional status.

Wasting: refers to acute loss (or low weight for height) and is an indicator of short-term nutritional status.

Severe Acute Malnutrition (SAM): a weight-for-height measurement of 70% or less below the median or 3 standard deviation of more below the mean international reference values, or a mid-upper arm circumference of less than 115 millimetres in children 6 to 60 months old.

Low birth weight: refers to a birth weight of less than 2,500 grams. This may be due to prematurity, growth restriction, or a combination of the two.

Micronutrient deficiencies: refer to inadequate intake and/or absorption of vitamins and minerals that are essential for healthy growth and survival. Globally, the most critical deficiencies are Vitamin A, iron, iodine, zinc and folic acid, due to their importance in the immune system, organ development and growth. Micronutrient deficiencies are measured by a variety of indicators, including biomarkers and clinical signs.

Food security: when all people, at all times, have physical, social and economic access to sufficient, safe and nutritious food that meets their dietary needs and food preferences for an active and healthy life.

Nutrition security: is achieved when secure access to appropriately nutritious food is coupled with a sanitary environment – alongside adequate health services and care, this ensures a healthy and active life for all household members.

Hunger: is often used to refer in general terms to MDG 1 (to eradicate extreme poverty and hunger) and food security. Acute hunger occurs when lack of food is temporary, and is often caused when shocks such as drought or war affect vulnerable populations. Chronic hunger is a constant or recurrent lack of food and results in underweight and stunted children, and high infant mortality. “Hidden hunger” is a lack of essential micronutrients in diets.

Acronyms

ANC	Ante-natal Care
BMI	Body Mass Index
CHW	Child Health Weeks
CIDA	Canadian International Development Agency
CSO	Central Statistics Office
CPs	Cooperating Partner
DALY	Disability-Adjusted Life Year
DHS	Demographic and Health Survey
EMLIP	Essential Medicines Logistic Improvement Programme
GDP	Gross Development Product
GRZ	Government of the Republic of Zambia
HEPS	High energy protein food supplements
HMIS	Health Management Information System
HIV	High Immunodeficiency Virus
IFMIS	Integrated Financial Management Information System
LCMS	Living Measurement Survey
MDG	Millennium Development Goal
MICS	Multiple Indicator Cluster Survey
MMR	Maternal mortality ratio
MNCH	Maternal, neonatal and child health
MoH	Ministry of Health
M&E	Monitoring and Evaluation
NGO	Non-governmental Organisation
NHSP	National Health Strategic Plan
NFNC	National Food and Nutrition Commission
NFSNP	National Food Security and Nutrition Strategic Plan
ORS	Oral Rehydration Salt
PFA	Programme Funded Advisor
PRD	Policy and Research Division
PMTCT	Prevention of Mother-to-Child Transmission
SNDP	Six National Development Plan
SUN	Scaling Up Nutrition
TAG	Technical Advisory Group
THET	Tropical Health Education Trust
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VFM	Value for Money
WHO	World Health Organisation
WFP	World Food Programme
ZISSP	Zambia Integrated Systems Strengthening Programme

# Intervention Summary
## Title: Tackling Maternal and Child Undernutrition in Zambia
What support will the UK provide?
The UK will provide up to £3,500,000 million to: / Expand coverage of direct nutrition interventions for children through the primary health care system / Test two innovative approaches for delivering nutrition interventions / Design a multi-sectoral programme to tackle undernutrition in Zambia, which will include a capacity building component to support the new National Food and Nutrition Strategy, focused on the first 1,000 critical days
Why is UK support required?
Zambia has one of the highest rates of childhood under nutrition in the world[1]: / 46% of under-5 children are stunted, 5% acutely malnourished (wasted) and 15% underweight (LCMS 2010; CSO; 2007). / 53% of Zambian children have Vitamin A deficiency and 46% have iron deficiency anaemia (NFNC; 2003). / 9.3% of the children are born underweight indicating poor maternal nutrition (CSO; 2007). / Undernutrition is likely to be the most significant factor in child mortality and morbidity, underlying up to 52% of under-5 deaths in Zambia (UNICEF 2008). Children who are stunted by the age of 2 will never meet their full potential of physical and mental development. / Direct nutrition interventions have been proven to be highly cost effective when they reach children in the ‘critical 1000 days’ between conception and age 2. Despite this evidence, proven effective interventions are not carried out to scale in Zambia because of weak health systems, lack of human resources, knowledge gaps, poor coordination and lack of investment. In the first phase of this programme, DFID will support the expansion of evidence based direct nutrition interventions through the Child Health Weeks (CHWks) programme focusing on this crucial window of opportunity and targeted at underperforming districts. We will also support two innovative pilots for delivering nutrition interventions and design a multi-sectoral programme to address under-nutrition in Zambia. This will include a capacity building component in support of Zambia’s new National Food and Nutrition Strategy priorities, focused on the first 1,000 critical days. / DFID has been advocating internationally for a multi-sectoral response to undernutrition, including through launching a Nutrition Position Paper at the UN General Assembly in September 2011. DFID is a major supporter of the Scaling Up Nutrition (SUN) movement internationally and has been identified by Cooperating Partner’s (CPs) to be co-convenor of the SUN CP group in Zambia. This is in recognition of DFID’s increasing technical capacity (a new Health and Nutrition Adviser has started in July 2011) and ability to scale up support to nutrition. Our lead roles in health and social protection, experience of working with a range of partners (including the Government of the Republic of Zambia (GRZ), other CPs, NGOs and the private sector) and our strong relationship with Ministry of Finance and Cabinet Office put us in a good position to support a multi-sectoral response and increased high level Zambian ownership and leadership.
[1] The Lancet 2008

What are the expected results?
The expected impact of the overall nutrition programme will be improved health and nutritional status of children under five measured primarily by a reduction in stunting from 46% (LCMS 2010) to 41% (2015). This will mean at least 130,000 fewer[1] children under 5 will be stunted. Together with other DFID investments in child health, we also expect a reduction in the child mortality rate from 119 to 56 per 100,000 by 2015. / The outcome of the programme will be a strengthened national nutrition response focused on the reduction of stunting. This will be measured by improvements in vitamin and micronutrient deficiencies, specifically : / 1) children under 5 suffering from anaemia reducing from 46% (2003 ) to 20%*(2015) and / 2) children under 5 with vitamin A deficiency reducing from 53 %(2003) to 20%* (2015). / This translates into more than 800,000 fewer children suffering from anaemia and Vitamin A deficiency. / Outputs of this first phase will be: / 1) Expanded coverage of Vitamin A and de-worming to >90% in 9 under-performing districts / 2) New evidence and lessons for scale up from two innovative delivery mechanisms / 3) Design of Phase 2: a multi-sectoral programme, including a capacity building plan to support the implementation of Zambia’s new National Food and Nutrition Strategy, focused on the 1,000 critical days. / 4) Agreement on support to strengthen nutrition expertise in Zambia. / * Targets to be confirmed based on the findings of the 2011 Micronutrient Assessment Survey. A target for reducing zinc deficiency will also be included once baseline data is available.
[1] Total projected population of children under 5 is 2,450,000 (Census 2000)

Business Case for Tackling Maternal and Child Undernutrition in Zambia

Strategic Case

A. Context and need for DFID Intervention / Undernutrition is a huge problem in Zambia / Zambia has one of the highest rates of childhood under nutrition in the world. / 46% of under-5 children are stunted, 5% acutely malnourished (wasted) and 15% underweight (CSO 2007). / 53% of Zambian children have Vitamin A deficiency and 46% have iron deficiency anaemia (NFNC 2003). / 9.3% of the children are born underweight indicating poor maternal nutrition (CSO 2007). / Zambia is off track to meet MDG 1 to halve the proportion of people living in hunger by 2015 and infant and child mortality rates are very high (119 per 100,000) (2007 DHS). 70% of the Zambian population cannot afford a minimum cost diet (WFP 2011). Undernutrition is likely to be the most significant factor in child mortality and morbidity, underlying up to 52% of under-5 deaths in Zambia (UNICEF 2008). Chronic malnutrition or stunting – short height for age – is the most common form of undernutrition in Zambia with higher rates (46%) than average for Africa (42%)[2]. This indicates high levels of deprivation and poverty. There is also a high prevalence of low birth weight (9%) which is the result of poor maternal nutritional status. In Zambia, micronutrient deficiencies (lack of sufficient amounts of one or more essential nutrients) due to poor dietary diversity and chronic food insecurity, are the primary causes of stunting. Poor sanitation and frequent infections further compound the problem. Children who are stunted by the age of 2 will never meet their full potential of physical and mental development. Underweight and young mothers are more likely to have low-birth weight babies and to die in childbirth. Wasting among children born to underweight mothers is higher than among children born to mothers with a normal weight[3]. / Undernutrition rates are highest in the North of the country, where cassava is an important part of the diet. There are also pockets with high wasting rates (Western province) with about 5% of children suffering from wasting nationwide. The South is more vulnerable to shocks which trigger acute food insecurity. Chronic food insecurity persists among small scale farmers and the urban poor. Although some support may be considered to fill gaps in the management of acute malnutrition or wasting, given the scale of the problem, the programme will focus on reducing stunting. It will also assess whether geographically specific approaches are needed and will target the worst affected areas. / There is no significant difference in undernutrition rates between girls and boys in Zambia (DHS 2007). However the time and knowledge available to mothers to care for their children is a significant factor in preventing malnutrition and we know that gender inequality blocks progress in tackling undernutrition. There is also international evidence that gender inequality can divert household expenditure priorities. When women have access to resources they tend to spend on their children’s food, health and education. Like in most developing countries, malnutrition disproportionally affects the poorest and most vulnerable. In addition, Zambia’s severe HIV epidemic significantly overlaps with populations already experiencing low diet quality and quantity, leading to worsened undernutrition for HIV positive men, women and children. / The elimination of iodine deficiency, reduction in stunting by 1% point per year and reduction of maternal anaemia by one third (all very achievable) would increase Zambia’s productivity by $1.5 billion over the next 10 years (NFNC 2011). Yet there has been no significant improvement in levels of undernutrition in the last 10 years. / We know how to prevent undernutrition / Direct nutrition interventions have been proven to be highly cost effective when they reach children in the ‘critical 1000 days’ between conception and age 2. A Lancet (2008) review concluded that universal coverage of a full package of proven interventions focused on women and young children (including breast feeding promotion, vitamin A and zinc supplementation and therapeutic feeding) could prevent one quarter of child deaths under 36 months of age, reduce the prevalence of stunting at 36 months by about one third and avert 60 million lost years of healthy life in the 36 worst affected countries, including Zambia[4]. Despite this evidence, proven effective interventions are not carried out to scale in Zambia because of weaknesses in the health system, lack of human resources, poor coordination with other sectors and lack of investment. There is also lack of knowledge and innovation about how best to deliver and scale up these evidence-based interventions and what the most cost-effective delivery channels are. / Undernutrition is caused by complex inter-related factors as illustrated in the following conceptual framework (UNICEF 2009). / This complex causality calls for a multi-sectoral approach and action at different levels to effectively address undernutrition in the long term. A multi-sectoral response requires strong national leadership across a range of sectors (namely agriculture, health, water and sanitation and social protection). / Human resources are needed / Experience shows that countries which have managed to reduce widespread malnutrition problems have given considerable attention to human resources[5]. Increasing the numbers of qualified nutritionists as well as strengthening human resources for supporting nutrition interventions in Zambia will be needed to successfully address malnutrition. Currently nutrition training is offered only up to diploma level. There is a critical shortage of higher degree holder nutritionists working at policy and programme level across key sectors. Zambia is one of the countries worst hit by the human resources for health crisis, with very low doctors and trained health personnel per population ratios. Zambia has already deployed some nutrition posts at district level but more will be needed at national and provincial level. It will be important to utilise district and community level manpower efficiently and look for synergies – rather than creating a new cadre of nutritionist volunteers, the objective should be to adequately include nutrition in the training of nurses, midwifes, community health assistants, safe-mother hood action groups and other volunteers. / National and international leadership and coordination / Undernutrition is a growing global development priority after many years of neglect. The SUN movement, launched in April 2010, is an international initiative aimed at increasing the scale and effectiveness of support to tackle undernutrition. Zambia has been identified as an ‘early riser’ country under SUN given its high undernutrition burden and commitment to work with CPs to address it. This offers unprecedented potential to increase political and donor support. / Zambia has a National Food and Nutrition Policy and nutrition is identified as a cross cutting issue in the Sixth National Development Plan. There is also a National Food and Nutrition Commission (NFNC) which has the mandate for inter-ministerial coordination and sits under the Ministry of Health (MoH). A new National Food and Nutrition Strategic Plan has been drafted under NFNC lead and its development has led to consensus on the need to prioritise stunting among children under 2, based on its permanent negative implications on healthy growth, cognitive development and human productivity. The document sets out strategic links between the Agriculture, Health, Education and Community Development and Social Services sectors. It has identified 8 priority areas which will be supported by 3 strategic directions. Priority areas include: prevention of stunting in children under 2; improving food and nutrition security; early identification and treatment of acute malnutrition; nutrition education and feeding through schools; increasing linkages between nutrition and infection control through hygiene, sanitation and safe water, nutrition and HIV; improving nutrition to prevent non-communicable diseases and emergency response preparedness. / The strategies identified to deliver on the above priorities are: / Strengthening governance, capacity building and partnerships at all levels / Monitoring and Evaluation (M&E) of the food and nutrition situation in Zambia, interventions and research to support their improvement and expansion and / Expanding and developing communication and advocacy support for food and nutrition / The NFNC has requested support from CP’s to strengthen its capacity and obtain high political support to implement the new Strategy and effectively lead a multi-sectoral response. / Other sectoral plans which are relevant to nutrition include: / The National Food and Nutrition Policy (2006) which informed the development of the NFNSP / The Sixth National Development Plan (SNDP), which aligns with Zambia’s efforts to meet the MDGs and the national aspirations stated in Vision 2030. Special priority is given to multi-sector collaboration on the national food and nutrition objective of preventing stunting in children under 2. / The Decentralisation Policy which sets plans to strengthen decentralisation across sectors. The NFNSP emphasises decentralised programme development and management, especially for multi-sectoral efforts and major community level participation. / The health strategic plan which highlights nutrition with a special focus on children. / There has been a multitude of nutrition and food security interventions supported by CP’s and the Government of Zambia in the past. However, these have tended to be at small scale, many have failed when CP support has come to an end, and systemic problems have posed sustainability challenges. To date, no attention has been put on the need to have a multi-sectoral response. There is an urgent need for a concerted national effort to scale up evidence-based nutrition interventions and to generate new knowledge on how best to do this and address the underlying causes of undernutritiom. To this end, the new NFNSP calls for the strengthening, adaptation and expansion of small-scale projects towards national scale implementation. To avoid the failures of past programmes, substantial training and capacity building, increased collaboration across sectors and organisations, advocacy at all levels and better monitoring will be needed. / A CPs group has been established in recognition of the need for greater coordination on nutrition. The group, which includes UK, UNICEF, Ireland, WFP, World Bank and USAID, is meeting regularly and are already co-funding nutrition activities. In response to Zambia’s NFNSP, the group are discussing setting up a pooled SUN Partnership Fund to align technical assistance and resources behind national nutrition priorities. / DFID has a key role to play / Tackling undernutrition requires a multi-sectoral approach that addresses both the immediate and underlying causes. DFID’s Global nutrition strategy and our wide range of interventions on human and social development in Zambia puts us in a prime position to make a real difference. The impact of our nutritional investments will be enhanced by ensuring that we leverage as many nutritional results as possible from our programmes in Zambia. / DFID has been advocating internationally for a multi-sectoral response to undernutrition, including through publishing a Nutrition Evidence Paper and Strategy in 2010 and the launch of a refreshed nutrition policy at the UNGA meeting in September confirming our commitment to reduce undernutrition. DFID is also a major supporter of SUN internationally and is co-convening the SUN CP group in Zambia. This is in recognition of our increasing technical capacity (a new Health and Nutrition Adviser has joined in July 2011 and a new PFA SUN Adviser is expected to join in the next six months to support the NFNC) and DFID’s ability to scale up support to nutrition. Our lead roles in health and social protection, experience of working with a range of partners (including GRZ, other CP’s, NGO’s and the private sector) and our interaction with Ministry of Finance and Cabinet Office put us in a good position to support a multi-sectoral response and increase high level national leadership. / If DFID does not invest in nutrition, a substantial change to stunting levels in Zambia is unlikely to occur. Whilst partners will continue to implement discreet nutritional interventions, these will not suffice to reduce stunting and will not address the underlying causes of poor maternal and child nutrition. Although Zambia is committed to the SUN initiative it is unlikely that any real action will be taken by the NFNC without DFID’s support to build their capacity, promote an enabling environment and coordinate an effective CP response.
[2] National Food and Nutrition Strategic Plan, 2011
[3] The Challenge of Hunger and Malnutrition, Copenhaguen Consensus, 2008
[4] The Lancet, Vol 371, 2008. Maternal and Child Undernutrition – What works? Interventions for maternal and child undernutrition and survival
[5] Narrowing socioeconomic inequality in child stunting: the Brazilian experience, 1974-2007. Bulleting of the World Health Organisation 2010; 88

B. Impact and Outcome / The expected impact of the overall nutrition programme will be improved health and nutritional status of children under five measured primarily by a reduction in stunting from 46% (LCMS 2010) to 41% (2015). This will mean at least 130,000 less children under 5 will be stunted. Together with other investments in child health, we expect a reduction in the child mortality rate from 119 to 56 per 100,000 by 2015. / The outcome of the programme will be a strengthened national nutrition response focused on the reduction of stunting. This will be measured by improvements in vitamin and micronutrient deficiencies, specifically : / 1) children under 5 suffering from anaemia reducing from 46% (2003 ) to 20%*(2015) and / 2) children under 5 with vitamin A deficiency reducing from 53%(2003) to 20%* (2015). / This translates into approximately 800,000 less children suffering from anaemia and Vitamin A deficiency. / Outputs of this first phase will be: / 1) Expanded coverage of Vitamin A and de-worming to >90% in 9 under-performing districts[2] / 2) New evidence and lessons for scale up from two innovative delivery mechanisms / 3) Design of the multi-sectoral component, including a capacity building plan to support the implementation of Zambia’s new Food and Nutrition Strategy, focused on the 1,000 critical days. / 4) Agreement on support to strengthen nutrition expertise in Zambia. / A key performance indicator in the SNDP is reduction of stunting to 30% by 2015. This is a laudable goal, but unlikely to be achieved. LCMS data indicates a 0.74% point reduction in U5 stunting per year between 2004 and 2010. The proposed 1% point reduction is therefore ambitious but realistic. / Programme targets will be confirmed after the Micronutrient Assessment Survey, currently being conducted, has been finalised. A zinc coverage target will be added once baseline data is available[3]. / Micronutrient interventions can be very effective. For example, iodine deficiency in school children in Zambia was reduced from 74% in 1992 to 4% in 2002 thanks to fortification of salt. These ambitious reductions in micronutrient deficiency are therefore considered achievable and overtime will contribute to a reduction in stunting levels in Zambia.
[2] Selected districts include: North Western - Chavuma, Mufumbwe and Zambezi; Northern - Kaputa, Mbala and Mpulungu (possibly also Luwingo) and Western - Kalabo, Kaoma and Mongu.

# Appraisal Case

A. What are the feasible options that address the need set out in the Strategic Case?
There are three high level options: / Option 1: Expanding the coverage of direct nutrition interventions and commodities which are known to reduce stunting. These interventions address the immediate causes of undernutrition – preventing and treating mineral and vitamin deficiency through supplementation and fortification, supporting exclusive breast-feeding, treatment of severe acute undernutrition, and treatment of infections. / Option 2: Supporting a multi-sectoral response to undernutrition. This is about leveraging nutrition impacts from key sectors, namely health, agriculture, social protection and water and sanitation and in so doing, addressing the underlying causes of undernutrition. It requires strong government leadership and capacity for resourcing and coordinating interventions and creating an environment which incentivises sectors to work towards a common set of objectives. / Option 3: A combination of Options 1 and 2. There is global consensus that in order to address undernutrition in the long-term, investment in direct, as well as in the indirect causes of malnutrition is needed. / The counterfactual – “do nothing”. The above options will be compared with the counterfactual of no DFID intervention in the sector. / The theory of change underpinning the options above, has been developed with reference to UNICEF’s conceptual framework for undernutrition (UNICEF 1990). Proven nutrition interventions are proposed to address the manifestation, immediate and underlying causes of undernutrition. Those interventions in italics are considered direct nutrition interventions. Indirect sectoral interventions are addressed either through other parts of DFID Zambia’s programme (e.g. cash transfers, sanitation and mosquito nets) or by other donors. Basic causes also need to be addressed to promote and enabling environment through political leadership, nutrition awareness, social accountability mechanisms and women’s empowerment. / B. Assessing the strength of the evidence base for each feasible option. / Option Evidence rating / 1 strong / 2 medium / 3 medium / Option 1: Expanding the coverage of direct nutrition interventions and commodities which are known to reduce stunting / Nutrition-specific interventions have been proven to deliver among the best value for money of all development interventions. The Lancet series (2008) demonstrated that 13 nutrition interventions had sufficient evidence to be implemented successfully at scale, and could together, reduce stunting by one third[6]. See Annex 1 for the full list of interventions as reviewed by the Lancet. In addition, the Copenhagen consensus ranked 6 nutrition interventions – Vitamin A and zinc supplementation, iron and salt iodisation, biofortification, deworming and community based nutrition programming among the top best development buys[7]: / Rank Intervention / 1 Micronutrient supplements for children (zinc and vitamin A) / 3 Micronutrient fortification (iron and salt iodization) / 5 Bio fortification / 6 De worming and other nutrition programmes at school / 9 Community based nutrition programming / For all the 13 interventions, the global evidence of impact has been largely proven, but there remain significant evidence gaps on how they can be successfully delivered to optimal levels of coverage and which combination of delivery channels can achieve this at the lowest cost – e.g. facility based health services, community based services, retail outlets or using other delivery platforms such as cash transfer programmes. In Zambia, there are still significant gaps in knowledge around the scale of under-nutrition, and the extent and impact of nutrition interventions. The last food consumption study was carried out in the early 1970s, micronutrient surveys have been limited and are outdated by 8 years and a full mapping of ongoing nutrition related interventions by GRZ, the private sector and NGO’s has never been done. These are all gaps that we would seek to address during the first phase of the programme. / In terms of coverage of these high impact nutrition interventions there are still major gaps in Zambia: / 56% of pregnant women do not take 90d of iron folate supplementation / No children aged 6-23 months receive iron supplementation / 40% of children aged 6-59 months do not receive regular deworming / 40%[4] of children aged 6-59 months do not have regular high dose Vitamin A supplementation / 56% of women do not receive Vitamin A after giving birth / 40% of children under five with diarrhoea do not take therapeutic zinc supplementation / Approximately 100% of pregnant women with very low BMI do not receive a food supplement / More detail on the evidence base of a selection of these high impact interventions is provided in Annex 1. The selected interventions are currently provided through the primary health care sector, offering greater and immediate scale up potential: Vitamin A and deworming for children under 5, iron folate for pregnant women and therapeutic zinc for the treatment of diarrhoea. / Hand-washing and the prevention of treatment of malaria infection are supported under other DFID Zambia programmes. Breast-feeding is covered by a nation-wide campaign funded by USAID but supporting adequate breast-feeding practices among HIV positive mothers to prevent HIV transmission to their infants will be considered under DFID Zambia’s new HIV programme. Iodine fortification has been largely addressed in Zambia through mandatory salt iodisation, as well as Vitamin A sugar fortification. Support to food supplementation and complementary feeding need further scoping and will be assessed in collaboration with the NFNC and other partners during the first phase of the programme for possible introduction later. / To reduce stunting, all the major vitamin and micronutrient deficiencies need to be addressed in a coordinated way and at sufficient scale. Potential health sector strategies for expanding coverage of the above selected interventions are summarised in the table below: / Intervention Existing delivery channels Innovative channels / Vitamin A supplementation CHWks / Fortified sugar Pro-vitamin A bio-fortified maize / Deworming tablets CHWks / Essential Medicines Logistics Improvement System (EMLIP) / Iron Folate Routine maternal health services / EMLIP / Zinc supplements EMLIP Private sector channels: Coca Life proposal / For Vitamin A and deworming tablets: / Multi-annual commitment to CHWks. The CHWks is a national government programme which is conducted on a campaign mode twice a year. The programme provides the main delivery channel for Vitamin A and deworming and may also be a vehicle to provide therapeutic zinc. The CHWks programme has the potential to reach most children under 5. It has achieved and sustained coverage of Vitamin A of over 80% in the last 4 years. The programme faces some implementation challenges which would need to be addressed to strengthen performance, including limited trained staff, erratic supply of essential medicines and medical supplies, inadequate education and communication materials and insufficient funding for the activity as a whole. Performance varies widely across provinces, with Northern, Western and North-Western provinces being in the bottom three with significant lower coverage levels. In the past, DFID has funded this programme on an ad hoc basis. A multi-annual commitment will support better planning, focus on strengthening key weaknesses and target the worst performing districts. / For iron and folate acid: / Support to routine services (ante and post natal). Iron and folate supplements for women can be best distributed through maternal and child health services, including Prevention of Mother to Child Transmission (PMTCT) services, which have been scaled up considerably amidst efforts to eliminate paediatric HIV in Zambia and are being integrated with ante-natal care (ANC). But there are major coverage gaps through these services with 56% of pregnant women not taking the required iron folate supplementation. / For all the above as well as zinc supplements: / Expand coverage of nutrition commodities through the scale up of EMLIP. This is a successful pilot that was supported by DFID and which is planned to be scaled up nationwide with the objective of strengthening the supply chain, key to enable timely and effective delivery of health commodities. The strengthening of EMLIP will be addressed through our new malaria programme. The roll out of EMLIP has been stalled for a while due to a shortage in essential medicine commodities, debate in the MoH about clarifications needed to ensure sustainability (including questions around costs, level of monitoring, drug storage capacity, etc). However, the new GRZ seems to keen to make quick progress and address this debate. EMLIP already includes a number of nutrition commodities such as iron, folic acid, ORS and mebendazole (for deworming). Options for improving the supply of nutrition commodities would need to include monitoring coverage of such commodities as well as increasing demand at the health centre level. / Support innovative delivery approaches. Given current limited coverage levels achieved through traditional channels, there is need to identify and test new delivery channels to support the scale up. Two opportunities to expand Vitamin A and zinc supplementation are appraised below: / Support to test whether Coca Cola’s distribution channels could be used to reach remote retail outlets with a diarrhoea treatment pack including oral rehydration salts (ORS) and zinc. DFID has received an innovative proposal from Cola Life to do this. The benefits of therapeutic zinc supplementation and need for alternative delivery mechanisms to expand coverage have already been described above. The project would address demand side issues based on a social marketing approach and the use of vouchers for mothers. One of the objectives is to encourage families to have ORS ready-to-mix packages and zinc readily available for use as needed, based on guidelines from the World Health Organisation. See Annex 3 for details. / Support efficacy studies and preparatory work needed for the successful introduction of bio-fortified orange maize, including efficacy studies among women and children to proof its health impacts (a request from the global health community). DFID has already received a proposal from Harvest Plus to do this. The project will introduce Pro-vitamin A bio-fortified maize to small scale farmers and grower-consumers. It aims to introduce this crop to at least 80,000 households in 3 provinces of Zambia by 2014. Public-private partnerships will be a core element of the project strategy, building alliances between farmer groups, government agencies, donors, the private sector and NGOs. Bio-fortification was identified as one of the best development buys by the Copenhagen Consensus and as a food based approach, if successful, it could pave the way for significant improvements in the health of Zambian mothers and children. See Annex 2 for further details. / Recommendations / Multi-annual support to the CHWks programme is a tested delivery mechanism, can allow for DFID funds to be targeted to the worst performing districts, and offers immediate results. / Strengthened nutrition as part of maternal and child health services is an option best explored as part of the design of the multi-sectoral component (option 2), which should consider how to mainstream nutrition into some of our sector programmes, including health. / Addition of new nutrition commodities (e.g. zinc or ready to use therapeutic food) to EMLIP would add complexity and needs to take into account the ongoing debate between the MoH and donors. This option should therefore be pursued at a later stage under this programme. / New approaches are urgently needed to scale up nutrition interventions and to address knowledge gaps, / If Option 1 is taken forward, it will therefore include support to the CHWks programme and the innovative pilots. / Option 2 : Supporting a multi-sectoral response to undernutrition focused on stunting / Evidence shows that a multi-sectoral response to malnutrition delivers greater impact than the sum of individual sectoral investments[8]. Brazil, Thailand, Tamil Nadu and Mexico have all successfully reduced malnutrition through the development and implementation of strongly led multi-sectoral strategies. But delivering a multi-sectoral response is challenging, requiring strong government leadership for resourcing and coordinating interventions and creating an environment which incentivises sectors to work towards a common set of objectives. / The NFNC currently provides the mechanism for driving this multi-sectoral approach but lacks the capacity and political clout to do so. Zambia’s renewed commitment to tackling undernutrition, as a signatory of the SUN initiative, provides an excellent opportunity to improve cross-government working on nutrition and strengthen NFNC’s leadership role. / Based on the above, Option 2 would entail the design of phase 2, which will consist of a multi-sectoral programme to support the implementation of Zambia’s new NFNSP, focused on the 1,000 critical days. The design will include: / A capacity building plan for the NFNC and key sector Ministries / A mapping and gap analysis of nutrition interventions in Zambia / The development and costing of a strong 1,000 days plan and launch of a multi-stakeholder platform to monitor its implementation / In-depth audit of DFID Zambia’s programmes to make our portfolio more nutrition-sensitive / The following is a brief description of what the design needs to scope under each of these components. / Capacity building: An in-depth institutional assessment of the NFNC and key sector ministries (namely agriculture, health, water and sanitation and social protection) would be conducted. This would be complemented by an ongoing study of governance in the nutrition sector of Zambia being conducted by the Institute of Development Studies which will be finalised by the end of October 2011. A Programme Funded Adviser will be recruited to support the design and implementation of this component. / Mapping of nutrition interventions. A stocktaking of current nutrition interventions and their impact, as well as gaps, will be conducted to inform decisions on where to target further investments. / Support the development and costing of a strong 1,000 days plan and the establishment of a multi-stakeholder platform. This would help to operationalise pillar 1 of the new National Food Security and Nutrition Strategy, which focuses on the reduction of stunting. It would build on renewed NFNC resources at provincial and district level to help increase political commitment, leverage additional donor interest and nationwide support for nutrition. / Audit of DFID Zambia’s sectoral interventions (health, social protection, hygiene and sanitation) to leverage nutritional impacts. Investments across multiple sectors to address the underlying causes of stunting are needed. Nutrition sensitive development involves adjusting and re-designing programmes which have potential to address the causes of undernutrition to explicitly deliver this result. These programmes have multiple objectives and casual chains and are difficult to measure. However, they represent a huge untapped potential for reducing undernutrition and may hold the key to much of the remaining 2/3 of the stunting problem. Programmes which offer the greatest scope to improve nutrition include food security and agriculture, cash transfers, water and sanitation and health[9]. See Annex 7 for details on available evidence. / The design will identify how to: / Build nutritional indicators into the monitoring and evaluation of these three programmes / Use them as a platform for testing ways to enhance their nutritional impact e.g. by delivering micronutrient sprinkles alongside the child grant, or delivering food hygiene education alongside sanitation interventions. / One immediate opportunity is supporting the development of a national nutrition Bachelors and a Masters degree through the Tropical Health and Education Trust (THET). Increasing Zambia’s national capacity in nutrition will be key to making sustained progress in tackling malnutrition. The University of Zambia (UNZA) wishes to host a nutrition degree programme and requires support to develop and impart the course. Adding a nutrition component to our current support to THET offers an excellent opportunity to support this effort. / The design of Phase 2 will also consider the provision of funding to support civil society organisations in advocacy on nutrition to raise awareness, support and resources. / Option 2 components directly support all the 3 'supportive strategic directions' of the NFNSP which have been described in the policy section above: 1) Leveraging existing and new capacity to scale up; 2) M&E of situation, interventions and research; 3) Communication and advocacy at all levels. / Recommendations: / Procure direct technical assistance to the NFNC for capacity building, the mapping of nutrition interventions, the development and costing of the 1,000 days action plan and the design of phase 2 of DFID’s nutrition programme, including the auditing of DFID Z sectoral programmes; / The deployment of a 50% PFA SUN Adviser / Support the UNZA to establish a nutrition bachelors and masters degree. / Option 3: A combination of the above. / This option would include support to scale up direct nutrition interventions as identified above, as well as support to design and build capacity for a multi-sectoral approach. This would address both direct and underlying causes of undernutrition. During phase 1, support to the interventions identified under Option 1 would be taken forward. Other interventions would be selected based on the design of phase 2 as well as further assessment of opportunities within existing delivery mechanisms such as routine maternal health services. / Option 4 – the counter-factual. Despite steady economic growth, there has been negligible improvements in undernutrition in the last 10 years. There is a new National Food and Nutrition Strategy (NFSNS) and an institution with the mandate for inter-sectoral collaboration, the NFNC, but this lacks the political clout, capacity and leadership to do so. The NFNC and the NFSNS are also inadequately funded. Without our support to increase nutrition awareness, capacity and political commitment to the global SUN initiative, it is unlikely that there will be significant improvements in Zambians’ undernutrition levels. / Gender and Social Appraisal. / Women and children’s health are at the very heart of this programme since efforts to reduce stunting in children must address women’s health before, during and after pregnancy and children, particularly during the critical 1000 days from conception to age 2. Work to improve nutrition awareness and demand at community and household level will strengthen women’s decision-making powers regarding children’s health and nutrition. / According to the last household survey, there is no significant difference in undernutrition rates between girls and boys in Zambia (DHS 2007). However the time and knowledge available to mothers to care for their children is a significant factor in preventing undernutrition and we know that gender inequality blocks progress in tackling undernutrition. There is also international evidence that gender inequality can divert household expenditure priorities[10]. When women have access to resources they tend to spend on their children’s food, health and education. To better understand the role that gender inequality plays in undernutrition in Zambia, and its implications for the 1,000 days action plan, the programme will support a study to look at the role of gender during the inception phase and use its findings and recommendations to inform our support to direct and enabling interventions. / Like in most developing countries, undernutrition disproportionally affects the poorest and most vulnerable. In addition, Zambia’s severe HIV epidemic significantly overlaps with populations already experiencing low diet quality and quantity, leading to worsened undernutrition for HIV positive men, women and children. Support to direct and indirect nutrition interventions will focus on the poorest areas and those with the highest rates of undernutrition. The findings from the ongoing food security and micronutrient assessment and the mapping exercise, will help to inform where to geographically target interventions so that they are focused on the most vulnerable. The programme will also support data disaggregation by age and gender, socio-economic and HIV status (wherever possible) as part of our planned support to strengthen nutrition surveillance and thus generate the necessary information to promote greater prioritisation of women and adolescent girls. / Governance and Institutional Appraisal / The proposed option combines direct interventions with work to build the capacity of government systems. This option therefore aims to make a significant impact on nutrition in the shorter term, whilst building sustainable systems in the medium term to deliver graduation from donor support. / Zambia has shown a strong rhetorical and policy commitment to improving nutrition. Zambia has a National Food and Nutrition Policy, and nutrition is identified as a cross cutting issue in the SNDP. The NFNC has been established with a mandate for inter-ministerial coordination under the aegis of the MoH. A new NFNSP has been drafted under NFNC lead. It remains to be seen if President Michael Sata’s new Patriotic Front Government elected on 22 September 2011 will want to change the NFNP, or the NFNSP which were both drafted under the previous Government. However the PF have made strong statements in favour of improved nutrition, and on the need to do more on poverty reduction more generally. / These commitments provide a good basis to build on and indicate a willingness to support nutrition interventions. A multi-sectoral response requires national leadership across a range of sectors (namely agriculture, health, water and sanitation and social protection). It also requires strong national capacity to deliver across all these sectors. However, previous experience has shown that in Zambia stated commitments do not always lead to delivery owing to a lack of real political will or a lack of capacity. Zambia is a centralised state where power is concentrated in the office of the President and central government. It also has a small population dispersed over a large area, with relatively low government capacity in the remote rural areas. The programme therefore aims to strengthen strong political will at the centre whilst boosting the capacity to deliver, particularly in rural areas. The advent of a new Government with a mandate for change and an apparent desire to help the poor arguably provides a stronger opportunity to strengthen political will at the centre compared with the previous Government. CP’s will aim to work closely with the new Government to mitigate that risk. / The NFNC has requested support from donors to strengthen its capacity and obtain high level political support to implement the new Strategy and effectively lead a multi-sectoral response. The proposed programme also recognises that in some areas Government systems currently lack the capacity to deliver unaided. Therefore DFID Zambia will initially fund other partners for certain interventions, for example funding CHWks through UNICEF. / An important aspect of building political will is to increase the demand for effective nutrition interventions from stakeholders, putting pressure on the Government to deliver. Civil society has an important role to play in increasing such accountability, and there are some early signs that the new Government is more willing to listen to civil society than its predecessor. The design of Phase 2 will consider the provision of funding to support civil society organisations in advocacy on nutrition to raise awareness, support and resources. / The MoH has oversight of the NFNC and would be the logical partner to deliver key nutrition interventions. However the Ministry faces challenges in terms of its governance and financial management. Following a major corruption scandal which broke in 2009, the MoH has demonstrated some progress in restoring confidence in its governance and financial management, taking short term actions to safeguard funds and suspending or sacking those involved. It has also shown some commitment to reform, requesting support to bring forward the implementation of key systems. Wider programmes supported by donors across the GRZ will also improve public financial management in the MoH. For example the Ministry is an early priority for the roll out of the Integrated Financial Management Information System (IFMIS), and should benefit from proposed procurement reforms. In addition the new Government more broadly appears committed to strengthening the fight against corruption. The President has already removed the head of the Anti Corruption Commission (ACC) who was regarded by many as being relatively ineffectual and close to the previous President. He has been replaced with a new head regarded by many commentators as stronger and more independent than her predecessor / In the medium term DFID expects MoH systems to have improved sufficiently to absorb significant amounts of financial aid. However in the shorter term this will not be the case. So funding for direct interventions as set out in option one, mainly delivered through CHWks will be routed through UNICEF. UNICEF would purchase the commodities and support government systems in distributing the commodities. This would reduce the fiduciary and governance risks involved in relying fully on MoH systems in the shorter term. / Another approach to tackling the challenge of delivery, particularly in remote rural areas, is by using innovative mechanisms and best practice that exist outside the government sector. The programme will support such approaches, e.g. the proposal by Cola Life. / More analysis is needed of the governance challenges and opportunities faced by the proposed programme. An in-depth institutional assessment (including a multi-stakeholder analysis) will be done at the start of phase 1. This will be informed by an IDS study which is looking at the institutional and political dimensions that can promote effective nutrition strategies at the country level, documenting legal frameworks and institutional reforms. The study is also exploring the political dynamics and cooperation of key policymakers across different government sectors, and their articulation across different territorial units (national, sub national and local) where the strategies are implemented. The study will cover 6 countries. The Zambia study will result in a country report, which will incorporate recommendations for moving nutrition higher on the political agenda (expected by November 2011). / Climate change and environment category. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities (A, B, C, D) / 1 C (low) C (low) / 2 C (low) B (medium) / 1&2 C( low) B (medium) / OUTCOMES / - Reduction in stunting / - Improved micro-nutrient status / - Reduced prevalence of acute malnutrition / Adequate dietary intake / Reduced disease burden / Increased micro-nutrient intake / Increased access & availability of food / Improved infant & young child feeding / Integrated mngt of acute undernutrition / Improve hygiene & parasite control / Therapeutic feeding / Micronutrient supplementation / fortification / Breastfeeding promotion / Complementary feeding / Deworming / Home based water treatment / Handwashing with soap / Impregnated mosquito nets and ITM / Cash transfers / Food production / Food supplements / IMPACT / Improved child health and nutritional status
[6] The Lancet, Vol 371, 2009 (as in iv)
[7] The Challenge of Hunger and Malnutrition, Copenhaguen Consensus 2008
[4] UNICEF and NFNC say that these rates have since increased.
[8] Brazil, Thailand, Tamil Nadu, Mexico, all countries which have successfully reduced undernutrition had developed and implemented multi-sectoral strategies.
[9] DFID Nutrition Position Paper, September draft
[10] IFPRI, 2006

C. What are the costs and benefits of each feasible option? / The international evidence demonstrates clearly that there is a strong economic case for investing in nutrition and that there are a number of well-known interventions available that are highly cost-effective. Zambia was included in the key cost-effectiveness study of nutrition interventions, the Lancet meta-analysis, lending weight to the assumption that the economic case for investing in nutrition applies here. / Improved nutrition leads to positive economic impacts in three main ways: / Direct gains in productivity arising from improvements in physical stature and strength, as well as improvements in micronutrient status. Productivity gains at a micro level from improving nutrition are estimated at 10% of lifetime earnings and at a macro level, GDP gains can be as high as 2–3%[5] / Indirect gains arising from links between nutritional status, schooling and cognitive development, as well as subsequent adult labour productivities, and / Savings of resources currently directed to health care, disease treatment and other problems associated with undernutrition. / The table below provides estimates of the global cost-effectiveness of a range of different nutrition interventions. Though these interventions would likely prove more expensive in Zambia (due to its large size and highly dispersed population), they would almost certainly still all prove to be highly cost-effective[11]. / Table 1 – Cost-Effectiveness of Various Nutrition Interventions / Source: DFID Nutrition Evidence Paper / VfM of feasible options / We focus here on the immediate actions proposed under phase 1, including some attempt to outline costs and benefits where possible. Potential actions under phase 2 will not be discussed here. As the different options for implementation in phase 2 are developed, they will be assessed on the basis of their costs and benefits and overall value for money. For further detail and further VfM discussion, see the full Technical Appraisal in Annex 5. / Option 1: Expanding the coverage of direct nutrition interventions and commodities known to reduce stunting / Component Costs Benefits VfM Metric / CHWks £0.93m (over 4 years) - 161,000 children covered with vitamin A supplements & deworming drugs twice a year for 4 years. / - 3,860 infant deaths & 127,000 DALYs averted Unit cost: £0.72 per child per year / Cost effectiveness: £240 per infant death averted, £7 per DALY averted / ColaLife pilot £0.75 m (over 2 years) - 20,000 anti-diarrhoea kits delivered, 15,000 children reached / - Knowledge gained on effectiveness of innovative delivery mechanism / - Income generation opportunities for low income rural micro-retailers Direct cost per kit: £2.30 / Distribution cost: £1 per kit / Harvest Plus biofortification pilot £0.68m - Knowledge gained on efficacy (nutrition impact) of innovative delivery mechanism / Overall, Option 1 would invest around £2.4 m over 4 years to fund the provision of nutrition commodities through a proven delivery mechanism (the CHWks) and to fund two pilots of innovative delivery mechanisms which, if successful, could lead to a large scale up of other vital nutrition interventions. The benefits of these components are likely to be large both in terms of the direct health benefits and in terms of the information created and knowledge gained. However, this option will not address the long term capacity issues facing the nutrition sector in Zambia. / Option 2: Supporting a multi-sectoral response to undernutrition / Component Costs Benefits / Supporting stocktaking, multi-stakeholder platform and 1,000 days costed action plan £0.15m (over 4 years) - A clearer understanding on type and coverage of nutrition interventions, challenges & relevant actors working on nutrition / - Improved focus on stunting, co-ordination & strategic direction in government and donor plans / Technical Assistance to NFNC £0.23m (over 3 years) - A strengthening of NFNC’s capacity to coordinate the implementation of Zambia’s National Food and Nutrition Strategic Plan / - Increased cross-government commitment to tackling under-nutrition / Audit of DFID Zambia’s sectoral interventions to leverage nutritional impacts £5,000 - Increased understanding of how to leverage programmes across DFID-Zambia’s portfolio to tackle under-nutrition / Supporting the development of a national nutrition degree through THET £0.55m (over 4 years) - Increased pool of highly trained nutrition professionals / - 200 students achieving Bachelors and/or Masters level professional qualification in nutrition / Overall, Option 2 would invest £0.94 m over 4 years to improve the institutional landscape around nutrition in Zambia. This investment in knowledge, institutions and capacity building should ensure that the problem of under-nutrition is tackled in a more effective and sustainable way in Zambia in the long term, but will not address any of the large gaps in provision of vital commodities in the short term. / Option 3: A combination of Options 1 and 2 / The interventions under Option 1 are designed to rapidly address key short term gaps in preventing under-nutrition. Those under Option 2 are designed to build Zambian capacity to respond in the medium to long term. As such, the two options are complementary and implementing them both will allow each to add value to the other. Hence Option 3 is the most systematic and sustainable approach. Total funding under Option 3 would amount to £3.3m over four years, plus an additional £150,000 for evaluation and auditing of each of the components. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Both options are classified as having a low risk for climate change and the environment. Option 1 is low risk for opportunity. Option 2 is rated as a medium opportunity due to the multi-sectoral nature of the intervention, particularly as this will include water and sanitation which will have positive impacts on the environment. Option 3 is the same, since this is a combination of the former. Depending on recommendations arising from the design of phase 2, the potential focus on agriculture may be an opportunity to promote sustainable agricultural practices such as conservation agriculture. These are good for the environment, address climate change and can increase yields. / D. What measures can be used to assess Value for Money for the intervention? / For Option 1 (direct nutrition interventions and pilots): / Evidence of the economy of inputs being sourced through a multi-lateral partner and other partners’ procurement systems / Justification of management costs on an ongoing basis, including direct costs of the delivery agents / Unit costs of commodities, recalculated regularly to reflect data collected through routine monitoring / A mid-term external evaluation of the programme will assess data on the programme at outcome level. This will also be done for all pilots supported, which will have rigorous evaluations, in order to provide the basis for future decisions about increased or extended investment of UK, other donors and government resources. / For Option 2 - design of a multi-sectoral response and capacity building, Value for Money will be a key consideration for identification of the interventions to be supported. / We will select consultants from DFID’s Human Development and Nutrition Resource Centres. VfM will be one criteria in the selection to support priority areas identified. / Adding a nutrition component to THET takes advantage of our existing accountable grant, reducing administrative costs. / Preferred option / As mentioned earlier, the complex causality of malnutrition calls for a multi-sectoral approach and action at different levels. DFID recognises that investment in direct and indirect approaches must be given equal attention[12]. Option 1 or Option 2 alone would not deliver the required results to reduce stunting. Evidence shows that the scale up of direct nutrition interventions would lead to a reduction of stunting by one third, and that leveraging nutrition outcomes from indirect interventions could hold the answer to reducing the remaining two thirds of stunting. In addition, whilst in the short term, direct nutrition interventions are expected to have the quickest impact, in the longer term, efforts should be towards improving food security and dietary quality. / Option 3 scores higher based on our appraisal. In addition, it scores higher when a selection of critical success criteria necessary for scaling up efforts to reduce undernutrition are considered. These criteria have been taken from the Lancet Series and include: / a) the potential impact on stunting among the poorest; / b) the potential to leverage a strong and sustainable response from government; / c) the potential to leverage a strong response from other donors and / d) the potential to identify new solutions and approaches to the problem. / Whilst Option 1, if targeted to the poorest areas, scores highly against criteria a), it does not score highly against b). Success criteria c) and d) are also best addressed through working together with government and other donors in support of a multi-sectoral response (option 2). The conclusion is therefore that both Options 1 and 2 should be supported. / Based on the environmental and climate change assessment of options 1 and 2 above, this option would be classified as C (low) for risk and B (medium) for opportunity. See also the environmental assurance form attached. / E. Summary of Value for Money Statement for the preferred option / Based on the strong international evidence on the effectiveness of nutrition interventions and on the assessments made above, it is judged that Option 3, a combination of the first two options, would be a cost effective way of tackling under-nutrition in Zambia and hence would offer very strong value for money. It would enable existing gaps in both provision and knowledge to be filled quickly, while laying the groundwork for institutional and other long- term improvements in tackling nutrition in Zambia. It will also provide a strong foundation for the design of further investments in Phase 2.
[5] DFID Nutrition Evidence Paper 2009
[11] The WHO defines a health intervention as cost effective if its cost per DALY averted is between one and three times GDP per capita and as highly cost-effective if its cost per DALY averted is less than GDP per capita. These thresholds follow the recommendations of the Commission on Macroeconomics and Health.
[12] The neglected crisis of undernutrition: DFID’s Strategy, 2010

# Commercial Case
## Direct procurement
A. Clearly state the procurement/commercial requirements for intervention / Five elements of the programme will be procured directly to design Phase 2: / Technical assistance for the design of phase 2 (the multi-sectoral programme) to support the mapping of nutrition interventions, costing and development of the 1,000 days plan / In-depth nutrition audit of DFID programmes to take place during phase 1 of the programme / Independent evaluation will be undertaken at mid-point (2013) and end of the programme (2015) / All the three elements will be procured directly by Procurement Group (PrG) through the existing framework arrangement with DFID’s Human Development and Nutrition Resource Centres. One or two contracts will be issued for elements 1 and 2. / Commercial capacity assessment and capacity building to support the effective delivery of the Cola Life operational trial in Zambia. The assessment function will be procured directly by DFID Zambia through a call down contract with KPMG. Based on the assessment report, DFID Zambia will decide how to procure the capacity building aspect. / Capacity building for NFNC - Recruitment of the SUN Nutrition Adviser will be through DFID’s internal recruitment procedures..
B. How does the intervention design use competition to drive commercial advantage for DFID? / DFID will carry out a mini-competition amongst the pre-qualified bidders to select suitable consultants to support the phase 2 programme design, in-depth nutrition audit of DFID programmes and independent evaluation. Recruitment of the SUN Nutrition Adviser will be done in accordance with DFID Human Resource policy and procedures. With support from the Nutrition Hub and the programme’s Technical Advisory Group (TAG) represented by the Senior Officials of the NFNC and CPs, DFID Zambia will develop separate terms of reference (ToRs) for the different pieces of work. The ToRs will have a defined set of milestones and results/deliverables expected to be delivered by the bidders/candidates. / While quality, technical expertise and innovation will be critical considerations in the selection of bidders/candidates, DFID Zambia will give high priority to technical capacity and efficiency and the ability to deliver the required service at the lowest cost. Past performance in working with programmes of similar nature will also be considered in order to ensure that optimum value for money is obtained.
C. How do we expect the market place will respond to this opportunity? / There is likely to be a limited local supply of competent consultants and advisers to provide technical assistance for the design, audit, delivery and evaluation of innovative nutrition interventions. Therefore, the use of DFID London’s Resource Centres to identify suitable bidders/candidates will provide a good pool of international expertise.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The key cost drivers are: consultancy and management fees, salaries, subsistence, travel, staff living and hardship expenses, and trainings. / Value for money for the programme will be ensured by engaging bidders/candidates with reasonable capacity and a proven track record to perform the tasks required to a high standard. DFID PrG has negotiated a set of prices for consultancy and management fees, subsistence and economy flights with the pre-qualified bidders. An action plan and budget with clear key performance indicators (KPIs) will be agreed with the successful bidders. These will be appended to the contract and provide benchmarks against which satisfactory performance is measured. Contracts will be designed in such a way that payments are made upon fulfilment of the agreed action plans/KPIs. A single contract will be issued for i) technical assistance for the phase 2 programme design and the in-depth audit of DFID programmes and ii) mid-term and end of programme evaluations. However, continuity of the contracts will be subject to satisfactory performance of previous assignments. It is anticipated that prospect of further work will generate an additional incentive to deliver a high quality product. In order to guard against cost fluctuations, the contracted bidders will be encouraged to identify savings within the approved budget and use these to meet any shortfalls that might arise thereof. / Although the Adviser will be contracted for three years, s/he is required to have annual performance objectives with DFID Zambia. The objectives will be reviewed every six months, and satisfactory performance shall determine continuity of the contract. The Adviser’s pay and benefits will be in line with DFID employee terms and conditions.
E. What is the intended Procurement Process to support contract award? / Procurement of consultants will be done by PrG through a mini competitive tender process using the existing framework arrangement with DFID’s Human Development and Nutrition Resource Centres. The PFA Adviser will be recruited through DFID internal recruitment mechanisms. External recruitment will be considered in the event that no suitable candidate is identified through the internal recruitment process. ToRs, selection criteria and timescales will be agreed with DFID SUN and/or Nutrition Hub and the programme’s TAG. Pre-qualified consultants will be invited to submit expressions of interest and those that meet the essential selection criteria shall be invited to submit a full proposal and budget. NFNC and TAG will be involved in evaluating the bids and selection of suitable bidders. DFID London will be responsible for the recruitment of the SUN Nutrition Adviser.
F. How will contract & supplier performance be managed through the life of the intervention? / Consultants’ contracts will include ToRs with a defined set of milestones and results/deliverables. Action plans and budgets with clear KPIs will be agreed with each of the successful bidders. These will serve as benchmarks for all payments. The contracts will also incorporate steps to be taken in the event of poor performance and failure to deliver the expected results and value for money. / The consultants will report to DFID’s Health and Nutrition Adviser and the NFNC on technical issues, and to the DFID Programme Officer on financial management. The Adviser will arrange for regular meetings with the consultants to discuss progress on the various assignments. The SUN Nutrition Adviser will be managed by the DFID Zambia Health and Social Development Team Leader.

# Indirect procurement
A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The programme will be mainly funded through Third Party Organisations (TPOs) as follows: / 1. Memorandum of Understanding (MoU) cost extension with UNICEF for the multi-annual support to the CHWk programmes. DFID has a framework agreement with UNICEF, and a local contribution arrangement for the food consumption and micro-nutrient assessment is already in place. The arrangement will be extended to cover the proposed components of this programme. / UNICEF works closely with MoH and has been financially supported by DFID Zambia in the past years to deliver these campaigns. CHWks form a key component of UNICEF’s Country Programme Plans for 2011-15 and these are expected to: / Increase equitable access to nutrition, maternal, newborn, child health and paediatric HIV prevention, care, treatment and support services; / Improve capacity in all health facilities in the target districts to provide community based health care; and / Contribute towards adoption of key healthy family practices and promote male involvement for nutrition, maternal, newborn, child survival as well as paediatric HIV prevention, care, treatment and support in all health facilities in the target districts. / 2. An MoU with the International Food Policy Research Instiute (IFPRI) for the Efficacy Trial on Vitamin A Bio-fortified Maize. IFPRI will work in partnership with HarvestPlus to carry out the trial. IFPRI is a globally renowned organisation that seeks sustainable solutions for ending hunger and poverty. It receives funding from a wide range of foundations, private sector national governments, regional and international organizations. HarvestPlus, a Challenge Program of the Consultative Group on International Agricultural Research (CGIAR), is co-managed by IFPRI and Centro Internacional de Agricultura Tropical (CIAT). HarvestPlus is a global leader in developing bio-fortified crops and works with more than 200 agricultural and nutrition scientists around the world. In Zambia, it has been developing pro-vitamin A maize varieties in partnership with local organisations such as the Zambia Agricultural Research Institute and Zamseed. DFID UK contributed £8 million to the core activities of IFPRI and HarvestPlus from 2004 to 2010 but none of this funding was allocated to the proposed Efficacy Trial in Zambia. / 3. Letter of exchange under the existing MoU with COMESA/TradeMark Sothern Africa (TMSA) for ColaLife Operational Trial in Zambia (COTZ). ColaLife is a new innovative concept which will be tested for the first time in Zambia. The concept has been under development for the past 3 years and is widely supported by expert leaders in logistics and global health. It is focused on distribution of Anti-Diarrhoea Kits (ADKs) to mothers and caregivers in under-served rural areas via the private sector commodity distribution network at an affordable cost. TMSA/COMESA is interested in the learning outcomes from COTZ, in particular, market access via remote rural distribution chains and potential for new/innovative Public-Private Partnerships (PPPs). TMSA is hosted by COMESA and is already governed by an MoU between DFID South Africa and COMESA. It also has a local office in Zambia with sufficient office space and competent personnel for project administration and management. Therefore, implementation of the COTZ through TMSA/COMESA will offer considerable time-savings and efficiency in project initiation and management. / 4. Accountable Grant (AG) cost extension with THET for the establishment of the nutrition degree at UNZA. THET has a track record in developing and delivering courses at UNZA by drawing on the expertise and commitment of UK and international health professionals to provide external teaching support. It has an AG arrangement with DFID for the Zambia/UK Health Workforce Alliance (ZUHWA) programme. Under the existing ZUHWA programme, THET has recruited a large network of UK and international health professionals who are successfully helping to support the delivery of Master of Medicine courses in Anaesthesia, Pathology and Psychiatry at UNZA. THET also has an established local office with qualified and a dedicated personnel that ensures sound coordination and management of programme operations. / The unique institutional arrangements with an established presence in country, level of expertise and commitment possessed by all the four organisations is most unlikely to be secured through the tendering process. Therefore, the use of MoUs and an AG to fund the programmes’ interventions is justified and in line with DFID procurement guidance. This will also minimise the management resource associated with the formal competition process as well as high office set up costs for organisations without a physical presence in Zambia. The use of MoUs/letter of exchange and AGs will provide DFID with a more flexible cost-effective mechanism to fund already existing interventions, and new innovative approaches that can then be adapted as necessary over the lifetime of the programme. DFID will also be investing in a process as a partner without needing to take a lead role in the development and operational management of the different projects. / The MoU and AG arrangements will be based on a detailed programme proposal with work plans, budgets and key performance indicators. DFID will: / Review the programme partners’ work-plans/procurement plans and budgets annually to monitor efficiency and identify cost savings; / Track progress and budget execution through quarterly meetings, activity and financial reports with all programme partners; / Review programme partners’ financial management, procurement and sub-contracting processes to ensure that sub-contractors provide VfM; and / Conduct formal annual reviews to monitor progress, efficiency and VFM.
B. Value for money through procurement / DFID has been providing support to a range of programme activities being undertaken by UNICEF, TMSA/COMESA, IFPRI and THET. So far, these organisations have demonstrated that they have reasonable corporate systems to effectively manage DFID’s funding as well as deliver value for money in procuring various goods and services. / The DFID’s Multilateral Aid Review (MAR) (2011) rated UNICEF as providing very good value for money for UK development objectives. As a result, the UK announced a near doubling of funding to UNICEF. The UN is an international organisation and its role as a provider of technical assistance in development work at both global and country levels is significantly recognised by DFID. However, working with and through the UN system and UNICEF in particular can be challenging. The MAR pointed out that UNICEF lacks a portfolio quality system to manage project performance and transparency policy for disclosure of full information on all projects. To address these concerns, strong performance indicators and requirements to share information with its programme partners as well as DFID will be built into the contribution arrangement. DFID will ensure that UNICEF Zambia: / Has quality assurance procedures to ensure goods and services are fit for purpose; / Undertakes due diligence checks on its development partners that will be contracted to deliver any component of the programme; / Carries out periodic cost comparison exercises for a range of commonly procured items as well as maintains an efficiency savings delivery plan for year on year cost savings. These will be monitored through quarterly meetings and progress reports; / Draws up clear ToRs with a defined set of outputs, deliverables/milestones and targets; and / Agree and monitor a formal risk strategy which sets out specific responsibilities of DFID, all programme partners and their sub-contractors for managing and mitigating risk. / Under the framework arrangement, DFID is required to contribute 7% of the total budget as ‘recovery costs’ to fund indirect programme support. In return for this UNICEF Zambia will get technical support from Regional and HQ staff and the programme will get support from local core funded staff (procurement officers etc). In addition to the central ‘recovery costs’, UNICEF Zambia will charge ‘programme support costs’ of up to 10%. This will be negotiated to ensure value for money. UNICEF will be required to specify as far as possible what will be funded from ‘programme support costs’ including named staff position dedicated to the programme. / TMSA/COMESA has a longstanding relationship with DFID. TMSA/COMESA commercial capacities have been assessed previously by DFID and other CPs such as USAID and the European Commission. The assessment findings show that TMSA/COMESA has in place accounting and procurement procedures that meet DFID’s required standards. TMSA/COMESA will set up a management and financial reporting structure for COTZ that will ensure DFID is provided with regular activity and finance reports outlining progress against agreed annual work-plans and targets in the logframe. TMSA/COMESA will receive the project funding and disburse to the project partners in conformity with the financial risk management processes and procedures as agreed with DFID Zambia. It will also agree with its partners the payment milestones in advance and in accordance with the COTZ plan and performance indicators. An MoU between ColaLife and TMSA/COMESA will be established to govern the relationship, with ColaLife devolving financial process for COTZ and the direct management line of its project management staff to TMSA/COMESA. TMSA/COMESA will not charge DFID Zambia any project management/administration fees. / IFPRI commercial capacities were assessed by the EU and CGIAR internal audit in 2007. The report shows that IFPRI benefits from a robust internal control environment, which is based on principles of proper segregation of duties and the adequate management control. IFPRI follows CGIAR financial guidelines for managing its procurement and these are very comprehensive – a copy has been shared with DFID Zambia and PrG. Since IFPRI’s core business is research, all consultant procurement goes through a vetting process that is performed by the program divisions and reviewed by the Finance Unit. Competitive tendering is carried out for procurement of US$10,000 and above. Quotations from several suppliers are routinely obtained, and fees of consultants are reviewed for reasonableness through, for example, curriculum vitas. Procurement spending is monitored through project summary reports, and project leaders review and approve consultants/collaborators’ output to ensure quality for the rendered services. A clearly identified set of deliverables are included in the ToRs and appended to all contracts signed with service providers. Payments are dependent on submission of technical and financial reports and approval of these reports by HarvestPlus Programme Coordinators. All original signed contracts are kept in IFPRI’s storage facilities. IFPRI finances are regularly audited internally by CGIAR Internal Audit Unit and externally by McGladrey and Pullen Certified Public Accountants. Costs associated with CGIAR system-wide initiatives are excluded from the indirect rate computation when IFPRI’s role is to disburse funds to other centres, and there is no responsibility for management of other other centres’ performance. A 2% administrative charge is applied to system-wide initiative activity. HarvestPlus will charge a maximum of 10% as overhead costs. The proposed management fees are deemed reasonable. / THET has been funded for several years by DFID and proven to properly account for the advanced resources. THET is renowned for its sound financial management, and the proportion of its expenditure on procurement of goods/services is minimal (less than 1%) because the main focus of its operation is advocacy for quality human resource for health. The only formal contract tendered has a total contract value of £40,000 over four years, an equivalent to 0.8% of turnover. A basic procurement procedures’ manual is in place and has been shared with DFID. THET’s formal procurement procedures are applicable to the procurement of goods/services in excess of £10,000 and these are undertaken on the basis of three quotes. Single source tender procurement for this category is also acceptable subject to a sound justification by the budget holder and demonstration of value for money. For procurement of less than £10,000 a single fixed price quote is acceptable. These limits are minimal and can be reduced to reflect circumstances by individual countries. THET’s project administration/management costs are pegged at 10% and these can be negotiated downwards. Therefore, DFID will attain value for money for the proposed intervention by supporting THET. DFID will arrange for regular meetings and annual reviews to monitor performance of the project.

# Financial Case
A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total funding required is £3,450,000 million for Phase 1 and a summary budget breakdown is provided in the table below. The budget includes a significant component on consultancy fees for research and evaluation. Phase 2 costs will be generated on the basis of findings and recommendations from Phase 1 activity reports. / Type of Intervention 2011/12 2012/13 2013/14 2014/15 Total / Phase 1 / TA for design of Phase 2 - 150,000 - - 150,000 / DFID audit of nutrition programs - 5,000 - - 5,000 / PFA post - 75,000 75,000 75,000 225,000 / Independent evaluation and audits - 75,000 - 75,000 150,000 / Child health week 200,000 245,000 245,000 245,000 935,000 / ColaLife Trial (including capacity building) 150,000 600,000 750,000 / Efficacy trial on vitamin A Maize bio-fortification 150,000 350,000 180,000 680,000 / Nutrition degree program - 185,000 185,000 185,000 555,000 / Grand total 500,000 1,685,000 685,000 580,000 3,450,000 / The annual work-plans and budgets submitted by each programme partner will be reviewed on a quarterly basis. DFID will agree any changes and use them to regularly update forecasts.
B. How it will be funded: capital/programme/admin / Programme resources have been allocated for nutrition in DFID Zambia operational plan for 2011-15. The SUN Adviser Post will be funded on a 50% basis through programme funds from Policy and Research Division in DFID London and DFID Zambia.
C. How funds will be paid out / For contracts, funds will be paid out in arrears upon satisfactory completion of the agreed tasks. / The initial payments will be done in advance at quarterly intervals for THET and TMSA/COMESA, and on a half yearly basis for UNICEF and IFPRI. The bi-annual payments are necessary to enable principal recipients and sub-grantees ample time to properly spend and account for the advanced funding. Each organisation will be required to provide forecast expenditure requirements for the periods to be covered by the advance. A statement of actual expenditure incurred during the previous period will be required in addition to forecast expenditures for subsequent advances. / These payment terms and conditions will be clearly stipulated in the issued contracts, MoU and AG arrangements.
D. What is the assessment of financial risk and fraud? / Although the commercial systems for UNICEF, TMSA/COMESA, IFPRI and THET’s have been tested and proven to be reliable, there is a risk that some of the sub-recipients do not fully understand the VfM concept and have weak systems for managing resources and procurements. This is likely to particularly affect the ability for UNICEF, TMSA/COMESA and IFPRI to timely spend and report to DFID. To minimise this, DFID Zambia will ensure that UNICEF, TMSA/COMESA and IFPRI carry out commercial assessments on each of the development partners prior to advancing them with any funding. DFID will agree in advance and jointly monitor a financial risk/fraud management strategy with UNICEF, TMSA/COMESA and IFPRI. Each organisation will be separately held accountable for any fraud or misappropriation of funds. In such instances, DFID Zambia will also consult with the Fraud Unit/Department on the appropriate action to be undertaken. Programme partners will also be encouraged to report any suspected financial risk or fraud to DFID Zambia or other relevant agencies. / E. How expenditure will be monitored, reported, and accounted for? / DFID Zambia will rigorously monitor the programmes’ expenditure using our financial management system. The consultants will submit invoices in arrears for works successfully completed. Authorisation of payment of such invoices will be done by the Health and Nutrition Adviser or the equivalent approving officer. / UNICEF, TMSA/COMESA, IFPRI and THET will submit half-yearly and quarterly progress activity and financial statements that clearly outline the activities carried out in any given period. Any invoices for payments will be scrutinised to ensure VfM and compliance with the agreed annual/quarterly work plans and budgets. Each of the organisations will also provide annual narrative reports, and certified audit statements/reports showing funds received and expended for the programme. They will be required to also maintain asset registers for items above a certain value. These will remain the property of the DFID, and their disposal during and at the end of the grant shall be arranged in consultation with the DFID Zambia. Except as may otherwise be decided by DFID and the individual implementing partner, any unspent funds upon completion or termination of the programme intervention will be returned to DFID. These requirements will be stipulated clearly in the signed MoUs/Letter of exchange and AG arrangements.

# Management Case
A. What are the managing arrangements for implementing the intervention? / A Technical Advisory Group (TAG) will be established from the outset of this programme with senior representation from the NFNC, DFID Zambia and the CPs. The TAG will be responsible for the overall quality control and managerial and technical oversight of the programme. It will be chaired by the NFNC’s Executive Director. The Management Team will meet at least on a quarterly basis to review progress and challenges. Other stakeholders (private sector partners, NGOs) will participate in quarterly meetings as appropriate. The TAG will report to the Minister of Health. / Key issues and lessons learnt from the implementation of the programme will be shared as part of the overarching national arrangements proposed by the GRZ to improve collaboration on nutrition actions: the National Food and Nutrition Ministerial Steering Committee at Cabinet level and the National Food and Nutrition Multi-stakeholder Committee, also chaired by the NFNC. The multi-stake holder committee will include participation of key government line ministries, CPs, Civil Society, and the Private sector. / Key issues, progress and lessons will also be fed to the relevant sectoral groups (SAGs), including Health, Education, Gender and Social Protection. / In sum, the TAG will: / Oversee the efficient management of the programme / Provide leadership for good functioning of the partnership, communications and results. / As noted in the commercial section, the design of phase 2 will be done through technical assistance contracts. MoUs/Letter of exchanges with UNICEF and TMSA/COMESA will be signed for the support to the CHWks programme and the ColaLife trial; and Accountable Grant arrangements will be made with IFPRI and with THET. All agreements will set out a detailed programme proposal with work plans, budgets and key performance indicators will be used as a basis for monitoring progress. In addition to engaging the TAG, DFID’s Health and Nutrition Adviser, with support from the Programme Officers, will: / Review the programme partners’ work-plans/procurement plans and budgets annually to monitor efficiency and identify cost savings; / Track progress and budget execution through quarterly meetings, activity and financial reports with all programme partners; / Review programme partners’ financial management, procurement and sub-contracting processes to ensure that sub-contractors provide VfM; and / Conduct formal annual reviews to monitor progress, efficiency and VfM. / The main beneficiaries of the project are the NFNC, key line Ministries (e.g. MoH) and the communities in which activities will be implemented. The NFNC and key line Ministries will be involved through the TAG and the Nutrition Ministerial Committee. The communities will be involved and consulted during the preparation of the innovative trials and throughout implementation. / DFID will include a clause noting its right to terminate any agreement entered in the event that this ceases to represent value for money in each contract, MoU and AG signed under the project. / Within DFID Zambia, the Health and Nutrition Adviser will have overall management oversight of the programme and report to the Human Development Team Leader. Additional inputs on financial and administrative issues will be provided by the Deputy Programme Manager and the Programme Finance Group. The SUN Adviser will work closely with the NFNC for drafting ToR in line with identified priorities, monitoring technical assistance and follow-up actions. / The Health and Nutrition Adviser and the SUN Adviser will liaise with DFID’s Evaluation Department and Research and Evidence Division for the inputs into the research and evaluation components of the programme. They will meet regularly with the NFNC, CPs Group and other partners. / The management of the various components will be handed over to a management agency once phase 2 of the programme has been designed in order to reduce transaction costs for DFID Zambia.
B. What are the risks and how these will be managed? / Risks Probability / (3 high, / 1 low) Impact / (3 high 1 low)) Mitigation strategies / 1 .Lack of Political Leadership under new GRZ (national elections held in September 20; Patriotic Front opposition leader Michael Sata elected as President) 2 3 The launch of the new National Food and Nutrition Strategic Plan was postponed until a new Cabinet is in place. Given global attention on malnutrition, buy in from the new Government is expected. Support to advocacy from civil society planned under the project will help mitigate this risk. Through our relationship with Ministry of Finance and Cabinet Office we will lobby for increased resources to addressing malnutrition. / 2. Financial fraud, corruption or funds not being used for planned purpose. 1 2 Given that no funding will directly be channelled through government institutions, and that we will ensure that our indirect implementing partners have the necessary checks and balances in place, the risk of misuse of funds is relatively low. Regular monitoring of financial implementation of activities will take place. We have allocated resources for additional audits of project partners if necessary. / 3. Increased food insecurity due to unfavourable climatic conditions 2 2 In the long term, Zambia is expected to be significantly affected by climate change and a number of initiatives to minimise climate shocks in the country are underway. There are areas – e.g. the South, which are more prone to droughts. If this were to happen, chronic food insecurity can rapidly escalate into acute food insecurity, especially for small subsistence farmers. In this case, we would apply for humanitarian funds to minimise the damage. / 5. Weak human resource capacity 2 1 Strengthening capacity at national (NFNC, key sectoral ministries) and decentralised level (selected districts) will be a key component of the project. We will support broad capacity building, addressing systemic issues, increasing technical expertise in the country, involving the NFNC in the management of the project, and will not just consist on short-term technical training courses or provision of technical assistance. / 6. Higher than expected estimates of micronutrient deficiencies 1 1 The ongoing food security and micronutrient survey might reveal a worse malnutrition situation in some pockets of the country than is currently thought. We will revise expected outcomes accordingly and target our support to the worst affected areas. We will also strive to encourage synergistic nutrition interventions which address several direct and indirect causes of undernutrition.
C. What conditions apply (for financial aid only) / Not applicable, as the programme does not involve financial aid to Government.
D. How will progress and results be monitored, measured and evaluated? / An independent mid-term review of the overall programme will be undertaken at the end of 2013 and a final evaluation will be done at the end of the programme, in 2015. It will include governance, social and economic expertise as well as involve consultation among beneficiaries. / The project has a significant monitoring and evaluation component, given the need to increase the evidence base for some nutrition interventions and what the best delivery channels might be. Embedding evaluation in nutrition has been identified as a key priority for DFID, and this project will contribute to building up the evidence base for scaling up nutrition globally. / The monitoring and evaluation strategy will include the following components: / 1) A routine programme monitoring plan. The project log-frame (see Annex) outlines the main monitoring arrangements and expected results. The TAG will be responsible for agreeing a monitoring plan incorporating process and outcome indicators, to review progress against work plans. All interventions funded through the project will have their own monitoring component which will include key nutrition indicators. Some of these indicators will be collated and reported through the Health Management Information System, others through special surveys (e.g. UNICEF ongoing micronutrient survey). In addition, baseline and end line data will be collected as part of their impact evaluations (ColaLife and HarvestPlus). / 2) Testing new delivery approaches for direct nutrition interventions. In the case of ColaLife, given that the intervention itself (zinc for the treatment of diarrhoea) has a strong evidence base, we will invest in a first proof of concept or operational trial to test this particular delivery approach and apply the findings within and beyond the life of the programme. / 3) Efficacy trial with impact evaluation. Support will be provided to conduct an efficacy trial on the nutritional impact of pro-vitamin A biofortified maize among children. / 4) Dissemination of evidence and lessons learnt to programme partners, policy makers and beyond to maximise uptake and impact of the findings and promote transparency. / 5) Annual reviews of the nutrition impact as a result of making DFID Zambia programmes nutrition-sensitive will also be undertaken. / Finally, the programme will undergo an annual DFID review process.

# ANNEX 1: Logframe
PROJECT NAME
IMPACT	Impact Indicator 1		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
Improved health and nutritional status of children under 5		Planned	119/100,000	not measured	75/100,000	not measured (rapid progress not expected over short-time period)	56/100,000
	Reduction in under 5 mortality	Achieved	2007
			Source:DHS
	Impact Indicator 2		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
		Planned	46%	not measured	43%	not measured	41%
	Reduction in under 5 prevalence of stunting	Achieved	2007
			Source: DHS
	Impact Indicator 3		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Reduction in prevalence of low-birth weight babies (<2.5 Kg)	Planned	9%	not measured	7%	not measured	6% (TBC)
		Achieved	2007
			Source: DHS
OUTCOME	Outcome Indicator 1		Baseline	2011/12	2012/13	2013/14	Target (2014/15)	Assumptions
Strenthened national nutrition response focused on addressing direct and undelying causes of stunting	Reduced prevalence of Vitamin and mineral deficiencies (improvement in micronutrient status in children <5)	Planned	46% iron deficiency anaemia; 53% Vit A deficiency	not measured	30%	not measured	20%	New Government of Zambia remains committed to the Scaling Up Nutrition global and natiomal initiatives ; donor support to maternal and child health interventions continues ; good candidate to take up SUN Adviser post identified
		Achieved	2007
			Source: DHS, specific micronutrient surveys
	Outcome Indicator 2		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Innovative channels for delivery of nutrition interventions developed	Achieved	Global call for investing in new nutrition interventions		GRZ and CP dialogue around lessons learned from pilot on scaling up	Successful interventions scale up began	Further scale up of successful intervention
			Source: Project review
	Outcome Indicator 3		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Total funding for nutrition interventions	Achieved	US$75,000 (MoH nutrition budget)				TBC
			Source: Gov accounts and project review

	Outcome Indicator 4		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	National 1,000 critical days strategy developed, costed and supported by multiple stakeholders	Achieved	ToR for 1,000 days plan developed	1,000 days plan developed and agreed between GRZ and CPs			Plan fully implemented
			Source: Project review
		Achieved
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£17 million (of which £3,150,000 million are for phase 1)
INPUTS (HR)	DFID (FTEs)					Strengthened efforts and supervision in underperforming districts leads to similar outcomes seen in better performing districts;
	0.5 DFID Health & Nutrition Adviser; 0.3 DFID SUN Adviser
		Source

OUTPUT 1	Output Indicator 1.1.		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
Strengthened implementation of Child Health Weeks programme	Anaytical study to identify how best to address gaps, with a focus on underperforming districts, done	Planned	no studies done to date	analytical study done by end 1st quarter 2012;
		Achieved
		Source: ToR and study report
OUTPUT 1	Output Indicator 1.2.		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
Strengthened implementation of Child Health Weeks programme	Cummulative number of CHW rounds completed (through this project)	Planned	0	2	4	6	8
		achieved
		Source: UNICEF reports

	Output Indicator 1.3		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Coverage of Vit A tablets (National and in 9 under-performing districts of (3 under-performing districts from Northern Province three from Western Province and three from North-Western Province will be monitored regularly to track sustained progress)	Planned	National (90%); 9 focus districts baselines: Chavuma, Mufumbwe, Zambezi, Kaputa, Mbala, Mpulungu; Kalabo, Kaoma, Mongu (TBC)	TBC	TBC	TBC	> 95% Vit A coverage in all 73 districts
		Achieved
		Source: UNICEF and GRZ reports
	Coverage of deworming tablets (National and 9 focus districts as above)	Planned	9 focus districts baselines: Chavuma, Mufumbwe, Zambezi, Kaputa, Mbala, Mpulungu; Kalabo, Kaoma, Mongu (TBC)	TBC	TBC		> 95% deworming tablets coverage in all 73 districts
		Achieved				TBC
IMPACT WEIGHTING (%)		Source: MoH and Unicef Programme reports					RISK RATING
35%					low
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£935,000
INPUTS (HR)	DFID (FTEs)
	0.1 Health and Nutrition Adviser

OUTPUT 2	Output Indicator 2.1		Baseline	2011/12	2012/13	2013/14	Target (2014/15)	Assumptions
		Planned					Commitment from other Cola Life supporting partners to test inteventions (e.g. Coca Cola) maintained; no major political instability impedes pilot implementation; pilot is completed as planned (for papers)
Support to promissing, well- designed innovative approaches provided and lessons diseminated	At least two innovative nutrition interventions tested (Cola Life and maize bio-fortification)	Achieved	3 proposals received	Support to 2 interventions agreed and programmes initiated	Two pilot s completed and reports of lessons learned finalised. At least 2 papers produced
		Source: Project review

IMPACT WEIGHTING (%)					RISK RATING
25%					medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£1,430,000
INPUTS (HR)	DFID (FTEs)
	0.2 Health and Nutrition Adviser

OUTPUT 3	Output Indicator 3.1		Baseline	2011/12	2012/13	2013/14	Target (2014/15)	Assumptions

Design of multi-sectoral approach completed	a) Mapping of nutrition interventions and gap analysis completed b) Development and costing of 1,000 days plan supported c) Phase two of nutrition programme approved	Planned	draft ToR for programme design consultancy completed	Mapping completed, 1000 day plan developed and costed	DFID response developed (June 2012) programme approved and implementation begins (August 2012)	Other DFID programmes enhanced to address nutrition		GRZ remains committed; NFNC and other partners are involved in and supportive of the design; civil society is willing to engage in nutrition advocacy action ; good technical assistance can be deployed and works effectively with key stakeholders
		Achieved
		Source
	Output Indicator 3.2		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Capacity building plan for NFNC and key sector Ministries developed and costed	Planned	No plan	Draft ToR discussed with NFNC and CPs.	Technical adviser in place and plan developed	Programme with NFNC fully operational
		Achieved

	Output Indicator 3.3		Baseline	2011/12	2012/13	2013/14	Target (2014/15)
	Development and implementation of of an appropriate degree courses (Bsc, Msc) in nutrition at UNZA	Planned	concept note received from THET and UNZA	Detailed assessment of UNZA capacity needs completed; BSC curriculum reviewed and updated;	BSC teaching support ongoing (with int lectures by July ); MsC Curriculum developed and first cohort of students begin course	Degree course continues	Degree course continues (ist cohort of BSc and MSc by 2016)
		Achieved
		Source
		UNZA reports
IMPACT WEIGHTING (%)		Source					RISK RATING
40%					medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£900,000		TBC+D30			90%
INPUTS (HR)	DFID (FTEs)
	0.5 of SUN Adviser; 0.2 of Health and Nutrition Adviser

Endnotes