Business Case and Intervention Summary

Intervention Summary

Title: Kosovo – Election Reform Response Fund

What support will the UK provide?
The UK will provide up to £350,000 over 12 months (to end September 2012) to support the current election reform process by ensuring successful implementation of the measures to improve the accuracy of the voters list; to train and improve capacity of the Central Elections Commission (CEC) secretariat to deliver effective and transparent national parliamentary, Presidential and local elections, as well as supporting the parliamentary working group on election reforms. This is an ongoing process of reform and UK will work with other development partners in agreeing and supporting the priority recommendations arising from the consultation, in order to implement agreed improvements to the current electoral system. / DFID will graduate from bilateral assistance to Kosovo at the end of 2012, so this is the last phase of our support to strengthening accountability and democracy in Kosovo.

Why is UK support required?
Kosovo still faces enormous political challenges that threaten the integrity of a newish state which only came into existence in 2008. Since the end of the conflict in 1999/2000 Kosovo has continued to be the recipient of UK and other receive international assistance. / As part of the UK’s Government’s Country Business Plan for Kosovo, one of our good governance goals is to reform the electoral system in order to have a stronger more accountable government n Kosovo. / In 2010, UK provided support for the monitoring of the extraordinary parliamentary elections. Due to the UK’s knowledge and expertise in this area and our quick response the CEC has approached DFID to support the current reform process. / The current Kosovo election system was designed by the Organisation for Security and Cooperation in Europe (OSCE) in 2000. The system has been changed on two occasions since, however, these were largely amendments to election law rather than a more comprehensive and inclusive process of reform. According to policy think tanks in Kosovo these changes did not specifically address reforms which would lessen the opportunities for election malpractice and did not take sufficient account of the views of the local population, which is required to improve greater trust and ownership of the system. / DFID supported the monitoring and observing of the December 2010 national parliamentary elections. Those elections highlighted some important gaps in the electoral system, the Central Elections Commission Secretariat (CEC-S) capacity to run elections and technical aspects related to the election day and polling stations. Moreover, the preliminary census results highlighted issue of the inaccuracy of the voters list. The overall size of the population almost corresponds to the number of registered voters and this needs urgent attention. / This new phase of DFID support will seek to build on the earlier UK intervention.

What are the expected results?
The project will be responsive in approach in order to address priorities and measures identified during this reform process. The project outputs will include: / Strengthened Kosovo institutional capacity for running elections; / Increased credibility of the election process by improved accuracy of voters list; / Greater public trust and ownership over the election system, election law and institutional architecture. / This is a relatively small but responsive project that will support the key needs and priorities as identified by the High Level Elections Working Group, the CEC and Kosovo Civil Society.

Business Case

Strategic Case

A. Context and need for a DFID intervention / This intervention will contribute to the overall Kosovo UK Country Business Plan and the specific objectives on Good Governance and Effective Rule of Law in particular. / The current Kosovo election system was designed by the Organisation for Security and Cooperation in Europe (OSCE) in 2000. The system has been changed on two occasions since, however, these were largely amendments to election laws rather than a more comprehensive and inclusive process of reform. According to policy think tanks in Kosovo these changes did not specifically address reforms which would lessen the opportunities for election malpractice and did not take sufficient account of the views of the local population, which is required to improve greater trust and ownership of the system / The December 2010 national elections had a number of flaws and failings with regard to electoral conduct. More than 100 complaints by individuals, political parties and CSOs were made to the Elections Complaint Mechanism. The general public demand for reform and the parliamentary blockage to elect the President resulted in a general consensus between all political parties and the Civil Society that the election reform with a simultaneous constitutional reform are urgent. A twenty-two months deadline to complete this process was agreed as well. / The positive aspect of this process of reform is its timing. Kosovo stakeholders now have much more practical experience of running elections and have clearer understanding of what works and doesn’t in the Kosovo cultural and legal context, than back in 2000 when the election system was designed. / The European Commission Liaison Office (ECLO) in Kosovo is providing support through a Technical Legal Elections Expert, who will help with the legislative aspect. The USAID funded projects, implemented by National Democratic Institute (NDI) and International Foundation for Electoral Systems (IFES) are also concentrated in this aspect only. The British Embassy, through funding a project implemented by Kosovo Institute for Policy research and Development (KIPRED) are facilitating public participation and inclusion in the reform process. / During this electoral policy reform and institutional strengthening of the CEC and its secretariat, DFID has already been asked to support the training of the new secretariat members. The Training Course on management of the voters list, will be provided by a specialised Institute in Hungary called the Association of Eastern European Election Officials (ACEEEO[1]), and it will be tailored to the individual needs of each Secretariat member. This support will form the first output of this project and its cost is estimated between £50-70K. / Our support will be closely coordinated with the CEC, Kosovo Parliament, the British Embassy in Prishtina and other key donors. / The reforming process has started and it gives an impression of being comprehensive and it insofar has demonstrated that it seeks to carefully address all current shortcomings and is seriously discussing advantages and disadvantages of policy options on the table. / Actions taken so far are: The establishment of the Parliament Committee on Elections Reform and the Parliament Committee on Constitutional Reform. / Feasibility / A DFID intervention in the areas outlined here is feasible and would be welcomed by all relevant Kosovan stakeholders. / We believe that the project will make a significant contribution to enhancement of democracy in Kosovo by increasing country capacity for managing the election process, by enhancing the credibility of the election process and also by improving the citizen trust in election. Because all inputs are well coordinated between donors the CEC and the Parliament, and given the fact that this is a home grown reform initiative, we believe that all key preconditions exist.
B. Impact and Outcome that we expect to achieve / The impact of this programme will be strengthened and entrenched democracy in Kosovo and improved ownership of democratic processes that will lead towards greater citizen trust in the political systems. / The Purpose of the project is to help establish sustainable systems that will ensure organisation of credible and efficient elections accepted both within Kosovo and by the wider international community. / Key outputs and outcomes from will be: / To strengthen the technical and managerial capacities of the CEC; / Improvement of the Voter List accuracy (This is very important in the light of preliminary census results (The current number of voters almost equals the overall population number; / Complement other donor support by providing responsive support during this comprehensive reform process.
[1] ACEEEO promotes the institutionalization and professionalization of democratic procedures in the regions, as a non-profit organization, independent from political parties and governments. ACEEEO since its establishment continuously addresses theoretical and practical issues related to elections in the regions. http://www.aceeeo.org/

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / ….Establish the “Do Nothing” counterfactual / Feasible options for this intervention are: / There are three feasible options: / The project is approved and implemented / DFID hands over earmarked funds for electoral reform to the UK Embassy Prishtina for supporting the electoral reform / Do nothing / Critical success factors for this intervention to achieve its overall goal and purpose are set out in the table above, with appropriate weighting of these. Two of the most important success factors are that the project is approved on time and that the security concerns over the north do not overshadow the need for an election reform. / The advantage and value added of the DFID intervention, over those of other partners, is that we will be working directly with the Secretariat members and will be responsive to the needs as identified by the Kosovo partners. The CEC will have a critical role both in the reform process but also in ensuring that their members understand the implications of the reforms promulgated by the Parliament. / The cost of the intervention will be £350,000 over 12 months (or equivalent in Euro). This will mainly cover the costs of provision of training capacity development support for the CEC and short-term technical assistance to the parliament whereas it may also include short term support for CSOs and/or contributions to other stakeholders. There will also be costs in terms of time of DFID (Deputy Programme manager) to monitor project implementation. / Benefits of options / We expect the project to lead to quantifiable benefits in terms of domestic capacities to organise credible elections that in turn will result in increased faith in democratic processes and this will lead to increased political and social stability in Kosovo. / Actually, quantifying the benefits attributable to the project would entail a number of methodological problems and assumptions. However, we intend to monitor key aspects of the performance of the reform process and will use these as “proxies” for evidence on the impact of the project. / For example: (a) if Kosovo can stick to the 4 year cycle of general elections, there will not be a need for extraordinary elections and thus prevent incurrence of huge costs for running elections (last elections have had a overall cost of Eur 7.5 M or Approximately £6.8M.) This, we would expect that, using a reasonable set of assumptions, the expected project benefits would significantly outweigh it’s costs. / This will be further explored and tested during the implementation. / Initial risk appraisal of options / There is a risk that this reform process will not be seen through especially if the security situation in the north deteriorates significantly. However, there are no signals that this will happen. This risk, even if real, is outside the scope of this project to influence or mitigate. / Assessment of optimal design / We believe that the optimal design is a stand alone DFID response fund but working with a wider range of local and international stakeholders, as set out in the Strategic Case section above. The project will coordinate closely with the relevant EU and USAID projects and they have both endorsed and welcomed this approach. / Balance of costs and benefits / See above. / Sensitivity analysis / Not considered relevant in these circumstances. / Option 1: / DFID is seen as a neutral and independent agency in Kosovo, without vested interests, so we are well placed to work with a wide range of local stakeholders. / DFID will work with the UK Embassy. The project will build on the previous DFID support for effective monitoring of elections. / DFID project will use its good relations with the Political parties and the CEC, as well as OSCE to ensure that impact of reforms are monitored and problems fed back to the Parliament via a dialogue process. / Even though other donors are involved in supporting the Elections process in Kosovo USAID, EU and OSCE and have demonstrated their ability to work effectively with the CEC and the Parliament, their support is merely focused on the legal aspect of reform. Moreover, because USAID and OSCE were seen as the designers of the existing electoral system, their openness to it’s change/reform is felt to be somewhat limited. / Option 2: / The British Embassy is involved in the reform International Stakeholders group. They are quite involved in giving a political steer to the process. However, their capacities to design and manage a response fund for elections are limited. / Option 3: / Doing nothing option is the least recommendable option. When the request was made to DFID, we have given signals that we were seriously considering the request, which has raised the expectations with the CEC and other donors. A decision to do nothing would potentially damage DFID reputation in country.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Supporting this election reform process in Kosovo at the given moment, ahead of graduation, is adding a lot of value to the overall DFID legacy in Kosovo. Firstly because we are strategically complementing other donors and we believe the result expected outweigh by far the allocated resources. / 2 The project/programme management capacity at the UK Embassy to be able to design this support is limited. We recommend close coordination with the UK Embassy in Prishtina instead. / 3 Doing nothing option is not recommended due to comparative advantage offered by this intervention which builds on earlier DFID support and due to the raised expectations with CEC and the OSCE on our support. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 1 C / 2 2 C / 3 3 C
C. Appraisal of options / Resource costs of options / The cost of the intervention will be £250,000 over 12 months (or equivalent in Euro). This will cover the costs of provision of training capacity development support for the CEC and short-term technical assistance to the parliament, will also include short term support for CSOs and possibly joint funding initiative with other stakeholders. There will also be costs in terms of time of DFID staff to monitor project implementation; this is mainly the local Programme Manager. / Benefits of options / We expect the project to lead to quantifiable benefits in terms of domestic capacities to organise credible elections that in turn will result in increased faith in democratic processes and this will lead to increased political and social stability in Kosovo. / Actually, quantifying the benefits attributable to the project would entail a number of methodological problems and assumptions. However, we intend to monitor key aspects of the performance of the reform process and will use these as “proxies” for evidence on the impact of the project. / For example: (a) if Kosovo can stick to the 4 year cycle of general elections, there will not be a need for extraordinary elections and thus prevent incurrence of huge costs for running elections (last elections have had a overall cost of Eur 7.5 M or Approximately £6.8M.) This, we would expect that, using a reasonable set of assumptions, the expected project benefits would significantly outweigh it’s costs. / This will be further explored and tested during the implementation. / Initial risk appraisal of options / There is a risk that this reform process will not be seen through especially if the security situation in the north deteriorates significantly. However, there are no signals that this will happen. This risk, even if real, is outside the scope of this project to influence or mitigate. / Assessment of optimal design / We believe that the optimal design is a stand alone DFID response fund but working with a wider range of local and international stakeholders, as set out in the Strategic Case section above. The project will coordinate closely with the relevant EU and USAID projects and they have both endorsed and welcomed this approach. / Balance of costs and benefits / See above. / Sensitivity analysis / Not considered relevant in these circumstances.
D. Comparison of options / The same weighting is used as for CSC above. The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention. / Analysis of options against Critical Success Criteria / CSC Weighting Option 1: DFID project Option 2: EU & USAID only Add more columns as necessary / 1 5 5 25 3 15 / 2 5 4 20 4 20 / 3 5 3 15 3 15 / 4 / Total
Option 1 is the preferred option based upon a comparative assessment of the likelihood of meeting the critical success factors – leading to the achievement of the ultimate objective of this intervention, which is increased social stability in Kosovo with enhanced and credible democratic political systems. / E. Measures to be used or developed to assess value for money / See Commercial Case below. The cost of the project covers training costs for the CEC. Fees for external and local consultants may be incurred depending on capacity gaps identified during the implementation phase. If fee rates will be applicable we will ensure that those are based on market rates negotiated by DFID's Procurement Group.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / A. Clearly state the procurement/ commercial requirements for intervention / The first strand of work will be contracted directly with single supplier. Other funds will be spend based on need and demand and will be reviewed by DFID Head of Office, the Deputy Programme Manager and (subject to successful recruitment) a Governance Advisor based in the UK. / B. How does the intervention design use competition to drive commercial advantage for DFID? / Not relevant to this project. / C. How do we expect the market place will respond to this opportunity? / N/A / D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / We believe that it is the type of support we will be offering that has been recognised by both local and international stakeholders and by other donor partners that is increasing the chances for success and therefore brings value added to the process and represents value for money for use of DFID funds. / E. What is the intended Procurement Process to support contract award? / N/A / F. How will contract & supplier performance be managed through the life of the intervention? / There will be a mid-term review undertaken by DFID staff after 6 months of project implementation.
B. How does the intervention design use competition to drive commercial advantage for DFID? / N/A
C. How do we expect the market place will respond to this opportunity? / N/A
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / We believe that it is the type of support we will be offering that has been recognised by both local and international stakeholders and by other donor partners that is increasing the chances for success and therefore brings value added to the process and represents value for money for use of DFID funds.
E. What is the intended Procurement Process to support contract award? / The total expected budget requirement for this project will be up to £500,000 split between the 2 years as follows: / Financial year 2011/12 2012/13 Total / 2011 £200,000.00 £150,000.00 £350,000.00
F. How will contract & supplier performance be managed through the life of the intervention? / There will be a mid term evaluation undertaken by DFID staff after 6 months of project implementation.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / N/A
B. Value for money through procurement / N/A

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total expected budget requirement for this project will be up to £250,000 split between the 2 years as follows: / Financial year 2011/12 2012/13 Total / 2011 £200,000.00 £150,000.00 £250,000.00 / Funding will be drawn exclusively from the DFID Kosovo Framework.
B. How will it be funded: capital/programme/admin? / The full amount will be drawn from the DFID Kosovo programme resource allocation.
C. How will funds be paid out? / Contract and/or Accountable grants will be signed between DFID and the appointed service provider with some direct coverage of costs to the CEC.
D. What is the assessment of financial risk and fraud? / There is no risk of financial risk or fraud.
E. How will expenditure be monitored, reported, and accounted for? / The Elections International Stakeholders Group (EISG) has already been established and one function of the group is to oversee the reform process and donor projects. Without unnecessary burdening on the Parliament or the CEC the EISG may assume the oversight role. The feasibility of this option is to be determined.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The project will be managed by DFID Kosovo.
B. What are the risks and how these will be managed? / Risks is rated at low to medium exclusively because there is strong demand for these inputs, with the President of the CEC being personally involved in our discussions on the project.
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / See Commercial Case below. The cost of the project covers training costs for the CEC. Fees for external and local consultants may be incurred depending on capacity gaps identified during the implementation phase. If fee rates will be applicable we will ensure that those are based on market rates negotiated by DFID's Procurement Group
Logframe / Quest / No of logframe for this intervention: