Business Case and Intervention Summary

Intervention Summary
## Title: Increasing Access to Reproductive Health Commodities in Ethiopia
What support will the UK provide?
How much funding does the UK expect to provide? / The UK will provide £18 million over the next four financial years (November 2011 – March 2015)
Why is UK support required?
What need are we trying to address? / Ethiopia is off track to meet its Millennium Development Goal (MDG) Target for reducing maternal mortality. The best estimates suggest that over 22,000 women and girls die each year in Ethiopia (more than two women every hour) due to pregnancy related complications. Additionally, more than 500,000 Ethiopian women and girls suffer from disabilities caused by complications during pregnancy and childbirth each year. / Behind the direct causes of maternal deaths which relate to access to health services, are a number of factors that increase the likelihood of women dying in pregnancy and childbirth. These include high fertility rates, limited access to safe abortion services, and factors related to the status of women and girls. Ethiopia's fertility rate of 4.8 births per woman is one of the highest in the world. It is estimated that in 2008 one in ten pregnancies in Ethiopia ended in abortion - less than 40% of these were performed safely. Pregnancy and delivery complications are the main reasons for deaths amongst girls aged 15 – 19 years. / There are also broader reproductive health concerns including prevention of HIV and AIDS. Whilst HIV prevalence in Ethiopia is lower than many sub-Saharan African countries, an estimated 1.1 million people in Ethiopia are living with HIV and AIDS. A survey focused on identifying people most at risk of infection is planned, however based on current evidence it is clear that sex workers and their clients are amongst the most vulnerable. / Reducing unmet need for family planning and transmission of HIV will require efforts to increase access to and quality of reproductive health service, ensure a consistent and accessible supply of and demand for reproductive health commodities, and reduce gender inequalities. / What will we do to tackle this problem? / This programme will focus on increasing access to reproductive health commodities[1] and will make up part of the UK’s efforts to accelerate progress towards the health related MDGs in Ethiopia. It will complement the UK’s support to broader health systems and services, and targeted support to increase equity. / An appraisal of the options concluded that the greatest results and best value for money will be achieved by channelling UK support through a social marketing organisation to increase the sustainable supply of and demand for reproductive health commodities particularly for family planning and HIV prevention. / Who will be implementing the support we provide? / During the first year of implementation (2011/2012), for the sake of continuity and to avoid a break in supplies, support will be provided through DKT an international social marketing NGO that DFID has been supporting for a number of years. For the outer three years of the programme a supplier will be contracted following a competition under the new DFID Reproductive Health Framework .
What are the expected results?
What will change as a result of our support? / The impact of supporting reproductive health commodities in Ethiopia will be accelerated progress towards its health related MDG targets, particularly maternal mortality and reducing HIV and AIDS. This targeted support will complement DFID’s scaled up support for Ethiopia’s Health Sector Development Programme. / The outcome is expected to be reduced unmet need for family planning and incidence of HIV infection, particularly in women and men most at risk of infection. / What are the planned results attributable to UK support? / The outputs from UK support will be: / Increased supply of reproductive health commodities / Increased demand for reproductive health commodities / Strengthened national systems for reproductive health commodity planning and supply / Over the four years commodities procured and distributed with UK funding will include: / 295 million male and 136, 000 female condoms / 12 million oral contraceptives / 5.6 million injectable contraceptives / 2.2 million emergency contraceptives / 1.2 million misoprostol to prevent post partum haemorrhage / It is estimated that these efforts will avert: / 2.5 million unintended pregnancies / More than 8,000 maternal deaths / More than 240,000 total abortions / Between 35,000 and 100,000 HIV transmissions / How will we determine whether the expected results have been achieved? / Impact, outcome and output indicators will be monitored throughout the lifetime of the programme. Data will be obtained through a combination of routine data systems, surveys and nationwide surveillance instruments such as the Demographic Health Survey (DHS). Independent annual reviews and an end term evaluation of the support are planned which will assess the overall effectiveness, cost efficiency and equity of the programme.
[1] In this programme, reproductive health commodities includes contraceptives including condoms, and other medicines and equipment required for reproductive health services.

Business Case

Strategic Case

A. Context and need for a DFID intervention / A1 The Ethiopian Context[1] / Ethiopia matters to the UK for a range of development, foreign policy and security priorities. It is populous, poor, vulnerable but comparatively stable in the Horn of Africa. From a low base, Ethiopia’s growth and expansion of basic services in recent years have been among the most impressive in Africa. The UK Government has an opportunity to make our support more transformational and accelerate Ethiopia’s graduation from aid dependency. The Government of Ethiopia (GoE) is capable and committed to growth and development, and is a proven partner in making rapid progress towards the Millennium Development Goals (MDGs). But its approach to political governance presents both substantive challenges to sustainable development and reputational risks to partners. / Ethiopia lies at the heart of an unstable region that has experienced almost continuous conflict and environmental shocks in recent decades. Ethiopia and its neighbours – including Somalia, Sudan and Eritrea – languish at the bottom of the Human Development Index. Poverty and instability in the Horn of Africa are among the drivers of migration to Europe, and also contribute to an environment in which fundamentalism and radicalisation can prosper. UK interests in the region include progress towards the MDGs, resolving conflict, bolstering stability, accelerating sustainable growth and development, mitigating the impact of climate change, tackling migration, and countering terrorism. A stable, secure and prosperous Ethiopia is critical to UK interests. / Ethiopia has come a long way in a short time, and has achieved stability through decentralised regional government. But Ethiopia has yet to successfully manage its democratic transition. The Ethiopian People’s Revolutionary Democratic Front (EPRDF) took power in 1991 and have held it since then. They have made progress towards a functioning democracy and respect for human rights, but there is still a long way to go. Ethiopia has a capable government that is demonstrably committed to addressing poverty, with an impressive record of pro-poor spending, sound financial management and relatively little corruption. Prime Minister Meles and others in GoE play a role on global issues, including climate change, reform of the international financial architecture, and global health. / Ethiopia has made impressive progress towards the MDGs. In the last five years, with substantial support from the UK and others, Ethiopia has: halved the incidence of malaria; deployed 34,000 more health extension workers; doubled the immunisation rate[2]; rolled out an innovative social safety net to protect almost 8 million of the most vulnerable people[3]; and put 4 million more children in primary school[4]. Strong macroeconomic leadership has helped Ethiopia achieve annual growth of over 7 per cent for the last decade. GoE’s new Growth and Transformation Plan (GTP) targets a doubling of the economy and achievement of the MDGs by 2015, and a greater (if still limited) role for the private sector and accelerated industrialisation. The GTP provides a platform to align UK support with GoE’s ambitions, make it more transformational, and accelerate Ethiopia’s graduation from aid dependency. / Despite recent progress, Ethiopia remains one of the world’s poorest countries, with more than 30 million people living in extreme poverty. It is comparatively under-aided, receiving less than the African average per capita aid[5]. Strong progress towards some of the MDGs is from a very low base, and will be difficult to maintain as the needs of harder to reach populations are prioritised. Population momentum will see the current estimated population of 83 million people rise to around 120 million by 2030[6], which is likely to be accompanied by rapid urban growth. Ethnic nationalism and underdevelopment fuel instability and insurgency in parts of the Ethiopian periphery, threatening the delivery of Ethiopia’s development objectives. External shocks, including climate change and fluctuating commodity prices, threaten growth. Ethiopia was badly affected by the oil and food price shocks in 2008, and will find it difficult to avoid price rises as global prices rise again in 2011. / Ethiopia can absorb more aid and use it well. DFID is a leader within the development community, championing results, aid effectiveness and transparency. DFID works closely with UK Government partners in pursuit of shared objectives for a stable, secure and prosperous Ethiopia. / A2 The Ethiopian reproductive health context / Ethiopia’s health needs are vast and reflect the high poverty levels and difficult past. In the last decade real improvements have been seen in health services and outcomes, but this was from a very low baseline. / Whilst the burden of disease in Ethiopia has not been systematically measured in recent years at the national level, the results of a study of the burden of disease in a rural area of Ethiopia showed that communicable, maternal, perinatal and nutritional problems contributed to 72% of the total Disability Adjusted Life Years (DALYs) lost; non-communicable diseases contributed to 24% of the DALYs lost while the proportion of DALYs lost due to injuries was only 4%. The results were similar to previous estimates for countries in Sub-Saharan Africa[7]. Table 1 below gives data for some key indicators compared with sub-Saharan Africa averages. / Table 1 Key health and service delivery indicators in Ethiopia and the sub-Saharan Africa (SSA) average / Indicator Ethiopia[8] SSA average[9] / Total Fertility Rate 4.8 5.1 / Under five mortality rate (per 1000 live births) 88 145 / Maternal mortality ratio (per 100,000 live births) 590[10] 640 / Unmet need for family planning (%) 25% 9.9%[11] / Skilled birth attendance at delivery (%) 10% 46%xi / Children (12- 23 months of age) vaccinated against measles (%) 82.4% 71.8% / Rate of stunting in children under five years 44% 40%[12] / Health sector spend per capita per year (USD) $16[13] $68.8 / Physician per 100,000 population 2.6ii 18 / Significant achievements have been made in recent years in expanding access to services, and there is some evidence that the FMOH’s strategy of predominantly targeting efforts at the community level through the Health Extension Programme (HEP) may have moved Ethiopia onto an improved trend path at least for child mortality. In recent years the focus has been on construction, equipping and staffing at the Health Post and Health Centre levels. A total of more than 38,000 community level Health Extension Workers (HEW) have been trained and deployed to provide basic preventative and curative services from Health Posts in their villages. / Largely as a result of the roll out of this HEW programme, gains have been seen in access to community level preventative and basic curative services over the last 5 years. The recently release preliminary data from the Ethiopian Demographic and Health Survey (EDHS 2011) indicates extraordinary progress in reducing under five mortality (from 123 per 1000 live births in 2005 to 88 in 2010), increasing the contraceptive prevalence rate (from 15% in 2005 to 29% in 2010) and improvements across the board in service delivery and nutrition indicatorsi. / Despite this progress, the likelihood of Ethiopia reaching its health related MDGs, especially for maternal mortality, remains uncertain and will require an increased rate of progress. A projection of trends to 2015 show maternal mortality rates are falling steadily but not by enough to meet Ethiopia’s MDG targets (see Figure 1 below)[14]. / Figure 1 Trends in Maternal Mortality Rate / The best estimates suggest that over 22,000 women and girls die each year in Ethiopia (more than two women every hour) due to pregnancy related complications. The latest data (from 2005 – the 2010 EDHS data on maternal deaths is expected in the coming weeks), suggests that a woman in Ethiopia faces a 1 in 9 chance of dying of pregnancy related causes during her lifetime compared with a 1 in 8800 chance for a woman in the UK. Additionally, more than 500,000 Ethiopian women and girls suffer from disabilities caused by complications during pregnancy and childbirth each year. A recent facility survey documented the direct causes of maternal deaths in Ethiopia, the main causes being obstructed labour, ruptured uterus, pre-eclampsia and post partum haemorrhage[15]. All of these are treatable with timely comprehensive emergency obstetric care (including the right equipment, drugs, and trained health workers). / Behind the direct causes of maternal deaths are a number of factors that increase the likelihood of women dying in pregnancy and childbirth. In addition to limited access to safe delivery and emergency obstetric care (with serious disparities in access to health services between and within regions in Ethiopia), a number of other factors put women at risk of disability and death through complications of pregnancy or child birth including high fertility rates, limited access to safe abortion services, and factors related to the status of women and girls, including early marriage. / Ethiopia's fertility rate of 4.8 births per woman is one of the highest in the world. Unmet need for family planning is estimated to be 25%i. As detailed above, it is estimated that the current estimated population of 83 million people is set rise to around 120 million by 2030.[16]Early marriage is common in Ethiopia - about 1 in 5 Ethiopian women are married by their 15th birthday, and 17% of girls aged 15-19 have already become mothers or are pregnant with their first child. Girls who bear children before they are 15 years old are five times more likely to die from pregnancy related causes (compared to older mothers).[17] / It is estimated that in 2008 one in ten pregnancies in Ethiopia ended in abortion - an estimated 382,500 induced abortions. Less than 40% of these were performed safely. In the same year 52,600 women received care in a health facility for complications of unsafe abortion including bleeding and infections. Estimates of maternal deaths due to unsafe abortions vary from 6% to around 30% of maternal deaths[18]. / There are also broader reproductive health concerns including prevention, treatment and care of HIV and AIDs. Whilst HIV prevalence in Ethiopia is lower than many sub-Saharan African countries at, estimated at 2.4%, an estimated 1.1 million people in Ethiopia are living with HIV and AIDS. The epidemic is concentrated in urban areas (including peri-urban and small towns) (prevalence is estimated at 7.7 % in urban areas), with 9.3% prevalence among urban women and 6.2% prevalence among urban men – a female to male ratio of 1.5 to 1[19]. A national survey focused on identifying people most at risk of infection is planned for this year, however based on current evidence it is clear that sex workers and their clients are amongst the most vulnerable. / A3 The policy context / There are clear imperatives for scaling up support for reproductive health in Ethiopia at the global level and within DFID’s Business Plan (2011 – 2015)[20]: / Achieving the Millennium Development Goal targets - Given the size of the country and scale of the problem, achieving the health related MDG targets in Ethiopia will make a significant contribution to achieving the MDG targets in sub-Saharan Africa and globally. / DFID’s Business Plan (2011-2015) commits to supporting actions to help achieve the MDGs, and lead international action to improve maternal health and family planning. Specifically, DFID has committed to embed in every relevant bilateral programme plans to double our impact in terms of the number of maternal and newborn lives saved, enable more couples to access modern methods of family planning over the next five years, and scale up our efforts to restrict the spread of major diseases like HIV/AIDS. Subsequently, DFID has produced “Frameworks for Results” on Reproductive, Maternal, Neonatal and Child Health which lay out DFID’s commitment to scale up action and results in these areas. / DFID’s Strategic Vision for Women and Girls includes delaying first pregnancy and supporting safe childbirth as one of the four pillars for action to enable girls to fulfil their potential. / DFID Ethiopia’s Operational plan sets out its vision to (i) protect the most vulnerable: by building the resilience of the very poorest by reducing food insecurity and improving livelihoods and security in fragile and/or conflict-affected areas; (ii) consolidate recent gains and help achieve the MDGs: by continuing to support, extend and improve proven programmes to expand access to quality basic services; and (iii) make the impact of the UK’s support more transformational. The DFID E Operational plan includes scaled up results for UK support for reproductive health including ensuring an additional 2 million couples using family planning in 2015. / National policy context - the goals of the GoE’s Health Sector Development Programme (HSDP) are to improve maternal health, reduce child mortality and combat HIV/AIDS, malaria, TB and other diseases with the ultimate aim of improving the health status of the Ethiopian people and achieving the MDGs. The HSDP is currently in its fourth phase (2010 – 2015) and the GoE is focussed on making sure efforts in support of HSDP IV provide the accelerated progress needed to meet the MDG targets[21]. / The GoE has also developed and is implementing the National Reproductive Health Strategy (2006-2015) which identifies priority areas for intervention including: the social and cultural determinants of women’s health; fertility and family planning; HIV and AIDS; and reproductive health of young people. However, there is a significant funding gap to achieve the ambitious HSDP IV targets (2010 – 2015) for reproductive health which include: / Reducing the maternal mortality rate to 267 per 100,000 live births / Reducing the Total Fertility Rate (TFR) from 4.8 to 4.0 / Increasing access to safe abortion services from 4% to 75% / Reducing the incidence of HIV in adults from 0.28% to 0.14% / Increasing the Contraceptive Prevalence Rate (CPR) from 29% to 66% / Increasing the proportion of young people aged 15-24 who use condoms consistently while have sex with non-regular partners from 59% to 95% / Increasing the proportion of population aged 15-49 years with comprehensive knowledge of HIV/AIDS from 22.6% to 95% / A4 Rationale and evidence for intervening / Increasing access to family planning is a priority for Ethiopia and for the UK. Investing in reproductive health represents good value for money and has far reaching benefits for women, communities and the environment[22]. Family planning is considered a best buy in global health and in development more broadly. It is one of the most cost effective ways to reduce maternal mortality and also impacts on poverty more broadly e.g. smaller families share income among fewer people, and average income per capita increases; families with fewer children are better able to invest in the health of children they do have. Additionally, DFID believes that women have a right to accessible, high quality family planning choices, and that family planning and modern contraception offer choice and opportunity for women to make informed decisions and have more control over their lives. / Unmet need for family planning remains high in Ethiopia and over the next four years the number of women of reproductive age (WRA) will increase by approximately two million. Meeting the challenge of providing services to this growing number of women will not be easy. WRA are not a homogenous group and require different reproductive health products and services depending on their age, marital status, sexual behaviour and other factors. Current barriers to couples using contraceptives include: gaps in access to and quality of services including lack of consistent supply of products, awareness and understanding, and cultural and religious beliefs. Figure 2 below illustrates the high unmet need for family planning compared with other low and middle income countries. ‘Space’ and ‘limit’ refer to the conscious efforts of a couple to limit or space the number of children they have through the use of family planning. / Figure 2 Unmet need for family planning in selected low and middle income countries where DFID is working[2] / DFID is planning to scale up support for health in Ethiopia including ensuring accelerated progress in reproductive health and malaria. The bulk of DFID’s will be provided through the Government of Ethiopia to deliver HSDP IV and strengthen health systems and services. Our resources, relationships and instruments allow us to complement this broader support with focussed efforts to give a big push and ensure greater impact on reproductive health which is a priority for the UK Government and for the Government of Ethiopia. Quick wins can be made by helping couples avoid unintended pregnancies and improving the reproductive choices of women and girls. / Government of Ethiopia strategies for increasing reproductive choices include scaling up community and facility based family planning services, social marketing of reproductive health commodities through non-state outlets, increased community involvement in health services and strengthening adolescent and youth friendly services. Their strategy for HIV prevention focuses predominantly on reaching those most at risk of infection. / DFID has been supporting the supply of RH commodities over the last six years in Ethiopia through a social marketing programme. In recent years this targeted support has complemented our support to broader health systems and services and responds to a significant shortage of resources in the health sector and for reproductive health specifically. / The outputs of DFID’s investment of £8 million over the last three years has included more than 118 million male condoms, more than 5 million cycles of oral contraceptives, more than 3 million injectable contraceptives. According to the Marie Stopes Impact Calendar (recognised by DFID) these are estimated to have averted more than a million unintended pregnancies, more than 4000 maternal deaths and approximately 170,000 unsafe abortions. No other donors are currently planning to scale up their support for reproductive health in Ethiopia. / A5 Consequences of not intervening / Without this proposed funding for reproductive health commodities in Ethiopia, to 2015 it is estimated that there will be: / More than 8000 more maternal deaths / 2.5 million more unintended pregnancies / 240,000 more abortions / Between 35,000 and 100,000 more transmissions of HIV infection
B Impact and Outcome / The impact of supporting reproductive health commodities in Ethiopia will be accelerated progress towards its health related MDG targets, particularly maternal mortality and reducing HIV and AIDS. This targeted support will complement DFID’s scaled up support for Ethiopia’s Health Sector Development Programme. / The outcome is expected to be reduced unmet need for family planning and incidence of HIV infection, particularly in women and men most at risk of infection.
[1] DFID Ethiopia (2011) Operational Plan (2011 – 2015), DFID Ethiopia, Addis Ababa.
[2] Federal Democratic Republic of Ethiopia (2010) Health Sector Development Programme III, Annual Performance Report: EFY 2002 (2009/10). Federal Ministry of Health, Addis Ababa.
[3] Devereux et al (2006) Ethiopia’s Productive Safety Nets Programme. Trends in PSNP Households with Targeted Transfers. Institute of Development Studies, Sussex.
[4] Federal Democratic Republic of Ethiopia (2010) Education Statistics Annual Abstract: 2009 - 2010. Ministry of Education, Addis Ababa
[5] OECD.STAT: data extracted on 20 Jul 2011 07:17 UTC (GMT)
[6] Population Division of the Department of Economic and Social Affairs of the United Nations Secretariat, World Population Prospects: The 2010 Revision, http://esa.un.org/undp/wpp/index.htm, data extracted on Wednesday July 20, 2011; 4:33:42 AM
[7] Abdulahi et al (2001) Burden of Disease Analysis in Rural Ethiopia. Ethiopian Medical Journal, Oct;39(4):271-81
[8] Unless otherwise indicated, these results are from Central Statistical Agency (2011) Ethiopia Demographic and Health Survey 2011. Preliminary Report, Addis Ababa.
[9] World Bank data accessed at http://www.tradingeconomics.com/sub-saharan-africa/health-expenditure-per-capita-us-dollar-wb-data.html, 6 July 2011.
[10] World Health Organisation (2010) Trends in Maternal Mortality: 1990 to 2008 Estimates developed by WHO, UNICEF, UNFPA and The World Bank, WHO, Geneva
[11] Data from United Nations Statistics Division accessed at http://unstats.un.org/unsd/default.htm on 10 July 2011
[12] UNICEF (2009) Tracking Progress on Child and Maternal Nutrition. UNICEF, New York.
[13] Federal Democratic Republic of Ethiopia Ministry of Health (2010) Ethiopia’s Fourth National Health Accounts (2007/2008), Addis Ababa.
[14] World Bank (2008) Project Appraisal Document, Protection of Basic Services Programme, Phase 2, World Bank, Washington DC.
[15] Federal Ministry of Health (2008) National Baseline Assessment for Emergency Obstetric and Newborn Care, Addis Abba, Ethiopia.
[16] Population Division of the Department of Economic and Social Affairs of the United Nations Secretariat, World Population Prospects: The 2010 Revision, http://esa.un.org/undp/wpp/index.htm, data extracted on Wednesday July 20, 2011; 4:33:42 AM
[17] Murphy and Carr (2007) Powerful Partners: Adolescent Girls’ Education and Delayed Childbearing, PRB brief, September
[18] Guttmacher Institute (2010) Facts on Unintended Pregnancy and Abortion in Ethiopia. In Brief. Guttmacher Institute, New York.
[19] Federal Democratic Republic of Ethiopia Ministry of Health and Federal HIV/AIDS Prevention and Control Office (HAPCO), (2010) Single Point HIV prevalence Estimate, Addis Ababa
[20] Department for International Development (2011) Business Plan, 2011 – 2015. http://www.dfid.gov.uk/About-DFID/Finance-and-performance/DFID-Bu.siness-plan-2011---2015/
[21] Federal Democratic Republic of Ethiopia Ministry of Health (2010) Health Sector Development Programme IV 2010/11 – 2014/15, Addis Ababa. More information can be found on Marginal Budgeting for Bottlenecks at http://www.who.int/pmnch/topics/economics/costing_tools/en/index12.html
[22] DFID (2010) Choices for Women: Planned pregnancies, safe births and Health Newborns. The UK’s Framework for Results for Improving Reproductive, Maternal and Newborn Health in the Developing World, London.
[2] Note that this has not been updated with the preliminary EDHS 2011 figures

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / A1 Generating feasible options / Based on the analysis above, options for achieving the outcome could focus on one or more of the following: / Increasing equitable access to and quality of reproductive health services / Increasing the supply of reproductive health commodities / Increasing the demand for reproductive health commodities / Reducing gender inequalities and empowering women and girls / Increasing access to and quality of health services is focus of DFID Ethiopia’s proposed broad support for Ethiopia’s HSDP. Focusing on empowerment of women and girls including their reproductive rights is the focus of work under design. Therefore feasible options for achieving the impact and outcome have been generated focusing on increasing the supply and demand for RH commodities based on the rationale and theory of change below. / A significant barrier to reducing unmet need for family planning is ensuring supplies of reproductive health commodities are consistent and adequate to meet a growing demand. USAID have coined the phrase “No product, no programme” i.e. security of contraceptive supplies requires sound logistics management which entails delivering the right product in the right quantity in the right condition to the right place at the right time at the right cost. Whilst supplies are not the only barrier, the public sector suffers from regular stock outs and shortages of supplies, and whilst procurement and distribution systems are being strengthened, they are imperfect. The health sector is significantly under resourced, including funding available for procurement of commodities and equipment. / Reproductive health commodities, including condoms for HIV prevention, are accessed through private sector outlets as well as public facilities so efforts are needed to increase the supply and demand for these commodities both inside as well as outside of public health services, and to make them more readily available to people. Condoms are currently largely accessed through the non-state sector, particularly by those most vulnerable to HIV and other sexually transmitted infections. One study showed that two-thirds of commercial sex workers access condoms through shops or kiosks in Ethiopia. [23] / As highlighted above, HSDP IV strategies to increase access to reproductive health services and commodities include social marketing, scaling up community and facility based family planning services, increased community involvement in health services and strengthening adolescent and youth friendly services. Table 2 shows the current interventions supporting supply of and demand for RH commodities. / Table 2 Main interventions to support reproductive health commodity supplies / Channel of funding Intervention Detail / Federal Government– Ministry of Health Health MDG PF / UN agency procurement of commodities Un-earmarked federal pool fund that supports implementation of HSDP including procurement of commodities and equipment. / UNFPA procures commodities from central funding / Regional Government – Bureaux of Health Budget allocated for procurement of contraceptives Particularly for gap filling and preventing stockouts / Through NGOs/contractors Procurement of commodities by the US Government / Social marketing of RH commodities Additionally, technical support provided by USAID DELIVER project to strengthen logistics and supply systems / Currently undertaken by international NGO DKT in partnership with the FMOH / Figure 3 Theory of Change (Assumptions are shown in the yellow ovals) / Evidence to support assumptions / Effective marketing and BCC leads to increased demand / The basic components of behaviour change communications (BCC) in the area of reproductive health are to increase knowledge about a product and to encourage behaviours associated with initiating trial and continued use. Many family planning campaigns are based on such approaches. Most awareness raising interventions draw from a variety of social change theories. Recognising that individual and family decisions are usually influenced by social norms, and that interventions to generate family planning demand may often need to influence social and gender norms, the term ‘Social and Behavioural Change Communication’ (S/BCC) is now frequently used. S/BCC interventions, and especially mass media using entertainment and education strategies, are important for stimulating discussion about and use of contraception among couples where unmet need is high. / A recent meta-analysis looking at increased knowledge, condom use and reduction of sexual partners as outcomes shows little evidence of mass media behaviour change communication in reducing number of partners, but stronger evidence for impact on increased knowledge and condom use. The review also shows increasingly strong effects over time, with the largest effects from mass-media combined with inter-personal communication, and greater effect on sex workers, especially in low income countries[24] . / A systematic review of the effectiveness of 24 mass communication programmes to change HIV and AIDS-related behaviours found that the most frequently reported outcome (17 studies) was condom use[25], and the recent South African National HIV Communication Survey also found that exposure to HIV communication programmes was related to increased condom use. Overall the survey was found to demonstrate “a causal connection between the communication programmes and people’s behaviour, and also that the more programmes people are exposed to, the more they are positively influenced” [26]. / Areas that have been identified for the improvement of BCC programmes include: better funded and longer-term campaigns, and improved programming and evaluation tools. Additionally, BCC programmes should not be stand-alone interventions but seen as an essential component of prevention packages, and ensure the right communication targeted to the right audiences. / Affordable commodities leads to increased use / Evidence from studies on the effects of contraceptive prices on use is mixed. Women’s ability and willingness to pay fees for family planning depends on many factors, including economic conditions, how high fees are set, whether clients see an associated improvement in the quality of services, and even the type of contraceptive for which the fee is charged. A number of studies argue that charging fees is an economic barrier to services for poor people, especially for women who have less control over household resources than men[27]. / Definitive evidence on the price elasticity of contraceptive demand is scarce because of the impracticability of experimental research, but the consistent impression from published studies is that demand is surprisingly inelastic[28]. A doubling in contraceptive prices results in declines in overall use of 0-15%[29]. An older review of 13 studies in Asia also found that prices were generally inelastic where increases were modest (increases of up to $0.20)[30]. It also found that there was no difference in demand between low or moderately priced contraceptives and free contraceptives; suggesting that clients value commodities where they pay (even a small fee), which explains why fee increases of US $0.10-0.20 cents may not lead to lower use. However, income was a factor in determining the elasticity of demand, implying that poor people are more likely to be affected by user fees than those with middle-level incomes or the wealthy. / Some economists have suggested that prices of about 1% of income appear not to affect demand[31]. This suggests that product affordability is highly variable across countries, and therefore pricing strategy and the associated choice of model should be sensitive to income levels, particularly among target groups. Reviews have concluded that "little difference in demand exists between free and moderately priced services"[32] in respect to ‘affordable’ pricing. However, reductions in price always seemed to stimulate demand, and prices high enough for full cost recovery would probably "pose a deterrent to low- and moderate-income couples." / Price is of course not the only barrier to contraceptive use; others include lack of knowledge, social opposition and concerns about health effects. In a review of all 56 countries with the relevant Demographic and Health Survey (DHS) data, fewer than 3% of married women not practicing contraception report that contraceptive prices are the reason for non-use, and that in the 19 countries with relevant DHS data, fewer than 3% of married women who have discontinued contraceptive use cite price as the reason[33]. / Effective and reliable distribution systems are need to increase supply / Higher contraceptive use is associated with higher contraceptive availability[34][35]. An analysis of family planning logistics systems from 12 countries indicates that countries with relatively high performing systems are associated with higher contraceptive method mix availability (see figure), and lower duration of stockouts for condoms, pills, and injectables in the previous six months.[36] / Figure 4 Correlation between availability of contraceptive method mix and logistics system performance / Failure to get the necessary drugs and commodities to customers at the point of care undermines the success of any public health programme. Often this is the result of weak drug management systems, poorly resourced supply chains, bad stock management practices, and inadequate planning. / A study on the human impact of shortage/stock-out/irregular supply of three family planning commodities in Bangladesh over one year calculated that these were responsible for 47,000 additional childbirths due to unexpected pregnancy. [37] Of the users who experienced irregular supply, about 63% suffered a range of consequences – physical, psychological, social, and economic. The study points to lengthy procurement processes, lack of proper forecasting mechanisms, and staff shortages. / Ethiopia faces similar challenges. The national survey on availability of reproductive health commodities in service delivery points [38] reports that ‘Stock out is a chronic concern that affects continued use of modern contraceptive methods and quality of services’. Logistics management (shortage of supply, delay in delivery, delay in order placement and inadequate budget) is one of the most frequently cited reasons for stock out. Five of the eight modern contraceptive methods were reported as out of stock for an average of about five months. The female condom was the least offered family planning method; 87.2% facilities not stocking it quoted scarcity of supply, and 8.3% low demand. Five (including three essential) life-saving medicines were about three times more available in urban service delivery points (94%) as compared to rural service delivery points (34%). / The effects of a strong supply chain is also shown by assessments of supply chain system strengthening projects in Ghana and Mali, which show sharp increases in product availability at service delivery points and warehouses after logistics interventions.[39] In Mali, availability of Protector condoms increased by more than 40% in the 2001-2005 period; in Ghana, availability of a range of contraceptives on the day of visits had been sustained at nearly 80% over several years. Much of the evidence however is anecdotal. A strong supply chain is reported as one of the programmatic factors contributing the increase in contraceptive uptake in Rwanda (from 4% in 2000 to 27% in 2008).[40] Two years after implementing a new management system for contraceptives, the Jordanian Ministry of Health found that stock outs in health centres had been lowered by 75%.[41] / Supplying RH Commodities through outlets that people will use leads to increased use / Making products conveniently available is a fundamental component of increasing contraceptive use. It is generally understood that, while convenience is not the only factor driving contraceptive use, without conveniently (and reliably) available products the overall effort to increase contraceptive use is constrained[42]. However the evidence on geographic access is mixed. / Studies from Nepal showed that women with less than 1 hour access to a family planning service outlet were 2 to 3 times more likely to use contraceptives than women whose access to these facilities was greater than 1 hour[43]. A retail outlet survey in urban Zambia showed that widespread availability of socially marketed condom in kiosks and grocery shops has resulted in “highly equitable access to condoms”: 66% of low income respondents and 56% of wealthier respondents reported being within 10 minutes walk of a condom source[44]. A survey of low income contraceptive customers in Nigeria found that they used pharmacies because they provide fast service, are close by, prices are affordable and they rarely experience stock outs[45]. / Other studies find that distance and lack of physical access is not a main factor deterring use[46],[47][48] and note that while women rarely cite lack of access as a primary reason for not using contraceptives, rigorously designed comparison of women with adequate and inadequate access might reveal substantial differences in the prevalence of unmet need. They also argue that well-designed quasi-experimental studies in several settings (e.g. Bangladesh and northern Ghana) demonstrate that improved access can have large effects on contraceptive prevalence. / Condoms that are of high quality and used consistently and correctly reduce HIV incidence / The male latex condom is the single, most efficient, available technology to reduce the sexual transmission of HIV and other sexually transmitted infections[49]. / The effectiveness of latex condoms, when used consistently and correctly, has been scientifically established in ‘real-life’ studies of sexually active couples as well as in laboratory studies[50]. The evidence is clearest in studies of discordant couples. In a study of discordant couples in Europe, among 123 couples who reported consistently using condoms, none of the uninfected partners became infected. In contrast, among the 122 couples who used condoms inconsistently, 12 of the uninfected partners became infected[51]. A review of 14 studies involving discordant couples concluded that consistent use of condoms led to an 80% reduction in HIV incidence[52]. / Consistency in use is key. Findings from Rakai, Uganda, showed that among 350 women who reported consistent male condom use, none became HIV-positive, but annual HIV incidence was 4.6% among women who reported inconsistent condom use[53]. Many studies have shown that inconsistent condom users are at higher risk of HIV transmission than those who never use condoms, although this may be because their behaviour is riskier in other ways. / Contraceptives that are of high quality and used consistently and correctly reduce unwanted pregnancies / Among American couples who use the male condom ‘perfectly’ (both consistently and correctly), the percentage of women who experience an accidental pregnancy during the first year, if they do not stop use for any other reason, is 2%. The percentage rises to 15% with non perfect use. For the combined pill and minipill, the percentage of pregnancy at perfect use is 0.8%, compared with 8% with non perfect use[54]. / The effectiveness of the contraceptive method in preventing unplanned pregnancy is dependent for some methods not only on the protection afforded by the method itself, but also on how consistently and correctly it is used[55]. Both consistent and correct use can vary greatly with such characteristics as age, income, users’ desire to prevent or delay pregnancy, and culture. / Reducing unwanted pregnancies reduces maternal mortality / Reducing the number of births reduces the number of times a woman is exposed to the risk of mortality. Although it is difficult to attribute change in the maternal mortality ratio to a particular cause, evidence exists to support the link between meeting the unmet need for family planning and reducing maternal mortality. The evidence regarding the effect of shorter birth intervals on maternal health is more limited although it is likely that there is an effect of maternal nutritional depletion, for example increased anaemia, which increases the fatality rate from postpartum haemorrhage[56]. Contraceptive use can also impact on women’s risk of maternal mortality at either end of the reproductive age span. Adolescence, older reproductive age, and parity greater than 4 births elevate the risk of maternal mortality. Providing contraceptive services to these groups can reduce the maternal mortality ratio by up to 58%[57]. / According to recent analysis of DHS data from 68 countries, it is estimated that the drop in observed total fertility rates from 1990 to 2005, due primarily to increased contraceptive use, resulted in 1.2 million fewer maternal deaths – 15% fewer than would have occurred with no fertility decline[58]. Overall, it has been estimated that one third of the total maternal deaths can be attributed to non-use or lack of availability of contraception – or 150,000 deaths per year[59]. Additionally it ahs been estimated that in 2000, about 90% of global abortion-related and 20% of obstetric-related mortality and morbidity could have been averted by use of effective contraception by women wishing to postpone or cease further childbearing[60]. / Just meeting unmet need for contraception could reduce current unintended pregnancies by 71%, the equivalent of a reduction from 75 million pregnancies in 2008 to 22 million (preventing 53 million unintended pregnancies per year)lvi. If family planning is focused on women in the highest risk categories for pregnancy and birth (e.g. older or younger women, women who have had a birth or abortion in the past two years, women of short stature, or high parity women) then both the maternal mortality ratio and the lifetime risk of death can be reduced, although to a lesser extent[61]. The figure below shows the strong association between contraceptive prevalence rates and maternal mortality ratio. / Figure 4 Relationship between contraceptive prevalence rate and maternal mortality ratio / A2 Feasible Options identified / Over the last three years the bulk of DFID support to the health sector has been provided to the Ethiopian Federal Ministry of Health, and this has been complemented by support through an international NGO for social marketing of reproductive health commodities. Given the plans to scale up DFID support for results in the health sector in Ethiopia it is now appropriate to consider all feasible options for increasing the supply of and demand for reproductive health commodities in the next four years. Three options are considered here: / Support for reproductive health commodities through the public sector / Support for social marketing of reproductive health commodities / Do nothing/leave it to the private sector / Option 1: Support for RH commodities through the public sector / DFID is planning to scale up its support for public sector delivery of health services through two main instruments – the Federal Ministry of Health’s MDG Performance fund and the Protection of Basic Services Programme, which provides support for decentralised service delivery including health. / PBS is a multi-sector Poverty Reduction Budget Support (PRBS) programme consisting of five components: The main component of the programme provides direct financing to regional and Woreda (district) governments to provide basic services (education, health, agriculture, water and sanitation, and rural roads). The funds are channelled through the block grant that transfers funds from federal to regional governments. This instrument does not allow earmarking of funds for a particular sector or subsector. / The MDG PF was established by the Federal Ministry of Health (FMOH) in 2008 to accelerate Ethiopia’s progress towards the health related MDG targets. It is a mechanism for the Government of Ethiopia (GoE) and development partners to pool unearmarked funds in support of key elements of Ethiopia’s HSDP. / The FMOH has been clear that they want any ‘earmarked’ funding, such as that for reproductive health, to be channelled through a third party agency and not through GoE channels. Therefore, support through the public sector would either need to be provided as unearmarked support for HSDP with a proportion of the funding used for reproductive health, or through a third part agency such as a UN agency that could procure on the FMOH’s behalf. Commodities would then be distributed through the health system to health facilities including health centres and health posts. / Option 2: Social marketing of RH commodities / Social marketing is a key strategy under HSDP to increase use of family planning and access to condoms. This option would channel funding through a social marketing organisation to procure and distribute commodities coupled with marketing and communication activities to increase their uptake. / DFID would contract a social marketing organisation to procure and distribute reproductive health commodities through predominantly private sector channels. DFID has been supporting social marketing of reproductive health commodities for the last six years in Ethiopia, and for the initial year support would continue to be channelled through the international NGO DKT. Following the first year a ‘mini competition’ would be undertaken under DFID’s central Reproductive Health Framework Agreement to award a contract for the outer three years. / DKT works as both a social marketing organisation as well as a back up supplier for the public sector and NGOs. Social marketing efforts include procurement and distribution of a wide range of commodities including condoms, hormonal contraceptives, drugs and kits for abortion, and misoprostol to prevent post partum haemorrhage. The distribution of products is accompanied by a wide-ranging combination of advertising, promotional and BCC activities including with groups at high risk of HIV infection. / Option 3: Do nothing/leave it to the private sector / This option would not earmark and channel funding in support of reproductive health commodities, rather the proposition is that without social marketing the private sector can be allowed to develop and supply commodities for profit. / This option would involve no intervention by DFID, rather we would undertake to monitor the availability of RH commodities through the private and public sectors.
B. Assessing the strength of the evidence base for each feasible option / Option 1 – the evidence / As indicated above, in large part as a result of the roll out of the HEP[62], gains have been seen in access to community level preventative and basic curative services over the last 5 years. This package of cost effective of preventative and basic curative services provided by the Health Extension Workers includes family planning counselling and services. The routine FMOH data and recent EDHS preliminary data indicate the following increases in utilisation and outputs between 2005 and 2010: / Under five mortality decreased from 123 to 88 per 1000 live births / Contraceptive prevalence rate increased from 15% to 29% / An increase from 6191 Health posts constructed in 2005/06 to more than 14,000 in 2009/10, and an increase in health centres from 710 to 2142 in the same period / A full evaluation of the HEP is currently underway including which will systematically evaluate the impact of the HEP to date. The data for this evaluation has been collected and the report is due in the coming months. The findings of an earlier review of the HEP completed in 2008 by independent consultants was reported in The Lancet[63] . The evaluation reported that the HEP had achieved great successes, was helping to prevent communicable diseases and enabling effective community participation in the planning and implementation of health care. It concluded that “From several studies carried out so far, it appears the community engagement of the HEWs in a number of regions is highly appreciated and seems effective. In those regions, HEWs work together with community health promoters, health workers, religious leaders, and community leaders”. / There is widespread international interest in the impact of the HEP as this model is seen as having great potential for other low income countries. / The more detailed final DHS data from 2005 suggests that the majority of contraceptive users get their supplies from public sector facilities. Family planning services are provided free through the public sector in Ethiopia so no financial barriers are presented to the poorest women and men accessing them. Additionally, the work of the health extension workers, including family planning counselling, is community based and aims to reach all members of the communities they serve. / In relation to HIV prevention the contrary is the case with two thirds of sex workers obtaining their condoms through kiosks (small shops). Additionally, the focus of HIV prevention in Ethiopia is on urban areas including small towns. The Health Extension Programme is currently strongest in the rural areas where HIV prevalence is lower. / Efforts are underway to strengthen distribution and supply systems for all medicines and commodities through the public sector, and health facilities continue to suffer stock outs of some medicines including contraceptives. As highlighted in the theory of change an interrupted supply of contraceptives impacts both on the effectiveness of the method as well as the enthusiasm amongst users to continue seeking services. / Option 2 - the evidence / Social marketing refers to a variety of strategies using traditional commercial-marketing techniques to promote socially beneficial behaviours, products and services[64]. In family planning, social marketing has focused on making supplies of methods of contraception more widely available in commercial retail outlets and on promoting these contraceptives to consumers through the mass media[65]. There are now several large international NGOs specialising in social marketing. In theory, social marketing programs should be readily subject to evaluation because it should be relatively easy to keep track of sales figures for products, advertising spots and market share. / Harvey notes that contraceptive social marketing (CSM) contributed over 4 million couple years of protection (CYPs) (A Couple Year of Protection (CYP) for a particular family planning method is calculated by multiplying the quantity of the method distributed to clients by a conversion factor. This yields an estimate of the duration of contraceptive protection per unit of that method) in Bangladesh and 10 million CYPs in India in 2005 alone[66]. In Pakistan, social marketing has been averaging about 2.5 million CYPs per year over the last three to four years[67]. However, again these figures need to be seen in the context of the national CYP total for the year to make a robust case of the potential contribution of CSM. / There have been at least 3 large scale reviews of the literature in this area. A DFID funded systematic review of 29 social marketing programmes in 11 sub-Saharan African countries indicated that such techniques have had a positive impact on clients’ knowledge and access to contraceptive methods[68]. The review also indicated increased use of certain types of contraception, with the largest increases for condoms. However, the extent of knowledge and behavioural change varied between country programmes. None of the social marketing programmes was evaluated in terms of their impact on equity. / Another systematic review of published evidence on uptake of condoms in sub-Saharan Africa and Asia reported that social marketing that target sex workers achieved larger increase in condom use compared with those that target casual relationships and/or young people[69]. A meta-analysis of six studies looked at the relationship between implementation of condom social marketing campaigns and changes in (self-reported) condom use. Overall, the review found that those exposed to condom social marketing were approximately twice as likely to use a condom as those not exposed. In all interventions, mass media was used extensively, and often this was supplemented with community-based outreach efforts such as peer education and promotional events[70]. / Additionally, in relation to HIV and STI control, it is argued that social marketing’s success in making condoms readily available in settings where the likelihood of high-risk sexual activity is greatest (such as bars, guest houses and brothels) “is now evident”[71]. / The most recent systematic review (albeit again with wide inclusion criteria) looked at the results of six social marketing evaluations[72]. The authors concluded that there was strong evidence of a positive impact from social marketing to increase access to FP products and messages but very little information on access by poor people. Although they cited evidence that social marketing has the potential to be cost-effective, utilisation was very sensitive to price, suggesting that the impact on poor people could be significant. / As highlighted above, in Ethiopia, there has been a significant increase in the Contraceptive Prevalence Rate in recent years and although this cannot be attributed to social marketing, the Federal Ministry of Health estimated that between 2002 and 2009 DKT distributed nationally: / 75% of the condoms; / 45% of the oral contraceptives; / 37% of the injectable contraceptives; / Approximately 50% of the misoprostol for treating/preventing post partum haemorrhage; and / 100% of the medical abortion drugs (on a pre-registration basis)[73]. / DKT estimate that over the last 20 years, their social marketing efforts in Ethiopia have averted: / More than 5.7 million unintended pregnancies / More than 4.2 million unintended births / More than 20,109 maternal deaths / More than 560,000 abortions / Between 102,000 and 307,000 HIV transmissions / Social Marketing is not intrinsically pro-poor, since it depends on consumer ability and willingness to pay, and on access to retail and commercial outlets and services, which are not equally distributed across the population. DKT has an extensive nationwide distribution system that reaches almost all private pharmacies, drug stores and rural drugs vendors in all regions of the country. These products that are sold through the private sector are used by all but the lowest wealth quintile of the country. Additionally, DKT products reach the lowest wealth quintile through DKT’s partnerships with the public sector and NGOs that provide free products and services (after these organisations buy products from DKT). DKT targets condom distribution to sex workers and their clients who are amongst the most vulnerable to transmission of HIV infection, they also work with youth groups and youth marketers to increase utilisation of condoms by young people. / In a ‘total market’ approach (the one used by DKT Ethiopia) all interested parties – public, commercial and NGOs - operate in an integrated way. The approach was recommended as the best way of taking forward the evolution of SM programmes in a 2003 DFID review of social marketing[74] . / Option 3 - the evidence / There is a substantial body of literature aimed at demonstrating the benefits of engaging with the private sector, both for the delivery of health services in general, and for reproductive health (RH) services and commodities specifically. However evidence on the counterfactual - what the supply and demand for RH services would be under a pure private market - is lacking[75], [76]. / In Ethiopia, the latest estimates from 2005 indicated that around 20% of contraceptive users obtain contraceptive methods from the private sector (including both the commercial sector and NGOs), and 3% from other private sources, which include drug vendors and shops (DHS 2005). As mentioned above, two-thirds of commercial sex workers obtain condoms from private kiosks. The DHS data doesn’t distinguish between socially marketed and ‘pure private sector products’, however data on condom availability indicates that the proportion of non-DKT condom brands at kiosks is negligible. / A recent study indicated that private sector pharmaceutical distribution systems in Ethiopia are currently inadequate to provide wide reach even in urban areas. Most systems work on a ‘collection’ rather than distribution basis, which favours larger retail outlets. / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Strong / 2 Strong / 3 Limited / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Implications on the environment/climate. The most significant impact of the proposed health activities on the environment are through the safe and appropriate management of health care waste. Evidence suggests that attention to health care waste management is rarely adequate. Given the volumes of commodities in this programme, there is a potential environmental impact related to the management of waste. As part of the support to the Health Sector being provided through a World Bank MDTF, an early assessment of implementation of environmental safeguard measures are being carried out. Additionally, PBS, an environmental sustainability assessment is planned to examine how development partner support for basic services impacts on the environment and the capacity of local government to implement appropriate mitigation measures. / Environmental and climate factors have the potential to diminish the effectiveness of Ethiopia’s health programme. Changes in vector and water-borne disease prevalence, in line with changing rainfall patterns could impact on health sector planning. These strategic considerations are being picked up by the Climate Resilient Green Economy strategic process – which is being implemented across all sectors including the health sector. Through its Strategic Climate Institutions Programme (SCIP), DFID Ethiopia will be working with the health sector to ensure that Ethiopia is prepared for both the positive and negative implications of climate change. Because of the work ongoing through SCIP, we will not be addressing these challenges directly in this programme. / Given the ongoing activities relating to climate change, environment and the health sector, we classify all the proposed options as having low potential risk/opportunity for climate/environment. / Option Evidence rating Climate change and environment category (A, B, C, D) / 1 Medium C (low potential risk/opportunity) / 2 Medium C (low potential risk/opportunity) / 3 Medium C (low potential risk/opportunity)
C. What are the costs and benefits of each feasible option? / Health Benefits / Both Options one and two will increase the supply of reproductive health commodities in Ethiopia, contributing to an increase in the supply of family planning services. The health benefits associated with a reduction in unwanted pregnancies and increased spacing of pregnancies will be felt both by women of reproductive age and also other family members. More women will survive health problems related to pregnancy or childbirth and newborns will have improved chances of surviving asphyxia, low birth weight and infection. Specific health related benefits include: / Healthy birth spacing and smaller families which improve women’s and infant’s health (for example babies born less then 2 years after the next oldest sibling are more than twice as likely to die in the first year as are those born after an interval of 3 years) [77] / Prevention of high-risk pregnancies (ie those among teenagers, woman older than 35 and women with many children) / Longer time to breast-feed, which improves infant health and survival / Fewer women suffering from anaemia / Reduced suffering and stigma due to fistula, infertility and other reproductive health problems / Reduced transmission of HIV/AIDS from family planning use among women with HIV / Option two will produce benefits through increased use of condoms. The benefit will not be felt through Option one as a very small proportion of condoms is accessed through the public sector. As well as contributing to reducing unintended pregnancies increased use of condoms will reduce transmission of HIV and other sexually transmitted infections. / Prevention of HIV has an additional effect on infant and child survival in addition to the prevention of orphan-hood. Children orphaned by HIV have even higher mortality than those orphaned by other reasons. Therefore, use of condoms has beneficial effects on infant and child health as outlined previously, as well as additional benefits through preventing adult HIV morbidity and mortality. Furthermore, prevention of maternal HIV will lead to less need for maternal to child transmission prevention and will reduce the overall number of infants born with HIV / Option two will work on building demand for family planning as well as bolstering the supply of commodities. This will happen through a range of marketing and BCC activities and the benefits will include greater awareness of the benefits of family planning and the choices available. / Economic and social benefits / Contraceptive prevalence and fertility are closely related. Although there are many other determinants of fertility, contraceptive use, especially modern contraceptives, is a key driver in the contemporary fertility transition. Therefore, increasing contraceptive prevalence (which both options one and two will do) has a direct impact on fertility levels. Reductions in family size are known to produce significant economic benefits for families and societies and be a major driver of development in low and middle income countries. This process is known as the demographic transition and consists of a virtuous circle of rising income per capita, lower desired family size, greater use of contraception, lower numbers of children, and so rising income per capita[78]. / Reduced fertility levels resulting from this intervention will generate other economic and other social benefits. In a recent paper the Guttmacher Institute and UNFPA outline some of the indirect benefits relating to increased uptake of family planning services but acknowledge that some of these benefits are difficult to quantifylvi. Specifically they identify the following benefits: / Improved education for women / Improved well-being of families because of mothers survival / Better nutrition and education for children, especially girls / More of parents’ time and income allocated to each child / Reduced public-sector spending on health services for long-term consequences of mothers’ and newborns’ ill health / Reduced public-sector spending on education, childhood vaccinations, malaria prevention, water and sanitation (it is estimated that for every dollar spend on family planning, Kenya would recoup US $3.75 in these sectors alone) / Improved productivity and higher income, greater savings and investment / Potential for faster economic growth when the working population has fewer children to support / Reduced population pressure on scarce natural resources (eg water, forests and arable land) / Less discrimination against girls / As highlighted above, Option 1 is likely to be more ‘pro-poor’ than Option 2 as all family planning services are provided free to users. That said around a third of DKT products are currently supplied to users free of charge through their supplies to the public sector and NGOs. / Benefits to women and girls / In addition to the health benefits of family planning for women and their children, and the macro-level economic benefits of the demographic dividend, studies have found that women who voluntarily plan their families reap personal, psychological and economic rewardslvi. Enabling women to have choices in their lives, especially the right to determine the number, timing and spacing of their children free of discrimination, coercion or violence, is key to women’s empowerment and gender equality. / When women enjoy equal rights and opportunities, including the right to determine their fertility, they are better able to make decisions in the household, participate in society and in non-domestic activities. The main and oft-cited source of such evidence is the Women’s Studies Project (WSP), a five-year, multi-country qualitative research set up to examine the impact of family planning on women's lives, moving beyond the impact on women;s physical health[79]. The range of social and economic benefits associated with contraceptive use include several aspects of women’s empowerment and quality of life, including: / greater freedom to participate in the work force. / freedom from fear of unplanned pregnancy and could improve sexual life, partner relations and family wellbeing. / Increased women's self-esteem and self-image and less worry about unplanned pregnancies / more time to participate in civil society such as parent teacher associations and religious organisations, and greater opportunities to socialise / More satisfied with their lives and more likely to share in household decision-making / The study also identified some costs to women contraceptive use including: / Side effects of contraceptives – real or perceived / When partners are opposed, practicing family planning can increase women’s vulnerability / When women have smaller families, they may lose the security of traditional roles and face new and sometimes difficult challenges, including the burden of multiple responsibilities at home work / It is important to note that existing studies have not determined the direction of causality of these relationships. It could be argued that women with these characteristics are more likely to use contraception. It is striking that there is little more recent evidence on the benefits of family planning on gender equality and women’s rights and empowerment. / In Ethiopia the only key population at higher risk for which there is biological evidence of infection is female sex workers. Female sex workers have been found to have high HIV prevalence in all serostatus studies performed. Option two would support work through a local nongovernmental organisation directly with sex workers to promote an increased level of condom use and safer sex amongst sex workers and their clients. The other benefits of this work will be increased sex worker involvement and control over their working and social conditions, and a reduction in the number of sexually transmitted infections occurring amongst sex workers. / Institutional benefits / The argument for Option 3 would be that social marketing through Option 2 could potentially ‘crowd out’ the private sector with subsidised products. The evidence on this is however inconclusive, although specific cases have occurred, and undoubtedly the potentially exists for subsidised products to undercut established suppliers. / There is also the potential for ‘crowding in’. Commercial brands of contraceptives generally do well in social marketing countries. The massive advertising campaigns conducted by social marketers almost always increase the total demand for family planning, making room for increased sales of all contraceptive products, especially well-packaged, branded ones. / Option one has the potential to increase the focus on supply systems within the public sector, and place the responsibility with the public sector for ensuring consistent supplies of reproductive health commodities. / Option two promotes relationships and partnerships between an NGO and the FMOH and links to the private sector. / Benefits to the environment/climate / There is some research to show that family planning can have a potentially impressive impact on carbon emissions. A paper last year concluded that family planning (with or without girl’s education) is one of the cheapest strategies for carbon emission abatement. Although the grounds for the level of carbon mitigation claimed in the paper are somewhat speculative at present and there are evident measurement challenges. It is accepted that reduced population growth will have a broadly positive impact through a reduced rise in carbon emissions in a low income country such as Ethiopia but given the low carbon emission per capita this should not be overestimated. / According to the Marie Stopes International impact calculator Option 1 would avert an estimated 1,484,011 global hectares of ecological footprint and 80,946 global hectares of carbon footprint, and Option 2 would avert an estimated 1,695,208 global hectares of ecological footprint and 92,466 global hectares of carbon footprint. / Quantification of benefits[3] / A Couple Year of Protection (CYP) for a particular family planning method is calculated by multiplying the quantity of the method distributed to clients by a conversion factor. This yields an estimate of the duration of contraceptive protection provided per unit of that method. / Using conversion tables developed for DKT by Marie Stopes International (MSI) as part of their Impact Calculator, the total potential increase in CYP and associated benefits are estimated using MSI’s Impact Estimator. This is a tool that measures the wider demographic, health, economic and environmental impact of family planning and safe abortion services, by converting CYPs: the number of births averted; infant, under five and maternal deaths averted; unsafe abortions averted; DALYs saved; and societal cost savings. The tool was developed by MSI in conjunction other technical agencies. The tool uses externally validated coefficients. / There are a number of limitations of the Impact Estimator. In addition, the tool excludes health benefits gained through the protection against HIV/AIDS and other sexually transmitted infections that condoms provide. It also excludes a range of non-health benefits including educational, social and political factors, such as aiding female empowerment, macroeconomic benefits from demographic transition and posited links between rapid population growth and civil conflict. / DFID’s Policy Division will work with MSI and global technical agencies both to refine the Estimator and to build consensus across agencies to ensure consistency of approach in reporting results in reproductive health in support of DFID’s Reproductive Maternal Newborn Health Framework for results. / The contraceptives that would be procured through options one and two are shown in the table along with these estimated benefits and savings. / Option One - £18 million / Estimated Benefit Quantification / Maternal deaths averted 7609 / HIV transmissions averted 0 / Unintended pregnancies averted 1,618,921 / Abortions averted 215,401 / Couple years of protection 6,214,285 / Condoms distributed 0 / Hormonal contraceptives distributed (chosen as the most commonly methods currently) Oral – 24 million cycles / Injectable – 18 million / These services will save an estimated / £118,097,516 On healthcare related to infant deaths / £62,003,097 On healthcare related to maternal deaths / £4,269,585 On healthcare to treat abortion complications / For every £1 invested in the services above an estimated £12.29 will be saved by health systems and families / Option Two - £18 million / Benefit Quantification / Maternal deaths averted 8691 / HIV transmissions averted 35,389 – 106,171 / Unintended pregnancies averted 2,516,228 / Abortions averted 246,056 / Couple years of protection 7,098,672 / Condoms distributed Male – 294,919,712 / Female – 136,378 / Hormonal contraceptives distributed Oral – 12,200,167 cycles / Injectable – 5,625,636 / Emergency – 2,218,212 / These family planning services will save an estimated / £134,904,579 On healthcare related to infant deaths / £70,827,076 On healthcare related to maternal deaths / £4,877,212 On healthcare to treat abortion complications / For every £1 invested in the services above an estimated £14.04 will be saved by health systems and families (this excludes the savings from HIV transmission) / These estimates are based on the assumption that these reproductive health inputs are filling the unmet demand for family planning in Ethiopia and that consumers are not substituting one effective family planning method for another. / Over a twenty year time horizon, an economic appraisal of the spend for Option 1 resulted in a Net Present Value (NPV) of £65.6 million, Internal Rate of Return (IRR) of 58% and a Benefit Cost Ratio (BCR) of 5.3 at a 12% discount rate. This is the average lending rate in Ethiopia representing the cost of capital. This is inline with the recent discount rate guidance in DFID. This implies that Option 1 would deliver a benefit of £5.30 for every £1 spent to support reproductive health commodities and savings to families and the health care system of an estimated £12.29 for every £1 investment. / Option 2 would deliver an NPV of £90.4 million, IRR of 72% and BCR of £6.90. Option 2 would deliver benefits of close to £7 for every £1 spent and savings to families and the health care system of an estimated £14.04 for every £1 investment. / Which is the preferred Option that will be progressed? / Based on the benefits outlined above Option 2 is the preferred option that will be progressed. This intervention will make up an important part of the overall investment in health sector results that DFID will make to 2015 that will contribute to: / Expanding access to and quality of health services / Increasing and measuring impact and results / Increasing equity of health services and indicators. / It will complement the anticipated significantly scaled up support for the broader HSDP systems and services though the Protection of Basic Services programme (PBS) and the Federal Ministry of Health MDG Performance Fund and help to support a ‘big push’ on increasing access to family planning. This investment will particularly contribute to increasing access to health services, impact and results. Other planned elements of the portfolio of investments to achieve the results detailed in the DFID Ethiopia Operational plan include. See Table 3 below for a mapping of how the MDG PF and other planned investments will complement each other. / Table 3 How DFID will meet its objectives in the health sector / Increasing access to services Increasing quality of services Increasing equity of services Increasing impact and results / To a major extent MDG PF / Scaling up support for the Protection of Basic Services (PBS) / Support for reproductive health commodities MDG PF / Support for NGOs to increase quality and equity of reproductive health services (in design) Peace and Development Programme focussed on the Somali Region (in design) / Support for NGOs to increase quality and equity of reproductive health services (in design) MDG PF / Technical Assistance support to the FMOH / Support for reproductive health commodities / To a lesser extent Scaling up support for the Protection of Basic Services (PBS) / Technical Assistance support to the FMOH MDG PF / Scaling up support for the Protection of Basic Services (PBS) DFID multi-country (evidence for action) programme (in design)
D. What measures can be used to assess Value for Money for the intervention? / At a Global Level the Guttmacher Institute has undertaken research which demonstrates the increasing the coverage of modern family planning methods is a highly cost effective interventionlvi. They calculate that meeting the need for family planning methods for 818 million women in developing countries would cost: / $ 28 to avert an unintended pregnancy / $ 3050 to save the life of a woman or newborn / $ 62 to save a DALY (women and newborns combined) / Putting this in the context of other common health care interventions in developing countries they demonstrate that such a cost-benefit figure represents relatively good value for money: / Intervention Cost per DALY saved in USD / Insecticide-treated bed nets 13-20 / Malaria prevention for pregnant women 29 / Tuberculosis treatment (epidemic situations) 6-60 / Modern contraceptive methods 62 / Antiretroviral therapy (Africa) 252-547 / BCG vaccination of children 48-203 / Oral rehydration therapy 1268 / Cholera immunisation 3516 / Furthermore the Guttmacher Institute in 2009 demonstrated that in Sub-Saharan Africa, providing modern contraceptives to all women who need them would more than pay for itself, saving $1.30 in the cost of maternal and newborn care for each dollar invested. / Value for money will be assessed during programme monitoring and evaluation through the following measures: / Comparisons within and beyond Ethiopia of unit costs of commodities procured / Number of and cost per couple year of protection provided / Number of and cost per unintended pregnancies prevented / Using a DFID accepted impact calculator – such as the Marie Stopes International Impact Tool – estimates will be made annually of the number and cost of maternal deaths and DALYs saved. / Estimates of the number of and cost per HIV infection averted.
E. Summary Value for Money Statement for the preferred option / As highlighted above, increasing the provision of family planning services is a cost-effective strategy that will provide benefits to the economy within a reasonable timeframe. The main health benefits of the intervention include the reduction in the numbers of unintended pregnancies and deaths averted. Better spacing of births and preventing unwanted pregnancies is also expected to improve the health of women and their children. The intervention will also prevent the transmission of HIV and AIDS which will have a significant benefit to the economy at large. / In aggregate the economic appraisal undertaken revealed that Option 2 is the best option from a VfM perspective as it will generate an NPV of £90.4 million, IRR of 72% and close to £7 of benefits for every £1 that is spent on social marketing of reproductive health commodities. For every £1 invested, an estimated £14.04 will be saved by families and the health care system. These health system savings do not include the savings associated with HIV and AIDS cases averted. The full appraisal (Quest No. 3234550) gives figures adjusted for sensitivities.
[23] Girma and Erulkar (2009) Commercial Sex Workers in Five Ethiopian Cities: A Baseline Survey for USAID Targeted HIV Prevention Program for Most-at-risk-populations. USAID, Addis Ababa.
[24] Meta-analysis by Lesley Snyder which looked at work between 1986 and 2006; under review for publication.
[25] Bertrand, et al (2006) Systematic review of the effectiveness of mass communication programs to change HIV/AIDS-related behaviors in developing countries. Health Education Research 21:567-597.
[26] Johnson et al (2010). Second National HIV Communication Survey 2009. Pretoria: JHHESA
[27] Yates (2009) Universal health care and the removal of user fees. Lancet 373: 2078–81.
[28] Cleland et al (2006) Family planning: the unfinished agenda. Lancet. 368 (9549):1810–27.
[29] Matheny(2004) Family planning programs: getting the most for the money. International Family Planning Perspectives; 30: 134-138.)
[30] Lewis. (1986) "Do contraceptive prices affect demand?" Studies in Family Planning 17, 3: 126-135
[31] Lande, and Geller (1991) Paying for family planning. Population Report; (39).
[32] Population Reports (1991) Paying for family planning. Population Reports Series I, no.39 (November), Family Planning Programs: 22- 23
[33] Matheny G. (2004) Family planning programs: getting the most for the money. International Family Planning Perspectives; 30: 134-138.
[34] Magnani et al (1999) The Impact of Family Planning Supply Environment on Contraceptive Intention and Use in Morocco. Studies in Family Planning 30(2): 120–132.
[35] Chen and Guilkey (2003). Determinants of Contraceptive Method Choice in Rural Tanzania between 1991 and 1999. Studies in Family Planning 34(4): 263–76; Tsui, A et al (2002) Health Program Effects on Individual Use of Service. Working paper 60. MEASURE Evaluation;
[36] Karim et al (2008) Measuring Family Planning Logistics System Performance in Developing Countries. Working Paper, USAID DELIVER Project.
[37] Barkat et al (2009) Human and Economic Impact of RH Supplies Shortage & Stockouts in Bangladesh.
[38] BETA Development Consulting (2010) National Survey on Availability of Modern Contraceptives and Essential Life Saving Maternal/RH Medicines in Service Delivery Points in Ethiopia. Study commissioned by UNFPA.
[39] Cited in DELIVER (2006). Reproductive Health Commodity Security Strategy for the West Africa Subregion.
[40] DELIVER Project (2009) A Strong Supply Chain Responds to Increased Demand for Contraceptives in Rwanda
[41] RH Supply Coalition (undated) The importance of the supply chain.
[42] DKT (2011) Focused Social Marketing Plus: Building on 20 years of experience in Ethiopia.
[43] Tuladhar (1985) Determinants of contraceptive use in Nepal. J Biosoc Sci. 17(2):185-93.
[44] Agha and, Kusanthan (2003) Equity in access to condoms in urban Zambia. Health Policy Plan. 18(3):299-305.
[45] Lande, and Blackburn (1989) Pharmacists and family planning. Population Reports.
[46] Agha et al (2002) Reasons for non-use of condoms in eight countries in sub-Saharan Africa. AIDSMark/USAID
[47] Casterline et al (2001) Obstacles to contraceptive use in Pakistan: a study in Punjab. Population Council, WP 145
[48] Casterline and Sinding (2000) Unmet need for family planning in developing countries and implications for population policy. Population Council.
[49] UNAIDS, WHO and UNFPA (2009), Position Statement on Condoms and HIV Prevention.
[50] CDC (2008) 'Male latex condoms and sexually transmitted diseases', Fact sheet for public health personnel.
[51] De Vincenzi (1994) A longitudinal study of human immunodeficiency virus transmission by heterosexual partners. NEJM; 331:341-346
[52] Weller and Davis-Beaty (2007), Condom effectiveness in reducing heterosexual HIV transmission. Cochrane Database of Systematic Reviews.
[53] Kiddugavu et al (2003) Hormonal contraceptive use and HIV-1 infection in a population-based cohort in Rakai, Uganda. AIDS; 17:233–240)
[54] Trussell J. Contraceptive efficacy. In: Hatcher et al (2004) Contraceptive Technology. 18th revised ed. New York, NY, Ardent Media.
[55] WHO (2004) Selected practice recommendations for contraceptive use. 2nd ed.; Trussell J. Contraceptive efficacy. In: Hatcher et al (2004) Contraceptive Technology. 18th revised ed. New York, NY, Ardent Media.
[56] Singh et al (2009). Adding it up: The costs and benefits of investing in family planning and maternal and newborn health. New York: Alan Guttmacher Institute, UNFPA.
[57] Tsui et al (2010) Family planning and the burden of unintended pregnancies. Epidemiol Rev. Apr; 32(1):152-74.
[58] Stover and Ross (2009) How contraceptive use has reduced maternal mortality. Matern Child Health J. 2009;14:687-695.
[59] Cleland et al (2006) Family planning: the unfinished agenda. Lancet. 368 (9549):1810–27.
[60] Collumbien M et al. (2004). Non-use and use of ineffective methods of contraception. In: Ezzati M, et al eds. Comparative quantification of health risks: global and regional burden of disease attributable to selected major risk factors. WHO: 1255-1320
[61] Prata (2007) The need for family planning. Population and Environment; 28:212–222.
[62] The Ethiopian Health Extension Programme (HEP) is a government-led community health service delivery programme designed to improve access and utilisation of preventive, promotive and basic curative services. At the heart of the programme is the training and deployment of community health extension workers.
[63] Wakabi (2008) Extension Workers Drive Ethiopia’s Primary Health Care. The Lancet, vol 372 September 13.
[64] Rothschild ML 2010. Using Social Marketing to manage population health performance. Pre Chronic Disease (7) 5 A96
[65] Levine R, Langer A, Birdsall N et al. Contraception. In : Jamison DT et al. Disease Control Priorities in Developing Countries. 2nd ed. World Bank, Oxford University Press. 2006
[66] Harvey PD. Social marketing: No longer a sideshow. Stud Fam Plann. 2008; 39 (1), 69–72.
[67] Greenstar Social Marketing Pakistan. Earthquake Reconstruction Project Reports. 2006–7. Islamabad
[68] Chapman S, Astatke H. Review of DFID approach to social marketing. Annex 5: Effectiveness, efficiency and equity of social marketing and Appendix to Annex 5: The social marketing evidence Base. DFID Health Systems Resource Centre. London, UK; 2003.
[69] Foss, AM, Hossain M, Vickerman PT, Watts CH. A Systematic Review of published evidence on interventions impact on condom use in Sub-Saharan Africa and Asia. Sex Transm Infect. 2007; 83: 510–516.
[70] Sweat et al. (2010) Effects of condom social marketing on condom use in developing countries: A systematic review and meta-analysis: 1990-2010. In progress.
[71] Price (2001) The performance of social marketing in reaching the poor and vulnerable in AIDS control programmes.” Health Policy and Planning 16(3): 231–239.
[72] Madhavan S, Bishai D. Private Sector Engagement in Sexual and Reproductive Health and Maternal and Neonatal Health: A Review of the Evidence. Johns Hopkins University, 2010.
[73] Federal Ministry of Health annual Health and Health Related Indicators Reports (except for medical abortion drugs), Addis Ababa, Ethiopia.
[74] Meadley et al (2003) Review of DFID Approach to Social Marketing. DFID Health Systems Resource Centre, London.
[75] Source: communication with Bruce Mackay, private sector specialist, HLSP
[76] WHO (2007) Public Policy and Franchising Reproductive Health: Current Evidence and Future Directions. Guidance from a technical consultation meeting.
[77] Smith et al. Family Planning Saves Lives, fourth ed. Washington DC Population Reference Bureau, 2009
[78] Bloom, David E. and Jeffrey G. Williamson (1998), Demographic Transitions and Economic Miracles in Emerging Asia, World Bank Economic Review, 12: 419 - 455.
[79] Women’s Studies Project. www.fhi.org/en/RH/Pubs/wsp/index.htm
[3] These estimates have been calculated the Marie Stopes International Impact Calendar which has been accepted by DFID as a valid tool for calculating the impact of family planning services.

Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / The first year of this intervention will engage the services of the international NGO DKT Ethiopia (through indirect procurement). DFID has been supporting DKT to socially market RH commodities in Ethiopia for a number of years and this will continue for the first year to prevent an interruption of the supplies of contraceptives, condoms and other reproductive health commodities for Ethiopians throughout the country. / For this first year DFID will sign a Memorandum of Understanding with Irish Aid and the Royal Netherlands Embassy who are also planning to fund DKT’s social marketing activities and join a pooled fund arrangement with them. An arrangement will be established, according to DFID procedures, with one of these donors to channel DFID funding through that donor to DKT. / DFID centrally has recently run a competition to establish an overarching Reproductive Health Framework Agreement for the supply of RH services at country level. This framework agreement will encourage consistency across DFID’s work on RH including on value for money and quality. For the outer three years of this intervention DFID will run a mini-competition amongst the suppliers who have been successful under the RH framework (direct procurement). Funding will be disbursed directly to the supplier by DFID. / Ideally, the mini-competition would be run now for the duration of the intervention, but it has been agreed with Procurement Group that DFID’s support to DKT can be continued for the coming year in order to ensure continuous supplies of commodities in the country. / Every effort will be taken to ensure that the mini competition will be transparent and fair; and DKT will not have an unfair advantage. This will include making all outputs (i.e. reports, manuals etc) from the work DKT are carrying out for the first year available to all bidders before the mini-competition. In addition, there would be a pre-bid meeting with all suppliers with DKT present as part of the panel so that they can answer questions on programme they are currently working on.
B. How does the intervention design use competition to drive commercial advantage for DFID? / For the outer three years of this intervention DFID will run a mini contract where suppliers will be invited to bid on the basis of Terms of Reference for the programme. / The Terms of Reference for the mini competition will be results and value for money focussed and will ensure that all proposed activities are based on evidence or where evidence doesn’t exist that efforts will be made to generate it. / The supplier will be engaged under a milestone based contract which will enable us to address performance on a continuous basis
C. How do we expect the market place will respond to this opportunity? / Whilst there are a relatively small number of social marketing organisations with the required expertise to design and implement this programme in Ethiopia, running a mini competition will attract more than one organisation to bid for implementation and will push partners to ensure they are offering the maximum impact and value for money.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The key cost drivers of this intervention will be (i) unit costs of commodities, (ii) mix of commodities procured, (iii) distribution costs, and (iv) freight and handling fees. / The principles of demand and supply will interplay to influence the mix of commodities distributed. This will include the availability of products, popularity of products, demand from supplier, and the brand of the products etc. / There are indications from the market that, due to the increased focus on family planning globally, that the unit cost of commodities is likely to reduce in the next year or two. There are also more generic products coming on to the market. However a challenge will be to ensure that the quality of new products is to an international standard and acceptable to Ethiopia which has its own registration process. / Annual reviews of the intervention will include analysis and comparisons of unit costs of commodities as well as couple years of protection provided. Processes for quality assurance of commodities will also be monitored.
E. What is the intended Procurement Process to support contract award? / The contract will be awarded to a supplier under a newly established DFID framework agreement. DFID Ethiopia will develop Terms of Reference and the process will be managed by DFID’s Procurement Group. Suppliers who have been successful under the RH Framework agreement will be invited to bid .
F. How will contract & supplier performance be managed through the life of the intervention? / For the outer three years the programme will be implemented by the supplier who was successful in the mini-competition outlined above. The supplier’s performance will be managed through a milestone contract in order to ensure delivery of results and value for money. Payments will be made on the basis of timely, good quality delivery of services and goods. Almost 75% of the funds will go to procure reproductive health commodities. / During the life time of this programme, regular reports, monitoring meetings and annual reviews will be used to monitor and address the performance of the supplier. In addition, annual audited accounts produced by internationally accredited auditors will be required under the contract.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / DKT is a well established NGO in Ethiopia. It partners with both government and non-governmental organisations to reduce the transmission of HIV and AIDS, and increase the availability and correct use of family planning methods and other reproductive health commodities. DFID has been providing support for DKT Social Marketing Programmes in Ethiopia since 2005. A recent independent evaluation of this support concluded that DFID was in a strong position to contribute to UK development objectives, particularly around improving maternal health and combating HIV/AIDS. The consistent supply of condoms and other contraceptive products in Ethiopia depends almost entirely on DKT’s continuing efforts. / DFID centrally has awarded a Reproductive Framework Agreement with successful suppliers which sets out the understandings of both organisations on the provisions that will apply to activities. This time next year a mini competition will be run for the outer three years of the intervention under this framework agreement. It has been agreed with Procurement Group centrally that for the first year support will continue through DKT under an MoU (jointly with other donors) to ensure that there is no major interruption in the supply of commodities in the country.
B. Value for money through procurement / The main goods to be procured under this programme are reproductive health commodities. With guidance from DFID’s Procurement Group, DFID Ethiopia requested DKT Ethiopia to complete a Third Party Organisation questionnaire on procurement. / In summary, the key findings are that DKT Ethiopia manages its commodity procurement as per Government of Ethiopia guidelines and procedures. This requires agency agreements with most suppliers. Before entering an agency agreement and registering products factors such as risk, alternative supplier options and supplier performance are considered. / DKT Ethiopia has staff who are professionally qualified in procurement. All procurement is managed at the country level. Proscribed procurement systems are appropriately followed because the Government of Ethiopia must approve every purchase order for contraceptives and other health products. In addition, DKT regularly monitors global prices for contraceptives/other health products through meetings with DKT teams in other countries, with UNFPA prices and through the Reproductive Health Supplies Coalition website. / DKT Ethiopia operates at the invitation of the Government of Ethiopia (GoE) and is required to adhere to all GoE rules and regulations. All DKT products come from suppliers that are registered by the Ethiopian Food, Medicine and Health Care Administration and Control Authority (FMHACA). The FMHACA registration process is rigorous and is based on international guidelines. For drug manufacturers outside of Europe and North America, a factory inspection and comprehensive dossier are required (medical devices, such as condoms only require a dossier). By nearly all accounts FMHACA is stringent in its registration requirements and is not known to be corrupt. / All shipments of medical drugs require a Certificate of Analysis in order to be allowed into the country. For condoms, DKT arranges for independent sampling and testing (by internationally accredited laboratories) of all batches prior to shipment. DKT also does regular independent sampling and testing of the other products it imports. Please note that independent testing is not required for importation of any of the products DKT imports (but it does reflect DKT's concern for quality). / In some cases, after a factory inspection has been conducted, DKT has received special permission to import limited supplies on a 'pre-registration' basis but these importations are not common. / Once a product is in Ethiopia, DKT tracks all sales in case there is a need to recall any product. / The recent independent review of DFID support for concludes that DKT is an organisation with exceptional procurement expertise.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / DFID will provide up to £18 million over four years (fiscal years 2011/12 to 2014/15). / The approximate breakdown of costs by year is as follows: / 2011/12 2012/13 2013/14 2014/15 / £6.5 million £3.5 million £4 million £4 million / For the first year intervention, DFID will release the money in one tranche upon the signing of the Joint MOU and Funding Arrangement. The majority of this fund will be for buying RH commodities. DKT would be able to disburse with in three months of time after the release of funds. For the last three year payments will be based on the milestone contract which makes accurate forecasting possible.
B. How will it be funded: capital/programme/admin? / The programme will be funded from programme resources, and has been budgeted for in the Operational Plan for DFID Ethiopia (2011 – 2015). The current planned resources are within the current spending round period (to 2015). Based on performance and need consideration will be given in 2014 as to whether to continue funding for reproductive health commodities and whether this continues to be the optimum channel to do so. / There are no contingent or actual liabilities.
C. How will funds be paid out? / DFID will sign a funding arrangement with with one of the Donor Partners to channel funds through them to DKT for the first year intervention. / Funding will be channelled directly to the Supplier as set out in the milestone-based contract for the outer three years. Funds will be used for the provision of goods and services as specified in the project proposal.
D. What is the assessment of financial risk and fraud? / In late 2007, DFID commissioned an independent fiduciary risk assessment. The report concluded that internal control systems were good and that the overall fiduciary risk for DKT is low. The following recommendations were made for improving systems which DKT implemented since that time: / Planning and Budgeting manual: comprehensive budget codes should be designed for each expenditure category and the codes should be aligned with the chart of accounts. In addition it would be appropriate to support it with a planning manual. / The introduction of a cash planning and management system. / Develop and implement procurement procedural manual: / To maintain finance as an independent unit: / In 2010 UNDP undertook a financial management assessment of DKT through an independent consultant, which also concluded that the overall risk of channelling funds through DKT was low and recommended the UN agency to fund DKT. The table below summarises their assessment of risk by area of assessment: / Areas of Risk Level of Risk / 1. Implementing Partner Low / 2. Funds Flow Low / 3. Staffing Low / 4. Accounting Policies and Procedures Low / 5. Internal Audit Moderate / 6. External Audit Low / 7. Reporting and Monitoring Low / 8. Information Systems Low / If the fiduciary risks of the supplier contracted for the outer years of the intervention have not been assessed recently then DFID will undertake an independent assessment before contracts are signed. If DKT win the contract an updated FRA will be undertaken.
E. How will expenditure be monitored, reported, and accounted for? / As per the programme requirements, DKT Ethiopia for the first year and the Supplier for the outer three years will submit six monthly progress report and financial statements. DKT Ethiopia for the first year intervention and the Supplier for the outer three years will also be responsible for submitting detailed Annual Work plans for the following year. In addition, both will submit Annual Audited Accounts produced by internationally accredited auditors. This report provides a detailed break down of income. Donor partners will carry out a joint annual review of the programme each year.

Management Case

A. What are the Management Arrangements for implementing the intervention? / As detailed above, the first year of this intervention will be funded through an MoU to the International NGO DKT. Thereafter, a contract for the outer three years will be awarded following a tendering process under the DFID Reproductive Health Framework Agreement. / For the first year, the management arrangements will along similar lines to the ‘joint grant’ to DKT that DFID has been co-financing for the last six years. The joint grant has been financed by DFID, the Royal Netherlands Embassy and the Irish Embassy and this arrangement, governed by a Memorandum of Understanding between the partners has included: / pooled funding in support of an agreed proposal and budget / joint financial and activity semi annual reports / joint annual action plan due by mid-December of the preceding year / joint meetings with DKT to review and agree progress reports and annual plans / jointly agreed ToR and selected consultant for an annual independent review of progress / Government of Ethiopia and representatives of the Reproductive Health umbrella organisation COHRA are also invited to programme review meetings. / These arrangements will continue for the first year of the grant, and thereafter management arrangements will be dependant on and agreed with the organisation that successfully wins the contract. The arrangements will not be less stringent than those outlined above. There will be a transition period of three months for DKT to handover to the new Supplier if DKT is not successful. / This programme will be managed by a DFID Health Adviser based in DFID Ethiopia. The DFID Ethiopia Health Adviser will call on other Advisers from the team as required e.g. for issues relating to public financial management, impacting on women and girls, results monitoring etc. / Financial reports, compliance and administrative functions will be managed by the DFID programme officer in DFID Ethiopia’s Human Development Team.
B. What are the risks and how these will be managed? / This programme is assessed as low risk at least for the first year whilst DKT is implementing the programme. DKT is a an established international organisation with longstanding experience of social marketing of RH Commodities in Ethiopia and extremely good working relationships with GoE partners. They have a proven record of delivery and results and the assessment of the fiduciary risk of channelling funding through DKT is low. / The main risks and the planned mitigation actions are presented in Table 4 below. All risks to this programme will be assessed along with mitigating actions as part of the DFID annual review process. / Table 4: Summary of key risks assessment and mitigation (where 1 is low risk and 5 is high risk) / Risk Probability / 1 – 5 Impact / 1 – 5 Mitigation Residual Probability / Health scares concerning new products result in adverse publicity and/or legal repercussions 3 3 Strong and appropriate marketing strategies and behaviour change communications. Medium / Supply of commodities is greater than demand effecting results of programme 1 4 Ensure flexibility to respond to possible changing demands for products. / If DKT doesn’t win the mini-competition and a new supplier comes into the picture affecting the momentum 3 3 Ensure partners are aware that there will be a competition for the outer three years and there might be a new supplier and there will be a transition period of the last three months Medium / Political risks / 7. GoE policies on reproductive health become more conservative 2 4 Ongoing dialogue with the GoE on health policies including those on reproductive health directly and through the implementing partner Low / 10. Change in FMOH leadership results in deterioration of relationship between implementing NGO and GoE 2 4 Ongoing engagement with the GoE on policies towards NGOs including support for capacity within the Charities and Societies Agency Low / Fiduciary risks / 13. Evidence of significant instances of corruption found 1 5 Annual procurement audits, plus annual financial audit will provide disincentive to corrupt behaviour and early identification of corrupt activities. Low
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / The logical framework will be the main monitoring tool for this programme. / Activities and outputs will be monitored against the logframe targets and milestones through semi-annual reports and an independent annual review of programme progress. Data sources will include (at least in the first year) DKT reports and data systems, surveys and FMOH routine data. Value for money will be monitored against the measures outlined above. / FMOH routine data is provided from the facility level up on a regular basis and aggregated at the woreda, regional and national levels. Efforts are underway to roll out a new HMIS, but progress has been slower then hoped for and this is a priority for systems strengthening efforts and policy dialogue. DFID is also working with the Central Statistics Agency and through the Monitoring and Evaluation component of PBS to strengthen national data quality. Data is triangulated through the DHS and other surveys. FMOH routine data is available every October for the preceeding Ethiopian Fiscal Year (which runs from July to June), the next round of DHS data will be available in 2015/16. Impact level indicators rely on survey data collected every five years so no annual milestones are set. / DKT has strong monitoring and tracking mechanisms including a Global Information System (GIS) for monitoring outlets and distribution of products. Their monitoring and tracking mechanisms will be assessed as part of annual reviews. The supplier that is successful in wining the contract for the outer years will be subject to similar checks. / Given the strong evidence of impact that this programme is based on, evaluation will focus on evidence of effective delivery, continued relevance of the approach, and the level of value for money achieved. DKT are planning a range of research activities to strengthen the evidence base for BCC, product promotion and operations. These will include retail audits, user studies, operational research and testing approaches to reaching low income groups.
Logframe / Quest No of logframe for this intervention: 3219631

REFERENCES