        National Secondary Education Programme
(RMSA)

Business Case

March, 2012

Contents	Pages

Acronyms	3-4

Intervention Summary	5-6

1. Strategic Case	7-15

2. Appraisal Case	16-40

3. Commercial case	41-45

4. Financial Case	46-52

5. Management Case	53-61

        6. Annexes

Annex 1: Economic Appraisal

Annex 2: Fiduciary Risk Matrix

Annex 3: Results Framework

Annex 4: Logical Framework

Acronyms

ARCS:	Audit Reports Compliance System
AWP&B:	Annual Work Plan and Budget
BCA:	Benefit Cost Analysis
BCR:	Benefit Cost Ratio
BRIC:	Brazil, Russia, India and China
CCT:	Conditional Cash Transfer
CVC:	Central Vigilance Commission
DEA:	Department of Economic Affairs
DFID:	Department for International Development
DHS:	District Level Household Survey
DIET:	District Institute of Education and Training
DISE:	District Information System for Education
DP:	Development Partner
DPC:	District Programme Coordinator
DSE&L:	Department for School Education and Literacy
EIRR:	Economic Internal Rate of Return
EMP:	Environmental Management Framework
EU:	European Union
FA:	Financial Aid
FM & PM:	Financial Management and Procurement Manual
GDP:	Gross Domestic Product
GER:	Gross Enrolment Rate
GoI:	Government of India
HMG:	Her Majesty’s Government
IA:	Internal Audit
IGNOU:	Indira Gandhi National Open University
IPAI:	Institute of Public Auditors of India
IUFR:	Interim Unaudited Financial Report
JRM:	Joint Review Mission
LSE:	London School of Economics
MDG:	Millennium Development Goals
MHRD:	Ministry of Human Resource Development
MI:	Monitoring Institute
MIS:	Management Information System
MMER:	Management, Monitoring, Evaluation and Research
MoF:	Ministry of Finance
MP:	Madhya Pradesh
NCERT:	National Council for Educational Research and Training
NCTE:	National Council for Teacher Education
NGO:	Non-Government Organisation
NIPFP:	National Institute for Public Finance and Policy
NIOS:	National Institute of Open Schooling
NPV:	Net Present Value
NSSO:	National Sample Survey Organization
NUEPA:	National University of Educational Planning and Administration
OECD:	Organization for Economic Co-operation and Development
OJEU:	Official Journal of European Union
PAB:	Project Appraisal Board
PFMA:	Public Financial Management Assessment
PISA:	Programme for International Student Achievement
PPP:	Public Private Partnership
RMSA:	Rashtriya Madhyamik Shiksha Abhiyan
SARH:	South Asia Research Hub
SB:	Savings Bank
SC:	Scheduled Caste
SCERT:	State Council of Educational Research and Training
SDMC:	School Development Management Committee
SEMIS:	Secondary Education Management Information System
SIEMAT:	State Institute of Educational Management and Training
SIS:	State Implementation Society
SPO:	State Project Office
SSA:	Sarva Shiksha Abhiyan
ST:	Scheduled Tribe
SWap :	Sector Wide Approach
TA:	Technical Assistance
TC:	Technical Cooperation
TCF:	Technical Cooperation Fund
TSG:	Technical Support Group
UPA:	United Progressive Alliance

Intervention Summary
Title: India - National Secondary Education Programme
What support will the UK provide?
£80 million over 4 years (2012- December 2015): £60 million financial aid to support India’s first national secondary school expansion programme; with £15 million in technical and management support to accelerate programme delivery in the most needy states; and £5 million to strengthen secondary education management information and systems that measure what secondary students learn.
Why is UK support required?
What are we trying to address? / India has doubled public spending on education in the last five years (2005-2010) and achieved 96% (net) enrolment in primary school. However, one third of students drop out of school before completing 5 years’ education. Nationally, secondary school enrolment (14-16 years) stands at 58%, leaving 20 million young people of secondary age out of school. In India’s 9 poorest states secondary enrolment is around 50%, with girls, rural young people and those from poor and socially disadvantaged backgrounds significantly[1] less likely to benefit economically and socially from the opportunity of post-basic schooling. / More children than ever graduating from basic education has resulted in a shortage of secondary places, especially in India’s poorest states. Currently the majority of secondary places are at fee-paying schools (60%). The Government of India (GoI) has launched a national drive to expand and improve the quality of secondary education for all social groups. Rashtriya Madhyamik Shiksha Abhiyan (RMSA) has a budget of £7.4 billion in the next five years (2012-2017) and aims to enrol 10 million additional students. The scheme will cover government schools initially and from 2013 expand to aided schools. / Expanding free education through RMSA schools will extend secondary education to currently unserved areas and help families who cannot afford school fees. India’s gender indicators are low and the social and economic benefits of secondary education are likely to be strong. Experience around the world also suggests that investing in the quality of secondary schooling is as important as expanding access to schools. / What will we do? / This programme responds to DFID’s India’s Operational Plan (2011-15) priority to break the cycle of inter-generational poverty for women and girls, through education, better nutrition and reproductive health. / Programme delivery (£60 million): GoI has asked DFID and the World Bank to work with it to improve the quality of RMSA delivery. GoI and India’s states run the programme on a joint funding basis (75:25). DFID’s financial aid and the World Bank’s concessional loan (£300 million[2]) will be added to government funds to pay for: school buildings, salaries for additional teachers; training for teachers and school heads; books and science equipment; and small grants for community-run school management committees. DFID and the World Bank will reimburse RMSA costs in arrears, provided GoI’s own investment reaches an agreed threshold. DFID will provide 2% of the total RMSA budget (2012-2015) and 6% of the year-on-year increase in RMSA funding. / Technical advice and management support (£20 million): DFID will provide technical expertise and management back-up to achieve two goals. First, accelerate RMSA implementation in the most needy states. This support will help education departments in the poorest states with secondary education budgeting and financial management, planning, procurement, civil works and teacher management, training and deployment. Second, to develop a national learning assessment system for secondary level and strong secondary education management information. DFID is the only donor providing technical support; a contract will be let by international competitive tender. / Who will implement? / DFID’s main implementing partners will be: India’s Ministry of Human Resource Development (MHRD), State Education Departments and the national apex National Council for Educational Research and Training (NCERT) [3], and National University of Educational and Planning (NUEPA)[4]. There are norms that determine what activities RMSA supports and DFID has agreed to these.
What are the expected results?
Results / 10.15 million additional enrolments at secondary level; / 7.64 million students completing secondary school better equipped for employment, of which 3.64 million girls; / Higher wage earnings of £2.95 billion as a result of improved secondary education access / Inter-generational benefits in health, monetised as £199 million in earnings due to reduced child mortality; / DFID attributed outputs by 2015-16[5] / 0.61 million additional students enrolled in secondary school, of which 0.47 million completers / 650 new schools and 7000 additional classrooms / 6,000 teachers recruited / 70,000 additional teacher training days delivered / £30 million value-for-money gains in secondary education supported in the most needy states / National Secondary Learning Assessment System established / Enhanced Secondary Education Management Information System (SEMIS) / Monitoring and Evaluation / RMSA progress will be measured against a common results’ framework agreed with GoI. Twice-yearly reviews by a joint donor/GoI mission led by Government of India will monitor progress, prescribe remedial actions and monitor follow up. DFID will commission an independent evaluation of the performance of its technical cooperation. Surveys will be commissioned (e.g. teacher attendance, student time on task) and policy and value for money analyses (e.g. unit costs, teacher education, the role of the private sector).
[1] There is a 20 percentage point gap between girls and boys attendance; a 40 percentage point gap between young people enrolled in urban compared to rural areas. Only 3.5% of students from families in the lowest income decile enrol.
[2] 2012-2017
[3] Responsible for curriculum standards and elementary national learning assessment.
[4] Tasked with strengthening planning, management and data collection and use.
[5] Based on an 6% share of RMSA’s total incremental costs

Strategic Case

A. Context and need for a DFID intervention / Education Context. / 1. Following a decade of sustained investment, India has achieved major progress in elementary education[6]: net primary enrolment stands at 96%. India’s other education priority has been to strengthen higher education, and tertiary graduates have underpinned India’s economic growth, promoting integration into the global ‘knowledge economy’. In contrast, secondary education has been neglected[1] - becoming a bottleneck rather than a bridge between elementary schooling, tertiary education and the world of work.[2] / 2. Sarva Shiksha Abhiyan (SSA), the national flagship programme to universalise elementary education has put India on track for achieving MDG2 - primary school access. Enrolment for 6-14 year olds has increased over 60 million, from 130 million in 2003 to 193 million by 2011. However, as Figure 1 demonstrates student attrition is a major challenge, and around half of the children drop out before completing grade eight (age 14)[3]. As Figure 2 below[4] shows, girls, particularly those from disadvantaged communities[7] and from the poorest states are least likely to progress into junior secondary education[8]. / Figure 1: Student Attrition in Indian Education / 3. Low levels of learning[5] partly explain student attrition. If education is not delivering learning, then the ‘opportunity costs’ are likely to outweigh the perceived social and economic returns, resulting in drop out. / Secondary Education / 4. Currently an estimated 20 million of 49 million children of secondary age are out of school [6] - most from disadvantaged communities in the poorest states. India’s United Progressive Alliance (UPA) Government has made education and labour-force skills the top priorities for its second term. In 2008, it launched Rashtriya Madhyamik Shiksha Abiyhan (RMSA), a national scheme to expand and improve the quality of secondary education. With a budget of £7.4 billion during the 12th Five Year Plan (2012-2017), RMSA is India’s first significant public investment in secondary schooling since Independence. Initial focus has been on government secondary schools; however from 2013, government-aided schools[9] will also receive RMSA support. RMSA aims to put 10 million into school by 2017 – however India is unlikely to achieve full secondary enrolment for at least another decade. / 5. Cost is a major deterrent to poor students attending secondary school. Although Government secondary schools (40% of places) do not charge tuition fees, families are required to cover the cost of transport, books, exams, uniforms and often private tuition. The World Bank calculates that secondary schooling is unaffordable without public subsidy for households in the lowest three consumption quintiles (perhaps the lowest four quintiles in rural areas)[7]. The poorest families find it hardest to sacrifice not only income but also girls’ domestic work. / Table 1: Household Per Student Expenditure on Secondary Schooling by School Type and Location / Government £ Government Aided £ Private £ / Urban 4000 rps £ 56 7294 rps £ 101 12514 rps £ 174 / Rural 2345 rps £ 33 3323 rps £ 46 5836 rps £ 81 / (72rps = £1 NSS 64th Round) / 6. Travel distances and concerns about personal safety are important reasons why girls are kept away from secondary school.[8] / 7. India’s desire to strengthen the coverage and quality of secondary schooling is due to at least three factors. Firstly, soaring demand as India reaches near universal elementary schooling. Secondly, the need for an expanded and better skilled workforce to support both economic growth (particularly in the service sectors) but also fulfil the need for public sector workers[9] Thirdly, the social imperative of ensuring India's largest ever youth population have opportunities to be fully productive citizens. / 8. International evidence points to the importance of good quality education in delivering economic and social benefits[10]. Research suggests that the quality of secondary provision in Indian schools is generally low[11]. Results from the two Indian states (with better than average educational performance) that participated in the OECD Programme for International Student Achievement (PISA) put them at the lowest levels of performance; well below BRIC and Middle income counterparts such as Brazil, Indonesia and Mexico[12]. Currently, India has no system for national learning assessment comparable across states and time – an essential prerequisite for increasing accountability and informing remedial strategies and resource targeting. / 9. The UK has supported the education sector for over 20 years, starting with the District Primary Education Project and moving onto the flagship national elementary (basic) education scheme Sarva Shiksha Abhiyan. The Government of India has asked DFID to graduate from aiding basic education in 2012/2013 and move assistance to secondary education. / Present evidence that clearly demonstrates the need for intervention / 10. While there is debate around levels and direction of causality – there is international consensus on the role of education in supporting economic growth[13] and delivering positive social outcomes. Research in India demonstrates strong benefits of education in labour market entry and raised income levels (including returns to agriculture, the predominant employer[14]). A recent study for the LSE linked education strongly to more inclusive economic growth[15]. Breaking the cycle of intergenerational poverty is more likely for those with access to secondary schooling[16]. Secondary education is positively correlated with improved health outcomes including reduced child mortality[17], and reproductive choice[18]. There is emerging evidence on the importance of education, particularly of girls as a cost effective response to climate change and disaster risk reduction[19]. / Demand rationale / 11. India’s shortage of good quality secondary schooling is evident in unmet demand from students, households and the labour market. Many secondary schools (especially in the poorest states) operate with class sizes of 80-120. This is a direct result of steadily rising enrolment without commensurate infrastructure or sufficient teachers, especially in such subjects as mathematics and science. In 2010, the number of elementary school graduates exceeded places in government secondary schools by over 5 million (a net shortfall that does not take account of the required geographical distribution of such places across states). Successive Indian employer surveys indicate / that shortages of skilled workers are constraints both to private sector investment and growth, especially in such ‘sunrise’ sectors as the financial services, IT, skill-intensive manufacturing, retail and tourism[20]. / Economic rationale / 12. The transition of India’s economy to one where the service sector generates the majority of GDP growth (Figure 3) demands that school leavers acquire a higher level of knowledge and skills than the 8 years of elementary education can provide. India’s level of secondary participation (14-16 years) compares unfavourably with its G20 economic competitors. Brazilian and Russian secondary school net enrolment rates are 27 percentage points higher than India’s; while India is estimated to be 30 years behind China in terms of the proportion of the population that has completed secondary and post secondary schooling[21]. / Figure 3: Service sectors contribute over 55% of India’s GDP growth / 13. Globally, education is positively associated with improved lifetime earnings. In India, the average earning of a secondary school certificate holder is calculated as 1.6 times higher than that of an elementary school graduate[22]. A 2010 study on economic returns to schooling in India [23] found that ‘education consistently and substantially raises earnings conditional on occupation, with ‘significantly larger returns to education accruing to women in wage work as compared to men’. Contrary to past assumptions that returns to education were greatest at the lowest education levels, the study found that the shape of the education-earnings relationship in wage work was convex, with increasing returns to higher education levels’[10]. The study also found that each additional year of schooling raised agricultural earnings by about 6.6 per cent (Figure 4), suggesting that education can play a productivity-enhancing and poverty reducing role beyond the formal sector. / Figure 4: Agriculture remains the Predominant employer / Social exclusion and social mobility rationale / 14. Striking social and gender disparities affect students’ participation in secondary schooling -as well as the quality of teaching they receive once in the classroom. This in turn reinforces unequal social and economic opportunity. 56.6% of girls are enrolled in secondary school nationally compared to 63.4% boys[24]. Only 61% of young people from the Scheduled Castes, 52% of Scheduled Tribes and 51% of Muslims attend secondary school, compared to 92% in the general caste category[25]. These gaps become even starker in India’s low income, low enrolment states. / 15. 60% of current secondary enrolments are in private and government-aided schools. The strength of the private sector offers DFID opportunity for innovative interventions and PPPs; but currently lack of tuition-free education partly explains the 40 percentage point gap in enrolment between students from the higher and lowest income quintiles (70% v 30%, respectively), and major differences in access between top and bottom quintiles across states (Figure 5). A 2011 study in rural Madhya Pradesh[26] found the combination of cost and distance to be the critical impediments to student transition from primary to lower secondary school. / Figure 5: Differential Access to Secondary Education Across Selected States / Source: Secondary Education in India: Investing in the. Future. Kin Bing Wu and Amit Dar. info.worldbank.org/etools/library/latestversion.asp?235784 / 16. Gender, health and family welfare rationale / India has achieved gender parity at primary level (to 11 years) but is off-track for achieving MDG 3, gender parity at secondary school. Nationally, the ratio of girls/boys is 0.87:1, but significantly lower for the poorest states – e.g. Bihar 0.57, and MP 0.66[27]. The World Economic Forum’s 2010 Global Gender Gap Report ranks India 112th out of 134 countries[28], and in the bottom three for health and survival indicators. Inequality is particularly marked in India’s poorest states. Globally there is strong evidence that health and family welfare indicators increase in proportion to each year of post-basic education (Figure 6). For India, these social benefits are clearly seen in the results of National Family Health Survey (Table 2). Secondary education, particularly for girls is a critical intervention with potential for big multiplier effects and inter-generational dividends[29]. / 17. More educated women tend to have more voice over marriage and fertility, leading to fewer and spaced pregnancies. Women with smaller families are more able and often more willing to participate in remunerative work, and are more likely to invest additional income in the health and education of their children - across generations, as well as to their communities at large. / Table 2: Influence of Education on Health Indicators / Education Level Fertility Rate Age of Marriage Age of first pregnancy % Malnourished Children / None 3.55 15.5 18.7 52% / < 5 years 2.45 16.5 19 45.5% / 5-7 years 2.51 17.3 19.6 38.5% / 8-9 years 2.23 18.7 20.8 34.5% / 10 -11 years 2.08 19.7 21.8 26.5% / > 12 years 1.8 22.8 24.8 17.9% / Third National Family Health Survey (2007) / Figure 6 / Infant Mortality by Education Vaccinations by Education / 18. Social cohesion rationale India’s youthful population will only fulfil the promise of demographic dividend (i.e. 70% of Indians will be of working age by 2025) if young people have opportunities to be fully productive citizens. Secondary education has an important role in expanding life chances, inculcating civic norms, challenging gender and caste stereotypes and equipping future generations for democratic and civic participation. Conversely, failure to address the growing demand for secondary education could suppress demand for primary education but also result in tensions among a disaffected, under-employed youth. In addition, a restricted flow of secondary graduates would also impede workforce development. India’s future teachers, doctors and business people will be drawn from the current cohort of secondary graduates[30]. / Explain specifically why DFID intervention is justified / 19. The Government of India (GoI) has asked its main development partners in education – DFID and the World Bank – to join its national secondary education programme because it believes they can enhance the quality of its own, much larger investment. The positive experience of donor engagement in India’s expansion of basic education (by over one third in the last decade) bears this out. A recent independent study found that a total donor contribution of less than 10% of GoI’s basic education programme Sarva Shiksha Abhiyan (SSA) resulted in a “…direct impact upon management practice, financial reporting, accounting procedures and monitoring arrangements. These changes probably improved the efficiency, and certainly the accountability, of the educational process[31]”. GoI is keen to secure similar engagement in RMSA. By adding to GoI’s £7.4 billion RMSA budget and the World Bank’s £300 million IDA loan (2012-17), DFID can make a far more scalable, strategic and sustainable contribution to secondary education in India than on its own. / 20. Secondly, DFID has conducted a prospective Value for Money Assessment for RMSA, which indicates that RMSA will lead to positive rates of return overall[32], with the highest direct economic benefits accruing in states with the lowest secondary enrolment rates currently, and opportunities for DFID to contribute to scheme efficiency gains in these same states through technical assistance. / 21. Thirdly, supporting secondary education is a good fit with DFID strategic priorities, both in India and globally. A key commitment of DFID India’s Operational Plan 2011-15 is to break the cycle of inter-generational poverty for women and girls in India’s poorer states; and better access to good quality secondary education, nutrition and reproductive health is central to our theory of change. DFID’s Structural Reform Plan Objective 5 is to ‘Lead international action to empower women and girls, a major component of which is to expand girls’ participation in secondary schooling. / 22. Fourthly, collaboration on education has been identified as an important part of the enhanced partnership between the UK and India; and DFID’s engagement in basic and secondary education is central to this. Other priorities for bilateral education co-operation include: participation by UK universities in India’s expansion of tertiary education; mobility of students between the UK and India; school exchange programmes; research and innovation collaboration; and skill development. / Is the intervention feasible? / 23. India has a proven record in rolling out national education programmes, as demonstrated by SSA. Through their engagement with SSA, donors have built strong working relationships and agreed ways of working with the government of India at both central and state levels. These are the foundations for successful support to RMSA. / 24. The major feasibility challenges for DFID support to secondary schooling in India’s poorest states are: strengthening existing secondary education management information systems in order to enable effective resource deployment and planning; enhancing financial management and planning; and increasing the availability of sufficient competent teachers, especially in such specialist subjects as maths, languages and science. Though challenging, these are areas DFID and the World Bank have practical experience in addressing both within India and more widely. / 25. The success of secondary expansion will depend on acting simultaneously on the supply side– schools, classrooms, teachers and materials - and demand-side challenges especially improving the quality of education and impediments to entry and retention, particularly for girls. GoI is fully aware of the need for a dual approach and has planned for two complementary national programmes on teacher development and stipends for grade 9 and 10 students from SC and ST families. / 26. While there are examples of centres of excellence, low levels of learning is a major concern throughout Indian education, increasingly recognised at both national and state levels. DFID has played an important role in strengthening capacity in learning outcome measurement at elementary level. / 27. GoI has invited DFID participation in secondary education through a SWap approach. This builds from its successful partnership with SSA. Becoming an RMSA partner will enable DFID to derive far greater impact and value for money than pursuing an initiative outside the national programme. Not least because DFID will be the sole provider of technical cooperation, putting it in a strong position to increase the effectiveness of the larger GoI and World Bank spend. Working through the national programme provides opportunity to pursue policy influence and results’ delivery in parallel. / What will happen if DFID does not intervene? / 28. If DFID does not intervene, GoI’s on-going efforts to expand secondary education will continue. DFID support will help them proceed more rapidly and effectively and ensure that the poorer states can derive maximum benefit from the huge Government of India resources available. / Summarise relevant evidence underpinning the intervention / Intervention choice: / 29. There is strong evidence – much of it summarised above - about the economic returns of education investment and specifically of secondary education in India[33]. Regionally, rates of return are favourable (see Table 3). / Table 3: Regional Rates of Return to Differing Levels of Education / Primary Junior Secondary Higher Secondary Survey / Year / India 8.5 16.8 16.3 NSS 2004 / Pakistan 4.8 14.2 13.9 PIHS 2001 / Bangladesh 4.7 4.1 7.1 BHIES 2004 / Source: World Bank: 2004 The knowledge economy and education and training in South Asia p31 / 30. Evidence on the social benefits of secondary education in improving women’s lives is well documented internationally[34] and in India. There is also research suggesting good quality secondary education (i.e. providing problem-solving, communication and team working skills) is more cost-effective and socially beneficial than traditional forms of vocational training, which tend to have higher unit cost and are weakly linked to labour market needs. / Maximising intervention effectiveness / 31. There is broad international agreement on what works to improve the quality of a country’s education system.[35] There is a growing evidence base on what works to improve the quality of primary education in India, to which DFID is actively contributing. In comparison, the evidence on what works at secondary level in developing countries including India is limited; as is DFID’s own recent experience. RMSA will be DFID’s first major intervention in secondary education in over ten years and is expected to contribute some 40% of DFID’s overall secondary results. / 32. Supporting RMSA is envisaged as part of a package of assistance benefiting girls’ education in particular, which will include three demand-side interventions: a conditional cash transfer to enable the most disadvantaged girls to go to and stay in secondary school (Odisha); experimental work in low fee private schools in urban areas (Bihar); and potentially a secondary education vouchers programme to expand school choice and drive up quality (Madhya Pradesh). / B. Impact and Outcome / 33. The key outcome of this programme is that: India’s poorest states achieve more equitable access to good quality secondary schooling leading to better educated and employable youth. DFID support will help RMSA put an additional 10.1 million students in school, with disproportionately higher gains for girls and disadvantaged groups (ST, SC and Muslim students). We will measure these changes through strengthened Secondary Education Management Information System (SEMIS, which we will support directly) and by helping India to establish a first national secondary learning assessment system, comparable across states and time. / DFID support will result in: / Performance Level Measured by : / Impact: Better educated and employable youth Youth employment rates disaggregated by gender and percent of women ages 15-19 who are already mothers or pregnant. / Outcome: More girls and boys, regardless of social background, benefit from good quality secondary education Enrolment, graduation, gender parity and social background indicators. / Output 1: Strengthened planning and management to better deliver quality education Development of a secondary national achievement survey, teacher attendance, in-service teacher training and prevalence of secondary school management committees. / Output 2: Schools are given the necessary resources to deliver quality secondary education Number of teachers (disaggregated by gender), Infrastructure provision including toilets, and teacher allocations by subject. / Output 3: Children, regardless of background, regularly attend and complete secondary school. Elementary to secondary transition rate, student attendance rates and gross completion rate. / 34. Using government projections, we estimate that an £80 million DFID contribution – equivalent to 6% of RMSA’s total incremental budget 2012-16 (and 2% of overall programme costs) can enrol an estimated 0.6 million students and deliver £30 million value for money gain in India’s most needy states. DFID support will fund the building/ up-grading of an estimated 650 new schools and the employment of 6,000 new teachers. Through technical assistance DFID will strengthen government’s management of over 74,000[36] government and government-assisted secondary schools. DFID will also support the development of an integrated secondary education management system and a learning outcomes assessment system that enables better informed decision-making. In keeping with GoI’s commitment to information transparency, improved data sets will enable civil society to better engage in the drive for greater equity and improved learning outcomes. / 35. Evidence from Sarva Shiksha Abhiyan suggests that strong gains in access and social equity are possible over this timeframe; and that transformation is achievable within a decade. Delivering a step- change in education quality - linked to retention and completion -in the time frame envisaged is unlikely. However, through technical assistance the programme will establish the prerequisites for sustained systemic improvement (i.e. developing the capacity to collect, analyse data/learning outcomes and to deliver appropriate responses through effective resource targeting). There is strong evidence from SSA that DFID investing alongside GoI and other donors can support reforms in such areas as sub-sector planning and monitoring, public financial management and national learning assessment systems. / DHS 2006 / Source: India Household Survey Data – Education and Child Health (DHS survey 2006) / DHS:2006
[6] Elementary education in India constitutes primary (ages 6-11) and upper primary (ages 12-14). India’s 8 grade primary cycle approximates the international definition of a basic education
[1] Panda, P., & Reddy, N. Secondary Education in India (2008). Asian Network of Training and Research Institutions in Education Planning – Newsletter Vol 12. No2.
[2] Tilak, J B G., Post Elementary Education. Poverty and Development in India (2005). Edinburgh University Centre of African Studies. Post Basic Education and Training Working Paper No 6.
[3] Who goes to school ? Exploring Exclusion in Indian Education. Govinda, R. Ed  Govinda & Bandyopadhyay 2011 p5.
[4] Ibid. p11
[7] The Scheduled Castes (SCs), also known as the Dalit, and the Scheduled Tribes (STs) are two groupings of disadvantaged people that are given express recognition in the Constitution of India
[8] Across India, the gender parity index for Schedule Tribe children at grade 8 (Age 14) is 1:0.94; while at junior secondary, Grade 9 and 10 (ages 15&16), this drops to 1:0.76. Moreover, there is considerable variance between states, with Bihar as low as 1:0.57 and Andhra Pradesh as high as 1:0.94.
[5] ASER 2005-11, Education Initiatives 2010, AP RESt 2011, NCERT 2012, PISA 2011.
[6] Based on Census 2001 and Government of India data
[9] Secondary schools in India can be categorised into: Government: government financed, tuition free, Government aided: privately managed, but up to 95% of funding derived from state ‘grants-in-aid’. Schools follow government regulations but charge fees. Private un-aided (recognised): Self financing (fee charging), Registered with government on fulfilling minimum standards. These schools encompass a range from elite schools to newly established schools for the urban middle class. Private un-aided (un-recognised): Emergent self financing schools not affiliated to the dept of education nor registered with any agency.
[7] World Bank 2009 Secondary education India: Universalizing opportunity.
[8] Siddhu, G., (2011) Who makes it to secondary school? Determinants of transition to secondary schools in rural India. Int. J. Educ. Dev., doi:10.1016/j.ijedudev.2011.01.008
[9] EFA Goals and Expanded Secondary Schooling – Taking Stock and Seeking Solutions Keith M Lewin http://www.cecomm.org.uk/attachments/CHOGM%20Paper%20Kampala%20Final.pdf
[10] Altinok, N. 2007. Human Capital Quality and Economic Growth. Breton, T.R. The quality vs. the quantity of schooling: What drives economic growth ?
[11] Das, J. & Zanonc, T. (2010) India shining and Bharat Drowning: Comparing Two Indian States to the Worldwide distribution of Mathematics Achievement, Journal of Development Economics, Vo. 92, Issue 2.
[12] PISA 2009 Plus Results. Walker, M.: Performance of 15-year-olds in reading, mathematics and science for 10 additional participants
[13] Hanushek, EA and Wößmann, L (2007) The Role of Education Quality for Economic Growth Washington, DC, World Bank, Human Development Network (Policy Research Working Paper, 4122)
[14] Aslam, M., A. De, G. Kingdon and R. Kumar (2010) “Economic Returns to Schooling and Skills - An analysis of India and Pakistan. http://recoup.educ.cam.ac.uk/publications/WP38-returns_to_education.pdf
[15] Bhalla, S.S. 2011. Inclusive growth in India: Some facts, some conclusions
[16] Rose, P., Dyer,C. (2008) Chronic Poverty and Education: a review of the literature. Working Paper 131, Chronic Poverty Research Centre. University of Manchester.
[17] Education Policy Data Center. Education Profile:India 2010 http://www.epdc.org/datavisualization/content/profiles/india_nep.pdf
[18] Dreze, J. and Murthi, M., Fertility, Education, and Development: Evidence from India by in Population and Development Review, Vol. 27 (1), pp. 33-63, Mar., 2001 www.jstor.org/stable/2695154
[19] Adaptation to Climate Extremes In Developing Countries: The Role of Education Policy Research World Bank. 2010. Working Paper 5342 & Education responses to climate change and quality: Two parts of the same agenda? International Journal of Educational Development 30 (2010) 359–368. Bangay, C., Blum, N.
[20] Emerging skill shortages in the Indian industry http://www.ficci-hen.com/Skill_Shortage_Survey_Final_1_.pdf
[21] Kingdon. G., The Progress of School Education in India (2007): ESRC / GPRG. http://economics.ouls.ox.ac.uk/12991/1/gprg-wps-071.pdf
[22] http://education.nic.in/secedu/sec_overview.asp
[23] Aslam, M., A. De, G. Kingdon and R. Kumar (2010) “Economic Returns to Schooling and Skills - An analysis of India and Pakistan. http://recoup.educ.cam.ac.uk/publications/WP38-returns_to_education.pdf
[10] The reasons for declining returns are likely two-fold in India: firstly the supply of primary completers has greatly increased over the past 3 decades and the wage rewards to primary education are likely to have correspondingly fallen. On the demand side, demand for employees with low skills may have fallen due to changes in the education and skill requirements in the job market
[24] SEMIS – 2009-2010
[25] NSSO – 64th Round
[26] Siddhu, G., (2011) Who makes it to secondary school? Determinants of transition to secondary schools in rural India. Int. J. Educ. Dev., doi:10.1016/j.ijedudev.2011.01.008
[27] Secondary Education Statistics, Government of India 2006-7.
[28] World Economic Forum (2010) Global Gender Gap Report. Categories are : economic participation; educational attainment; health and survival; and political participation.
[29] DFID Evidence paper in Support of the Girls Education Challenge Fund – EDRF ref 3074468
[30] EFA Goals and Expanded Secondary Schooling – Taking Stock and Seeking Solutions Keith M Lewin http://www.cecomm.org.uk/attachments/CHOGM%20Paper%20Kampala%20Final.pdf
[31] The impact of aid on education policy in India: Colclough, C, De. A., International Journal of Educational Development 30 (2010) 497–507
[32] Kingdon, G., Atherton P. 2010. Value for Money Assessment of DFID Assistance to Education in India. EDRM no: 2746099
[33] (a) Kingdon, G., Atherton P. 2010. Value for Money Assessment of DFID Assistance to Education in India. EDRM no: 2746099 (b) Aslam, M., A. De, G. Kingdon and R. Kumar (2010) “Economic Returns to Schooling and Skills - An analysis of India and Pakistan, Mimeo, RECOUP Project, Faculty of Education, University of Cambridge.
[34] The 2012 World Development Report: Gender Equality and Development wwwr.worldbank.org/wdr/
[35] Mc Kinsey (2010). How the world's most improved school systems keep getting better & World Bank (2011) Systems Analysis and Benchmarking for Education Results.  http://web.worldbank.org/WBSITE/EXTERNAL/TOPICS/EXTEDUCATION/0,,contentMDK:22710669~menuPK:282391~pagePK:148956~piPK:216618~theSitePK:282386,00.html
[36] 74000 including government aided schools (SES 2007-08)

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case?

36. Rashtriya Madhyamik Shiksha Abiyhan (RMSA) is the Government of India’s first national investment to universalise secondary education. Launched in 2008, the programme builds on the success of Sarva Shiksha Abhiyan (SSA), India’s decade-old flagship scheme for basic education. DFID and the World Bank have funded SSA as a sector-wide approach since 2003. 75% of RMSA funding is provided by India’s Union government, with India’s states making up the remainder. A breakdown of the RMSA’s main expenditure is provided in the Financial Case (page 49).
37. Initial options. The appraisal team first compared the potential to support secondary education through RMSA with a private sector option. India’s market for low fee primary schools is expanding rapidly. DFID India is supporting 13,000 places with low fee private providers in Bihar. Although the market for low fee secondary schools has not yet developed (i.e. secondary education is intrinsically higher cost), a DFID and World Bank feasibility study on public-private partnerships (PPP)[37] found that 17% of seats in private secondary schools across India were vacant – suggesting potential to expand access to some 0.85 million additional secondary students without the expense of additional infrastructure or teachers. The study also reported a willingness amongst private school providers to expand their operations into rural areas (conditional on government financial support for ten plus years).
[37] Feasibility study for an operational partnership between the public and non public sector in non-elementary education ORG Centre for Social Research 2009
38 Our scoping judged that although innovative, a DFID project with private sector providers would have high transaction costs (i.e. dealing with individual schools) and relatively small-scale impact when compared to the potential to harness private sector providers under the RMSA framework itself. India’s policy space for private sector engagement is widening. The forthcoming 12th 5 Year Plan contains a commitment to incorporate all aided schools into RMSA and builds on a past commitment[38] to create 2,500 model schools through PPP operation. A number of states with a small stock of government schools (e.g. Bihar) are keen to partner private schools through initiatives such as capitation grants. We concluded that DFID could make a strategic and scalable impact by brokering private sector engagement within RMSA, specifically by providing PPP transaction advice through technical support to state and national governments.
[38] Srivastava, P. (2010) Public–private partnerships or privatisation? Questioning the state’s role in education in India, Prachi Srivastava. Development in Practice, Volume 20, Numbers 4–5

39. Three different types of support through RMSA channels were then considered: financial assistance (FA); a package of FA and technical assistance (TA); and TA only. The last option was ruled out, as GoI had invited pooled donor contributions to a sector-wide approach in order to address a funding shortfall; and because not having a financial stake in RMSA would limit engagement on the full spectrum of RMSA delivery questions. Consequently, three main options were taken to full economic appraisal (i) an exclusive FA support and (ii) a combined FA and TA package and (iii) do nothing.

Theory of Change

40. Our theory of change has three main elements. Firstly, if DFID is to help India achieve its ambition of ‘good quality education available, accessible and affordable to all 14–16 year olds by 2017’ tackling supply side constraints (e.g., shortages of teachers and school buildings) at scale –- is essential. DFID’s financial contribution will make up a relatively modest share of GoI’s plan to rapidly expand secondary provision (i.e. 6% of RMSA’s total incremental budget and 2% of programme costs, 2012-2016); therefore DFID resources will make greater impact if pooled with GoI’s own far larger funds and those of the World Bank.

41. Secondly, removing supply constraints alone will not be enough to ensure the poorest and most disadvantaged students attend and complete school, especially the girls. Demand side interventions[11] will also be required to tackle the barriers that prevent boys and girls from entering and remaining in secondary school even when places are available. The GoI is currently devising a national secondary stipend programme to address the financial impediments that prevent the most disadvantaged gaining a secondary education. Though complementary to RMSA, this programme is being formulated outside the Ministry of Human Resource Development. Recognising this DFID India’s education portfolio includes support to non MHRD demand side initiatives. Separate business cases are in preparation for a conditional cash transfer programme targeting disadvantaged secondary girls in Odisha; a girls’ vouchers programme encouraging access and quality improvement in Madhya Pradesh; and distance teacher education support project which will operate nationwide. These programmes will complement RMSA’s predominantly supply side focus strengthening impact and VFM. These initiatives are represented by the purple boxes within the Theory of Change diagram (Figure 7).
[11] Demand side interventions help raise student/family demand for schooling - e.g. funding support to the poorest conditional on school attendance or providing free bicycles to improve access.

42. Thirdly, capacity for systemic reform in secondary education is limited, both at national and state level; and distinct capacity gaps exist between India’s low income and high-income states. At central level technical assistance to the apex institutions charged with developing a secondary learning assessment framework; National Centre for Education Research and Training (NCERT); producing annual education statistics; National University of Educational Planning and Administration (NUEPA); and the RMSA Technical Support Group (TSG) would provide the foundations for national systemic reform beneficial to all states. Strengthened data and analysis would enable more informed decisions, remedial strategies and better resource targeting. At state level, capacity building targeted at State Implementation Societies (SIS) in the most needy states could close the gap in the pace and quality of RMSA expenditure, thereby increasing the efficiency and effectiveness of RMSA spending overall.

Figure 7 and Figure 8 provide a conceptual overview of how RMSA is designed to work and the theory of change underpinning DFID support.

43. The RMSA conceptual model (figure 7) envisages the momentum for change being generated from both within the system (GoI and donor partners) and from external stakeholders (Community, Civil Society Organisations, CSOs, Private Sector, Researchers, Teachers and students). External players will be mobilised via: RMSA’s commitment to school based management; a focus on results and results publishing (e.g. the establishment of a secondary learning assessment programme) and ever increasing levels of transparency (e.g., from community monitoring of school expenditure to web based publication of evaluations and education management information data).

44. DFID’s theory of change (figure 8) looks at the need for (i) more accurate and timely data to inform planning and resource allocation; (ii) learning assessment to ascertain what is and isn’t being learnt and to provide information for remedial action: (iii) the physical resources (schools, classrooms, teachers, etc) that will expand access to the poorest; (iv) the role of key stakeholders in the education process (e.g. brokering debate between government and the private sector on school provision, engaging communities in school governance, and CSO’s in an ongoing search for higher standards).

45. Technical assistance to support capacity building is critical to fulfilment of the theory of change. DFID is the only donor partner proposing to provide technical support to the RMSA programme. DFID will contract a management firm to lead a consortium to strengthen and accelerate the delivery of the RMSA programme.

46. The expected outcome of the technical assistance are (i) strengthened implementation capacity within the most needy states; (ii) strengthened national level learning assessment and education management systems.

47. At state level an annual workplan developed by the management agent in consultation with stakeholders. This will be presented to and agreed by a level steering committee chaired by MHRD on an annual basis.

48. It has been agreed with MHRD that for the first year the priority areas of activity will focus on four thematic areas identified by state administrations as high priority - namely: (i) budgeting and planning: (ii) financial management and procurement; (iii) civil works – building design, and quality monitoring; (iv) teacher education and management.

49. Indicative state level activities could include: support in the preparation and costing of detailed annual work plans; strengthening practice in commercial tendering to secure value for money; support in the introduction of e-procurement systems; development of model secondary school and school building designs; development of appropriate build quality protocols and associated pro-forma; human resource audits to determine state teacher workforce profiles and future need and enhanced teacher education which addresses existing subject and pedagogical weaknesses.

50. National level TC support will focus on activities that benefit all states. This will include developing a management information system on which a needs based fund allocation systems can be built; a national learning measurement process to inform diagnosis and remedial action and strengthening of RMSA implementation capacity. Activities will include:

Support to MHRD’s technical support group (TSG) tasked with supporting the implementation of RMSA on an as needed basis;

Support to the National University of Educational Planning & Administration (NUEPA), for the development, implementation and use of a secondary education management information system (SEMIS);

Support to the establishment of a national secondary diagnostic learning assessment working with the National Council of Educational Research & Training (NCERT) or equivalent body as identified by MHRD;

Figure 7: Conceptual overview of RMSA and key change agents

Students
Demand side Impediments to transition from elementary school and retention and learning performance in secondary school addressed
Teachers
Strengthened teacher performance and attendance through teacher education and improved attendance monitoring
Community
Strengthened school governance and accountability through village education committees EMIS & transparency
Non State Sector
Harnessing the dynamism of the private sector and NGOs to leverage investment and access specialist expertise
Policy Makers & Implementers
Increased responsiveness to beneficiary voices, strengthened capacity for data collection, diagnosis and remedial action through actionable policy.

8.
Review of Options
51. Based DFID’s experience of successful support to SSA and RMSA’s development to date, three options were considered against their potential to deliver the conceptual model and theory of change. Considerations of impact, cost-benefit and value for money were taken into account.

Option 1: Support RMSA core expenditure from financial aid only; / Option 2: Support RMSA (core expenditure), plus contracted implementation technical assistance support. / Option 3: Counterfactual (do nothing).

Option 2, a package of financial and technical assistance for selected areas of intervention is our recommended option

52. Option 1- Provide £80 million in financial assistance to support RMSA core expenditures through sector support. This option ensures UK grant aid operates at scale, since RMSA involves all 35 States and Union Territories. In the next five years RMSA seeks to upgrade over 100,000 secondary schools, open 11,000 more, recruit over 100,000 additional teachers and increase the Gross Enrolment Ratio from 58% in 2009-10 to 78% in 2015-16. Grant aid in conjunction with support from the World Bank £300 million[12] and EU €80 million[13] has the advantage of reduced transaction costs derived from access to World Bank expertise and services (particularly financial monitoring).
[12] Exchange Rate - $ 1.66 =£ 1
[13] The EU will provide budget support to the education sector and does not plan to join RMSA as a pooling partner, alongside DFID and the World Bank

53. RMSA has been designed to allow States greater decentralised decision making. Though option one would have lower transaction costs it precludes the targeted technical support which underpins the theory of change. Evidence from SSA, as well as DFID India’s ongoing programmes in the social sectors indicate that lower levels of planning and implementation capacity in the low income states holds them back in absorbing and using central schemes well.

54. Option 2 – Support RMSA core expenditures (£60 million) plus contracted implementation technical assistance support (£20 million). In this option, DFID’s technical support would respond to key national reform issues (e.g. learning assessment, monitoring and evaluation systems, public private partnerships) as well as provide targeted implementation support to the most needy states[14] with lowest GER enrolment. Option two has the same advantages of scale, leverage, broad poverty focus and sustainability as the first option, with a facility to address the differing positions among states (see Figure 9). As with SSA, DFID will be providing technical support on behalf of all development partners. An independent analysis of DFID’s technical cooperation fund for SSA found strong rates of return[39].
[14] States below the national secondary GER will be targeted. Currently this constitutes nine states.
[39] Kingdon, G., Atherton P. 2010. Breakeven analysis of DFID India technical cooperation fund. p ix EDRM no: 2746099.

Figure 9 : Percentage Growth Needed to Reach RMSA gross enrolment target of
78% as % of total by State

Source: Lewin, K.M. (2011) Beyond Universal Access to Elementary Education in India: Is it Achievable at Affordable Costs? DFID CREATE research monograph No. 5
55. Option 3: Do Nothing. Should DFID not engage, GoI’s RMSA programme will continue. It is also unlikely that a DFID withdrawal will significantly affect the World Bank’s proposed disbursement of a £300 million loan; or that DFID’s support will be replaced by another donor. However, DFID’s flexible technical assistance is valued by the GoI and donor partners and its removal will reduce the pace of RMSA implementation. It will also likely impact on impetus to create a national learning assessment at secondary level, the speed that a secondary education management information system develops and the pace of implementation particularly in the most needy states. DFID’s contribution to policy dialogue and RMSA supervision through the six monthly joint review missions will also be missed.
A. Assessing the evidence base for each option

56. Improvement in education system performance is caused by multiple factors. Evidence that secondary education offers high rates of economic and social return particularly in the context of countries approaching universal primary enrolment has been dealt with extensively in the Strategic Case. In our Theory of Change, we rate the relative strength of the evidence for each sub component by colour code. Table 4 below rates the strength of evidence for each option by the funding channel used, compared to ‘do nothing’

Table 4: Evidence Rating of Options
Option	Evidence Rating	Detail
1. Financial aid only	Medium	There is limited evidence that increased inputs can convert into improved access to schools (enrolment). The evidence is far less conclusive when focusing on learning outcomes[40]. / There is no impact analysis of SWAP only approaches to education.
2. Financial aid provided with technical assistance	Medium-High	Economic value for money analysis in India indicates technical assistance does offer good rates of return[41] / Qualitative political economy analysis indicates donor collaboration has been effective in policy influencing and driving accountability[42] / DFID India practical programme experience suggests that technical assistance can have strong positive impact upon economy, efficiency and effectiveness[43]
3. Do Nothing	Medium	GoI implementation of SSA indicates its capacity to deliver impressive results over a long period. Determining the relative contribution of donors in this endeavour is difficult.
[40] Prichett, L., ‘People can't believe the same economy that produces 100,000 students a year in global top 10% also churns out millions with zero skills’  http://www.indianexpress.com/news/-People-can--t-believe-the-same-economy-that-produces-100-000-students-a-year-in-global-top-10--also-churns-out-millions-with-zero-skills-/872364/
[41] Kingdon, G., Atherton P. 2010. Breakeven analysis of DFID India technical cooperation fund. p ix EDRM no: 2746099.
[42] Colclough, C., De, A. 2010. The impact of aid on education policy in India, International Journal of Educational Development, 30 (2010) 497–507
[43] In 2010, DFID assistance in the urban sector helped the Government of Madhya Pradesh unlock central funds hinged on achievement of key reforms at state/urban local body level to the tune of around £84 million. This order of return is typical for our technical assistance in other states and sectors.

Evidence Generation
57. India is in a privileged position in its ability to strengthen the ‘global good’ evidence base. Research and evaluation are embedded within the RMSA results framework. This lists ten specific studies to be conducted during the lifetime of the programme: including work on: learning achievement; teacher in-service training, school management committee effectiveness, school leadership; ‘time on task’ and a public expenditure tracking exercise.

58. In addition to the work undertaken within RMSA, DFID India’s wider education portfolio has a strong evaluation and research component including: evaluation of a low fee private school model in collaboration with DFID’s South Asia Research Hub (SARH) engagement with the ‘Young Lives’ longitudinal study on childhood poverty. Evidence from these studies will inform RMSA implementation.

Likely Impact on Climate Change and Environment for Each Feasible Option

59. This intervention is regarded as a category C (No / Low potential impact / opportunity) in accordance with the ‘Technical How to Note Climate Change and Environment’ Dec 2010, p5

Table 5: Climate and Environment Rating of Options
Option/Overall Rating	Climate change environment risks and impacts, Category	Climate change and environment opportunities, Category
Option 1: Rating = C / C (medium risk and potential)	Climate change: Impact will be limited to the carbon footprint associated with the building materials / school construction. For the most part this will be a one off impact. / Environmental degradation: Most of the activities are environmentally benign. Though construction/rehabilitation of schools, and adding missing facilities (e.g., boundary walls, classrooms, toilets) could have potentially negative impacts.	While option 1 will ensure additional secondary graduates proven to be important in climate change mitigation. The absence of TC limits research and policy influence as well as civil works monitoring follow up – lessening impact. / A World Bank Economic case study concludes: “Educating young women may be one of the best climate change disaster prevention investments in addition to high social rates of return in overall sustainable development goals.”[44] / Education particularly of girls has been proven to have an impact on fertility (Bledsoe et al 1999) thereby reducing the numerical pressure on natural resources.
Option 2 = Rating C/ A (Medium risk / High Potential for climate change mitigation)	As above	As above but with enhanced potential because: (i) strengthened capacity to follow up on implementation and particularly civil works monitoring; (ii) greater opportunity to commission research and shape policy dialogue.
Option 3 = Rating C	As above – Risks remain	D Do nothing – no DFID intervention. No leverage to address issues.
[44] Adaptation to Climate Extremes in Developing countries: The Role of Education 2010: Blankespoor, B., Dasgupta, S., Laplante, B., Wheeler, D. World Bank.

Note: risks and opportunities are categorised above on the following scale - A: high potential risk/opportunity; B: medium/manageable potential risk/opportunity; C: low or no potential risk/opportunity; and D: core contribution to a multilateral organisation (MO).

B. Costs and benefits of each option

60. The primary beneficiaries of RMSA will be an estimated 10.1 million additional secondary school students who will access an improved quality of education. As detailed in the strategic case, improved access to secondary education will deliver both individual and social returns including economic, social and intergenerational health benefits.

61. Second tier beneficiaries will be teachers, educational administrators and school management committee members who will receive training support. Commercial beneficiaries will include civil works contractors (up to 50% of expenditure in the early years will focus on construction), contracted service providers e.g. auditors, training institutions, educational materials providers and management agents.

62. In line with other economic appraisals[15] DFID India has taken an incremental approach[16] to estimate costs and benefits.  This approach, i. calculates the historical growth in enrolment and completion rates over the last five years and projects forward the level they would reach over the programme period if this pre-existing trend was continued; and ii. calculates the accelerated rates that could be achieved with both new financial resources to the sector (from GoI, World Bank and DFID) and improved efficiency in the sector as a result of technical support from DFID.  We calculate the programme benefits as the difference between these two trends (i.e. the additional number of students enrolling and completing over and above what would have been expected with current rates of improvement), and the programme costs as the new resources, both financial and technical, required to achieve this.
[15] DFID Bangladesh Primary Education Programme
[16] The DFID attributable figure derived from the economic appraisal will be larger than the figure generated under the March 2012 FCPD guidance for standardised results reporting because (i) the FCPD  requirement is for an annual calculation not cumulative results over the programme period as per the economic appraisal; (ii) the economic appraisal factors in the additional impact of technical support; (iii) FCPD guidance requires attribution against the total secondary education budget and not total government expenditure on RMSA only.

Cost Benefit Framework (refer to Cost Benefit Analysis spreadsheet in Annex 1)
Option 1

Estimated incremental resource costs of the intervention:	Rs. 7409 crore (£988 million)

Estimated incremental benefits of the intervention:	Rs. 12727 crore (£1697 million)
Option 2
Estimated incremental resource costs of the intervention:	Rs. 7409 crore (£988 million)
Estimated incremental benefits of the intervention:	Rs. 18234 crore (£2431 million)
Option 3

Estimated incremental resource costs of the intervention:	Rs. 6877 crore (£930 million)

Estimated incremental benefits of the intervention:	Rs. 8361 crore (£1115 million)

Table 6 below presents a summary of benefits of each option (for detail refer to Cost Benefit Analysis Spreadsheet at Annex 1).

Table 6: Summary of Benefits
Option	Description of who benefits, and how and when they benefit	Quantification of benefits of the total programme (units)	Monetary value of benefits of the total program (not discounted)
1	Higher benefits accruing as a result of higher enrolment eventually leading to higher completion even with the same completion rate.	10.15 million additional enrolment of which 6.03 million complete	£2954 million
	Higher benefits accruing as a result of higher completion leading to reduced child mortality	2.96 million additional girls completing secondary education	£112 million
2	In addition to the benefits above, Option 2 will have following benefits:
	1. Wage gains as a result of reduced child (under-5) mortality due to secondary education;	3.64 million additional girls completing secondary education / (2.96m+ 0.68m)	£87 million
	2. Wage gain as a result of additional higher completion rate in secondary education	Additional completion at secondary level is 1.61 in addition to 6.03 under option 1 (a total of 7.64 million)	£622 million
	3. Higher earning as a result of better learning outcomes		£384 million
	4. Efficiency gains in RMSA spending due to TA support enhancing effective implementation		£30 million
3	Higher benefits accruing as a result of higher enrolment eventually leading to higher completion even with the same completion rate.		£2332 million

63. Our appraisal indicates targeted technical assistance delivered results over and above option one (financial assistance only) in terms of raised completion rates (resultant from making schooling a more rewarding experience for students) and higher levels of learning of those who complete. These benefits are attributable to (i) improved opportunities to learn resulting from better trained teachers, better data - enabling better resource targeting - including teacher utilisation; (ii) the benefits not being confined to DFID’s FA expenditure only but having an impact across the whole RMSA investment. The evidence for the enhanced impact from efficiency is derived from DFID India experience with SSA as well as broader and DFID India and international experience.

Political Risks and Opportunities
64. GoI would support either options 1 or 2. From an institutional perspective Option 1 provides limited opportunity to support strengthening of management and implementation. The political appraisal therefore advises for Option 2, FA with additional TA support.

Option 1: financial aid for core RMSA expenditure
65. There is political consensus on the importance of education in ‘inclusive growth’. State governments are enthusiastic that RMSA will provide for the first time significant resources for secondary education, easing their financial burden in responding to growing secondary schooling demand.

66. The most recent and reliable data suggests that while government schools accounts for less than 40% of school places, between 46%[45] to 62%[46] of secondary enrolments are in government schools). Figure 10 below highlights that the vast majority of students in lower income states (including almost all N.E. hill-states) are enrolled in either government or government-aided (Grant-in-Aid) schools.
[45] Secondary Education MIS
[46] NSS D. Sankar, 2011: 37

Figure 10: Relative Shares of School Enrolment by School Type.

Source: D. Sankar, World Bank 2011

Option 2: Financial aid plus technical assistance for implementation in the most needy states

67. Although RMSA is a Centrally Sponsored Scheme and will use funding to incentivize reforms, enhancing the quality of education service delivery is the domain of the states. A dual approach of FA + TC support at central level and state level which puts in place: a needs based formula; and capacity development in data collection and use to promote informed policy dialogue and remedial action is the optimum solution.

68. GoI officials continue to show respect for UK technical cooperation in education. Doing nothing could have negative ramifications for wider bilateral education relations including HMG collaboration through the UK India Education and Research Initiative.

Institutional Risks and Opportunities
69. RMSA will be the first central scheme for secondary education. Institutional arrangements and capacity in lagging states are weak and require additional support to ensure they secure the benefits of the programme from the outset. The institutional appraisal therefore supports Option two, FA with additional TA support over other possible alternatives.

Option 1:

70. This proposal limits opportunities to provide technical support to strengthen systems and accelerate implementation as set out in the theory of change.

Option 2:
71. Option two would provide needed resources to support the development of a culture of data analysis and use to inform policy reform and effective resource targeting. Support is regarded as most influential in:
- Building the capacity of administrative cadres to guide and manage RMSA.
- Supporting the convergence of MHRD’s seven other schemes into RMSA.

Brokering partnerships with different ministries (Ministry of Social Justice, Minority Affairs, Youth Affairs, Women and Child) in order to strengthen RMSA impact.

Introducing a national learning assessment which reports on system performance (rather than examinations which report on individual mastery of a curriculum).

Strengthen School Development Management Committees (SDMCs).

Option 3: Do Nothing

72. Failure to invest in RMSA would preclude opportunities for DFID to engage in areas which have significant policy dialogue / transformational change potential such as PPPs and strengthening learning.

Social Risks and Opportunities

73. To help bridge substantial socio-economic gaps, Option 2 is recommended as the most appropriate. Any programme which aims to improve secondary education in India must be attuned to the striking gender and social disparities that affect not only students’ participation in secondary schooling but also the quality of teaching they receive once in the classroom. There is a 30 percentage point gap in participation between students from below the poverty line and non-poor families. These gaps become even starker in India’s low income, low enrolment states such as Bihar, UP, MP, Orissa.

74. SSA provides evidence that disadvantaged groups will make use of free educational opportunities where provided. SSA technical assistance has been effective in promoting equitable classroom practices which international research suggests is important in addressing prejudice, reducing female drop out, and ensuring higher completion, particularly for the girl child.[47]
[47] Lloyd, C (2011) Evidence Paper for the Girls’ Education Challeng Fund (Draft)

75. RMSA interventions – more and better facilities, water and sanitary provision, recruiting additional female teachers combined with state governments’ own schemes such as bicycles for girls, transport vouchers, and residential hostels will help overcome impediments disadvantaged children face (including distance from school, a lack of transport facilities and maintaining the safety and security of girls).

Option 1:

76. FA only support of RMSA would not give DFID the opportunities for evidence gathering, policy dialogue and capacity building.

Option 2.

77. The addition of TC support provides DFID greater opportunity to strengthen systems improvement in favour of the disadvantaged. Through such activities as: development of a needs based allocation formula; support in disaggregated data collection including on learning outcomes and improving the training of teachers around gender and inclusion.

Option 3:

78. Should DFID not invest in RMSA it would forego an opportunity to shape a large scale national programme in favour of the poor. Non-investment would also compromise DFID’s overarching targets for reaching disadvantaged secondary girls.

Climate and Environment Risks and Opportunities.

79. To effectively address environmental concerns, Option 2 is proposed as the most effective option. RMSA will involve significant amounts of civil work. Areas of potential environmental impact range from new build work potentially involving change in land use and requirements for additional infrastructure, roads, electrification, drainage etc. Conversely refurbishment also offers opportunities for retrofitting for seismic resilience and adding features such as communal rainwater catchment and fuel efficient catering facilities.

80. A detailed environmental assessment has been conducted and covers but is not limited to the following aspects: (i) integration of environmental principles during site selection, design and construction; (ii) improve operation and maintenance of the school buildings; and; (iii) expand and augment the current good practices with regard to environment, health and safety aspects. The assessment will inform an Environmental Management Framework (EMF) for RMSA. The framework will be a dynamic document and updated in light of changes in law, operational procedure and best practice.

Civil Works / Infrastructure

81. Under RMSA the GoI intends to construct 11,000 new schools, refurbish a further 100,000 schools and construct an additional 88,500 classrooms. DFID is following World Bank operational procedures which cover both environmental assessment and resettlement. These require for GoI to ensure due process has been followed in the procurement and development of public buildings and that no forced resettlement has occurred. Decisions over school sites and school design rest with state government but must comply with national legislation. National building regimes will be followed with quality assurance being undertaken by state agencies.

82. State government procurement procedures legislate for contractors to include environmental management to ensure that sites are kept safe and clean. However the veracity with which these are conducted is variable. The GoI has agreed to an annual third party review of a 20% random sample of all civil works contracts commissioned by the development partners. This would cover all states within a three year period.

83. Although the environmental appraisal does cover issues of civil works and infrastructure it does not go into detailed specification of building standards. In the recent review mission DFID expressed concern at the level of understanding on school expansion planning, construction standards and the extent to which testing regimes and capacity are equipped to oversee upgrading of existing schools - in particular where this involves addition of extra storeys to school buildings (where the adequacy of foundations are of critical importance).

84. In response to concerns DFID will commission a study within the first six months of support to map current practice and assess the veracity of compliance mechanisms. This will draw heavily on the DFID guidance note “Delivering Cost Effective and Sustainable School Infrastructure.” The study will also explore how value for money can be leveraged through effective competition between private and state construction concerns. Recommendations from the report will inform DFID state level technical support as well as further national studies as required.

Option 1:
85. DFID would be supporting an important educational intervention – but its ability to raise awareness and engage on issues of environmental sustainability would be limited.

Option 2
86. The addition of TC gives greater opportunity for monitoring civil works, commission research and respond to capacity building in support of implementation of the environmental management framework.

Option 3
87. Failure to invest in RMSA would preclude opportunities for DFID to engage in areas which have significant policy dialogue / transformational change potential.

Balance of Costs and Benefits

88. The economic case for the RMSA is based on the premise that improving access, higher retention and completion in secondary education, particularly for the girl child has a significant impact on income and productivity. This is derived through better employability and improved health outcomes for women and children, which in turn leads to reduced child mortality.

89. The economic appraisal covers the following options (i) financial assistance to cover RMSA core expenditures (ii) financial assistance along with technical assistance to GoI and selected low enrolment states to improve awareness, enrolment, retention and completion at secondary level, particularly for the girl child; and (iii) the counterfactual (do nothing).

90. The economic appraisal finds option 2 as the most favourable option. This option has a Net Present Value (NPV) of £1443 million at a discount rate of 10% and a benefit cost ratio (BCR) of 2.46. The sensitivity analysis indicates that the benefits exceed the costs even when the programme effectiveness is lowered by 50% and thus the investment is robust.

Table 7: NPV and BCR compared

(Figures in £ million) / Present Value of Incremental Benefits	Option 1	Option 2	Option 3
	1697	2431	1115
Present Value of Incremental Costs	988	988	930
NPV at 10% Discount Rate	709	1443	185
BCR at 10% Discount Rate	1.72	2.46	1.20
EIRR (%)	13%	23%	4%

91. Option 1- This option proposes to use DFID funds to contribute to the RMSA budget of the Government of India to address the requirements of meeting the demand for secondary education in India. DFID’s contribution will be £80 million or 6% of the total incremental cost of the program.

92. The monetisation of attributable benefits includes DFID’s contribution towards improved gross enrolment ratio in secondary education, particularly for girls. Higher enrolment, in turn, is expected to lead to a raised completion rate of students in secondary education. Evidence suggests completion of secondary education leads to higher employability and wage earning potential when compared to upper-primary level graduates. This option has a BCR of 1.72 and an economic internal rate of return (EIRR) of 13%, thus out-weighing the benefits against the costs.

93. Under this option, the total program will enrol an additional 10.1 million students at the secondary level. £80 million in financial assistance to RMSA, i.e, the GoI’s secondary education program would enable DFID to enrol an additional 0.61 million students at the secondary level. However, it will be difficult to ensure the subsequent benefits of higher completion particularly for girls, better learning outcomes and efficiency in implementation of the government sponsored secondary education program without the corresponding technical assistance.

94. DFID intervention through this mechanism (only financial assistance) is expected to help the secondary education program of the Government of India accrue additional gains to the tune of £2954 due to wage gain as a result of higher gross enrolment (GER) ratio in secondary education with the assumption that the current completion rate of 59.4% at the secondary level in India continues. In addition, there will be benefits accruing as a result of reduced child mortality for those completing secondary education to the tune of £112 million.

95. Option 2- Under this option, DFID will contribute to provide financial assistance to the RMSA budget of the Government of India to improve the quality and coverage of secondary education with a focus on girl child education (as in Option 1).

96. In addition, this option also includes provision of technical assistance to Government of India and selected low-enrolment states. Total DFID contribution will be £80m (£60m financial assistance and £20m technical assistance) or financial assistance of 6% of the total incremental cost of the program.

97. As with Option 1, the financial assistance will help improve the gross enrolment ratio at the secondary level in addition to an improved completion rate even with the existing completion rate. In addition, technical assistance at the central level will help improve the data management and learning assessment. This is expected to improve the learning outcome performance and better targetting of program funds at the grass root level. At the state level, the TA support will help improve overall implementation efficiency.

98. The total program will enrol an additional 10.1 million students at the secondary level. £60 million in financial assistance to RMSA would enable DFID to enrol an additional 0.61 million[17] students in secondary school. There is strong evidence from SSA that DFID investing alongside GoI and other donors can support reforms in such areas as sub-sector planning and monitoring, public financial management and national learning assessment systems.
[17] DFID's £60 m financial assistance is proportionately 6.1% of the total new resources for secondary education that RMSA implementation will require (i.e. total GoI, World Bank and DFID financial assistance to RMSA), i.e, £60m (DFID FA)/ £988m (Total Incremental Cost).  Therefore 6.1% percent of enhanced enrolment in secondary education is attributed to DFID. The total incremental benefit arising out of enhanced enrolment is calculated to be the difference between what would have been expected with the pre-existing trend and the accelerated trend that we forecast can be achieved due to the RMSA programme. It is assumed that as a result of RMSA intervention, the GER will grow at close to 8% per annum (as compared to a historical annual average growth in gross enrolment at secondary level of 6.52%). The additional 1.5% point growth is assumed on the basis of DFID experience in SSA, in which, over the project period, has seen a 1.5% annual average increase in enrolment.

99. DFID intervention through this mechanism (a combination of technical and financial assistance) is expected to help the secondary education program of the Government of India secure the following gains. These are in addition to the £2954 million due to higher enrolment and £112 million due to reduced child mortality that was estimated to be achieved had DFID gone ahead with the Option 1.

- £87 million due to wage gains as a result of reduced child (under-5) mortality as a result of attainment of secondary education;
- £622 million due to wage gain as a result of higher completion rate;
- Higher earning of £384 million as a result of better learning outcomes; and
- Efficiency gains in RMSA spending due to effective implementation leading to £30 million of higher spending.

Option 1 vs. Option 2

The table below compares the benefits accruing through both options.

Table 8: Estimated impact of programme and attribution to DFID

	Total programme	Attributed to DFID Under Option 2	Attributed to DFID Under Option 1
Incremental costs (£ million)	988	80	80
Incremental benefits include:
High wage earning due to reduced child (under- 5) mortality (£ million)***	199 (112 mn with Option 1)	12.13	6.83
High wage earning due to enhanced GER (£ million)	2954	180.19	180.19
High wage earning due to enhanced completion rate (£ million)	622	37.94	29.13
High wage earning as a result of better educational outcomes (£ million)**	384	23.42	0.0
Efficiency gains in RMSA spending (£ million)**	30	1.83	0.0
Total number of additional enrolment (million)	10.15	0.61	0.61
Total number of additional completion (million)	7.64 (6.03 million under Option1)	0.47	0.37
Total number of additional girl child completion (million)	3.64 (2.96 million under Option 1)	0.22	0.18
Benefit Cost Ratio		2.46	1.53
Economic Internal rate of Return		23%	13%

Note: DFID attribution is prorated to DFID’s share of financial assistance in the total incremental cost (minus the technical assistance, i.e, 6.1%) .
 **: These benefits will accrue only if the RMSA program of the GoI is supported through the Option 2, i.e, a combination of financial and technical assistance.
***: A part of these benefits will accrue even under Option 1 for those girls completing secondary education as a result of higher enrolment.

Break- even Analysis

100. A break-even analysis was done to determine the optimum TA and FA break-up to achieve the maximum number of enrolment, completion and other benefits expected from this intervention. Reducing the TA by £10 million would completely erode the benefits arising as a result of (1) better learning outcomes and (2) higher girl child completion due to focussed TA at the state level. On the other hand, this would add marginal benefits as a result of addition to the RMSA corpus through increased enrolment.

101. Analysis shows that reducing the TA allocation by £10 million and adding it to the RMSA corpus would reduce the BCR of the program to 2.33. Moreover, the total number of students completing secondary education would decrease to 7.02 million and number of girls completing secondary education would decline to 3.46 million. A further reduction of the TA to £5 million and adding it to the RMSA corpus would completely erode the benefits from the technical assistance except for the public financial management support at the national level. This reduces the BCR to 2.25 despite additional enrolment to the tune of over 4 million leading to additional completion.

102. The alternative of enhancing the TA support to £30 million was also analysed. Since the project is for a 4 year period, the absorptive capacity of TA to feel its impact at the grass root level would be an issue of concern. Analysis shows higher completion of both boys and girls as a result of the additional TA to the tune of 0.05 million. However, the additional enrolment is affected due to reduction in the RMSA corpus by about 1.5 million. A further reduction to the RMSA corpus would further reduce the enrolment at the secondary level leading to reduction in retention and completion which accounts for the highest share of the monetised benefit. Consequently, the BCR goes down to 1.84.

103. The graph below plots the proportion of the technical assistance (TA) to the total RMSA budget on the horizontal axis and the BCR of the RMSA programme on the vertical axis. This shows that £20 million which is the technical assistance commitment under the proposed option and accounts for 25% of the total DFID’s RMSA contribution has the highest BCR.

Monetising the Benefits

104. Major benefits of the program are estimated to accrue from the higher enrolment ratio at the secondary level. It is assumed that the intervention will help improve the annual growth in enrolment ratio in secondary education from the historical 6.52% to almost 8%. Higher enrolment with the same completion rate[18] at the secondary level is expected to lead to more number of students completing secondary education. The benefits accruing out of higher completion rate (due to higher enrolment) have been monetised using the NSSO 2004-05 report which estimates 25% higher wages for a secondary graduate compared to an upper primary graduate. The additional wages estimated to be earned by a secondary graduate for the respective years of appraisal have been inflation-indexed based on the last 5 years annual average rate of inflation as per the wholesale price index in India.
[18] The National Sample Survey Organisation (NSSO) of India does quinquennial survey every 4 years on employment- unemployment situation and wages based on level of education. NSSO 2007-08 provides the all India completion rate of 59.4% at the secondary level.

105. The financial assistance is expected to improve enrolment and hence completion even with the existing completion rate, in addition to reduced child mortality for those completing secondary education. It is assumed that the technical assistance will improve the completion at the secondary level by 1% point. The assumption of additional 1% is based on the low base of completion at the secondary level. This is expected as a result of the technical assistance in the low enrolment states to retain and support children to complete education at the secondary level. A similar methodology as referred to earlier has been used to monetise the benefits accruing as a result of higher additional completion expected to be accrued as a result of the technical assistance to the selected states. Due to the lack of availability of state level completion rate figure, the all India completion for 2007-08 from NSSO has been considered for this purpose, though the technical support under the current intervention remains confined to the neediest states.

106. There is evidence, such as the World Bank study of the Secondary Education Sector[48], which indicates that there are other additional benefits as a result of attainment of secondary level education, particularly for girls. The economic appraisal assumes that attainment of secondary education while enhancing the wage rate will also improve wages as a result of better learning outcomes at the secondary level. In addition there are additional gains in terms of reduced child mortality for women who have attained the secondary level of education. An additional 2% point faster decline in child mortality has been assumed to estimate this benefit. This is based on the World Bank Report referred to above. It analysed from the data in the National Family Health Survey in India in 2007 that attainment of secondary level education reduced under- 5 mortality by almost 17 per 1000 births. There is substantial other evidences to this end. However, the NFHS data for India has been used for the purpose.[19]
[48] Secondary Education in India: Universalising Opportunity, January 2009, HDU, South Asia Region, Document of the World Bank.
[19] “An additional year of schooling reduces the probability of child mortality by 5 to 10%”- Shultz, P (1993) “Mortality Decline in the Low- Income World: Causes and Consequences”: AER 83 (2) 337-342. “4 million lives of children under 5 years old were saved due to female education”- Gakidou, E; Cowling, K; Lozano, R; Murray, CJL; “Increased Educational Attainment and its Impact on Child Mortality in 175 Countries between 1970 and 2009: A Systematic Analysis; lancet 2010; 376, 959- 94.

107. The estimation of additional benefits as a result of the attainment of secondary education by a girl is based on the Secondary Education management Information System (SEMIS) data for 2009-10 on the proportion of girls completing secondary education. 44.6% of the total number of students attaining secondary level of education were girls in 2009-10. It is assumed that each girl attaining secondary education would give birth to 2 children during her life time. Assuming a productive life expectancy of 18 years based on a labour entry age of 15 years, each child has been assumed to work for at least 11 years (assumed to be the life span of jobs in the informal sector in India). The additional wage earning due to reduced child mortality has been estimated based on a minimum wage of Rs.148.53 for at least 100 days of work for 11 years for the additional number of children born (due to reduced child mortality). A labour force participation rate of 41% has been assumed to arrive at this benefit. Studies have revealed that providing girls with an extra year of schooling increases their wages by 10 to 20%[49].
[49] Psacharopoulos, G. and Patrinos, H.A. (2002): Returns to Investment in Education: A further update World Bank Policy Research Working paper Series 2882.

108. DFID technical assistance to selected states is expected to train the teachers for better learning outcomes at the secondary level. The World Bank study of the secondary education sector in India revealed that better learning outcomes at the secondary level leads to higher wage earning. The study shows that 1 standard deviation improvement in learning outcomes at the secondary level leads to 18% increase in wages. On a conservative note, this appraisal assumes that there will be 0.75 standard deviation improvement in learning outcomes which is expected to lead to a 10-13% increase in income. The conservative assumption is driven by the fact that the efficacy of TA in learning outcomes at the secondary level is yet to be tested. Finally, the support for public financial management is expected to improve efficiency in spending by about 5% which has been estimated as one of the benefits accruing out of the technical support.

109. Option 3 assumes the programme continues without DFID support and this generates a BCR of 1.20 – the programme effectively functioning as a fully government funded (with additional support from the World Bank) mechanism for financing secondary education. Assumptions remain same as discussed under Option 1. The option has an economic internal rate of return of 4%, significantly lower than the Option 1 that commits only financial assistance to the RMSA core framework. However, it is substantially lower than the BCR obtained for Option 2. This option has, significantly lower than the EIRR of the proposed option, i.e, the Option 2.

Sensitivity Analysis

110. Sensitivity analysis has been used to assess the worst case scenario for all the 3 options, i.e., project benefits reduced by 50% for all the 3 options with the same level of costs. The results indicate that economic benefits outweigh the costs even if the programme effectiveness is reduced by more than half for option 2 only, i.e, the option which is a combination of technical support and financial assistance to Government of India through the RMSA framework. Moreover, only Option 2 has a positive NPV (and an EIRR of 5%) even if the program runs at 50% effectiveness.

Table 9: Sensitivity analysis
Option 1	Option 1	Option 2	Option 3
Figures in £ million)
Present Value of Incremental Benefits	848	1216	557
Present Value of Incremental Costs	988	988	930
NPV at 10% Discount Rate	-139	228	-373
BCR at 10% Discount Rate	0.86	1.23	0.60

Sensitivity to the assumptions of higher enrolment and completion
111. Further sensitivity analysis has been conducted to do an analysis of the risk of a lower enrolment and completion compared to what was assumed as a part of the economic appraisal for the proposed option. In other words, how sensitive are the program benefits to a lower enrolment and a lower completion rate at the secondary level than that has been assumed. In case, the program intervention fails to achieve the growth of enrolment increase of 8% per annum and manages to achieve just 7% per annual growth in enrolment which is just 0.5% higher than the historical increase of enrolment at the secondary level, the benefits of the proposed program intervention under option 2 will still outweigh the costs with a BCR of 1.05 with an economic internal rate of return (EIRR) of 1%.

112. On the other hand, in case the proposed program intervention fails to achieve the additional 1% completion rate at the secondary level, the program benefits still outweigh the costs with a BCR of 1.94 and an economic internal rate of return of 16%. Thus, it shows that the program benefits are more sensitive to the changes in enrolment than completion. Hence major focus should be initially given to enhanced enrolment at the secondary level as enrolment has suffered due to lack of infrastructure. This should be followed by enhanced focus on higher completion and improved learning outcomes during the later years.

Preferred Option

113. Option 2 i.e. a combination of technical support and financial assistance is the preferred option. It has a Net Present Value (NPV) of £1443 million at a discount rate of 10%, compared to the NPV of £709 million and £185 million for options 1 and 3 respectively. Option 2 has a BCR of 2.46, higher than 1.72 and 1.20 for the Options 1 and 3 respectively. EIRR for Option 1 is 23% compared to 13% and 4% for Options 1 and 3 respectively.

Climate and Environment Assurance Note

114. This intervention is regarded as a category C (No/Low potential impact / opportunity). Table 10 below details the sensitivity analysis as per p 6 of the How to Note 2010.

Table 10: Climate Environment Sensitivity Analysis

Negative Impact
Are the objectives of the project likely to be at risk from:	Climate change: The direct and indirect consequences of climate change and associated environmental degradation will over time impact upon educational service provision (supply side) and school uptake, retention (demand side) and learning performance. However within the time frame envisaged the overall objectives of this intervention are not at risk. / Environmental degradation: While overall objectives are not at risk from environmental degradation – in some locations e.g. semi arid areas and coastal areas – flooding/ deterioration in crop yields would likely impact on family income in general and girls domestic work burden in particular. This would likely impact on school enrolment, attendance and performance. In addition in some areas may experience an increase in the incidence of malaria – with associated impact on student and teacher attendance.
Is the proposed intervention likely to contribute to:	Climate change: The impact of this intervention will be limited to the carbon footprint associated with the building materials associated with school construction. For the most part this will be a one off impact. / Environmental degradation: Most of the activities to be financed are environmentally benign. However, some programme activities, including construction/rehabilitation of schools, and adding missing facilities (e.g., boundary walls, classrooms, toilets) could have potentially negative impacts, which will need to be monitored and managed effectively.
Positive Impact
Could the outcomes of the intervention be enhanced by:	Improved management of natural resources? The intervention has no direct bearing on immediate natural resource management. Improved schooling particularly science education can contribute to improved environmental management / behaviour change
Could the proposed intervention help:	Tackling climate change? The intervention has no direct mechanism to tackle climate change.
	Tackle climate change? Yes. / India specific research indicates education to yield strong investment returns on mitigation and disaster reduction[50]. More generally research indicates strong performance in science education and awareness of global environmental problems tend to go hand in hand, and both are associated with a sense of responsibility supporting sustainable environmental management. Conversely, weak performance in science is associated with lower awareness of environmental problems. Failure in scientific education will mean less widespread – and less informed – public debate on issues such as climate change and wider environmental problems. UNESCO (2008). Education For All Global Monitoring Report 2009 p37. / Education particularly of girls has been proven to have an impact on fertility (Bledsoe et al 1999) thereby reducing the numerical pressure on natural resources.
	Improve environmental management? Yes: Focus will be placed on optimising the design of school infrastructure to optimise use of resources, including water catchment and storage, energy efficiency, in lighting and cooking, and to protect against environment damage for instance installing protective plinths in flood prone areas. The provision of sanitation facilities should reduce environmental contamination and improve public health
	Reduce vulnerability and / or build resilience and adaptive capacity to climate change / environmental degradation and shocks? Yes: In the short term school buildings can be designed to incorporate community facilities – e.g. storm shelters for cyclone prone areas – and provide some degree of community water catchment and storage facilities. Provision of sanitation facilities will help reduce environmental contamination and could offer community level use during disasters (e.g. cyclones or floods). Schools have also been used to generate the inter-generational transfer of knowledge on issues of environment causes, consequences and responses to environmental degradation.
[50] Adaptation to Climate Extremes In Developing Countries: The Role of Education Policy Research World Bank. 2010

Value for Money:

115. DFID India has already developed a matrix of value for money indicators as detailed in Table 11 below. This includes experimental work on which DFID India is collaborating with the centre to develop indicators for the whole of DFID's portfolio.  These include: (i) ‘Opportunity to Learn’ sample study which will quantify the number of days lost to learning from the official school year as a result of: official / unofficial school closure, teacher absence and student absence. (ii) A study to quantify the cost to achieve a minimal level of learning (e.g. basic addition / reading). It is also proposed to monitor the ratio of average salary cost of private and government teachers relative to GDP per capita. In many instances changing the unit costs variables will be beyond the control of DFID (e.g. in setting teacher salaries etc. that are often regulated by the Ministry concerned of the Government of India). The utility of new measures rests in their use in shifting the focus of policy dialogue from inputs to outcomes.

Table 11: Education VFM Indicators

Effectiveness	Quantitative Assessment	Qualitative Assessment
Additional number of children enrolled at secondary level	Increase in enrolment rate	Analysis of increased enrolment and attendance
Additional number of children complete secondary school	Increase in completion rate at secondary level
Learning levels of children at secondary level are enhanced	Cost per student to achieve grade appropriate learning level (in language and math): / Improvement in grade 10 pass rate for secondary	Feedback mechanism established from national assessment to learning enhancement strategies at state/district level; external evaluations for state-wide learning enhancement programmes
Efficiency	Quantitative Assessment	Qualitative Assessment
Increase in the number of qualified teachers at secondary level	Increase in the number of teachers qualified through the Teacher Eligibility Test / Increase in the number of trained teachers (pre-service) / Reduction in pupil-teacher ratio	Systems & processes put in place or streamlined for recruitment; quality of teacher training
Improved teacher in-service provision	Increase in number of teachers trained through in-service training / Improved monitoring of participant satisfaction with training provided	Quality of in-service training improved
Improved spending of RMSA funds in states	Decrease in fiduciary risk rating (overall/specific) between intervention time period / Increase in value of e-procurement of works, goods and services	Quality of interventions undertaken to manage fiduciary risks; Systems & processes put in place for improving procurement
Economy	Quantitative Assessment	Qualitative Assessment
Cost of procuring works, goods or services (through financial assistance	Cost per unit of infrastructure built (classroom) and cost per unit of text books / Cost per unit of qualified and trained teachers (salaries at secondary level) / Cost per child (secondary)	Quality of works, goods and services procured
Teacher cost	Expenditure on teacher costs as a % of overall budget / Ratio of average private and government school teacher salary to GDP per capita	Analysis of relative cost spent on non-teacher learning inputs

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / 116. DFID will undertake a direct commercial procurement through the Official Journal of European Union (OJEU – EC directives on public procurement) procedure to select a management firm to manage the RMSA Technical Co-operation (TC) funds. This firm will be tasked with supporting (i) the national institutions responsible for learning assessment (NCERT), data management (NUEPA) programme implementation at national level (MHRD Technical Support Group) and implementation in the most needy states (RMSA state implementation societies).
B. How does the intervention design use competition to drive commercial advantage for DFID? / 117. The competitive tendering process will be used to generate an innovative technical assistance model. In response to the ToRs competing parties will be expected to (i) lay out detailed responses and provide robust methodologies in their proposals which demonstrate what they intend to achieve, how and by when; (ii) build a strong consortium of international and national sub contractors with the requisite technical and field experience to deliver to expectations. / 118. Consolidating technical assistance tasks will raise value and thereby raise international interest and stimulate competition to deliver a strong international / national consortium. An integrated TC service will better exploit synergies between activity streams. / 119. To get best value for money, results and impact, the contract(s) for managing technical co-operation funds will be output-focussed with payments linked to achievement of agreed outputs / milestones which are in turn linked to the logframe. / 120. The TORs for the assignment will be written in "performance" terms, which focus on the function of the product or the output of the service required and encourage suppliers to propose innovative while workable solutions.
C. How do we expect the market place will respond to this opportunity? / 121. The total commitment for technical cooperation support is £20 million. Competitive bidding will determine the final size of the services contract; however we estimate this to be between 12 and 18% of total commitment. We, therefore expect high levels of interest for this opportunity from both domestic as well as international firms. We received 14 expressions of interest for the tender for the management consultants for technical assistance to basic education (Sarva Shiksha Abhiyan). / 122. This opportunity will provide competition amongst national (Indian) and international bidders. We will include suitable criteria such as ‘use of national consultants’ and ‘transfer of knowledge to the local market’ so that local firms get opportunities to participate in this assignment. We will make it explicit that we do not feel one provider alone can provide the breadth of services required and that a consortium led by a head contractor is the preferred modality. / 123. In order to encourage the widest range of bidders and to provide an opportunity for interested parties to meet and discuss potential collaborative opportunities we will organise a ‘meet the market’ in DFID India. This will entail DFID providing a presentation on services required, fielding bidder questions as well as a ‘free form’ opportunity for interested parties to meet each other (with the view of encouraging strong consortium).
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / 124. The cost of providing support may be affected by a number of drivers, including but not limited to: nationality and foreign exchange rates, supplier fee rates, travel expenses, accommodation, documentation and other operating costs. / 125. Outputs of the contract will be linked to project outputs. An external DFID funded independent evaluation of the impact of DFID’s TC component will be commissioned to run alongside the broader RMSA’s six-monthly monitoring cycle. TC fund operations will be under the governance of a joint GoI and DP steering committee who will review progress. In addition, DFID will conduct regular review of performance against milestones agreed in the contract. Appropriate safeguards and sanctions to ensure satisfactory performance will be written into the contract. Payments will be linked to agreed deliverables or achievement of contract outputs.
E. What is the intended Procurement Process to support contract award? / 126. Competitive procurement process will be the underlying principle to support contract award. OJEU process will be used for procuring technical and management services for the TC funds. Where relevant expertise is available, call down contracts may be used from DFID’s Human Development Resource Centre or other resource centres to reduce transaction costs.
F. How will contract & supplier performance be managed through the life of the intervention? / 127. A performance based terms of reference will be used as the basis for a contract with the management firm. Contracts will have an inception report which will set out the detailed implementation strategy, a work plan linked to anticipated results and outputs in the log frame, with measurable indicators, under each output. The suppliers will be expected to submit reports at regular intervals providing summaries of progress against the work plan deliverables and log frame outputs. Regular review meetings and interactions with the supplier will be held to ensure satisfactory performance. / 128. The design of the technical support to RMSA will require the supplier to develop a comprehensive monitoring framework. This will ensure the supplier takes ownership of key performance indicators and service level agreements, which will be agreed in advance with the state governments, from the outset of the programme and form the basis not only for management of the programme by the supplier but also for performance-based management of the supplier by DFID. The overall impact of the technical support fund will be subject to an ongoing impact evaluation – with results reviewed on a six monthly basis. / 129. The technical assistance services that DFID is purchasing are intended to build the capacity of state education departments and national education apex bodies. The effectiveness and value for money of these services relies on partners’ commitment to and ability to absorb the help available. Regular trilateral meetings will be held with partners and suppliers, especially in the contracts’ early stages.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / 130. RMSA is a national programme and a sub-sector wide approach with minority share of pool financing from the World Bank and DFID. The main items to be procured are building and infrastructure, teaching materials, textbooks, computers, teaching services and consultant and non-consultant services. A tripartite MoU will be signed to formalise the implementation arrangement including procurement between GOI, World Bank and DFID. Following the Indian Government’s procurement procedures is both appropriate and has precedent. For RMSA programme, the Ministry of Human Resources and Development, GoI will procure good and services following guidelines set out in the RMSA Manual for Financial Management and Procurement (FM&P) (being finalised), developed by the National Institute for Public Finance and Policy (NIPFP), in collaboration with MHRD and the World Bank and DFID. These procedures adhere to international good practice and the same will be referred to in DFID’s exchange of letters with Government of India. / Procurement Arrangements / 131. Procurement Plan: The Ministry of Human Resource Development /State Implementation Society (SIS) will prepare a procurement plan as part of annual work and budget plans which provides the basis for the procurement methods. A procurement plan will be forwarded to the World Bank for review. It will also be published on the MHRD/SIS website and on the Bank‘s external website. The World Bank will lead on behalf of development partners in matters of procurement oversight which has been a similar arrangement in SSA and other Centrally Sponsored Schemes in India. Such work arrangement has worked well in the past. The Multilateral Aid Review (MAR) has been appreciative of the WB and has projected a positive trajectory of change indicating that its performance is set to get stronger. The quality of bank staff has been appreciated in this report. The WB has a good reputation across the world and in India too where they have an office staffed with a strong complement of Public Procurement and Finance Experts. / 132. Procurement Manual: MHRD is finalising the FM&P manual for program implementation. Any amendment to the FM&P manual shall be carried out only after a review and clearance from DPs. / 133. Procurement Staffing and Capacity Building : MHRD will nominate a senior official in charge of procurement. At state level the State implementation Society (SIS) will nominate a civil servant to supervise procurement, assisted by a Procurement Consultant recruited from open market through a competitive process and at market remuneration. MHRD will also be supported by a Technical Support Group which will help in monitoring procurement. This staff will be trained in the use of the FM&P manual. MHRD will develop a training strategy and share with the Bank for appraisal. / 134. MHRD has agreed that DPs may declare a State’s RMSA expenditures ineligible for financing if an adequate SIS is not operational. DPs will support additional short-term technical assistance, through DFID’s TC Fund on request from MHRD. The TC fund will also be used to facilitate procurement capacity building and monitoring the procurement performance at State level. / 135. Prior review by the World Bank for works and goods and Consultancy Services: All contracts of £3[20] million and above for works and £300,000 and above for goods; and all contracts of £120,000 and above for consulting services (firms) and £60,000 and above for consulting services (individual). In RMSA as per current assessment most of the contracts are likely to fall under post review. / 136. All contracts not covered under prior review will be subject to post review during supervision missions, and/or review by consultants to be appointed by the Bank.
B. Value for money through procurement / 137. Value for money through procurement will be approached in two ways (i) strengthening procurement and financial risk management; (ii) promoting competitiveness through greater transparency, use of e-procurement and strengthened tendering processes. The World Bank who has specific expertise in these areas will lead for the donor partners. In addition, DFID is working with the bank to design a study focused on engaging private sector in major civil works to leverage efficiency, economy and effectiveness into the process. / 138. Procurement under RMSA will be handled at National, State, District and Village/School levels. The main items to be procured are building and infrastructure, teaching materials, textbooks, computers, teaching services and consultant and non-consultant services. / 139. The procurement related risk is currently rated as “High”. This reflects the relatively recent introduction of the RMSA FM&P manual. Experience with SSA suggests the FMP manual will provide a strong framework as it is embedded into the implementation process. In addition DFID commissioned a full FRA. Additional mitigation measures detailed within this report will be incorporated within the RMSA FM&P Manual. DFID technical support will assist in ensuring adequate training in use of the FMP manual. As with SSA, compliance will also be carefully monitored through the bi annual joint review missions. / 140. RMSA will involve significant infrastructure investment in the early years. Measures have been proposed to mitigate infrastructure-related risks. Unit costs for various civil work interventions have been specified in the FM&P manual. For instance, while smaller building and infrastructure of a value not exceeding £12,000 approx will be allocated to School Development and Management Committees to manage on a shopping basis (as has been done successfully under the Sarva Shiksha Abhiyan (SSA), larger building and infrastructure (e.g. new school construction or major expansion of existing schools) will be contracted following national competitive bidding procedures, in most cases at the State level using specialized infrastructure firms. In all cases, these firms will sign contracts as per the agreed terms and conditions. / 141. To strengthen the compliance regime, MHRD has agreed to a DP proposal for an independent third party monitoring of building and infrastructure procurement for a sample of contracts (i.e. 800-1,000) in a sample of States, such that all States are covered over a three-year period. This will be done annually using RMSA budgets. The Terms of Reference for this independent monitoring were discussed with the Development Partners, and closely follows the terms of reference used for a standard ex post procurement review. / 142. E-procurement will be encouraged under RMSA, for increased efficiency and transparency. On a State by State basis, DPs will review State e-procurement systems before they are authorized for RMSA expenditures, and will work with MHRD to encourage usage of a standard e-procurement platform developed by the National Information Centre. / 143. MHRD has agreed to publish financial and procurement audit reports of State Implementing Societies (SIS) on the RMSA website. In addition, the States will be asked to disclose the procurement plan, contract opportunities, bid documents and contract award information on their website, as per Central Vigilance Commission (CVC) requirements. Standard bidding documents will be issued to all States by MHRD. / 144. Annual procurement audits will be conducted through the statutory auditors of each RMSA SIS, and internal audit functions will be further strengthened through use of a standard procurement audit checklist shared with the States by MHRD. A concurrent financial review, which also covers procurement review, will be conducted through the Institute of Public Auditors of India (IPAI), as is done under SSA. In addition, FMP specialists (one each from GOI and DPs) will participate in the Joint Review Missions for RMSA. / 145. Joint Review Missions would have representatives of Government of India and funding agencies. The missions would be expected to visit individual States and examine first hand the implementation of the programme through visits to select districts of the State. The approach would be a holistic one with emphasis on assessing both the quantitative and qualitative aspects of the implementation of the programme. The Missions are expected also to flag the areas of concern, both in the programme implementation and also in the general educational scenario in the State. / 146. All contracts issued under RMSA will be subject to post review on a sample basis, and the need for post review will be determined in consultation with MHRD. Representatives of national level institutions like NCTE, NUEPA and NCERT will also undertake periodic monitoring and provide resource support to the SIS to strengthen appraisal and monitoring systems. They will undertake regular visits to the States and UTs. State Governments/UT administration will prepare a panel of experienced and reputed institutions and civil society organizations. They will monitor the program in consultation with the Planning Core Team as envisaged in the RMSA framework. These risk mitigating measures along with the use of output based contracting will ensure value for money.
[20] Exchange rate : £1=$1.66

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / 147. DFID will contribute up to £80 million over four years (2012/13-2015/16) to the RMSA programme. This financial envelope will be divided into two broad components comprising £60 million as sub-sector non-budgetary financial assistance and £20 million as technical cooperation. The financial aid component is further broken down into two components – FA programme and FA capital with equal outlay over the period of the programme. / 148. The World Bank and DFID will pool their funds with those of the GoI to support the programme from 20012/13-2016/17 and meet a proportion of eligible costs. The World Bank contribution will be £300 million. European Union will be providing €80m over a five year period outside pool financing through budget support to the education sector. / Table 12 below illustrates this arrangement (all figures in GBP[21]) / SECONDARY EDUCATION (CENTRAL SCHEME) 2012-13 2013-14 2014-15 2015-16 2016-17 Total / Projected Expenditure in GBP Million (GoI’s estimates) 1410 1410 1510 1608 1830 7768 / DP's Share In GBP Million / IDA 60 60 60 60 60 300 / DFID FA 19 19 19 3 Nil 60 / Total DP support 79 79 79 63 60 360 / The disbursement profile for DFID is likely to be as follows / Table 13: Disbursement Profile (figures in GBP million) / DFID Contribution Allocation (million) 2012/13 2013/14 2014/15 2015/16 / Financial Aid programme / Financial Aid Capital / FA sub-total / Technical Co-operation £30 / £30 / £60 / £20 £10 / £10 / £20 / £5 £10 / £10 / £20 / £5 £10 / £10 / £20 / £5 £0 / £0 / £0 / £5 / Total £80 £25 £25 £25 £5 / The projected DFID resource allocation of £80 million by component is represented in the graph below: / 149. Disbursement would be based on the semi-annual Interim Unaudited Financial Reports (IUFRs) and shall be 100% of the eligible expenditure incurred during the fiscal year. DP disbursements will be a fixed amount each year, subject to expansion of the programme by at least 10% over the previous year. This increase should be on the basis of approvals by the Project Appraisal Board (PAB) of national and State AWPBs, and not on eligible expenditures. All categories of RMSA expenditures would be eligible for reimbursement. Each year, the first disbursement shall be based on the September IUFR; in case this results in disbursement of the entire £60 million IDA and of the available DFID amount then disbursement against the March IUFR shall be Nil. Any discrepancies between the amounts of programme expenditures reported by the Financial Management Reports (FMRs) and those reported in the Consolidated Report on Audits will lead to adjustments of subsequent disbursements. / 150. Monthly review of spend and forecasts will be adhered to. Financial aid payments will be made once in a year. Bi-annual formal review of programme with GoI along with the periodic DP meetings will ensure close monitoring and accuracy of the FA forecasts. For TA spend, the project steering committee will review and approve the annual work plans and budget to ensure that the proposed plans are feasible and the budget estimates as realistic as possible. In addition, the DFID project team will review TA spend and projected requirement with the TA agency on a monthly basis. Any significant changes will be tracked early on and remedial measures taken accordingly.
B. How will it be funded: capital/programme/admin? / 151. Funds will be drawn against the programme resources budget approved under the DFID India’s operational plan. The year-wise outlay for this programme is provided for within the DFID India Aid framework. Capital funding will be required for building and infrastructure expenditure, which is likely to be 50% in proportion of the total FA budget. No contingency reserve is required.
C. How will funds be paid out? / Financial Aid / 152. A comprehensive assessment of FM arrangements and Fiduciary Risk Assessment has been conducted (using the DFID methodology) by Price Waterhouse Coopers. The draft Financial Management and Procurement Manual (FMPM) have been compiled through collaborative effort. / 153. Disbursement by the DPs would be made twice per year around September/October and March/April for eligible expenditures incurred during the fiscal year. Disbursements would be based on IUFRs covering the current fiscal year, and programme expenditures reported in the FMRs would be subject to confirmation/certification by the annual audit reports of all implementing agencies and States. Any discrepancies between the amounts of programme expenditures reported by the IUFRs and those reported in the Consolidated Report on Audits would lead to adjustments of subsequent disbursements, to be recovered from or reimbursed to GoI through the next disbursement. Agreement would be reached among the GoI/ DPs on amounts approved for disbursements before GoI would submit applications for withdrawal to the Bank and DFID. / Budgeting and Fund Flow / 154. The RMSA funding pattern between Government of India and State government is in the ratio of 75:25 for the 11th Five Year Plan; this will be reviewed for the 12th Five Year Plan. For the North Eastern States, 90:10 sharing ratio will apply for the 11th and 12th Five Year Plan. / 155. The fund flow arrangement for RMSA is similar to the one used for the elementary education programme (SSA). Funds from the Bank and DFID will be received in accounts (Special Account) maintained with the Reserve Bank of India (RBI); the account will be denominated in US$ and GBP in case of World Bank and DFID respectively. The rupee equivalent of the receipts will be transferred to the Consolidated Fund of India[22], where it is pooled with GoI’s own funds. Adequate funds are provided to the relevant budget head of MHRD and similarly at the state level, a budget is provided by the state to the Department of Secondary Education for its share of RMSA. Both GoI and the state government transfers funds to the State Implementation Society (SIS) from where it is further disbursed for expenditure at State level. The SIS will release funds to the implementing agencies for civil works or to the School Development and Management Committees (SDMCs) for civil works/ other project expenditure. In certain cases, States will have the flexibility of revising the fund flow arrangements and transferring funds to the SDMCs through the District Offices. The funds flow is depicted in the following diagram. / Figure 11: RMSA Funds Flow / 156. The programme for each state is prepared in the form of an Annual Work Plan and Budget (AWP&B). This details the activities and costs proposed in terms of numbers of teachers, targets for building and infrastructure, goods, computers, laboratory equipment, books, etc. Districts will prepare their AWP&B based on the broad RMSA Framework for implementation. The RMSA SIS will forward these proposals to the National Mission for release after appraisal by the State level Executive Committee. The Technical Support Group of the National Mission will appraise the AWP&B. The Project Appraisal Board of the National Mission will approve the Annual Plan on the basis of the Appraisal Report, the recommendation of the SIS, the availability of Central Plan funds, and the commitment of the State government regarding financial resources. The Central Government will release the funds directly to the SIS. / 157. State Governments are required to give written commitments regarding their contribution towards RMSA i.e. transfer of its share to the State Society within thirty days of the receipt of the Central contribution. / 158. After utilising at least 50 per cent of the released funds, the State Government will apply to the Ministry of Human Resource Development for the next instalment. MHRD will release on the following conditions: / Submission of certified expenditure statement showing that at least 50 per cent of released funds have been utilised at the time of submission of the proposal for the next instalment. / Submission of certificate regarding the release and receipt of the State Share against the amount of the Central funds released so far. This must be accompanied with (i) a copy of the order sanctioning the State Share; and (ii) a certified copy of the bank statement indicating the credit of the State Share. Submission of non- diversion and non-embezzlement certificate. / Any other condition notified from time to time. / 159. It will be mandatory on the part of the RMSA programme to transfer funds to the schools within 15 days of the receipt of funds from the Government of India and State government. A certificate to the effect is required to be furnished to the MHRD, GoI. / Technical Co-operation Funds / 160. Technical support will be provided for planning, implementation, management, monitoring and evaluation and capacity building. As with SSA, the funds will not enter the GoI budget system. A competitively-selected management agency will undertake a pre-agreed work programme. A contract with the selected agency will form the basis of agreement of the deliverables, expected performance and the related payments to be made. DFID will reimburse the contractor on satisfactory completion of performance milestones, jointly reviewed with GoI. TA agency will be required to submit monthly progress reports along with the expenditure statements.
D. What is the assessment of financial risk and fraud? / 161. A Fiduciary Risk Assessment at this early stage in the implementation of RMSA must be qualified by the fact that the draft Financial Management & Procurement Manual is as yet not fully adopted by the States. On the basis of DP experience with SSA the overall risk rating for RMSA is likely to improve once the FMP manual, which is close to finalisation, is adopted and ‘rolled out’ for use by all implementing partners. / 162. The programme is expected to have a large building and infrastructure spend in the initial few years of DP financing. Civil works are a high risk area. Moreover arrangements for building and infrastructure vary across states. The DPs have secured MHRD commitment to do an independent third party monitoring of building and infrastructure procurement for a sample of contracts (i.e. 800-1,000) in a sample of States, such that all States are covered over a three-year period. Details of mitigation measures are listed in Section B of Indirect procurement in the Commercial Case. / 163. MHRD has allowed states flexibility in terms of the implementation arrangements; either they can use the Society implementing the SSA or establish a new Society for RMSA implementation. Support during the implementation phase will specifically seek to address identified capacity building needs in budgeting, planning and financial management, procurement and civil works (see management case). DFID support will also be provided to the Technical Support Group (TSG) established by MHRD at the centre which will support and guide the states. / 164. It is expected that RMSA implementation will see the development of a Financial Management Information System. This would be an electronic repository where all budget heads from the school level upwards would be aggregated as per the AWP, and expenditure will be booked against them at the school, district and state levels. Information on financial transactions will be uploaded and consolidated regularly for public access to ensure greater accountability of expenditure. / 165. Other mitigation measures focus on transparency to deliver better monitoring by key stakeholders at School/ local community, District, State and National level. For example, (i) every school will have a notice board showing all the grants received and spent by the school and the details thereof; (ii) uploading of component wise details of approved funds and sanction orders for pre-project/project activities on the district, State and National level web-site; (iii) State Governments to prepare and table annual report before the State Legislature etc. / 166. The Fiduciary Risk related to the TC Fund is adjudged low. A technical management agency will be selected through international tendering. A milestones based contract will drive progress and disbursements in arrears against invoices. Regular and random checks on invoicing will be in place. / While Table 14 below notes the key highlights of the fiduciary risk rating, further detail is of the risks and the possible mitigation measures are provided in the Annex 2. / Table 14 Highlights of PFMA Risks: Good Practice Principles & Risk Rating / GPP 1: A clear set of rules govern the budget process. S/ H / GPP 2: The budget is comprehensive. L / GPP 3: The budget supports pro-poor strategies. M / GPP 4: The budget is a reliable guide to actual expenditure. H / GPP 5: Expenditure within the year controlled. H / GPP 6: Government carries out procurement in line with principles of value for money and transparency. S / GPP 7: Reporting of expenditure is timely and accurate. S/ H / GPP 8: There is effective independent scrutiny of government expenditure. H / Risk Rating Nos. of benchmark / Low Risk (L) 2 / Moderate Risk (M) 2 / Substantial Risk (S) 5 / High Risk (H) 6 / Overall risk rating S
E. How will expenditure be monitored, reported, and accounted for? / Accounting/ Reporting / 167. The FM&P Manual lays down arrangements for Internal Audit (IA) as an ongoing activity on the program. This may however be conducted by in-house staff or by a firm of Consultants/ Chartered Accountants. The IA process is important to provide the necessary coverage to this vast decentralized program. / 168. Accounting will be done on a cash basis, at the state, district and school levels. Adequate records will be maintained at accounting locations and will include vouchers, invoices, cash books, ledgers and asset registers. Guidelines cover: requirements for bank reconciliation; payments to be under the joint signatures of two persons; requirements for submission of utilization certificates etc. The summary of transactions will be sent to the next higher level based on common formats. / 169. Joint signatory savings bank (SB) accounts with nationalized banks shall be opened under the scheme at the State, District and School levels. The Head Master or Principal and Chairman of the SDMC will be the joint holder of the account at School level. / 170. Reporting of expenditure to the Development Partners will be in the form of semi-annual IUFRs. These will provide information on approved AWPB, releases, balances, and expenditure for each state and intervention separately. The first IUFRs for the fiscal year will be due by September/October followed by the second one by March/April. / Audit / 171. Audits of SIS will be conducted by firms of Chartered Accountants accredited by the India Comptroller and Auditor General. The Audit will cover Programme Financial Statements, including a Statement of Receipt and Expenditure and a Balance Sheet. The Audit will cover all SISs/ District Offices and sub-district units. Audits will be carried out in accordance with agreed terms of reference. Audited Accounts/Audit Report will be furnished to GoI. / 172. GoI will then provide the Partners with a Consolidated Report on Audit of the program within six months of close of the Financial Year i.e. by September 30th. This report will consolidate the Program Expenditure incurred under the state/ national components. The report will also consolidate the key observations forming part of the audit report of each state. Further the MHRD will be required to provide copies of the State Audit Reports to the Bank as well as disclose them on the MHRD website. The following audit reports will be monitored by the DPs in the Audit Reports Compliance System (ARCS). / Table 15: Auditing Arrangements / Implementing Agency Audit Auditors / Entire Program Project Audit Consolidated Report on Audit of RMSA / DEA/GOI Special Account Comptroller & Auditor General of India / Support during Implementation Phase / 173. Support during implementation phase will focus on both the financial management guidelines as well as their implementation in the states. Firstly, since the fiduciary guidelines will be finalized very close to project start and will be tested during implementation. An evaluation of whether the guidelines are reasonable and comprehensive will be carried out. Secondly, outlays will increase steeply during the initial few years of the project with focus on building and infrastructure. In this context, adequate capacity building effort, supporting MHRD monitoring, visit to states/ districts, monitoring audit timeliness etc will continue. This intense support during implementation phase is expected to last for at least two/ three years; subsequently the direction and intensity of Development Partners‘ support may be calibrated in the context of the implementation experience. / 174. Audits for the initial years of the programme are not yet complete. However the MHRD is in the process of establishing a Technical Support Group (TSG) at the centre which will support and guide the states. Further awareness training if provided in a timely manner should make new staff aware of the RMSA programme requirements.
[21] Exchange rate: £1=$1.66
[22] All revenues received by the Government by way of taxes like Income Tax, Central Excise, Customs and other receipts flowing to the Government in connection with the conduct of Government business i.e. Non-Tax Revenues are credited into the Consolidated Fund constituted under Article 266 (1) of the Constitution of India. Similarly, all loans raised by the Government by issue of Public notifications, treasury bills (internal debt) and loans obtained from foreign governments and international institutions (external debt) are credited into this fund. All expenditure of the government is incurred from this fund and no amount can be withdrawn from the Fund without authorization from the Parliament.

Management Case

A. What are the Management Arrangements for implementing the intervention? / 175. RMSA institutional and implementation arrangements provide for: (i) programme direction and oversight; (ii) decentralized management and implementation; and (iii) technical support and capacity building. / 176. The institutional arrangements were established as part of preparation of the RMSA Framework document, issued by the GoI in 2008. They have been further strengthened as part of the process of preparation of DP financial and technical support for RMSA following the GoI‘s request for DP support in May 2009. DP engagement has included preparation of a comprehensive Financial Management and Procurement (FMP) Manual and Implementation Manual for RMSA. / Programme Implementation Responsibilities By Level / 177. The Ministry of Human Resources and Development (MHRD)[23], Government of India is the implementing agency for RMSA. The governing council of the National Mission for RMSA, chaired by the Minister, sets overall policy and exercises oversight with the authority to make financial and physical norms flexible within the RMSA scheme, as well as changes in planning, implementation, monitoring and evaluation parameters. An Executive Committee of the National Mission serves as the Project Approval Board (PAB), chaired by the Secretary of School Education and Literacy and has representatives from the Planning Commission, Ministry of Finance, NUEPA, NCERT, National Institute of Open Schools and Central Board of Secondary education. / 178. National Level. The Project Approval Board serves as the primary review mechanism for the financing of States’ Annual Work Plans and Budgets (AWPBs). The PAB is supported by a Technical Support Group (TSG), which helps States to prepare their AWPBs and conducts the appraisal of these AWPBs to ensure their completeness and conformity with the RMSA Framework before they are forwarded to the PAB. Finally, a separate Bureau in MHRD’s Department for School Education and Literacy (DSE&L) is in charge of RMSA on a day-to-day basis, comprised of approximately 15 staff (Joint Secretary, Directors/Deputy Secretaries, Under Secretaries and administrative support staff). This group is supported by experts from the Technical Support Group (TSG). / 179. State Level: A State RMSA Mission Authority whose governing council is chaired by the Chief Minister operates an autonomous State Implementation Society (SIS), which provides direction and oversight at the State level. The SIS, through the State Project Office (SPO), coordinates with District and sub-District level organizations; supports Districts in preparing annual plans; handles State-level procurement and contracting; conducts monitoring and evaluation activities; serves as a channel for the flow of funds to the lower levels, is responsible for financial management and audit reports. The SPO reports on implementation progress, and submits and negotiates the consolidated AWP&Bs, to the national level. / 180. District Level: At the District level, the implementation and oversight functions are carried out by the RMSA District Programme Coordinator (DPC), located in the District Education Office. The DPC works in close collaboration with the School Development and Management Committees (SDMCs) within the District to prepare the district AWP&B, and monitors physical and financial progress of RMSA at the school level on a regular basis. / 181. Community and School Level: All schools are required to establish School Development and Management Committees (SDMCs), which are responsible for all RMSA activities at the school level – planning, data collection, monitoring, and implementation. In particular, SDMCs will directly manage all building and infrastructure work under Rs. 10 lakhs (approximately £12,000), maintain all relevant records, and be subject to the annual external audit process. They also manage the annual school grant, funds for laboratories, textbooks, libraries and other consumables. States have the flexibility to decide on the specific composition of the SDMC, although MHRD has provided guidelines to ensure representation from parents, women, school officials, the local political authority (Panchayat) and disadvantaged groups (SC / ST). / 182. Donor Partners: DFID, the World Bank and the Delegation of the European Union in India (EU) share responsibilities for programme and financial management oversight. A Memorandum of Understanding will be signed between DPs and MHRD setting out respective roles and responsibilities during implementation. World Bank will be the lead partner on financial management to identify eligible expenditure, support on development and implementation of the financial guidelines and conduct of audit. DFID will support through review of the fiduciary risks and mitigation plans using the fiduciary risk assessment tool (see financial appraisal for detail). / 183. DFID India: In DFID India, the MDG Team will be responsible for the management of DFID inputs and monitoring of RMSA. This will be carried out by a dedicated Education Task team led by Senior Education Adviser and a Senior Deputy Programme Manager with support from Economic, Governance, Social Development Advisers and Programme Staff. / Technical Support / 184. At the National level there is a dedicated RMSA Technical Support Group providing assistance to DSE&L and the States in all aspects of RMSA implementation. Apex national institutions, such as NCERT, NUEPA, NIOS, National Council for Teacher Education and Indira Gandhi National Open University, provide support to the DSE&L and to State institutions in pedagogy, student assessment, teacher training, educational planning, and monitoring and evaluation. At the State level, State Councils of Educational Research and Training (SCERTs) and State Institutes of Educational Management and Training (SIEMATs), are apex institutions for improving the quality of school education and management. At the District level, District Resource groups are constituted who, under the guidance of District Institutes of Education and Training (DIETs), provide training to school and community level personnel on school management and pedagogy related issues. / DFID’s Technical Cooperation Fund (TCF) / 185. DFID will provide £20 million funding for the Technical Cooperation Fund (TCF). DFID will fund and manage technical support to accelerate and sustain the effective implementation of RMSA. The TCF has central and state level objectives: / 186. Central level objectives: To strengthen secondary education management information systems (NUEPA), establish a national secondary learning assessment system (NCERT) and support implementation through the (MHRD / technical support group) at the centre; / 187. State level objectives: To strengthen implementation capacity in low enrolments/low income states, enhancing the efficiency and effectiveness of scheme expenditure overall. Overall, the purpose of this intervention would be to rapidly build capacity and systems at state level in the early years of RMSA implementation, thereby enabling them to take full advantage of the RMSA programme from the outset. At state level, the focus will be on the ‘most needy’ states. These may vary over time however preliminary planning is based upon the nine states with the lowest GER based on 2009-10 SEMIS statistics. These are: Bihar, Uttar Pradesh, Jharkhand, Assam, Madhya Pradesh, Haryana, West Bengal, Rajasthan and Orissa. / 188. Support will be delivered to implementing authorities and focus on four themes of broad need: (i) Budgeting and Planning; (ii) Financial Management and Procurement; (iii) Building and infrastructure and (iv) Teacher Development. The fund would also be sufficiently flexible to respond to emerging areas of support such as transaction advice on PPP initiatives. / 189. Technical support will be provided via a two tier modality. Embedded support through offices located within DFID focus states and peripatetic outreach from these to the remaining states. Considerable use will be made of regional ‘surgeries’ and ‘workshops’ on areas of common concern as a cost effective means of promoting the sharing of best practice amongst states. Table 16 provides an indicative overview of the types of activities envisaged. / Table 16 : Indicative TC Fund activities and beneficiaries / RMSA – Monitoring and Performance Enhancement / Partners: MHRD - TSG, NCERT, NUEPA , Research Institutions / MHRD / TSG Mobilisation and funding of short term expert support as needed / Commissioning research / services as required / Professional development programmes / Funding of study tours and visiting experts / NUEPA Support to NUEPA’s plans for integration of DISE and SEMIS to form a seamless education management system / Strengthening of internet based EMIS system - capacity building support at state level / Support to NUEPA plans to develop geographic information systems (GIS) / Support to development of decision-support tools which ensure timely production of accessible and pertinent management information data. / MHRD Assessment Cell / NCERT Development of grade 10 national learning outcome measurement, analysis and data use. / Support to GoI engagement with OECD Programme of International Secondary Assessment (PISA). / RMSA Planning and Delivery: Partners: MHRD – TSG, State Implementation bodies / MHRD / TSG Supporting the development and application of an equitable allocation formula / Supporting development of RMSA priorities and procedures in line with the 12th Plan, e.g., consolidation of other secondary schemes within RMSA framework / Supporting the evolution of RMSA programme on request – e.g. monitoring results framework indicators, formulating standards / guidance e.g., civil works, development of e-procurement etc / TCF Focus States Expert support to implementation agencies on key areas of common concern: e.g. AWP&B, teacher education, EMIS, e-procurement, etc / Provision of regional workshops / surgeries on areas of common interest e.g., Annual Workplan and Budget preparation, teacher education management / AWP&B – quality assurance services / Production of manuals and support materials to assist implementation – e.g. planning school expansion, using e-procurement, managing civil works / Training modules for State Project Directors and other administrators / All States All RMSA states will benefit from the TCF. This will be achieved through a coherent communication and dissemination strategy as well as selective invites to regional workshops. The TCF will use a variety of media as well as the JRM process and MHRD channels to disseminate research, best practice, free sharing of any computer software / materials developed via electronic media and the JRM process. / 190. The governance structure for the TC fund will ensure government and key stakeholder ownership. It is expected that the governance structure will follow the model successfully used under SSA. / A Steering Committee chaired by MHRD, with senior representation by appropriate concerned bodies e.g. Director, NCERT; Vice Chancellor, NUEPA; NCTE; NIOS; donor partners and appropriate state representatives will meet annually. The purpose of the steering committee will be to set strategic direction, verify the annual report and agree on an annual workplan for the TC going forward. / An Executive Committee. The executive committee will meet more frequently (bi-annually or quarterly as deemed appropriate). It will provide the opportunity for the implementing agency to report on progress and take feedback. Committee members will be drawn from the same institutions as the steering committee but from the implementation level. / Implementing agency: As with SSA, a managing agency will be contracted to coordinate all technical support and capacity building activities. / B. What are the risks and how these will be managed? / The programme is judged to be medium risk and high impact. Key risks include
Risk Mitigation Prob Rating / / Impact / 1 While currently substantial fiduciary risk will decline with the introduction of the FM&P Manual (As experience with SSA). The fact that SEMIS is still not fully functional also presents challenges for management information. Strengthening financial management systems with the implementation of the FM&P guidelines will significantly reduce risks related to procurement. Audit regimes will assess compliance. Strengthened SEMIS data will provide the information for better budgetary planning and monitoring of expenditure. H/M H / 2 The DFID predicted outcomes are dependent on coordination of multiple government bodies and growing implementation capacity. Agreement that the TC Fund should engage at state implementation society level will provide opportunities to strengthen coordination/ build capacity raising the likelihood of achievement of expected outcome. M/M M / 3 Complexity of TA support results in poor implementation Two tiered support at national and state level along with the need to manage expectations and needs of different stakeholders will be a challenge. A well designed ToRs, competitive tendering consortium approach and regular review will help manage it effectively. M/H H / 4 Limited human resource capacities result in poor implementation – this risk is particularly acute at state and district levels MHRD has established a Technical Support Group (TSG) for the Bureau for Secondary Education, which will enhance capacity at the central level. This will be supported by the DFID TC fund as with SIS. H/H H / 5 Lack of political will in the States to implement RMSA. In an era of excessive demand in relation to supply ‘quality’ issues may not get sufficient priority. Secondary education access is an increasing political priority for government in India and is already important in states like Bihar. The TC fund will support quality enhancement opportunities. It has already supported Indian participation in OECD Programme for International Student Assessment. This has created significant public scrutiny on learning outcome results. L /H H / 6 Insufficient leverage in addressing women and disadvantaged groups as the many of the equity-related incentive programmes (eg scholarships, residential hostels, free uniforms) currently sit outside MHRD / parameters of RMSA The RMSA Framework includes measures to improve equity and access. This will be monitored through the JRM process. DFID is funding complementary girls incentive schemes with other ministries. The 12th plan indicates that schemes such as hostels and scholarships will be subsumed within RMSA over the period of the plan. M/H H / 7 Low transition rates from elementary schooling impede meeting RMSA’s ambitious goal of 75% GER by 2017 The GoIs national incentive programme for disadvantaged children should promote higher transition by addressing demand side constraints. DFIDs support to the development of an integrated (primary and secondary) EMIS will ensure a more accurate calculation of transition rate to facilitate informed policy making – better monitoring allowing for better remedial action M/H H / 8 Expansion of school infrastructure is at an inadequate rate to meet enrolment demand. Short cuts in construction lead to inferior construction. Where appropriate, policy advocacy for double shifting as an interim measure to meet demand. Technical via the TC fund to support capacity and standard in school building. Annual sample audit of civil works construction and contracts. H/H H / 9 Learning outcomes remain low despite heavy investments in infrastructure and teachers. Tangible improvements in learning outcome are difficult to identify particularly in a situation where there is no systematic learning assessment conducted at secondary level. DFID’s TC will continue the work done at primary level in establishing a much-needed platform for time based systemic quality monitoring, diagnostic analysis, remedial action and better resource targeting M/H H / 10 Weak Governance resulting from poor management systems and inadequate numbers of staff The secondary education management information system is not yet fully functional. It has however recently been provided with significant funding. DFID TC Funds will be used to strengthen SEMIS at centre and state-level as required thereby improving governance of RMSA. M/H H / Table 17 : Risk Matrix Summary / IMPACT / HIGH MEDIUM LOW / PROBABILITY HIGH [4] [8] [1] / MEDIUM [3] [6] [7] [9] [10] [2] / LOW [5]
C. What conditions apply? / 191. Disbursements would be based on Interim Unaudited Financial Reports (IUFRs) covering the current fiscal year, and programme expenditures reported in the IUFRs would be subject to confirmation/certification by the annual audit reports of all implementing agencies and States. Any discrepancies between the amounts of programme expenditures reported by the Financial Management Reports (FMRs) and those reported in the Consolidated Report on Audits would lead to adjustments of subsequent disbursements, to be recovered from or reimbursed to GoI through the next disbursement. More details can be seen in section C of the Financial Case.
D. How will progress and results be monitored, measured and evaluated? / Three Tier Evaluation Framework / 192. DFID’s monitoring of RMSA progress will use a three tier ‘nested’ approach. At the programme level MHRD and the donor partners have collaboratively developed a RMSA Results Framework. This is the primary document against which performance will be monitored through bi-annual joint review missions (JRM) which track performance and implementation right down to district level. This practice builds on a successful approach developed under SSA. All reports from JRMs are made publicly available on a dedicated website. Recommendations made by JRMs are followed up in the following review mission. / 193. The RMSA framework contains a full range of performance indicators (disaggregated by gender and social group) for access, equity, efficiency, quality and innovation with annual milestone targets and data sources from which targets will be monitored. The RMSA key performance indicators are listed below. In addition to results monitoring a comprehensive list of research products to be commissioned is detailed within the framework. The full framework is at Annex 3. / The full RMSA results framework and notes are located in Annex 3. / Table 18: Key Performance Indicators from the RMSA Results Framework / Indicators Policy Domain Base-line / 2009-10 2011-12 2012-13 2013-14 2014-15 2015 -16 Source / Student Enrolment Secondary (Grade IX and X): (numbers) Access 28.3 m 31.5 m 33.1 m 34.8 m 36.5 m 38.4 m SEMIS (NUEPA) / AWP&B, (TSG) / Gender Parity Index (GPI) (in schools covered by RMSA) Equity 0.87 0.91 0.92 0.93 0.93 0.93 SEMIS, / (NUEPA) / AWP&B / (TSG) / Secondary education graduation rate (those who enrolled in grade IX in year t appearing for the final exams in grade X in year t+1) (in schools covered by RMSA) Internal efficiency 78% 80% 82% 84% 86% 88% SEMIS, / (NUEPA) / AWP&B / (TSG) / RMSA’s Quality Improvement Policies modified using the analysis of the new System for National Assessment of Students’ Achievement Quality No Assess-ment National Assessment system that interfaces with elementary school learning assessment in place and data used for remedial action and resource targeting. NCERT / 194. DFID’s Logframe (Annexe 4) for RMSA draws extensively from the indicators and data sources specified within the RMSA Results Framework but with a particular focus on tracking key themes detailed within the theory of change. At impact level youth employment and age of pregnancy will be tracked through the National Sample Survey (NSS) and through the DFID supported ‘Young Lives’ Longitudinal study. Results will be monitored on a 6 monthly basis (where data sources allow) as per FCPD guidance. The statutory DFID annual output to purpose review (OPR) will review and report on progress as well as remedial actions to be taken. A summary of the DFID logframe indicators is detailed within Table 19. All indicators are disaggregated by both gender and social group to the extent possible. / Table 19: Summary of Logframe Indicators / Performance Level Measured by : / Impact : Better educated and employable youth / Impact 1: Youth employment rate disaggregated by gender (Young Lives Sample) / Impact 2: Percent of women ages 15-19 who are already mothers or pregnant. (NSS survey 2014/15) / Outcome: More girls and boys, regardless of social background, benefit from good quality secondary education / Outcome 1 Secondary education graduation rate (Source: Annual SEMIS / AWP&B) / Outcome 2 Secondary education enrolment (grade IX & X) (Source: Annual SEMIS / AWP&B) / Outcome 3 Gender parity index (Source: Annual SEMIS / AWP&B) / Outcome 4 Number of SC & ST girls per 100 boys (Source: Annual SEMIS / AWP&B) / Output 1: Strengthened planning and management to better deliver quality secondary education / Indicator 1.1 National Achievement survey for grade 10 conducted (Process indicator – system to be established) Grade 10 survey to be conducted by 13/14) / Indicator 1.2 Teacher attendance rate (Source: Annual SEMIS / AWP&B + Independent surveys) / Indicator 1.3 Proportion of teachers receiving in-service training (RMSA Implementation Reports) / Indicator 1.4 Proportion of schools with School Management Committees (RMSA Implementation Reports) / Output 2: Schools are given the necessary resources to deliver quality secondary education / Indicator 2.1 Number of grade 9 & 10 teachers disaggregated by gender (Source: Annual SEMIS / AWP&B) / Indicator 2.2 Proportion of schools with a complete set of infrastructure – classrooms, library, science lab, (Source: Annual SEMIS / AWP&B) / Indicator 2.3 Proportion of schools with adequate numbers of toilets (girls and staff separate as defined by MHRD norms. (Source: Annual SEMIS / AWP&B) / Indicator 2.4 Proportion of RMSA schools with full allocation of qualified subject specific teachers (Maths Science, Social Science). (Source: Annual SEMIS / AWP&B) / Output 3: Children, regardless of background, regularly attend and complete secondary school. / Indicator 3.1 Elementary to secondary transition rate (Source: Annual DISE - SEMIS / AWP&B) / Indicator 3.2 Gross completion rate – class 10 completers as proportion of class 1 entrants (Source: Annual SEMIS / AWP&B) / Indicator 3.3 Share of SC and ST completers as compared to their share of the population (Research & QMT analysis). / Indicator 3.4 Student attendance rates (Quality Monitoring Tool / MI & Implementation Reports) / 195. Independent Monitoring of the Technical Cooperation Fund. DFID will commission an independent monitoring programme for its technical support programme. This will review both impact and value for money of its technical support programme on a cycle of six monthly reviews. The review will be commissioned through a multi supplier Framework Agreement already in operation within DFID India. Indicators will specifically track progress at both state level as well as against thematic priorities. Decisions on specific indicators will only be possible on finalisation of geographical focus and the nature of technical support. A detailed evaluation plan will be expected as the key output of the contractor inception phase. / Data Sources / 196. While India is well served by data collection in terms of primary level and detailed periodic household surveys, annual data collection at secondary level is still in its early stages. To date planning for RMSA has relied heavily on the Secondary Education Statistics data which captures all public and recognised private secondary schools in the country for the years 2006-2009. A comprehensive Secondary Education Management Information System (SEMIS) is currently under development by the National University of Education Planning and Administration (NUEPA). This will be a full internet linked system enabling states to input and utilise data electronically. / 197. A critical task for the RMSA period is to address the twin challenges of uneven capacity of the states/districts in terms of data collection, data reliability, and timely reporting. This uneven capacity affects the reliability of aggregated national level statistics. A second challenge is to address capacity and interface issues in state level data entry and deliver enhanced transparency by NUEPA in sharing data on the SEMIS website. Addressing these twin issues will be essential in promoting use of data in planning and analysis – and to inform resource targeting. This will be important both at State level to inform the creation of a needs based allocation formula and within states to insure AWP&Bs target the biggest educational challenges and neediest blocks and districts. / 198. In addition to the aforementioned it is possible that SEMIS will be merged with DISE (the elementary education MIS system) as part of the 12th Five Year Plan. Such a rationalisation may cause some disruption but would be desirable particularly as it would enable more accurate calculation of the transition rate from basic to secondary education. Increased transition (input of students into the secondary system) is essential if RMSA is going to achieve its 75% GER goal. / Independent Monitoring / 199. Following the successful procedures of SSA, MHRD will ensure third party monitoring of implementation performance by contracting independent Monitoring Institutes (MIs) in each state across the country. The MIs will be selected from Universities, Indian Institutes of Management, Foundations, Trusts and NGOs active in the education sector. They will have standard terms of reference for monitoring a sample of RMSA schools in every State. Reporting will synchronise with the JRM process and findings factored into the six monthly JRM Aide Memoires. As with SSA MIs will publish all report findings on the internet. / 200. In addition to supporting the build of a SEMIS system a critical intervention will be the development of a national assessment system. The DFID TC fund has been instrumental in establishing a diagnostic national assessment system in elementary education under SSA. The RMSA result framework includes the development of a national learning assessment system of students in class 10 using modern testing techniques and regular assessment of classroom practices. GoI has just decided (Dec 2011) to expand its involvement with the international assessment OECD PISA programme. DFID / HMG partners anticipate providing substantive technical support for this work. This will fall outside RMSA but strongly complement the quest for improved learning outcomes at secondary level.
[23] http://education.nic.in/orgastru.asp