Type of Review: Project Completion Review

Project Title: Haiti earthquake response 2010 (201483)

Date started: January 2010	Date review undertaken: March 2012
Introduction and Context
What support did the UK provide?
1. The UK provided £18.5 million for the Haiti earthquake response. This provided resources for a mixture of direct operations and partner funding. Within 24 hours after the earthquake, DFID had mobilised and deployed a UK Search and Rescue team, and a team of humanitarian specialists to Port au Prince, followed a week later by military and stabilisation teams. / 2. DFID assistance was focused on alleviating critical needs in shelter and sanitation, and strengthening the effectiveness of the international humanitarian response. Over 50% of DFID assistance was provided directly, through the in-kind provision of non food items (NFIs) from DFID’s emergency stockpile, and the deployment of specialist humanitarian staff to Haiti. Indirect assistance was provided via the United Nations agencies, the Red Cross and NGOs. / 3. DFID assistance also aimed to strength international coordination and response efforts through direct and indirect secondments into the UN and cluster system, including direct support to the Government of Haiti. / 4. DFID’s involvement in the humanitarian response to the earthquake was limited to the relief phase only, with a project timeframe of 6 months. / 5. Table 1 below provides details on DFID support: / Direct support Support provided Cost / Search and Rescue 64 person UK International Search and Rescue (UKISAR) team rapidly deployed to Port au Prince £245,415 / Non-Food Items Shelter items plus buckets, blankets, household kits £2m / Non-Food Items Vehicles, including forklift trucks £1.5m / Non-Food Items (delivery costs) Air broker and freight costs covering delivery of non-food items (NFIs) and deployment of the UKISAR team £2.2m / Non-Food Items (delivery costs) Royal Fleet Auxiliary from Ministry of Defence provided delivery of NFIs and other equipment. £645,000 / Personnel Deployment of DFID humanitarian operations team (including support and security costs) £2.3m / Personnel Deployment of a Stabilisation Unit team with equipment to help the Ministry of Justice structurally survey prison buildings damaged in the earthquake £283,000 / Personnel 10 secondments of varying lengths to strengthen the UN system and international response: / UN Office for the Coordination of Humanitarian Affairs (OCHA): Civilian/Military coordinator (3 months) / Information Manager (3 months) / World Food Programme (WFP): / Air Operations (3 months), / Logistician (3 months) / International Office for Migration (IOM): Shelter advisor (1 month) / World Bank: Community Development advisor seconded to Post Disaster Needs Assessment (PDNA) (4 months) / UN Children’s Fund (UNICEF): Sanitation specialist (3 mths); / Water Supply, Sanitation and Hygiene (WASH) cluster: / Capacity Building specialist (3 weeks); / WASH specialist (3 months) / USAID: DFID liaison specialist (3 weeks) £670,000 / Indirect support – Addressing urgent humanitarian needs / International Federation of the Red Cross (IFRC) Contribution to the International Federation of the Red Cross (IFRC) Emergency Appeal. £1m / Pan American Health Organisation (PAHO) Support for the establishment of an Early Warning and Response Network (EWARN) and support to primary & secondary healthcare. £300,000 / Merlin Deployment of a medical assessment/surgical team £398,998 / Action Contre Le Faim (ACF) To meet the immediate needs of the earthquake affected population (WASH, shelter, food distributions, cash for work) £1m / Agency for Technical Cooperation and Development (ACTED) To reduce the vulnerability of earthquake affected populations through an integrated response (shelter, WASH, NFIs, disaster preparedness training) £400,000 / Handicap International Shelter £500,000 / OXFAM Shelter £1m / IOM To support coordination, shelter and temporary settlements £1.12m / IOM To support the rehabilitation of prison facilities. £591,054 / Indirect support - Enabling the international response / WFP Contribution to WFP’s Special Operation in the Flash Appeal, to augment logistics and telecommunications) £2 million / OCHA To reinforce and improve humanitarian coordination mechanisms at both national and local levels; improve access and information sharing in the humanitarian community; to manage the Emergency Response Fund (ERF) £1 million / CARE Secondments to the shelter cluster £287,000 / Government of Haiti Advisory support to GoH to assist with response and recovery issues to strengthen clear leadership and decision making. £500,000 / Other / Helping Haiti Appeal Contribution to The Sun “Helping Haiti Appeal” to offset the VAT charged on sales of the Haiti charity single “Everybody Hurts”. The funds were disbursed through the Charities Aid Foundation and split equally between UNICEF and the DEC. £236,000

What were the expected results?
6. The impact of the programme was: to save lives, alleviate suffering and maintain the dignity of earthquake victims in Haiti and to promote a return to normality. / 7. The outcome was: To provide humanitarian assistance to earthquake-affected populations, in particular those currently living in informal settlements, to enable the humanitarian system to function effectively (through high-level strategic support to the relief effort), and to support coherent transitional planning and implementation. / 8. The main targets were: / 80,000 families assisted by DFID provision of assistance by June 2010 / 10 agencies provided with DFID assistance by June 2010 / Humanitarian coordination system established and fully staffed in the sectors DFID has assisted by mid-March 2010. / 3 prisons rehabilitated and functional within 6 months / Post Disaster Needs Assessment (PDNA) process incorporates and benefits from technical support of a community development adviser. / 9. The outputs of the DFID programme were focused on : / Rapid deployment of Search and Rescue teams / Improved effectiveness of the humanitarian response through support to the architecture of the international system. / Provision and facilitation of humanitarian assistance and protection including provision of emergency shelter as contingency – for use in Hurricane. / 10. In the immediate aftermath of the earthquake there was a lack of information on key sectoral issues. The need to programme funds quickly inevitably meant that initial funding decisions were drawn from previous experiences and based on the limited information available. To ensure the response was evidence based, as the situation unfolded DFID instigated close follow-up with agencies funded, updated strategy documents, proposals, logframes and budgets. Later decision making was informed by the field team.

What was the context in which UK support was provided?
11. On 12 January 2010 a magnitude 7 earthquake struck the Haitian coast at 17:00 hours. The epicentre was located 22 kilometres from the capital city, Port-au-Prince and 15 kilometres from the closest towns. A series of aftershocks followed the largest measuring 5.9 and 5.5 respectively. / 12. The earthquake affected Ouest province which has a population of 2.2 million people, with the most affected cities being Port-au-Prince, Carrefour and Jacmel. At the time of the quake many people were at work, and many office buildings collapsed, causing large numbers of casualties. Port-au-Prince is densely populated with over two million inhabitants, of which approximately 50 percent were reported to be living in ‘shanty’ areas. / 13. The scale of the disaster was severe. / Reportedly 230,000 were killed / 300,000 injured (government Civil Protection agency figures). / It is estimated between 1.3 and 1.5 million people were displaced (OCHA figures), into settlement sites. / 661,000 people migrated from the West Department (and were living with host families). / 14. The human impact of the earthquake was immense. By striking at the very heart of the Haitian economy and administration, the earthquake had an acute effect on the human and institutional capacity both of the public and the private sectors, and of international technical and financial partners and NGOs. / 15. Critical services including water, electricity, communications and fuel supplies were seriously disrupted. Government buildings collapsed or were severely damaged, including the Presidential Palace and several Ministries. Many UN and NGO agencies present in Haiti at the time of the earthquake were severely affected. Staff were killed or injured. OCHA suffered the loss of its head of office and many of its national staff lost loved ones. The entire staffing of the OCHA operation pre-earthquake had to be replaced and surged. The psychological and physical distress caused had a significant impact on affected populations and international agencies working in Haiti. / 16. The earthquake compounded what were already very difficult humanitarian conditions in Haiti. Prior to the earthquake, UNICEF reported that Haiti had the highest rates of maternal and infant mortality in the western hemisphere, with diarrhoea, respiratory infections, malaria, tuberculosis and HIV/AIDS the leading causes of death. 60% of the population did not have access to basic health services. Potentially the onset of the rainy season combined with unsanitary and cramped living conditions posed further risk of outbreaks of measles, diarrhoea and sharp increases in respiratory infections. / 17. There was massive infrastructure destruction. Some 188,383 homes were completely or partially destroyed. Over 1,300 educational establishments and over 50 hospitals and health centres collapsed. The Presidential Palace, Parliament, the Law Courts and most of the Ministry and public administration buildings were destroyed. The earthquake shattered the capital city, destroying what existed of the governance of an already fragile state. Government virtually ceased to function, with health services and infrastructure severely compromised.

Section A: Detailed Output Scoring

Output 1: Search and Rescue services rapidly deployed
Output 1: final score and performance description: A
Final results: / 18. The 64 person UK International Search and Rescue team landed in Port au Prince approximately 48 hours after the earthquake (this was despite a 12 delay caused by the closure of Gatwick airport due to snow). They stayed in-country for ten days and helped to save the lives of 3 people and provided recovery assistance. / 19. The UK team formed part of a larger international SAR response which helped to rescue 132 people. The UN Inter-Agency real time evaluation of the earthquake response concluded that whilst lives were saved in the immediate aftermath, there were “not that many”. [1] This partly resulted in the Humanitarian Emergency Response Review (HERR )recommendation that the UK consider using other UK niche capabilities which could potentially save more lives when responding to future humanitarian emergencies. The Haiti response and lengthy travel time from UK, highlights that DFID should keep under review whether it dispatches a UKISAR team such long distances to respond in future. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[1] Quoted in HERR Haiti Case Study p1

Output 2: Provision and facilitation of humanitarian assistance and protection
Output 2: final score and performance description: A+
Final results: / 20. DFID provided assistance directly using supplies from its stockpile and indirectly through support to partners: / Target Results / 30,000 families assisted with shelter by June 2010 Approximately 29,249 families assisted, through both direct assistance (up to 13,000 families) and indirectly through partners (16,249 families). Other families benefited from related shelter items (3,498 wood planks, 9,800 ropes) provided via IFRC. / 10,000 families assisted with WASH provision by June 2010 Approximately 74,360 families received indirect assistance through partners. / 50,000 families provided with NFIs by June 2010 Approximately 61,738 families assisted. In-kind consignments of NFIs via the IOM benefitted 28,669 families, and further indirect assistance through partners helped 39,069 families. / Any outbreaks of communicable disease are identified and controlled before an outbreak occurs The Pan American Health Organisation (PAHO) disease surveillance system reported no major disease outbreaks in the six months following the earthquake. Prompt potable water distribution is believed to have prevented diarrhoea outbreaks. / The strengthened capacity of Haitian Ministry of Health’s (MoH), in surveillance and disease control helped to counter malaria, dengue, tuberculosis and rabies. Accurate forecasts of numbers affected by the cholera outbreak (Oct 10) were also produced, and the more resilient systems in place enabled effective control of the disease. / Other results : Over 90,000 people benefited from cash for work activities; / Over 25,000 families received food distributions. / 10,000 injured people benefited from hospital and community based treatment. / 21. Estimated breakdown of DFID in-kind assistance is as follows: / Item (s) Quantity Beneficiaries (total numbers of people, on basis of 5 people per household) / Shelter kits 6,500 32,500 / Pole sets for shelter kits 6,500 32,500 / Plastic sheeting (6x4m) 5,190 25,950 / Blankets 34,500 34,500 / Buckets 24,000 24,000 / Kitchen sets 5,000 25,000 / Household kits 5,000 25,000 / Vehicles 7 Nissan Patrols / 8 Landcruisers / 2 trucks / 11 forklift trucks / 22 trailers General support to humanitarian operations / CHASE OT assessments, deployments and office support Various staff inputs / Haiti Office/ staff living costs / Security support General support to humanitarian operations / Emergency stockpile / Shelter Kits /poles sets 8,700 shelter kits / 5,954 poles / 2,600 mosquito nets Held in reserve for emergency hurricane season needs. / 22. Breakdown of DFID indirect Assistance provided via UN, Red Cross and NGO partners and the main results: / Partner Main Results / ACF Over 23,000 households benefited from DFID support including: / Up to 75,000 people received daily water supplies (10 litres per day), / Sanitation facilities provided for 115,500 people (up from a target of 75,000 due to high demand) (23,100 families), / 15,275 households received NFI distributions (15,061 hygiene kits and 20,957 water storage and transport kits also distributed) / Cash for work provided to over 87,000 people (against original target of 5,000). This activity benefited from a reallocation of shelter assistance due to resettlement and land ownership issues. / 23,324 households received food distributions, including 50,311 children <5. / ACTED Targeted at providing 3,750 households with emergency assistance, results included / 2,790 family shelter kits distributed, plus 239 NFI kits (plus 138 mattresses), / 9,103 people (1820 families) provided with access to 5 litres of water per day, plus other WASH support / 4,614 people benefited from hygiene sessions / cash for work activities (10,529 unskilled and 536 skilled man days of labour) / emergency stockpile established – 8724 shelter kits, 5,954 pole kits, 2,600 mosquito nets. / 69 Disaster Risk Management Committees established and members trained. / Handicap International DFID provided £0.5m to a £3.1m project so 16% of the figures below can be attributed to DFID support: / 4,527 families received shelter kits (exceeded target due to donations from Shelterbox and IOM) (DFID attribution 724 families); / 8,089 families received NFIs (DFID attribution 1294 families); / 2,210 families received food (DFID attribution 350 families); / 1,181 injured people benefited from hospital rehabilitation sessions (DFID attribution 188 people); / 8,828 people received community based treatment (DFID attribution 1412 people); / 3,275 mobility devices distributed (DFID attribution 524 devices); / 19,834 people received psycho-social support (DFID attribution 3173 people). / IFRC 40% of DFID’s funding was allocated to the purchase of relief items – contributing to meeting the needs of a minimum of 22,500 families; / Emergency shelter items – included 3,498 wood planks, 9,800 ropes; / 36,000 families received water for 22 days (@ 8 litres per person per day) plus other WASH supplies; / Logistics support for deployment of British Red Cross Emergency Response Unit. / IOM DFID contributed 32% of the total costs for IOM’s Camp Coordination, Camp Management Programme (CCCM), overall results were: / training to 1,370 people from CCCM cluster partners, including government departments, NGOs, international organisations, camp committee members, UN military and police (DFID attribution 438 people), / 317,690 households registered in 1,269 camp sites (DFID attribution 101,660 households in 406 camps), / financial assistance to seven Camp Management Agencies (CMAs) provided basic services to 42,000 households in 41 camps/spontaneous settlements. Services provided included WASH, education and health, drainage and disaster risk mitigation, shelter and security (DFID attribution 13,440 households assisted), / CCCM Protection Unit handled case management of vulnerable individuals, monitored forced removals from camps and developed advocacy materials to deal with forced removals from private land; / coordination, technical support and guidance provided to humanitarian partners involved in IDP camps and settlements; / over 2.3m items distributed through logistics pipeline, including WASH, shelter and other NFIs. DFID in-kind NFI items distributed by IOM benefitted 28,669 families. / funding for four CARE secondees provided information management and technical capacity to the shelter cluster. / Merlin A team of highly qualified surgeons were deployed to work on complicated trauma wounds. The UK medical facility was in Haiti for 14 weeks and treated an average 200 patients a day. From these were drawn a smaller number requiring major surgery with 623 operations carried out. Evidence from Haiti demonstrated that UK surgical teams can save lives and limbs if appropriately trained staff were deployed quickly. / Oxfam 12,600 households benefited from the distribution of plastic sheeting; / Cash for work reached 5,229 households (52% of the 10,000 target). Post-earthquake, financial institutions lacked capacity to make payments on time, which undermined the effectiveness of the programme. Unspent budget was reallocated to support WASH activities; / 1,293 latrines constructed. On average there were 154 people using each latrine so in total almost 200,000 people supported; / Public health promotion in camps targeted at 50,000 families. / PAHO Supported the Haitian Ministry of Health’s (MoH) efforts in epidemiological surveillance, disease outbreak and control of communicable disease threat: / 51 sentinel sites established in existing health structures, / 42 sites in IDP temporary settlements); / strengthened the National Laboratory of Public Health (supplies, equipment, specimen collection/transport costs); / prevention and response to communicable disease threats (management, coordination, vaccines etc) including malaria, dengue, tuberculosis, rabies. / UNOPS transitional shelters provided to 135 families; / cash-for-work for approximately 60 skilled / unskilled construction workers involved in shelter building. / Impact Weighting (%): 40% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: Improved effectiveness of the humanitarian and transitional response through support to the architecture of the international system, including the Government of Haiti
Output 3: final score and performance description: A
Final results: / 23. DFID interventions to support the humanitarian system achieved the following results: / Targets Results / GoH and shelter cluster have agreed standards and targets for shelter by mid March 2010 DFID funded secondments filled key strategic gaps in the shelter cluster through technical support, providing specialist support on land and property rights and urban settlement, and helped maintain continuity in the cluster during several cluster lead changes. Guidance available from the Shelter Cluster evolved slowly and considerable variation of design and of international standards were required to overcome the particular difficulties and constraints associated with working in an urban context. / OCHA achieves effective civ/mil coordination and management of information within 3 months. OCHA established a joint government /humanitarian /military body, known as the Project Management Coordination Cell (PMCC) to ensure joint activities were implemented in line with humanitarian principles and priorities. OCHA produced guidelines for civil-military coordination which were endorsed by the Humanitarian Country Team (HCT). / The DFID Information Manager (IM) secondees supported the development of OCHA products, including advocacy on funding needs, maintaining humanitarian data and the Haiti humanitarian response website. OCHA reported that partner feedback indicates that they find these products useful. IM support to clusters and government entities also provided. / GoH is supported to take a leadership role in humanitarian activities from March – July 2010. DFID provided humanitarian advisory support to the Prime Minster’s office for 6 months to assist with the response and recovery processes. This included helping the GoH to coordinate their interactions with the international community, including channelling their own requests more effectively. / WFP aircraft movements are supported and effective from January – March 2010 Air Operations specialist seconded to WFP for 3 months. In addition DFID’s contribution to the WFP Special Operation supported inter-agency storage and base camps, airlifts, coastal vessels with own derricks; logistics coordination, telecommunications and information management. Between January and April 2010, WFP provided emergency food assistance through general food distributions to some 4 million Haitians in Port-au-Prince and earthquake-affected areas. / UNICEF provides effective hygiene and sanitation leadership, while coordinating the WASH cluster and managing information efficiently. DFID provision of WASH and other specialists supported UNICEF’s surge staffing requirements, which it had difficulties meeting quickly from its own internal resources. This helped UNICEF to rapidly get the WASH cluster functioning, coordinate with government partners and deploy cluster staff in strength. It enabled UNICEF to provide water to the affected communities from the fifth day onwards and then throughout the response. However, sanitation remained a challenge in the densely populated urban context of Port-au-Prince. / Haiti Shelter commission (via UNOPS) provides effective engineering coordination, and efficiently manages communications and data UNOPS, working through the CCCM Cluster, was active in the survey and assessment of land suitability for transitional settlement for those displaced. Each site was assessed for current usage, environmental hazards and suitability. UNOPS conducted rapid assessments in February – March 2010 to determine shelter capacity, technical standards being used, and coverage of tents and sheeting. / 3 prisons re-established by June 2010 DFID support through the IOM successfully contributed to the reconstruction and rehabilitation of two prisons (Delmas juvenile detention centre and Arcahaie prison). Sourcing local quality construction materials proved challenging due to the overwhelming demand post-earthquake for rebuilding, and contributed to implementation delays. The full works at Arcahaie were completed in October 2010, and at Delmas by February 2011. In addition. A Stabilisation Unit team provided support more generically (across the prisons services) to security and contingency planning, improved prison administration and raising standards within prisons to meet international standards. / Post Disaster Needs Assessment (PDNA) report and recommendations show clear Community Development advisor inputs To support the PDNA, the Stabilisation Unit funded a Community Development advisor position through the World Bank. The PDNA was finalised by UNDP and the international community in March 2010. It identified needs of $3.9 billion to Dec 2011, and longer-term needs in excess of $11 billion – with 60% of these needs falling in the social sectors, including health, education, nutrition and WASH. The PDNA forms the basis of the GoH’s Action Plan for National Recovery and Development. / Impact Weighting (%): 45% / Revised since last Annual Review? N. / Risk: High / Revised since last Annual Review? N

Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the logframe been changed since the last review? N / 1.2 Final Output score and description: / A – Met expectation
Direct feedback from beneficiaries / 24. Direct feedback was received from beneficiaries during the PCR visit in March 2012. This included feedback from both international and humanitarian stakeholders who received DFID funding, as well as members of the disaster affected population who were direct or indirect recipients of DFID funding. In addition a number of DFID funded partners conducted their own beneficiary surveys. Selected examples include: / The DFID team visited the camp administered by ACF in Champ du Mars, Port au Prince, and spoke to a number of beneficiaries. They were generally positive about the support the camp set-up and support they had received, however many people expressed concerns about the camp clearance and relocation process. On cash for work, ACF maintained regular post-distribution monitoring throughout the project based on a sample of 5% of the target population. On the basis of these results it was found that 90% of targeted households fitted vulnerability criteria, also most interviewed households stressed that cash-for-work earnings were insufficient to cover basic needs. / To deal with beneficiary concerns Oxfam established a freephone hotline (and card system for those without phones) for people to call with concerns and requests for help. This has helped to bridge the communication gap between NGO and the community. More than 40% of calls were related to direct requests for water, shelter, food. / In terms of DFID support to the international humanitarian response system, feedback from the CARE UK evaluation found that the DFID secondments to the shelter cluster made a valuable contribution to cluster coordination in terms of rapid deployment of experienced staff who made important technical contributions to strategy and policy documents.
Overall Outcome score and description: / A – Met expectation / 25. DFID interventions achieved the following results at Outcome level: / Target Results / 80,000 families assisted by DFID provision of assistance by June 2010 74,360 families benefited from DFID assistance. However, this figure may be higher as its not possible to determine whether the same families benefited from more than one type of sectoral assistance. Sector totals are: shelter (29,249), WASH (74,360) and NFIs (61,738). / 10 agencies provided with DFID assistance by June 2010 DFID assistance was provided through 6 NGOs, the IFRC and 6 UN agencies (IOM, PAHO, OCHA, WFP, UNICEF, UNOPS). / Humanitarian coordination system established and fully staffed in the sectors DFID has assisted by week 8 (mid March 2010). DFID funding and 10 specialist secondments to UN Agencies helped provide essential support to a depleted system. Although clusters were rapidly established, all clusters struggled initially with capacity issues and failed to coordinate efficiently the large number of partners involved in the operation. / 3 prisons rehabilitated and functional within 6 months Working closely with the Haitian Ministry of Justice and Director of Prisons, funding provided through IOM contributed to the reconstruction and rehabilitation of two prisons (Delmas juvenile detention centre and Arcahaie prison). A Stabilisation Unit team provided support more generically (across the prisons services) to security and contingency planning, improved prison administration and raising standards within prisons to meet international standards. / Post Disaster Needs Assessment (PDNA) process incorporates and benefits from technical support of a community development adviser. To support the PDNA, the Stabilisation Unit funded a Community Development advisor position through the World Bank. The PDNA was finalised by UNDP and the international community in March 2010. It identified needs of $3.9 billion to Dec 2011, and longer-term needs in excess of $11 billion – with 60% of these needs falling in the social sectors, including health, education, nutrition and WASH. The PDNA forms the basis of the GoH’s Action Plan for National Recovery and Development. / 1.5 Impact and Sustainability / 26. In terms of lives saved and suffering reduced, the UN managed Inter-Agency real time evaluation of the international relief response in Haiti concluded that whilst lives were saved in the aftermath of the earthquake, there were “not that many” and most of those occurred within the first 15-20 days. This is arguable as overall records were not kept for those receiving assistance. Key findings are: / Rescue teams pulled 132 people from the rubble – the UK team saved three people and stayed for some 10 days. / Many lifesaving operations were performed. Whilst no complete figures exist, MSF carried out 11,749 operations and treated 173,757 patients in total; the Red Cross saw 95,000 patients in their temporary clinics. The DFID funded Merlin surgical team treated 7,338 patients of which 150 were complex multiple operations. / Disease surveillance and prevention - No major disease outbreaks were reported in the six months following the earthquake. A national surveillance system was established 2 weeks after the earthquake, which DFID supported through PAHO. / Provision of prompt potable water distribution is believed to have helped prevent diarrhoea outbreaks. One month after the earthquake UNICEF reported 900,000 people in affected areas were receiving 5 litres of water per day. DFID contributed to the work UNICEF and IFRC supported in the sector. / Shelter - A total of 267 camp sites were registered, covering 164,356 households (or 721,106 individuals). Despite these efforts, the shelter response was inadequate, even with such a huge effort (including from DFID). The significant major increase in illness following the earthquake was in acute respiratory infection, normally associated with lack of shelter. Adverse weather conditions damaging shelters and land tenure issues hampered progress in this sector. Congestion in some urban settlements presented a public health risk as well as protection and security issues. / Food distributions consumed much logistics time and effort in the first weeks and accounted for a significant amount of the finance. Evidence is limited on whether it was nutritionally necessary, although it was certainly felt politically necessary by those in charge. / Protection of vulnerable groups-especially children was a priority issue, particularly in terms of their trafficking within and outside of Haiti and care for those left orphaned or separated from family. / The capacity of the health sector remained low. Many hospitals damaged by the quake eventually closed and the number of health personnel per 10,000 population is reportedly low. As the majority of health services are delivered through the private sector a large part of the population does not have access to health services. / Sanitation: The Consolidated Appeals Process (CAP) reported that 11,000 toilets were constructed within 3 months, but average coverage was low at 200 people per toilet (sphere standard is 20). However, there is evidence that open defecation is low (5-15% WASH Cluster Survey, February 2010). Many people continue to return to damaged homes or use neighbours facilities, or plastic bags which are deposited in solid waste receptacles. Challenges identified included the lack of space to build latrines due to dense urban environment, inability to construct pits due to concreted in sites, land tenure issues where landowners do not allow construction and the issue of “ghost camps” where it is not clear how many permanent residents are residing in certain camps. / 27. In terms of sustainability, shelter relief items provided by the international community were of varying quality, indeed much stock is already degrading and will need to be replaced in the near future. DFID and others provided support to designing and building transitional shelters, which are sturdier structures that can provide better protection and are more spacious than emergency shelter materials. / 28. The sustainability of WASH activities is also an issue. By the end of May 2010, 5 litres of safe water per person per day was being delivered to approximately 1.1 million people in 500 sites. This involved daily tankering of 6,000 m3 of water. The challenge is to maintain quantities over time, and eventually replace water trucking operations with more sustainable medium term options such as increasing connections, repairing the network and borehole drilling. / 29. DFID’s strategy did not consider in detail any transitional arrangements or exit strategy. The sudden reduction in donor funding when the emergency phase was completed is proving problematic, especially given the Haitian Government’s lack of capability to move resources into this vacuum. Building transitional and exit arrangements into humanitarian response planning could have helped mitigate the problems caused by the abrupt reduction in donor funding. / 30. Post earthquake, longer term structural interventions need to be found in both food security and agriculture sectors, including to rebuild the agricultural sector; support economic growth in rural areas; safeguard and improve food security; and create employment and livelihood opportunities for rural populations and internally displaced people.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / 31. The project was completed within budget - £18.5m was eventually disbursed, out of a total funding envelope of up to £20 million. Individual components were completed within their respective budgets. / 2.2 Key cost drivers / 32. For both direct and indirect assistance the key cost drivers were related to the deployment of humanitarian and other specialists and the delivery of relief items and equipment. These were: / Flights: DFID used its service contract with its air broker to charter aircraft to deliver DFID stockpile items and other procured goods to Haiti. The air broker was also used to deploy the UK Search and Rescue team to Haiti. The key cost driver for this activity was the difficulty of finding an appropriate flight (commercial or charter) at very short notice. Total flight costs amounted to £1.95m. / Staff deployments and related support costs: DFID deployed its Operations Team for initial humanitarian assessment and ongoing specialist advice and support for 6 month period. The total cost amounted to £2.2m. OT deployment costs were kept down by ensuring core staff were deployed first, and where additional resources were required, fee rates were kept down by moving staff onto longer term lower fee contracts as soon as feasible. Additional costs included office and living accommodation, which had to be arranged as there was no DFID office or UK Embassy in Port-au-Prince, and many hotels had been destroyed or damaged in the earthquake. Fee rates for secondments to UN agencies were at market rates. / Security costs: Haiti is a fragile and insecure environment, even more so post-earthquake. A local security company was used to provide the security arrangements for the OT team and seconded personnel for a period of 6 months at total cost of £1m. / NFIs were provided from the DFID stockpile in Dubai, or purchased from the most accessible and expeditious market source of supply to meet emergency needs. Total cost of these items was £2.45m – and included vehicles for use in the delivery of items and humanitarian operations. / Management fees: Arrangements were in line with pre-agreed rates agreed with UN agencies and NGOs through Framework Agreements and Accountable Grants. / 2.3 Was the project completed within the expected timescale: Y / 33. The majority of activities were completed within the 6 month January – June 2010 timescale for the project. There were Components which continued for longer, these were: / CARE – DFID funded secondments for the shelter cluster (Aug 10 to July 11) / IOM – an extension was granted until 30 September 2010 to take account of delays encountered by some camp service management providers, caused by challenges with IDP return to place of origin, camp committee and service provider coordination, weather related delays. The extension allowed IOM and its partners to provide supplementary services and complete contingency planning for the hurricane season. / ACTED – DFID provided funding for an additional year to ACTED to support structural damage assessments of 12,000 buildings and repair of over 300 damaged houses, enabling earthquake affected households to return home. Funding was from the DFID Caribbean budget, with CHASE advisory support, as it fitted into their ongoing engagement on reconstruction issues.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / 34. The DFID response was based upon assessments and information from agencies present in Haiti, agency headquarters and other donors. The findings of a CHASE assessment mission which arrived in country on 14 January 2010 further informed the response. The Project Document was updated 4 times in part to reflect any budget changes and/or changes in the humanitarian situation on the ground. The impact and outcome of the project did not change. / 35. Outputs were consolidated during the course of the project to incorporate diverse aims and impacts. While continuing to monitor needs in all key sectors, DFID focused direct support on alleviating the critical needs in shelter and sanitation, primarily through strategic level engagement and provision of key technical, managerial, coordination and advisory capacity within government as well as within the cluster system. / 3.2 Set out what plans are in place for an evaluation. / 36. The Haiti earthquake response was reviewed as part of the Humanitarian Emergency Response Review (HERR) published in 2011, and informed the conclusions of the main HERR report http://www.dfid.gov.uk/what-we-do/key-issues/humanitarian-disasters-and-emergencies/how-we-respond/humanitarian-emergency-response-review/ / 37. The overall international humanitarian response to the earthquake has been widely reviewed and evaluated by various actors. / 38. DFID conducted an internal lessons learning exercise in mid 2010, and a review team visited Haiti in March 2012 for purpose of completing the PCR and further lesson learning. An earlier review planned for June 2011 had to be postponed due to conflicting work priorities.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? N / Risk funds not used for purposes intended / 39. This response was classed medium risk due to the evolving nature of needs, partner capacity and operating environment at this point. DFID’s strategy prioritised working with tried and tested funding partners with demonstrable ability to deliver and relevant experience in Haiti, as well as appropriate security arrangements. In line with the Good Humanitarian Donorship (GHD) initiative, the response strategy included working through multilateral partners and NGOs and retaining flexibility to respond – DFID’s strength in humanitarian situations. / 40. Reporting from some partners was poor, with limited information, regarding progress, challenges and lessons learnt. This meant monitoring progress against agreed outputs was difficult. In some cases, information regarding financial expenditure was very limited, for example, a detailed breakdown of local partner costs would have been useful. / 4.3 Climate and Environment Impact / 41. Haiti is a high risk country for hurricane and other severe weather related events. This was recognised by DFID and partners and an element of preparedness and contingency was built into most projects. / 42. A number of components included building resilience to climate and other shocks. For example, in preparation for the hurricane season ACTED established an emergency stockpile of shelter items; and UNOPs developed a transitional shelter designed to be more resilient to future earthquake shocks. / 43. Weather related events did have an impact on programme delivery. IOM reported that several storms caused severe damage to IDP camps, aggravating the humanitarian emergency caused by the earthquake. In response, the IOM project supported CCCM partners to regularly complete canal clearing and other mitigation work to prevent flooding. Additionally, IOM supported the GoH in the development and implementation of an emergency preparedness strategy.

5. Value for Money
5.1 Performance on VfM measures / 44. Value for money has been assessed taking into account the three key components of the humanitarian value for money triangle: cost, quality/appropriateness and speed/timeliness: / Cost: DFID supported a range of interventions in the Haiti response, whilst all had value in saving lives and reducing suffering, some reached greater numbers of people. For example, in terms of lives saved the humanitarian cost effectiveness of search and rescue operations was over £250,000 per life saved, compared to around £2,500 per life saved for surgical teams. / Quality/Appropriatness: DFID assistance was viewed as high quality. The direct provision of shelter and other NFIs was well received. The support provided through the UN and NGOs focused on supporting sectors where there were clear needs and gaps. The specialist secondments to support the humanitarian system proved effective in filling staffing gaps and in providing technical advice in key areas. / Speed/timeliness: DFID mobilised immediately: humanitarian assessment teams, UKISAR and medical teams were on the ground within the first few days. Emergency supplies were delivered promptly, despite the difficulties with access to the affected areas, and good use was made of partners to ensure emergency supplies were delivered to where they were most needed. / 5.2 Commercial Improvement and Value for Money / 45. Deployment of personnel and provision of emergency supplies were sourced directly through DFID’s service contract with Crown Agents. Due to the need to respond rapidly in a humanitarian crisis it is not feasible to apply standard procurement processes. However, there is a competitive market for these types of services and DFID ensures that our service contracts and pre-qualifying arrangements offer value for money and are open to competition when the contracts come up for renewal. / 46. Assistance provided through the UN and NGOs was based on previous experience of working with these organisations in Haiti and which organisations were best placed to deliver effective assistance. The Haiti earthquake response predates the work done for the Multilateral Aid Review (MAR) which assessed the value for money of contributing funds through multilateral organisations, and for the future will provide DFID with better evidence to take decisions on how to deliver funding through multilaterals to make the greatest impact. DFID has developed core funding Business Cases with agencies to serve as institutional strategies and include analysis that can be drawn on when completing country specific business cases. / 5.3 Role of project partners / 47. DFID provided a considerable amount of assistance through project partners, and secondments were also useful in supporting a weakened UN system. / 48. DFIDs use of project partners to distribute NFIs to affected areas did not always go as smoothly as planned. For example, IOM experienced major difficulties when acting as consignee for two batches of DFID NFIs, received in late January and February 2010. There were delays of several weeks regarding IOMs onward distribution of NFIs, and issues regarding accounting for those distributions. To speed up the process DFID recommended that on receipt of goods IOM should immediately allocate items to a cluster partner, this system was used during the distribution of the second consignment. / 49. The criteria covering how DFID project partners select partners to act as camp management agencies could have been clearer. For example, it was unclear why some relatively inexperienced NGOs were selected as camp management agencies. / 5.4 Did the project represent Value for Money : Y

6. Conditionality
6.1 Update on specific conditions / Not applicable.

7. Conclusions
50. DFID responded rapidly to the Haiti earthquake. The scale and impact of the disaster was recognised and mobilisation decisions were taken quickly. The CHASE field team deployed immediately. The first decisions were made quickly on the basis of experience, before any data was available. These appear to have been the right decisions based on the impact data. Later, decision-making was informed by the field team, and these decisions too appear to have been largely the right ones. / 51. DFID’s arrangements for deployment of search and rescue teams provided by the UK Fire and Rescue Service was effective, and despite very congested and heavily controlled US management of Haitian air space a 64 strong search and rescue team arrived in Haiti on day two. / 52. The deployment of the DFID-funded Merlin surgical team to Haiti was a success. Despite many other surgical teams and field hospitals present in Haiti, the Merlin team were able to play a important role, saving crushed limbs whereas other teams were amputating. As a result DFID is establishing a standing arrangement for UK surgical teams to be quickly deployed during future humanitarian emergency responses. / 53. DFID delivered a significant amount of relief supplies - 313 metric tonnes of relief supplies on ten flights and some 300 metric tonnes on RFA Largs Bay. Supplies were focused on meeting the most pressing needs – water, sanitation, shelter and ways of overcoming logistics/supply bottlenecks – and required assessment of partner procurement and delivery capability. / 54. The main challenges in key sectors were: / Relief: distributing relief at this scale in an urban environment, with fluctuating numbers of displaced people in settlements, spontaneous new camps developing and security issues. / Shelter: needs were unprecedented. Over 2 million people were displaced with 1.3 million people finding refuge in settlements. Major challenges included a lack of space to install shelter; land rights and access issues; and high population movement, with families moving from camp to camp. / Water, sanitation and hygiene promotion: Access to water and sanitation was already extremely low before the earthquake. The earthquake exacerbated the situation. Indeed SPHERE indicators for the optimum number of latrines could not be followed, and one latrine for every one hundred persons was adopted a more realistic target. Working in a crowded urban context proved challenging and innovative solutions had to be found. / Logistical support: Challenges were the availability of trucks and access due to the poor state of roads and bridges. During the first 3 months there was a critical shortage of fuel. Customs clearance was another challenge. / 55. DFID funded secondments to the international system were well received by partners, and provided a wide range of specialist skills ensuring strategic issues were better addressed. This was particularly important for United Nations agencies in Haiti which had been devastated by the earthquake. DFID support enabled UN Agencies to quickly fill vacant positions with specialist support, and provide support to the cluster system which was overwhelmed in the early stages of the response. DFID support focused mainly on the water and sanitation, shelter and co-ordination clusters. / 56. DFID provided a humanitarian adviser to the office of the Haitian Prime Minister. This reflected the reality that an affected government, however weak, has to play a central role in humanitarian leadership and co-ordination; and donors and international agencies should not by-pass national government, but should support and respect their efforts and not exclusively support international agencies and NGOs. / 57. DFID’s strategy responded to immediate humanitarian need only. The strategy did not consider in detail any transitional arrangements or exit strategy. It is arguable that DFID ceased funding too early, leaving humanitarian needs unmet. But given DFID’s limited aims and role in the response it is equally arguable whether DFID should have remained engaged for longer. By building in transitional and exit arrangements from the beginning of a response, DFID could have better mitigated the risks that rapid exit causes. The pre-existing conditions in Haiti however meant that transitional arrangements could only mitigate these problems to a limited extent.

8. Review Process
58. A multidisciplinary DFID team visited Haiti in March 2012 to review the impact of both the Haiti earthquake and cholera programmes. The Team consisted of Dylan Winder (Team Leader), Jack Jones, Tanya Axisa, Matthew Benson, Lucy Earle and Andrew Jordan. The team reviewed project documentation and met with partners and beneficiaries. The PCR was completed on return to the UK.