Type of Review: Project Completion Review

Project Title: Consortium of British Humanitarian Agencies

Date started: March 2010	Date review undertaken: 22 May 2012
## Introduction and Context
What support did the UK provide?
The UK provided £8m to the Consortium of British Humanitarian Agencies (CBHA), to fund and resource humanitarian responses which strengthen the coordination and capacity of the "third pillar" - the NGO sector - to deliver appropriate, higher quality, more effective and quicker humanitarian responses. Funding was provided for period March 2010 to March 2012.

What were the expected results?
Outcome: New approaches pioneered to fund and resource humanitarian responses which strengthen the coordination and capacity of the "third pillar" - the NGO sector - to deliver appropriate, higher quality, more effective and quicker humanitarian responses. The overall indicators were: / consortium set up; / NGO members remain active in the governance of the CBHA; / donors choose to channel further funding through CBHA; / increase in the capacity of member agencies to respond to humanitarian crises; / and, during and after 2 year period DFID will sign up for further funding or other donors will be funding the project. / Expected results at the output level / Output 1. Emergency Response Fund (ERF) resources allocated and used to meet the criteria to reduce suffering, morbidity and mortality in humanitarian emergencies. Decisions for consortium to respond and allocation of funding made within 36 hours of emergency occurring. The ERF is a reliable funding mechanism that meets a proportion of NGO early response resourcing needs and allows members to respond more quickly and effectively – activities start in 7 days and are completed in 30 days. / Output 2. The Capacity Building Programme of the CBHA increases the numbers and competencies of potential humanitarian leaders, as well as the overall humanitarian skills and knowledge base of existing staff, in three objective areas. The first area establishes a shared competency and leadership behaviour framework that forms a basis for the other two programmes. The second develops humanitarian skills and leadership competencies of existing staff at national and regional level. The third increases the pool of internationally available humanitarian leaders through a humanitarian apprenticeship training programme based in UK and the Horn of Africa. / Horn of Africa / 80% of trainees have completed training programme. / UK / 80% of trainees have completed training programme. / Upon completion, participants progress against at least 50% of humanitarian and leadership competencies. At least 70% of participants are working in emergency context or fragile states in the humanitarian sector, 50% of those in leadership roles (1 year after cycle ends). / Output 3. Surge capacity of the organisations and sector to rapidly and effectively increase (the sum of its) available resources in a specific geographic location in order to meet increased demand or stabilise a situation. Surge capacity can also be understood as the ability to respond effectively to surprising events. CBHA’s third output is designed to ensure Consortium member agencies have available standing capacity to respond quickly and effectively to new emergencies. / Output 4. At least four CBHA members have prepared outline business cases targeting more effective supply and cost reductions based on actual use of a supply chain system. At least four CBHA agencies will have evaluated HELIOS – a web based supply chain solution designed specifically for humanitarian logistics – for functional fit and business benefit in their organisations. Helios was designed to increase operational efficiency by automating recurring processes and thereby improve transparency, save money and reduce wastage. / Output 5. Evidence available to assess the effectiveness of the programme in the first two years, which is integrated into future strategic planning of the CBHA. All activities of the CBHA pilot emphasise monitoring, learning and evaluation. End of project: / 1 final global review of 5 outputs made by external consultant; / 1 information hub; / 2 learning workshops; / 3 learning papers are produced; / 1 Strategic Planning Workshop; including analysis of reviews; and learning products.

What was the context in which UK support was provided?
The CBHA, consisting of 15 of the leading UK NGOs, was created through DFID’s 2009 call for proposals for the Conflict, Humanitarian and Security Fund (CHSF). The CBHA is not an organisation in the traditional sense rather it is an inter-organisational collaboration – a virtual organisation that consists of a governance structure, decentralised projects, systems of feedback and accountability, and a set of formal and informal agreements, procedures and relationships. The CBHA was enabled by two legal agreements between all 15 members, and is governed by a board of humanitarian department directors or equivalent from all members, each with an equal vote. The programme was implemented through an MOU with Save The Children acting on behalf of the consortium. / Activities were implemented by member agencies on behalf of the consortium, and governed by elected sub-committees. A three-person Programme Management Unit (PMU) hosted by Save the Children, provided co-ordination, reporting and facilitation services to the Consortium. CAFOD chaired the CBHA over the two-year pilot, and Concern and World Vision held the vice-chair position. / The CBHA sought to address, in partnership with DFID, key gaps and weaknesses in the current system which significantly affected their ability to respond effectively and quickly to emergencies. Issues included lack of available immediate funding, key materials and supplies. The CBHA was created to strengthen the results achieved by the civil society ‘third pillar’ of the international humanitarian system – NGOs. Activities were implemented in five areas that addressed long-standing challenges in NGO performance.

## Section A: Detailed Output Scoring

Output 1: Consortium member agencies have immediate access to emergency response funding enabling them to mount focused and effective field operations in the immediate aftermath of a disaster or other crisis.
Output 1: final score and performance description: / A++ Output substantially exceeded expectation.
The ERF mechanism has functioned successfully with all £4m budget used in 12 separate global emergencies 2010-12 assisting over 1 million beneficiaries. ERF funds have been allocated within a quicker timeframe than envisaged to agencies for crises in Kyrgyzstan, Pakistan, Myanmar, Sri Lanka, Somalia, Liberia, Horn of Africa, South Sudan, Bangladesh, India, and Central America.[1] / Over the two years the structure and processes of the ERF were continually refined, and currently exist as follows. The ERF was established with a separate legal agreement between the 15 agencies, with Save the Children acting as lead facilitating member. Potential crisis investments were discussed in full-consortium teleconferences, and if an investment was agreed, the amount was decided by vote. A strict set of procedures and timelines was followed within an overall 72 hour period between crisis onset and bank transfer. Each grant was made in the form of a sub-grant between Save the Children and the implementing organization. An elected sub-committee of 5 board members made decisions on individual grant awards, according to a mixture of formal and informal criteria in the context of peer review. Application and reporting formats were continually improved over the two years to enhance decision-making, improve transparency, and reduce bureaucracy. The Programme Management Unit provided financial and programmatic oversight, while the learning and evaluation sub-committee explored options for peer-based accountability and quality assurance. / Impact Weighting (%): 30 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[1] Further detailed information on outputs and results can be found in the CBHA’s overview of ERF response: http://www.thecbha.org/news/2012/03/08/cbha-emergency-response-fund-overview-2-years/

Output 2: Increased numbers and competencies of leaders through developing a competency framework and delivering it through both National and international programmes.
Output 2: final score and performance description: / A+ Output substantially exceeded expectation.
The CBHA final external evaluation thoroughly investigated the three capacity building programmes, and concluded that all delivered upon their targets, and in some cases exceeded expectations. For example, the core competency framework has quickly achieved a surprising level of acceptance in the sector. As a result of this two year pilot, the humanitarian sector now has three well-tested talent development products which are freely available and ready to be taken to scale. / Initial aspirations to incorporate national government officials into the programme were not met. The programme addressed middle level leaders, rather than the originally aspired senior level leaders. The evaluation concluded that this component was more of an extension of pre-existing organisational routines than a strategically designed programme to address civil society capacity for humanitarian response. This is understandable considering that the CBHA was a first experiment in collaborative capacity building between organisations. Yet, in spite of its flaws, the programme created initiatives with transformative potential. For example, the trainee scheme offers more features (such as coaching) than its potential equivalent, the UN Junior Programme Officer scheme (JPO), yet it is several times less expensive. This programme therefore provided good value for money for the British taxpayer. / CBHA core competency and leadership behaviour framework was agreed and signed off in August 2010. The corresponding training curriculum content of national and international programmes was designed and used in training programmes. The framework was reviewed and revised following practical testing and feedback and an online guide developed for practical application. Branding, design and marketing for launch of final framework have been completed. / 77 (target 80) participants in four countries were trained in core humanitarian skills and 75 participants in four countries trained in management and leadership skills development. Use of learning and improved performance have been closely tracked by coaches. [2] / Horn of Africa 1: / 12 out of 14 trainees (86%) successfully completed the Horn of Africa training programme (both capital and regional deployment) in August 2011, / UK: / 13 out of 13 trainees (100%) are on track to complete the UK cycle in March, and are currently on field placements, / Horn of Africa 2: / trainees currently participating in 2nd Horn of Africa programme, due to complete in Aug 2012 (Letter of agreement with DFID for extension of programme agreed). All participants confirmed their progress against core competencies in 1 to 1 meetings and self assessments. All participants of the first cycle (1 year after) are working in the humanitarian sector (Horn of Africa), with more than 50% of them in central emergency response positions. / Impact Weighting (%): 30 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[2] Further detailed information on outputs and results can be found in the CBHA’s overview of ERF response: http://www.thecbha.org/news/2012/03/08/cbha-emergency-response-fund-overview-2-years/

Output 3: Consortium member agencies have available standing capacity to respond quickly and effectively to emergencies
Output 3: final score and performance description: / A+ Output moderately exceeded expectation
Final results: / All CBHA agencies successfully secured surge grants and reported this funding to have increased their capacity. ERF summary is presented in table below: / Emergency ERF activities (percentage breakdown) Total number of people affected Total number of direct beneficiaries from ERF activities Budget / Planned Actual / Kyrgyzstan Ethnic Conflict June/July 2010 Food/Cash Assistance 50%; Hygiene kits 48%; First Aid Kits 2% 560,000 (IDPS/returnees/host families) 26,125 (4.7% of affected population) 24,863 (4.4% of affected population) £161,212 / Pakistan Floods July/August 2010 Health 43%; Hygiene kits 23%; NFI kits 12%; Food assistance 10%; Shelter 7%; water 5% 21,000,000 215, 306 (1.03% of the affected population) 201,118 (0.96% of the affected population) £750,033 / Myanmar Cyclone Giri October/November 2010 NFI kits 44%; Shelter 32% Food assistance 24%. 260,000 27,850 (10.7% of affected population) 49,655 (19.1% of affected population) £450,000 / Sri Lanka Floods January/February 2011 NFI kits 46%; Food assistance 39%; Health 5%; Clothing 5%; Physcosocial 4%; Infant kits 1%. 991,467* 39,605 (3.99% of affected population) 55,086 (5.56% of affected population) £287,169 / Somalia Drought February/March 2011 Water trucking and hygiene promotion 96%; cash distribution 3%; Healthcare and provision of drugs 1%. 2.4 million 151, 528 (6.3% of the affected population) 187,811 (7.8% of the affected population) £440,707 / Ivorian Refugee Crisis March / April 2011 Health activities 66%; Protection/camp management 27%; NFI distribution 7%. 150,000 72,675 (48.5% of affected population) 37,488 (25% of affected population) £197,046 / Horn of Africa Crisis April / May 2011 Water supply 80%; De-stocking (cash) 10%; Food assistance 6%; Animal health 4%. 8,800,000 203,728 (2.3% of the affected population) 265,658 (3% of the affected population) £555,814 / Sudan IDP Crisis (South Kordofan) June/July 2011 NFI Packages 100%. 200,000 21,220 (11% of the affected population) 29,200 (15% of the affected population) £181,431 / Pakistan Floods August/September 2011 Shelter kits 67%; Hygiene kits 14%; Food 10%; Water 9%. 5,400,000* 39,562 (0.73% of the affected population) 32,875 (0.61% of the affected population) £200,000 / Bangladesh Floods August/September 2011 NFIs (WASH and household) 45%; Food 39%; Shelter 15%; Mobility aids 1%. 1,250,000* 86,275 (6.9% of the affected population) 90,713 (7.3% of the affected population) £325,000 / India Floods September / October 2011 Shelter 46%; NFIs (WASH and household) 29%; Livelihood 12%; Nutrition 11%; Food 5%; WASH 5%. 1,700,000*1,700,000* 52,425 (3.1% of the affected population) 265,658 (15.6% of the affected population) £222,000 / Central American Floods October / November 2011 Food Aid 44%; NFIs 34%; Water 16%; Health 3%; FSL 3%. 342,247 29,624 (8.7% of the affected population) 29,624 (8.7% of the affected population) £219,981 / Impact Weighting (%): 15 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
Output 4: Improve the ability for organisations to respond more efficiently in humanitarian and relief work through the adoption of information technology and best practices in the control of their supply chains . / Bring these improvements to both individual CBHA agencies as well as the wider community by supporting proof of concept HELIOS pilots and the writing of outline business cases. / Develop the processes and tools to allow multiple agencies to share supply chain information to improve joint responses in emergencies. / Make available generated learning and tools to the wider community.
Output 4: final score and performance description: / A Output met expectation
Five CBHA member agencies have run pilot tests of the Helios system and prepared business cases for an integrated supply chain management system. A HELIOS working group has met regularly throughout the project. Multi agency evaluation of benefits of shared supply chain information completed. Questionnaires completed and reviewed. Report on website material prepared by Islamic Relief (non-participating agency). Generated learning and tools have been made available to the wider community through the HELIOS website: http://www.helios-foundation.org/docs/ / Impact Weighting (%): 5 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 5: Evidence is available to assess the effectiveness of the programme in the first two years and it is integrated in future strategic planning of the CBHA
Output 5: final score and performance description: / A+ Output moderately exceeded expectation
Real Time Evaluation Toolkit piloted in several emergencies in 2010. Baseline assessment completed in May 2010. Mid term and final global review of 5 outputs has been completed. CBHA Extranet has been developed. 3 Learning Workshops (ERF, Surge, Capacity Building) have taken place and been reported on through either learning papers or videos. Strategic Planning & Final Evaluation Workshop took place on the 5th of March. [3] / Impact Weighting (%): 30 / Revised since last Annual Review? Yes (revised from 20) / Risk: Low / Revised since last Annual Review? No
[3] Further detailed information on outputs and results can be found in the CBHA’s overview of ERF response: http://www.thecbha.org/news/2012/03/08/cbha-emergency-response-fund-overview-2-years/

## Section B: Results and Value for Money.

1. Achievement and Results
Has the logframe been changed since the last review? No. / 1.2 Final Output score: A+ Outputs moderately exceed expectation.
Direct feedback from beneficiaries / Accountability to beneficiaries was managed at the level of each consortium member. Real time as well as other evaluations were conducted, which are accessible on the CBHA website.[4] For example, feedback from the CBHA’s largest response in Pakistan 2010 included: “Beneficiaries’ satisfaction was high. Beneficiaries particularly appreciated cash-based interventions providing them with flexibility concerning the use of transferred resources”.[5]
Overall Outcome score and description: / The target for outcome was an increase in the capacity of member agencies to respond to humanitarian crises. During and after the two year period DFID would sign up for further funding and/or other donors will be funding the project. The CBHA strengthened the capacity of the British NGOs to deliver results to people affected by emergencies. Where used the ERF increased access to fast, efficient and effective funding fostering front-line humanitarian work. CBHA capacity building programmes strengthened the humanitarian competencies of new, junior and mid-level humanitarian workers; for the first time a core competencies framework was developed, endorsed and used by a group of INGOs with networks that jointly cover the globe. The CBHA effectively served as an incubator that moved the long standing capacity building agenda forward in a step change. In some organisations the CBHA proved the concept of surge capacity and has raised the internal priority of having such surge capacity. / 1.5 Impact and Sustainability / At the end of the two year pilot, CBHA members are convinced of the value of the Consortium, and are preparing to scale this up across the entire civil society pillar of the humanitarian sector. This is evidenced by the fact that member agencies have put their own independent resources into the Consortium as a bridge until the next round of institutional funding can be secured. The CBHA has two overarching priorities in 2012: exploring new business models and securing funding for an expanded independent global civil society emergency fund; and developing an expanded capacity building programme for civil society actors in humanitarian action – from communities, to local partner organisations, to international NGOs and non-traditional non-political actors. If other donors are on board then the project will be sustained.
[4] http://www.thecbha.org
[5] http://www.thecbha.org/media/website/file/CBHA_Pakistan_Final_Evaluation_Report.pdf

2. Costs and timescale
Was the project completed within budget / expected costs: / £ 8m from DFID core funding. Interest received on funds invested with the assistance of Save The Children finance department totalled £ 73,533. The Budget was revised to include this income, and to reallocate savings of £28k on the Helios project. The additional income was allocated to the Knowledge and Learning programme, to Capacity Building programmes 2 and 3, and to the PMU budget to cover expenses related to communications and strategy. / Key cost drivers / CBHA Summary Budget vs / Actual - February 2011 DFID / contribution Revised / Budget Actual to / Feb 2012 Percentage / of budget / to date Mar - Aug / 2012 / budget Total to / Aug 2012 / Knowledge and learning 40,125 66,394 64,832 98% 64,832 / ERF Fund 3,999,660 3,999,660 4,016,545 100% 4,016,545 / Capacity / Building Surge 1,650,000 1,650,000 1,629,603 99% 1,629,603 / Obj 1 + / mngmt 206,671 206,671 206,669 100% 206,669 / Obj 2 720,110 731,692 731,692 100% 731,692 / Obj 3 635,349 679,226 492,739 73% 186,487 679,226 / Cap sub-total 3,212,130 3,267,589 3,060,703 94% 186,487 3,247,190 / Helios Project delivery 371, 178 343,031 343,031 100% 343,031 / PMU - subtotal Staff and / running 350,158 396,859 401,935 100% 401,935 / Total 8,000,000 8,073,533 7,887,046 98% 186,487 8,073,533 / 2.3 Was the project completed within the expected timescale: Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Substantial evidence was submitted to DFID in the CBHA’s Second Year Report to DFID, which has fed into this PCR.[6] No evidence emerged that impacted on theory of change. / 3.2 Set out what plans are in place for an evaluation. / No further evaluation after this PCR is planned by DFID. There was an independent review conducted by DARA and Action Against Hunger.[7] Its key recommendations were: / The CBHA should consider dropping the tag “British” while maintaining a requirement for regular face-to-face meetings. The model could be replicated in other countries with the support of existing members’ families and networks. / The CBHA secretariat should continue its effort to obtain alternative funding in order to maintain the ERF and increase member agencies capacity to respond to low-profile emergencies. / The next phase of the ERF could include the plan to develop a mechanism for an NGO emergency fund that would function similarly to the CERF but would be open internationally and not just to British CBHA members as at present. / There is a continuing need for a peer mechanism for addressing specific blockages to more effective humanitarian action in the sector. The CBHA need to continue in some form to provide a platform for launching such initiatives. / The DEC and the CBHA should conduct a dialogue to explore both the possibility and modalities of having the CBHA as a sub-project of the DEC. / CBHA agencies should review whether the current institutional location of humanitarian departments is appropriate given the critical importance of humanitarian action to organisation growth and sustainability.
[6] http://www.thecbha.org/news/2012/03/19/cbha-second-year-report/
[7] http://www.thecbha.org/resources/

4. Risk
Risk Rating (overall project risk): Low / Did the Risk Rating change over the life of the project? No / Risk funds not used for purposes intended / This project did not include any risk funds. / Climate and Environment Impact / This project did not include climate and environmental impacts.

5. Value for Money
Performance on VfM measures / Cost: the project was broadly delivered within the initial costs set out in the business case, noting the additional £73,533 received on funds invested with the assistance of Save the Children finance department. Expected outputs were delivered. / Quality: on the whole, the project delivered a quality and appropriate response necessary to achieve the project outcomes. / Speed/timeliness: There was some delay to projected completion of output two, but this was achieved by the end of the project. The response time under the ERF was particularly impressive. / Commercial Improvement and Value for Money / The project was not delivered through DFID direct assistance. There is limited information on partner procurement or commercial capabilities or improvements that occurred. On 12 April 2011 DFID was informed that one of Chritian Aid's partners uncovered an instance of fraud in the procurement of emergency food items by one of their local partners in the CBHA funded emergency response to Cyclone Giri in Myanmar. Full information on the amounts involved and the follow up by both Metta and Christian Aid was provided to DFID. This was referred to DFID’s counter fraud unit. Metta (Christian Aid's partner) covered the loss by making up the shortfall in the rice distribution from their own funds, so there was no impact on what was delivered to beneficiaries. / Role of project partners / All members of CBHA played an active role. / Did the project represent Value for Money : Yes.

6. Conditionality
Update on specific conditions / N/A

7. Conclusions
The CBHA theory of change over the pilot was based on developing and testing innovations that will improve the ‘third pillar’ when they are taken to scale in the future. It is safe to conclude that this pilot programme has created three capacity development programmes that are ready to be taken to scale. The Emergency Response Fund has also proven itself and is ready for evolution. In other areas, the CBHA has generated new knowledge about surge capacity, business process analysis and supply chain management automation. The consortium has also contributed to the humanitarian sector’s knowledge about national-level NGO consortia for early recovery projects, and about inter-organisational collaboration at the global level. / The intangible and unanticipated benefits of consorting have also been of considerable value to the members. For example, the peer review methodology for project selection and report review used in the ERF enabled the members to benchmark their performance against one another. This ‘friendly competition’ did drive up the quality of proposals submitted to the CBHA, and likely had an impact on agency performance. Another example emerges from the boundary-spanning relationships established amongst Consortium members. This increased information and knowledge exchange between the members, and increased the likelihood of informal cooperation around specific crises and issues. A third example emerges from the creation of a single access point to the 15 agencies. / This access point was capitalised upon by the newly in-post UN humanitarian chief Valerie Amos, the Ashdown Humanitarian Emergency Response Review, and by numerous external stakeholders seeking to engage with the civil society pillar of the international humanitarian response system. It would be equally plausible to speculate that the CBHA was able to influence DFID and other external stakeholders more strongly than a single member. A fourth example emerges from the confidence the consortium obtained from the capacity building programme. Over the first two years, the CBHA proved that by working together NGOs could influence the approach to staff development across the sector through its core competency framework. Finally, by tackling a sector-wide issue such as NGO capacity and capability, the CBHA discovered and contributed a unique civil society perspective to an ongoing conversation about 21st Century humanitarian challenges. With NGOs implementing some 80% of humanitarian operational work, this contribution could be fundamentally important. / In response to the central thesis of the HERR (that the scale of 21st Century Humanitarian challenges were exceeding the capacity of the humanitarian system), the CBHA has adopted a comprehensive approach to civil society strengthening. A new CBHA programme will emerge in 2012 with four components: community resilience strengthening; individual talent development; organisational development; and a platform for leveraging the capacity of the consortium. / This two-year pilot required two legally binding agreements between the UK headquarters of the 15 member organisations, which in turn unlocked an unprecedented network of civil society organisations engaged in humanitarian action. This network is present in 140 countries, employs 347,000 people, works through 2450 local partner organisations, and served 350 million people in 2010 through $12.9 billion in relief and development work. While the CBHA has met or exceeded all its targets agreed in the MOU, the process of consorting has also allowed the transformative potential of the CBHA to become apparent.

8. Review Process
DFID and CBHA agreed a DFID managed joint approach to the evaluation. This project completion report therefore draws heavily from and incorporates sections of CBHA’s second year report to DFID and the independent review by DARA and Action Against Hunger. The project completion report also includes desk based review of all project documentation.