Type of Review: Project Completion Review

Project Title: Congo Basin Forest Fund (CBFF) Start-up Programme

Date started: 01/04/2008	Date review undertaken: June 2012

## Introduction and Context
What support did the UK provide?
In 2008, the UK provided £10 million to the Congo Basin Forest Fund (CBFF) start-up programme, established and managed directly by DFID. / As a result of preliminary work and discussions with key stakeholders in the Congo Basin region, the programme was designed to achieve two broad objectives: / Firstly, the start-up programme aimed to facilitate the establishment of the main Congo Basin Forest Fund (CBFF), housed at the African Development Bank (AfDB). / Secondly, recognising that this would take some time, the CBFF start-up programme also supported a number of start-up activities which aimed to demonstrate to central African governments and other stakeholders the kinds of activities that the main CBFF would support. In particular, the start-up activities set out to illustrate that the CBFF would focus on initiatives providing local communities with sustainable livelihoods, while maintaining forest–related environmental benefits to the global community. Support was provided to improve monitoring and data collection; to strengthen government capacity for natural resource management in post conflict environments; to pilot work on finance models which benefit poor people; and to study critical issues to inform decision making. / Overall, the CBFF start-up programme included the following components: / Expanding ‘community forest mapping’ (to Congo-Brazzaville, Central African Republic (CAR) and Gabon. / Strengthening the Ministry of Environment in the Democratic Republic of Congo (DRC) / Piloting community forestry in DRC / Identification of transformative rural energy interventions in DRC. / Piloting community-level payments from international/global community in Cameroon. / Facilitating the installation of a satellite data receiving ground station in one of the COMIFAC (Commission of Central African Forests) countries / Provision of a high resolution camera for a Brazilian satellite to cover Central Africa and guarantee free at source data to all Central African stakeholders / Initial support to the establishment of the main CBFF / The start-up activities took place in several countries including the Central African Republic (CAR), the Democratic Republic of Congo (DRC), Gabon, Cameroon and the Republic of Congo. They were designed to respond directly to clearly articulated needs from the region, and were in alignment with the following areas of the COMIFAC Convergence Plan[1]: / Knowledge of the Resource (2), / Poverty Reduction (6); and / Innovative Financial Mechanisms (9).
[1] COMIFAC Convergence Plan http://www.biodiv.be/comifac2/plandeconvergence

What were the expected results?
The project log frame highlights that the principal goal (impact) of the CBFF start-up programme was to develop the capacity of the people and institutions in Congo Basin forest countries[2] to manage and protect resources. / Expected goal (impact) level results were : / Effective participation of 4 of the 6 main Congo Basin Forest countries in collaborative programmes to conserve forests / COMIFAC governments and secretariat actively engaged. Strategic alliances built for future CBFF implementation / The purpose (outcome) of the CBFF start-up programme was for the main CBFF to be fully operational and supporting forest communities and countries to manage their resources sustainably. / Expected purpose (outcome) level results were: / 50 high quality projects (with a value of $90million) approved by CBFF Governing Council and operational. / 40% of the CBFF Portfolio to be Government projects, 30% national civil society projects and 30% international NGO projects.
[2] Burundi, Cameroon, Central African Republic, Congo-Brazzaville, Democratic Republic of Congo, Equatorial Guinea Gabon, Rwanda.

What was the context in which UK support was provided?
The forests of the Congo Basin are the second largest contiguous rainforest in the world after the Amazon. They cover over 300 million hectares (approximately one quarter of the world’s remaining closed canopy tropical forest) and harbour biodiversity of global importance. These forests are also critical to the livelihoods of more than 50 million people from 150 different ethnic groups. / It is estimated that the forests of the Congo Basin store up to 30 million tonnes of CO2 and they therefore play a vital role in combatting climate change. The forestry sector also contributes between 5-13% to GDP of the countries in this region. / Historically the Congo Basin has experienced a relatively low rate of deforestation. Current annual rates of deforestation are 0.23% (compared to 0.44% in the Amazon and 0.41% in South East Asia). However, logging, shifting agriculture, population growth and impacts from oil and mining industry activities in the region are placing more pressure on the forest and deforestation rates are likely to grow if the wrong policy options are pursued. / In March 2007, the UK Government pledged £50m for sustainable management of the Congo Basin ecosystem through a ‘Special Fund’ entitled the Congo Basin Forest Fund (CBFF). This is part of a wider £800m component of the UK’s Environmental Transformation Fund (ETF-IW), which seeks to achieve poverty reduction through tackling environmental problems and to effect progress on climate change adaptation and mitigation in developing countries. / Its current total value is £100m, comprising £50 million from the UK Government, and £50 million from the Norwegian Government. / The aim of the main CBFF is to reduce poverty and address climate change through reducing the rate of deforestation by developing the capacity of the people and institutions in Congo Basin forest countries to sustainably manage their forest. / Its initial focus was to support certain elements of the COMIFAC Convergence Plan, as described above. This has subsequently been refined, so that the new areas for funding are grouped under the following headings: / Forest Management and Sustainable Practice / Livelihoods and Economic Development / Monitoring, Reporting and Verification (MRV) / Benefits from an International Regime on REDD+ and Payments for Ecosystem Services (PES) / Capacity Building in REDD+, in Monitoring, Reporting and Verification (MRV) and in sustainable forest management / The CBFF Board makes decisions about the granting of funds under these headings. The Fund is managed on behalf of its two donors by the African Development Bank. / To demonstrate DFID’s commitment to the main fund, the UK committed to financing a CBFF start-up programme to support the main CBFF’s establishment. / All the start-up activities were endorsed by the CBFF Governing Council at their inaugural meeting in London on 17th June 2008 and were linked to the overall framework of the main CBFF.

## Section A: Detailed Output Scoring

Output 1: Forest Resource assessment & monitoring technologies in place & operational
Output 1: final score and performance description: / Score B: Outputs moderately did not meet expectation / Output indicators: / Community forestry mapping extended to Republic of Congo/Central African Republic/Gabon / A High-resolution remote-sensing camera for forest assessment & monitoring is built and operational / A Remote-sensing data receiving station is built and operational / Progress on the community participatory mapping component for Indicator 1 was good and outputs were met. There has been no real progress with indicator 2 for reasons outside DFID and UK control. Indicator 3 was achieved, but outside the DFID start-up programme and DFID was not involved. The DFID project component contributing to indicator 3 was closed early in the lifetime of the project. No funds were spent and it is not included in the output score.
Final results: / Community forestry mapping has been extended to Republic of Congo, Central African Republic and Gabon / DFID awarded an accountable grant to Rainforest Foundation UK (RFUK) to use community mapping as a means to promote recognition of communities’ rights to access, control, and use forests in the legislative, political and strategic processes of three Congo Basin countries (Central African Republic, Gabon and Congo Brazzaville). As a specific objective, the project aimed to ensure that forest communities, civil society organisations and governments in each of the three target countries have the capacity and resources to accurately map the occupation and use of forests by target communities and use the resulting data to inform decisions related to forests and forest communities. This objective was met and the project was successful in extending community forest mapping to Republic of Congo, Central African Republic (CAR) and Gabon. / Overall the project has worked with 85 communities (57 with individual maps, 14 in a 3D (P3D) mapping exercise, and 14 who have participated in the development of the community forest manual) in the three countries, and produced 57 individual maps and one P3D model whose area covered 13 villages, covering 0.4 million hectares of land. / Within the 85 focus communities in Gabon, CAR and Congo, the project has achieved significant results in terms of: i) building the organisational and technical capacities of the local implementing organisations, ii) producing a number of geo-referenced community maps that are now serving as useful advocacy tools, iii) enhancing awareness of forest communities’ rights, including indigenous peoples in terms of access and control of forest and land resources, iv) raising further the awareness of governments and other stakeholders on Indigenous Peoples’ rights as well as the importance of communities’ involvement in natural resource management, v) introducing multi-actor platforms enabling communities and governments to dialogue and share their views, and vi) influencing some policies in CAR. / Key results include: / 14,193 direct beneficiaries of this project. / Three national mapping laboratories are fully operational. / The technical capacities of local implementing organisations, other local NGOs and government staff have been increased (346 community mappers trained, 88 mapping facilitators trained and 27 GIS technicians trained). / 57 geo-referenced community maps, involving 180 forest community members, have been produced and are serving as useful advocacy tools / The development of a community mapping internet interface for the Congo Basin, www.MappingForRights.org, which is beginning to reveal the full extent of customary land tenure and resource use in forests throughout the Congo Basin. / In CAR, the project contributed to the suspension of a national park management plan that would have resulted in the displacement of indigenous communities from their ancestral lands. The project has also influenced the design of the Ministry of Forestry (MEFCP)’s approach and guidelines for the allocation and management of Community Forests, taking into account traditional governance of communities. / An external evaluation carried out on completion of this project has concluded that the Community Mapping Project was well designed, implemented and coordinated and achieved significant results. / Given the lack of culture in participatory forest governance in the region and generally weak civil society, further work that RFUK is already implementing aims to continue to strengthen the capacities and achieve the overall objective of the project, i.e. to promote the inclusion of forest community rights to control access and use forest with legislation, policy and planning processes. / High-resolution remote-sensing camera for forest assessment & monitoring was not built and made operational / This component intended to fund a high resolution camera on a planned Brazillian satellite to monitor Congo Basin Forest cover. DFID contracted The Rutherford Appleton Laboratory (RAL) to build the camera, in conjunction with the Brazillian National Space Agency (INPE). These sorts of images can be used to monitor deforestation and degradation, and assist with responding to and tackling illegal logging, climate change and land management issues. / However, after the project started, it emerged that Brazil was not able to fly the camera on the planned satellite. Alternative options were considered but these were not feasible and the project component was closed. Some costs were incurred on this component (2.4% of the total CBFF start-up programme) that did not lead to the desired outcomes. / A remote-sensing data receiving station built was built and operational by 2011. / DFID had planned to partner the French Development Agency (AFD) to develop a remote-sensing data receiving station in Gabon. This had been identified as a high priority for regional partners as there was no ground station capable of receiving satellite date in the Congo Basin region. This meant that satellites passing over Central Africa could not download their data before limited memory space meant that images were deleted. / However, the French provided this support bilaterally in cooperation with the Brazilians and Gabon to get the ground station built and operational. There was therefore no need for DFID support and the project component was closed at an early stage, with no spend. / Impact Weighting (%):20% / Revised since last Annual Review? No / Risk: Medium/ / Revised since last Annual Review? No

Output 2: Transformative pilot projects undertaken and results disseminated.
Output 2: final score and performance description: / Score A : Outputs met expectation / Output indicators: / Pilot roadmap for laws, policy and institutions required for community forestry developed in DRC / Study to identify transformative rural energy interventions completed / Community-level payments from international/global partners piloted in Cameroon
Final results: / A pilot roadmap for laws, policy and institutions required for community forestry was developed in DRC / DFID awarded an accountable grant to Forest Monitor (FM) to contribute to the development and widespread uptake of a system of community forestry that works for the DRC. Forest Monitor worked primarily with the Ministry of Environment, Tourism and the Conservation of Nature (MENCT), which is responsible for forests in DRC. / Key results include (all produced with a large consensus through a national dialogue process): / A Roadmap/policy document on community forests, including mapping methodologies and approaches, technical and community guides. / Draft Decree for the prime minister / Draft Arrêté for the Minister (MENCT) / A video series presenting community forestry to a largely uninformed audience of this potential model for forest management. / The creation of a large consensus around the drafts of the decree and arrêté on community forestry / The creation of the Community Forest Division within the organisational structure of MENCT. / A program of work for 5 years in the form of a proposal to the CBFF / The main result of this component was the development of a roadmap on community forests with the DRC Ministry of Environment, Tourism and the Conservation of Nature (MENCT) and a range of other partners. This roadmap became the concept base for the production of a draft policy document, supported by draft legislation and the proposal for a five-year plan of work. The policy document itself was to provide the framework for the legislation and other activities including identifying actions required from a range of different actors. / A national dialogue was also successfully established which engaged a large number of participants, from the village, provincial and through to national level. Policy dialogue meetings with experts from government, private sector, civil society and others also took place. The dialogues took place in villages surrounding the field site offices in different provinces and Kinshasa. MENCT and civil society representatives were taken to Tanzania where much more progress has been made in the area of community forestry than possibly anywhere else in Africa. / As a result of the national dialogue and the roadmap discussions, a formal community forestry division was created within the forest management division of the MENCT. This was done in preparation for the continuation of the work program on community forests, as discussed with MENCT and others. Though the policy was produced in close cooperation with Ministry officials, it has not yet been adopted as an official policy position, a step that may be taken as the Community Forest Division becomes more operational. / The most significant obstacle in completion of all the project outputs was the endorsement by the Prime Minister on the Community Forest Decree, which is necessary to enable the MENCT Minister to sign the subsequent arrêté. The activities of the project have been completed to the maximum extent possible without a signature of the Prime Minister on the legislation. An outstanding workshop or consultation may be required to secure this signature and arrangements have been made by Forest Monitor to support this. This work will also be continued under a grant support by the main CBFF. / An external evaluation of the project suggests this CBFF start-up activity was radical in its approach and challenging in its outputs, consulting large numbers of individuals, and a broad range of institutions. At the outset of the project, the challenge was to ‘think big’, and to deliver something that would work. Many colleagues and partners delivered on their obligations but a number of established viewpoints were challenged, making progress difficult at times. However, the model proposed is a good one and the roadmap for its implementation is sound. We await the conclusions of the DRC government for its final word on the texts and proposed next steps. / A study to identify transformative rural energy interventions in DRC was completed / DFID awarded an accountable grant to Practical Action Consulting and ECO consulting Group, to carry out a review and appraisal of potential transformative rural energy interventions in the Congo Basin. / This main output of this component was the production of the report. It was based on kick-off meetings, the development of a methodological framework, a literature review and a field mission to the DRC to conduct interviews with key informants. The preliminary conclusions of the review were shared with the key stakeholders in the DRC through two workshops on forestry and rural electrification. The process was largely a desk study and was successfully completed. / The report provides a good overview of rural energy and forestry sectors in the Congo Basin with examples from DRC that are applicable to the region as a whole. The report highlights the immense natural renewable energy resources of the region in respect to biomass energy and hydro potential. The analysis of current energy demand clearly demonstrates the huge reliance on wood fuel as a primary cooking fuel for over 90% of people and a source of deforestation in the Congo Basin. Electricity demand is characterised by the lowest rates of rural electrification in Africa at below 2%. / Potential interventions focus on wood fuel and rural electrification. As far as wood fuel is concerned, interventions in the field of agroforestry are the most favourable options. The positive impact of such interventions could also be increased if they were to be combined with the dissemination of improved stoves and kilns. Substitution of charcoal by briquettes is also an intervention which should be considered. With regards to rural electrification, out of seven technology options examined, four options were considered as relevant and complementary given their varying end uses. These options were: micro and mini hydro, river turbines, solar PV and biogas. / The report does have shortcomings and is not as authoritative as one would hope. For example, referencing all the numerous studies of rural energy that have taken place over the last 20 years or so, both within the Congo Basin and elsewhere would have been a helpful addition. In addition, the report does not give clear guidance on technical, economic, social or environmental criteria that would need to be applied before judging future proposals for investment in this sector. / However, this in no sense diminishes the findings of the report and the importance of establishing interventions in this domain for the future of the Congo basin forest. / Community Payments for Ecosystem Service (PES) pilot projects established at two community forest sites in southern Cameroon (Nkolenyeng and Nomedjoh) covering a cumulative area of more than 2,500 ha and a total of more than 1,300 inhabitants. / DFID awarded an accountable grant to Bioclimate to test the suitability of PES in the context of community forests in Cameroon. The overarching goal of the project was to support communities of the Congo Basin to protect forests by finding ways to integrate PES with community forest management. Cameroon was chosen as the initial focal point because it is currently the only Congo Basin country with a legal framework that recognises community forests. / The project tested the PES approach in two community forests: Nomedjoh and Nkolenyeng. The partners agreed to use the ‘Plan Vivo System’ to help inform and assist the development of the project. Plan Vivo provides an established but flexible framework for working with communities and is recognised internationally as a credible and robust voluntary standard for the administration of PES. / Despite a challenging environment and low technical capacity for PES, the highly participatory nature of the process, meant that communities were engaged in the project, now have a greater awareness of the multiple values of the forest resource, and a strong sense of ownership and identification with the project goals. / Key results include: / PES activities have been defined and are being implemented at two community forest sites: Nomedjoh village and Nkolenyeng village. The project intervention at both sites was reduced deforestation and degradation, through reduced felling of trees, and intensifying agriculture to reduce the need for agricultural expansion into primary forests. / PES has been integrated into revised/new simple management plans for both community forests, and these have been formally approved by Ministry of Forestry and Fauna (MINFOF). Whilst community forests are recognised in Cameroon, PES is a relatively new concept and the communities of Nomedjoh and Nkolenyeng are the first in Cameroon – and for that matter the whole Congo Basin region – to have PES as the focus of their community forest management plans. This achievement is significant. / Comprehensive technical development processes were undertaken at both pilot sites in order to decide, design, plan and enable project activities to be implemented, monitored and valorised. This included technical and social baselines, the quantification of expected carbon benefits of PES activities, and the development and application of technical and social monitoring systems. / More effective local institutions for overall community forest governance and enterprise activities are now in place at both pilot sites, including PES management and benefit sharing arrangements geared towards improving the wellbeing of the most disadvantaged groups as well as other sections of the communities. / Agricultural support and extension services for participating communities were provided and this has led to more diverse and improved agroforestry and land management practices, as well as increased yields of food crops. For example, one of the encouraging early outcomes in Nkolenyeng is a reported increase in cocoa income due to the use of improved tree management techniques. In Nomedjoh the women’s Manioc (cassava) group, which has been successful in sharing out improved cassava stock to plant in their fields, are also selling their cassava jointly and fetching higher prices for it. / Diversification of income generating activities and improved collection, processing, and marketing of non-timber forest products has contributed to improved livelihoods and more sustainable management of forest resources. For example, the Non Timber Forest Product (NTFP) development activity in Nomedjoh has focused on the women’s NTFP activity group and has definitely been one of the success stories of the project. The group has organised the harvest, safe storage, and sale of Moabi and Mbalaka fruits. The Moabi fruits are being collected to extract valuable oil from the seeds. The oil is used for cooking and for manufacturing skin creams and other cosmetics. Mbalaka fruits are sold into Nigeria, where they are highly prized for cooking. In 2011 the Nomedjoh women’s NTFP group was able to produce and sell 130 litres of Moabi oil, generating revenue of CFA 450,000 (£552.82[3]). The women used some of this money to buy household objects such as bush lamps, kitchen utensils and mattresses. They put CFA 120,000 (£147.28) towards a revolving fund, to which they will add their PES monies, and they will use this to invest in communal basket making and the production and sale of Moabi oil and Mbalaka in future years. The women are effectively using their PES money as ‘risk capital’ to invest in new income-generating enterprises (e.g. Mbalaka), but safely reinvesting the money they generate from existing enterprises (e.g. Moabi oil) in order to sustain those enterprise activities. / Replicable and cost-effective livelihoods and forest monitoring systems have been developed. The latter uses simple community forest protection performance indicators to link ecosystem payments to results / Finally the project has resulted in increased local capacities to design and monitor PES projects and there has been a dissemination of project experiences and lesson learning on subjects relating to community forest management and the practical steps and considerations involved in developing community PES REDD-type projects. / The technical and livelihood monitoring systems in place have shown that the project sites are on track to meet targets of: / Overall forest conversion across two pilot sites reduced by at least 50% relative to 2010 levels by Q3 2012, / Average improvement of at least 20% in wellbeing indicators by Q3 2012 relative to end-2010 levels across participating communities / Carbon is the Plan Vivo ecosystem metric for this project and the project has a crediting period of ten years, divided into two five-year periods. If performance remains in line with the with-project scenario, the combined carbon benefits from both community forests are expected to be 23,021 tC (84,412 tCO2) in the first five-year period to September 2015, and 81,456 tC (298,744 tCO2) over 10 years. / In July 2012 the project will enter its 21st month of an initial five-year phase of full PES activity implementation that runs until September 2015. During this first implementation phase the communities at the two sites will implement PES activities and earn and manage their PES monies without significant external assistance. At the end of the DFID CBFF start-up activity, the local NGO partner, CED, will assume full responsibility for on-going coordination, monitoring and reporting of project activities and results in accordance with the requirements of the Plan Vivo System. Bioclimate and Plan Vivo will continue to monitor and validate the project. / Impact Weighting (%):30% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[3] Exchange rate GBP 1 : CFA 814.74 on 1 June 2012. http://www.xe.com.

Output 3: The Democratic Republic of Congo Ministry of Environment, Tourism and Conservation (MENCT) supported in strengthening its capacity to manage the country’s natural resources
Output 3: final score and performance description: / Score A: Outputs met expectation / Output indicators: / Adequacy of MENCT offices, equipment & transport to perform tasks / Adequacy of staff numbers and competency to perform tasks for the MENCT / Adequacy of MENCT capacity to plan, prepare documents, implement & monitor its projects / All indicators were met through the program of cooperation with the German Technical Cooperation (GTZ),
Final results: / DFID provided support to the German Technical Cooperation (GTZ), in support of 4 elements of a wider German sector development programme to the Congolese government. The four elements were: / Support and extend the planning of institutional restructuring of MENCT that is already considered as part of an overall programme of change within the Government of DRC; / Improve the productivity of MENCT staff in two ways (capacity building as well as improving the working conditions of staff in Kinshasa and selected provinces); / Develop a social and strategic plan that will rejuvenate MENCT staff with criteria for retirement of personnel and beginning an initial phase of retirement; / Enable MENCT staff, through improved planning, to produce successful financial requests and proposals to the donor community (including the CBFF). / MENCT offices have been refurbished and equipped and are now adequate to perform tasks / The refurbishment and equipment of the three main MENCT buildings in Kinshasa was completed and MENCT agents now have a working environment which is conducive to performing tasks. / Training and capacity building was carried out which has enhanced MENCT’s staff capacity to manage the country’s forest resources / On the basis of a study conducted in June/ July 2008 by the programme, a training plan for 2008 –2010 was developed. This plan was successfully implemented and progressively adapted according to the needs of the Ministry and Nature Conservation Agency, ICCN. As of March 2011, more than 600 training sessions had been provided to agents of the Environment Ministry and Nature Conservation. 505 staff members undertook short training courses in modules such as IT, project management, community conservation, survey methods, monitoring and evaluation etc…. 117 staff were given access to longer training courses (some at international universities) in subjects including environmental law, protected area management and forest engineering. / This training has increased the technical and operational capacities of the Ministry’s and the Nature Conservation Agency’s Staff. The support given to the training of future forestry engineers by the University of Kinshasa in partnership with the Canadian University of Laval, has contributed to the creation of a pool of young qualified Congolese forest engineers, ready to be employed in the national institutions. This in turn will lead to improved technical capacities of the Ministry and the forest sector in general. The first group of forest engineers will graduate in February 2012. This is a considerable achievement considering that the last group of forest engineers in DRC graduated in 1991. / A special emphasis was also placed on the Human Resources Department. As a result, the HR employees can now analyse staff training needs and implement their own training programmes. / Impact Weighting (%):20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 4: African Development Bank (AfDB) supported to establish and operationalise the CBFF Secretariat on a sustainable basis
Output 4: final score and performance description: / Score C: Outputs substantially did not meet expectation / Output indicators: / Interim Co-ordinator appointed and operationalized / CBFF (Challenge Fund) Procedures and Guidelines in place and Challenge Fund Operating effectively / CBFF Governing Council Meetings facilitated effectively and support provided to Co-Chairs / The AfDB has made progress to create the CBFF special fund and put in place a permanent CBFF secretariat. Through two calls of proposals, 41 projects have been approved. However, management of the fund is not as effective as we would expect and more improvement is needed to ensure current operations are more efficient and that the fund is sustainable in the long term.
Final results: / A CBFF Interim Co-ordinator was appointed. This has now been replaced with a permanent CBFF co-ordinator and secretariat. / Through the CBFF start-up programme, DFID provided resources for the provision of an Interim CBFF Secretariat Co-ordinator, who was in post August 2008 - Nov 2009. A permanent co-ordinator was appointed by AfDB at end Nov 2009 and was in place by December 2009. The co-ordinator is supported by Secretariat staff at HQ and in the Congo Basin Region (DRC & Cameroon). The Secretariat, under the responsibility of the Coordinator, ensures the daily management of the fund and is placed under the joint supervision of the Board, for policy matters, and of the Agriculture Department of the AfDB (OSAN), for administrative and operational matters. / A Fund Management Agent (FMA) was also appointed in 2011 to assist the Secretariat and the AfDB with the administration and oversight of projects under 2.5 million Euros. The FMA comprises a consortium of Price Waterhouse Coppers (PwC) and the Dutch Development Agency SNV. The FMA operates from the region and has been initially appointed for a period of 3 years. / CBFF Procedures and Guidelines have been developed but further work is needed to make the fund operate effectively / The Framework Document of May 2008 outlines the general principles of financial management, procurement and disbursement to be employed by the AfDB on behalf of the CBFF. In October 2009, these principles were further developed in the Operational Procedures. / However, a recent Operational Effectiveness Review of the CBFF has highlighted that although these procedures exist, are sensible and flexible they have not been sufficiently applied. They are written in the form of advice ("guidance") that is not appropriate at the operational level, and in a risk-averse environment, they are not taken in the spirit in which they were agreed. This has contributed to sub-optimal fund effectiveness. / The FMA are currently developing a more detailed operating manual to provide guidance on how the existing procedures should be implemented at an operational level. The manual will be presented and approved at the next Governing Council meeting in June 1012 and should make the fund operate more effectively. / CBFF Governing Council Meetings are facilitated effectively and support is provided to Co-Chairs / Governing Council Meetings have taken place on a regular basis since the fund was launched in 2008 and the Secretariat has facilitated the GC and Co-Chairs effectively and with increasing confidence. The next GC meeting is scheduled for June 27th 2012 in London. There is currently one CBFF chair who is effectively being supported by the CBFF secretariat. / Impact Weighting (%):30% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? No / The Log frame has not been updated since the last review. / 1.2 Final Output score and description: / Score B: Outputs moderately did not meet expectation
Direct feedback from beneficiaries / DFID has spoken to a number of the CBFF start-up programme beneficiaries as part of this review. Overall, the feedback from beneficiaries on this project has been very positive. This is particularly true for out NGO partners who undertook field activities in the region and who found DFID management of the accountable grants excellent.
1.4 Overall Outcome score and description: / Score B: Outcome moderately did not met expectations / The purpose (outcome) of the CBFF start-up fund was for the Congo Basin Forest Fund (CBFF) to be fully operational and supporting forest communities and countries to manage their resources sustainably. / It should be noted, that the design of log frame for the CBFF start-up programme is not ideal as the outcome indicators poorly reflect the programme as a whole. The way the log frame is constructed means that only output 4 is contributing to the outcome indicators. Therefore, based solely on the existing outcome indicators, the outcome score for the CBFF start-up programme could be considered a C. However, an overall outcome score of B is considered more appropriate and better reflects the success of the programme as a whole, taking into account the achievements and scores of the all programme outputs and activities. / Outcome indicators: / 50 high quality projects (with a value of $90million) approved by CBFF Governing Council and operational / 40% of the CBFF Portfolio to be Government projects, 30% national civil society projects and 30% international NGO projects. / 41 projects accounting for £68 million pounds have been approved by CBFF Governing Council and 32 are operational (grants have been signed). / During the first two years of the Fund’s operation, progress focused on establishing the mechanisms, administration procedures of the fund and staff resourcing of the CBFF’s Secretariat. There have been two competitive calls for proposals to the Fund: August – Dec 2008 and Dec 2009 – March 2010. / To date 41 projects have been endorsed for funding by the CBFF’s Governing Council, accounting for around £68 million (84 million Euros or 105 million USD) of the Fund’s £100 million resources. The endorsement profile has been 1st call: 15 projects, 2nd call: 25 / The number and value of projects approved by the GC has met our targets. However, management of the fund by the AfDB has not been as efficient as we would expect and there have been delays to implementation of some of the projects. Current focus is on operationalising the endorsed projects, and starting to communicate individual and aggregated results from the programme. / 34% of the CBFF Portfolio is accounted for with Government projects, 30% with national civil society projects and 36% with international NGO projects. / This largely meets the target and is considered to be an appropriate balance of partners. The slightly higher than expected percentage of international NGO projects perhaps reflects the levels of capacity amongst government partners to produce high quality CBFF project proposals. A recommendation would be to provide more support to governments during the development of projects for the 3rd call for proposals. / Impact and Sustainability / The principal goal (impact) of the CBFF start-up fund was to develop the capacity of the people and institutions in Congo Basin forest countries[4] to manage and protect resources. / Impact indicators : / Effective participation of 4 of the 6 main Congo Basin Forest countries in collaborative programmes to conserve forests / COMIFAC governments and secretariat actively engaged. Strategic alliances built for future CBFF implementation / Impacts / It is still early in the project life cycle to measure impacts of each project component. The start-up activities took place in the Central African Republic (CAR), the Democratic Republic of Congo (DRC), Gabon, Cameroon and the Republic of Congo, meaning that 5 of the 6 main Congo Basin countries benefitted from the fund and were participating in collaborating programmes to conserve forests and the capacity of the people and institutions in these countries has been enhanced through the start-up activities. / A number of the project components were particularly successful in their outcomes and have the potential to have a large impact on the way forest resources in the Congo Basin are managed and protected into the future. The main Congo Basin Forest Fund, once the operational effectiveness has been improved, also has the potential to have a positive impact on the forests and people of the Congo Basin in the future. / Demand is strong from Congo Basin constituents (Governments, local and international non-government actors) to participate in and receive funding from the main CBFF, particularly from DRC, Cameroon, Republic of Congo and Central African Republic. Demand from applicants for the first two calls for proposals has been high. Over 560 concepts were received, with 41 suitable proposals from 10 countries selected for available funding. These are Cameroon, DRC, Gabon, Congo Brazzaville, Central Africa Republic, and Equatorial Guinea, as well as Rwanda, Burundi and Sao Tome and Principle. More proposals were judged suitable if funds had been available. / The COMIFAC Secretariat is represented on the Governing Council (GC) of the CBFF, and has participated in all GC meetings of the Fund to date. Congo Basin countries are collaborating in CBFF implementation and the capacity of people and institutions to manage and protect forests as a result of CBFF projects will become clearer when CBFF projects have made more progress. / Sustainability One of the main objectives of the start-up programme was to support the establishment of a fully operational CBFF. The existence of the main CBFF will ensure the sustainability of the start-up programme and provide support for ongoing work in the Congo basin region to manage and protect forests. 2 of the start-up programme activities also resulted in the successful preparation of proposals to main CBFF. / Making the CBFF operational is an ongoing process. An independent operational effectiveness review of the CBFF was undertaken in the 1st quarter of 2012. The review makes a number of recommendations to improve fund performance and donors are currently discussing how to take these forward with the Governing Council Chair and AfDB. / Ensuring the fund is operational will enhance its sustainability and attract news donors to contribute to the fund. Canada is interested in contributing to the fund and will do so dependent on the outcomes of the operational effectiveness review. / A 3rd call for proposals is expected to be launched in 2013.
[4] Burundi, Cameroon, Central African Republic, Congo-Brazzaville, Democratic Republic of Congo, Equatorial Guinea Gabon, Rwanda.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: / The total commitment from HMG/DFID was to provide up to £10.5 million. This included the estimated costs to DFID of administering and managing these activities, including support and oversight. / The project was completed under budget. / 2.2 Key cost drivers / Each individual project had its own cost drivers and the DFID appraisal of individual projects included attention to costs. The cost drivers vary and include project identification and preparation costs, asset acquisition and maintenance, technical assistance and associated staff costs, logistical and travel expenses associated with multi-country participation, and technical expert costs for a wide range of procured services for development of technical planning tools (such as participatory mapping, livelihoods surveys, legal and institutional assessments etc..). / Given the remoteness of field sites in the Congo Basin and the logistical constraints of accessing them, field work is a key cost driver of many components. The low technical capacity for sustainable forest management in the Congo Basin region also means that all components were required to include capacity building activities into their budgets. Several of the individual project components also included a budget line for an independent evaluation to be carried out. / DFID oversight, appraisal and supervision also entailed some administrative costs. / 2.3 Was the project completed within the expected timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / N/A / 3.2 Set out what plans are in place for an evaluation. / There are no plans for a final evaluation of the programme. An independent mid-term review was carried out in 2010 and recommendations of the review were taken forward. / Of the 5 individual projects that were supported under the fund, 2 have carried out external final evaluations and a third is planned in the coming months. / With regards to the activity relating to making the main CBFF operational, a major external operational effectiveness review has recently been carried out and the recommendations of the report are currently being acted upon.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? No / The CBFF start-up programme remained a programme of medium risk rating over the life of the project. / 4.2 Risk funds not used for purposes intended / This risk is low - all project partners submitted quarterly financial management reports and yearly audited statements. / 4.3 Climate and Environment Impact / This programme is addressing many long-standing weaknesses in environmental governance in the Congo Basin region. The start-up activities supported under the start-up programme directly support improved forest management and protection and environmental awareness. Reducing deforestation and better management and protection of forest has a positive climate and environmental impact.

5. Value for Money
5.1 Performance on VfM measures / No specific VfM performance measures were identified when this project was originally approved in the Project Memorandum. However, an overall approach to VfM was taken when considering the approach to project design. For example, developing remote sensing capability can be done cheaply and rapidly and vastly enhances the forest data coverage. Community involvement in the management of forest resources has also proven to be very cost effective in similar environments elsewhere (including Indonesia, Guyana, Brazil and other countries in Africa) and the expectation is that it should have a similar impact in at least parts of the Congo Basin. / Each of the eight distinct components of the CBFF start-up programme had differing cost drivers and we cannot consider all the possible VfM measures in this project completion review. However, using the DFID 3E’s VfM framework below, we can highlight some key VfM aspects of the individual project components. / It should be noted that the logistical constraints of the Congo Basin and weak technical capacity of partners mean that the “costs of doing business” are overall relatively high in comparison to other regions. It should also be noted that there is a trade-off between carrying out broad stakeholder consultations/participatory approaches with local forest communities and cost. However, despite their high cost (both logistical and time), these types of approaches are essential for ensuring the longer term impact of activities. There is also evidence that for PES schemes, participatory processes are likely to be scalable and economically efficient over the long-term because it lowers monitoring costs. / DFID’s 3Es Framework / Economy: relates to whether we are paying the best price for the appropriate quality of project inputs (staff, consultants, raw material and capital) that are used to produce the outputs. / During the design phase, a number of component interventions were identified and each component budget was constructed with a consideration of input costs. / The majority of components involved working with local partners, and contracted existing local expertise as far as possible to keep down costs. / A number of the components included high capital costs for cars and other equipment, and achieving the best price for these high capital costs was considered in the project design. / Efficiency: relates to how well inputs are converted into outputs / It was noted in the external mid-term review that project management by DFID staff was excellent. The level of DFID management support has been a factor in the smooth running of individual components and all beneficiaries commented on it having an important influence on the ability to achieve results. / The satellite camera component was terminated early and inputs (staff and equipment costs) did not lead to results. This inefficiency amounted to 2.4% of the overall budget. / The PES activity in Cameroon spent just over 20% of its total budget on technical development costs. This high cost was mainly due to the participatory nature of the technical development process. As noted above, although this is initially costly, it can be argued that it leads to greater economic efficiency over the longer term. / However, the PES project developers question the merits of its costly and ‘carbon rigorous’ technical development process. Having spent a lot of money assessing forest carbon stocks, developing carbon baselines and with-project scenarios, and quantifying the expected carbon savings of project activities, carbon is conspicuously absent from both the PES contracts with the communities and from the monitoring system. One simple reason is that a cost effective monitoring system needs to focus on what community members are able to observe and record efficiently, which are the creation of fields, reopening of fallows, and the presence or absence of trees. Payments need to be based on what is monitored and observed. If that is something other than carbon, it does rather call into question the need to assess and quantify carbon stocks and expected carbon savings in the first place, particularly as the quantification of forest carbon is a costly process. This experience will be useful for other similar interventions in the future. / Effectiveness: relates to how well all the outputs are achieving the desired outcome / This project was conceived in part to prepare the way for the main Congo Basin Forest Fund. Output 4 directly contributes to the outcome. / The start-up activities which contribute to the other 3 project outputs were designed to demonstrate the kinds of projects the CBFF would fund and were necessary to build support amongst stakeholders in the region. 2 of the start-up activities also resulted in the preparation of proposals to main CBFF to continue activities. / Overall, the CBFF start-up programme has facilitated the establishment of the CBFF. / Cost-effectiveness: relates to how much impact an intervention achieved relative to the inputs invested. / Overall the final spend on the project was under budget. / While it is possible to discuss costs with reasonable certainty, assessing impact is more difficult, particularly for forest projects where impacts can accrue many years after project implementation. / The CBFF start-up programme has contributed to developing the capacity of the people and institutions in the Congo Basin forest countries to manage and protect resources. This is particularly true in DRC through the particular success of two DRC components. / The Ministry responsible for sustainable forest management has been completely revamped (including a considerable amount of staff training and rehabilitation of office buildings, and a retirement plan for ageing staff) and this component has helped to give rise to a new generation of trained forest managers, able to successfully manage and protect forest resources in the future. / The community forestry component in DRC is very close to having a very large impact (and which may do so in the future). A wide reaching national dialogue for community forestry was built around community forestry and a large consensus for the policy document and accompanying legislation was achieved. The remaining piece of the puzzle is for the legislation to be signed into being. Once this occurs the impact on forest management will be considerable. The innovative, community approaches to forest management which are currently being piloted in isolated projects will be formalised and allow them to be scaled up across DRC. / Feedback from one project partner expressed the view that had DFID/HMG given more support at the policy level to influence the finalisation of the community forestry legislation then the overall impact of the project would have been far greater. / Highly innovative in its nature, the Cameroon PES component of this project also has the potential to have wider impact on the sustainable management of Congo Basin forests in the future, once lessons are learned and disseminated in the region. / 5.2 Commercial Improvement and Value for Money / DFID worked closely with all the partners of the CBFF start-up programme to ensure that project budgets were built with an appropriate consideration of value for money. / 5.3 Role of project partners / The project partners were key to the success of this programme. / For example, the GTZ managed project was able to stick faithfully to its well-prepared work plan and logframe and achieved good results. This reflects GTZ’s considerable experience of working in DRC and with the relevant Ministry. The lesson to be drawn from this is that experienced implementation partners have a significant impact on project outcomes. A further lesson to be drawn is that the more closely projects worked with government partners, the more successful they were in achieving their objectives. / Other experiences from this programme have highlighted that well defined roles and responsibilities amongst partners from the outset leads to better implementation and results. / 5.4 Did the project represent Value for Money : / Yes, overall this programme represents Value for Money. A number of successful start-up activities achieved significant results in challenging environments. / The satellite camera component of this project, was terminated early for reasons outside DFID control, and does not represent VfM. Lessons from this component have been learnt and documented by DFID to prevent similar incidents arising in the future.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions
The CBFF start-up programme supported 5 successful project activities that have resulted in: / Extending community forestry mapping to 85 communities in the Republic of Congo, Central African Republic and Gabon. The 57 community maps produced are serving as useful advocacy tool to raise awareness amongst governments and other stakeholders of forest communities’ rights, especially in terms of access and control of forest and land resources. / Developing a pilot roadmap for community forestry in DRC which became the basis of a draft policy document supported by draft legislation and a five year plan of work. The road map has also lead to the creation of a specific community forestry unit within the forest management division of the ministry. / Identifying a number of potential transformative rural energy intervention in DRC. / Piloting two community PES projects in Cameroon that are on track to reduce forest conversion by 50% at each intervention site and improve wellbeing by 20% amongst the participating communities. / Supporting the DRC Ministry of Environment, Tourism and Conservation in strengthening its capacity to manage the country’s resources. / The PES project is of particular note given its innovative nature and the fact that it is the first project of its kind in the Congo Basin. The lessons learned from this project are being disseminated in the form of a series of technical papers and will be highly relevant to future PES schemes developed in the region. / The main CBFF has a large portfolio but needs to be more effective at managing project operations. This is an on-going process and the UK, as part of the CBFF Governing Council will ensure that the conclusions and recommendations of the recent external operational effectiveness review are acted upon.

8. Review Process
The review undertaken by DFID on the basis of the following documents: / Original programme conception note and project memorandum document. / The programme logframe. / External mid-term review carried out in November 2010 / DFID Annual review carried out in July 2011 / Final reports for the individual start-up activities, completed by project partners. / External evaluation reports for the Forest Monitor and Rainforest Foundation UK led start-up activities. / DFID also spoke with a number of project partners as part of this review: Bioclimate, Forest Monitor, Rainforest Foundation UK, Practical Action Consulting.