Type of Review: Project Completion Review

Project Title: EU Water Initiative &ACP EU Water Facility

Date started: 1/4/2009	Date review undertaken:

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
DFID has been involved in the European Union Water Facility (EUWF) and European Union Water Initiative (EUWI) since its inception and has, since that time, been involved in the informal advisory group for the EUWF, Chaired the Africa Working Group, provided financial support for the EUWI Finance Working Group (FWG) and led on a review/reform of the EUWI. It has also been involved in the EUWI Steering Group and other EUWI working groups, in particular: / Multi-stakeholder Forum, / Research working group, / Monitoring working group, / Africa water and sanitation working group, and / EECA working group. / The FWG was funded solely by DFID, the grant totalling £446,554 for the period April 2009 to May 2012. The second tranche due of £450,000, due in 2009, was reduced to £300,000 by DFID in Summer 2010 due to the limited effectiveness of the project. No further contribution was made by DFID to the project. / This project was consistent with DFID’s previous involvement. We funded over £165,000 in support of the FWG 1st Work Programme 2003-2004. This was successfully completed in early 2004, and paved the way for the 2nd Work Programme (2004-2005). / Other working groups are funded by different Member States or by the Commission itself. The Commission keeps records of the amount of funding provided by each member States for their respective working group. DFID’s funding to the FWG, for example, was modest compared to other major member states.

What were the expected results?
The objectives of the EUWI are to ensure: / Greater efficiency between EU member states and developing countries in the use of water-related development systems; / Greater political commitment to action on water and sanitation; / Better water governance arrangements, including stronger partnerships between public and private sectors; / Better co-ordination and co-operation moving towards sector wide approaches, establishing multi stakeholder processes; / Development of regional and sub-regional co-operation by application of integrated water resources management; and / The development of innovative funding mechanisms to attract additional financial resources and partners, as a basis for sustainable financing for water. / Within these broad objectives DFID’s support to the Finance Working Group (FWG) of the EUWI aimed to provide cross-cutting advice and support on matters concerning the financing of the water sector, focusing on improving financial flows to the sector.

What was the context in which UK support was provided?
The EU is the largest donor to the water sector with a strong focus on Africa. The EUWI was an initiative that was established with strong support from recipient countries with the overarching objective of increasing the prioritisation of the water sector while ensuring greater efficiency and effectiveness of the resources dedicated to the sector.

## Section A: Detailed Output Scoring

Output 1: Water Supply &Sanitation sector financing strategies in two Sub-Saharan Africa countries completed.
Output 1:final score and performance description: B / A financial strategy was completed for Lesotho. Further proposed studies did not take place due to a variety of external factors (Burkina Faso – suspension by Gov’t; Mauritania – coup; Niger – procedural difficulties).
Final results: The Lesotho financial strategy prompted good engagement with the Government and was strategic and influential. Whilst the study in Lesotho was successful, it is unfortunate that a second study was unable to be undertaken as this would have provided a basis for wider piloting of the approach and comparison with the Lesotho study. It is notable that Lesotho is one of only four countries (out of 74 developing countries that participated in the 2012 UN-Water Global Analysis and Assessment of Sanitation and Drinking-Water) the others being Iran, Bangladesh and Thailand, that was able to provide comprehensive data on financial flows to WASH. / Impact Weighting (%): 60% / Revised since last Annual Review?N / Risk: Medium / Revised since last Annual Review?N

Output 2: Experiences and lessons from these strategies disseminated.
Output 2:final score and performance description: A / This project encouraged greater collaboration with OECD around the FEASIBLE methodology. The Chair of the Finance Working Group (FWG) also participated on the OECD Task Team on Sustainable Financing, contributing to and OECD report on financing for the sector, for the WWF. In addition, a paper on financing water infrastructure and services was commissioned by the FWG, which was disseminated through workshops. / The FWG also provided advice to countries on Strategic Financial Planning (SFP), most notably Cote d’Ivoire, on using the approach and helping to prepare TORs. The SFP approach was also taken up and promoted by the African Water Facility of the African Development Bank.
Final results: / There is clear evidence that the good practices developed in the strategic financial planning processes were well disseminated and were taken up in additional countries. The FWG linked well to other initiatives looking at financing for the sector, allowing cross-learning and dissemination of results. / Impact Weighting (%): 10% / Revised since last Annual Review?N / Risk: Medium / Revised since last Annual Review?N

Output 3: Water practitioners’ awareness of financing mechanisms and tools raised.
Output 3: final score and performance description: A / Seminars have successfully been held throughout the duration of the project to bring together financing experts with water practitioners. The FWG worked closely with a range of stakeholder groups, including UNDP, Africa Working Group, AMCOW, AfDB, IFAD, various African Government Ministries and NGOs, making presentations and sharing lessons from the work. During the project, the FWG has also funded the participation of key speakers, from the developing world, at major international events such as Africa Water Week, the Stockholm World Water Week and the inaugural SWA high-level meeting, to provide case studies of practical experiences at the national level.
Final results: / The working group identified all significant opportunities to maximise dissemination of findings and successfully undertook activities to share experiences and learning opportunities with key stakeholders across the sector. / Impact Weighting (%): 10% / Revised since last Annual Review?N. / Risk: Medium / Revised since last Annual Review?N

Output 4: Realistic costing of Integrated Water Resource Management plans and schemes identified.
Output 4: final score and performance description:B / The FWG secretariat is hosted by the Global Water Partnership (GWP). GWP have a strong focus on IWRM. Work focussed on the issue of financing IWRM was also undertaken with OECD, with FWG contributing to major OECD expert meetings and reports. / Case studies were carried out on financing WRM in developing countries which aimed to improve the understanding of the issue. These complemented those organised by OECD.
Final results: / Demand from networks for water finance workshops and the response to these from FWG helped increase the awareness of financing and costing strategies for these interventions, however, there is insufficient evidence to suggest that this led to significantly improved costing of IWRM plans. / Impact Weighting (%): 20% / Revised since last Annual Review?N / Risk: Medium / Revised since last Annual Review?N

## If the project involved more than 4 Outputs please copy the box above and paste below.
## Section B: Results andValue for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? N / 1.2 Final Output score and description: B / The project successfully accomplished two of the four outputs, that of improving dissemination of experiences and lesson learning of WaSH financing strategies and the raising of awareness of the financing tools and mechanisms. Unfortunately, external problems associated with several countries selected for pilot studies severely affected the ability of the project to fully meet the output on undertaking two country-related WaSH sector financing strategies (although the one study that was carried out proved to be highly successful), whilst a lack of clear evidence of awareness raising of best practices leading to improved costing and financing strategies for IWRM affected this output.
Direct feedback from beneficiaries
1.4 Overall Outcome score and description: B / There is strong evidence that this project contributed substantially to an increased focus on water and sanitation within EU budgets. Also evidence of increased awareness of effective financial planning and budgeting for the water and sanitation sectors amongst developing country partners. Only limited evidence that this awareness resulted in large-scale adoption of improved financial planning practices. / Impact and Sustainability / Good documentation of the findings and lesson learning of this project will provide useful baseline evidence for future studies. Linkages and integration with the work of others, particularly OECD and UNDP ensured that findings from this work were incorporated into follow on work on this topic. / Although evidence of developing countries’ adoption of improved financial planning practices is limited, their growing engagement in initiatives such as the Sanitation and water for All Initiative is an indication of increased awareness of the importance of these, however, this engagement needs to continue to build to have a significant impact.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes. / 2.2 Key cost drivers / 2.3 Was the project completed within the expected timescale: Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / During the period of the project there was an increased awareness of the need for greater investment planning of the water sector by recipient countries including the need for the water sector to be included in Poverty Reduction Strategies. / 3.2 Set out what plans are in place for an evaluation. / No current plans for evaluation of the project.

4. Risk
4.1 Risk Rating (overall project risk): Medium / The following is a review of the risks inherent in this project and measures to reduce or mitigate that risk. / Risks Measures to reduce or mitigate / 1. Failure to influence the EU and its Member States to implement harmonized approach to funding the water and sanitation sector in developing countries. Mechanisms through the Steering Group, Multi-Stakeholder Forum and publicity of working group findings are included in the project. / 2. Creating dependency on funding of working group efforts by the UK. Other member States and the Commission share the burden of chairing and subsidizing the efforts of different working groups. / 3. Failure to find appetite in development sector for EUWF funding. EUWIFWG Phase 1 report identifying need for funding for water and sanitation. / Did the Risk Rating change over the life of the project?No. / 4.2 Risk funds not used for purposes intended – No. / 4.3Climate and Environment Impact

5. Value for Money
5.1 Performance on VfM measures / No specific vfm criteria were set at the project approval stage although it was recognised that any improvement in the effectiveness of financing the water sector would be highly beneficial given the large amount of funds (around £1 billion per year) provided by EU member States. / 5.2 Commercial Improvement and Value for Money / 5.3 Role of project partners / The Global Water Partnership (GWP), as host of the FWG Secretariat played a key role in the relative success of the project. / 5.4 Did the project represent Value for Money : Y (although difficult to measure objectively)

6. Conditionality
6.1 Update on specific conditions – Not applicable.

7. Conclusions
Many of the lessons that emerged from the EUWI, whether connected to finance or other key issues relating to the sector, have been taken on board by the Sanitation and Water for All initiative.

8. Review Process