## A1 Goal, Purpose, Risk
Project Completion Report (reviewed December 2011)
ARIES Project Code
ARIES Project Description | Poverty Reduction Budget Support (PRBS) 2 2009 – 2013
A1: Goal, Purpose, Risk
Goal
Goal statement | To help GoP achieve higher economic growth and poverty reduction as set out in the Poverty Reduction Strategy (PRS)
Indicator 1 | GDP growth rate
Target (if any) | 5% in 2010/11
What progress was made? | Target not achieved. The Pakistan Economic Survey 2010/11 records a provisional rate of growth of 2.4% for 2010/11.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | % of population living in poverty
Target (if any) | 3.06 percentage point decline on baseline [5 million people lifted out of poverty]
What progress was made? | Target highly unlikely to have been met (recent poverty head count data, including from 2009/10 and 2010/11 PSLM not available). Latest WB estimate (PRSCII ICR) shows headcount of 17.2% in 2007/08, down from 34.5% in 2001/02 and from 23.9% in 2004/05. 17.2% also reported for 2007/08 in unpublished GoP data. Further unpublished PSLM panel survey on a truncated sample of 8,000 households in second half of 2007/08 suggests headcount rise to 23% by the second quarter of 2008. Volatility in headcount suggests substantial portion of population lives close to poverty line. (Economic Survey states '75% of the population surrounds both sides of the poverty line'.) ADB estimates that 60% income of poor households spent on food. Economic Survey quotes average food price inflation in Pakistan of 18% over previous four years. ADB estimates that Pakistan poverty head count would increase by 4.5 percentage points with every 20% rise in food prices. Food price inflation alone, therefore, suggests poverty rate could now be 30% or more (even before impact of floods is taken into account).
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Goal Recommendation 1 | In future programmes of this nature, include poverty information additional to head count in goal statement and/or indicators. Evidence suggests that a large proportion of the population in Pakistan lives close to the poverty line, such that relatively large changes in the poverty head count can occur with relatively small changes in circumstances for households. A more reliable understanding of changes in circumstances could be achieved, therefore, by incorporating some sensitivity analysis around marginal changes to the poverty line specification.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Goal Recommendation 2 | In future programmes of this nature ensure that there is a clear commitment from government to produce regular and up to date poverty data (the most recent official estimates at December 2011 are from 2005/06)
Goal Recommendation 3
Purpose
Project Purpose | PRS programme implementation better supported by greater coherence between PRS policy, public expenditure and sector reform
Indicator 1 | PRSP budgetary expenditure targets (as a % of GDP)
Target (if any) | 2.2% of development budget spent on PRSP programmes; 4.43% of recurrent budget spent on PRSP programmes
What progress was made? | Target achieved for aggregate spend under current definition for PRSP expenditure (6.88% against a target of 6.63%), but aggregate target spend not achieved under original definition (5.72% against a target of 6.63%).
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Allocative efficiency in public spending
Target (if any) | Begin preparations for development of MTBF into Medium Term Expenditure Framework (MTEF) including: • Refinement of top down resource envelope consistent with macroeconomic stability and PRSP2 priorities • Bottom up estimates of current and medium term costs of national programmes • Preliminary PRSP 3 objectives and cost estimates developed (Review assumes date for milestone is 2010/11)
What progress was made? | Target only partially achieved in 2010/11. With regard to indicator bullet point 1, the fact is that the MoF now has a robust process and relevant tools for specifying a top-down resource envelope that is consistent with macroeconomic stability. Macroeconomic stability not delivered in practice because of failure at political level to deliver difficult policies assumed in macroeconomic projections. Otherwise, functional allocations remain more ad hoc than based on a strategic vision for the PRSP (largely due to weak political support for the PRSP). With regard to bullet point 2, whilst ministries are now required to specify outputs and outcomes and to allocate ceilings to these accordingly, these do not derive from dedicated sector strategies. Moreover, there is little evidence of robust costing taking place and arbitrary allocation of ceilings to desired targets cannot be fully ruled out. With regard to bullet point 3, work on defining objectives and associated cost estimates for a PRSP 3 has yet to commence.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Social Indicators (i) Increased net enrolment rate in primary education A: Boys B: Girls (ii) percentage of children under 5 who are underweight (iii) % of assisted births in a public or private health care facility
Target (if any) | (i) A: 70% B: 64% ii) 33% iii) 48% (Review assumes date for milestone is 2010/11)
What progress was made? | Targets largely not achieved (part (i) partially achieved; part (ii) achievement unknown; part (iii) not achieved). 5 - 9 age group (from 2010/11 PSLM data) net enrolments in 2010/11 = 60% (boys) and 53% (girls). 6 - 10 age group (from 2010/11 PSLM data) net enrolments in 2010/11 = 71% (boys) and 61% (girls). Children under five who are underweight in 2010/11. Data not available. Proportion of assisted births in 2010/11 = 45% (doctor = 35%; nurse = 6%; midwife = 4%).
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Were Purpose Assumptions realised? If so, to what degree, and what was the effect on the project? | Key purpose assumptions substantially weakened towards the end of the programme. Global economic crisis has worsened since project design (Eurozone crisis in addition to effects of high international food and commodity prices). Domestically, SBA went off track in 2010 and never recovered, reflecting underlying failure to implement difficult economic reforms in tax administration, energy sector and subsidies, resulting in planned expenditures scaled back (particularly PSDP), plus inflationary and 'crowding out' consequences from deficit financing. Revenue mobilisation has been weaker than anticipated (tax to GDP in 2010/11 no different from previous 10 year average, and non-tax ratio slightly below 10 year average). FG support for MTBF reasonably robust, though continued failure to secure institutional changes envisaged under reform process. Continued commitment to pro-poor spending difficult to fully grasp because of breadth of content of PRSP spend and particularly because of inclusion of subsidies without dilineation of pro-poor component.
What evidence is there that achievement of the Purpose contributed or continues to contribute to the realisation of the Goal? If it has done so or is doing so, to what degree? | Weak evidence of Purpose contributing to Goal. Aggregate PRSP spend above target but includes substantial non-poor expenditure expenditure components (e.g. subsidies, higher education, referral hospitals). Capacities for top-down expenditure planning (including FPF, BFP) consistent with macroeconomic projections substantially strengthened, but failure of politicians to drive through policy reforms assumed in macro projections. Otherwise link between strategic vision of PRSP and functional ceilings remains underdeveloped. Moreover, PRSP does not constitute primary strategic planning tool at federal level (cf MTDF) and ownership at provisional level is very weak. Not surprising, therefore, that social indicators are generally falling short of targets.
What is the evidence that the achievement of the Purpose can be attributed to progress made in delivering the Outputs? | Achievement of purpose is weak which reflects weak achievement in output delivery. Lack of ownership of PRSP outside FG Finance Division meant that Output 3 (National Assembly oversight of PRSP) became de-linked from purpose. Failure to deliver policy reforms under SBA impacted on delivery of both outputs 1 and 2 and effectively removed any scope for progress on Output 4 (common donor/GoP approach to GBS monitoring), undermining delivery of project purpose. 18th Ammendment made key indicator for Output 1 irrelevant (National Education Strategy). A degree of output delivery was achieved with BISP implementation (Output 1), which contributed to progress observed in Purpose indicator 1, and with strengthened PFM (Output 2), which contributed to progress observed in Purpose indicator 2.
Purpose Recommendation 1 | In future programmes seeking to influence delivery of pro-poor social sector policies (including SBS at provincial level) purpose statement should seek to include indicators capturing GoP strategic vision at sector level for delivering pro-poor policies. The purpose statement in this case was supported by a good mix of indicators, including pro-poor spending, key pro-poor outcome indicators and processes for preparation of output-based and policy-led budget submissions (i.e. through effective MTBF reform). The effectiveness of the purpose statement was weakened by absence of an indicator of extent to which strategic vision exists at sector level for planning and delivering pro-poor policies in a resource constrained environment (e.g. through effective sector strategies).
If more Recommendations need to be made, click the '+' box on the left-hand side.
Purpose Recommendation 2 | In future programme, ensure that log-frame definitions for purpose indicators are clear and unambiguous and, when policy underlying an indicator changes, ensure that relevant change is captured in log-frame if required. (cf ambiguity over log-frame indicator for net primary enrolment with regard to age groups 5 - 9 and 6 - 10.
Purpose Recommendation 3 | In future programmes of this nature, ensure that indicators representing poverty-focussed spending are defined to exclude spending on activities and outputs that are predominantly not used by the poor. The broad coverage of PRSP spending in Pakistan is such that it is unclear whether changes in overall PRSP spending are representative of de facto changes in pro poor spending.
Project Purpose Score | 3
Purpose Justification | Key purpose assumptions not holding resulting in deteriorating economic circumstances, growing deficits (and deficit financing) and ability of government to deliver budgets as planned. Whilst underlying causes are partly exogenous, the key domestic issue has been failure of government to drive through difficult policy reforms. Although target for overall PRSP spend was achieved, spending also incorporated non pro-poor components. Targets for social indicators partially met (although exogenous factors, particularly floods, have undoubtedly contributed to this).
Risk
Project Risk Rating or latest Overall Risk Score. | High
Was the Project Risk Rating revised since the last review? | No
If Yes, why was this?
If new risks have emerged since the last review, click the '+' box on the left-hand side and list them in the appropriate boxes.
Risk Recommendation 1
If more Recommendations need to be made click the '+' box on the left-hand side.
Logframe, DSOs, Cross-Cutting Markers
Logframe revised since the last review? | No
If Yes, why was this?
Logframe Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
DSOs revised since the last review?
If Yes, why was this?
DSO Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Cross-Cutting Markers revised since the last review?
If Yes, why was this?
CCM Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Government improves conditions for inclusive growth and basic service delivery
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 60%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | High
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 100%
Indicator 1 (leave blank if standard indicator | Status of IMF Stand By Arrangement (SBA) programme
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Successful completion of IMF programme (Review assumes date for milestone is December 2011 - the month of the review)
What progress was made, including numbers | Target not achieved. First four reviews concluded successfully (fourth in May 2010 following observance of end-March 2010 performance criteria). SBA extended by nine-months to September 30, 2011 following GoP request for time to complete performance criteria for 5th and 6th Reviews. Fifth review delayed due to failure to implement VAT on July 1, 2010 and end-June 2010 performance criteria (general budget deficit, government borrowing from central bank). Further economic deterioration and impact of floods meant it was not possible to complete corrective actions for fifth review before December 31, 2010. Extension granted to enable completion of GST reform, correct fiscal policy, and amend legislation for financial sector. Discussions have continued with IMF (with missions in March, May and November 2011, the latter of which was for Article IV discussion and analysis). Core unresolved issues included enforcement of RGST and its passage through the Federal and Provincial Governments, resolution of the circular debt in the power sector and curtailment of non pro-poor subsidies.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Implementation status of national education strategy
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Implementation strategy approved and under implementation (Review assumes date for milestone is December 2011 - the month of the review)
What progress was made, including numbers | Not achieved. Relevance of National Education Strategy (NES) at federal level removed following 18th Ammendment. Chapter 9 of the National Education Policy (NEP) provides implementation framework with modilities to be decided by implementaion agencies. Following approval of 18th Amendment, all implementing work in Federal Ministry of Education (subsequently abolished) stopped. NEP largely leaves implementation responsibilities to the stakeholders (i.e. provinces). Substantial work at province level largely yet to commence at the closure of PRBS2. At time of annual review, KPK had a full sector plan and was on track for preparation of a sector strategy. Punjab working toward a sector plan (but not yet established). Action plan developed in Balochistan (but no sector plan as such yet). Sindh still to prepare planning framework.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Expansion of Benazir Income Support Programme (BISP) | 2.8
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 7 million families reached by BISP in 2010/11
What progress was made, including numbers | Not achieved (4 million families catered for in FY10/11 budget, with around 2.5 million reached towards end of the year. BISP attempts creation of welfare state for poorest of the poor within very short time period. BISP initiated with allocation of Rs.34 billion in FY08/09 (aimed at 3.5 million families). No existing targeting mechanism, so use of makeshift mechanism relying on politicians to identify poor families (subsequently found to have wrongly identified eligible households in 75% of cases). In meantime, DFID/WB support used to create objective targeting mechanism based on a proxy means-testing Poverty Scorecard and a nationwide survey. A huge undertaking - test survey carried out mid 2009, main survey underway from October 2010 and still ongoing. 5.9 million elligible families identified by November 2011 from 80% population coverage. FY09/10 allocation (Rs. 70 bn) for 5m families. 35.3 bn disbursed to 2.29 million (Rs. 31.6 bn under initial targeting mechanism, Rs. 3.7 bn under new mechanism). FY10/11 allocation (Rs. 50 bn) for 4 million families, with some 2.5 million families reached towards end of the FY. Rs. 50 billion also allocated for FY11/12
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 1 | 3
Impact Weighted Score | #VALUE!
Justification for the Score | Indicators only partially achieved. Ultimately failure to secure key tax administration and power sector reforms and to address non pro poor subsidies meant SBA programme could not be completed beyond 4th review. Last two disbursements not made and key economic policy reforms not undertaken. Less than 4 million families out of a target of 7 million reached in BISP. Resource requirements aside, reaching the full target amount depends on completing the proxy means testing survey, processing the data and a range of other logistical tasks. Log-frame targets were almost certainly not consistent with institutional and logistical requirements for establishing and delivering the BISP. NES indicator no longer relevant following 18th Ammendment.
Output 1 Recommendation 1 | Targets for indicators similar to that for BISP implementation in future log-frames should be established consistent with GoP capacities for design and delivery of relevant institutional and logistical requirements.
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Government strengthens public financial management and encourages better use of federal resources
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 30%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | Medium
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 30%
Indicator 1 (leave blank if standard indicator | PEFA performance indicators: PI1: Aggregate expenditure out-turn compared to original approved budget PI3: Aggregate revenue out-turn compared to original approved budget PI6: Comprehensiveness of information included in budget documentation PI12: Multiyear perspective in fiscal planning, expenditure policy and budgeting PI23: Availability of information on resources received by service delivery units
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | PI1: C P3: B+ PI6: B+ PI12: B+ PI23: B+ (Review assumes date for milestone is either December 2011 - the month of the review - or FY2010/11 - the previous financial year - as appropriate with regard to PEFA criteria)
What progress was made, including numbers | See Attachment 1 for more details with regard to the following. PI-1 target achieved. FY80/09, FY09/10, FY10/11 performance equivalent to PEFA 'B'. PI-3 target achieved. FY80/09, FY09/10, FY10/11 performance equivalent to PEFA 'A'. PI-6 target achieved. The baseline likely to be incorrect. 2011/12 target incorrect. (basline should be 'C'; 'B+' is not a valid score for PI-6, therefore assume 'B' is the correct target; current score = 'B') PI-12 target not achieved. The baseline likely to be incorrect (basline should be 'D+'; current score = 'D+') PI-23 target not relevant The baseline likely to be incorrect (basline should be 'D'; current score = 'D'). Analysis for PI-23 is no longer relevant at the federal level following implementation of the18th Amendment.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Tax as a % of GDP
Is this a Standard Indicator? | Yes
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 12.5% (Review assumes date for milestone is 2010/11)
What progress was made, including numbers | Milestone not achieved. Provisional estimate of tax as a proportion of GDP for 2010/11 as reported in Economic Survey = 10.5%.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 2 | 3
Impact Weighted Score | #VALUE!
Justification for the Score | Milestones for PI-1, PI-3, PI-6 achieved (assuming milestone for PI-6 should read 'B' instead of 'B+'). Despite clear progress in both process and quality of budget and MTBF preparation over PRBS2 period, PI-12 has not been met (Note, PEFA baseline incorrectly established). However, change management requirements to achieve 'A' over 3 year period were completely unrealistic. With regard to PI-23, indicator no longer of relevance following movement of social sector service delivery from federal to provincial level after 18th Ammendment. In addition, milestone for tax to GDP ratio (Indicator 2) has not been achieved.
Output 2 Recommendation 1 | In future log-frames for PRBS (or other) purposes using PEFA scores as milestones, ensure appropriate and correct baselines are established and relevant scores are used for milestones.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | In future log-frames that refer to progress with PEFA indicators, ensure that targets are based on realistic timescale for reform, taking proper and full account of government circumstance and capacities
Output 2 Recommendation 3 | In future log-frames that refer to progress with PEFA indicators, ensure that relevant indicators only are used and be prepared to use different indicators if and when any of those in use are no longer relevant.
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Enhanced responsiveness and accountability of Federal and Provincial Governments
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 5%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | Medium
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 100%
Indicator 1 (leave blank if standard indicator | Capacity of National Assembly to scrutinise PRSP implementation
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Budget standing committee provide informed responses to regular progress reports on PRSP implementation and present this to the National Assembly
What progress was made, including numbers | Not achieved. There has been no progress on this indicator as the Budget standing committee has not been oriented on PRSP according to information available.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 3 | 5
Impact Weighted Score | #VALUE!
Justification for the Score | No progress made.
Output 3 Recommendation 1 | Where change management indicators are to be incorporated in future log-frames, ensure that these are specified in a participatory manner and are consistent with government vision with regard to the changes under consideration. The review team found little or no institutional knowledge of the decisions underlying inclusion of indicator for National Assembly PRSP scrutiny in log-frame in DFID or GoP which suggests indicator not sufficiently widely discussed with GoP or part of GoP vision for change in this area.
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Progress towards common agreement between budget support donors and government on performance and financial mechanisms to support the PRS
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 5%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | Medium
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 100%
Indicator 1 (leave blank if standard indicator | PAMF implemented
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Parameters on common performance assessment and monitoring framework (PAMF) agreed (Review assumes date for milestone is December 2011 - the month of the review)
What progress was made, including numbers | Not achieved. No discussions for establishing a common performance assessment monitoring framework for budget support donors took place. Potential scope for such discussion occured through distribution of a Foreign Assistance Policy Framework (FAPF) by GoP among donor partners for comment in late 2010. Scope for such discussion in practice effectively removed by cessation of GBS instruments by major donor partners, including DFID.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 4 | 5
Impact Weighted Score | #VALUE!
Justification for the Score | There has been no discussion among partners with regard to the estalishment of a common framework, let alone agreeing parameters for such a framework.
Output 4 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 5
Impact Weighted Score | #VALUE!
Justification for the Score
Output 5 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 6
Impact Weighted Score | #VALUE!
Justification for the Score
Output 6 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 7
Impact Weighted Score | #VALUE!
Justification for the Score
Output 7 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 8
Impact Weighted Score | #VALUE!
Justification for the Score
Output 8 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 9
Impact Weighted Score | #VALUE!
Justification for the Score
Output 9 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 10
Impact Weighted Score | #VALUE!
Justification for the Score
Output 10 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-12-09
Impact Weighting (must = 100) | 100%
Total Impact Score | #VALUE!
Output Risk | #REF!
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners
Working with Partners Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
2. Best Practice / Innovation
Best Practice / Innovation Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
3. Project Management
Project Management Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships evolved. | Experience of this programme emphasises the need for greater investment in knowledge and understanding of political context and constraints and likely impact on these on the outcome of the programme.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1 | Ensure that design of future programmes in Pakistan are appropriately informed by an understanding of the political context and constraints within which the programme is to be implemented. One of the key outputs for this programme was delivery of a successful IMF SBA. In turn, this required effective political commitment to driving through difficult and unpopular (but required) economic policy reforms (tax policy, energy pricing and cost recovery, subsidies). Ultimately, this turned out not to be politicaly feasible. Delivery of the programme otherwise relied to a large extent on solid political support for the PRSP both federal and (particularly) provincial level. The GoP consituency for the PRSP, however, has been thin throughout the life of the programme, with support largely confined to the Finance Division at federal level (with much of this being form rather than substance) and little or no ownership of the PRSP at provincial level (where most of the delivery was meant to be).
If more Recommendations need to be made, click the '+' box on the left-hand side.
Evidence: Key documents
Quest No.
Evidence Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions were attached to this project, was disbursement suspended at any point because of the conditions?
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Sustainability
Comment on the likelihood of the benefits arising from this project being sustained beyond the end of project, and any challenges to sustainability.
Sustainability Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.

## E Recommendations
E: Recommendations
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | In future programmes of this nature, include poverty information additional to head count in goal statement and/or indicators. Evidence suggests that a large proportion of the population in Pakistan lives close to the poverty line, such that relatively large changes in the poverty head count can occur with relatively small changes in circumstances for households. A more reliable understanding of changes in circumstances could be achieved, therefore, by incorporating some sensitivity analysis around marginal changes to the poverty line specification.
R2 | In future programmes of this nature ensure that there is a clear commitment from government to produce regular and up to date poverty data (the most recent official estimates at December 2011 are from 2005/06)
R3 | 0
A1: Purpose
R1 | In future programmes seeking to influence delivery of pro-poor social sector policies (including SBS at provincial level) purpose statement should seek to include indicators capturing GoP strategic vision at sector level for delivering pro-poor policies. The purpose statement in this case was supported by a good mix of indicators, including pro-poor spending, key pro-poor outcome indicators and processes for preparation of output-based and policy-led budget submissions (i.e. through effective MTBF reform). The effectiveness of the purpose statement was weakened by absence of an indicator of extent to which strategic vision exists at sector level for planning and delivering pro-poor policies in a resource constrained environment (e.g. through effective sector strategies).
R2 | In future programme, ensure that log-frame definitions for purpose indicators are clear and unambiguous and, when policy underlying an indicator changes, ensure that relevant change is captured in log-frame if required. (cf ambiguity over log-frame indicator for net primary enrolment with regard to age groups 5 - 9 and 6 - 10.
R3 | In future programmes of this nature, ensure that indicators representing poverty-focussed spending are defined to exclude spending on activities and outputs that are predominantly not used by the poor. The broad coverage of PRSP spending in Pakistan is such that it is unclear whether changes in overall PRSP spending are representative of de facto changes in pro poor spending.
A1: Risk
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Logframe
R1 | 0
R2 | #REF!
R3 | #REF!
A1: DSOs
R1 | 0
R2 | #REF!
R3 | #REF!
A1: Cross-Cutting Markers
R1 | 0
R2 | #REF!
R3 | #REF!
A2: Outputs
R1.1 | Targets for indicators similar to that for BISP implementation in future log-frames should be established consistent with GoP capacities for design and delivery of relevant institutional and logistical requirements.
R1.2 | #REF!
R1.3 | #REF!
R2.1 | In future log-frames for PRBS (or other) purposes using PEFA scores as milestones, ensure appropriate and correct baselines are established and relevant scores are used for milestones.
R2.2 | In future log-frames that refer to progress with PEFA indicators, ensure that targets are based on realistic timescale for reform, taking proper and full account of government circumstance and capacities
R2.3
R3.1 | Where change management indicators are to be incorporated in future log-frames, ensure that these are specified in a participatory manner and are consistent with government vision with regard to the changes under consideration. The review team found little or no institutional knowledge of the decisions underlying inclusion of indicator for National Assembly PRSP scrutiny in log-frame in DFID or GoP which suggests indicator not sufficiently widely discussed with GoP or part of GoP vision for change in this area.
R3.2 | #REF!
R3.3 | #REF!
R4.1 | 0
R4.2 | #REF!
R4.3 | #REF!
R5.1 | 0
R5.2 | #REF!
R5.3 | #REF!
R6.1 | 0
R6.2 | #REF!
R6.3 | #REF!
R7.1 | 0
R7.2 | #REF!
R7.3 | #REF!
R8.1 | 0
R8.2 | #REF!
R8.3 | #REF!
R9.1 | 0
R9.2 | #REF!
R9.3 | #REF!
R10.1 | 0
R10.2 | #REF!
R10.3 | #REF!
B: Scoring
R1 | 0
R2 | #REF!
R3 | #REF!
C: Knowledge Sharing
Working with Partners
R1 | 0
R2 | #REF!
R3 | #REF!
Best Practice / Innovation
R1 | Ensure that design of future programmes in Pakistan are appropriately informed by an understanding of the political context and constraints within which the programme is to be implemented. One of the key outputs for this programme was delivery of a successful IMF SBA. In turn, this required effective political commitment to driving through difficult and unpopular (but required) economic policy reforms (tax policy, energy pricing and cost recovery, subsidies). Ultimately, this turned out not to be politicaly feasible. Delivery of the programme otherwise relied to a large extent on solid political support for the PRSP both federal and (particularly) provincial level. The GoP consituency for the PRSP, however, has been thin throughout the life of the programme, with support largely confined to the Finance Division at federal level (with much of this being form rather than substance) and little or no ownership of the PRSP at provincial level (where most of the delivery was meant to be).
R2 | #REF!
R3 | #REF!
Project Management
R1 | Targets for indicators similar to that for BISP implementation in future log-frames should be established consistent with GoP capacities for design and delivery of relevant institutional and logistical requirements.
R2 | In future log-frames for PRBS (or other) purposes using PEFA scores as milestones, ensure appropriate and correct baselines are established and relevant scores are used for milestones.
R3 | Where change management indicators are to be incorporated in future log-frames, ensure that these are specified in a participatory manner and are consistent with government vision with regard to the changes under consideration. The review team found little or no institutional knowledge of the decisions underlying inclusion of indicator for National Assembly PRSP scrutiny in log-frame in DFID or GoP which suggests indicator not sufficiently widely discussed with GoP or part of GoP vision for change in this area.
C: Other Comments
R1
R2 | #REF!
R3 | #REF!
C: Evidence
R1 | 0
R2 | #REF!
R3 | #REF!
D: Conditionality
R1 | 0
R2 | #REF!
R3 | #REF!
D: Sustainability
R1 | 0
R2 | #REF!
R3 | #REF!
Additional Recommendations arising
R1
R2
R3