Type of Review: Project Completion Review

Project Title: DFID Support to the Nepal HIV / AIDS Programme 2005-11

Date started: 2005	Date review undertaken: 16 March 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
Between 2005 and December 2011 DFID provided £16.6 (approx $26) million of grant support to Nepal’s response to HIV/AIDS to assist the Government of Nepal to implement its HIV and AIDS strategies and plans and to address areas of the response not covered by other donors. The programme focused on: / targeted HIV prevention, care, treatment and support for three of the groups most at risk of contracting HIV (injecting drug users, men who have sex with men and seasonal male labour migrants and their wives) and people living with HIV/AIDS (PLHA) (64% of total expenditure); / strengthening and improving the safety of national blood supplies (5% of expenditure); and / developing the capacity of the national entities responsible for the national response to HIV (3% of expenditure).

What were the expected results?
The programme goal was to optimise prevention and reduce the social impact of HIV and AIDS, as measured by a reduction in HIV prevalence amongst three most at-risk populations – men having sex with men (MSM); injecting drug users (IDU); and labour migrants. / The programme purpose was to optimise prevention, thereby changing behaviour to reduce the transmission of HIV among most at-risk populations, and to provide care and support and reduce social impact among vulnerable groups (10-24 years, labour migrant, male sex workers (MSW), MSM, IDU, and PLHA), as measured by: / increased awareness and knowledge of safer injecting and safer sex among injecting drug users, men who have sex with men, male sex workers, people living with HIV/AIDS, and migrants; / increased access to prevention, care and support services; / provision of quality services of HIV care and support throughout the continuum from health facilities to home and community; and / a strengthened National AIDS Programme. / The full expected results are shown in Appendix A.

What was the context in which UK support was provided?
Nepal is a country of 26.6 million people (2011 Census). Although the proportion of the population living below the poverty line substantially decreased from 42% in 1995/96 to 25.2% in 2010/11 (Central Bureau of Statistics, 2011) about seven million Nepalese still live in poverty. The country’s relatively low incomes, levels of literacy and health mean that Nepal has the second lowest Human Development Index ranking of all Asian countries (138/169 countries), with only Afghanistan ranking lower. Armed conflict between 1996 and 2006 resulted in a fragile political settlement. On average Nepal has experienced one government a year since the return of multiparty democracy in 1990 and in 2011 the country saw five health ministers. The governance issues that this has created have constrained many of Nepal’s development gains. / Nepal has a declining estimated adult HIV prevalence rate of 0.33% (down from 0.4% in 2009) with an estimated 55,626 HIV-positive Nepalese (NCASC 2011) of which approximately 10% are currently registered for anti-retroviral treatment. 72% of estimated people living with HIV/AIDS are men, and 28% women. There are an estimated six new HIV infections per day and about 4,900 people die from AIDS each year (NCASC 2011 fact sheet 1). Nepal has a concentrated HIV epidemic with infection mostly concentrated amongst most at-risk populations: these include injecting drug users (IDU), men who have sex with men (MSM), male sex workers (MSW), female sex workers (FSW) and their clients, and male labour migrants and their spouses. Until now infection has been transmitted mostly by unprotected sex amongst these and other at-risk groups and via injecting drug use. Infection is becoming more common amongst the wives of men in the high risk categories including the hundreds of thousands of wives of migrant workers, creating a risk of a generalised epidemic. Government, United Nations and civil society institutions play an important role in Nepal’s response to HIV. A strong set of networks and NGOs has developed to represent IDU, MSM, FSW and PLHA. These organisations are mostly made up of affected people. They represent the interests of their constituents and provide prevention, treatment, care and support services, some of which may be in short supply from the public health service. The networks of male and female sex workers, IDU, PLHA and MSM participate in national HIV/AIDS coordination bodies including the Country Coordinating Mechanism of the Global Fund and District AIDS Coordination Committees (DACC), and in drafting the biannual UNGASS report and preparing national standard operational procedures. / The national HIV programme enjoys some political commitment and policy level support. The response to HIV and AIDS is included in the current three-year national development plan (2010/11 to 2012/13) and the Nepal Health Sector Programme 2 (NHSP 2). An important milestone for improving the legal framework was the Supreme Court ruling of 2007 that protects the rights of sexual minorities (Third Gender). Other key policy measures such as the AIDS bill and the Drugs Control Strategy are pending. / The main national policy documents for Nepal’s HIV response are the fourth National HIV and AIDS Strategic Plan (NSP, 2011–2016) and the National Action Plan on HIV and AIDS (2008-2011). All HIV programmes in Nepal are framed within these guiding documents: / The NSP recognises the need to scale-up and decentralise HIV and STI services to improve access for the general population — important given the increasing number of HIV infections among the wives of labour migrants. / The national action plan (2008–2011) prioritises targeted interventions for sex workers, MSM, IDU and migrant workers and their families and also has strategies targeting youth (including street children), uniformed services, prisoners and trafficked women and girls. / The estimated cost of implementing the national action plan was $128 million. / Nepal’s response to HIV/AIDS has been almost entirely funded from external sources. The Global Fund, DFID, USAID and UNODC were the main donors between 2006 and 2010 and from 2011, the World Bank became a major donor. The government provided 1% of the national HIV programme budget in 2009 and 2% in 2010. In 2009 and 2010 most spending went on prevention (46%), followed by programme management and administration (23%), the enabling environment (10%), treatment and care (7%) and voluntary counselling and testing (7%) (HSCB 2011). / The end of DFID funding was designed to coincide with the beginning of a new mechanism for donors to fund HIV and STI interventions in Nepal. In September 2009 DFID and UNDP Nepal agreed that DFID would conclude its commitment to the national HIV response via UNDP on 31 March 2011. It was also agreed that support for most at-risk populations NGO activities via UNDP would end in December 2010. It was expected that from 31 March 2011 that National Centre for AIDS and STI Control (NCASC) would take over the contracting of HIV/AIDS service provision to NGOs with funding under NHSP 2. / The new funding mechanism is going ahead under the government’s second Nepal Health Sector Programme (2010-2015). NHSP 2 is funded by a combination of pooled and non-pooled donor funds through the government’s budget. The World Bank, DFID, AusAID, KfW and the GAVI Alliance are pooling their funds whilst the non-pooled funds are from GIZ, USAID, UNFPA, UNICEF and WHO. Most funding for HIV related services by NGOs to most at-risk populations comes from pooled funds. Coordination, supervision and monitoring of this programme is being carried out by NCASC with the Department of Health’s Logistics Management Division managing the procurement of services from NGOs. The aim of this approach is to promote donor harmonisation and government ownership of the national HIV response. / The financial agreement between the Government of Nepal and external development partners (EDPs) was signed in August 2010 and the process of contracting services out to NGOs began in September 2010. However, delays meant that the first contract was only signed with an NGO to deliver services (to prisoners) in August 2011. Further contracts have been signed to deliver services to IDU, MSM, migrants and PLHA in October and November 2011. / DFID planned to reduce funding in 2010 as it was expected that funds would be soon channelled through the government under NHSP 2. The slow contracting process under NHSP 2 meant however that DFID funding for services was extended into 2012. / Much of this assessment draws on the independent evaluation of the programme completed in early 2012[1].
[1] Roos J, Gleason GR, Poudyal PR, Dixit S (2012). DFID Support to the National HIV/AIDS Programme in Nepal 2005–2011: External Evaluation Plus.

## Section A: Detailed Output Scoring

Output 1: Implementation of Comprehensive HIV prevention packages for most-at-risk population groups
Output 1: final score and performance description: A+ / The table below shows achievements against target during 2006-11 for each of the indicators specified for Output 1. Six out of fifteen targets (40%) were substantially exceeded. A further five out of fifteen targets (33%) were exceeded or met. Four out of fifteen targets (28%) were not reached. Overall therefore, it is judged that the performance was slightly above expectation. The reviewer’s view is that the weighting attributed to this output is too low at 50%. The original logframe contained a weight of 70% for this target and the rebalancing is possibly due to a rising emphasis on sustainability and capacity development as partners working in the sector got closer to the date where government would take over service delivery.
Final results: / Indicators 2006 to 15 Oct 2011 / target achieved % achieved / No. IDU received detoxification, treatment & counselling thru rehab. centres (new & old) 13,844 12,114 88% / No. condoms distributed to IDU 392,005 602,753 154% / No. IDU received STI diagnosis and treatment (no. of treatments) 2,959 3,164 107% / No. IDU completed voluntary counselling & testing for HIV (VCT) 3,693 3,959 107% / No. needles with syringes distributed through harm reduction programme 1,015,150 1,386,843 137% / No. IDU reached by HIV/AIDS prevention programme (harm reduction) (new 2006, 2010, 2011; new & old 2007, 2008, 2009)[2] 30,138 20,881 69% / No. MSM/MSW completed VCT 16,355 17,162 105% / No. condoms distributed to MSM/MSW 3,026,756 4,611,572 152% / No. Information Education and Communication (IEC) materials distributed to MSM/MSW 470,175 726,338 154% / No. MSM/MSW reached with targeted HIV prevention (new 2006, 2010, 2011; new & old 2007, 2008) 167,242 180,694 108% / No. migrants & families diagnosed and treated for STI 135,731 119,532 88% / No. migrants & families completed VCT 93,227 96,538 104% / No. condoms distributed to migrants & families 4,690,300 4,023,904 86% / No. migrants & families reached with targeted HIV prevention (new 2006, 2010, 2011; old 2007, 2008, 2009) 1,921,728 3,371,597 175% / No. PLHA received palliative care (medical, psycho-social, economic support) (new & old) 10,910 13,859 127% / Impact Weighting (%): 50% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N
[2] Note inconsistency in the recording of this indicator over time by the UNDP Programme Management Unit.

Output 2: Interventions in three prisons
Output 2: final score and performance description: B / The programme fell slightly short of expectation in reaching prisoners with targeted HIV prevention information, due to an increasing realisation during the programme that prison populations, unlike some other countries, are unlikely to be a significant driver of the HIV epidemic in Nepal. The independent evaluation recommended that in future, there was little justification for making prisoners a targeted most at-risk population for HIV prevention work.
Final results: / Indicators 2006 to 15 Oct 2011 / target achieved % achieved / No. prison inmates reached with targeted HIV prevention information 2,000 1,742 87% / Impact Weighting (%): 5% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review?N

Output 3: Blood Safety
Output 3: final score and performance description: A / The programme met expectations in screening blood for HIV..
Final results: / Indicators 2006 to 15 Oct 2011 / target achieved % achieved / % blood units adequately screened for HIV according to national / WHO guideline All units 100% 100% / No. blood units screened 657,983 100% / Impact Weighting (%): 5% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 4: Establishing a National Strategic Information System
Output 4: final score and performance description: B / Final results: / Targets for this output were: / National monitoring and evaluation (M&E) system established and strengthened at both NCASC and HIV/ AIDS and STI Control Board (HSCB) / Number of districts pilot testing the National M&E System (10 by 2010) / Number of districts where the DACC has been activated and strengthened (35 by 2010) / The independent evaluation of the programme judged that its support for development of a national HIV/AIDS strategic information system had resulted in substantial progress towards full implementation of a system at NCASC. Key functions needed to effectively gather, report and analyse information on the health aspects of HIV and AIDS were expected to be operational soon. Piloting of district health M&E in six districts with programme support contributed to the development of formats and procedures, but at the end of 2011 only the national HIV M&E system was functioning, and nothing at sub-national level. / From 2009, the Project Management Unit of UNDP (PMU) provided NGO and other network partners with national indicator forms and reporting procedures, but nevertheless reports were not sent by many CBOs and NGOs and poor quality reporting was provided by some CBOs and NGOs. The problem was exacerbated by the fact that much donor funding of these organisations took place without a direct link to Ministry of Health and Population (MoHP). The former director of NCASC and district health officers said that, because NGO funding came directly from UNDP and others, NGOs’ priorities were to report to donors instead of Government M&E channels (DACC, NCASC and HSCB). There is little evidence that NCASC and HSCB made use of the data fed to them, although the evaluation did find some evidence of use by district health offices in the pilot, to help prepare district plans on HIV and AIDS. The evaluation did not find any examples of feedback to NGOs and networks on information submitted to NCASC, HSCB and their DACC. / Nepal’s HIV health strategic information system is the responsibility of NCASC whilst the non-health part comes under HSCB. However, the end of funding for non-health HIV M&E in 2010 led to the suspension of the development of the non-health HIV M&E system. Indicators for this have not been included in NCASC’s HIV M&E database. Accordingly, the evaluation found a lack of clear organisational responsibility for non-health related M&E information generated by NGOs and government organisations outside the Ministry of Health and Population. This included information generated under the Ministry of Education, Ministry of Labour, Ministry of Women, Children and Social Welfare on social protection programmes. Programme investments in the M&E system for non-health HIV data may be lost unless further resources are made available for developing the system. / DACC have a major role to play in coordinating the district level response to HIV and in gathering strategic information on the response. However, the evaluation found that most DACC are severely under-resourced and their lines of reporting are unclear. Most NGOs seem to liaise directly with district development committees and district health offices.

Only one out of the target of two national monitoring and evaluation systems were established and strengthened (the one at NCASC dealing with health-related HIV information was established but the one at HSCB dealing with non-health HIV information was not).

Of the ten target districts piloting the national HIV M&E system, only six actually did so.

The evaluation fell short of assessing the level of activity and strengthening that took place in DACC, although it did specify that inputs were provided to 35 as per the target in the programme logframe. Nevertheless, it has not been possible to assess this indicator.

Impact Weighting (%): 5%
Revised since last Annual Review? Y

Risk: Low
Revised since last Annual Review? N
Output 5: Strengthen Institutional Framework for effective HIV/AIDS response
Output 5: final score and performance description: B / The reviewer’s view is that the weighting attributed to this output is too high at 30%, especially considering that only 3% of programme expenditure was used to deliver the output.
Final results: / Targets for this output were: / Capacity development plan for NCASC/MoHP developed and implemented / Institutional Review of NCASC conducted and Human Resource Plan developed and implemented by NCASC / Effective HIV/AIDS monitoring and data base system developed and implemented at NCASC / Programme management & Financial Management System strengthened at NCASC / NCASC and HSCB are responsible for the national response to HIV in Nepal. The National Centre for AIDS and STD Control (NCASC) is a department of the Ministry of Health and Population (MoHP) and is the key agency for HIV/AIDS service delivery. It is mandated to coordinate and supervise service delivery in the public sector and between the public sector and NGOs working on HIV/AIDS. The National HIV/AIDS and STI Control Board (HSCB) was established as a semi-autonomous entity in August 2007 to lead the multi-sector response to HIV. It is tasked with policy development, strategic and operational planning, strengthening multi-sector coordination, overall M&E of the national response and mobilizing national and international resources for the multi-sectoral response to HIV and AIDS. They are overseen by the National AIDS Council, which meets under the guidance of the Office of the Prime Minister, but infrequently and ineffectively. / A capacity assessment of NCASC by an external consultant in 2009 recommended a three year long capacity building programme from 2010. However, Government pushed hard to take on the role of managing upcoming donor-funded HIV programmes — the Global Fund Round 7, Phase 2 HIV grant and including pooled donor funding for HIV under NHSP 2, where the Government had stated its commitment to implement prevention services through NGOs by 31 March 2011, meaning an accelerated capacity building programme from DFID and UNDP, with technical assistance from UNAIDS. The capacity assessment concluded that in spite of several years of support from UNDP and DFID, NCASC still lacked capacity for NGO supportive supervision, faced high staff turnover (meaning investment in staff skills was routinely lost quickly) and was weak at fulfilling its responsibilities to maintain standards and provide normative guidance for VCT, community home-based care, ART and linking VCT with STI management. In addition, NCASC had no experience in managing contracts for service delivery.

A capacity assessment of HSCB, responsible for ensuring a multi-sectoral response to the HIV epidemic, identified several critical issues including inadequate multi-sector representation and coordination, potential conflicts with the roles and responsibilities of NCASC and the Country Coordinating Mechanism of the Global Fund (CCM), and an inadequate organisational structure and staffing, the latter requiring amendment of the formation order and bylaws. In addition, HSCB received neither political nor financial support from Government, making it rather a lame duck. DFID subsequently supported many of the set-up costs of HSCB including equipping its office and providing a vehicle, part of HSCB’s running costs including office rent and the salaries of several staff, and the development and testing of a national M&E system for the multi-sector response to promote a more coordinated response and more coordinated reporting. (This support also built the monitoring capacity of the six district AIDS coordination committees.) But without significant spending power and no support from the Prime Minister’s Office, HSCB was judged unable to be effective and DFID funding ended on 28 February 2011.
The independent evaluation concluded that NCASC’s managerial capacity had been significantly strengthened, to an extent that enabled it to pass the assessment to become Principal Recipient for the second phase of the Global Fund Round 7 HIV grant to Nepal. This was a major achievement of the DFID Programme and can be directly attributed to Programme support. However, the programme’s support to HSCB was largely ineffective. Further, the evaluation judged that the ten core programme staff in NCASC at the time of the independent evaluation (Feb 2012) will be insufficient for NCASC to both carry out its responsibilities as Principal Recipient for the Global Fund and for coordinating the pooled donor funding under NHSP 2. The evaluators were told that NCASC did not even have enough funds to pay its salaries at the time of the evaluation. In spite of institutional strengthening NCASC only has limited capacity for the supportive supervision of civil society organisations to provide HIV-related services — a major role of NCASC under NHSP 2.

Impact Weighting (%): 30%
Revised since last Annual Review? Y

Risk: Medium
Revised since last Annual Review? N

Output 6: End of project Evaluation
Output 6: final score and performance description: A / The evaluation was completed.
Final results: / The end of project evaluation was formulated. / Impact Weighting (%): 5% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? Y

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? No, only the output weighting has been revised and redistributed across 6 outputs. / 1.2 Final Output score and description: A / This is an aggregate score generated from (50% A+) x (5% B) x (5% A) x (5% B) x (30% B) x (5% A). The programme exceeded expectations in the most fundamental objective of delivering HIV prevention services to most at-risk populations, met expectations in blood safety, but fell short in lesser, but still important, objectives of strengthening M&E and strengthening institutional capacity in the public sector in HIV.
Direct feedback from beneficiaries / Although not an explicit objective of the programme, the evaluation commended the rights-based approach taken by the programme. It concluded that the programme was instrumental in improving respect for the rights of the three at-risk groups and people living with HIV, and for increasing their access to their rights. It strengthened the civil society organisations that represent the at-risk groups to provide HIV related services and to advocate for their constituents. The partnerships with the national networks and NGOs of people living with HIV, drug users, female sex workers and men who have sex with men (NAP+N, Recovering Nepal, JMMS and the Blue Diamond Society) linked the programme with major human rights and social protection advocates and activists. Part of the success was attributed to the fact that the organisations prioritised to receive funding were established and run by members of the most at-risk populations – beneficiaries or former beneficiaries of the interventions provided. / The programme also supported civil society organisations to run activities that reduced stigma and discrimination against these groups. A 2011 study found low levels of discrimination and stigma against people living with HIV with 90% of respondents saying they were rarely or never excluded from social gatherings whilst 84% were rarely or never discriminated against by family members and very few respondents reporting poor behaviour by health personnel towards them. These results show a marked change from a decade before and will be in large part due to interventions by the DFID and other HIV programmes. Reduced stigma makes men who have sex with men and injecting drug users more likely to seek information on HIV and to access prevention services. The programme also extended the access of the often socially marginalised men who have sex with men, drug users and people living with HIV and AIDS to social protection measures including by supporting the setting up and operation of community care centres for PLHA and rehabilitation centres for injecting drug users and by promoting livelihood opportunities for PLHA and ex-injecting drug users. Programme support to the main organisations advocating for men who have sex with men and injecting drug users led to the legalisation of homosexuality in Nepal in 2007, the challenging of regressive aspects of the proposed new criminal and civil codes and the incorporation of harm reduction principles in the draft National Drugs Control Strategy.
1.4 Overall Outcome score and description: B / The following logframe indicators track progress against three of the programme’s four purposes of: / increasing awareness and knowledge of safer injecting and safer sex among IDU, MSM, MSW, PLHA and migrants; / increasing access to prevention, care and support services; and / ensuring quality services of HIV care support throughout the continuum from health facilities to home and community. / The programme is graded B – “outcomes moderately did not meet expectation” since although for three indicators (1.2 - % of IDUs who both avoid sharing non-sterile injecting equipment and use condoms in the last month; 1.3 - % of migrant workers that report the use of use of condoms at last sex with FSWs; and 2.1 - number of service delivery points providing counselling and testing for HIV) the achievement is well below target, it is also the case that at goal level, achievements in Nepal since the start of the programme have been substantial. Notably, there has been a reduction in HIV prevalence amongst three key affected populations – men having sex with men (MSM); injecting drug users (IDU); and labour migrants. The independent evaluation of the DFID / UNDP programme argued that since services delivered to most at-risk populations well exceeded the programme’s own targets, the programme is highly likely to have contributed significantly to the containment of HIV prevalence in Nepal over the period 2006-11. / Indicator Target Achieved / % of MSM reporting the use of condoms for last anal sex 80% Most recent data from 2009 shows 71% / % of IDU who both avoid sharing non-sterile injecting equipment and use condoms — in the last month 98% No data available for this indicator. In 2009 97% of IDU reported using sterile equipment and 35% reported using a condom during their last use of drugs / sex. / % of migrants workers that report the use of use of condoms at last sex with FSW 80% No national data available. The table below indicates the results identified by the independent evaluation on similar indicators since the start of the programme, indicating that the rates are far below the programme target. / No. of service delivery points providing counselling and testing for HIV 65% 196 VCT sites in country (source 2009/10 DoHS Annual Report) but not clear what the denominator is. If all health facilities, then this indicator is very far from target. / No. of people with advanced HIV Infection receiving ARV 5,945 NCASC estimates 5,876 people on ARV in Nepal in 2011 – likely to be a slight over-estimate / No. of children with advanced HIV Infection receiving ARV (<15 yrs) 234 353 children with advanced HIV receiving ARV. / Area Year Ever had sex with sex worker in India Used condom with last sex with female sex worker in India Ever had sex with female sex worker in Nepal Used condom at last sex with female sex worker in Nepal HIV+ / IBBS / Mid & Far West 2008 21.7% 16.7% 6.4% 8.7% 0.8% / Mid & Far West 2010 32.8% 68.4% 11.6% 6.9% 4.5% / Western 2008 9.7% 11.4% 2.5% 44.4% 1.4% / Based on Table 42 of IBBS 2010 for male labour migrants (SSO 2010 Success Search Options) / 1.5 Impact and Sustainability / Although the independent evaluation of the programme commended the programme for building confidence and management capacity amongst NGOs delivering HIV prevention services, which will have implications for sustainability (for example, some are now implementing revenue-generating projects such as drinking water processing plants in order to maintain funding), it also pointed out that the programme largely functioned as an autonomous project, with little integration into the public health sector. Although this was the only feasible option, such approaches seldom see interventions sustained once project funding ends. The pooled funding of HIV interventions under NHSP 2, with funding channelled through the government’s budget and programme management by NCASC in theory provides a more sustainable modality, and management capacity strengthening of NCASC will contribute towards this.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / DFID and UNDP ensured uninterrupted service delivery until Government services were up and running in early 2012. Although Government took longer to ensure that contracts for service delivery were in place, requiring an extension of DFID funding, DFID had made contingency plans that ensured this was within budget. DFID Nepal agreed several cost extensions to ensure that services could continue to be provided while Government of Nepal was busy with the contracting process until January 2012. / 2.2 Key cost drivers / contracts for prevention services procured competitively by UNDP / key cost drivers included: / UNDP management time & staff costs / NGO staff time and infrastructure costs / Commodities: notably condoms, HIV test kits / Transport and logistics, esp for blood safety services / External advisory support for capacity strengthening work / 2.3 Was the project completed within the expected timescale: No / There was a need for a cost extension to the programme to ensure continued service delivery. Capacity development of NCASC was not achieved by the end of the initial phase of support, necessitating an extension.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / No change. / 3.2 Set out what plans are in place for an evaluation. / Independent evaluation completed and forms the basis for this completion report. Evaluation was one of the output milestones in the programme logframe.

4. Risk
4.1 Risk Rating (overall project risk): Low. / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / Low. There is clear evidence of significant growth in service delivery from contracted NGOs and the UNDP M&E system was judged reliable enough by the evaluators to give DFID the level of assurance needed to know that these results are not exaggerated or falsified. / 4.3 Climate and Environment Impact / No assessment made. Climate and environment risk was judged to be medium at initial programme design – the main risk being disposal of waste from HIV test kits and needle replacement programmes.

5. Value for Money
5.1 Performance on VfM measures / The programme is judged to have achieved mixed performance on VFM indicators. / Some activities appear extremely good value for money – such as the average cost of $1.90 per labour migrant (or family member) reached with HIV prevention messages (compared to $18 in Cambodia[3]) and the $3.10 per unit of blood screened for HIV safety (compared to international estimates of $25-$40 per unit[4]) – and are highly likely to be cost-effective and therefore VfM. / 28% of the programme budget was spent on administration by UNDP (including monitoring and evaluation), and although M&E and fiduciary risk management costs are likely to be high in a post-conflict country with high corruption risk such as Nepal, the independent evaluation of the programme noted that this figure seemed high but also concluded that UNDP managed the Programme well. Knowing whether this combination of high costs and high effectiveness resulted in value for money would require benchmarking against similar programmes which the evaluators were unable to find. / Some activities funded appear extremely expensive, for example $1,894 per injecting drug user accessing voluntary counselling and testing for HIV – but no international data is available to determine whether this is cost-effective. Internationally, provision of rehabilitation centres for injecting drug users is known to not be cost-effective as a means of achieving HIV prevention due to the high costs involved and the high rate of post-rehab relapse. / 5.2 Commercial Improvement and Value for Money / Although UNDP ran a competitive procurement process for selection of NGO contracting partners, suggesting that good commercial practice was followed in the use of the 72% of the programme funds allocated to service delivery, there is little information available about the commercial practices of the NGO implementing partners. The initial agreement between UNDP and DFID was not based on a rigorous competitive selection process but on a judgement at the time (just after the end of the Nepal civil war) that UNDP represented a reliable and low-risk implementing partner for the HIV prevention programme. The 28% of expenditure absorbed by the programme management unit included a 12% overhead administration charge by UNDP HQ which has since been renegotiated to 7%. / 5.3 Role of project partners / UNDP managed the contracts for service delivery with NGOs and networks. The NGOs and networks implemented outreach, prevention behaviour change communication, distribution of commodities and provision of treatment alongside national advocacy. Various external organisations such as SWASTI provided technical support. Government agencies NCASC and HSCB were beneficiaries of capacity development support. / 5.4 Did the project represent Value for Money : Y / The independent evaluation judged DFID’s funding as instrumental in containing a rise in Nepal’s HIV prevalence over the life of the programme.
[3] Saphonn V, Chhorvann C, Sopheab H, Luyna U & Seilava R (2010): The Long Run Costs And Financing Of Hiv/Aids In Cambodia. Comparisons are not straightforward, since we do not have a measure of quality of the different approaches.
[4] Jacobs B, Mercer A (1999): Feasibility of hospital-based blood banking: a Tanzanian case study. Health Policy & Planning 14(4): 354 – 362. Comparisons are not straightforward, since we do not have data on the specificity of the screening processes being compared.

6. Conditionality
6.1 Update on specific conditions / None.

7. Conclusions
A successful programme that empowered some stigmatised groups at high risk of HIV and gave them advice and support in-kind to seek testing, become aware of their HIV status, practice healthy behaviours that reduced their risk of contracting and passing on HIV, and access treatment. Services delivered to these groups well exceeded the programme’s own targets. This is highly likely, in the assessment of the independent evaluation, to have contributed significantly to the containment of HIV prevalence in Nepal over the period 2006-11. Mixed evidence in three areas: first, the extent to which the programme was implemented with the best possible attention to value for money (particular concerns about the high costs of the UNDP programme management unit); second, the attribution of Nepal’s success in reducing prevalence, new HIV infections and the mortality rate from AIDS complications to the work of the programme; and third, the success of capacity development of Government institutions to provide the same services to ensure long-run sustainability of the programme.

8. Review Process
This review was written by the DFID Nepal Human Development Team Leader, with inputs from the team, based on the independent evaluation of the programme, which consulted implementing partners, beneficiaries and other stakeholders and put their views alongside objectively verifiable data about the programme’s achievements, as well as DFID Nepal’s working knowledge of the programme.

# ANNEX A - REVISED LOGICAL FRAMEWORK FOR 2010
PROJECT TITLE	SUPPORT TO THE NATIONAL HIV/AIDS RESPONSE
GOAL	Indicator	Baseline + year	Milestone 1 / (achievement)		Milestone 2 / (achievement)		Milestone 3 (target for 2010)	Baseline and targets derived from National HIV/AIDS strategy 2006-2011[5]
Optimise prevention and reduce the social impact of HIV and AIDS / (Goal from National M&E Framework)	% of men having sex with men infected with HIV / (relates to indicator 1.2 of the national M&E framework)	3.9% (2004)*	**3.3% (2007)		*3.8% (2009)		2% (2010/11)
		Sources: / *Integrated Bio Behavioural Survey amongst Men having Sex with Men in Kathmandu, / ** Average of IBBS (Integrate Bio Behavioural Surveillance Survey) sample sites
	Indicator	Baseline + year	Milestone 1 / (achievement)		Milestone 2 / (achievement)		Milestone 3 (target for 2010)
	% of injecting drug users infected with HIV / (relates to indicator 1.2 of the national M&E framework)	52% (2005)	34.7%(2007/08)		18% (2009)		24.9% (2010/11)[6]
		Sources: / According to the latest 2009 IBBS data the target for 2011 was reached in 2009 with the IDU HIV prevalence of at 21%, in Kathmandu 3% in Pokhara, and 8% in the two Terai areas. / Baseline is taken from Integrated Bio Behavioural Survey amongst Injecting Drug Users in Kathmandu, 2005 and so does not include other sites. The 2009/10 target is taken from the National HIV/AIDS Strategy (2006-2011) and is a weighed average of the four main intervention sites.
	Indicator	Baseline + year	Milestone 1 / (achievement)	Milestone 2 / (achievement)		Milestone 3 (target for 2010)
	% of labour migrants infected with HIV / (relates to indicator 1.2 of the national M&E framework)	8% (2001)	2.8% (2006)	2% (2008)		1% (2010)
		Sources: / Integrated Bio Behavioural Survey among labour migrants in Far West, 2001 and 2006 and the National HIV/AIDS Strategy (2006-2011). / Note: Targets are set for each project region (Far and Mid West) above baseline and targets are for Far West due to lack of good baseline data for the West
[5] National HIV/AIDS Strategy (2006-2011), Ministry of Health and Population, National Center for AIDS and STD Control, annex 1, p.55-62 - When available July 2010 -July 2011 targets are taken - however for most targets July 2009-July 2010 have had to be taken
[6] IDU 2009/2010 is taken from the National HIV/AIDS Strategy (2006-2011) and is a weighed average of the regional targets from the four IDU assessment sites. It is therefore also higher than the target indicated in earlier logframe but is in line with the national target.

PURPOSE	Indicator	Baseline + year	Milestone 1 / (achievement)		Milestone 2 / (achievement)			Milestone 3 (target for 2010)		Notes
Optimise prevention, thereby change behaviour to reduce the transmission of HIV among most at-risk populations. Provide care and support and reduce social impact among vulnerable groups (10-24 years, labour migrant, MSW, MSM, IDUs, and PLWH) / (Slightly amended purpose statement from previous log frame to align to national purpose statement of the National M&E framework)	1. Increase awareness and knowledge on safer injecting and safer sex among IDUs, MSM, MSW, PLWHA and migrants. Increase access to prevention, care and support services									The first two of the three purpose level indicators are drawn from the National Strategic plan 2006-2011. / These are national level indicators. It is not possible to collect results data on project specific targets. At the project end we will analyze the level of attribution of DFID to the national response. Surveys specific to project sites have not been carried out. / The programme is supporting 55% (36 out of 65) of the service delivery points that provide counselling and testing for HIV in Nepal. / DFID is one of the donors supporting residential care for PLHA/AIDS through care homes. Procurement and provision of ARV and other drugs is being supported by GFATM.
	1.1 % of MSM reporting the use of condoms for last anal sex	41% (2004)	71.6% (2007)		75.3% (2009)			80% (2010)
		Source: Strategic Information Framework for HIV in Nepal: Baseline, latest data and national targets (2007-2011)
	1.2. % of IDUs who both avoid sharing non-sterile injecting equipment and use condoms — in the last month	78.3% (2005)	96.9% (2007)		50.8% (2009)			98% (2010)
		Source: Strategic Information Framework for HIV in Nepal: Baseline, latest data and national targets (2007-2011)
	1.3. % of migrants workers that report the use of use of condoms at last sex with FSWs	50% (2006)	50% (2008)	50% (2009)			80% (2011)
		Source: Integrated Bio Behavioural Survey among migrants, 2006 and 2008. / Note: targets are set for each region (Far and Mid West) above baseline and targets are for Far west
	Indicator	Baseline + year	Milestone 1 / (achievement)			Milestone 2 / (achievement)			Milestone 3 (target for 2010)
	2. Provision of quality services of HIV care support throughout the continuum from health facilities to home and community
	2.1 No. of service delivery points providing counselling and testing for HIV	65 / (2006)				36 (2009)			65 (2010/11) / (target of National Strategic plan 2006-2011)
	2.2 No. of people with advanced HIV Infection receiving ARV	472 / (2006)				3,915 {target of National Action plan 2008-2011)			5,945 / (target of National Action plan 2008-2011)
	2.3 No. of children with advanced HIV Infection receiving ARV (<15 yrs)	17 / (2006)				175 (target of National Action plan 2008-2011)			234 / (target of National Action plan 2008-2011)

PURPOSE (cont.)	Indicator	Baseline + year	Milestone 1 / (achievement)	Milestone 2 / (achievement)	Milestone 3 (target for 2010)	Notes
	3. Strengthen National AIDS Programme
	3.1 Strengthening of capacities in organization, human resources, communication and coordination at NCASC and district level stakeholders including DACC	No baseline line			Significantly more effective NCASC (2011).
INPUTS (£)	DFID	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£3,3800,000	0%	0%	0	100%
INPUTS (HR)	DFID (FTEs)

	OUTPUT 1: Implementation of Comprehensive packages for most-at-risk population groups
Output 1A: Implementation of comprehensive package for IDUs	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4		Assumptions/ Remarks
						2010	Cumulative 2006-2010
	Number of IDUs receiving detoxification, treatment and counselling services through rehabilitation centres	0 (2005)	1,944 (2007)	5,466 (2008)	8,866 ( 2009)	1,100	9,966 (2010)	DFID is the main donor supporting the rehabilitation and treatment of IDUs and so contributes to over 100% of the national targets.
			Source: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4
						2010	Cumulative 2006-2010
	Number of condoms distributed to IDUs for free	0 (2005)	N/A	285,736 (2008)	218,649 (2009)	60,000	278,649 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4
						2010	Cumulative 2006-2010
	Number of IDUs received STI diagnosis and treatment	0 (2005)	N/A	1,754 (2008)	2,347 ( 2009)	776	3,123 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4		The target is for DFID to contribute to 59% of the national target of 40% coverage by 2010
						2010	Cumulative 2006-2010
	Number of IDU completed HIV counselling and testing process	0 (2005)	N/A	2,332 (2008)	2,826 (2009)	700	3,526 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4
						2010	Cumulative 2006-2010
	Number of needle and syringes distributed through harm reduction programme	0 (2005)	N/A	166,887 (2008)	370,935 (2009)	300,000	670,935(2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008	Milestone 3 / Cumulative 2006-2009	Milestone 4		DFID contributes to 66% of the national target of 17,063
						2010	Cumulative 2006-2010
	Number of IDU reached by HIV/AIDS prevention programme	0 (2005)	1674 (2007)	10,038 (2008)	16,662 (2009)	8,139	24,801 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
INPUTS (£)	DFID	Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	£642,998	0%	0%	0		100%
INPUTS (HR)

	OUTPUT 1 (cont.): Implementation of comprehensive packages for most-at-risk population groups
Output 1B: Implementation of comprehensive package for men who have sex with men (MSM) and male sex workers (MSW)	Indicator	Baseline + year	Milestone 1 / Cumulative 2006-2007	Milestone 2 / Cumulative 2006-2008		Milestone 3 / Cumulative 2006-2009		Milestone 4			Assumptions/Remarks
						2010		Cumulative 2006-2010
	Number of MSM/MSW completed voluntary counselling and testing process (VCT)	0 (2005)	39,029 (2007)	93,562 (2008)		15,578 (2009)		5,100		20,678 (2010)	DFID contributes to more than 100% of the national target of 60% coverage by 2010
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU
	Indicator	Baseline + year	Milestone 1	Milestone 2		Milestone 3		Milestone 4
						2010		Cumulative 2006-2010
	Number of condoms distributed	0 (2005)	390,552 (2007)	2,006,619 (2008)		3,267,818 (2009)		650,000		3,917,818 (2010)
			Sources: Annual Reports, 2007, 2008 and 2009
	Indicator	Baseline + year	Milestone 1	Milestone 2		Milestone 3		Milestone 4
						2010		Cumulative 2006-2010
	Number of IEC materials distributed	0 (2005)	0	509,265 (2008)		687,934 (2009)		52,175		740,109 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008

IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2		Milestone 3		Milestone 4			DFID contributes to 97% of the national target of 107,924 reached by 2011
						2010		Cumulative 2006-2010
	Number of MSM reached with targeted HIV prevention	0 (2005)	39,029 (2007)	93,562 (2008)		120,239 (2009)		25,000		145,239 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
INPUTS (£)	DFID	Govt (£)			Other (£)		Total (£)				DFID SHARE (%)
	£497,608	0%			0%		0				100%
INPUTS (HR)

	OUTPUT 1 (cont.): Implementation of Comprehensive packages for most-at-risk population groups
Output 1C: Implementation of comprehensive package for labour migrants and their family	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4		Assumptions/Remarks
						2010	Cumulative 2006-2010
	Number of migrants and families diagnosed and treated for STI	0 (2005)	2,670 (2007)	45,428 (2008)	78,349 (2009)	30,000	108,349 (2010)	DFID contributes to 77% of the national target
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4		DFID contributes to 64% of the national target
						2010	Cumulative 2006-2010
	Number of migrants and families completing the HIV testing and counselling process	0 (2005)	3,058 (2007)	44,319 (2008)	77,677 (2009)	17,640	95,317 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4
						2010	Cumulative 2006-2010
	Number of condoms distributed	0 (2005)	112,769 (2007)	1,895,059 (2008)	3,221,600 (2009)	10,000,000	13,221,600 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4		National targets only for migrants while DFID contribution targets both migrants and families
						2010	Cumulative 2006-2010
For all of output 1 = 50%	Number of migrants and their families reached with targeted HIV prevention	0 (2005)	87,426 (2007)	1,678,943 (2008)	2,709,242 (2009)	2,090,768	4,800,010 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
INPUTS (£)	DFID	Govt (£)		Other (£)	Total (£)			DFID SHARE (%)
	£859,372	0%		0%	0			100%
INPUTS (HR)

	OUTPUT 1 (cont.): Implementation of comprehensive packages for most-at-risk population groups
Output 1D: Implementation of Comprehensive packages for PLWH	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4		Assumptions/remarks
						2010	Cumulative 2006-2010
	Number of PLWH receiving palliative care (medical, psycho-social or economic support)	0 (2005)	2,502 (2007)	5,840 (2008)	8,043 (2009)	3,129	11,172 (2010)
			Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
INPUTS (£)	DFID	Govt (£)	Other (£)	Total (£)				DFID SHARE (%)
	£555,852	0%	0%	0				100%
INPUTS (HR)	DFID (FTEs)
Weighting

		OUTPUT 2: Interventions in three prisons:
Output 2:		Indicator	Baseline + year		Milestone 1		Milestone 2	Milestone 3	Milestone 4		Assumptions/remarks
							2010	Cumulative 2006-2010
		Number of prison inmates reached targeted with preventive HIV information	n/a(2005)		n/a (2007)		n/a (2008)	631 ( 2009)	1,500	2,131 (2010)	DFID contributes to 44% of the national target
					Source: Internal Record
INPUTS (£)		DFID	Govt (£)		Other (£)		Total (£)				DFID SHARE (%)
		£67,284	0%		0%		0				100%
Weighting = 5%
INPUTS (HR)		DFID (FTEs)

		OUTPUT 3: Blood Safety:
Output 3:		Indicator		Baseline + year	Milestone 1		Milestone 2	Milestone 3	Milestone 4		Assumptions/remarks
							2010	Cumulative 2006-2010
		Percent of blood units that have been adequately screened for HIV according to national/WHO guideline		n/a(2005)	n/a (2007)		100% (2008)	100% (2009)	100%	100% (2010)
					Sources: Annual Programme Progress Reports submitted by HIV/AIDS, PMU in 2007, 2008
INPUTS (£)		DFID		Govt (£)	Other (£)		Total (£)				DFID SHARE (%)
		£68,711		0%	0%		0				100%
Weighting = 5%
INPUTS (HR)		DFID (FTEs)

		OUTPUT 4: Establishing a National Strategic Information System:
Output 4:		Indicator		Baseline + year	Milestone 1		Milestone 2	Milestone 3	Milestone 4	Assumptions/remarks
		National monitoring and evaluation system established and strengthened at both NCASC and HSCB		n/a(2005)	n/a (2007)		n/a (2008)	2 (2009)	2 (2010)	Established both at NCASC and HSCB
					Source: n/a
		Indicator		Baseline + year	Milestone 1		Milestone 2	Milestone 3	Milestone 4
		Number of districts pilot testing the National M&E System.		n/a	n/a		n/a	6 (2009)	10(2010)
					Source: n/a
		Indicator		Baseline + year	Milestone 1		Milestone 2	Milestone 3	Milestone 4
		Number of districts where the DACC has been activated and strengthened		n/a	n/a		n/a	35 (2009)	35 (2010)
					Source: n/a
INPUTS (£)		DFID		Govt (£)	Other (£)		Total (£)			DFID SHARE (%)
		116,832		0	0		0			100%
Weighting = 5%
INPUTS (HR)		DFID (FTEs)

	OUTPUT 5: Strengthen Institutional Framework for effective HIV/AIDS response:
Output 5:	Indicator	Baseline + year	Milestone 1	Milestone 2	Milestone 3	Milestone 4	Assumptions/remarks
	Capacity development plan for NCASC/MOHP developed and implemented	n/a(2005)	n/a (2007)	n/a (2008)	1 ( 2009)	1 (2010)	Plan developed, submitted for endorsement at MOHP. Implementation planned for 2010
	Institutional Review of NCASC conducted and Human Resource Plan developed and implemented by NCASC					1 (2010)	NCASC should be capacitated so as to support the entities manage a transition to the new arrangements
	Effective HIV/AIDS monitoring and data base system developed and implemented at NCASC					1 (2010)	Number of service delivery points submitting reports regularly / Number of reports generated and disseminated
	Programme management & Financial Management System strengthened at NCASC					1 (2010)	# of human resource trained to deliver programmatic and financial requirements

Weighting = 30%

INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	£84,137	0	0	0		100%
INPUTS (HR)	DFID (FTEs)

		OUTPUT 6:End of project Evaluation
Output 5:		Indicator		Baseline + year		Milestone 1	Milestone 2		Milestone 3		Milestone 4		Assumptions/remarks
		End of project evaluation formulated		n/a(2005)		n/a (2007)	n/a (2008)		n/a ( 2009)		1 (2011)
						Source: n/a
Weighting = 5%
INPUTS (£)		DFID (£)		Govt (£)				Other (£)		Total (£)			DFID SHARE (%)
		£18,750		0				0		0			100%
INPUTS (HR)		DFID (FTEs)