Business Case and Intervention Summary

Intervention Summary

Addressing basic humanitarian needs in northern Yemen through a Consortium of International Non-Governmental Organisations (INGOs) in 2012/13

What support will the UK provide?
DFID will address the basic humanitarian needs of 270,000 people in Northern Yemen in the health, nutrition, WASH (water, sanitation and hygiene), protection, education and early recovery / livelihoods sectors. This will be achieved through funding to a Consortium of International Non-Governmental Organisations (INGOs). / How much funding does the UK expect to provide? £5,292,532. / Period of funding? June 2012 – March 2013

Why is UK support required?
What need are we trying to address? / Yemen is facing a complex humanitarian emergency. Protracted internal conflict, political unrest and insecurity have led to the displacement of over 460,000 civilians and the disruption of essential public services. This includes an estimated 300,000 persons displaced as a result of repeated rounds of conflict between Houthi tribal groups and government forces in the North of Yemen. Whilst the intensity of fighting has reduced recently, since the Houthis secured control of parts of the territory, 2012 has witnessed sporadic fighting and further, small-scale displacement. The past year has also seen increases in the number of refugees, asylum seekers and migrants reaching Yemen from the Horn of Africa - over 100,000 new arrivals were registered in 2011. / Poor living conditions have been exacerbated by rises in the price of fuel and food commodities and economic fragility, placing a chronically vulnerable civilian population under increasing strain. Recently released data indicates that malnutrition rates in many parts of Yemen are amongst the highest in the world, whilst the risk of communicable disease outbreaks has soared. Although the on-going political transition process offers an opportunity to restore stability and lay the foundations for longer term recovery, humanitarian agencies assess that acute large scale assistance needs will persist for three to five years. In this context, principled, needs-based humanitarian assistance can facilitate the attainment of longer-term goals and wider UK policy objectives. Improving the living conditions of the most vulnerable and tackling the grievances that fuel conflict and radicalisation can reduce the risk of state failure. / What will we do to tackle this problem? / This business case proposes provision of emergency health services, water and sanitation, child protection, education, nutrition and livelihoods in six northern governorates (Al-Jawf, Amran, Hajjah, Sa’ada, Sana’a and Hodeidah). Interventions will focus on emergency needs as well as building community capacity and resilience to cope with further shocks. / Who will implement the support we provide? / The Consortium consists of five international NGOs – Care International, Oxfam, Save the Children, Islamic Relief and ADRA (Adventist Development and Relief Agency), with Care International acting as the lead organisation. Locations include conflict affected areas such as Amran and Al Jawf, as well as the non-conflict affected governorate of Hodeidah, where recent data suggests that levels of acute malnutrition are more than double emergency thresholds. / This programme is the third phase of an existing intervention by this Consortium which DFID has funded for the last two years. In response to evolving humanitarian needs, the Consortium has added a nutritional component, focussed on Hodeidah governorate, and has also expanded the scope of its livelihoods work, in light of improved security and stability in northern governorates. An independent evaluation of the second phase concluded that the Consortium had shown a ‘strong performance in difficult circumstances’. Despite a shortened implementation period of nine months and the challenges presented by an extremely difficult operating environment, the Consortium delivered over and above its original targets in many areas. In 2011/12, results included providing primary health care primary or maternal health care to over 70,000 people (63% more than planned) and providing hygiene kits to over 13,000 people (24% more than planned). The Phase II evaluation also recommended a number of concrete actions in support of closer integration of interventions and more effective management structures, which the Consortium has incorporated into Phase III, with DFID’s encouragement. / The Consortium’s structure allows for emphasis on sectoral and geographical expertise, whilst addressing key gaps in humanitarian response. This approach avoids duplication of effort, is needs based and provides DFID with a streamlined and efficient mechanism for funding multi-sectoral interventions.

What are the expected results?
What will change as a result of our support? / The intended outcome of the intervention is to assist and protect the lives of people affected by conflict, disaster and economic decline. / What are the planned outputs of the project attributable to UK support? / The project will reach an estimated 270,000 different beneficiaries in the following sectors: / Health care to 75,600 beneficiaries, including: / improved access to primary and maternal health care, including the treatment of chronic and conflict-related cases, vaccination and medical referrals for 43,300 people; / 13 health centres provided with essential equipment and supplies; and / delivery of health education messages to 7,250 people. / Nutrition support to 35,600 beneficiaries, including: / nutrition education for 32,600 people; and / treatment for 3,000 children with moderate and severe acute malnutrition. / Water, Sanitation and Hygiene (WASH) services to more than 68,800 beneficiaries, including through: / rehabilitation of 19 water facilities; and / hygiene materials for 8,300 households. / Education support to 60,600 beneficiaries, including through: / rehabilitation of 30 schools to provide a safe learning environment for children; / training for more than 600 teachers, school managers and school councils on education in emergencies; and / mine awareness training for 60,000 children. / Protection services for more than 4,400 beneficiaries, including: / 4,000 vulnerable women receiving protection services; and 475 government aides and community leaders receiving training on the protection needs of women and girls. / Emergency livelihoods support for 24,400 individuals, including: / 3,455 households provided with vocational / business management training and non-financial inputs. / How will we determine whether the expected results have been achieved? / Due to the security environment in Yemen and limited DFID staff presence and travel restrictions, this project will be monitored primarily from London. It will be monitored by DFID staff throughout the year with quarterly reviews of financial and narrative reports as well as a Project Completion Report when the project has ended. The Consortium has budgeted for an independent in-country end of project evaluation. This will provide a useful additional appraisal of the Consortium’s delivery over the project period. DFID will continue to work with partners to provide quality baseline data, and develop in-house monitoring and evaluation capacity.

Business Case for addressing basic humanitarian needs in northern Yemen through a Consortium of International Non-Governmental Organisations (INGOs) in 2012/13

Strategic Case

A. Context and need for a DFID intervention / Background / Yemen is facing a complex humanitarian emergency. Repeated cycles of internal conflict, protracted political unrest and insecurity have caused the displacement of over 460,000 civilians[1] and led to the disruption of essential public services. Recent months have also seen increases in the number of refugees, asylum seekers and migrants reaching Yemen from the Horn of Africa; over 100,000 new arrivals were registered in 2011[2]. The situation has been aggravated by rises in the price of fuel and food and a weak economy. Yemen is also disaster prone, with a ‘very high vulnerability’ to floods and landslides, according to the World Bank and UN International Strategy for Disaster Reduction. / Until recently, humanitarian relief efforts in Yemen were restricted to areas directly affected by conflict, alongside assistance and protection activities for refugees and asylum seekers. However, conditions have deteriorated markedly over the past 18 months; there is now increasing evidence that the emergency has spread to other parts of the country and is impacting on the population as a whole[3]. / Priority humanitarian needs / The implications of the crisis are far-reaching. Available data suggests that rates of malnutrition in some parts of the country are amongst the highest in the world and that almost 45% of the population – 10 million people – do not have access to sufficient, safe and nutritious food (are food insecure); levels of food insecurity have almost doubled since 2009[4]. The risk of communicable diseases has soared and the population is increasingly reliant on relief agencies for delivery of health, education and water/sanitation services. Conflict- and displacement- affected communities, including children and females, are also vulnerable to physical violence and other forms of abuse. / The needs, as identified by humanitarian organisations operating in Yemen, a country with a population of around 24 million, include: / 10 million food insecure, including five million who are severely food insecure and in urgent need of assistance[5]; / 7.9 million children under 10 at risk of measles and other communicable diseases[6]; / An estimated 800,000 children under five suffering from acute malnutrition[7]; / Three million people facing public health risks, including disease outbreaks and malnutrition, due to poor water, sanitation and sanitation[8]; / One million children with limited access to education as a result of conflict, including Internally Displaced Persons (IDPs), host communities and others in areas affected by fighting;[9] / Over 460,000 IDPs in northern and southern governorates, as well as 200,000 refugees, asylum seekers and economic migrants (primarily from the Horn of Africa), with a range of basic assistance and protection needs[10]; / 340,000 farmers who have lost their livelihoods[11]. / Many of the most urgent humanitarian needs in Yemen are interconnected. For example, infections can contribute to and exacerbate malnutrition, whilst people with poor nutritional status are more susceptible to infectious disease. Humanitarian needs in Yemen are also rooted in underlying chronic vulnerabilities and long standing human development challenges. / In northern Yemen, the intensity of the conflict between the Houthis and government forces has reduced in recent months, since the former secured control of Sa’ada in early 2011. Localized unrest continues, including between Houthis, local tribes and Salafist groups, and the risk of renewed escalation is high. Across northern governorates, large-scale humanitarian needs remain: the official number of IDPs from six rounds of fighting between the government and the Houthis – dating back to 2004 – stands at 300,000, although the actual number may be lower[12]. Inter-tribal fighting has led to around 40,000 new IDPs in Hajjah since the start of 2012. The vast majority of those displaced have not yet returned to their homes and remain in urban areas or camps. Efforts continue to integrate IDPs locally or to resettle them permanently in other governorates. / Humanitarian needs in these governorates are considerable. Recent data from Hajjah and Hodeidah suggests that around one in three children under five are suffering from acute malnutrition, more than double emergency thresholds. / Humanitarian response / In response to increased humanitarian needs, many humanitarian organisations in Yemen are looking to expand their operations in 2012. The 2012 UN humanitarian appeal (Consolidated Appeal or ‘CAP’) is seeking US$455m, an increase of more than 50% compared with 2011, making this the largest such appeal outside Sub-Saharan Africa and the seventh largest globally[13]. It is anticipated that CAP funding requirements will increase further when the appeal is reviewed at mid-year point. DFID has committed to spending a total of £28 million on humanitarian support in Yemen in 2012/13. / Table 1, below, provides more details of 2012 CAP requirements by sector/cluster and changes compared with 2011. / Table 1: CAP financial requirements by sector, 2011 and 2012 / Sector / cluster Total requirements in 2012 (US$ m) Total requirements in 2011 (US$ m) 2012 requirements by sector as share of total requirements Absolute increase in 2012 requirements compared with 2011 % increase in 2012 requirements, compared with 2011 / Coordination and support 5.4 5.1 1.2% 0.3 5.6% / Early recovery 26.5 11.1 5.8% 15.4 128.0% / Education 12.3 4.9 2.7% 7.4 151.0% / Food and agriculture 162.7 114 35.8% 48.7 42.7% / Health 56.2 21.5 12.4% 34.7 161.4% / Multi-sector (refugee response) 42.8 47.2 9.4% -4.4 -9.3% / Nutrition 70.5 37.1 15.5% 33.4 90% / Protection 21.5 15.5 4.7% 6.0 38.7% / Shelter / NFI / CCCM 27 22.6 6.0% 4.4 19.5% / Water, sanitation and hygiene 30.1 13.3 6.5% 16.8 126.3% / Total 455 292.3 100.0% 162.7 56.0% / Notes: / NFI = non-food items / CCCM = Camp Coordination and Camp Management / Rationale for DFID intervention / The case for maintaining and expanding DFID’s humanitarian programme in Yemen is grounded in the needs outlined above. The 2012 Yemen CAP forecasts that conditions will deteriorate further over the next one to three years, notwithstanding the opportunities that the on-going political transition process provides for restoring stability and laying the foundations for longer term recovery. / By 8 May, the appeal was 42% funded, with a funding gap of around $262m. Our current presence in Yemen and relationships with partners on the ground means we are well placed to respond. DFID will continue to lobby Western and Gulf donors to meet these needs, as well as providing the UK’s share of support. / Humanitarian assistance is a central plank of DFID’s programme in Yemen[14]. In the immediate term, humanitarian aid is vital for saving lives and preventing further declines in living conditions. It can also facilitate the attainment of longer-term goals and wider UK policy objectives that reduce the risk of state failure. / DFID’s humanitarian programme in Yemen began during FY 2010 – 2011. In total £7.5m was provided during that financial year, rising to £20m in FY 2011 – 2012, in response to growing needs. The latter included £4.6m approved by Ministers in March 2012 for ICRC and the Emergency Response Fund (ERF), a pooled humanitarian fund managed by the UN Office for the Coordination of Humanitarian Affairs (OCHA)[15]. According to data collected by OCHA, DFID was the third largest bilateral humanitarian donor to Yemen in 2011 after the US and UAE, providing just under 9% of all funds received; DFID was also the second largest donor to ICRC’s 2011 emergency appeal for Yemen. / DFID humanitarian strategy in Yemen / The overall aim of our humanitarian programme in Yemen is to save and improve the lives of those affected by conflict, disaster and economic decline[16]. The intended impact is to prevent any further deterioration in crude mortality rates. Our proposed response has been determined on the basis of (a) the analysis in the 2012 CAP, the reference document for determining humanitarian needs in Yemen, (b) ICRC’s 2012 emergency appeal and (c) assessments conducted by MENAD’s Senior Humanitarian Adviser and DFID-Yemen’s Nutrition Adviser during missions to Yemen in October 2011 and February 2012 respectively. / We will work towards the following three strategic goals: / Responding effectively to on-going protection and assistance needs resulting from conflict, economic decline and disasters. / Activities under this objective will reach: / IDPs, hosting communities and returnees, as well as other communities affected by conflict and violence; / Communities facing deprivation and acute needs who lack access to adequate food, water, sanitation, health care, education and other basic services. / Supporting preparedness for rapid-onset emergencies, including sudden spikes in violence and the effects of economic shocks or medium-scale natural disasters. / Activities under this objective will support life-saving response in the immediate aftermath of a crisis, through effective pooled funding mechanisms. / Improving the efficiency and effectiveness of humanitarian action. / Improving the evidence base for humanitarian action, through better data collection and systematic common needs assessments; / Strengthening the leadership of the humanitarian response efforts, including international advocacy and in-country efforts to secure access and humanitarian space; / Improving coordination, planning and monitoring mechanisms, particularly through the ‘cluster approach’; / Expanding the donor base (with a particular focus on non-traditional, i.e. Gulf donors), and improving donor coordination.
B. Impact and Outcome that we expect to achieve / Impact = Improved lives of people affected by conflict, disaster and economic decline / Outcome = Civilians affected by conflict, disaster and economic decline are assisted and protected with DFID support / We anticipate that, overall, the DFID Yemen humanitarian programme will deliver the following results in 2012-13: / up to 250,000 people reached with emergency food security support; / lifesaving nutrition support for 150,000 children; / provision of safe water to more than 68,000 people affected by conflict; / provision of emergency shelter to 23,500 internally displaced persons (IDPs); / access to health care for around 170,000 IDPs and others affected by conflict; / access to education for around 60,000 children living in conflict affected areas; and / emergency livelihoods support for around 35,000 people, including cash for work and agricultural inputs. / A number of delivery channels are at our disposal in Yemen to respond to needs in priority sectors: / UN organisations represented in the 2012 CAP; / the Emergency Response Fund, a small scale pooled fund managed by OCHA in Yemen, with a current budget ceiling of US$10m; / national and international NGOs represented in the 2012 CAP; / an international consortium of NGOs delivering an integrated, multi-sectoral response; and / the International Committee of the Red Cross. / DFID will use a combination of all of these channels to deliver the indicative results outlined above. This approach is consistent with UK humanitarian policy. Using a range of organisations will allow us to spread risk, helping address the operational challenges outlined above. It will also allow us to deliver at scale with large partners and use the comparative advantages and mandates of different partners for delivery with certain sectors. / This Business Case appraises the options for delivering results in northern governorates of Yemen in the following sectors: health, water and sanitation, child protection, education, nutrition and livelihoods. A consortium of NGOs made a proposal to DFID to provide such an intervention. This business case appraises this proposal against alternative options to assess whether the Consortium approach offers value for money. Other business cases will be developed to deliver other parts of the strategy. / Overarching results framework / The theory of change above outlines how DFID-Yemen financial and human resources will contribute to improving the lives of vulnerable and conflict affected people. The hypothesis, based on strong evidence and grounded in the UK government’s Humanitarian Policy (‘Saving lives, preventing suffering and building resilience’), is that needs based assistance, delivered through a well-coordinated humanitarian system which able to respond effectively and in a timely manner, can improve the lives of those affected by conflict, natural disasters and economic shocks. / This business case will contribute to the strategic goal of responding effectively to on-going protection and assistance needs resulting from conflict, economic decline and disasters, through delivery of interventions in the six priority sectors identified above. Through investment in a consortium model, which ensures a coordinated, multi-sectoral approach in a number of governorates, we will be supporting the development of a more efficient and effective humanitarian system. This approach also implies reduced DFID human resource inputs, as compared with a portfolio approach, involving multiple projects implemented by different actors. Available evidence for these associations is indicated in the diagram above.
[1] UN OCHA, Humanitarian Bulletin Yemen, Issue 2 – 5 April 2012. http://reliefweb.int/sites/reliefweb.int/files/resources/OCHA%20Yemen%20Humanitarian%20Bulletin%20-%20issue%202%20-%205%20April%202012.pdf
[2] UNHCR, New Arrivals at Coast in Yemen, 2006 – 2011.
[3] UN OCHA, Yemen Humanitarian Response Plan 2012. http://www.unocha.org/cap/appeals/humanitarian-response-plan-yemen-2012
[4] WFP Yemen, Comprehensive Food Security Survey (CFSS), Preliminary Findings, Overview and Summary, 14 March 2012. The previous iteration of the CFSS, based on 2009 data, counted 7 million food insecure, including 3 million living in severe food insecurity.
[5] WFP, ibid.
[6] “UNICEF supports a massive measles and polio vaccination campaign in Yemen,” 3 April 2012 http://www.unicef.org/infobycountry/yemen_62162.html
[7] UNICEF projections, 2012.
[8] UN OCHA, Yemen Humanitarian Response Plan 2012.
[9] UN OCHA, ibid.
[10] UN OCHA, Humanitarian Bulletin Yemen, Issue 2 – 5 April 2012.
[11] UN OCHA, Yemen Humanitarian Response Plan 2012.
[12] UPDATED Secondary Data Review, Yemen July – August 2011, Assessment Capacities Project (ACAPS) http://www.acaps.org/en/news/secondary-data-review-on-yemen.
[13] It is anticipated that the budget may be revised upwards at mid-year point, driven by an expansion of food and nutrition programming.
[14] The other programme pillars are: poverty reduction; wealth creation; and governance.
[15] DFID’s humanitarian portfolio in FY 2011 – 2012 supports ICRC’s protection and assistance activities, the ERF (a pooled funding mechanism managed by OCHA), UNICEF’s health, sanitation and nutrition services, alongside similar activities implemented by a consortium of international NGOs and other UNICEF health and education interventions. Food security is supported through a separate WFP emergency safety net programme.
[16] See DFID Humanitarian Strategy in Yemen, FY 2012 – 13.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / In this section we evaluate three options for delivery of results in the priority sectors of health, nutrition, education, protection, WASH (water, sanitation and hygiene) and early recovery / livelihoods in northern Yemen. DFID Yemen recommends proceeding with Option 1. / Provide support to the INGO consortium (recommended option) / Provide support to multiple projects managed by different non-governmental organisations participating in the 2012 Yemen CAP / Do nothing / Option 1: Provide support to the INGO consortium / How it would work / The INGO Consortium (‘the Consortium’) consists of five international NGOs – Care, Save the Children, Islamic Relief and ADRA (the Adventist Development and Relief Agency) – with a long established presence in Yemen. CARE acts as the lead agency, working through a Project Management Unit (PMU) based in Yemen. Additional back-office support is provided by CARE UK in London. Retaining this group of INGOs for the third phase was a key recommendation of the external review from the last phase so as to capitalize on the trust and understanding already achieved. / The Consortium was established in 2010 to respond to the needs of those affected by the conflict in northern Yemen. The first phase of the project (the Integrated Emergency Response Project or IERP) was co-funded by DFID and the Dutch Ministry of Foreign Affairs (MoFA); DFID was the sole funder of the second phase of the project, which ended in March 2012[17]. An independent evaluation of the second phase of the project, focussed on consortium systems and management structures, concluded that the consortium had “shown a strong performance in difficult circumstances.[18]” It also identified a number of weaknesses and inefficiencies in the coordination and management structure and made a number of recommendations concerning governance and decision-making processes, designed to improve integration of activities and actors and flexibility of response in a rapidly evolving environment. These have been incorporated into the design of the third phase of the project. They include the following: / Improved programme management structures and process, including clearly lines of authority and decision making, and an enhanced role for geographical and sectoral leads / Improved integration of project activities, underpinned by the development of a strategy for integration with related performance measures / Development of a longer term strategy for the consortium, to ensure a more strategic and effective approach. / The third phase, which runs from June 2012 to end-March 2013, maintains a focus on those affected by the on-going conflict in northern Yemen, including IDPs and hosting communities. It also seeks to tackle the acute malnutrition crisis in Hodeidah, where around one-third of children under five are acutely malnourished, and one in ten are severely acutely malnourished, i.e. double the established emergency threshold. Furthermore, the third phase incorporates an increased focus on livelihoods and early recovery, in response to the improved stability in the security and operational environment and the opportunities that this affords for more sustainable interventions. This is in line with the findings of the external review of Phase II, which recommended limiting the geographic scope of the Consortium’s work to the same five Governorates plus Hodeidah. / More specifically, the programme will provide emergency support to an estimated 269,525 vulnerable beneficiaries in six northern governorates of Yemen, i.e. Al-Jawf, Amran, Hajjah, Sa’ada, Sana’a and Hodeidah. Interventions will focus on addressing immediate life-saving needs, whilst building capacity of local service providers and increasing community resilience to future crises. The project will work across the following sectors: health, nutrition, WASH, protection, education and early recovery / livelihoods. / The Consortium will ensure access to primary and maternal healthcare, including the treatment of chronic and conflict related cases, for an estimated 75,600 beneficiaries in Al Jawf, Sana’a and Hodeidah during the lifetime of the project. / A total of 35,600 individuals in Hodeidah and Hajjah will also receive preventative and curative nutrition support. Services will be targeted towards children under five suffering from severe and moderate acute malnutrition as well as pregnant and lactating women with infants under six months. Treatment will include supplementary and therapeutic feeding as well as awareness raising and health promotion services. Referral mechanisms between communities, clinics and hospitals will also be supported. / Emergency water, sanitation and hygiene (WASH) support will be provided to 69,000 people in Amran, Sa’ada and Hodeidah, through the rehabilitation of water points, promotion of hygiene awareness, training of local community health committees and the distribution of hygiene materials. / Protection services will be provided to 4,500 vulnerable women and girls, with a focus on IDPs in Amran. The Consortium will develop the capacity and strengthen service provision in areas such as legal protection, case management, mediation and referrals. The Consortium will also work with government agencies and local community leaders to raise awareness on sexual and gender based violence. / More than 60,000 school age children affected by conflict in Amran, Hajjah and Sana’a will receive education support. This will be achieved through the distribution of school items, the rehabilitation and repair of temporary school spaces and capacity building for teachers, government officials and community members. / An estimated 24,400 conflict affected individuals in Sana’a, Sa’ada and Hodeidah will benefit from livelihoods assistance, in the form of vocational training, provision of agricultural inputs to farmers and training of village committees. / Table 2, below, provides an overview of the geographic and sectoral coverage of the project by different members of the consortium. Table 2 identifies sectoral leads and support. / Table 2: consortium activities by governorate and organisation / Governorate Health Nutrition WASH Protection Education Early recovery/liv. / Al Jawf ADRA -- -- -- -- -- / Amran -- -- CIY CIY SCI -- / Hajjah -- SCI -- -- SCI -- / Sa’ada -- -- OXFAM -- -- OXFAM / Sana’a ADRA -- -- -- SCI ADRA / Hodeidah ADRA / IRY ADRA / IRY / SCI OXFAM -- -- ADRA / IRY / OXFAM / Table 2: sectoral lead agencies and support / Sector Lead agency Supported by / Health ADRA IRY / Nutrition SCI -- / WASH Oxfam CIY / Protection (cross-cutting) PMU (CIY) IRY, SCI / Education SCI -- / Early recovery / livelihoods Oxfam ADRA / Theory of change / Support for phase 3 of the IERP will help to deliver the outputs detailed in the strategic case above and will contribute towards attainment of all three strategic objectives articulated above, under the section ‘DFID’s humanitarian strategy in Yemen’. It will also deliver on CAP 2012 targets in the relevant response sectors. / In particular, funding for the Consortium will advance DFID’s strategy for meeting humanitarian assistance and protection needs, including amongst IDPs and others affected by conflict and violence, economic decline or disasters. It will also support preparedness for rapid-onset crises and shocks. / The well-being of vulnerable and conflict affected populations in northern Yemen will be improved through the delivery of a range of basic services, including health care, water and sanitation and education, meeting needs in key areas and contributing to the stabilization and reduction of mortality and morbidity. Interventions recognise and address the inter-related nature of humanitarian needs in Yemen, particularly related to malnutrition, in the form of a complementary response package. This is built into the entire project management cycle, beginning with the use of common needs assessments and application of agreed standards. / The Consortium will also provide support for the restoration of livelihoods, including for displaced persons and returnees and others affected by conflict and food and commodity price rises. This will be delivered through skills development / vocational training and business support, as well as provision of agricultural inputs and livestock. / Preparedness for rapid-onset crises and shocks will be improved where possible, through building the capacity of local service providers, including health providers, community sanitation networks and organisations working on protection and rights issues. / Environment and climate change / Typically, armed conflict can contribute to environmental degradation and worsen the impact of climate change. This is especially the case where there is destruction of community infrastructure and services – such as the destruction of water supplies and disruption to waste management and water treatment processes. Displacement of communities, as a result of conflict, invariably brings about increased localised pressures on the natural resource base, such as deforestation (firewood collection and sale), increased pressure from grazing livestock, localised waste accumulation and pollution, and over-exploitation of water supplies. Management of resources becomes weaker as displaced communities have neither a controlling stake nor interest in the environment in which they are temporally displaced to. DFID will ensure that any review of the programme in Yemen looks, in particular, at the impact of interventions on water resources. / We assess the likely impact on climate change to be low and manageable. / Option 2: Provide support to multiple I/NGOs working separately in priority sectors / How it would work / Whilst the operational capacity of the humanitarian sector in Yemen remains limited, a number of other agencies (I/NGOs and UN agencies) participating in the 2012 CAP could separately deliver many of the activities proposed in option 1. These organisations do vital work and achieve important results; their inclusion in the CAP reflects their contribution towards priorities agreed by the humanitarian community. / This would involve DFID entering into a number of accountable grant agreements (up to six) with multiple partners and managing these separately. Whilst partners would be working independently, activities would be coordinated at sectoral level through the UN-led cluster system, which is designed to avoid duplication of effort and minimize gaps in service provision. However, we assess that such an approach would limit our ability to tackle the inter-related nature of many humanitarian needs in Yemen and develop synergies across different sectors of intervention. Our ability to programme flexibly could also be constrained, depending on the areas of expertise of individual partner organisations, with limited scope to re-allocate funding to best meet needs. Although this approach would incur additional administrative costs on DFID, these costs might be offset if interventions delivered by the consortium did not provide value for money. This is assessed in section C, below. / Theory of Change / Support for multiple partners in priority sectors would help deliver outputs in the strategic case and would contribute towards attainment of the first two objectives, namely: (1) responding effectively to on-going protection and assistance needs resulting from conflict, economic decline and disasters; and (2) Supporting preparedness for rapid-onset emergencies. / The theory of change would operate in the same way as under option 1, above. / Environment and climate change / We assess the likely impact on climate change to be low and manageable, as outlined under option 1, above. / Option 3: Do nothing / We assess that not providing funding to INGOs with a proven track record of delivering humanitarian assistance in Yemen will increase the risk of further deterioration in conditions and loss of lives which could otherwise be saved. It will further undermine the ability of the humanitarian community to respond to new and emerging needs. It also risks sending a negative signal to other donors and INGOs that are looking to establish programmes in Yemen to meet growing humanitarian needs. Not addressing humanitarian needs risks not addressing some roots causes of grievances and insecurity. / We recommend that this counterfactual option should not be considered because: / The benefits of providing assistance to affected populations far outweighs the costs of doing so (see section on ‘Costs, benefits and risks,’ below) / The political and security situation would be negatively affected if urgent humanitarian needs were not met in a timely fashion / It is unlikely that other donors would meet the full range of needs. / Environment and climate change / The likely impact on climate change is assessed as medium potential risk. The net impact on the environment is assessed as negative. This reflects our assessment that unmet humanitarian needs can result in negative environmental practices which, in the counterfactual, would not be offset by programming interventions.
B. Assessing the strength of the evidence base for each feasible option / Security conditions, access restrictions and logistical constraints have directly impacted on the ability of agencies to adequately assess needs and develop an evidence base for humanitarian action. Whilst a number of assessments have been conducted, there are gaps in data and concerns about accuracy of findings, due to small sample sizes[19]. Concrete steps are being taken to address these shortcomings and the humanitarian community has acknowledged the need for further action[20]: the 2012 Yemen CAP gives priority to needs assessments, improving coordination and building the capacity of the clusters. Nevertheless, Yemen is likely to remain a difficult environment in which to collect and verify data. / However, in light of the available information of the Consortium’s ability to deliver the intended results and the strengths and potential weaknesses of the consortium model, as outlined in the independent evaluation of the second phase of the project and the final narrative report, the quality of evidence for this option is rated more highly than for the two alternative options. / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Strong / 2 Medium / 3 Medium / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 B C
C. What are the costs and benefits of each feasible option? / Option 1: provide integrated programmatic support through the INGO Consortium / The project aims to improve the lives of vulnerable and conflict-affected people in northern Yemen, assisting recovery from shocks of conflict and the socio-economic crisis through an integrated package of interventions. The proposed interventions include health services; nutrition services; water, sanitation, and hygiene inputs; protection services; formal and informal education; and livelihoods support. These programmes will be integrated at both a programmatic and operational level to deliver additional spill-over benefits. / Costs / The total cost for all proposed interventions, including the management and integration elements is £5.29 million. The breakdown of costs between the different elements is provided in the table and chart below. The proposed DFID contribution is 100% of these costs. / The largest single component of the proposed programme is for livelihoods interventions at over a quarter of costs. Health, education, and water, sanitation, and hygiene services make up just under half of the costs collectively. The remainder of costs relate to nutrition, protection and overall management costs. / INGO project costs / Sector Organisation Area Cost £ / Health ADRA, Islamic Relief Al Jawf, Sana'a, Hodeidah 1,071,040 / Nutrition Save, ADRA, Islamic Relief Hajjah, Hodeidah 405,170 / Education Save Amran, Hajjah, Sana'a 903,266 / WASH Care, Oxfam Amran, Sa'ada, Hodeidah 1,029,185 / Protection Care Amran 221,168 / Livelihoods Islamic Relief, ADRA, Oxfam Sa'ada, Sana'a, Hodeidah 1,376,029 / Sub-total 5,005,858 / Overall management Care International 286,674 / Total 5,292,532 / Breakdown of costs per programme component £ / Unit costs / A full assessment and monetisation of benefits is not appropriate for the proposed package of interventions, due to a lack of comparable data. To analyse value for money, a unit cost analysis has been undertaken, which allows a comparison of the various components of the programme with alternative options. The table below outlines the cost of each component, along with the number of beneficiaries and services. The spread of unit costs ranges from £11 per beneficiary for nutrition interventions, to £56 per beneficiary for livelihoods interventions. The average cost per beneficiary is around £18.5. / In some cases, the number of services is significantly higher than the number of beneficiaries – implying that some beneficiaries are receiving more than one type of service from each sector. The main methodological issue with the unit cost analysis is the level of detail regarding the bundle of assistance for each beneficiary is not known. Some detail is provided on disaggregated unit costs which comprise individual elements of service provision the INGO consortium interventions, but many of these are not directly comparable to alternatives assessed in the CAP. This is a common problem in analysis of humanitarian interventions value for money. Nevertheless, the unit cost analysis does provide a basis for understanding the value for money of the proposed interventions. / Unit costs / Area Detail Cost (£) Beneficiaries Cost/ beneficiary (£) Services Cost/ service (£) / Health Essential health services 1,071,040 75,600 14 126,050 8 / Nutrition Preventive and curative nutrition services 405,170 35,600 11 35,600 11 / WASH Water, sanitation and hygiene inputs 1,029,185 68,853 15 109,150 9 / Protection Protection services provided 221,168 4,472 49 4,458 50 / Education Formal and informal education services 903,266 60,600 15 90,600 10 / Livelihoods Livelihoods support 1,376,029 24,400 56 27,855 49 / Benefits / 68,853 vulnerable people will benefit from water and sanitation interventions to increase access to safe water sources, promotion of appropriate hygiene practices, and distribution of hygiene materials. This will assist in reducing morbidity and mortality associated with a number of diseases, including diarrhoea, which is widespread in Yemen. At any given time, half of the world’s hospital beds are occupied by patients suffering from a water-related disease[21]. Unclean water is the world's second biggest killer of children. In adults, water based diseases are a major cause of ill-health, reducing the ability to work and causing much suffering. A 2008 WHO study[22] found that in Yemen, 16% of all deaths in 2002 were attributable to problems with water, sanitation and hygiene. Of these, just over 60% were due to diarrheal diseases. Moreover, 14.7% of total Disability Adjusted Life Years (DALYs) lost were attributable to water and sanitation related problems. / Health benefits for 75,600 vulnerable people will be in the form of free medical consultations and follow up of chronic diseases, conflict-related cases, and maternal cases. Equipment, medication and supplies will be provided along with training for staff. These programmes will not only provide benefits in terms of lives saved, but a healthier population is also more likely to attend school or engage in productive activities. Higher levels of school attendance can raise future productivity, and keeping people in work now helps maintain skills as well as the immediate benefits to household income and consumption. / Education services will be provided for 60,600 school age children through provision of school facilities and teacher training. Increased access to basic quality education will enable progress in and completion of studies, generating significant future private and social returns. Average social returns to basic education have been found to be as high as 20% for boys and 12% for girls.[23] Benefits will be derived through maintaining education levels in the country, increasing long term income earning potential and associated spillover benefits such as better health. / Preventive and curative nutrition services provided to 35,600 vulnerable people. Direct nutrition activities will be implemented both to cure children suffering from malnutrition and to prevent children from becoming malnourished. Malnutrition rates are above emergency levels in the regions of intervention focus (global acute malnutrition rate of 31.7%, and severe acute malnutrition of 9.9%.[24]) Nutrition benefits could be assessed on the ability of the intervention to reduce malnutrition, potentially saving (DALYs) from nutritional deficiency. WHO provide a comprehensive list of DALYs lost through a range of diseases and health care conditions, although is based on 2004 data.[25] DALYs could then be monetised on the basis of Gross National Income per capita. The WHO Commission on Macroeconomics and Health (2008) suggest the benefit associated with a DALY is up to three times the GNI per capita of the country. However, the WHO data on malnutrition is only available for low and middle income countries for the Eastern Mediterranean region, and is based on 2004 malnutrition data – the data is therefore not relevant to the food insecure populations in Yemen which will be targeted by this programme. We therefore do not quantify or monetise the nutritional benefits. / Protection services provided to 4,472 conflict-affected people through supporting local partners’ protection services, and advocacy and training. The interventions proposed here aim particularly to increase knowledge of available services and protection issues, which is a key constraint in accessing appropriate support. / Increased livelihoods support for 24,400 vulnerable people through the provision of business management training and grants. The benefits of training and small scale business support have been well assessed.[26] / Benefits of integration / Integration of programme activities through the consortium approach should in theory deliver two kinds of additional benefits: i) efficiency savings from reduced administrative costs; and ii) increased effectiveness from synergies realised from mutually beneficial programmatic interventions. / Efficiency savings will occur for both DFID and the INGO Consortium. For DFID, these have been calculated based on the amount of staff time saved through developing and managing one consolidated programme rather than six individual programmes. This is based on the assumption that the INGO Consortium will require 5% of an advisor and programme manager’s time, whereas six individual projects would require 25% of their time. Based on these assumptions, the cost saving of funding a joint programme would be just over £22,000. / DFID management costs staff time / Staff Joint programme £ Separate programmes £ / Programme manager 2,200 11,000 / Humanitarian advisor 3,582 17,910 / Total 5,782 28,910 / Administrative and management cost savings should also be realised for the INGO Consortium, through streamlined administrative processes and procedures (such as work plans, capacity development plans) and shared amenities such as use of office space. Details of these potential cost savings are not available – however, they should be reflected, in principle, in competitive unit costs. / The other major potential benefit arising from integration of activities would be spillover benefits arising from complementary interventions. Too much focus on individual sectors may have limited or even negative impacts on society through the opportunity cost of resource allocation. For example, one study suggests that in economies suffering from large scale malnutrition and poverty, too much focus on education may have limited impact. In these cases increased food consumption is needed to complement the education. One study shows how consumption of nutrients in Indonesia affects nutritional status, and how better nutrition in turn affects labour earnings, employment, leisure, and physical health.[27] / The 2012 independent evaluation of INGO Consortium’s work under earlier project phases suggests that while these integration elements have high potential returns, the Consortium is yet to realise them in a systematic manner. / ‘Such synergies are currently achieved mostly through serendipity, and are not planned in advance; they depend on whether or not the necessary complementary programs exist in a particular geographic area. The consortium could intensify the creation of such synergies by planning them into a technically integrated approach. (p34)’[28] / The report therefore recommends: / ‘Improve integration of CP activities for greater synergy. This will require pre-defining what type of integration should be achieved, specifying mechanisms of integration, setting measurement indicators, and including these indicators in the project log frame. (p3)’ / The proposal by the INGO Consortium outlines the strategy for integration, which includes improved planning processes, sectoral leadership, improved coordination mechanisms, and strengthened monitoring and evaluation processes. Through this strategy, integration would be achieved both at the programmatic and operational level. A lack of evidence means a full assessment of the effectiveness benefits arising from more integration is not possible. However, it is suggested that this is incorporated into future evaluations to ensure full appraisal of this critical element of the programme. / Option 2: provide similar programmatic support through alternative organisations in the CAP / The alternative option is to provide similar interventions through a range of alternative service providers identified in the CAP. Similar interventions are identified through the appeals included in the CAP, which provide some details of services provided, cost, and beneficiaries. Under this option, there would be a set of six different projects, with separate management arrangements under each one. There would also be no benefits of integration between the different programme components. / Assessment of the alternative service providers allows a value for money assessment in comparison to the INGO Consortium option through analysis of unit costs. The average unit cost across the six areas of programmatic intervention is £8.10 (cost per beneficiary), which is 57% lower than the average cost under the INGO Consortium. The unit costs range from £4 per beneficiary for basic education, and water, sanitation, and hygiene services, to £51 per beneficiary for livelihoods interventions. / Unit costs of other organisations in the CAP / Area Detail Provider Cost Beneficiaries Cost/ beneficiary / Health Life saving health care International Organisation for Migration 1,915,144 60,000 32 / Nutrition Preventing malnutrition Relief International 731,870 122,444 6 / WASH Water and hygiene services International Medical Corps 369,600 95,000 4 / Protection Protection from armed conflict Danish Refugee Council 360,976 15,360 24 / Education Basic education services UNICEF 1,315,127 352,000 4 / Livelihoods Cash grants and cash for work Danish Refugee Council 613,536 12,000 51 / The of cost per beneficiary for each component of intervention is shown in the chart below, comparing the INGO Consortium unit costs with unit costs for alternative service providers identified in the CAP. This shows that INGO Consortium unit costs are higher for four out of the six interventions – nutrition, WASH, protection, livelihoods, and education. In the case of WASH, protection, and education, the INGO unit costs are more than 50% higher than alternative service providers. / Three issues need to be explained here. Firstly, as stated above, the detail of each package of intervention will not be the same between service providers – for the alternative providers under the CAP, less detail is provided than for the INGO Consortium, limiting direct comparability. For the INGO Consortium, multiple services under each sector are being delivered to the same beneficiary. If the average cost per service is used for the INGO Consortium (£12.50), then the average unit cost differential reduces significantly, to just over 35% more expensive for the INGO unit cost. / Benefits / There is no evidence to suggest that services provided by alternative service providers are of higher quality or more effective than services provided by the INGO Consortium. Given the rationale for integration of services, one could expect that services provided by discrete organisations would be less effective. However, we do not have sufficient evidence to enable such analysis. Therefore the question of relative impact is a question of efficiency of service provision – and the value for money assessment therefore rests on the unit cost and other analysis outlined above. / Option 3: Do nothing / Without DFID funding, there may be a reduction of rapid humanitarian service delivery. There are no benefits (beyond budget conservation). The counterfactual in the do nothing case is difficult to determine accurately. However, the urgency of Yemen’s humanitarian situation cannot be overstated. Yemen is facing a full-fledged humanitarian crisis that is rapidly deteriorating and becoming more complex. The country is gripped by a number of overlapping conflicts that are increasingly bringing the civilian population to the brink of an emergency situation. / Yemen’s economy faces multiple challenges, following a year of political and social unrest. The national budget is under pressure as expenditure and the deficit have increased, while sources of financing are limited. Foreign reserves are gradually dwindling, putting pressure on the exchange rate. The economy contracted by 10% in 2011,[29] with significant increases in unemployment reported.[30] The economic challenges are having a severe impact on the social and humanitarian situation. Malnutrition in some areas has reached 32% – more than double the internationally recognised emergency threshold of 15%. Poverty is likely to have increased beyond the estimated 42% living on less than $2 a day, as households suffer from a combination of high inflation, job losses, and collapse in public services such as health and education. / Therefore the counterfactual in the case of no DFID funding can be considered to be severe – with potential increases in morbidity and mortality, among other impacts. / Assumptions, risk, and uncertainty / The primary area of uncertainty is the limited information to undertake comparable value for money analysis. This has been mitigated where possible through comparison of costs, and sensitivity analysis to test assumptions and key cost drivers. / The analysis is based on a given scenario in Yemen, which may change and impact on delivery, costs, and consequently outcomes. The future trajectory of Yemen’s political, economic, and security is highly uncertain, which poses a risk to the expected benefits and cost-effectiveness of the humanitarian interventions.
D. What measures can be used to assess Value for Money for the intervention? / Measures used to assess value for money include: / Unit cost measures by assistance type / Qualitative and partial quantitative analysis of benefits / Primary assessment of value for money has been conducted based on unit cost analysis. These are imperfect and have methodological limitations, as set out above. Unit cost analysis is complemented through qualitative and partial quantitative analysis of benefits where possible. / Given the amount of DFID funding to humanitarian interventions in Yemen, an evaluation of DFID’s humanitarian support in Yemen should be considered, in order to assess which interventions have had the most impact, which organisations have been the most effective, and to inform future funding decisions. An external evaluation of this project will be conducted upon its completion. / .
E. Summary Value for Money Statement for the preferred option / The value for money appraisal of the proposed options is based on DFID’s 3E framework: economy, efficiency, and effectiveness. However, data and information to fully appraise all these elements is not available – the majority of the analysis is focused on the cost-efficiency and cost-effectiveness of the proposed interventions, based on the unit costs of the INGO Consortium and alternative service providers under the CAP. / The analysis suggests that the average and individual unit costs of INGO Consortium interventions are generally higher compared to alternatives. However, this is largely qualified by potential multiplication of services, and differences between bundles of components of services between the INGO and alternative service providers. The difference in unit costs varies considerably across the different interventions. Taking the average unit costs, the difference, although material, could be explained by alternative bundles of services delivered and differences in quality. / The element that is more difficult to assess is the benefits arising from integration of humanitarian activities. Additional benefits of integration which have not been captured by the analysis could be significant, such as better health and education outcomes among the target population, and may at least compensate for the differences in unit cost. Only partial analysis has been undertaken of this – and it is suggested that future monitoring of the impact of systematic integration is built in to the project to enable more analysis in the future of this element. It is also noted that this monitoring has been factored into the logframe for the third phase of the project. / Based on the appraisal, the preferred option is the Consortium of International NGOs (Option 1).
[17] MoFA did not provide funding for the second phase due to stricter rules around the classification of development and humanitarian assistance).
[18] Integrated Emergency Response Project II for Yemen 2011/2012 External Review. Sharon Beatty, Februrary 2012. This evaluation considered the functioning of the consortium model and the systems, structures and procedures in place. A second evaluation, focussed on the delivery of project outputs, is still on-going.
[19] UPDATED Secondary Data Review, Yemen July – August 2011, Assessment Capacities Project (ACAPS), ibid.
[20] An ACAPS review of secondary data was carried out in June 2011 and updated in September. ACAPS, ibid.
[21] UNDP, Human Development Report 2006, Beyond Scarcity: Power, Poverty and the Global Water Crisis, 2006
[22] A.Pruss-Ustun et al., Safer Water, Better Health: Costs, benefits and sustainability of interventions to protect and promote health, WHO, Geneva 2008
[23] Psacharopoulos, G. and Patrinos, H.A. (2002) Returns to investment in education: a further update World Bank Policy Research Working Paper Series 2881
[24] UNICEF, Nutrition Survey, December 2011
[25] 2004 data is out dated and malnutrition has increased significantly in recent years in Yemen (WFP 2010). The target population is also at risk of food insecurity, whereas the WHO data is for the Middle East region as a whole. We have therefore trebled the WHO DALY estimate (approximately 4% of total DALYs lost through nutritional deficiencies*3).
[26] Including recently ‘Duflo et al (2010), ‘The Miracle of Microfinance? Evidence from a Randomised Evaluation’ MIT
[27] Thomas et al (2006)
[28] Integrated Emergency Response Project II for Yemen 2011/2012, External Review, Sharon Beatty, February 2012
[29] IMF estimate
[30] Reported by Ministry of Planning and International Cooperation, Government of Yemen, October 2011

Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / The recommended option of this business case is for DFID to provide funding to a Consortium of International NGOs. This requires payment through an Accountable Grant. It is therefore judged to be ‘indirect’ procurement of goods and services.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / This programme is Phase III of an existing intervention funded by DFID. Over the previous two years the Consortium has demonstrated that it can meet humanitarian needs in Yemen. Their project proposal makes clear how they will continue to do this in a third phase, delivering results in six sectors that have been identified as priorities in the UN’s Consolidated Appeal Process (CAP) and DFID Yemen’s Humanitarian Strategy. The Consortium has also proven itself capable of delivering results in governorates such as Amran, Al Jawf and Sa’ada, where humanitarian access has continued to be difficult. / All the Consortium partners have at least ten years of operational experience in Yemen; some such as Save the Children have over forty. Members of the Consortium are also established implementing partners for UN agencies, a sign of their trusted ability to deliver and unique access. Use of local participation and community mobilization broadens the reach of the INGO Consortium helping it to resolve access issues and establish relationships with local authorities and communities. / Working as a consortium also allows an integrated approach to be taken, with the consortium partners sharing experience, referring beneficiaries to one another as appropriate and tacking needs such as nutrition in an integrated fashion. There are a number of other agencies that DFID could fund that could separately deliver some of the results proposed, however there is no single agency or alternative consortium mechanism that could deliver the comprehensive package of support proposed by the five member INGO Consortium. / DFID has encouraged the Consortium to work in an increasingly integrated manner. Measures of this have been included in the logframe for this project. The enhanced authority of the Consortium’s Programme Management Unit for this phase should also ensure that the Consortium acts as one coordinated body. Working with a consortium also brings efficiencies for DFID – managing one integrated project through an Accountable Grant rather than managing five separate projects to deliver the same results.
B. Value for money through procurement / As per the Accountable Grant letter, Care International UK (CIUK), as the lead agency, must ensure that any procurement using grant funds meets international good practice, is untied and free of narrow national self-interest, and uses transparent processes, transparently fair and open competition, and good contract management, including prevention of malpractice. / All five Consortium partners have procurement policies that outline procedures they must follow to ensure value for money is achieved through procurement in Yemen. Members of the Consortium will follow competitive tendering practices for procurement activities, but decisions remain devolved to each Consortium partner. Where it is possible to do so, items will be procured in country and locally to boost the local and national economy, as well as reducing transportation cost and time. / ADRA Yemen’s Procurement Policy is intended to guide and regulate the procedures under which ADRA employees procure necessary project and administrative materials. It ensures accountable and transparent use of donor funds and that competition in the selection of contractors/vendors is free, fair and uncompromised. It provides guidance on the identification of suppliers, obtaining and analysing quotations, authorization of purchases and payments and upkeep of the inventory. Purchases over US$300 require three quotes and those over US$5,000 require four. / Care International’s ‘Supply Chain Management Procurement Policies and Procedures Manual for Care Country Offices’ sets out how Care achieves value for money when procuring goods. For example, to the extent possible, procurement activities should try to support local businesses when sourcing goods and services that are available locally to contribute to the local economy. CARE will use competitive solicitation in the acquisition of required goods and services. All procurements shall be conducted in a manner to provide, to the maximum extent practical, open and free competition amongst potential vendors. The solicitation process will be ethical, fair, competitive and in compliance with donor requirements. Procurement of goods and services in excess of US$1,000 requires at least two quotations and those in excess of US$5,000 requires at least three. / Islamic Relief’s ‘Purchasing Policy’ facilitates the acquisition of goods and services of the optimum quality and quantity, at the lowest prices and preserves organisational and financial accountability. Purchases exceeding US$2,000 require three written quotations and those in excess of US$25,000 require at least five written, sealed bid tenders and supporting documentation must be retained giving reasons for choices made. Islamic Relief’s Procurement Department supports and controls the process to facilitate good working purchasing practice within the organisation. All purchases must be made by the full, tacit approval of the Procurement Department, wherever possible. / Oxfam’s ‘Logistics, Purchasing and Supply Procedures Manual’ sets down the approved integrated logistics, purchasing and supply policies, procedures and authorisations that are mandatory for all Oxfam GB operational programmes and their partners as well as best practices. Oxfam develops and adopts optimum supply strategies and processes that achieve best value for money in procuring goods, works and services. Purchases in excess of £250 should be subject to competition with a minimum of three quotations required. Quotations are evaluated to identify the supplier(s) best qualified to perform the contract or fulfil the order at the most advantageous cost with the least risk. / Save the Children’s Procurement Policy sets out how they will obtain goods, construction works and services that provide good value (balancing quality with cost) for their programmes and those they serve, through procurement processes which are fair, transparent, and in compliance with donor rules and applicable laws. Three written quotes are required. Local procurement is preferred if it is better value for money and quality can be assured, to promote the local economy and have positive impact on the environment. A clear authorisation and audit trail must accompany the payment for any goods or services procured and a record should be kept of the procurement at the relevant office. / The Consortium’s Programme Management Unit (PMU) will regularly review value for money, working closely with finance and procurement staff to ensure best value purchases. They will also record and share successful value for money approaches between consortium partners. One example of the Consortium delivering value for money in this regard is that they will share space in existing offices and use communications equipment purchased in Phase II.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / DFID Yemen will pay up to £5,292,532 for the 2012/13 financial year. The amounts to be received by each NGO within the Consortium are: / Consortium Partner Funding (£) Percentage of total / ADRA 1,013,822 19.2 / CARE International 920,487 17.4 / Islamic Relief 505,240 9.6 / Oxfam 1,337,740 25.2 / Save the Children 1,179,416 22.2 / Project Management Unit (PMU) 287,526 5.4 / CARE UK 48,300 0.9 / Total 5,292,532 100 / The funding to each partner includes their direct costs and 10% for Organisational Management Support, split equally between the Consortium partner (5%) and Care International UK (5%) as the lead agency. The £48,300 for Care UK is earmarked specifically for monitoring and evaluation, including an independent evaluation and internal audit. / DFID is the sole donor to this project, so costs will be profiled using resource accounting throughout the 2012/13 financial year. Care International, as the lead agency, will collate reports and budgets from consortium partners and provide quality assurance of these. The Consortium will report quarterly on delivery of results and expenditure and request funding for the next quarter against budget forecasts. This will allow DFID to monitor expenditure and forecast accurately.
B. How will it be funded: capital/programme/admin? / DFID Yemen will fund the whole allocation from its programme resources, under the humanitarian pillar.
C. How will funds be paid out? / Three payments, totalling up to £5,292,532, will be made against an Accountable Grant agreement. The first tranche of funding will be paid at the in July 2012 upon receipt of ministerial approval, the second tranche in October 2012, and the final tranche in January 2013. / As a general rule, DFID does not make advance payments, however where justification has been provided as to the urgency of the funding and the inability of the partner to pre-fund, an exception can be made. Care International provided this, explaining that they have limited capacity to arrange loans for pre-payments. They have limited unrestricted reserves with other projects having been earmarked for the limited funds that exist. In this case, DFID Yemen supports this approach to ensure greater agency preparedness and ensure need is met in a timely manner. / Payments are stated in pounds sterling but will be paid in dollars (at the exchange rate prevailing on the day of transfer).
D. What is the assessment of financial risk and fraud? / Given the security situation in Yemen there is a risk of loss of resources through misappropriation. There is on-going conflict in the north where the Consortium delivers humanitarian assistance. However, the Consortium has been a partner of DFID in Yemen for the last two financial years and there has been no indication of fraud or corruption. By establishing relationships with local authorities at the district level and with communities, the Consortium’s activities are accepted and understood, reducing the risk of misappropriation. / In the previous two phases, misappropriation of non-food items has been reported twice. On both occasions the Consortium has taken the appropriate action - reporting the events to DFID in a clear and timely fashion and pursuing the issue with local authorities. In the first instance, the case was pursued and it was established that misappropriation had in fact not occurred and the items were accounted for. In the second event, the Consortium reported the theft of items amounting to around $7000 – the case is being pursued. Such risks must be balanced against the importance of meeting humanitarian need. / In applications to DFID’s Rapid Response Facility, Care International UK, who are the lead agency in the Consortium, were the top ranked NGO on ‘administrative and financial’ measures. CIUK has a designated Risk Manager charged with the responsibility of establishing and maintaining a risk register and ensuring implementation of mitigating processes. There is also a Risk Management Committee responsible for identification and assessment of business risk and developing specific mitigation measures. / Items on the risk register focus on management of funds through partners. CIUK’s due diligence and oversight of these local entities is therefore extremely important. All partners are required to make disclosure and they are also vetted by anti-terrorism software. Although slightly more expensive, this helps create a much stronger control environment. CIUK utilises local audit and independent review to ensure effective management of partner funds. CARE also uses beneficiary complaint mechanisms to report fraud and corruption. / Transparency International’s 2011Corruption Perceptions Index ranked Yemen 164 out of 183 countries (where 1 is perceived to be the least corrupt)[31]. This is however based on perceptions of government corruption. DFID works through multilateral and non-governmental organisations to avoid this risk. DFID is also developing a new anti-corruption strategy to further ensure risks of corruption are mitigated. / In regards to risk of corruption, CIUK has in place full policies addressing: anti-bribery, anti-money laundering and frauds and losses, conflict of interest, and whistle blowing. All key staff members are trained on these policies. Recent investigations in Haiti and Pakistan have addressed instances of fraud quickly and effectively. CIUK enforces these policies and reviews them accordingly based on needs and changes in the risk management environment. / As set out in the Accountable Grant, if at any stage CIUK should become aware of, or suspect, any misappropriation or diversion of funds or possible fraud or corruption relating to the project/ programme activities funded by the DFID grant, CIUK must report the matter immediately to DFID. / Of the other consortium partners, Oxfam, Save the Children and Islamic Relief also applied to the Rapid Response Facility and were approved for pre-qualification. Oxfam and Save the Children were ranked second and third respectively (behind CIUK) on administrative and financial measures.
E. How will expenditure be monitored, reported, and accounted for? / Given the current security situation in Yemen and the limited DFID presence in country, the Accountable Grant will largely be monitored from London. However, both DFID Yemen’s Humanitarian Adviser and Humanitarian Programme Manager will make visits to Yemen to meet with partners and understand any issues that may arise with the project. / The Consortium will produce quarterly standard reports including financial and narrative reporting in advance of tranche payments. The Programme Manager will review reports, raising any issues of concern and checking delivery against indicators in the logframe. DFID will ask for operational updates from the Consortium Programme Management Unit (PMU) via quarterly teleconferences and when the situation requires. / The timeline below is based on funding approval in May 2012: / Type of Report Date Due / First Report 30th September 2012 / Second Report 31st December 2012 / End of Project Report 31st May 2013 / CIUK are audited annually and will submit these to DFID by 31st December 2013. The project has also budgeted for an internal audit. / As is standard in an Accountable Grant agreement, should any changes occur which, in DFID’s opinion, impair significantly the humanitarian or developmental value of the project, DFID and the Consortium will discuss these changes, attempt to resolve them and, in the very last resort, DFID will modify or terminate its financial contribution to the project giving three months’ notice in writing.
[31] http://cpi.transparency.org/cpi2011/results/#CountryResults

Management Case

A. What are the Management Arrangements for implementing the intervention? / As a result of the learning captured during Phase II and in response to the recommendations from the external review of the project, the Consortium is adopting an amended management structure for Phase III, with a ‘modified consensus approach’. This structure comprises two key bodies, the Programme Management Unit (PMU) and the Programme Steering Committee (PC). The external review for Phase II recommended a ‘red flag’ system to indicate if performance by consortium partners is behind schedule. This has been incorporated for this Phase – the PMU will have the authority to inform Consortium partners’ senior management and Headquarters, before reallocating funds among sectors or partners if appropriate. / The PMU, led by Care International Yemen with support from CIUK, comprises the following staff roles: / Consortium Manager: responsible for the focus on; integration, coordination, accountability and quality oversight as well as provision of technical expertise and capacity building on humanitarian standards, accountability, protection and monitoring. / Assistant Manager: responsible for reporting, following up with partners, contractual management, supporting the monitoring of compliance and regular monitoring of project achievements, monitoring of burn rates, follow up on sectoral and geographical coordination meetings / Finance Officer: responsible for consolidated accounting, financial reporting and forecasting / M&E Officer: responsible for strengthening M&E systems, planning and implementation of monitoring and review activities plans and supporting partners in M&E, as well as liaising with sectoral and geographical leads on monitoring and standard harmonisation. / The PMU will fulfil the same administrative and management role as the Programme Coordination Team did in Phase II. However, it will also have the following new roles and responsibilities: / Executive decision making: the PMU will have the authority to reallocate funds between Consortium partners and/or adjust project plans as a measure of last resort if insufficient mitigating action is taken by a Consortium partner and/or the Project Steering Committee. This will be based on pre-defined and agreed ‘red flags’ on project delivery. / Representation and communication: PMU will represent the Consortium and its members in existing humanitarian fora in Yemen, leading on the dissemination of agreed messages in support of increased effectiveness and coordination of humanitarian action, policy change. / M&E: coordination between the PMU and assigned sectoral leads will enable more in-depth, consistent and, therefore, effective monitoring of project activities and results. This in turn will provide a solid basis for more rigorous lesson learning and more effective and cohesive planning. / Shared standards: PMU will be responsible for monitoring Consortium partners’ adherence to agreed shared standards in humanitarian practice and programming. / Integration: PMU will lead on the development of the three year strategy for the Consortium’s work, providing technical support and leadership as well as capacity building support. / The Project Steering Committee will comprise the PMU as described above, plus one named representative from each of the partner agencies, who will hold the authority to represent and make decisions on behalf of their agency within the committee. This is based on another recommendation from the external review to ensure the PMU has a ‘leadership and technical role’, not just an administrative role. PSC meetings will be convened monthly or as called by the PMU. The PSC will function as the decision-making body of the Consortium. / Technical Working Group / This group comprises the assigned sectoral leads and will meet regularly to review progress and share learning. While the individual sectoral leads will be managed by their respective agencies, the group will report to the Consortium Manager on technical/sectoral matters to ensure effective coordination and information sharing between this group and the rest of the Consortium (via the Project Steering Committee). Members of this group will also work closely with the M&E officer to strengthen M&E processes and monitor sector-level progress. / CIUK support: Emergency Programme Officer / A dedicated Emergency Programme Officer (EPO) will be recruited to support the programme in Phase III. The EPO will be the primary contact point for DFID and will ensure all reporting/other requirements are met, as well as providing day-to-day support to the Consortium Manager and PMU on project management, compliance, monitoring, burn-rate and budget issues. Support will also be provided to the consortium on communication messages within the UK development and humanitarian sectors, as well as networking and sharing lessons within relevant fora. The EPO will also ensure links and networking with CP offices in London for enhanced consortia integration. Over 30% of the EPO’s time will be spent in-country with the project team. / DFID will monitor these interventions through examining quarterly reporting as well as quarterly teleconferences and ad hoc operational updates when required. Where possible, we will conduct in country meetings with Consortium partners.
B. What are the risks and how these will be managed? / The situation in Yemen is evolving on a daily basis. In addition, humanitarian interventions are more likely to be implemented in areas with a higher risk of conflict and with higher security concerns. Clauses in the Accountable Grant letter will enable DFID to review its assistance in the event that implementation is significantly compromised. Risks to project delivery and mitigating actions are: / Risk Probability Impact Mitigating Actions / Civil unrest: risk of violence and new displacement impede project delivery Medium High PMU will continuously monitor developments at national and governorate levels. / PMU will liaise closely with other humanitarian actors (HCT, OCHA and UNHCR) to monitor changing landscape. / PMU will execute rapid assessments if required to identify emerging or crisis needs. / PMU will conduct ad hoc contingency planning, in coordination with other actors. / Proposed activities can be secured by revising security management plans and modifying delivery mechanisms. / Proposed activities can be rapidly adjusted by adaptation of methodology and/or reallocation of targets/resources. / Increased conflict leads to limited Government capacity and national economic collapse Medium Medium Work closely with INGO Forum members, consortium partners and other humanitarian actors to identify short and medium term critical needs. / Use the platform of the Consortium to address rapidly emerging humanitarian needs. / Work with other humanitarian actors to raise advocacy issues in the international arena to support humanitarian response as a result of political and economic instability. / Seek strategies to maximize impact of responses to emerging humanitarian needs that draw on resources and capacities to fill gaps in the absence of government functions (i.e. working with a broader sector of Yemeni civil society organizations). / Lack of access to target areas Medium High Security clearance by the local authorities, community/ tribal leaders and relevant parties / A two pronged community acceptance approach of working with IDPs as well as the host communities, as well as other identified vulnerable groups / Working with female staff in specific areas to reduce security risks and allow access to communities (tribes are reluctant for cultural reasons to target women) / Working with local partners such as YWU who have existing volunteer networks in communities that are difficult to access / Detailed community actor mapping / Outreach strategy, community mobilization and local participation in planning and implementation of the suggested activities / Engage the government and the anti-government forces in providing humanitarian access / Quiet diplomacy to positively influence the Yemeni government for improved access / Increased capacity support and work through partners / Increased frequency of NGO visit to the field for consistent partner support / Recruitment of outreach workers from the target districts / For Al-Jawf: Possibility of moving mobile units to a more accessible area if denied access in one location / Agencies focus on areas where they have strong connections, i.e. agencies are not new to the target population / Security of field staff due to continued fighting and proximity of conflict belligerents and GOY armed forces High High Maintaining established security networks (formal and informal) to facilitate collection of security reports / Security management protocols and plans in place at all CPs. / Local authorities see intervention as a means of supporting anti-government forces Low Medium Continuous dialogue with local authorities explaining the immediate and urgent need for the intervention / The on-going conflict in Sa’ada might delay implementation of project activities Medium Low Some consortium partners have relocated activities to different governorates as a result of security and access issues in phase II / Oxfam (only partner working in Sa’ada in Phase III) has an established presence (field offices) and a good working knowledge in the area / Mine risk Medium Medium Save the Children will provide Mine Risk Education to partners’ staff to mitigate against the risk of landmines/unexploded ordinance / Difficult to hire/retain qualified staff Medium Medium Minimise staff loss by prompt inception of Phase III / Share available resources across agencies – e.g. provision of technical support by sectoral leads, joint training. / Overlapping funding on the side of the consortium partners Low Medium In order to avoid any risk of overlap CPs are committed to transparently share information on their fundraising efforts for complementary action between the partners, with DFID as well as with the wider humanitarian community / Of special importance in this context is the close coordination with the CAP as well as the full integration of this project and its partners under the IASC Cluster system / Capacity Challenges for local NGOs (especially Yemen Women Union, YWU) Medium Medium Consortium partners acknowledge the risk of entering into capacity constraints when working through local civil society actors as implementing partners / CARE is already involved in a comprehensive capacity building project with YWU and other local NGOs, which can complement any ER specific capacity building / CPs will systematically assist field partners in planning their capacities. / CPs will assist YWU and other partners in drafting work plans and resource allocations in a joint planning session at the onset of the Consortium project to mitigate this risk / CPs will immediately select pre-identified alternative partners should the capacities of planned partners be insufficient. / Poor project coordination and leadership undermines project delivery Low Medium Enhanced authority of Programme Management Unit (PMU) / Measure of integration included in logframe to ensure they are monitored / Quarterly monitoring of project by DFID to ensure delivery.
C. What conditions apply (for financial aid only)? / There are no conditions attached to this programme.
D. How will progress and results be monitored, measured and evaluated? / The Project Management Unit described above will be responsible for monitoring the progress of the project. Additionally the dedicated Emergency Programme Officer for the project in CIUK will support the PMU in this. / The Consortium operates a common monitoring and evaluation system with the following components: / common definitions of direct and indirect beneficiaries; / standardised data collection templates for each sector, defining suitable means of data collection for each indicator, frequency and the person responsible for collecting the data; / exit monitoring data sheet and methodology (to measure beneficiary satisfaction of services post-activity); and / quarterly indicator tracking; and monthly progress updates. / DFID has encouraged the Consortium to improve the quality of reporting, bringing together outputs of consortium partners to ensure the logframe can be reported against. In this third phase, sectoral and governorate level monitoring systems and processes will be designed and implemented by the Monitoring and Evaluation Officer in conjunction with sectoral leads. The adoption of common outputs, indicators and activity descriptions in the project logframe will enable greater synergy in monitoring processes and reporting. The consortium will conduct detailed monitoring of implementation, aggregating data by consortium partner, sector, governorate as well as by output-level indicator and overall aggregation at the outcome level. / A detailed monitoring framework and associated processes will be finalised during the inception phase of IERP Phase III. Learning from monitoring and evaluation in Phases I and II will inform the design process. The enhanced authority of the PMU in this phase means that transfer of funds to partners will be contingent on the provision of timely reporting by consortium partners. To ensure a greater level of integration amongst consortium partners, measures of integration have also been included in the logframe and will be monitored during the project’s life-cycle. / Quarterly narrative and budget reports will be submitted to DFID as set out in the Commercial Case of this document. These will be scrutinised by the DFID Programme Manager in advance of tranche payments being made. The Programme Manager will also conduct a standard Project Completion Report within three months of project completion. / In addition to this the project has budgeted for an evaluation. The evaluation of Phase II looked at the Consortium model as well as results delivered by the project. The recommendations from that evaluation, particularly on the Consortium model have informed the proposal for this third phase. This would be the case for any successive phases of this programme. The evaluation will look at similar questions to those for Phase II – understanding the extent to which integration has been achieved and what scope there is for increasing this to realise the full benefits. It would also look at beneficiary satisfaction to evaluate the quality of the interventions.
Lograme / Quest No of logframe for this intervention: 3501729