PROJECT TITLE	CONSULTATIVE GROUP FOR INTERNATIONAL AGRICULTURAL RESEARCH (CGIAR)
GOAL	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + 2013
Greater contribution of agriculture and natural resources to food security, inclusive growth, poverty reduction, and environmental sustainability	Increased agricultural productivity in developing countries (% annual growth).	2008 - zero	0.5% over baseline	1.0% over baseline	1.5% (2013) over baseline
		Source
		FAOStat / ISPC impact assessments / CRP system wide evaluations against performance contracts
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + 2013r
	Hunger and under nutrition in developing countries.	2008 - zero	3% under baseline	6% under baseline	10% under baseline
		Source
		MDG progress against targets UN / CRP system wide evaluations against performance contracts

PURPOSE	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + 2013	Assumptions
Increased relevance and impact of international agriculture and natural resources research.	Regional and National programmes using CGIAR outputs	2008 - zero	5 over baseline	10 over baseline	20 over baseline	National governments, multilaterals and bilateral donors increase their investment in effective agricultural programmes. / Increase in agricultural productivity are related to actual uptake of new technologies and improved policies / Policies (markets, trade, land etc) are conducive to increased agricultural development
		Source
		GFAR and GCARD roadmap updates / Independent evaluation of CGIAR reform impacts planned for 2012/13 (mid term of current SRF period 2010-16) / Annual CPR reports
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + 2013
	Impact studies including productivity changes, environmental benefits, impact on hunger and value for money indicators	2008 - zero	1 over baseline	3 over baseline	5 over baseline
		Source
		Impact studies conducted by ISPC SPIA under Independent Evaluation Arrangement guidelines / Centre and CPR impact assessments / Country and international statistics / FAO reports / Annual CPR and CPR component reports
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£150m		£1,752m	£1,875m	~8%
INPUTS (HR)	DFID (FTEs)
	0.5 Adviser / 0.1 Research Manager / 0.5 B1

OUTPUT 1	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Consortium Research Programmes are generating high quality research outputs contributing to at least one of the system level results areas.	CRPs approved by Fund Council with budget allocations	0 (2010)	2 (2011)	6 (2012)	8 (2013)
		Source
		CGIAR Consortium and Fund Office Reports
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
	M and E framework of CRPs approved by Fund Council.	0 (2010)	0 (2011)	4 (2010)	8 (2013)
		Source
		CGIAR Independent Evaluation Arrangement (IEA) reports
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
20	i) Number of peer reviewed publications from CGIAR / ii) Number of open access publications from CGIAR	i) 2400 (2010) / ii) Baseline	2500 (2011) / + 200 (2011)	2700 (2012) / + 400 (2012)	2800 (2013) / + 600 (2013)
		Source				RISK RATING
		Consortium performance management system				Low

OUTPUT 2	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Climate change challenges addressed across all CGIAR research with specific CC research targeted by CRPs delivering relevant adaptation strategies and solutions.	Annual milestones of CGIAR CRP on Climate Change, Agriculture and Food security met	0% (2010)	80% (2011)	90% (2012)	100% (2013)
		Source
		CCAFs annual reports against Performance Contract / Consortium PMS
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
	Number of CRPs and CGIAR Centres using CCAFS outputs	0 (2010)	2 (2011)	5 (2012)	8 (2013)
		Source
		CPR annual reports / CCAFS component evaluations
IMPACT WEIGHTING	Indicator	Baseline	Milestone 1	Milestone 2	Target (date)
10	Number of National and Regional programmes using CCAFS outputs	0 (2010)	4 (2011)	8 (2012)	12 (2013)
		Source				RISK RATING
		SRO reports / CCAFS annual reports				Low

OUTPUT 3	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Effective mechanisms for CGIAR system-wide support in gender and capacity building.	Consortium gender and capacity building platforms established and operationalised.	Outline of gender and capacity building platforms in the 2011 Strategic Results Framework.	Gender platform operational (2012). / Capacity building platform plans approved (2012)	1st Annual review of Gender Platform demonstrates that the platform is largely on track.	Gender and capacity building platforms fully institutionalised (2013)
		Source

	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
	% approved CPRs with gender and capacity building strategies	0 (2010)	50% (2011)	75% (2012)	100% (2013)
		Source
		CRP annual reports / Gender platform annual reports
IMPACT WEIGHTING	Indicator	Baseline	Milestone 1	Milestone 2	Target (date)
10	Number of fellowships awarded/training undertaken for men and women CGIAR staff / (numbers need to be adjusted to baseline following Capacity building and gender platform frameworks)	2010 / Men 50 / Women 20	2011 / Men 60 / Women 30	2012 / Men 70 / Women 50	2013 / Men 250 / Women 175
		Source				RISK RATING
		Gender platform annual reports / Capacity building annual reports / AWARD reports				Medium

OUTPUT 4	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Governance and structural reforms required to transform the CGIAR into a more effective research for development body are implemented speedily and effectively.	i) System costs as % of overall CGIAR spend / ii) % total CGIAR budget flowing through Fund	i) 2.5% / ii) 0 (2010)	i) 2.0% / ii) 40% (2011)	i) 1.9% / ii) 60% (2012)	i) 1.9% / ii)75% (2013)
		Source
		Fund Office and Trustee Reports / Audit reports / Consortium annual reports
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
	Number of evaluations commissioned by Independent M&E arrangement (IEA)	0 (2010)	0 (2011)	2 (2012)	6 (2013)
		Source
		IEA and Fund Office Reports
IMPACT WEIGHTING	Indicator	Baseline	Milestone 1	Milestone 2	Target (date)
30	% of new agreed operating procedures of Fund and Consortium implemented	10% 2010	60% 2011	80% 2012	100% 2013
		Source				RISK RATING
		Common Operating Procedures for CGIAR (covers issues like managing Fund Council meetings, Trustee Operations, etc) / Two year CGIAR System review				Low