Business Case and Intervention Summary

## Improving the way knowledge on forests is understood and used internationally (KNOW-FOR)

What support will the UK provide?
£20,000,000 over four years from March 2012 to April 2015.

Why is UK support required?
Forests are fundamental to DFID’s development efforts on three fronts. Forests reduce carbon emissions, help reduce poverty in rural communities and protect global and local environmental services such as water, soils and biodiversity. / Developing countries are ramping up their practical efforts to reduce and reverse deforestation and forest degradation on the ground. / Demand has grown for knowledge, evidence and information on international forestry. Policymakers and practitioners wish to know what works best where; and be able to apply that knowledge to what they do. / Forest policies and projects that are poorly underpinned by science and evidence, or do not use the best combination of technology and local know-how, run the risk of repeating and replicating past mistakes; for example, high mortality of tree seedlings in tree planting schemes; poor match between tree species and site-specific conditions; unworkable park conservation projects; limited participation of local people in design and monitoring of projects with subsequent poor project results; and inequitable arrangements for sharing the benefits from trees and forests, leading to lack of care and maintenance of trees and other elements of forest ecosystems. / There are gaps in knowledge. There is a need for, first, systematically gathered and rigorous information that is comparable across sites and countries; second, more knowledge about how forests contribute to livelihoods, poverty reduction and economic development in developing countries; third, measurement of the range of impacts on the ground from projects that aim to deliver Reduced Emissions from Deforestation and Degradation (REDD+); and fourth, understanding about the varying cost of different land use practices and the benefits they provide. Finally, practitioners and policymakers need to know what kinds of financing and investment arrangements work for forests. / This programme will help improve the way knowledge about forests is understood, communicated and used so that decision makers and practitioners working on the remote frontline in developing countries are well-equipped to develop and implement policies and projects that work.

What are the expected results?
The programme will help develop: / At least 120 toolkits, analyses and knowledge products that are mainstreamed into operations and activities in 30 countries; / Application of knowledge on how forests’ contribute to economic development, poverty reduction and climate change increasing by 30% and improving the design and implementation of broader national policies and programmes in 40 countries; / Techniques and practices for forest restoration (the “+” in REDD +) creating healthy landscapes in up to15 countries; / Systematic, rigorous and comparable evidence of what works and what does not in forestry science and practice, which rapidly reaches those who need it internationally and on the frontline. / The programme will promote the use of technology and bring private sector innovation into the process of knowledge dissemination. It will give a high return of £6 for every £1 invested. 382 million tonnes of CO2 equivalent emissions will be avoided by reducing deforestation and sequestering carbon from the atmosphere by restoring forests. £32 million worth of biodiversity and forest ecosystems goods and services will be protected and restored. Incomes or livelihoods (food, fuel, fodder, medicines) worth £46 million to poor people will be generated by the efforts of the initiatives to which this programme will contribute. / Specifically, the programme will fund the development by the Program on Forests (PROFOR) of 120 knowledge activities (toolkits, field notes, publications, videos, etc. that are combined with interactive search-based web learning and face-to-face groups in country). It will mainstream these into the geographic operations of the World Bank, the International Finance Cooperation and other donors, in at least 30 countries. (WB forestry lending portfolio is $200-300m a year, not including the Strategic Investment funds (SIFs).) / It will improve the way the Centre for International Forestry Research (CIFOR) applies knowledge and learning with a focus on (a) the Poverty and Environment Network (PEN), which promotes knowledge of forests’ contribution to poverty reduction based on a network of 50+ partners in 46 countries and thousands of households; and on (b) the Global Comparative Study on REDD+ that tracks the impacts of 200 or so REDD+ projects globally (24 in detail), organising global and local communities of practice around these, with key publications downloaded at least 100,000 times a year. / It will support the Global Partnership on Forest Landscape Restoration, hosted by the International Union for Conservation of Nature (IUCN) to mobilise knowledge on how practically to restore trees into landscapes in up to 15 partner countries across its learning network of academia, governments and civil society. This will mobilise “pioneer investment” in restoration with the aim that 70 million hectares of forest be planted, 50 million hectares of farmland benefit from agro-forestry and silvi-pastoril systems; and 30 million hectares of standing forest be enriched within the timeframe of the programme, with the goods and services from these forest landscapes being worth, using conservative estimates, £182 per hectare to those that live in them[1].
[1] Values for the (non-carbon) goods and services from forest ecosystems vary. For example, £182/hectare/year (The Economic evaluation of biodiversity (TEEB). (2010). UNEP and Lescuyer et al (2007); US$18-697/ha/yr (variously cited in Bush et al; Ferrero et al; beauchamp and ingram; Emerton and Murarira; Mullan and Kontoleon); average income from community forests in Cameroon (US$275-1050/ha/yr estimated by by Beauchamp and Ingram) and in Uganda (US$140/ha/yr by Bush et al). A lower end value has been used for this “scaled up” appraisal and the use of higher values from what may be “honeypot” sites, avoided.

Strategic Case
Context and need for a DFID intervention / Theory of Change / The theory of change behind this intervention is as follows: / Deforestation is a major contributor to global greenhouse gas emissions. International efforts to reduce deforestation are gaining pace and with these efforts demand for high quality knowledge on what makes for effective forest polices is increasing; / The stock of knowledge and research on forests and land use is increasing but at present much of this knowledge is not effectively disseminated and so does not reach practitioners on the ground; / This intervention will improve the value and impact of forestry research by improving dissemination, knowledge pathways, and uptake; / Improved uptake of forestry knowledge will enable policy makers and practitioners to implement effective polices that quicken the pace by which deforestation is reduced. / These steps are explored in more detail in the narrative that follows. / Why forests matter / Forests are fundamental to UK’s global and national efforts on three fronts; reducing carbon emissions, eradicating poverty in rural communities and protecting global and local environmental services such as water and biodiversity. / Forests are central to the world’s carbon budget; on the plus side (as “carbon sinks)”, standing forests remove 2.4 billion tonnes of carbon per year from the atmosphere (equivalent to one third of annual emissions from burning fossil fuels). In addition tropical forest regrowth can purge 1.6 billion tonnes of carbon from the atmosphere a year. On the minus side (as an “emissions source”), deforestation is running at about 13 million hectares a year, emitting 2.9 billion tonnes of carbon a year (with total annual human-induced emissions currently at just above 10 billion tonnes of carbon)[2] The Intergovernmental Panel on Climate Change states that deforestation is now the ‘single most important source of emissions’.[3] Together deforestation and forest degradation account for about 17% of human-induced global greenhouse gas emissions, more than the entire global transportation sector and second only to the energy sector. / The UN REDD+ programme[4] asserts that it will be practically impossible to constrain the impacts of global climate change within limits that society can reasonably tolerate without reducing emissions from the forest sector, in addition to other climate mitigation actions.[5] A framework for REDD+ is likely to be included in a post-2012 global agreement on climate. Avoiding future deforestation, reducing deforestation now, and restoring forests on degraded land to stop the net forest carbon budget tipping from “sink” to “source” is a hugely important global challenge[6] with action on forests being an important way of reducing emissions in the immediate term. [7] / Forests contribute directly to the livelihoods of 90% of the 1.2 billion people living in extreme poverty and are a cost-effective way of tackling poverty.[8] The Amazon forest, for example, provides 10 million poor forest dependent people with between US$500 million and US$1 billion a year from the goods they catch and harvest.[9] Forests and trees regularly contribute between 20-30% of rural household incomes[10], a contribution often unrecognised by policy makers, and worth about $130 billion to the rural poor.[11] In Nepal it cost UK aid about £35 to bring one person out of economic poverty by developing forest-based livelihoods.[12] / Forests also provide immensely important environmental services “such as maintaining soil stability, protecting water flow and quality and serving as the repository of the bulk of the world’s terrestrial biodiversity”.[13] While forest degradation and deforestation cause a loss of $1.9 trillion to $4.5 trillion in ecosystem goods and services,[14] restoration of forests in the landscape can also build back what has been lost and bring additional benefits. / The United Nations Framework Convention on Climate Change conference of the parties held in Durban in 2011 (UNFCCC COP17)[15] also highlighted the potential that restoring up to 2 billion hectares of lost forests and degraded lands worldwide (an area the size of South America) had for enhancing carbon stocks. In Durban key figures championing the “plus+” in REDD+[16] cited evidence that this area could sequester up to twice as much carbon as avoided deforestation,[17] benefit poor forest dependent people,[18] improve soil and water conservation, and benefit plant and animal life (biodiversity).[19] / Efforts to address deforestation at country level are gaining pace / Countries are ramping up practical efforts to reduce and reverse deforestation and forest degradation on the ground. The commitment made by Ghana in 2007 to tackle the underlying ‘drivers’ of illegal logging and unplanned forest clearance[20] in its Forest Law Enforcement Governance and Trade Voluntary Partnership Agreement (FLEGT VPA) has expanded in 2011 to include ten countries[21] that have signed up to the EU Forest Law Enforcement Governance and Trade (FLEGT) Action Plan. / A group of multilateral development banks, in which the World Bank participates, are implementing the Forest Investment Programme and the Forest Carbon Partnership Facility (FCPF), which are targeted programmes of the Strategic Climate Investment Fund (SCIF). Eighteen countries have been developing REDD+ Readiness Preparation Proposals (R-PPs) with support from the Forest Carbon Partnership Facility (FCPF), with seven R-PPs completed to date.[22] (R-PPs lay out a roadmap of activities for achieving a national state of “readiness” or “preparedness” to deliver REDD+). / The Forest Investment Programme (FIP) has endorsed the forest investment plans of five countries,[23] with a number of these including forest restoration. / Other countries, including Rwanda, Brazil, Indonesia and China, have also joined in a Global Partnership on Forest Landscape Restoration (GPFLR) that seeks to mobilise knowledge about the practice of restoring landscapes as well as seeking to avoid unplanned forest clearance. / The Strategic Climate Investment Fund (SCIF) portfolio on forests is dwarfed by the additional mainstream World Bank investment in forestry, which amounts to $200 to $300 million of forestry lending disbursed every year over the past 10 years.[24] / In addition, beyond the investment supported by the World Bank, the number of forest and land use initiatives has grown to more than 200 formally registered REDD+ country level projects. However, these tend to be small, short term projects, often delivered through ‘third parties’ or proxies resulting in a fragmentation of initiatives both within and across countries. [25] / Knowledge on forestry is key to success and demand for it is growing / With increased investment and a proliferation of efforts on the ground, the demand for high quality, evidence-led information and reliable tools that are ready for use and application, is in high demand. There is demand, in particular, for well-founded evidence that goes beyond the anecdotal, that is systematically gathered, rigorously documented and can be aggregated and compared across sites and projects. / Forestry and tree research, innovation and analysis can achieve very high rates of return of 40%.[26] A further study on benefit /cost ratios in a range of countries (where natural assets provide an important contribution to the local economy) estimate that research and development (R&D) provides a return of between £5 and £50 for every £1 invested.[27] For the returns to research to be realised, however, research findings need to be applied and, in the case of forests, the public need to be engaged in their application. / Knowledge about how to improve forest and land-use management internationally is a “global public good”, that is to say, it contributes to development and can “provide benefits for an increasing number of people without incurring additional marginal costs”. Public support for knowledge, combined with private support, can help ensure that poor people and countries are not “excluded” from benefiting from knowledge and can also help “increase the pace of innovation” more broadly.[28] / A thematic paper on international forestry and climate presented to the UK’s International Climate Fund (ICF) Board in March and June 2011 identified the lack of knowledge uptake in countries as a major constraint underpinning the international community’s ability to effectively reduce deforestation and degradation. / Knowledge is critical for rational decision-making / Decision-makers will not make economically rational decisions if they do not have reasonable access to robust evidence.[29] Un-informed policy and programming leads to ‘hit and miss’ results on the ground, putting at risk the credibility and progress of major international efforts to reduce emissions ( REDD+) and improve the way forests are governed and their goods and services are marketed. (FLEGT or Forest Law Enforcement Governance and Trade). / Information is of particular importance when it comes to the goods and services that forests provide as their value is not accurately reflected in their prices and some are “intangible” or, as yet, have no market price. The availability of quantified, comparable and agreed information on the value of forest goods and services, on how these benefits can be captured, and on how forests can be managed and financed to realise these benefits, is key for effective decision-making. / By addressing the way international forestry knowledge is understood, communicated and used, this programme will enhance the strategic nature and effectiveness of the overall international forestry and climate effort. It will support a more systematic approach than has been taken in the past, and focus support to those institutions that are pre-eminent in the field of forestry knowledge internationally. It will tackle the specific risk of poor decision making by frontline policy makers and practitioners. It will address weaknesses in existing knowledge uptake pathways by applying new approaches. / By improving the routes and flows by which technology and information gets into the hands and minds of practitioners, the programme will enable them to put knowledge to use. / An allocation of up to £20 million to the programme over the next four financial years (2012-15) will be made from UK’s International Climate Fund (ICF) to mainstream knowledge and tools into international forestry and REDD+ policy making and operational programmes in developing countries. / Rules-based forestry versus knowledge-based forestry / The forest sector is highly regulated and until recently prevailing practice has been ingrained in long-standing legal, financial and procedural frameworks and professional cultures. This underpins “business as usual”, with many decisions based on rules rather than on evidence. Uptake of new knowledge based on best practice is critical to ensuring that the momentum for change over the past 5 to 7 years is sustained. / Complexity / Knowledge uptake pathways for the forestry sector are more complex than, for example, for arable crops (like rice) due to the longer productive cycle of trees and forests. Furthermore, in order to capture the broader returns and impacts of forests’ contribution to water and biodiversity conservation, this requires the use of highly sophisticated impact assessment techniques. Finally, natural resource management technology, unlike genetic grain crop improvement, involves a complex combination of “embodied technology” (e.g. seeds, plants) and “disembodied” technology (e.g. management rules and strategies).[30] / In some cases, while knowledge on one aspect may be available, its impact is limited by lack of knowledge on another; for example, while a seed bank may be available, there may be lack of knowledge on how to get private investment flowing into tree regeneration. Much of knowledge in forestry and land use management needs to have a range of elements “packaged” together and complex processes and techniques may need to be communicated as simple steps for successful uptake. (See http://www.profor.info/profor/knowledge/mobilizing-private-investment-trees-and-landscape-restoration) / Many tools and frameworks, however, have immediate practical application, such as the national forest landscape restoration assessments developed by the International Union for Conservation of Nature (IUCN) or the poverty and social impact toolkits developed by the Programme on Forests (PROFOR). / Critical, well placed knowledge / Key knowledge products can change mind sets internationally. The first global maps and spatial imagery drawn together by the World Resources Institute (WRI), the Programme on Forests (PROFOR) and the International Union for the Conservation of Nature (IUCN) showed not just where forests are being lost, but where they can be regained; and shifted world opinion. / Connecting globally and locally / However, this needs to be complemented by knowledge uptake pathways that can reach and be applied to local realities. For example, global maps, when combined with further studies by PROFOR[31], helped shift the view of the World Bank geographic operations or country level investments in forestry and also influenced regional and national players in their own decision-making. / Local know-how can also combine with globally generated information to create knowledge products that are powerful. A study[32] for the Global Partnership on Forest Landscape Restoration concluded that local members wished to share knowledge globally of specific restoration site techniques, learn more about financing options from others, test more widely a globally generated approach for national assessment frameworks in their own countries, with 90% responding to a survey wishing the network to continue its knowledge operations. / Specific knowledge gaps / There are a range of specific knowledge gaps: first on the approaches and methods for reducing carbon emissions through avoided deforestation and by enhancing forest carbon stocks; second, on ways to mobilize private investment and capital into forests and practices that avoid or reverse deforestation; third, on how forests help reduce poverty and contribute to peoples’ livelihoods, including the very different ways they benefit men and women; fourth, on the technologies to apply to different ground conditions; fifth, on the embedding of forests and climate in mainstream national policy for broader economic development and growth. / Specific knowledge gaps Lack of :- / 1. Mapping and monitoring deforestation and forest carbon emissions levels Basic information and methodology for establishing emissions reference levels and monitoring baselines. / National forest inventory data (forest carbon inventories require at a minimum forest stock data). Where inventories are held, over 40% of them are over 10 years old[33] and require updating to internationally agreed standards. However, past experience shows that inventory data gathering has had limited impact in the past as it has not fed into or properly influenced policy and decision-making processes.[34] / Global comparative evidence of what incentives, types of project and policies work or do not work and their corresponding impacts on REDD+. / Information on what local practices might meet REDD+ compliance criteria (as and when these are agreed internationally) / 2. Mobilising private sector finance into enterprises for better forest and land use management Innovation in financing which combines the disparate perspectives of investors, governments, insurance companies and foresters. / Use of forest governance benchmarking in rating and assessing investment risks. / Identification of the capital constraints suffered by small and medium forest enterprises. / Ways to integrate business associations into partnerships, for example, “clustering” or “bundling” enterprises together with financial investment and business services, certification against standards and technology transfer, to reduce risk and increase economies of scale. / Ways to contract in private investment for restoration, / 3. Forests contribution to poverty reduction and poor peoples’’ livelihoods Understanding of the conditions under which, for example, community forestry leads to increases in family income and better livelihoods.[35] / 4. Tools and site-specific technologies and techniques Proven techniques and technologies for forest management, conservation and restoration across varying types of forest and types of landscape. / 5. Getting forests and climate embedded into broader national policy formulation and implementation Mainstream understanding of how deforestation impacts on poverty and economic development in the short and long term. / Systematic evidence amongst national practitioners about the competitiveness, viability and sustainability of different types of forest and land use enterprises. / Understanding what changes in regulation, market and economic policy will move agricultural expansion from “greenfield” to “brownfield” sites. / General knowledge constraints / There are also significant general knowledge constraints to overcome; first, the occasional disconnect between the knowledge held by those who frequent international arenas and the realities on the ground; second, insufficient expenditure on knowledge uptake and exchange as compared to basic research; third, limited use of interactive communications technologies and approaches in the forest sector. / Although the costs of outreach and mainstreaming of information and knowledge into in-country and field-based operations have traditionally been high with forests located in remote areas, there is evidence of a shift in approach to knowledge exchange and uptake by the forestry sector. For instance, UK Forestry Commission Research has recently agreed a ratio of knowledge generation to knowledge exchange of 75:25 while PROFOR estimates it’s spend on dedicated knowledge dissemination has improved to nearly 20% in the past 18 months. CIFOR has also recently moved to a new Knowledge Sharing Model[36] (away from a traditional one-directional communications model to a new ‘viral’ or ‘hurricane effect’ model with numerous impact pathways to many stakeholders) with positive and measurable results.[37] / General knowledge constraints Lack of:- / 1. Knowledge not reaching the people it needs to reach. Knowledge management systems within developing country forestry sectors that help frontline staff and policymakers navigate a plethora and diversity of fragmented evidence and case studies.[38] / 2. Expenditure disproportionately weighted towards research over practitioner uptake[39] Dedicated professional communications expertise to develop appropriate dissemination methods and uptake pathways, thereby increasing agencies’ abilities to effectively mainstream analytical and research work / Resources dedicated to monitoring the impact of knowledge dissemination. / 3. Cost effective communication and knowledge technologies Two-way interactive, query-based sites with a client-focus (as opposed to one-way passive global web-based dissemination). / Use of local social networks as well as face-to-face approaches. / Use of hand held telephony, information and mapping. technologies that can reach an increasing number of individual consumers’, including in Africa. / The niche this programme fills / This programme will not directly provide finance to early stage or basic research on avoided deforestation or forest restoration. It will not support development of scientific “proof of concept”.[40] A proof of concept is a “prototype”, for example, a new tree species or fabrication technique or mapping technology, which demonstrates some feasibility and potential of being used, but stops short of being an early version of a production design / This programme will support the later stage of generation, deployment and application of knowledge. This is the stage where there is greater certainty that the technology works in a development context and greater opportunity to partner with private sector in its application. The programme will work, in other words, on “proof of development”. For example, it will work at getting the right information about a tree species into the hands of staff and enterprises on the frontline in a developing country. This will be a species already “proven” to grow well in a particular humid or dry condition and particular soil type. That knowledge will be packaged together with other information on how that species germinates, needs to be planted and cared for it, as well as what its market opportunities or soil fertilising properties are. This packet of knowledge or “knowledge product” will be communicated in a timely fashion (i.e. before planting season) to ensure practical uptake of that knowledge or technology. / The programme complements, but does not substitute for, the core financial contributions that DFID’s Research and Evidence Division (RED) makes from DFID’s research budget to basic scientific research by the Consultative Group in International Agricultural Research (CGIAR) [41] and UK’s National Environment Research Council (NERC). / The programme will not start from scratch. In 2009 DFID’s Climate and Environment Department provided a small 3 year grant to the Center for International Forestry Research (CIFOR) to initiate a Global Comparative Study on REDD+, including publication of the first guidance books on REDD+ (e.g. “Realising REDD+: National Strategy and Policy Options”[42] that has been downloaded 200,000 times). Prior to that DFID provided some finance to help establish a large database of thousands of households as part of the Poverty and Environment Network (PEN). This programme expands on that work, as well as on the knowledge activities of the Program on Forests (PROFOR), to which DFID made a contribution in 2010 to help mainstream these into the country operations of the World Bank and other donors. Similarly, the programme will build on pilot work, supported by the Forestry Commission of Great Britain, to develop and test assessment approaches for forest landscape restoration. / A significant amount of research has been done or is underway. Some of this is “tacit” knowledge, which is written down and inventoried. However, much important knowledge about forests is “explicit” and is based on accumulated practical experience. The theory of change underpinning this programme is that tacit knowledge can result in behavioural change, namely improved forest and land-use management, if it is broadcast to the world’s public through more, better and smarter media, documentation, publication, packaging and promotion. However, for explicit knowledge to result in changed behaviour this requires public engagement. The understanding and behaviour of policy makers and forest managers will change if they engage in collaborative working practices and “learning networks”. However, public engagement can be supported in private partnership which brings new technology and innovation into the way networking happens and information shared. This programme will work on both aspects of tacit and explicit knowledge.[43] A separate and distinct project on “forest governance, markets and climate” is already working to change incentives and rules and will fit alongside this new knowledge programme. / Working with other donors / For the period 2008-2010 Norway was the largest forestry donor (28% of total international forest finance), followed in order by Japan (21%), Germany (9%), Finland and, the European Commission, Australia and UK.[44] UK’s contribution to the organizations proposed as partners in the appraisal for this “knowledge” programme would average about 7% of total overall collective budgets of those partner organizations. Other donors are likely to include Norway (roughly similar order of magnitude), the European Commission, Australia, UK, Finland, France, USA and Germany. Entry of potential new donors in the future could reduce the UK percentage of total contributions, such as Korea, Brazil and private donors (like the Fidelity Charity Foundation, the Cristensen Family Foundation, and the Climate Works Foundation). / Overall private investment in forestry tends to be larger than public domestic and ODA investment. A key challenge for the partners in this programme will be to leverage some of this private investment into improved knowledge and technology for more sustainable management of forests and land use. They will do this through joint ventures that bring private sector thinking and finance into the ways technologies are developed and used (while ensuring these develop international private goods and do not create conflicts of interest with respect to forest access). / A clear pathway linking knowledge generation to impact, combined with baselines, is described in the Management case (below) and will allow evaluation of whether results from interventions can be attributed to the UK’s finance.[45]
B. Impact and Outcome that we expect to achieve; and evidence for it / A logical framework for this business case is included in Annex 1 / Impact / The programme will contribute to the global impacts of poverty reduction, biodiversity conservation and climate protection through improved management of forests. / Despite considerable investment in international policy oriented research and analysis, the lack of corresponding investment in impact assessment has created some uncertainty about the effectiveness of policy research and analysis in delivering development goals. However there is evidence that where attention is paid to making findings “visible” and to identifying and using “uptake pathways”, knowledge generated through forestry research and analysis can deliver major, and extremely cost effective, impacts on avoided deforestation. / A thorough assessment[46] of the impact of CIFOR’s policy research into the political economy of the Indonesian pulp and paper industry, which was carefully targeted towards informing investment in the sector, concluded that CIFOR’s work had resulted in an averted loss of between 76,000 and 212,000 hectares of natural forest, depending on assumptions applied, with 135,000 hectares of natural tropical rainforest saved under the main set of assumptions. Much of the savings were in areas of deep moist peat, with more than 1,000 tonnes of carbon stored per hectare, and in areas of high biodiversity. Economic benefits attributable to CIFOR, and which principally resulted from reduced carbon emissions, were determined as ranging from $19 million to $583 million, depending on assumptions used, with a main estimate of $133 million (discounted US dollars). In the context of less than half a million dollars of direct research costs, this represented an exceptional return on investment, and illustrates the potential effectiveness of targeting knowledge to specialized press and other information channels. / It is estimated in the appraisal below that the knowledge generated by this programme will help increase the household incomes or livelihoods (food, fuel, fodder, medicines) by £46 million. / Outcome / The desired programme outcome is that policymakers and practitioners in developing countries are equipped with strategic knowledge, comparable evidence, reliable tools and systematic analysis on forests and climate. This in turn reduces forest degradation and deforestation, and enables successful forest restoration and management of the goods and services forests provide to poor people. / Outputs / The expected outputs from the programme are: / At least 120 toolkits, analyses and knowledge products that are mainstreamed into operations and activities in 30 countries; / Application of knowledge on how forests’ contribute to economic development, poverty reduction and climate change increasing by 30% and improving the design and implementation of broader national policies and programmes in 40 countries; / Techniques and practices for forest restoration (the “+” in REDD +) creating healthy landscapes in up to15 countries; / Systematic, rigorous and comparable evidence of what works and what does not in forestry science and practice, which rapidly reaches those who need it internationally and on the frontline. / There is considerable documented evidence that information, analysis and research findings on forestry and land use have influence and are used to good effect, if they are communicated well by strategically placed bodies through an intelligent mix of media and collaborative working. Evidence shows that new information technology allows for more diffuse and extended uptake of knowledge products that can be accessed or “surfaced” at need beyond the usual “retirement” or “shelf” life of printed information. PROFOR progress reports indicate that, with use of new technology, demand for individual knowledge products, increased overall, with greater demand for more products in more themes, and continued demand for some “old” products produced prior to 2009. However, CIFOR annual report 2011 argues that effective public engagement often requires the use of more traditional mass media as well as face to face working. / Putting in place effective and efficient financing from public and private sources and business arrangements at global, national and local levels, will be at the heart of future success in protecting forests and REDD+. Knowledge on finance will be critical. Findings[47] from two case studies show that, where effective mechanisms to share the benefits from forests and REDD+ were established, community returns increased by £200/community/year in the first case and in the second from about £12,000 to £60,000/year after 4 years. (See http://www.profor.info/profor/knowledge/making-benefit-sharing-arrangements-work-forest-dependent-communities). / Work through the “Forest Enterprise Connect” network that links small and medium forest enterprises and business service providers convinced donors and government agencies in Burkina Faso, Malawi and elsewhere to support non-timber forest enterprises. It helped rollout results from a small village tree enterprise project, established by the non-governmental organisations (NGO) TREEAID in Burkina Faso and Phytotrade in Malawi on better marketing of “baobab powder”, (processed from baobab tree seeds, developing a local market of 100 tonnes in Malawi in 2011; and ensuring the product was approved by European food safety standards so it could enter international markets.See videoclip on the Program on Forests (PROFOR) website at http://www.profor.info/profor/notes/trees-private-sector-carbon-credits-and-baobab-powder.) / In Nepal the Forest Connect web directory (http://www.ansab.org/fcn/smfedatabase.php) made available detailed information on 872 small forest enterprise producing: ayurvedic clinic services, essential oil, furniture, handmade paper, health and beauty care (including shea butter), input supplier, natural fibre, trading in non-timber forest products, such as resins, turpentine, spices and silk. The site provides monthly price information for 32 products in 6 different markets. / This is mobilising in Nepal value-adding investment in forest product market chains of about US$6 million, and in Burkina Faso of US$20 with the total cost of Forest Connect network in 8 countries over four years being an estimated US$400,000. Cost: benefit ratios for specific country examples ranged from 1:14 to 1:75 in estimates by the Programme on Forests (PROFOR) that has supported Forest Connect.[48] / A recent independent evaluation of PROFOR’s overall knowledge activities concludes its knowledge generation and deployment is “high quality and effective”, achieving “impressive results and impacts from relatively modest financial resources in critical regions”.[49] With every pound PROFOR puts into a knowledge activity, it mobilises a further 90p of additional finance. [50] / Recent publications have either initiated international debate or swayed it. The cover article in The Economist (September 2010) “The World’s Lungs: Forests and How to Save Them” received the Grantham prize for supporting the environment, with a third of sources cited from the Center for International Forestry Research (CIFOR). (See http://www.economist.com/node/17093495 ) / The PROFOR- financed book “Rising Global Interest in Farmland: Can it yield sustainable and equitable benefits” was launched by President Zoellick in September 2010 is the first significant peer-reviewed work on land acquisition. .PROFOR’s publication on “Forests and Fragile States” contributed to the World Development Report 2011 and its “Forest Sector Public Expenditure Reviews” toolkit has been widely distributed as a seminal handbook for national forestry agencies. / In 2011 CIFOR Global Comparative Study on REDD+ developed an approach for setting Reference Emissions Reduction Levels (RELs/RLs) (partly funded by the UK Department for Energy and Climate Change (DECC)). This demonstrated how the approach would work in Brazil, Cameroon, Indonesia and Vietnam using models that incorporated economic drivers, and were based on available data. This was presented to the negotiators and other stakeholders at an expert meeting in the Durban Climate Change conference and formed the basis for the text in decisions by the United Nations Framework Convention on Climate Change (UNFCCC)’s Subsidiary Body on Science and Technology Assessment (SBTSA). / Most of the REDD+ Readiness Preparation Proposals (RPPs) submitted by countries to the Forest Carbon Partnership Facility include “evidence of having used PROFOR analysis and tools”[51]. For example, Congo Basin countries (Cameroon, Central African Republic, Gabon, Democratic Republic of Congo, Equatorial Guinea and Republic of Congo) cite the study on the major drivers of deforestation and forest degradation in the Congo Basin. / A tool for assessing the potential for forest landscape restoration in different countries, as well as globally, has been developed using spatial maps and other knowledge. (See http://www.profor.info/ profor/knowledge/assessing-potential-forest-landscape-restoration). This was used at a Ministerial meeting in Bonn, as well as of The Subsidiary Body on Scientific, Technical and Technological Advice to the Convention on Biological Diversity (CBD)),[52] to provide a clear way forward and mandate for the “Global Partnership on Forest Landscape Restoration” (GPFLR)[53]. Its homepage is at http://ideastransformlandscapes.org/). / This Partnership is starting to create a critical mass of opinion makers, including former Prime Ministers and Airbus Industries, about the opportunities in forest landscape restoration. (See http://www.airbus.com/newsevents/news-events-single/detail/airbus-becomes-ambassador-for-global-restoration-council-and-coalition/) It does not fund the actual implementation of restoration on the ground, but helps partners mobilise “pioneer investment” into country initiatives (for example, it has helped secure finance from the German Senate of the Economy for country level investment). / The Forestry Commission of Great Britain, which helped establish the Global Partnership on Forest Landscape Restoration is exploring with Kew Gardens ways to reinforce UK's involvement with specialised technical expertise and skills. / In November 2011 the Brazilian Mata Atlantica Restoration Pact (a group of government, civil society and private sector representatives) assigned IUCN as country “knowledge focal point on restoration.” Rwanda asked the Global Partnership on Forest Landscape Restoration to help it develop a “border to border” landscape restoration initiative that ”builds an accessible knowledge base on forest landscape restoration in Rwanda”.[54] / The Indian Forest Service has offered to share with other countries its successful examples of forest restoration in 6,000 hectares of watersheds in Madhya Pradesh, Orissa and Uttarakhand, as well as how it restored 10,900 hectares of formerly degraded land which used to contain 25 mines[55]. / The Scottish Forest Alliance of BP, Scottish Woodland Trust, Forestry Commission and the Royal Society for Protection of Birds is also an example that forms part of the Global Partnership on Forest Landscape Restoration. This brings together communities, companies, government and business across 14 locations in a Scottish landscape restoration project planned for 200 years to bring back 11,600 hectares of native forests for the local people. (See http://www.scottishforestalliance.org.uk/) / The UN Food and Agriculture Organisation (FAO) plays a key role in helping countries monitor and assess their forest resources. Increased finance for climate change, increased private investment in forests locally and new field approaches combined with modern mapping technologies are already enabling the update of formal forest inventories. A forest inventory is the systematic collection of data on forests and estimates the volumes, distribution and diversity of forest resources, ranging from timber to wildlife and lately carbon stocks. Usually forest line agencies and companies are responsible for collecting this information nationally and locally, with FAO consolidating globally. UK will be supporting improved monitoring and indicators for forest and climate assessment under a separate, although related, programme of work and Business Case. / However, past experience shows that where forest inventories and assessment do exist, they do not necessarily translate into well-informed guidance that is then used in decision-making for either policy or practice. Much forest resource information that is publicly disclosed is “politicised”. As FAO stated in 2002 “The situation cannot be remedied by introducing or improving national forest inventories and related data gathering. It is necessary to consider the role of information more broadly in the policy process and at all stages of it.”[56] / There is a significant body of published evidence which shows that generally a “lack of appreciation of the dynamic relationship between data, information and knowledge leads to mistimed and ineffective policy interventions that do not result in the hoped for progress in science intended to underpin policy.”[57] The literature is also littered with examples where using a combination of independent and collaborative approaches to deploy and apply already existing knowledge has helped overcome some of the barriers of “politicisation”, often associated with forests and land. This by has helped avoid repetition and replication of past mistakes, for example, high mortality of tree seedlings in tree planting schemes[58]; poor match between tree species and site-specific conditions; over estimation of timber volumes, unworkable park conservation projects; limited participation of local people in design and monitoring of projects with subsequent poor project results; and inequitable arrangements for sharing the benefits from trees and forests, leading to lack of care and maintenance of trees.
[2] Pan et al. A Large and Persistent Carbon Sink in the World’s Forest. Science. 14 July 2011: These figures are carbon stock data. A rough assumption has been made in this Business Case about CO2e emissions as follows: Total human-induced emissions: 13 billion tonnes C roughly equivalent to 48 gigatonnes CO2e; Emissions from deforestation: 2.9 billion tonnes C roughly equivalent to 10 GT CO2e..
[3] IPCC 4th Assessment Report. Climate Change 2007. Intergovernmental Panel on Climate Change
[4] United Nations programme for Reduced Emissions from Deforestation and Degradation – with deforestation referring to forest clearance, degradation to logging and other damage and the + referring to increasing carbon stocks through forest management, afforestation and reforestation – or increasingly forest restoration
[5] www.un-redd.org/AboutREDD/tabid/582/Default.aspx
[6] Avoiding future deforestation in High Forest cover - Low Deforestation rate (HFLD) countries like Democratic Republic of Congo Guyana, Suriname; reducing deforestation now in High Forest cover - High Deforestation rate (HFHD) countries like, Brazil, Bolivia Cambodia, Malaysia Indonesia; and restoring forests in Low Forest cover – High Deforestation rate (LFHD) countries like Cameroon, Ghana and Liberia. Prepared for the Government of Norway by the Meridian Institute. REDD: An Options Assessment Report (REDD-OAR). 2009
[7] Intergovernmental Panel on Climate Change (IPCC). 2007. Annual Report 4/AR4. (Mitigation in the Short Term (until 2030)
[8] Sustaining Forests: A World Bank Strategy (World Bank, 2002)
[9] The Economics of Ecosystems and Biodiversity (TEEB), UNEP (2010)
[10] Angelsen, A. 2011. Poverty Environment Network (PEN). CIFOR
[11] Shepherd, G. 2011. Livelihoods and Landscapes Strategy. IUCN
[12] Community Forestry for Poverty Alleviation: How UK Aid Has Increased Household Incomes in Nepal’s Middle Hills. Household Economic Impact Study 2003 to 2008, Livelihoods and Forestry Programme, 2009
[13] Sustaining Forests: A World Bank Strategy (World Bank, 2002)
[14] The Economics of Ecosystems and Biodiversity (TEEB), UNEP (2010)
[15] Opportunities for Non Carbon Benefits of REDD+ event organised by the EC Directorate General for Climate Action, Convention on Biological Diversity, Federal Ministry for the Environment, Nature Conservation and Nuclear Safety, Germany, IUCN, World Bank. Cop 17, Durban 2011
[16] ‘Restoring 150 million ha of degraded land represents an exciting and largely untapped opportunity to create more jobs and economic growth while protecting our climate.’Goren Persson (former Swedish Prime Minister). Bonn Challenge Ministerial Roundtable. September 2011
[17] Faststartfinance.org website managed by the Government of The Netherlands; supported by Colombia, Denmark, Germany, Indonesia, Marshall Islands, Mexico, Norway, the United Kingdom and Vietnam and in consultation with UN Framework Convention on Climate Change (UNFCCC), UN Environment Programme (UNEP), UN Development Programme (UNDP) and The World Bank.
[18] Making Benefit Sharing Arrangements Work for Forest Dependent Communities – Insights for REDD+ Initiatives. Policy Brief (on work in progress). PROFOR, 2011
[19] The UN Convention on Biological Diversity (CBD) has agreed on a target to restore 15 percent of degraded ecosystems by 2020.
[20] Combating illegal logging and corruption in the forest sector, World Bank (2006)
[21] For status of countries in the EU Forest Law Enforcement Governance and Trade (FLEGT) Action Plan see www.euflegt.org
[22] FCPF Dashboard of country status (revised 8th November 2011) http://www.forestcarbonpartnership.org/fcp/ UK government is a contributor to the FCPF
[23] http://www.climateinvestmentfunds.org/cif/fip_pilot_programs. UK government is a contributor to the FIP.
[24] World Bank, personal communication, 2012 (Table: Total Forests Commitments and Disbursements FY01-11)
[25] Financing Flows for Forests”. Simula. (2010). PROFOR/UNFF
[26] “A Meta-Analysis of Rates of Return to Agricultural R&D” (2000) Alston et al. IFPRI found that rates of return to agricultural research varied with 40-60% being the norm and forestry and natural resources having longer production cycles being at the lower end of the range. “International Research on Natural Resource Management – Advances in Impact Assessment” (2007).
[27] Waibel et al. CABI/FAO; A study by Alston in 2010 evaluates ex-post benefit:cost ratios of between $10 and $70 to agricultural R&D with the higher returns found in States where natural assets played an important part in the State economy and lower ratios where agriculture was shrinking as a contribution (Alston .J (2010)..”The benefits from Agricultural research and Development, innovation and productivity growth.” OECD Food, Agriculture and Fisheries Working papers, No 31. OECD Publishing; Further work in Austrial can be found in hearn, S. (2011). “Benefit/Cost Impact of Australian Research Partnerships. ACIAR.
[28] Stiglitz, J.E.. 1999. “Knowledge as a Global Public Good”. In: Global Public Goods: International Cooperation in the 21st Century, Inge Kaul, Isabelle Grunberg, Marc A. Stern (eds.), United Nations Development Programme, New York: Oxford University Press, 1999, pp. 308-325. Also published in International Intellectual Property in an Integrated World Economy, F. Abbot, T. Cottier, and F. Gurry, eds., Aspen Publishers, 2007
[29] ## Pullin, A. 2011. “International funding for forestry and environment policies based on weak evidence”. University of Bangor
[30] “A Meta-Analysis of Rates of Return to Agricultural R&D” (2000) Alston et al. IFPRI; “International Research on Natural Resource Management – Advances in Impact Assessment” (2007). Waibel et al. CABI/FAO.
[31] Wells et al. PROFOR. (2011)
[32] Wageningen Centre for Development Innovation. Report of a consultancy on the assessment of forest landscape potential., October 2010
[33] The Eliasch Review, 2008
[34] Janz and Persson, (2002):
[35] PROFOR Work Program and Knowledge Projects carried out in 2011
[36] The new model had its origins in CIFOR’s 2008-2018 Strategy.
[37] In 2011 after the launch of the new CIFOR model and website, traffic to the site increased by 35% and page views climbed by 300% or 3.5 million pages. The number of followers on their Facebook and Twitter pages has increased from roughly 300 to 2,600 daily.
[38] Research Communications and Uptake Survey; Unpacking the Results”. (2010). Research to Action (R4D)
[39] For instance, in its 2005 Science and Innovation Strategy, UK Forestry Commission Research identified the problem of a ‘disconnect’ between research and practitioners. The Strategy acknowledges that there is a trade-off between funding research and funding knowledge exchange, but increasingly since 2005 the FC firmly believes ‘that knowledge exchange is important and we will make that trade off.’ (Jason Hubert, FC Research, per comm to DfID appraisal).
[40] . Finance for this is channelled through a single fund to the CGIAR (originally the Consultative Group on International Agricultural Research) an alliance that unites international organizations involved in agricultural science with a major emphasis on arable food crop research. The DFID Ecosystems Research for Poverty Reduction (ESPA) partnership with the UK Natural Environment Research Council (NERC) finances very limited forestry research. The Darwin Initiative, managed by Defra, support a number of small conservation and biodiversity projects, with some element of capacity building.
[41] The fund capitalisation reached $330m in 2011, with the research budget of the 15 centres requesting a total of $1 billion a year - the grain variety research centres (rice, wheat, maize) being the largest centres. See http://www.cgiarfund.org/cgiarfund/
[42] Angelsen, A.; Brockhaus, M.; Kanninen, M.; Sills, E.; Sunderlin, W.D.; Wertz-Kanounnikoff, S.; (eds.). 2009. “Realising REDD+: National Strategy and Policy Options”. CIFOR
[43] Networks Reconsidered. Hagel J. et al. Harvard Business Review. January 2010,
[44] OECD DAC Statistics, January 2012
[45] “The Magenta Book: Guidance for Evaluation” (“01).HM Treasury Crown Copyright
[46] Assessing the Impact of CIFOR’s Influence on Policy and Practice in the Indonesian Pulp and Paper Sector. David A. Ratzer. CIFOR Impact Assessment Paper (2008). This impact assessment used key informant interviews to trace contributions of this research to impact pathways via civil society, government agencies, donor agencies, financial institutions and the Indonesian pulp and paper industry. Document review and time series statistical tests were used to triangulate interview results.
[47] PROFOR staff, per comm
[48] ISource: IIED. 2011
[49] Wells et al, 2011. PROFOR
[50] EU Monitoring Report on PROFOR. April 2010. Ref:MR-11278002. PROFOR is “well positioned to continue supporting and informing the rapidly expanding debates on forests and climate, and to effectively mainstream new knowledge into Bank operations and the country level work of the Climate Investment Funds.” It adds ”PROFOR often supports processes that are already in motion, providing the necessary analysis, research or capacity building to allow a more strategic and evidence based decision making whereas in other actions PROFOR offers the initial impulse that allows the consideration of new approaches to forest management and livelihoods in the framework of new programmes or policies”.
[51] Wells et al, 2011. PROFOR
[52] The Convention on Biodiversity (CBD) Subsidiary Body for Scientific and Technical Advice (SBSTA) met in August 2011 to discuss “Ways and Means to Support Ecosystem Restoration” and urged the Conference of Parties to support countries in implementing ecosystem restoration by: “compiling and disseminating case studies, best practices and economic aspects, facilitating the sharing of public information and knowledge, convening regional and subregional technical training, designing and implementing communication programmes highlighting the economic, ecological and social benefits of ecosystem restoration including awareness raising amongst the general public, policy makers and environmental managers not only on the crucial role that ecosystems and biodiversity play in providing ecosystem services but also on the costs associated with ecosystem degradation, lost incomes, increased expenses in production, the cost savings, benefits and the potential solutions to common political challenges that restoration can contribute.”
[53] A Partnership animated by the IUCN, PROFOR, World Resources Institute (WRI) and UK Forestry Commission (FC)
[54] Project Outline – Meeting the Bonn Challenge in Rwanda, IUCN, August 2011; Republic of Rwanda, statement delivered by Minister of Environment and Lands to the General Assembly of the UN. February 2011
[55] Mike Smith and Sandeep Tripathi. September 2011. “UK-India Forest Landscape Restoration”. UK Forestry Commission.
[56] # Evolution and prospects of global forest assessments. (2002). P. Holmgren P, Persson, R. Unasylva. Vol 53. FAO
[57] Sarah Michaels, Nancy P. Goucher, and Dan McCarthy. May 2006. “Considering Knowledge Uptake within a Cycle of Transforming Data, Information, and Knowledge.” The Review of Policy Research. University of Waterloo
[58] Afforestation refers to the planting of trees on areas that were not covered with forests. Reforestation refers to the re-planting of trees on areas that were once covered with forests. Forestation is sometimes used instead of Afforestation. Deforestation means to remove or cut down forests or trees.

Appraisal Case

Determining Critical Success Factors / Each Critical Success Criteria is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / 1 Knowledge products and tools reach the hands of key global and frontline decision makers and practitioners 5 / 2 Lesson learning generates a critical mass of opinion-makers, movers and shakers leading to coherence 4 / 3 Tools and lessons are applicable and demonstrate “competency” in a range of local developmental contexts 4 / 4 The aggregation of local site monitoring results is timely and influences the global level 3 / Four factors are critical to ensuring the integrity of programme outputs. The first factor, that of timeliness and targeting of uptake and use of appropriate “uptake pathways” is critical to the success of the overall programme. The programme will monitor this by ensuring that partner organisations carry out regular client uptake surveys and improved communication strategies that take into account lessons about the current barriers to uptake. / Other factors will vary in importance depending on the context. For critical knowledge and analysis to bring about fundamental change in forest policy and practice globally, it has to be generated systematically by credible agencies and be widely applicable and ”championed” for it to be taken up by key global and frontline decision makers. A critical body of knowledge, aggregated from across local sites, involving a spectrum of actors working at different levels from local to global will help bring about change.
Feasible options to address the need set out in the Strategic Case / Three options were assessed as follows: / Option 1: Better knowledge uptake of technical basics for establishing REDD+ (focusing on a ‘narrow’ knowledge area – REDD+ reference levels) / Option 2: Better uptake of a broader spectrum of knowledge on forestry (using a learning and network approach) / Option 0: Do nothing (the counterfactual) / Option zero: do nothing (the counterfactual) / Under this option UK provides no support targeted to uptake of knowledge. Despite high quality international research being available, its accessibility to those working in remoter and more difficult regions is constrained. By doing nothing UK would miss opportunities to capitalise on UK’s other investment in research. This option would not improve the understanding, deployment, application and use of the findings and knowledge which result from research. / There are few large donors (for example, Germany, Norway, the European Commission) that include forests and climate as an area of significant focus in their development budgets. Overall donor spending on forest-related knowledge generation tends to be fragmented and the evidence collected also fragmented (or patchy) and, therefore, not easily aggregated or compared. / Under Option 0 (the counterfactual) it is assumed that other donors maintain their current level of spending to forestry knowledge. With this option there is a risk of poorly formulated policy and field responses in the forest and land use sectors because they are less well informed. Option zero is rejected. / Option 1: Better knowledge uptake of technical basics for establishing REDD+ (focusing on a ‘narrow’ knowledge area – establishment of REDD+ reference levels and forest carbon inventories / The knowledge needs for REDD+ are huge. Option 1 would be to focus on improving knowledge uptake in a critical, but narrow, knowledge area that is a prerequisite for the envisaged international REDD+ compliance mechanism currently under negotiation though the UN process. It would aim to support and progress REDD+ by providing knowledge on how to produce accurate and reliable national forest carbon inventories and reporting in a range of countries. It would focus on building knowledge and use of better inventory techniques. / Forest inventories are required to ascertain carbon baselines and for on-going assessment of changes in carbon stocks and stores. Baselines and reference levels will be required to attract REDD+ finance once a forest carbon compliance market is established in the future, and an international REDD+ financing framework is agreed. However, many countries have limited expertise, tools or knowledge to calculate these reference levels. / Significant REDD+ finance will provide some incentive to forest management activities that conserve existing forest carbon stocks and enhances future forest carbon sequestration. REDD+ finance also provides an incentive to countries to reduce forest clearance and degradation, which in turn maintains forest ecosystem services and conserves livelihoods benefits from fully functioning forests. / Under this option the theory of change is therefore that improved uptake of knowledge on carbon inventory methods alone will help countries determine their reference/credit levels and meet Intergovernmental Panel on Climate Change (IPCC) guidance on best practice so that, once the basic international finance and compliance architecture is in place, this will kick start investment into REDD+ in those countries. / The IPCC[59] lays out a three-tiered approach to forest carbon inventory, monitoring and reporting with increasing detail and accuracy from Tier 1 to Tier 3. The simplest approach (Tier 1) keeps track of changes in forest area and uses global default values or carbon emission and stock factors to calculate forest carbon density (or tonnes carbon per hectare). Tier 1 does not qualify as REDD+ reporting because it contains large error rates. Tier 2 improves accuracy by using country-specific data to estimate carbon densities. Tier 3 uses carbon modelling and inventory measurement based on high resolution of data collected from field sampling at regular time intervals, as well as GIS systems to analyse land use data. The higher tiers reduce uncertainty, but increase cost and complexity. The good practice guidance of the IPCC allows for a combination of Tier 2 for changes in carbon stock and Tier 3 for land use. / Only India, Brazil and Mexico are considered to have Tier 2 compatible systems with few or no countries using Tier 3.[60] / The estimated costs of taking up or implementing carbon inventory and monitoring systems approach varies, with best estimates ranging from between £250,000 to £700,000 per country for Tier 2 (with annual costs of £350,000) and £600,000 to £1,200,000 or more per country for Tier 3 (with £700,000 annual costs a year).[61] / However, this does not take into account the additional costs of building the national and local institutional capacity to ensure that an inventory can be carried out, updated, the information maintained and the quality of data and integrity of monitoring be verified. Nor does it take into account the broader knowledge of forest and land use management required to deliver emissions reductions and other social and environment “co-benefits” on the ground. / An investment of £20,000,000 over 4 years could help move 10 to 15 countries with Tier 1 knowledge of forest cover towards applying knowledge about Tier 2 inventory assessment and reporting approaches although it would not provide all the annual support costs to maintain information, monitoring and verification. As discussed in the economic appraisal section below, there is a risk that the required support from other donors to maintain inventories would not be forthcoming. / This option 1 assumes that the UK does not provide support to the broader spectrum of knowledge needed for countries to become “REDD+ Ready”. With REDD+ carbon markets unlikely to bring direct finance before 2020, sustainability of benefits and value for money invested in such a narrow option needs to be carefully appraised. / UK’s Overseas Development Administration (DFID’s predecessor organisation) supported many countries to carry out forest inventories during the 1980s, but few maintained the capacity to do so. However, the UN Food and Agriculture Organisation (FAO), Finland, Norway, USA and the World Bank are currently providing dedicated support to knowledge and capacity building in this area; for example, the Finland-supported National Forestry Resources Monitoring and Assessment project (NAFORMA), the USDA Forest Service support on Forest Inventory and Analysis (FIA), FAO’s support to National Forest Monitoring and Assessment (NFMA), support by Australia and Norway on REDD+ monitoring reporting and verification (MRV), as well as GIZ assistance to national forest programmes. / There has been a long tradition of aid in support of forest inventory and mapping during the 1980s in particular. The UK Overseas Development Administration (ODA) supported inventories based on the establishment of permanent sample plots in tropical forests in Bangladesh, Bolivia, India, Indonesia, Brazil and other countries. This work helped establish the inventory approach for tropical forests, which (with different patterns of tree species distribution) requires a tropical forests, which require a different sampling approach to that of temperate forests. / There are many technical manuals available on the use of natural resource assessment and information as a tool for forest management and land use planning. However, in these and many countries the rules and regulations established (for example on allowable annual cut, species management and regeneration) are often decoupled from the technocratic process of inventory. / The overall drivers of poor forest management and deforestation tend to be of a political economic nature. UK has a comparative advantage and demonstrated track record in developing approaches to strengthen weak forest law enforcement and governance. A key element laid out in the overall theory of how to achieve behavioural change and regulatory reform in the forest sector is the generation and use of evidence. / What evidence is generated, the way it is generated and how and by whom it is used is key to building broad and informed coalitions of interest able to change the rules and maintain the momentum for change. This is laid out in more detail in the Forest Governance Markets and Climate Business Case, available at http://projects.dfid.gov.uk/project.aspx?Project=201724. / Option 2 lays out an alternative approach, which does not ignore the importance of ecological information and natural resource assessment, but argues for a broader base of knowledge and the use of networks and multi-level uptake as a means to achieve change. / Option 2: Better knowledge uptake across a broad spectrum of knowledge, (through a strategic, programmatic approach) / Option 2 will support investments in uptake across a broader and more strategic front of knowledge to achieve greater returns overall in 3 result areas (a) improved global and national knowledge uptake for poverty reduction, (b) ecosystem services and (b) reduced carbon emissions, including REDD+. Unless a broad range of knowledge needs are met, the “multiple wins” from forests will not be realised. / The approach taken by UK and others working on forest law enforcement governance and trade (FLEGT) over the past 10 years has demonstrated the political gains that can be made by sharing knowledge with a wide group of multiple stakeholders. An example of this approach is cited in paragraph 42 above of CIFOR’s research on the pulp and paper industry that was taken up by a range of actors, including financial investors, and resulted in some positive reforms in the sector. / If forests do not provide multiple benefits, they will not be protected or planted. Their potential to mitigate the impacts of climate change, and help adapt to those impacts, relies precisely on that multiplicity. / Under this option the programme focuses on two contexts: how to “avoid deforestation and degradation” and how to “restore back forests”. The latter implies a landscape of mixed uses that provide livelihood and conservation opportunities, while hitting carbon emissions targets. It specifically tackles concerns about developing huge vistas of uninterrupted monoculture plantations. / The focus of Option 2 will more directly address weaknesses in the way knowledge is understood, communicated and implemented by supporting a range of key networks and bodies tasked with the provision of forestry knowledge internationally. / The Collaborative Partnership on Forests is a voluntary arrangement among fourteen international organisations and secretariats with programmes on forests, six of which are knowledge bodies. The Partnership is formally mandated with the “global public good” of international forestry knowledge, and to keep up to date the main forest-related international conventions and processes, such as the United Nations Framework on Convention on Climate Change (UNFCCC), the Convention on Biological Diversity (CBD) and the United Nations Forum on Forests (UNFF). / The six knowledge agencies in the Collaborative Partnership on Forests (CPF) are the Food and Agricultural Organisation (FAO), the Center for International Forestry Research (CIFOR), the Programme on Forests (PROFOR) administered by the World Bank, the International Union for Conservation of Nature (IUCN), the World Agroforestry Center (ICRAF) and the International Union of Forestry Research Organisations (IUFRO). / Option 2 proposes that the programme work through key bodies or secretariats in the Collaborative Partnership on Forests that maintain knowledge networks, have clear uptake pathways to country level, the potential to deploy knowledge actively and effectively (according to independent evaluations) and that can expand the size of their knowledge networks to scale during the time period of this programme. Combining these into a single programmatic effort from the UK side will help these organisations and their knowledge networks work together better. It will focus on quality amongst a few bodies, rather than scatter small grants across many as a strategy to achieve a critical mass of impact at country level through the networks chosen. It will also build on past investments by the UK. / Under Option 2 the programme will support three agencies that maintain four major networks or partnerships which are a principal source of global and regional knowledge for the large majority of international forestry practitioners and decision makers in partner countries. These are: / the Center for International Forestry Research (CIFOR), which runs the Global Comparative Study on REDD+ and the Poverty and Environment Network (PEN); / the Programme on Forests (PROFOR) with its secretariat housed in the World Bank, which has varied knowledge activities and is designed to mainstream knowledge activities into geographical operations; and / the Global Partnership on Forest Landscape Restoration, with its secretariat housed in IUCN, which is a large union combining civil society and sovereign states drawing upon over a thousand volunteer experts. These are knowledge networks active internationally and in countries, with potential to strengthen impact at country level within a short period. / PROFOR, for example, works with established partnerships and a range of enterprises, markets, and businesses, including with the World Bank's private sector arm, the International Finance Corporation. CIFOR is held in high international regard amongst research and academia, with a reputation for linking policy to practice. It works “without walls” through national research and extension agencies. The Global Forest Landscape Restoration Partnership convenes a mixed constituency on environmental and land use management linking best practice from the USA, UK, India and elsewhere to practitioners in Asia, Africa and Latin America who seek that knowledge. / PROFOR supports a range of partnerships and networks encompassing a range of specific knowledge themes, including forest finance and enterprise, improving the livelihoods of forest-dependent people, enhancing forest governance, coordinating forest policy with other sectors. Each knowledge product or toolkit is targeted to specific audiences, with field notes, news and events “feeds”. The programme’s support to PROFOR will result in knowledge activities that span many countries as well as topics. (See programme LogFrame.) / The “learning network” of the Global Partnership on Forest Landscape Restoration links together formally 13 core countries with a range of other partners that house specialist expertise on restoring landscapes. Its online learning network brings together people from different constituencies (civil society, academia and government) and from 46 countries.[62] The programme will help the network expand and better support those who are practically involved in building landscapes on the ground, particularly those which give people food security. / With the programme’s support, IUCN will extend the considerable body of practical knowledge and experience in landscape restoration and agroforestry amongst a broader community of frontline practitioners in developing countries. It will help develop a better and broader understanding of farmers’ specific constraints to adoption of technical practices, and highlight opportunities for investment in better land use management. / Although the Global Partnership on Forest Landscape Restoration communicates anecdotal stories of successful forest restoration (in Niger, China, Burkina Faso) and support to individual country-led initiatives (Rwanda), this programme will help it build a more effective platform for sharing more rigorously documented evidence and for replicating effective practices out from champion countries such as India, UK, USA, China, where forest restoration is a more common practice, to a further 12 countries in Africa, Asia and Latin America. / The programme will not directly support the Food and Agriculture Organisation (FAO) as its uptake pathway to country level through its country offices is variable.[63] A recent independent review[64] of the FAO managed National Forest Programme (nfp) Facility considered that with delivery costs “reported as being 20% of total costs incurred”, greater efficiency could have been achieved by the facility if it reduced the number of countries supported (currently 70 countries), decentralised the technical assistance provided and coordinated more with other forest related efforts at country level. The FAO also has core responsibility for collating the global Forest Resource Assessment (FRA), which is a key public good and the basis for tracking Millennium Development Goal (MDG) 7 target on Forest Cover. Finland and other donors provide support to this (see paragraph 70 in section on Option 1 above.) However, a separate programme of work on monitoring and indicators on forests and climate may seek to align with FAO work in that area. / The programme will seek to source expertise from the 15,000 forest scientists from across the world in the international network of the International Union of Forestry Research Organisations (IUFRO) indirectly through PROFOR and CIFOR, which support activities in up to 40 countries, including some of the twenty-five tropical timber producer countries that are members of the International Tropical Timber commodity Agreement (and which this particular programme will not support directly). / In this way the programme will support networks with broad coverage and organisations that already have some core capacity in managing complex knowledge products, which have made a start on improving the accessibility of their products and which seek joint ventures with private sector innovators. It will place the UK in a visible role that sponsors pioneering of the latest knowledge technology and combining that with practical action on the ground in remote forest regions. It will bring knowledge into the hands of those most disconnected from the globalised information society. / Knowledge networking on better livelihoods for poor people / The international knowledge Network on Poverty and the Environment Network (PEN), managed by the Center for International Forestry Research (CIFOR), constitutes the largest and most comprehensive global analysis of tropical forests and poverty with comparative socio-economic data collected quarterly from 8000+ village households by 50+ local partners in 40 study sites in 25 developing countries. / Early findings from the Poverty and Environment Network (PEN) partners show that, for people living in and around forests, forests contribute 20-25% of household incomes. Deforestation may deprive them of part of these incomes, with conservative values for the full range of non-carbon forest goods and services lost averaging £182 per hectare per year.[65] / PEN preliminary findings also provide evidence that relatively wealthier households deforest more than poorer households, breaking the commonly held myth that poverty drives deforestation[66] (See http://www.cifor.org/pen) / PEN will increase global and local understanding of whether and how forests impact on poverty. It will help mainstream forest into national policy formulation and implementation where poverty reduction and income levels are key concerns. The PEN sample of information will be the subject of further longitudinal analyses and engage partners in tracking the tenure and livelihoods implications of forests. The network will manage a range of outreach events run with members to mainstream knowledge at country level. / Knowledge networking on forest finance, investment and enterprise development / Forest Connect is one of a range of partnerships with private sector supported by PROFOR, and is a social network that links small and medium forest enterprise (SMFEs) in at least 9 countries with 800+ active members. (See http://forestconnect.ning.com/) This programme will help PROFOR engage with more practitioners and enterprises on the ground. It will also help mainstream these networks and the tools into the significant portfolio of national investment by World Bank in countries, and which PROFOR is well placed to influence. [67] (See http://www.profor.info/profor/knowledge/forest-connect-supporting-small-and-medium-forest-enterprises-toolkit) / The programme will help mobilize private sector investment and finance into forests and REDD+. It will build on a recent analysis by PROFOR of 30 types of national and “benefit-sharing mechanisms”, described in the toolkit “Making Benefit Sharing Arrangements work for Forest Dependent Communities – Insights for REDD Initiatives”. / It will support regional and national Forest Investment Forums that bring together finance experts and those who work on forestry and climate change. These forums will help “cluster” together small and medium enterprises, giving them greater potential to access larger sources of finance. The forums will help investors assess the relative competitiveness of different forest enterprise development approaches, reducing their risk By helping public and private investors discover unit costs and make judgements in future about relative unit costs. / They will attract more responsible players to the sector and educate participants in how to avoid the pitfall of “carbon cowboys” (as unscrupulous carbon credit dealers are known).[68] The accompanying toolkits on forest enterprise that the programme develops will package complex information in an accessible way and help practitioners organise such events. / Knowledge networking on restoration of biological life critical to the planet / The Global Forest Partnership on Landscape Restoration sets out the challenge amongst its members of restoring 150 million hectares by 2020. This programme, over the next four years, will help it mobilise support more widely and, with that, plant 70 million hectares of land apt for planting but currently denuded of trees; benefit 50 million hectares of farms and pastures with agroforestry and silvi-pastoril systems; and enrich 30 million hectares of standing forest. This land area, if fully restored, would be a valuable asset or investment with a net present worth of £1.26 billion, equal to an annualised value of non-carbon benefits of £280 per hectare (according to IUCN). The economic appraisal for this programme (see below) uses a conservative estimate of £56 to £139 worth of non-direct ecosystem goods and services per hectare per year.[69] / The programme will enable knowledge network partners to compare restoration techniques, practices, costs and benefits. These vary greatly from site to site. For example, restoration approaches used as a result of the Gulf of Mexico oil spill are different to those used in the Iraqi wetland marshes, or on the denuded slopes of grazed Scottish highlands, or along the deep mechanically dug drainage channels in the peat swamps of Indonesia, or for restoring coastal sand dune habitats or for the restoration of open cast, surface-mined land in the tropics or in areas suffering from salt inundation. / Techniques usually combine the use of modern technology with local and traditional ecological knowledge in a range of activities. The range of techniques makes it critical that practical experience is shared and national frameworks established for assessing the conditions and the costs. / Forest restoration goes beyond planting trees or establishing forest cover. Its aim is to restore a varied range of “ecological and social functions” that have been lost or disrupted to a degraded landscape. [70] Restoration incorporates forests and trees within a wider practice of environmental management, using a dynamic, lesson-learning approach that can cover large areas, and with an emphasis on involving a range of stakeholders in the actual “doing”. / This programme will help countries in Africa and Asia in particular to assess the potential and costs of restoring the ecological and social benefits and functions that trees can provide. It will support knowledge on restoration for governments, companies and communities. With stringent regulations about who bears the responsibility for restoration in place in some countries, the programme will provide knowledge to stakeholders who are increasingly concerned about what the standards they will need to comply with. Restoration may take place on private, community, tribal or state land with implications for who bears the costs of restoration. The programme will also help assess what revenue streams can be expected from restored landscapes, and who captures those. / Knowledge networks on reducing carbon emissions and climate change / This programme will ensure better measurement and monitoring of the impacts of REDD+ projects globally with methods for setting baselines (or Reference Emissions Levels as they are currently referred to by the UNFCCC) using a progressive approach and across a consolidated database. The Global Comparative Study on REDD+ will compare and contrast twenty-four sub-national REDD+ project sites in six countries (Brazil, Peru, Cameroon, Tanzania, Indonesia, Vietnam) and track the impacts of national policies in these countries as well as in Bolivia, DRC and Nepal comparing communities and villages without interventions and those where REDD+ incentives have been introduced. It will assess how effective REDD+ policies and projects are in sequestering carbon, how efficient and equitable in terms of the distribution of costs and benefits, and whether they are capable of delivering various livelihood, governance, and biophysical co-benefits. / The programme will help the Comparative REDD+ Study create a longitudinal time series data set that enables robust empirical monitoring of REDD+ impacts over time, as it will on forests’ contribution to poverty reduction with the Poverty and Environment Network (PEN). It will aggregate the lessons and knowledge from “first generation” REDD+ projects in order to improve the design and implementation of “second generation” policies and projects / The programme will support analysis that is comparable and consistent, informed by the database on REDD+ project sites. On the basis of this information it will support CIFOR to make policy and technical recommendations to all relevant stakeholders, including practitioners and carbon project developers for use when designing and implementing REDD+, and ensure their wide dissemination through events, conferences, workshops as well as online tools. / Support to the Poverty and Environment Network will complement the platform of sites participating in the Global Comparative Study on REDD+, by allowing practitioners to better understand forests’ role in climate change adaptation and how forests help people and countries respond to shocks of differing severity. It will inform about the welfare impacts of REDD+ and also allow decision makers to compare different welfare measures and the impacts on conservation and climate policy and practice. / The programme will also help national policymakers working on REDD+ to apply knowledge, based on the key international research findings, in a timely fashion. An example of timely and rapid knowledge uptake by CIFOR was that in response to Indonesia’s ambitious target of reducing greenhouse gas emissions by 26 per cent. A central research finding was that achieving significant emissions reductions through a massive tree-planting program alone would not be feasible, as the number of trees needed to fully achieve emissions reduction targets would require a land area twice the size of Indonesia.[71] The findings were made available to the Government of Indonesia and other stakeholders less than 2 weeks after a Letter of Intent on REDD+ was signed between Norway and Indonesia. This analysis likely contributed to an early and significant shift in emphasis away from tree planting as a main strategy to achieve emissions reductions. / Knowledge networks for women and girls / Although men bring as many forest products to the household as women, different products tend to be controlled by either men or women (so a development focus on a specific product has strong gender implications)[72]. / The programme will support knowledge that improves the livelihoods of women and girls specifically. For example, information on the marula tree in South Africa has enabled 4,200 women to become business partners of Marula Natural Products. They crack the nuts for cooking oil which they sell. The fruit juice (rich in Vitamin C) and kernels that taste like pine nuts supplement meals when rainfed crops fail. (See http://www.profor.info/profor/notes/free-lunch-shade-marula-tree). This is one of hundreds of examples of studies, findings from the field (“field notes”) and toolkits supported by the Program on Forests (PROFOR) with a further 100+ examples that will be made available on CIFOR’s site. / The programme will also help ensure that the tools developed to deploy and apply knowledge are “gender-differentiated” and put into action. For example, it will help roll-out “gender roadmaps” whereby country-level practitioners are trained on the different impacts that forest-related climate change has on men, women and children. [73] / Improving the way knowledge is understood, communicated and implemented / The programme will help improve the way knowledge on forests is understood, communicated and put into use generally across the elements its supports. It will ensure that complicated science and research results, as well as common and technical practice, are made accessible through broadcast, web and print media worldwide to a broad range of stakeholders. / Local accessibility will be a critical element across the programme. This means it will combine digital, online information technology with practical face-to-face networking. It will help local networks “bud off” from the global learning networks. / Global Forest Day, convened by CIFOR on behalf of the Collaborative Partnership on Forests, is now held every year on the side of major international climate events (the largest being Forest Day 4 being at Cancun, which included 276 UNFCCC negotiators, more than 100 journalists and the Mexican President). The programme, in addition, will support smaller more focused uptake at country level and on specific themes, so that knowledge is in the hands and minds of government officials and others involved in policy formulation and the frontline. All the knowledge products supported will involve the bringing together of local stakeholders face-to-face to disseminate findings, build capacity and knowledge and promote uptake of results. / The programme will also help national and local government agencies in developing countries to develop their own national websites on forest and climate change. It will support the development of Forest Blogs to increase younger readership. It will also ensure that paper publications, cds, local audio or radio interviews and face-to-face presentations are available and assimilated at events, conferences, training workshops in country, as well as international level. / The programme will help move the networks it supports away from passive, one-way web dissemination to sites with options for queries, comments and online learning. It will help networks better identify and respond to members or clients’ needs, where members discuss and share their progress on what is, and is not working. The programme will help partners to include new social and multi-media components with greater inter-active capacity and better targeted knowledge dissemination; for example, smarter use of video clips and news feeds on Facebook and Twitter. / At the moment an “ad hoc” approach to translation (or no translation) means that knowledge and training material in languages other than English is scarce. This isolates knowledge to a few and limits outreach to those many non-Anglophone tropical forested countries, ironically at a time in the world’s history when there is greater opportunity than before to be connected. The programme will support more translation of “must-read” briefs, toolkits and guides and into a range of languages (at a minimum Portuguese, Spanish and French, and possibly other Asian languages). [74] It will also consider the transfer of knowhow across cultural as well as language barriers. [75] / It will also support the employment by agencies of dedicated expert outreach managers, ensuring that CIFOR maintain media expertise on staff. It will encourage CIFOR and IUCN to follow PROFOR’s example by developing more search-enabled websites, with more field notes and video clips. / The programme will also support the agencies to make use of client perception and satisfaction surveys, as well as rapid phone surveys. It will encourage a culture of systematic analytical assessment amongst the group of collaborators to help them reflect and learn from experience and establish the impact of each activity.[76] This will bring them greater understanding of what knowledge has (or has not) made a difference to their different client groups and why. The programme will also encourage greater debate on the value and impact of knowledge uptake approaches amongst the collaborating donors and other supporting development partners. / In some cases, a specific piece of research or evidence may be identified by the UK government as critical for it to respond rapidly to a particular policy process or in order to draw lessons from successful project implementation. For example, in 2010 the UK government supported an independent review “Funding for Forests: UK support for REDD+” which led it to consider the impacts of its international work on forestry and climate and the development of UK government’s current forestry development and climate portfolio of work. DFID will maintain a small budget in-house for such rapid response. / Option 2 is the preferred, feasible option, namely to work through significant existing networks managed by bodies, which are tasked, as part of the “Collaborative Partnership on Forests”, with the provision of the “global public good” of forestry knowledge internationally. / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 0 Strong / 1 Limited / 2 Strong / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 0 A C / 1 A C / 2 C A / Option 0 (no intervention) represents a low opportunity for contributing towards emissions reductions, livelihoods and biodiversity benefits and a high risk for achieving positive impacts. It extends these risks to other UK-supported programmes that rely on a good forestry knowledge base to achieve some of their impact. / Option 1 represents a low opportunity to contribute towards emissions reductions, but is subject to high risks due to its dependence on other funding to ensure successful implementation, with risks to livelihood benefits without rigorous safeguards being applied. / Option 2 represents a high opportunity to contribute towards emissions reductions, ecosystem services conservation and forest using people’s incomes. There are risks that the organisations supported do not take steps to improve the way they communicate knowledge and target their uptake pathways to those that will use it. The programme mitigates this by putting in place is monitoring and evaluation systems. (See Management Case below)
What are the costs and benefits of each feasible option? [Economic case and value for money] / Option 0 (the counterfactual) is rejected. Existing research and development on forests leads to a decline in global deforestation rates by encouraging agricultural expansion on degraded rather than forest land as well as better natural forest management. However, under this Option, uptake by local practitioners, businesses and communities of knowledge on forestry is not fully realised. Quality up-to-date information is largely held by international researchers and high level global policy stakeholders. As explored elsewhere in the Business Case, there is a strong risk that without DFID support the expected benefits will not be realised. / Option 1 (narrow focused uptake of knowledge about approaches for forest carbon inventories) is rejected on the grounds that its offers less value for money than Option 2 and is high risk. Success relies on additional donor funding as well as finance from the carbon market for benefits to be realised. The economic case for option 1 is negative under the medium impact scenario. / Option 2 (Uptake of a broader spectrum of forestry knowledge at all levels), is the recommended option. By using this approach to knowledge uptake the programme improves effectiveness of the “without programme scenario” by 10% per year, slowing to 5% per year after 2020. The economic case for option 2 is strong, producing a benefit to cost ratio of £6 for every £1 spent, with conservative assumptions of low and constant carbon values (sensitivity analysis is included below). / Option 0 (The counterfactual): Some research on forests, but no DFID funding to support uptake of research results / The UN Food and Agriculture Organisation estimate that the current rate of global deforestation is around 13 million hectares per annum. The economic model developed to appraise this option assumes that the deforestation rate will decline over time by 342,100 hectares per year from 2012 to 6.5 million hectares per year in 2030[77]. (The analysis assumes a linear decline in deforestation rate to half its current rate by 2030). / It is assumed that the linear decline in deforestation rates would happen anyway – without any research or knowledge development on forests. However, under this option an additional “hectares saving” takes place on top of the linear decline as a result of existing (non-UK supported ) research on forests. The theory of change is that forest research encourages large scale agriculture to: (i) improve productivity of existing plantations; and (ii) expand on to degraded rather than forest lands. / The level of funding for knowledge and research without any further UK funded intervention is: (i) the current core research budget for the Global Comparative Study on REDD+ and the Poverty and Environment Network (both at CIFOR); (ii) other donors’ contributions to PROFOR; and (iii) Forest Landscape Restoration programmes mobilised by the International Union for Conservation of Nature (IUCN). As explored in the Strategic Case, there is a strong risk that the benefits of forests research will not be realised without further UK support to these organisations. However, existing research programmes will have some outreach to and influence over just under half of the total area deforested (i.e. research reaches some countries but not all).[78] / The additional “hectares saving” on top of the linear decline, which results from non-UK funded research, is calculated as a proportion (x) of the deforestation area influenced by research. This proportion (x) is assumed to be 1% in 2015, rising gradually to 16% in 2030. Proportion (x) is the extent to which knowledge creation and dissemination improves the effectiveness of REDD+. The CGIAR Research Programme on Forests, Trees and Agroforestry (CRP6) anticipates that research outcomes translate into improved effectiveness and implementation of REDD by 1-25%[79]. The model presented here is more conservative – assuming that research improves REDD effectiveness by 1% rising to 16%. Box 1 provides a worked example. / One of the methodological challenges associated with modelling the impact of forest policies is inclusion of the costs of alternative land use – i.e. the revenue that private developers could have received from agricultural expansion had deforestation not been averted. Box 2 outlines the approach taken in this appraisal. / Box 1: Worked example / In 2014 11.9 million hectares of forest are deforested / In 2015 11.6 million hectares are deforested (deforestation is declining over time even without research) / Of the 11.6 million hectares deforested in 2015, 46% (5.3 million hectares) are “influenced” by research outputs / An area the size of 1% of the 5.3 million hectares (53,000 hectares) is saved in addition to normal decline in deforestation. This is the “hectares saved by research adoption’” figure. / Box 2: The Costs of Alternative Land Use / The theory of change behind this intervention is that knowledge dissemination results in large scale agriculture being diverted on to degraded land rather than cleared natural forests. Some of the diverted large scale agriculture will now take place on land previously used for subsistence farming. / The model assumes that an area equal to 50% of the avoided deforestation displaces subsistence farming. This is included as a negative benefit equal to £221 per hectare. / However, some of the avoided deforestation could result in the expansion of large scale agriculture being prevented all together. It would therefore be prudent to include the lost revenue from agricultural production as negative benefits in the model. Inclusion of these estimates would require the appraiser to: / Estimate what proportion of avoided deforestation has moved large scale agriculture to degraded lands, and what proportion has prevented agricultural expansion all together. / Define which specific countries research dissemination would impact. Estimate what proportion of forest land in that country would have been converted to each use (soya, palm oil, livestock, and other crops). Estimate the expected scale of these enterprises (as this will affect yield); / Multiply [estimate of expected returns to land] for each land use type by the [estimated proportion of deforested land that will be converted to that land use]. / The calculations above are clearly highly complex and therefore for analysis to be proportional to the size of investment proposed they have not been included in the options analysis below. In order to balance the omission of a potentially large cost (negative benefit) of the programme, the following safeguards have been put in place: / Large scale agricultural expansion on forest land would result in emissions of greenhouse gasses other than carbon dioxide. For example, nitrous oxide from palm oil plantations and methane from cattle farms. These substantial positive benefits are not included in the cost benefit analysis. / Positive benefits are further understated because only one-off carbon savings from avoided deforestation are included in the analysis. Carbon sequestration of the cumulative stock of forest land left standing is not included. / Option 1 (narrowly focused on uptake of knowledge on forest carbon inventories for REDD+) / Theory of change / The analysis of this option focuses on the knowledge for production of quality forest inventories as a sufficient prerequisite for accessing REDD+ finance. It assumes that forest carbon inventories are developed in 15 countries. Inventories provide policy makers with improved knowledge of forest carbon stocks and lead to improved management and policy making. Inventories are required to ascertain carbon baselines and for on-going assessment of carbon stocks saved. This leads to an increased annual decline in deforestation in countries with inventories (in addition to the decline in deforestation rate assumed under the counterfactual). The additional decline in deforestation only comes into effect after 2025 when REDD+ finance becomes available from carbon markets and elsewhere. / There are approximately 40 countries (with high forest cover and rates of deforestation) that require forest inventories. The analysis estimates that around 25 of these countries have existing inventory development projects. With the available finance (£20 million) UK could fund inventory development in a further 15 countries. / The additional avoided deforestation in 15 countries means that less carbon is emitted and more ecosystem services are protected than under the counterfactual scenario. REDD+ generates carbon value through protecting and managing standing forest carbon stocks and reducing depletion of these stocks through degradation. It also enhances forest carbon stocks. The forest ecosystem services associated with thus conserving the quantity and quality of existing forest resources are thereby maintained and restored as an inherent co-benefit of REDD+ activities. In a similar way the goods and services these forests provide to poor communities are thus also maintained and restored. / Option 1 Costs / The Eliasch Review estimates the average costs of producing a basic forest inventory at £1.27 million per country. In 15 countries these costs would total £19.05 million.[80] It estimates the minimum costs of running and updating the inventories and administering forest protection at £6.23 million per country per year.[81] These costs are included in the analysis, but are assumed to be met by other donors (see risks section below). / There are also potentially large costs associated with implementation of forest protection and land management polices based on inventory information (the mechanism by which inventories lead to reduced deforestation). The model includes implementation costs of £4.55 per t/CO2e averted. The Intergovernmental Panel on Climate Change ( IPPC) has estimated that the cost of carbon sequestration forestry projects can vary between US$0.5 and US$7/tCO2e. [82] Analysis uses the high estimate and converts to pounds sterling There is a risk that these costs are understated, which would imply the benefit to cost ratio could be lower than presented below (see risks section for further discussion). / Costs are assumed to be incurred annually for 2012, based on availableity of UK’s contribution. As discussed below the benefits, however, are not realised until 2025 (assuming a REDD+ incentive and compliance mechanism). The risks and uncertainties section below looks at the viability of this programme were the costs to be put back to 2025. / . / Option 1 benefits / Avoided deforestation / The model estimates that 15 countries contribute to approximately 4% of total global deforestation.[83] This is based on average country contribution to total global forest land (excluding Brazil, Indonesia, USA, Canada, Russia, China and Democratic Republic of Congo – all of which are unlikely candidates for intervention). In the counterfactual scenario the number of hectares deforested per year in these 15 countries declines by approximately 13,000 per year (from approximately 500,000 hectares per annum in 2012 to 250,000 hectares per annum in 2030). / Three scenarios estimate the impact of inventories on deforestation in the 15 intervention countries: low (annual reduction in deforestation increases by 10%); medium (annual reduction in deforestation increases by 50%); and high (annual reduction in deforestation doubles). / The analysis assumes that benefits of inventory development are only realised from 2025 – 2030, when REDD finance from other sources becomes available and governments begin to use inventories to inform forest protection policies. Under the medium scenario approximately 16,000 hectares of deforestation would be avoided each year from 2025-2030 over and above the counterfactual. / Monetised benefits – carbon and ecosystems / Hectares saved are not counted as a benefit in themselves (as it would be double counting to include trees plus their carbon and ecosystems benefits). Carbon and ecosystem benefits come online in 2025 when additional deforestation is avoided. / The appraisal take three steps to monetise the carbon benefits of reduced deforestation: (i) convert the number of hectares saved into above ground carbon stocks (t/CO2)[84]; (ii) convert carbon stocks to avoided emissions (t/CO2e)[85]; (iii) convert emissions to money using the carbon value series of the UK Department for Energy and Climate Change (DECC). In the base case a conservative constant value of carbon of £14 per t/CO2e is used. Sensitivity analysis (below) tests the results using DECC’s rising carbon values / Ecosystem services comprise a wide range of goods and services, including provisioning services such as food and fibre; supporting services such as nutrient recycling and primary production; regulating services such as climate, water and soil; and cultural and social services. The model assumes that ecosystems benefits are £182 per hectare avoided each year.[86] This value includes direct and indirect use values and is therefore taken as combining the biodiversity and livelihoods benefits accruing from fully functioning standing, protected forests. / As discussed in Box 2 above, the theory of change for this intervention is that improved forest inventories will divert large scale agriculture away from natural forest areas on to degraded land. Some of this diversion will displace small holder farmers. The analysis assumes that 50% of avoided deforestation displaces substance agriculture. This is included as a negative benefit at £221 per hectare. / Option 1 Risks and uncertainties / HIGH: The most significant risk associated with this option is that inventories are produced but additional funding for running and administration is not sufficiently forthcoming. This option is not workable if other donors do not finance running and administration costs of inventories. / HIGH: There is a risk that finance from carbon markets is not as large as anticipated during climate negotiations, and so carbon inventories are not utilised in the future. Additional finance will be required to implement policies that make the link between inventories and reduced deforestation. These costs are included in the model at £4.55 per t/CO2e, however evidence to inform this figure is limited and so costs could be understated. / Table 1 compares the viability of option 1 under three cost scenarios. The option has a positive net present value with implementation costs at £2 per tonne of CO2e; but a negative net present value under higher cost scenarios. / Table 1: Value for money of option 1 with different implementation costs / Cost of implementation £2 per t/CO2e Cost of implementation £4.55 per t/CO2e Cost of implementation £10 per t/CO2e / NPV (£million) 2 -41 -134 / Benefit to cost ratio (£) 1: 1 / Medium scenario; 10% discount rate for non-carbon costs and benefits; constant carbon values at £14. / MEDIUM: Uncertainties concerning the application of REDD+ safeguards persist. Unless these ensure that the ecosystem service functions are maintained or restored, and are accessible to forest dependent peoples there is a risk that the non-carbon benefits and poverty alleviation benefits from REDD+ could be lower than those included in this model. / If inventories are developed between 2012 and 2015 they must then be maintained until benefits come online in 2025. In this option, therefore, the timing of costs versus benefits is a factor in reducing value for money. / Table 2: Value for money of option 1 under different cost scenarious / Inventories developed from 2012 onwards (4 in 2012; 4 in 2013; 4 in 2014; and 3 in 2015) Inventories developed from 2025 onwards (4 in 2025; 4 in 2026; 4 in 2027; and 3 in 2028) Break even? / NPV (£million) -41 500 The option has a positive net present value and benefit to cost ratio if implementation commences after 2013 / Benefit to cost ratio (£) 1: 4 1: 1 / (if implementation in 4 in 2013; 4 in 2014; 4 in 2015 and 3 in 2016) / * medium scenario; 10% discount rate for non-carbon costs and benefits; constant carbon values at £14. / Option 1 summary statistics / In the base case all non-carbon costs and benefits are discounted at 10% and carbon benefits are discounted at 3.5%. Sensitivity analysis is presented below. Option 1 only has a positive net present value when: (i) the discount rate is 15% or higher; (ii) rising carbon values are used. / Usually lower discount rates make investment projects seem more attractive because although costs are incurred upfront, benefit streams that are increasing in the future are not heavily discounted. In this model there are large and rising costs in the future (associated with implementing forest policies) which are discounted more heavily when a higher rate is used. The carbon benefits which are large and rising in the future are discounted at the lower 3.5%. Higher rates therefore produce a larger gap between costs and benefits. / Table 3: Option 1 Expected results / Impact scenario Total hectares avoided (2025 – 2030) Emissions avoided (t/CO2e) / LOW 88,057 75 million / MEDIUM 96,063 82 million / HIGH 160,105 135 million / Table 4: Option 1 sensitivity analysis (all under medium impact scenario) / 8% discount rate non carbon costs/benefits 10% discount rate non carbon costs/benefits 15% discount rate non carbon costs/benefits / NPV (£million) -178 -41 66 / Benefit to cost ratio (£) 1: 1 / Constant carbon values at £14 DECC low series DECC medium series / NPV (£million) -41 811 2,188 / Benefit to cost ratio (£) 1: 2 1: 4 / Medium impact scenario; where not stated 10% discount rate for non-carbon costs and benefits; implementation of policies costs £4.55 per t/CO2e / Option 2 (Uptake of a broader spectrum of forest knowledge at all levels via three organisations that support networks) / Theory of change / Existing research on forest management and policy fails to be transformed into useful tools for decision makers. DFID funding to the three international organisations identified in the appraisal above, which support a broad spectrum of knowledge on forests and networks of policymakers and practitioners, increases the number of hectares of deforestation avoided relative to the counterfactual through improved uptake of research results which involves well-targeted, timely “co-production” of knowledge activities involving decision makers and practitioners, and public engagement using the traditional and non-traditional media. The economic model assumes that the knowledge uptake under option 2 improves effectiveness of without programme scenario by 10% per year, slowing to 5% per year after 2020. / The increase in the number of hectares deforested (relative to the counterfactual) means that less carbon is emitted, more ecosystem services are protected and more livelihood benefits from forests are protected. / Option 2 Costs / This option assumes that the institutions identified continue to receive core funding from other donors (as in the counterfactual scenario). In addition UK provides £4.5 million in 2012; £5 million in 2013; £5.5 million in 2014; and £5 million in 2015 to these institutions to finance improved knowledge dissemination and uptake. £4 million of the total funding is allocated to the ‘global forest landscape restoration partnership’ component of the programme. / The size and timing of contributions were calculated based on prior experience of working with the institutions and assessment of their absorptive capacity. See Financial Case below for further details. / The costs of implementation of improved forest polices are assumed to be £4.55 per t/CO2e as per under option one above. / Option 2 Benefits / Avoided deforestation / The approach is similar to the counterfactual and assumes that existing research programmes have some outreach to and influence over just under half of the total area deforested (i.e. research reaches some countries but not all). For example, CIFOR estimate that the thirteen priority countries in which they work contribute to 46% of global deforestation. / The additional “hectares saving’” on top of the linear decline in deforestation is calculated as a proportion (x) of the deforestation area influenced by research. In the counterfactual (where non-UK funded research goes ahead) this proportion (x) is assumed to be 1% in 2012, rising gradually to 16% in 2030.[87] / This option assumes that the programme improves knowledge uptake by 10% per year until 2020 (5 years after programme funding ceases), thereafter declining to an improvement by 5% per year.[88] That is, proportion (x) increases from 1% to 1.1% in 2015. / The number of hectares attributable to the additional UK knowledge uptake finance is calculated as: [number of hectares saved under UK plus core funding] – [number of hectares saved with core funding]. All ecosystems and livelihoods benefits refer to the additional hectares saving attributed to UK finance. / Additional benefits accrue from forest restoration activities under the specific ‘Global Forest Landscape Restoration Partnership’ component managed by the International Union for Conservation of Nature (IUCN). The programme aims to restore up to 15 million hectares of forest land by 2020. For this analysis, IUCN provided a conservative target of forest restoration of 150,000 per year with UK’s specific support. Of this approximately 50% is on completely degraded land, 33% is on silvo-pastoral and agro-forestry matrix lands, and 17% is standing but partially degraded forest lands. / In the without programme scenario the option assumes that only 98% of target restoration hectares are achieved. In the with programme scenario UK finance enables IUCN to fully meet the 150,000 hectares target each year. The number of restored hectares attributable to UK is calculated as the difference between the ‘with programme’ and ‘without programme’ scenarios. / Monetised benefits – carbon, ecosystems and livelihoods / Hectares of deforestation avoided are not counted as a benefit in themselves (as it would be double counting to include trees plus their carbon and ecosystems benefits). / Carbon benefits are a significant part of total benefits in this option. Total present value of carbon benefits over the 2012- 2025 period is £3,611 million (at £14 per tonne of CO2e) compared to £44 million for non-carbon benefits. However, as iscommented below, the estimate of eco-system and livelihoods benefits is conservative. In addition the value of forests’ contribution to energy and health, which in many countries is large, is not included. (For example, the Uganda Energy budget for 2011 was $514 million, while forests contributed three times as much in fuel wood. Uganda spends $38 a head on health annually, while every rural Ugandan gets $27 worth of protein, vitamins and minerals and $7 worth of herbal medicine annually from forests.[89]) / The analysis takes three steps to monetise the carbon benefits of reduced deforestation: (i) convert the number of hectares saved into above ground carbon stocks (t/CO2); (ii) convert carbon stocks to avoided emissions (t/CO2e); (iii) convert emissions to monetary value using DECC’s carbon values series. The analysis assumes forest carbon stocks of 231tC/ha equating to 845tCO2e per hectare.[90] In the base case a conservative constant value of carbon of £14 per t/CO2e is used. Sensitivity analysis (below) tests the results with DECC’s rising carbon values. / Carbon benefits are also derived from sequestration of carbon in the restored forest areas. The analysis assumes that 50% of the restoration forest area (the fully degraded areas) will sequester carbon at a rate of 1tC per hectare a year; 33% (the agro-forestry matrix area) at 2tC per hectare a year; and 17% (the partly degraded area) at 4tC per hectare per year.[91] / Ecosystem services comprise a wide range of goods and services, including provisioning services such as food and fibre; supporting services such as nutrient recycling and primary production; regulating services such as climate, water and soil; and cultural and social services. The analysis disaggregates the direct use ecosystem service values from the non-direct use values, so as to avoid double counting with the livelihoods benefits below. This produces a conservative benefits estimate as it assumes that different components of option 2 target the same people (in reality a larger group of people could be beneficiaries). / The analysis uses an average value of £139 per hectare per year for non-carbon indirect ecosystem services for the area of avoided deforestation.[92] Ecosystem service values on the forest restoration areas are assumed to be slightly lower at £56 hectare a year on average.[93] / The option does not include any direct use livelihoods values that would benefit forest dependent people as a result of hectares of deforestation avoided. It does however include direct livelihood benefits that accrue to beneficiaries of the CIFOR Poverty and Environment Network (PEN) component. / The model assumes an average household income from forests of £43/year.[94] According to PEN research, 1.2 billion rural poor people use forests to some extent and many hundreds of millions of people depend directly on forests for their livelihoods. The analysis uses a figure of 200 million for the number of people for whom PEN findings are relevant and could provide benefits.[95] The average household size of forest using peoples is taken as 6.8[96], giving the number of households which could benefit from the PEN findings as 29 million households. / The model assumes the value to livelihoods of option 2 is = [total number of households that could benefit from the PEN research*£43 per household*proportion (x)]. Under the counterfactual scenario research improves uptake of the PEN programme by 1% rising to 16% and in option 2 by 1.1% rising to 16.8%. / As discussed in box 2 above, the theory of change for this intervention is that improved forest knowledge uptake will lead to policies that divert large scale agriculture away from forest areas on to degraded land. Some of this diversion will displace smallholder farmers. The analysis assumes that 50% of avoided deforestation displaces substance agriculture. This is included as a negative benefit at £221 per hectare.[97] / Option 2 Risks and uncertainties / HIGH: the costs of implementing forest polices are higher than included in this economic model. As discusses in box 2, the model presented here does not include negative benefits associated with lost revenue from agricultural expansion on to forest land (though this may be balanced in part by exclusion of positive benefits from avoided agricultural emissions). This risk will be mitigated by ensuring that forestry knowledge displaces agricultural expansion on to degraded land as far as possible (rather than preventing expansion). / Some attempt has been made to include the costs of implementing forest policies (that result from improved research dissemination). Table 5tests the sensitivity of the findings to increases in the cost of implementation per t/CO2e. Net present value is positive until costs reach £28 per t/CO2e. / Table 5 Sensitivity Analysis of Option 2 / Cost of implementation £2 per t/CO2e Cost of implementation £4.55 per t/CO2e Cost of implementation £10 per t/CO2e Break even / NPV (£million) 3,372 3,031 2,302 NPV is zero at £28 per tonne of emissions / Benefit: Cost Ratio (£) 1: 13 1: 6 1: 3 / Discount rate non-carbon costs/benefits 10%; carbon values constant at £14 per tonne CO2e; implementation costs £4.55 per tonne CO2e; knowledge uptake 10% improved to 2020 then 5% to 2030 / MEDIUM: International leakage - deforestation that is avoided through the programme could to be diverted to other areas as some countries benefit from improved knowledge and tools and others do not. This would reduce the net emissions saving benefits. / Table 6 below shows that even if 50% of deforestation is diverted elsewhere, option 2 has a net present value of over £1 billion. Option 2 continues to produce a positive net present value even with 99% diversion because the forest restoration component alone (which produces hectares of new standing forest) has a net present value on its own of £260 million (and benefit to cost ratio of £1.20 to each £1 expended). / Table 6: Value for money of option 2 under different assumptions about the area of deforestation that is diverted elsewhere / 0% hectares diverted 25% hectares diverted 50% hectares diverted Break even / NPV (£million) 3,031 2,289 1,547 Even at 99% Net Present Value of £272 million because restoration component alone has positive NPV of £260 million / Benefit to cost ratio (£) 1: 6 1: 6 1: 6 / Discount rate non-carbon costs/benefits 10%; carbon values constant at £14 per tonne CO2e; implementation costs £4.55 per tonne CO2e; knowledge uptake 10% improved to 2020 then 5% to 2030 / MEDIUM: Poor knowledge uptake pathways could reduce the total global deforestation area that benefits from the programme. Table 6 below tests this risk under three scenarios. Option 2 retains a positive net present value even when only 10% of global deforestation is impacted by improved research dissemination. / Table 7 Value for money of option 2 under different assumptions about the area of global deforestation that is impacted / 10% of global deforestation impacted 25% of global deforestation impacted 46% of global deforestation impacted Break even / NPV (£million) 705 1,764 3,031 NPV still positive when only 1% of global deforestation is impacted (because restoration component has positive NPV). / Benefit: Cost Ratio (£) 1: 6 1: 6 1: 6 / Discount rate non-carbon costs/benefits 10%; carbon values constant at £14 per tonne CO2e; implementation costs £4.55 per tonne CO2e; knowledge uptake 10% improved to 2020 then 5% to 2030; Note that costs as well as benefits change when you alter this variable as costs driven by cost per hectare of emissions / MEDIUM: Knowledge is not effectively taken up by decision makers in a timely manner. Table 8 tests the extent to which knowledge uptake is improved under the ‘with programme’ scenario. Option 2 still has a positive net present value even with a knowledge uptake improvement of just 1% over the 2012-2030 period. This risk will be managed by including conditions attached to funding mandating demonstration of effective mechanisms for improved knowledge uptake. / Table 8 Value for money of option 2 under different assumptions about improvement in knowledge uptake / Knowledge uptake improves by 1% Knowledge uptake improves by 5% Knowledge uptake improves by 10% falling to 5% Break even / NPV (£million) 499 2,390 3,031 NPV still just positive (benefit to cost ratio 1:2) when improvement is 0.1% over the whole period / Benefit: cost ratio (£) (rounded) 1: 6 1: 6 1: 6 / Discount rate non-carbon costs/benefits 10%; 46% global deforestation impacted; carbon values constant at £14 per tonne CO2e; implementation costs £4.55 per tonne CO2e; / note that in scenarios where fewer hectares are saved from deforestation, by construction costs will decreases as well as benefits / MEDIUM/LOW: Carbon values are lower than anticipated. In the base case the model uses extremely conservative assumptions relating to the value per tonne of carbon emissions. Table 9 tests the findings against different carbon value scenarios. The net present value of option 2 remains positive for all carbon values higher than £2.15 per tonne. / Table 9 Value for money of option 2 under different assumptions about the value of a tonne of carbon / Constant carbon values at £14 DECC low series DECC medium series Break even / NPV (£million) 3,031 5,402 9,763 NPV is positive for all carbon prices above £2.15 constant over the period / Benefit: Cost Ratio (£) 1: 6 1: 10 1: 17 / Discount rate non-carbon costs/benefits 10%; 46% global deforestation impacted; implementation costs £4.55 per tonne CO2e; / MEDIUM/LOW: the forest restoration component (managed by IUCN) is less successful than anticipated. Table 9 depicts the net present value of the forest restoration component only (carbon and ecosystems benefits minus UK costs plus implementation costs). As shown, the net present value of the restoration component is positive and relatively insensitive to changes in the non-carbon costs/benefits discount rate. Benefit-to-cost ratios are much higher than for option 2 as a whole. / Table 10 shows that the forest restoration component has a positive net present value and good benefit to cost ratio even when the number of hectares of forest restoration is much smaller than anticipated by IUCN. / Table 10: Option 2 sensitivity analysis of the restoration component on its own / 8% discount rate non carbon costs/benefits 10% discount rate non carbon costs/benefits 15% discount rate non carbon costs/benefits / NPV (£million) 43.07 41.12 38.02 / Benefit: Cost Ratio (£) 1: 11 1: 12 1: 13 / 50,000 hectares restored per annum 100,000 hectares restored per annum 150,000 hectares restored per annum Break even / NPV (£million) 11.65 26.38 41.12 Net present value is still positive even when the total restoration area is as small as 10,000 ha per annum, / Benefit: Cost Ratio (£) 1: 4 1: 8 1: 11 / Discount rate non-carbon costs/benefits 10% unless stated; implementation costs £4.55 per tonne CO2e; 2% of total restoration area attributed to DfID finance. / Option 2 Summary statistics / Table 11 summarises the expected results from option 2. As shown in table 11, the intervention retains a positive net present value and benefit to cost ratio under different discount rate scenarios. / Usually lower discount rates make investment projects seem more attractive because although costs are incurred upfront, benefit streams that are increasing in the future are less heavily discounted. In this model there are large and rising costs in the future (associated with implementing forest policies) which are discounted more heavily when a higher rate is used. The carbon benefits which are large and rising in the future are discounted at the lower 3.5%. Higher discount rates therefore produce a larger gap between costs and benefits in this model. / Table 11: Option 2 expected results under base case assumptions / REDD+ component Restoration component / Total number of hectares (2012 – 2030) 422,456 57,000 / Total emissions savings (t/CO2e) (2012 – 2030) 378 million 4 million / Table 12: Additional sensitivity analysis / 8% discount rate non carbon costs/benefits 10% discount rate non carbon costs/benefits 15% discount rate non carbon costs/benefits Break even analysis / NPV (£million) 2,911 3,031 3,234 NPV remains positive with discount rate of 1% / Benefit: Cost Ratio (£) 1: 5 1: 6 1: 9
D. What measures can be used to assess Value for Money for the intervention? / Value for Money is assessed by calculating the Net Present Value (NPV) and the cost benefit ratio of the options. The total incremental environmental, climate change and social benefits are higher for the recommended Option 2 with a benefit-cost ratio of £6 for every £1 of costs. / The difference in NPV and cost benefit ratio between options 1 & 2 shows option 2 as clearly offering a better return on investment. These results stand for all sensitivity analyses of option 2. / The risks under option 2 are more controllable than for option 1, as option 2 risks can be internally managed, with mandated safeguards attached to funding. The risks under option 1 are external to the programme and therefore can be less easily managed. / The opportunities for synergy between elements is far greater for option 2, with non-emissions benefits from option 2 contingent on external safeguards.
E. Summary Value for Money Statement for the preferred option 2 / The programme (Option 2) will give a high return of £6 for every £1 of costs (programme costs plus implementation costs are included). / UK’s effort will also contribute to broader results. Carbon emissions are avoided by reducing deforestation and additional carbon is further sequestered from the atmosphere by restoring forests to 385 million tonnes of CO2 equivalent. / £32 million worth of biodiversity and forest ecosystem goods and services are protected and restored. / Incomes or livelihoods worth £44 million to poor people (for example food, fuel, and fodder) will be generated by the efforts of the initiatives to which this intervention will contribute. / Table 12: options comparison / Option 1 Option 2 / NPV (£) -41 million 3,031 million / Benefit: Cost Ratio (£) N/A 1: 6 / Total hectares of deforestation avoided (2012 – 2030) 96,000 avoided deforestation 442,456 avoided deforestation / 57,000 forest restoration / Emissions avoided (t/CO2e) 81 million 382 million / Value biodiversity/ecosystems goods service (NPV, £) 3million 32 million / Value livelihoods (NPV, £) Included in ecosystems value 46 million / * Under base case assumptions (see analysis above; all non-carbon costs and benefits discounted at 10%; all carbon benefits discounted at 3.5%)
[59] IPCC 2003b Good practice guidance for land use, landuse change and forestry (GPG-LULUCF). In: Penman, J., Gytarsky, M., Krug, T., Kruger, D., Pipatti, R., Buendia, L., Miwa, K., Ngara, T., Tanabe, K. and Wagner F. IPCC-IGES, Kanagawa (eds.)
[60] Hardcastle and Baird (2008) for The Eliasch Review
[61] Simula. Analysis of REDD+ Financing Gaps and Overlaps. REDD+ Partnership. (2010)
[62] An Online Learning Network on FLR, Evaluation of a pilot event (2010). By Marjolein Mann, in cooperation with Cora van Oosten, Mirjam Schaap and Joitske Hulsebosch
[63] DFID. 2010. Multilateral Aid Review. This concludes that FAO’s impact at country level is dependent on individuals and not on institutional performance systems. FAO country offices tend lack a focus on forestry..
[64] Heuch, J., Ducenne, Q., and Sardi, R. January 2011. Independent review of NFP Facility administered by FAO. Rewview commissioned by the EC DGs ENV and DEV
[65] Valuation techniques applied to tropical forest environmental services. G. Lescuyer (2007). The estimate is for Cameroon and includes NTFPs, watershed benefits, option values and non-use values
[66] Poverty and Environment Network (PEN). 2011. CIFOR “More than a quarter of all sample households had cleared forest area for crops within the last year of the survey, with the most well-off 20% of predominantly smallholder households clearing 30% more than the poorest 20%. Such results do not lend support to the hypothesis that poverty drives deforestation.”
[67] ‘Until recently forest investments in Latin American countries were generally perceived as offering high risks, controversy and low returns. This situation now shows signs of changing, with PROFOR deserving at least some of the credit of having highlighted sector opportunities..’ (Wells et al, 2011)
[68] The Sydney Morning Herald. February 18, 2012. (See http://www.smh.com.au/environment/ conservation/carbon-cowboys-20110722-1hssc.html)
[69] IUCN staff, per comm
[70] Ecological functions can be defined as involving ecological and evolutionary processes, including gene flow, disturbance, and nutrient recycling, water flows and movement, sediment movement and predator-prey (‘food chain’) relationships, with social benefits that include water quality improvement, flood storage and reduced flood damage, shoreline erosion protection, opportunities for recreation and aesthetic appreciation, natural products for human use at little or no cost and preservation of major groups of microbes, animals, fish etc.
[71] Lou Verchot et al. 2010. Reducing Forestry Emissions in Indonesia. CIFOR.
[72] Poverty and Environment Network (PEN), 2011. CIFOR
[73] See http://www.iucn.org/about/work/programmes/forest/ fp_our_work/fp_our_work_thematic/redd/?8366/Mainstreaming-Gender-Considerations-into-REDD-Plus-Policy-Implementation-in-Ghana
[74] An Online Learning Network on FLR, Evaluation of a pilot event (2010). By Marjolein Mann, in cooperation with Cora van Oosten, Mirjam Schaap and Joitske Hulsebosch.
[75] One key informant recommended that its organisation carry out exit interviews at the end of each knowledge activity to elicit open discussions beyond what is politically correct and comfortable to document in writing. IUCN reported that key areas in which the learning network can be improved are: languages – having some activities in Portuguese, Spanish or French; creation of decentralized networks or country groups that may help engage people with a bad internet connection, more real-life events related and linked to the network to strengthen the network and provide members with an opportunity to meet in real life; tease out gender aspects and implications for network functions; there is a need to have a critical mass in a country not lone individuals; field learning sites can become static cases. Key lessons are also being learnt from the alliance with FC UK Research which has successfully re-invented its Research & Innovation Strategy
[76] Wells et al. 2011 An Evaluation of the Impacts of Selected Activities Supported by the Program on Forests. PROFOR .(PROFOR Evaluation Series. Impact Notes 1& 2. June 2011)
[77] The EU target of zero deforestation by 2030 is assumed to be optimistic; the analysis assumes a linear decline in deforestation rate to half its current rate by 2030. These assumptions are consistent with modelling work by Greig-Gran (2006) produced for the Eliasch and Stern reviews.
[78] CIFOR report that their programmes primarily target thirteen countries that together account for 46% of global deforestation
[79] CGIAR, 2010, p146
[80] $50M for 25 country inventories, equating to $2 million per country or £1.3 million. The Eliasch Review, 2008, p70
[81] Inventory running costs of $7-17M per year for 25 countries, and administering forest protection costs of $233-500M per year, giving a minimum of $240 for 25 countries or £6.23M per country. The Eliasch Review, 2008, p72
[82] Forsyth et al. 2007. IPCC
[83] Forests Resources Assessment Data 2011 (average 0.26 per country *15 = 3.85%)
[84] REDD+ country forest carbon stocks are site specific and can vary enormously. Studies of above ground carbon stocks produce average values of 225tC per hectare (Ferraro et al (2012) and 231tC/hectare (Lawson & MacFaul, 2010), with some estimates up to 435tC/hectare (Lawson & MacFaul, 2010). CIFOR estimate the above ground carbon stocks in the REDD+ countries their work targets of around 300tC/hectare (0.15-0.65GtC/yr from 0.5-1.7Mha, CGIAR, 2010).
[85] This appraisal assumes forest carbon stocks of 231tC/hectare equating to 845tCO2e/hectare (Lawson & MacFaul, 2010) (carbon dioxide equivalent). This is conservative as it excludes soil carbon stocks.
[86] Valuation techniques applied to tropical forest environmental services. G. Lescuyer (2007) within the report ‘Mainstreaming the Economics of Nature’ (TEEB, 2010). The estimate is for Cameroon and includes non-timber forest products, watershed benefits, option values and non-use values.
[87] CRP6 Ch2 p146 gives 1-25% range, 1-16% used to make the results more conservative
[88] Lawson & MacFaul, 2010. For example, proportion (x) rises from 1% to 1.1%
[89] Cross-Country Forest Study. Gill Shepherd, IUCN/UNFF. May 2012
[90] Lawson & MacFaul, 2010.
[91] Much of the forest landscape restoration programme’s target forest areas are less productive than humid tropical forest (the priority for avoided deforestation), with the least productive being African dryland forest.. The average above ground carbon stock of such dryland forests is 72tC per hectare. (Ferraro et al. 2012). The growth rate of these forests is low, and therefore the rate of carbon sequestration is low. However, enhancing forest carbon stocks through landscape restoration would broaden the range of countries able to participate in REDD+.
[92] Compiled from G. Lescuyer (2007) and others within the report Mainstreaming the Economics of Nature (TEEB, 2010)
[93] IUCN estimate that total potential value of ecosystem value for restored forests is £272 per hectare per year. However this includes carbon value (previously included in the analysis) as well as direct use values (included under livelihoods). IUCN estimate that ecosystems values minus carbon and direct use values are on average £56 per year.
[94] Bush et al, 2006
[95] CIFOR staff, personal communication
[96] Bush et al, 2006 – the average size of household across 639 study sites in Uganda
[97] The average return to annual food/subsistence crops in eight countries (Cameroon, DRC, Ghana, Bolivia, Brazil, PNG, Indonesia and Malaysia) with large areas of forest under threat from expanding agriculture and livestock sectors (Grieg-Gran, M. The Cost of Avoiding Deforestation IIED. 2008.Table 3)

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The majority of the programme involves indirect (not direct) procurement whereby the bulk of the programme finance (£18,000,000) is managed by three international bodies with straightforward transfers to them, where possible through existing framework arrangements held with DFID. (See section on Indirect Procurement below.) / A small part of the programme, not exceeding £500,000 a year (up to £2,000,000 over the full duration of the programme) will be directly procured when UK cross-government working group on international forestry and climate require catalytic, time-bound knowledge products that rapidly respond to a strategic priority, including procurement of independent programme monitoring and evaluation. / Under this component DFID will directly contract analysis and services of knowledge management and dissemination either through restricted open competition for amounts below the EU Procurement Threshold of £101,323 or, for amounts above that, through the Forest Governance Markets and Climate (FGMC) Framework Agreement, which has been established through an open competitive process following EU Directives and advertised in The Official Journal of the EU with a notice in The Economist.
B. How does the intervention design use competition to drive commercial advantage for DFID? / The majority of the programme is indirectly procured. Downward pressure has been brought to bear on overheads of the 3 international partners and all are in a process of benchmarking their internal unit costs at the recommendation of their boards. / Where DFID directly procures international forestry knowledge products that rapidly and opportunely respond to UK priorities on climate change and international development, it will assess offers against relevance, effectiveness, economy and efficiency criteria (economy being the quality and price of unit inputs; efficiency being the quality and quantity of output generated for the value of the inputs, and cost effectiveness being the how deliverable outputs contribute to the specific outcome).
C. How do we expect the market place will respond to this opportunity? / The service provision market currently is divided into 4 segments: / agents advocating around international forestry and REDD+ negotiations; / local and field project developers; / global and local scientific researchers; and / agents helping put knowledge into use. / While all the segments are linked, market supply is stronger in the first three segments. The indirect procurement or choice of core partners for the programme have put in place (and will be monitored against) policies for increasing their own relationships with segment four of the market, while bringing to bear world class expertise (in some cases exclusive to the organisations in question) that is internationally recognised as such (and independently evaluated as such). / By indirectly procuring the services of three dominant and proven knowledge providers in the third segment, it will increase the impact of market activity in the third segment and shift them to develop better linkages with local actors. It will also encourage suppliers that are in the market generally (both the dominant and smaller ones) to better combine expertise in forestry and climate scientific analysis with that of knowledge application. / By directly procuring some activities identified in-house that focus on putting knowledge into use, the programme will also encourage new, smaller suppliers to prove their capacity in delivering the fourth segment.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Output-based TORs and contracts will enable offers from a range of suppliers to be benchmarked against each other at the stage of mini-competition and selected on the basis of both technical and commercial criteria. / Evaluation criteria will include, for example, quality and unit cost of particular specialist technical knowledge and expertise to be supplied; unit cost per knowledge activity developed; past examples given of the supplier’s capacity for outreach at international policy events or to remote and difficult environments at country level.
E. What is the intended Procurement Process to support contract award? / Restricted, limited competition or through the Forest Governance Markets and Climate Framework Agreement (see FGMC Framework for details).
F. How will contract & supplier performance be managed through the life of the intervention? / Catalytic knowledge activities directly procured in rapid response to strategic priorities will not be for durations of longer than 6 months. The TORs for each activity will specify time-bound deliverable outputs. The DFID Forestry Team will assign responsibility within the team to manage each individual knowledge activity that is contracted and, in event of non-delivery or poor performance against any of the specified outputs, the payment for those outputs may be withheld until delivery is made.
Indirect procurement
A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The majority of the programme involves indirect (not direct) procurement whereby the bulk of the programme finance (£18,000,000 of the total £20,000,000) will be managed by three well-known international bodies. DFID will make straightforward transfers to these through three administrative arrangements in the form of Memoranda of Understanding, and where possible under existing framework arrangements held with DFID. / CIFOR and IUCN are not-for-profit, international bodies managing multi-donor contributions, including from DFID. The World Bank is a multilateral agency and PROFOR is an already established World Bank administered multi-donor trust fund. / The three partner agencies provide almost exclusive specialist services and are tasked internationally to provide the “global public good” of forestry knowledge. Independent reviews have assessed the level of competency in provision of this service as above that of other providers (indeed other providers being limited or in some cases non-existent). / The Center for International Forestry Research (CIFOR) is the world’s pre-eminent international forestry research organisation. It is the Lead Centre of the CGIAR international Research Program on Forests, Trees and Agroforestry. It has proven itself to be a solid performer in previous management of DFID finance. A memorandum of understanding with the CIFOR will enable a voluntary grant contribution (up to £8,000,000) to CIFOR under the existing CGIAR Fund Window 3 mechanism. / The Program on Forests works closely with the World Bank Group including the International Finance Coporation, with special access to World Bank Regional Geographic Operations and country offices. A recent independent evaluation of PROFOR concludes it is “high quality and effective”, achieving “impressive results and impacts from relatively modest financial resources in critical regions”.[98] With every pound PROFOR puts into a knowledge activity, it mobilizes a further 90p of additional finance and invest into its knowledge activities. / A memorandum of understanding with the World Bank will enable a grant contribution to the Program on Forests (PROFOR) multi-donor trust fund under an existing framework arrangement (up to £6,000,000). / The IUCN is present in 60 countries with a diverse portfolio of activities. It convenes more than 1200 Union Members made up of a mix of local NGOs and sovereign states, and can draw upon 10,000 volunteer experts (who make up the IUCN Commission). This provides a solid platform for organizing and facilitating the work of the Global Partnership on Forest Landscape Restoration. A memorandum of understanding with the International Union for Nature Conservation (IUCN) will enable a restricted grant contribution to the Global Partnership for Forest Landscape Restoration Secretariat. (up to £4,000,000).
B. Value for money through procurement / The PROFOR Secretariat houses the right technical expertise. An independent review in 2010[99] concluded this and that the World Bank’s systems for PROFOR were successfully managing an active portfolio of between 30 and 48 initiatives or knowledge products annually under the trust (with about a third to a half opening and closing each year); and that it provided opportune and strategic support for new initiatives in a timely manner with efficiency unmatched by other instruments. / The “framework outcome” is agreed by the PROFOR Advisory group, currently consisting of the European Commission, UK, Finland, GIZ, Italy, Japan, Netherlands, Switzerland. / The Center for International Forestry Research (CIFOR) is an international organisation included in DFID’s central database. It is a lean organisation providing exclusive global expertise and services in forestry that cannot be sourced elsewhere, with effective partnerships internationally, and accredited through the CGIAR system and the CGIAR Fund. / The International Union for Conservation of Nature (IUCN) hosts the small, agile and responsive Secretariat for the Global Partnership on Forest Landscape Restoration. / CIFOR’s current overhead is 19%. The Consortium of International Agricultural Research Centres (CGIAR), of which CIFOR is one of fifteen of members, aims to reduce and harmonise overheads to 15% or below (including the 2% Fund “cost sharing percentage”) within the next 2 years. / The World Bank cost recovery and administration fee for PROFOR trust fund is 5%. / The IUCN overhead for management of the GPFLR secretariat is [10%]. Both CIFOR and IUCN will carry out benchmarking exercises to assess the value they get for their administrative unit costs this year, their cost recovery approaches and compare value with similar bodies, including those of DFID itself.
[98] Wells et al, 2011. PROFOR
[99] Wells et al. 2011. Ex-post Review of PROFOR. Heuch et al 2010. EU external evaluation of PROFOR

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / KnowFor programme: Indicative Budget Profile / Outputs Year 1 / £ Year 2 / £ Yr 3 / £ Yr 4 / £ Total / £ / 1. PROFOR/WB 2,000,000 2,000,000 2,000,000 0 6,000,000 / 2. CIFOR 2,000,000 2,000,000 2,000,000 2,000,000 8,000,000 / 3. IUCN 500,000 1,000,000 1,500,000 1,000,000 4,000,000 / 4. Rapid Response 500,000 500,000 500,000 500,000 2,000,000 / TOTAL 5,000,000 5,500,000 6,000,000 3,500,000 20,000,000 / The total programme budget is £20,000,000 over 4 years, with an allocation of 30% to PROFOR to generate 120 knowledge products in 30 countries; 40% to CIFOR (including the 2% of total contribution to CGIAR Window 3 as the mandatory “cost-sharing percentage”) which manages two pre-eminent learning networks that will expand and/or deepen their coverage, the Poverty and Environment Network (PEN) and the Global Comparative Study on REDD+, (amongst a range of other networks, for example, on Non-Timber Forest Products (NTFPs)). and 20% to IUCN for the Global Partnership on Forest Landscape Restoration which consists of an on inline learning network and deployment of tools and techniques for restoration in 15 countries. / Through this programme UK would contribute about 7% of CIFOR’s budget, 23% of PROFOR’s budget and 2% to the costs of the broader Global Partnership on Forest Landscape Restoration (GPFLR). / About 10% of the programme budget will support between 2 and 5 directly procured knowledge products a year, and includes at least 1% of total budget from this output for external monitoring and evaluation with at least 2% of total budget to be spent on monitoring and evaluation across the various elements of the programme. / A knowledge product, that is the knowledge development, communication and deployment, including through face-to-face events at country or regional level, costs between £20,000 and £200,000 per product Each output will produce between 100 and 200 products in between 20 and 40 countries. The budget is estimated on that basis and its value for money appraised in the Economic Appraisal. / For outputs 1, 2 and 3 (PROFOR, CIFOR, IUCN) 6 monthly forecasts and scheduled payments are envisaged. Under output 4 contractors provide a monthly forecast by short email on the 15th of each month to the DFID Project Officer prior to invoicing at the end of each month. The budget for Output 4 will be planned against the cross-department International Forestry Team’s annual workplan and the expenditure forecast updated monthly.
B. How will it be funded: capital/programme/admin? / £20,000,000 will be allocated from DFID’s programme (R-DEL) budget as part of UK International Climate Finance (ICF). There is no contingent liability incurred or uncertainty associated with the proposed disbursements.
C. How will funds be paid out? / DFID will make in accordance with DFID Blue Book guidance: / six-monthly payments as laid out in the current administrative arrangement with the World Bank/PROFOR / six-monthly payments to the CGIAR Trust Fund Window 3 located in the World Bank for CIFOR / quarterly grant payments to IUCN.. / These payments will not be made in advance of need. / For directly procured contracts DFID will make payments against monthly invoices for completion of work against the specific, time bound deliverable products described in each contract., / Up-front payments will only be made where justification is made that meets the approval of DFID Accounts Department
D. What is the assessment of financial risk and fraud? / Financial risk is assessed as low. Each agency provides a management assertion and attestation of external auditor concerning adequacy of its internal control, with accounts independently audited annually. DFID will closely monitor the financial risk and potential for fraud throughout the life of the project and take appropriate action where necessary to mitigate the likelihoods of such cases arising.
E. How will expenditure be monitored, reported, and accounted for? / Costs for overall programme monitoring and evaluation are included within the budget for Output 4 (described above) and will probably be 2% of total budget. / CIFOR, World Bank/PROFOR and IUCN will provide quarterly unaudited financial statements within 90 days of quarter end; a management assertion and attestation of external auditor concerning adequacy of internal control with 6 months of fiscal year end; an annual progress report (presented at the respective annual Advisory Board Meetings) at the beginning of new calendar year; and a mid-year review on the work programme. / For output 4 short term contractors will provide financial expenditure reports monthly against a narrative report on the time bound deliverables and workplan in the contract. Monthly invoices will be sent no later than 30 days after the last day of the month for which the entity has incurred expenditure.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The cross-government Working Group on International Forestry and Climate (which is currently chaired on a rotating basis by DFID, DECC and DFID) will for the purposes of this programme convene operational steering meetings at least twice a year (more frequently if required), chaired by a DFID Forestry Adviser. It will plan priority work, ensure knowledge products from Outputs 1, 2 and 3 help inform UK’s international policy and country level operations, and review progress of work under the broader programme. / DFID will keep minutes of programme Steering Committee meetings on file. / Each of the partner bodies is responsible for delivering one or two of the programme outputs, and will meet amongst each other at least twice a year during key events to coordinate their work. The overall governance structure, operational guidelines, workplans, annual reports, that govern decisions on the portfolio of each entity and its resource allocation, are available on their respective websites. / The Director General of CIFOR reports annually to its Board of Trustees, chaired by Professor Hosney El-Lakaney, University of British Colombia with a UK member on the Board. CIFOR leads an integrated effort, together with the World Agroforestry Center (ICRAF) and other partners, that carries out 53 long term scientific research projects in the 5 areas of (i) management and conservation of forests and tree resources, (ii) landscape management for biodiversity conservation, environmental services and livelihoods, (iii) climate change adaptation and mitigation, (iv) smallholder productions systems and markets, (v) impacts of trade and investment on forests and people. / PROFOR Secretariat is a small unit housed by the World Bank Sustainable Development Network. The World Bank funds the PROFOR Programme Manager, who reports annually to the PROFOR Advisory Board on which UK has a seat, together with Finland, Japan, Switzerland, EU, Germany, Italy, The Netherlands, and is chaired by the World Bank.[100]The core Secretariat is further staffed by PROFOR-funded co-terminus positions. Its work programme encompasses 4 knowledge areas: livelihoods, governance, financing sustainable forest management and cross-sectoral themes / The Director General of the IUCN is accountable to the IUCN Council. The IUCN hosts the small Secretariat team of the Global Partnership on Forest Restoration Landscape and provides the Coordinator of the Partnership,. which is currently chaired by the Director General of the Forestry Commission Great Britain. The Partnership is guided by an Advisory Steering Committee made up of donors (such as The Netherlands, Germany and Uthe United States) and technical participants from the IUCN, the World Resources Institute (WRI), the Wageningen Center for Development Innovation, the GB Forestry Commission (FC), Tropenbos International, the Forestry Commission Ghana, the Forestry Service of India amongst others. The partnership is currently championed by Fernando Henrique Cardoso, a former President of Brazil, and by Göran Persson, a former Prime Minister of Sweden.
B. What are the risks and how these will be managed? / There are a range of risks identified in the Economic Appraisal as follows: / Despite the availability of information, the costs of implementing policies for more sustainable management of forests and to reduce deforestation are high and constrain implementation. This risk is high and will be partially mitigated by ensuring that knowledge that enables agricultural expansion on to degraded land is disseminated. / Countries benefiting from better information may reduce their deforestation, but “displace” this to other countries that do not benefit. This is a medium risk and to an extent mitigated by ensuring broader access to information and extending planning and discussion of knowledge and evidence across borders at regional and global levels. / Uptake pathways for knowledge are poor, for example knowledge does not reach decision-makers in a timely way. This is a medium risk and will be managed by including impact and user surveys in programme monitoring so that partners are mandated to demonstrate effective mechanisms for improved knowledge uptake as a “condition” of continued funding. / There is a risk that, if broader budgets to each entity shrink, less priority will be given to the way knowledge is communicated, understood and used, with a focus on maintaining core functions of research and less on dissemination of information. / However, tighter monitoring of the impact of each body will demonstrate the extent to which each is credible and generating useful knowledge. The annual advisory groups or boards for each entity will discuss and assess annual independent reviews of impact, of the communications strategy in place and the results of client satisfaction surveys to verify the confidence held in the services provided by each entity with respect to their key knowledge and learning networks and products.
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / DFID will draw upon the following monitoring and evaluation reports carried out by CIFOR, PROFOR and IUCN for its own overall independent annual review of this programme. It will quality assure their conclusions and, when timing allows, feed into them providing additional information drawn from further interviews. . In 2010 the EU also carried out a further independent review of international forest finance, including CIFOR and PROFOR; the programme might support a similar broad evaluation together with other donors. / The programme will also support the three organisations to carry out monthly monitoring of website traffic the specific the network and related sites; as well as evaluations of website views, unique visitors, page views, bounce rates and publication downloads. / PROFOR, for example, holds an individual progress record sheet on each of its 30 to 50 knowledge activities. Each sheet records the objectives, activities and outputs envisaged, progress to date, changes in planned outputs (of the knowledge product), a summary of the knowledge generated and put in to use, the policy framework and relevance of the knowledge uptake, including donor and government funded projects or international processes, implementation performance, next steps, replication potential, expenditures, additional co-financing[101]. The programme’s annual review will draw upon these records. / It will also draw upon the regular internal independent monitoring that the PROFOR Secretariat will commission to review the results of 10-20 selected activities in-depth that have been “completed” or “closed” in order to track results through to impacts and adjust PROFOR’s “impact pathway” or “theory of change” if necessary. This will include spot checks in the field. / The programme will draw upon CIFOR’s records as it tracks 53 different lines of research against “uptake pathways, specifically within that, the work on poverty and the environment and REDD+. CIFOR will measure the number of publications downloaded and distributed, aiming for,a download of 1 million key publications, with popular publications downloaded about 200,000 times (as was "Realising REDD+: National strategy & policy options"). / The programme will draw upon IUCN monitoring against 10 knowledge uptake indicators that its uses across its Intersessional Programme of Work as applied specifically to the Global Partnership on Forest Landscape Restoration. (For the IUCN “Comprehensive Monitoring Framework” see http://www.iucn.org/knowledge/monitoring_evaluation/policy/) / It will take into account in particular the progress made against a “knowledge index” (1 to 15 scale for limited to good progress) compiled from some of the following indicators: / # practices or items of knowledge used by surveyed projects, enterprises, persons / # people using 1 item of knowledge or practice / # practices/knowledge used more than once, replicated or used to significant scale with demonstrable impact on the ground / # of people surveyed who have accessed 1 knowledge product and passed it on to their constituencies / # of references by other organizations, networks, websites, in media / # of people who have joined 1 online learning network/forum, subscribed to newsletter, on twitter, etc / # of website hits, downloads, clips played, publications distributed / # of national and regional learning networks that have formed themselves and have asked to be nested within the global learning network [and the number of people, sites, hectares they represent] / # of comments, messages, queries, resources posted by participants / Amount of additional investment mobilised by initial £1 / Documented changes in practice and policy supportive of forests, REDD+ and people’s livelihoods / The following areas will be covered by monitoring and evaluation questions: / Reach: number of members, demographics, roles, ratio of experts to practitioners / Outputs: number of publications, models, terms, concepts, methods, dialogues, practices in use, decisions taken / Participation: number of messages posted, number of resources posted, obstacles to participation, level of trust / Change: improved productivity of members, types of benefits to and contributions from members / Relevance: of content, ownership, who are members, who are the lead organizations, does the community in question improve its knowledge and practice, does it stimulate initiatives, benchmarking, are members leaving and why / Culture of systematic internal evaluation and reflection: routine internal performance reports, questionnaires, studies. / Monitoring the above will help partners test their uptake pathways for knowledge and adjust them if they prove to be ineffective. / In addition, as partner organisations monitor along the uptake pathways they have laid out and starting from research through to use and impact, they will consider the extent to which application of specific knowledge can help reduce the cost of implementing policies for more sustainable land use management, and what further regulatory changes and market incentives need to be put in place. They will track the extent to which, on the one hand, better policies implemented by some countries, such as China and Brazil, are helping other countries raise the bar and reduce deforestation, or, on the other hand, whether they are helping exacerbate deforestation elsewhere. They will shape the participation in their knowledge discussion activities accordingly.
Logframe / Quest No of logframe for this intervention: 3409906
[100] Whose specific role is to integrate PROFOR findings into World Bank activities
[101] PROFOR expenditure report REFERENCES . Angelsen, A; Wunder, S; Babigumira, R; Belcher, B; Börner, J & Smith-Hall, C (2011) Environmental incomes and rural livelihoods: a global-comparative assessment Bush, G; Nampindo, S; Aguti, C & Plumptre, A (2006) The Value of Uganda’s Forests: A livelihoods and ecosystem approach CABI / FAO (2007) International Research on Natural Resource Management – Advances in Impact Assessment. CABI/FAO CGIAR (2010) Forests, Trees and Agroforestry: Livelihoods, Landscapes and Governance Chapter 2: Research Portfolio CIFOR (2008) CIFOR’s Strategy 2008-2018, Making a Difference for Forests and People. CIFOR (2011): Learning from REDD: A Global Comparative Analysis. June 2010-May 2011. Annual Report. August 2011. CIFOR DECC (2009) Carbon valuation in UK policy appraisal: a revised approach. DfID Annual Reviews of PROFOR Eliasch Review (2008) The Eliasch Review: Climate Change: Financing Global Forests EU Monitoring Report on PROFOR. April 2010. Ref: MR-11278002 FAO (2010) Global Forest Resources Assessment FC (2005) Science and Innovation Strategy, UK Forestry Commission Research Ferraro, P.J.; Lawlor, K; Mullan, K.L. and Pattanayak, S.K.(2012) Forest Figures: Ecosystem Services Valuation and Policy Evaluation in Developing Countries Review of Environmental Economics and Policy 6(1):20–44 GPFLR (2011) A World of Opportunity – The World’s Forests from a Restoration Perspective. GPFLR Brochure with Map of Restoration Opportunities. HM Treasury (2001)‘The Magenta Book: Guidance for Evaluation.HM Treasury Crown Copyright HM Treasury and DECC (2010) Valuation of energy use and greenhouse gas emissions for appraisal and evaluation. IFAD (2011) Rural Poverty Report IFPRI (2000) A Meta-Analysis of Rates of Return to Agricultural R&D. IFPRI; IPCC (2007) 4th Assessment Report. Intergovernmental Panel on Climate Change IUCN (2011) Project Outline – Meeting the Bonn Challenge in Rwanda, IUCN, August 2011 Lawson, S and MacFaul, L (2010) Illegal Logging and Related Trade: indicators of the global response Chatham House Lescuyer, G. (2007) Valuation techniques applied to tropical forest environmental services. LFP (2009) Community Forestry for Poverty Alleviation: How UK Aid Has Increased Household Incomes in Nepal’s Middle Hills. Household Economic Impact Study 2003 to 2008, DfID Livelihoods and Forestry Programme, Nepal. Mann, M (2010) An Online Learning Network on FLR, Evaluation of a pilot event (2010). By Marjolein Mann, in cooperation with Cora van Oosten, Mirjam Schaap and Joitske Hulsebosch. Millennium Ecosystem Assessment (MEA) 2005 Ecosystems and Human Well-being: Synthesis Report. Island Press, Washington, DC Monela, G.C. et al (2005) A study on the Social, Economic and Environmental Impacts of Forest Landscape Restoration in Shinyanga region, Tanzania by IUCN Eastern Africa Regional Office and the Ministry of Natural Resources and Tourism, Forestry and Beekeeping Division Mullan, K. and Kontoleon, A. (2008). Benefits and costs of forest biodiversity: Economic theory and case study evidence. Final report, July 2008 Pan et al. (2011) A Large and Persistent Carbon Sink in the World’s Forest. Science. PROFOR (2010) Manual for Social Impact Assessment of Land Based Carbon projects. Part II. Toolbox of Methods and Support Materials. PROFOR (2011) Making Benefit Sharing Arrangements Work for Forest Dependent Communities – Insights for REDD+ Initiatives. Policy Brief (on work in progress). PROFOR Proposed Work Program and Financial Projects Calendar Year 2011 Ratzer, D.A. (2008) Assessing the Impact of CIFOR’s Influence on Policy and Practice in the Indonesian Pulp and Paper Sector. CIFOR Impact Assessment Paper. Report of a consultancy on the assessment of forest landscape potential Wageningen Centre for Development Innovation, October 2010 Republic of Rwanda, statement delivered by Minister of Environment and Lands to the General Assembly of the UN. February 2011 TEEB (2010) Mainstreaming the economics of nature – synthesis report Valatin, G. (2010). Forestry carbon: valuation, discounting and risk management. Forest Research discussion paper. Roslin, Scotland. Wells, M.P. et al (2011) An Evaluation of the Impacts of Selected Activities Supported by the Program on Forests (globally and in Central America). PROFOR Evaluation Series. Impact Notes 1& 2. June 2011. World Bank (2002) Sustaining Forests: A World Bank Strategy World Bank (2006) Combating illegal logging and corruption in the forest sector