DEPARTMENT FOR INTERNATIONAL DEVELOPMENT
PAKISTAN

AAWAZ
STRENGTHENING VOICE AND ACCOUNTABILITY IN PAKISTAN PROGRAMME

BUSINESS CASE

 19th August 2011

Contents

	Abbreviations and Acronyms	iii
	Glossary, definitions and measures	iii
	Programme summary	1
	What support will the UK provide? / Why is UK support required? / What are the expected results?
	BUSINESS CASE
1	Strategic case	5
1	Context and need for DFID intervention / Impact and desired outcome / Evidence base and investigative approach / Developmental priorities / Fit with other strategic priorities / Feasibility of intervening
2	Appraisal case	14
	Determining critical success criteria / Feasible options / Appraisal of options / Measures to be use to assess VfM
3	Commercial case	31
4	Financial case	32
	How much will it cost / How it will be funded / How will funds be paid out / How expenditure will be monitored, reported and accounted for
5	Management case	35
	A. Oversight / B. Management / C. Conditionality / D. Monitoring and evaluation / E. Risk Assessment / F. Results and Benefit Management
	Annexes	43
	Annex 1 – Logical Framework

Abbreviations and Acronyms

BHC	British High Commission
CAR	Capability, Accountability and Responsiveness (Framework)
CBO	Community Based Organisation
CEDAW	Convention on the Elimination of All Forms of Discrimination Against Women
CSO	Civil Society Organisation
DTCE	Devolution Trust for Community Empowerment
ESCAP	UN Economic and Social Commission for Asia and the Pacific
FATA	Federally Administered Tribal Areas
GJP	Gender Justice Protection programme
GSDRC	Governance and Social Development Resource Centre
HMT	UK Treasury
ICED	Improving Citizen’s Engagement through Devolution
IDP	Integrated Delivery Plan for Pakistan (UK Government)
KP	Khyber Pakhtunkhwa (Province)
LGO	Local Government Ordinance
MDG	Millennium Development Goal
MDTF	Multi-Donor Trust Fund
MO	Management Organisation
NGO	Non-Governmental Organisation
PAC	Programme Advisory Committee
PACS	Poorest Areas Civil Society (Programme)
PARR	Programme Analysis, Research and Results (Facility)
PEOP	Punjab Economic Opportunities Programme
PITF	Political Instability Task Force
PrG	Procurement Group (DFID)
RF	Response Fund
RSP	Rural Support Programme
SECP	Securities and Exchange Commission, Pakistan
SNG	Sub-National Governance
STAEP	Supporting Transparency, Accountability and Electoral Processes in Pakistan
TC	Technical Cooperation
UN	United Nations
VAW	Violence Against Women
VfM	Value for Money

Glossary

AAWAZ	Means “voice” in many west and south Asian languages

Exchange Rate
£1.0= Rs137.5

PROGRAMME SUMMARY

AAWAZ
STRENGTHENING VOICE AND ACCOUNTABILITY IN PAKISTAN PROGRAMME

What support will the UK provide?

Programme resources and technical assistance to implement the AAWAZ - Voice and Accountability Programme

How much funding does the UK expect to provide?
Up to £34.3 million (cash prices).

Period of funding
Over 5 years (April 2012 to March 2017)

Value for Money data
The Economic Appraisal indicates a positive return to the UK’s investment.

Why is UK support required?
Over time, the Pakistani State has been unable to allocate sufficient resources to meet the development and security needs of the majority of its citizens especially women, young people, low status castes and religious and ethnic marginalised groups. As a result, over 50% of the population remains poor, under-educated, vulnerable to co-option by radical extremist groups and marginalised from the workings of the state. Gender inequality[1] and violence against women is endemic, and Pakistan has some of the worst social indicators in South Asia[2]. In addition to this, the population is set to increase by nearly half again over the next twenty years, leading to a massive youth bulge in search of jobs and even more rapid urbanisation.
[1] Pakistan is 3rd worst country in the world on Gender Gap Index (2010) by World Economic Forum. Also in UNDP’s Human Development Report (2010) , Pakistan is ranked 153 out of 155 countries on the Gender Development Index (GDI).
[2] For example, approximately 50% of children are out of school, 60% of women are illiterate and infant mortality is 71 per thousand live births.

UK support is required to assist Pakistan in becoming a stable, inclusive and tolerant democracy. The situation is urgent: the Millennium Development Goals (MDGs) are unlikely to be achieved if governance and society do not become more open and tolerant. In order to make progress, the social exclusion of the majority of the population from politics and governance must be addressed. Robust representation of the voices of women and other excluded groups in decision-making processes at all levels is required to strengthen opportunities for Pakistan’s resources to be distributed more fairly and equitably and for all its citizens to benefit.

What need are we trying to address?
We will address the gulf between the political classes and the people which threatens to destabilise the country further. This is exacerbated by the fact that the government has lost the trust of many citizens because of its inability to protect them from violence and militancy, and to deliver basic services[3]. Additionally there is a serious risk that social/ethnic/religious divisions in communities will lead to greater violence and lawlessness: these existing divisions are fuelling growing intolerance, and making minorities and women even more vulnerable. Strengthened inclusion of those currently excluded from political processes, and enhanced citizen capacity to demand access to health and education services, will build the social compact between citizen and state and lead to a fairer allocation of resources.
[3] the government has never delivered efficient public services in FATA

What will we do to tackle this situation?
Working through experienced locally based organisations, we will strengthen opportunities for ordinary citizens to engage in governance and hence increase their influence in policy and legislative dialogues. We will bring these organisations together around agreed programmes of work in 45[4] districts prone to local level disputes and disagreements. These districts will form about 75% of the total districts in Punjab and Khyber Pakhtunkhwa, and 30% of districts in Pakistan. The programme will also work at national level to strengthen the legislative and policy environments for women’s equality. Activities will:
[4] This is a critical geographical mass to achieve change. Areas to be chosen by AAWAZ team in consultation with virtual ‘synergies’ team led by the Sub National Governance team in DFID Pakistan.
- increase the safe participation of the excluded (women, ethnic and religious minorities, disabled) in politics and in local, provincial and federal governance structures, enabling them to play more robust roles in decision-making;[5]
  [5] DFID's new strategic vision for women and girls states that 'Increasing the power of girls and women includes enabling their active participation in political processes, and this will continue to be an important area of our work.”
- enhance tolerance of diversity and strengthen the capacity of communities to resolve disputes and differences peacefully without resort to violence;
- enable community members to work constructively together in inclusive ways to demand improved service delivery and to address other local problems;
- support a locally based facility[6] to develop a robust evidence base to stimulate debate and dialogue, build popular demand for reforms and changes in elite attitudes and behaviours, and maximise results across DFID programmes.
  [6] the Policy, Analysis, Research and Results (PARR) facility

We cannot achieve these outcomes through this programme alone. A comprehensive and integrated approach to implementation across DFID Pakistan’s programmes and with the wider HMG will be necessary. This will ensure that the results from the programmes are greater than the sum of their parts.

Are any other donors supporting this or similar projects?
The programme will complement and build on programmes of other donors, including the USAID funded Gender Equality Programme with Aurat Foundation and good quality community empowerment programmes and gender programmes implemented by NGOs such as Sungi, Strengthening Participatory Organisation (SPO) and Shirkhat Gah. Through its demand-side focus, AAWAZ will strengthen DFID’s own supply-side Sub National Governance and Health and Education programmes in Khyber Pakhtunkhwa and Punjab, and districts will be selected on the basis of complementarity with these programmes. Synergies will also be maximised with the existing support to citizens’ participation in more transparent elections (STAEP), and DFID’s support for stabilisation in Pakistan’s border areas.

What are the expected results?
In approximately 5000 villages and urban communities in the 45 districts, the programme will between 2012 and 2017:
Reduce incidents of local disputes in programme districts by 10% from the baseline, thus protecting the lives, livelihoods and assets of excluded groups and improving safety;
Increase by 20% the number of direct engagements between communities and local officials to seek improved delivery of health and education services to women and girls (liaising closely with DFID Education and Health programmes);
- Increase women’s representation and voice in political organisations by 20% (local and district) and 10% (provincial and national);
- Reduce tolerance of violence against women by 10%.

In addition, the programme’s advocacy campaigns will result in progress towards strengthened implementation of six key laws on gender equality, creating a framework for bringing Pakistani domestic law into line with the Constitution and Convention on Elimination of all Forms of Discrimination against Women (CEDAW).

What will change as a result of our support?
Pakistani politics will be more open, democratic and accountable, nationally and provincially in Khyber-Pakhtunkhwa and Punjab and in the 45 priority districts of focus. Violence against women will become less socially acceptable, the incidence will drop, and women and other excluded groups will be better able to participate safely in politics and in public spaces at local levels, and articulate demands on the issues that affect them. With effective oversight, communities will be better able to resolve disputes peacefully and work together for improved service delivery[7]. The generation and synthesis of robust evidence and its communication to political leaders/elites and Pakistani society will underpin strengthened citizens’ demands for reforms and changes. The programme will also enhance the capacity of participating civil society partners to work effectively on governance and accountability themes beyond 2017.
[7] John Gaventa and Gregory Barrett state that “Citizen engagement can be linked positively in a number of instances to achieving development outcomes, such as health, water, sanitation and education, as well as to democratic outcomes, such as building accountable institutions and making real national and international human rights frameworks. The challenge for donors and policy makers is how to support such engagement effectively." Development Research Centre, 2010: Mapping the Outcomes of Citizen Engagement

What planned outputs of the project are attributable to UK support?
The majority of the outputs will be directly attributable to UK support. Where AAWAZ is addressing complementary themes with other DFID programmes, monitoring indicators will be adjusted accordingly between the teams involved. Where other donors are also working in the same thematic and/or geographic areas, attribution of results will be assessed and agreed in advance. In real life, many complex interactions contribute to social and political changes: one of the tasks of the Policy and Analysis Research and Results (PARR) facility (see below) will be to analyse different factors and support analysis of findings to promote improved understanding to bring about sustainable reforms.

How will we determine whether the expected results have been achieved?
Rigorous monitoring against the logical framework will enable progress to be tracked effectively as the programme is being implemented. Because of the lack of robust evidence in this field, AAWAZ will be treated as an investigative as well as an implementing programme. The Policy, Analysis, Research and Results (PARR) facility will conduct rigorous evaluations and ensure that information is analysed, and evidence is developed, documented, disseminated widely to government counterparts, donors and civil society. At the same time it will be used to guide the AAWAZ programme as it evolves, and to maximise impact of the results across a range of interventions tackling improvement in government systems, gender equality and citizens’ empowerment.
AAWAZ
STRENGTHENING VOICE AND ACCOUNTABILITY IN PAKISTAN PROGRAMME

BUSINESS CASE

1. STRATEGIC CASE

A.	Context and Need for DFID Intervention

  1. Pakistan is a state which has experienced instability under both democratic and military led governments in its 64 year old existence. If it were to fail, it would have serious political and security implications for the entire region.

  1. Since Independence in 1947, the Pakistani State has been unable to allocate resources in ways which meet the development and security needs of its citizens, especially women, young people, and religious, ethnic and other minorities.[8] As a result, over 50% of the people remain poor, under-educated, excluded from participation in political processes and vulnerable to co-option by radical extremist groups.[9] Gender inequality and violence against women is endemic in the country,[10] and the population is set to increase by nearly half again over the next twenty years, leading to a youth bulge needing jobs. This will fuel increasing urbanisation (over 35% now, likely to pass 50% in 2030s), and a breakdown of traditional community links in urban centres. Much of the focus of this programme will be on rural communities, but it will also include urban and peri-urban districts.
    [8] Gazdar, H. (2007). Class, Caste or Race: Veils over Social Oppression in Pakistan.
    [9] Oxford Policy Management (2004) A quantitative assessment of social exclusion in Pakistan. http://www.eldis.org/assets/Docs/19405.html
    [10] Pakistan rated 3rd most dangerous country for women in a poll conducted by Thomson Reuters Foundation in 2011. http://www.trust.org/trustlaw/womens-rights/dangerpoll/

  1. Pakistan has been characterized as exemplifying the paradox of ‘growth without development’[11] because of its failure to achieve levels of human development commensurate with levels achieved by other countries at similar levels of per capita GNP[12]. There have been periods of robust economic growth, but the poor have not benefitted proportionately and growth is currently low.
    [11] Easterly, W. (2003). “The Political Economy of Growth Without Development: A Case Study of Pakistan,” in D. Rodrik (eds.) In Search of Prosperity: Analytical Narratives on Economic Growth. Princeton University Press, New Jersey.
    [12] ‘A Review of Social Protection in South Asia’, Naila Kabeer 2009,

  1. The inability of the State to meet the needs of all of its citizens has distorted governance in the country[13]. Fissures are developing in society, which together with existing inequalities are fuelling growing intolerance and community violence, and making minorities and women even more vulnerable. Low levels of government accountability are compounded by the prevalence of corruption, a weak justice system, and a poor security situation, particularly related to terrorism and crime. Pakistan is ranked 60th among 66 countries (lowest in South Asia) on the rule of law index[14]. Citizens are not hopeful that the current government will be able to deliver economic growth and prosperity[15] or basic services and the government is also criticised for its inability to protect citizens from violence and militancy[16]. The gulf between the political classes and the people threatens to destabilise the country and there is a serious risk that Pakistan will become more unstable.
    [13] See Farazan Shaikh ‘Making Sense of Pakistan’ 2009, and many others
    [14] http://worldjusticeproject.org/rule-of-law-index/
    [15] Global Barometer on Hope and Despair; Pakistan, Trend data: 1977-2010; Gallup Pakistan (www.gallup.com.pk ) and Gilani Research Foundation (www.gilanifoundation.com), According to this survey, 71% of Pakistanis think that the situation will stay the same or get worse in 2011
    [16] 30 Years of Polling on Crimes, Violence, Terrorism & Social Evils (1980-2010): Perceptions and Fears of the Pakistani Public; 2011, Gallup and Gilani, http://www.gallup.com.pk

  1. At community level, there are numerous small-scale disputes based on existing fault-lines of class, caste, religion and sex among others, which impede citizens coming together, articulating local priorities clearly and holding service providers to account.[17] These disputes can escalate into violent, larger scale conflict, attracting young people many of whom have few other options in their lives.
    [17] Ahmed, Z., 2010, ‘An Insight into the Peacebuilding Initiatives of PAIMAN’, Insight on Conflict; http://www.insightonconflict.org/2010/05/an-insight-into-the-peacebuilding-initiatives-of-paiman

  1. Weak governance, social exclusion and the limited capacity of citizens to develop co-ordinated demands to tackle resource allocation and improved service delivery are some of the reasons for continuing mass poverty in Pakistan. Although the World Bank classes the country as ‘low middle income’, it has some of the worst social indicators in South Asia: 17% of the population in 2008 was surviving on less than $1/day, 60% of women are illiterate (49% in India and 22% in Bangladesh) and infant mortality in 2009 was 71 per 1000 (50 in India and 41 in Bangladesh)[18]. On current trends, despite some modest improvements in primary school enrolment and literacy rates over the last 10 years, Pakistan is unlikely to achieve the MDGs.
    [18] UNICEF: http://www.unicef.org/infobycountry/pakistan_pakistan_statistics.html and UNESCO Institute for Statistics (2010), Adult And Youth Literacy: Global Trends In Gender Parity.

  1. Improved citizen engagement with the state, and especially reform of the patronage-based political system and improved access to the political decision making will help to improve governance.[19] For this to come about, a new and inclusive political compact is needed, which involves all sections of society. This requires women, young people and other excluded groups to be empowered to demand change, and for the state to respond effectively to the demands of all of its citizens for improved service delivery. Excluded groups, including women, will need to feel safe enough to become organised and involved in politics, local affairs and governance processes at all levels (community, district, province, nation). Community cohesion and tolerance will need to be strengthened so that local disputes are resolved peacefully and do not escalate into violence; and the attitudes and behaviours of elites will need to change (including the patron-client relationships which lock poor people into dependency). Laws on gender equality will also need to be strengthened and enforced at provincial levels as devolution progresses, in order to provide a framework for change, which will then be strengthened by demands from grassroots women and men calling for reform. The fast expanding electronic media will be used to raise issues of democracy and governance and encourage new ways of thinking about the future of the country.
    [19] DFID strategy paper on Realising Human Rights for Poor People (2000), for example, argues that rights will become real only as citizens are engaged in the decisions and processes which affect their lives. ADB also considers citizen engagement essential for good governance www.adb.org/documents/periodicals/gb/GovernanceBrief17.pdf

  1. A focus on Basic Services: the inability of the Pakistan government to deliver core services, including security, is widely recognised and is a cause of disaffection with the state. Poor performance has created space for other providers, including religious service delivery organisations, which are increasingly active in many parts of the country.[20] At times of crisis, the power and organisational capacity of these groups becomes apparent, such as during the floods in 2010. Radicalised religious organisations are also active on state education boards, and recent analysis indicates that the state education system is as important as religious seminaries in radicalising young people[21].
    [20] DFID Country Governance Analysis for Pakistan (2011) states that Religious CSOs have been prominent in delivering services but in some cases be linked to militancy.
    [21] C. Christine Farr, 2007. “Militant recruitment in Pakistan- a new look as the Militancy-Madrasa connection”. Asia Policy, No 4.

  1. Given that the state is less stable, peace-building and state-building work is needed to address issues of citizen engagement, representation and capacity to make demands, whilst at the same time providing provincial and federal governments with support to become more responsive and effective[22]. Contested religious values, ethnic divisions, insecure boundaries and other factors challenge the weakly understood notion of Pakistan as a nation-state. Working in this unstable context will require action at local, governmental and societal levels.
    [22] such as that being developed by DFID-Pakistan’s Sub National Governance programmes

  1. Achieving change will require an increase in the range of social actors engaged in political life, in order to shift the incentives, disincentives and constraints operating on the political elite. The AAWAZ programme will work through local level, experienced Pakistani organisations with strong track records in their fields. By bringing these organisations together around strategically focused programmes in 75% of districts in Punjab and KPK, DFID will drive aggregation of results to achieve transformational changes in the lives of women, girls and other excluded groups[23].
    [23] DFID-P’s own Gender, Justice and Protection and Increasing Citizens’ Engagement in Devolution projects, have developed successful advances at local levels – the challenge is to take to scale.

  1. The Pakistan CGA (2011) recommends that aid policy should support the recent positive influence of civil society in generating demand for a better social contract. The AAWAZ programme will encourage the growing urban, middle class and community based groups who want change, and are prepared to work together to achieve it, to apply pressure for more accountable government and make it more difficult for feudal elites to continue to dominate politics and resource allocation.

  1. The AAWAZ programme will support the UK Integrated Delivery Plan (IDP) for Pakistan by contributing to the first three pillars of DFID’s state-building and peace-building approach. The programme will work on community level disputes in conflict-affected and conflict-prone districts bringing direct benefits to women and other excluded groups, and at provincial and federal levels to strengthen laws and challenge elite attitudes and behaviours. The programme will act as a ‘backbone of support’ to other DFID Pakistan programmes, building the demand side for Education, Health, Border Areas, Punjab Economic Opportunities Programme (PEOP), Social Protection[24] and Sub-National Governance (SNG) activities. Over time shared results will be produced between these programmes and AAWAZ.
    [24] DFID also anticipates supporting the Benazir Income Support Programme (BISP) in future which provides modest cash grants to women only to overcome poverty-related constraints. AAWAZ will complement this by strengthening access to a range of rights-based services.

  1. The economic evaluation for the AAWAZ programme uses very prudent assumptions and shows that the return to DFID investment is positive; the net present value which demonstrates the gains to beneficiary households are higher than the amount DFID invested.
Impact and desired outcome

  1. The impact of AAWAZ[25] is a stable, tolerant, prosperous and democratic Pakistan. The desired outcome of the programme, by 2015/16, is that the fragile democratic process in Pakistan is strengthened and becomes more inclusive, and the state becomes more accountable to citizens’ voices. The programme will achieve this by:
    [25] ‘AAWAZ’ is the word for ‘voice’ in Urdu and several other languages in Western and Southern Asia.
- increasing the safe participation of the excluded (women, ethnic and religious minorities, and the disabled) in politics and governance structures at local, provincial and federal levels and giving them voice, thus enabling them to play more robust roles in decision-making[26];
  [26] Through the DFID-P GJP project, there are examples of successful approaches upon which to build
- enhancing tolerance of diversity and strengthening the capacity of communities to resolve disputes and differences peacefully without resort to violence[27];
  [27] Organisations such as South Asia Partnership Pakistan (SAP-PK) and Pakistan Initiative for Mothers and Newborns (PAIMAN) have numerous documented small scale approaches to peacebuilding www.sappk.org; www.insightonconflict.org
- enabling community members to work constructively together in inclusive ways to demand improved service delivery and to address other local problems[28]; and
  [28] DFID-P’s ICED programme has successfully demonstrated local level approaches community empowerment
- supporting a locally based facility to develop a robust evidence base to stimulate debate and dialogue, build popular demand for reforms and changes in the attitudes and behaviours of political leaders, and maximise results across DFID programmes.

  1. AAWAZ will focus on 45 dispute-affected or conflict-susceptible districts in Khyber-Pakhtunkhwa and Punjab provinces, and will also work at provincial and federal levels to change laws, attitudes and behaviours. To speed up change, a Programme Analysis, Research and Results (PARR) facility will synthesise evidence from programme activities in communities and districts and use it to enable modification of approaches, promote government reforms directly (i.e. through legal processes or organised lobbying), and maximise impact through media campaigns and underpin programme M&E.

  1. AAWAZ will not transform the democratic process in Pakistan on its own. It will demonstrate what can be achieved by reducing social exclusion, building peace and tolerance and broadening citizens’ participation and engagement in community affairs and local bodies to oversee public management and service delivery. AAWAZ will form a ‘backbone’ to complement other DFID Pakistan programmes, enabling the achievement of strengthened results through demand creation at community level.

Evidence base and investigative approach
  1. There is increasingly strong evidence that liberal democracies (i.e., fully democratic governments) are more likely than autocracies or transitional democracies to deliver economic growth, poverty reduction and stability, and meet the basic needs of their people over the long run[29]. Democracies based on inclusive political settlements, are more responsive to their citizens and generally make better progress towards the MDGs[30] than poorly governed, non-responsive ones. Moreover, democracies generally have higher growth rates than autocracies[31] and this generally gives better poverty reduction outcomes[32]. Effective governance is a key factor underlying economic growth[33] and poverty reduction[34].
    [29] Sen, A (2009) Development as Freedom, Oxford University Press.
    [30] DFID (2009) Building the State and Securing the Peace, Emerging Policy Paper, p.2
    [31] Low income democracies have average growth rates 30% higher than low income autocracies. See Halperin H, Siegle J and Weinstein M (2010) The Democracy Advantage: How democracies promote prosperity and peace.
    [32] World Bank (2005) Economic growth in the 1990s – learning from a decade of reform. Washington
    [33] Kaufmaan D. and Kraat, A. (2002) Growth Without Governance, World Bank Policy Research Working Paper No 2928.
    [34] www.adb.org/poverty/good-governance

  1. Furthermore, there is a growing body of evidence that shows improved gender equality can contribute significantly to economic growth by expanding the stock of human capital, raising labour productivity, improving agricultural productivity and attracting investment in physical capital[35]. While gender equality is a basic right that does not need economic justification, gender inequality is economically inefficient as well as democratically dysfunctional. Long term sustainable growth rates cannot be achieved without effective female participation.
    [35] See, for example, Gender Equality and Economic Growth; John Ward, Bernice Lee, Simon Baptist and Helen Jackson; Chatham House September 2010.

  1. In order to reduce poverty and achieve the MDGs, the underlying causes of conflict and fragility must also be addressed. Specifically in this programme, focusing on disputes at community level where impact is strongest for vulnerable groups. Of the 34 countries furthest from reaching the MDGs, 22 are in or emerging from conflict and fragility. One-third of all child and maternal deaths in developing countries occur in fragile states[36].
    [36] In less stable states child mortality is five times that of middle income countries, and almost twice that of low income countries (speech by Andrew Mitchell, Secretary of State, September 2010)

  1. The Political Instability Task Force (PITF) research,[37] based on Polity IV and other data concludes that fully democratic followed by fully authoritarian governments are the most stable, and transitional democracies are the most unstable. Pakistan has been erratically unstable, since 1955, with four transitions from transitional democracy to autocracy and three from autocracy to transitional democracy. The current government is already the longest serving civilian government since 1977. For transitional democracies to evolve into stable and liberal democracies, the PITF research suggests that they need to develop:
    [37] PITF (2003) Political Instability Task Force Report: Phase IV Findings .

- effective ways for citizens to hold government to account (e.g. strong civil society and media; robust state audit and oversight mechanisms; a robust compact between state and citizens);
- effective mechanisms for the smooth transfer of political power;
- political parties and organisations, which are inclusive of women, minority groups[38], young people and moderate opinion (and less based on parochial interests and factionalism)[39].
  [38] Minority groups reflect ethnic and religious groups, including Hindu, Christian and Sikhs religious minorities, but also Muslim minorities and those linked to caste related segregation.
  [39] Ulfelder J and Lustik M (2005) Modelling transitions to and from democracy. Paper prepared for the Annual Meeting of the American Political Science Association.

1.21.	The AAWAZ programme responds to these conditions through support to citizens and media in holding government to account, and through facilitating the participation in political fora by groups excluded from political processes, thus enabling them to become broader based and inclusive, and to demand services. At the same time, building community cohesion and peace will help to reduce instability resulting from local disputes and community based violence[40]. The STAEP[41] programme, supported by DFID, addresses the strengthening of mechanisms for the transfer of political power through free and fair elections.
[40] See for example: Key Findings from 2008 External Evaluation Youth in Peacebuilding and Community Decision Making Search for Common Ground, Nepal
[41] Supporting Transparency, Accountability and Electoral Process in Pakistan.

1.22.	The PITF evidence supports the overall AAWAZ design, but there are less robust conclusions in relation to the most effective ways in which these aims can be achieved. Findings from programme reviews and studies do indicate that empowerment, community peace-building and a reduction in violence against women (VAW) can significantly increase political participation of women and other excluded groups[42] and strengthen responsiveness of government to citizens’ voices[43], but rigorous evaluation or research studies of the different approaches to complex change factors have yet to be produced.
[42] The DFID-funded Western India Rainfed Farming Project, Phase 2 PCR (2006) notes that community empowerment of poor tribal communities led to the community ‘activists’ being elected to panchayats (the lowest level of local government) and that economically empowered women suffer lower levels of VAW. Similarly, in Bangladesh many activists from DFID-supported poverty reduction programmes (e.g., the Samata Land Rights Project; BRAC Challenging the Frontiers of Poverty Reduction) have been elected to Union Councils. In India, Reddy, C.S. and Manak, S., 2005, ‘ Self-Help Groups: A Keystone of Microfinance in India - Women Empowerment and Social Security’, Mahila Abhivruddhi Society, Andhra Pradesh (APMAS), Hyderabad show how many women participating in self-help groups go on to be elected to local panchayats.
[43] John Gaventa and Gregory Barrett Mapping the Outcomes of Citizen Engagement Development Research Centre, 2010

1.23.	This is partly due to challenges in measuring and defining concepts (e.g. empowerment) across programmes[44], in data collection (e.g. on VAW)[45] and in generalising from specific contexts (see independent evaluations of community peace-building programmes in Afghanistan, which demonstrate good outcomes but point out that more evidence is needed)[46].
[44] GSDRC (2010) Helpdesk Research Report: Community Empowerment Outcomes – South Asia.
[45] GSDRC (2011) Helpdesk Research Report: Violence Against Women and Political Engagement.
[46] Waldman M (2008) Community Peacebuilding in Afghanistan: The Case for a National Strategy. Oxfam Research Report.

1.24.	Given this lack of robust evidence, AAWAZ will partly be treated as an investigative programme. Monitoring and evaluation through the Management Organisation and the PARR (using a range of methods including randomised controlled trials) will be rigorous and ongoing to ensure that analysis can be carried out, lessons developed, documented and used to guide activities as necessary, and disseminated more widely in Pakistan and used to maximise impact[47]. The evidence is reviewed in more detail in the Appraisal Case (below).
[47] Rigorous monitoring and flexibility to adapt approaches are recommended in John Gaventa and Gregory Barrett Mapping the Outcomes of Citizen Engagement Development Research Centre, 2010

Developmental priorities
1.25.	Pakistan is a priority country for DFID. Over the next four years, it could receive £1.4 billion and become the largest recipient of UK aid[48]. DFID’s top priorities in Pakistan include building peace and stability and making democracy stick by improving poor governance and strengthening democratic principles[49]. The AAWAZ programme addresses both of these through a citizen lens. It will complement other programmes, which support: (a) electoral reform, (b) ‘state survival functions’ (e.g., federal and provincial budget reform and public management programmes in sub national governance; and access to justice and security in Border Areas); and (c) improved responsiveness of the state to citizens’ demands (e.g. major investments in primary and secondary education and maternal health).
[48] DFID (2011) Bilateral Aid Review: Technical Report, p.33-34. Increased aid will be linked to progress on reform by the Government of Pakistan as it takes steps to build a more dynamic economy, tackle corruption and bring stability.
[49] DFID (2011) Bilateral Aid Review Results: Country Summaries. P.21. The other two priorities are: (a) supporting economic stability and creating economic opportunities and (b) helping the state to deliver better quality services to the people who need them most.

1.26.	The AAWAZ programme will also complement the UK government’s £30 million contribution to the World Bank-managed Multi-Donor Trust Fund (MDTF), for post-crisis reconstruction and development in Borders Areas (Khyber Pakhtunkhwa Province, FATA and parts of Balochistan)[50].
[50] The MTDF will deliver on services+ economic development (PCNA strategic objectives 2 and 3). AAWAZ will strengthen the ability of citizens, to voice needs and hold service providers to account. (PCNA objective 1).

Fit with other strategic priorities
1.27.	The AAWAZ programme will help to strengthen community engagement with local government in Pakistan, which is one of the UK government’s key Strategic Objectives of its Integrated Delivery Plan (IDP)[51], by ‘[building] the strong communities and institutions [in Pakistan] upon which democracy rests’[52]. It reflects UK Priorities outlined in the Peace Building State Building Framework (2010), and the Capability, Accountability and Responsiveness (CAR) framework. AAWAZ also reflects the UK Coalition Government’s ‘Big Society[53] concept by empowering excluded communities to hold authorities accountable and take more responsibility to do things for themselves.
[51] The Integrated Delivery Plan has been designed and agreed between HMG departments in Pakistan, namely DFID, FCO, MoD and UKBA
[52] Quoted in the News 20/10/10 from a speech by Foreign Secretary, William Hague.
[53] Only when people and communities are given more power and take more responsibility can we achieve fairness and opportunity for all.’ www.cabinetoffice.gov.uk/media/407789/building-big-society.pdf

Feasibility of intervening
1.28.	DFID is one of many bilateral donors to Pakistan. It has supported community empowerment programmes for over 20 years and has partnered civil society organisations in many conflict-affected and conflict-susceptible districts (in terms of community violence), and in provincial and national campaigns (e.g. on the 2006 changes in the Hudood Ordinance, which prescribed an interpretation of Shari’a law punishments for various offences and was used against women)[54].
[54] The Hudood Ordinance enforced shari’a punishments mentioned in the Quran and Sunnah for Zina (extramarital sex), Qazf (false accusation of zina), Offence Against Property (theft), and Prohibition (the drinking of alcohol). It was replaced in 2006 by the Women’s Protection Bill.
1.29.	By scaling up successful smaller interventions and building on best practice, AAWAZ aims to give political voice to women and excluded groups and to increase demands on government to provide them with services[55]. Other DFID (and other donor-supported) programmes in Khyber-Pakhtunkhwa and Punjab provinces aim to strengthen the capacity of provincial government’s education, health and justice systems to respond to citizens’ demands. The AAWAZ programme team has had a number of discussions with the Planning Commission, specifically the Social Sector Member, and the Prime Minister’s Special Assistant on Social Sectors, which support the programme.
[55] A number of local level examples exist through the work of DFID’s existing Gender Justice Protection programme (Quest Doc 3128629); and examples from PAIMAN (http://www.insightonconflict.org/); SAP-PK (www.sappk.org)
1.30.	AAWAZ will be managed by a Management Organisation or MO (a consultancy firm with a proven track record in implementing voice and accountability programmes in Pakistan or neighbouring countries). It will partner with leading Pakistani civil society organisations working on gender, social exclusion, peace-building and research and analysis. Although civil society in Pakistan is not as strong as in some other countries in the region, it is considered that there is sufficient capacity in the country to implement the programme[56].
[56] See discussion on the relevance and impact of Pakistani civil society in Annex 3: Institutional Assessment document produced by HTSPE for the Pakistan Civil Society Programme 2009; Quest document 2298658
2.	APPRAISAL CASE

A.	Determining Critical Success Criteria
2.1.	The Impact and Outcome of AAWAZ are as follows:

Impact:	Stable, inclusive and tolerant democracy in Pakistan.
Outcome:	Democratic processes in Pakistan are more open, inclusive and accountable to citizens.

2.2.	Pakistan is experiencing increasing social and political tensions. Elite group capture and control of access to many resources leaves over half the population excluded and poor. Exclusion is deeply rooted in the Pakistani social, economic and political experience. It is based on many factors including how wealth and other resources have been divided up over many years and used to reward loyalty, thus fuelling schisms in society based on class, gender, religion, ethnicity and clan.[57] Exclusion underpins powerlessness and hampers poverty reduction efforts.
[57] Hooper E and Hamid I (2003) Scoping Study on Social Exclusion in Pakistan, DFID Pakistan.

2.3 Bearing in mind the above, the following Critical Success Criteria were developed to support evaluation of feasible options (Table 1 below).

Table 1: Critical Success Criteria

Will the feasible option:		Weight

1.	Achieve reform : strengthen the responsiveness of duty bearers in Pakistan to be more open, inclusive and accountable to citizens?	5

2.	Tackle social and cultural barriers: address barriers that prevent women and other marginalised groups from engaging safely in politics and accessing services?	5
3	Support community empowerment: enable communities to resolve local scale disputes?	4

4	Improve service delivery: build the responsiveness of state providers to demands to deliver better services?	4

5.	Generate and use evidence: maximise impact of results and analysis coming out of the programme?	3

6	Build sustainability, in order that the outcomes and impacts are sustainable?	3

7	Add value to existing DFID projects and programmes, and those of other donors?	2

B.	Feasible Options
2.5.	Building on analysis developed for a DFID ‘Civil Society’ programme over the last 2 years, a review was undertaken of the changes needed to achieve the impact of a stable, inclusive and tolerant democracy in Pakistan. This identified a number of possible approaches, of which i) promoting gender equality in politics, ii) supporting community tolerance and peace; and iii) building the capacity of citizens to demand change as being the most critical to the achievement of the objectives, feasible options for DFID, and not covered by other programmes.

2.6.	The three options were considered separately and together, and additionally a ‘do nothing’ scenario was evaluated (see Section C).

1.	Base Case/No Change - Elites will continue to control most of the resources, excluded groups will remain marginalised, the Taliban and other extremist groups will increase their influence and social, political economic difficulties will persist.
2.	Increasing gender equality in politics and reducing VAW at all levels (community, district, province, nation).
3.	Building tolerance and acceptance, and community cohesion by supporting citizens and communities to resolve disputes peacefully through locally recognised mediation mechanisms.
4.	Strengthening community capacities to work together for common solutions to problems, monitor local authority budgets and articulate strengthened demand for services.
5.	Building inclusive, proactive demands for reforms and services from communities (Options 2 + 3 + 4 combined) by reducing VAW, building women’s involvement with political processes and by enabling communities to address disputes and work in more integrated and inclusive ways to achieve accountability from local government administrations.

Theory of Change
2.7.	The outcome of the AAWAZ programme is that democratic processes in Pakistan are more open, inclusive and accountable to citizens (by 2017). This will contribute to achievement of the impact of a stable, inclusive and tolerant democracy in Pakistan. The theory of change is summarised in Figure 1 (p.18).

2.8.	Achieving the outcome will mean increasing the range of social actors engaged in political life so as to shift the incentives, disincentives and constraints operating on the political elite.  The growing urban, middle class and community based groups who want change, and are prepared to work together to achieve it, will apply pressure for more accountable government and make it more difficult for feudal elites to continue to dominate politics.

2.9.	Global evidence indicates that consolidating democracy requires key institutional changes, including: (a) more open apex politics with smooth transfers of power; (b) stronger accountability bodies; and (c) the consolidation of issues-based political organisations.   Aawaz will make a significant contribution to pushing greater reform and openness in these three areas by:

i.  Increasing the range of social actors in politics through greater gender inclusion, by empowering women to participate in community and political organisations; building the capacity of women in elected bodies at all levels and others to advocate for change; and raising the awareness of decision-makers on the importance of giving women voice in political society.
ii.  More co-ordinated issues-based politics through community cohesion and tolerance by involving citizens and communities, including excluded groups, in resolving disputes peacefully, and working together for common solutions in community conflict-prone districts.
 iii. 	Greater political accountability by building the capacity of AAWAZ’s civil society partners to support women and other excluded groups in holding government to account during the programme and beyond, including demanding services.
iv.  Encouraging issues-based politics that draws on evidence and advocacy by generating and synthesising evidence from AAWAZ and other DFID programmes, testing approaches and using evidence to advocate for government reforms, including through media campaigns, and bring pressure on decision-makers for greater accountability.

2.10.	These four outputs are designed to influence key decision-makers (elected politicians, officials and others) actively to support women’s and excluded people’s rights, thus strengthening the demand side of governance. The three key outcomes of this process will be:
- implementation and enforcement of improved laws so that women and other excluded groups can achieve their rights and entitlements;
- a more tolerant society in which women and excluded groups can participate more fully in politics;
- improved access to priority government services for women, other excluded groups and poor communities.
2.11.	Outputs 1 and 2 both aim to reduce the violence and threat of violence, which is used to exclude women and religious and ethnic minorities from society, and will involve addressing deep-seated norms and attitudes in society.

2.12.	As was noted above (para. 1.17 in Strategic Case), experience from Pakistan and other countries supports the approach proposed under Outputs 1 and 2, although most evaluation evidence to date is context specific. In view of this, a rigorous learning/ evaluation programme (the Policy Analysis, Research and Results facility - PARR) will be established to generate robust evidence on what works and does not work and use this in advocacy campaigns targeting key decision-makers.

2.13.	Pakistan is an unstable democracy, which has experienced long periods of military rule over the last 60 years. If the country is to make the transition to the impact of a stable, inclusive and tolerant democracy, the international evidence (e.g., from the PITF) indicates that it will need to ensure it has in place (a) effective ways for all citizens to hold government to account; (b) inclusive political parties and organisations, involving women, minorities and young people; and (c) effective mechanisms for the smooth transfer of political power. AAWAZ is designed to make an important contribution to (a) and (b) and complementary initiatives targeting the other two pillars of DFID’s State Building and Peace Building framework (especially ‘state survival’ functions, and a more responsive state) will be developed through the Sub National Governance and Border Areas programmes[58] and through major health and education programmes.
[58] strengthening public management in Khyber Pakhtunkhwa and Punjab, reducing conflict and strengthening access to security and justice in Border Areas

2.14.	A critical assumption, which will be carefully monitored, is that the traditional elites in Pakistan are prepared to cede some of their power. Evidence indicates that elites do not willingly cede power, but that particular circumstances may encourage or induce them to do so[59]. For example, a recent analysis of the 18th Amendment to the Constitution of Pakistan (on devolution of powers) argues that elites were prepared to concede ground as no one political party wished to be seen as breaking an important historical consensus[60].
[59] GSDRC Helpdesk Research Report, 15/04/2011
[60] Haris Gazdar, ‘Democracy in Pakistan: The Chasm’ Economic and Political Weekly, May 29 2010

2.15. AAWAZ is a medium to high risk programme and important assumptions are needed for the outputs to lead to achievement of the outcome and the outcome to the impact. These are as follows:
Output to outcome assumptions:
- Government and other service providers are willing and able to respond sufficiently to increased levels of demand from women and other excluded groups for services;
- Complementary DFID and other donor-supported programmes in health, education and governance are able to strengthen service delivery sufficiently;
- Parliamentarians and justice system actors are open to pressure to enact and enforce legislative reforms;
- Media campaigns are effective in changing public attitudes and can bring about increased tolerance;
- Politicians and other decision-makers are willing and able to respond to evidence-based media campaigns and implement evidence-based policies;
- Conservative groups accept or are unable to prevent greater participation of women and other excluded groups in politics and public spaces;
- Community groups are able to overcome divisions and work cooperatively for shared priorities.
- Citizens’ desire for change motivates them to take action
Outcome to impact assumptions:
- Political will exists to consolidate and strengthen inclusive democratic processes and tackle violence and exclusion;
- Elites will perceive it as in their interests not to block all efforts at reform;
- Donors continue to support efforts to establish and consolidate a stable, inclusive democracy in Pakistan;
- Concerted actions are taken to build the state and build the peace in Pakistan;
- A critical mass of Pakistani citizens across the country is proactive in advocating for democracy.
2.16.	The design team considers that the output-to-outcome assumptions are realistic and it should be possible to achieve the outcome, if all the outputs are delivered effectively. The outcome-to-impact assumptions indicate the scale of the task if Pakistan is to become a stable, inclusive and tolerant democracy.
ACTIVITIES (to be finalised in inception phase)			OUTPUTS			INTERMEDIATE OUTCOMES					PURPOSE/ / OUTCOMES		GOAL/ / IMPACTS

- Activities to ensure VAW reduced, legislation to protect women enforced; campaigns against VAW. / - Activities to ensure women are included in community other organisations; / - Activities to build capacity of women and men in elected bodies at all levels to advocate for change / - Activities to build sustainable lobbying groups around interests of the excluded			1. Gender equality in politics / Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab			Less tolerance of violence against women. / Greater participation and ‘voice’ of women in politics at all levels.					Democratic processes in Pakistan are more open, inclusive and accountable to citizens.		Stable, inclusive and tolerant democracy in Pakistan.

- Activities to strengthen/ establish community mediation committees in villages and urban communities to resolve disputes and build tolerance. / - Training of young people as peace activists / - Peace campaigns and citizen’s peace committees at district level. / - Social, cultural, sports events.			2. Community cohesion and tolerance / Citizens and communities, better able to resolve disputes peacefully, and inclusively and work together for common solutions/ make demands on government in Khyber Pakhtunkhwa and Punjab			Less tolerance of violence against socially excluded groups. / Greater ‘voice’ and participation of religious, ethnic other minorities in politics at all levels.					Key decision-makers pro-actively support women’s and excluded people’s rights and respond to their demands			Improved laws on gender and social equality enforced / Improved tolerance in society at large. / Better access to govt services for women and other excluded groups		Women and socially excluded groups making a difference to political agendas / Transparent and effective accountability mechanisms / Smooth political transitions

Activities to develop/strengthen local groups (CCBs, VNCs, others) to: / - apply for funding for local projects, / - strengthen knowledge of budgets, / - monitor spend public service delivery; / dialogue with local authorities			3. Demand for services / Citizens groups working through govt and non-gov instruments to monitor budgets and spending, and articulate demand for services in KPK and Punjab			Authorities providing more information, spend more accountable / Service delivery better (health, education)		Figure 1: THEORY OF CHANGE / Key / Grey boxes = Logical framework Impact, Outcome, Output and Activity statements / Yellow boxes = Intermediate outcomes, outcomes or impacts

- Generate and synthesise evidence from outputs 1, 2 and 3 and other projects / - Commission research to test emerging findings / - Develop and test new / approaches / - Communicate evidence strategically using media			4. Evidence and advocacy / Evidence on ways to increase gender and social equality generated and communicated to policy makers in KPK and Punjab			Politicians and the general public better informed on importance of tackling gender and social exclusion.

Relevant Information and evidence

Social
2.17.	Social exclusion is deeply rooted in the social, economic and political experience of Pakistan. It is based on class, biraderi (clan), caste, ethnicity, hereditary occupational group, access to land ownership and productive resources, and gender. Socially excluded groups in Pakistan form “the 80%’ – those excluded from both development benefits and the ability to earn an income which enables other than basic survival.”[61] Exclusion underpins powerlessness and poverty.
[61] Emma Hooper, Imran Hamid, 2003 ‘Scoping Study on Social Exclusion’ for DFID Pakistan,
2.18.	At local level, communities are fractured by fault lines such as caste, class, religion, ethnicity, age and gender. These divisions cause frequent small disagreements which on occasions escalate to become serious disputes. They destroy community cohesion and foster distrust and intolerance, so that in many parts of the country communities have little willingness or capacity to work constructively together to prioritise needs and articulate demands. Particular groups (such as women, young people and minority religions) have become disenfranchised - their voices are not heard.
2.19.	This is significant in a context where government has consistently failed to deliver the services for which it is responsible. Despite being a low middle-income country with significant periods of growth over the last 20 years, approximately half of Pakistan’s children are out of school and over 60% of these are girls. In some parts of the country, only 3% of women are literate. Pakistan’s maternal mortality rates are similar to those of poorer African countries[62].
[62] Sources: World Bank 2009, latest UN MDG data
2.20.	Strengthened citizens’ voices and greater engagement of women and other excluded groups in political processes (as citizens, voters and representatives) is needed to deepen democracy, build accountability and motivate action for improved legislation and decision making. The success of the lawyers’ movement in politically mobilising segments of an emerging young urban lower middle class during the last days of the military regime indicates that such approaches can be effective.
2.21.	There is evidence to show that putting pressure on local government structures to deliver can improve services, although results are not conclusive and more analysis is necessary[63]. What is clear is that a careful analysis of approaches is necessary, and robust monitoring to identify potential obstacles. However, in the context of the 18th Amendment, which underpins greater devolution to Provincial Governments, there are opportunities for more cohesive and more representative communities to be articulating more successfully for strengthened government delivery of services at local and district levels. This will be carefully monitored using randomised controlled trials and other mechanisms to ensure that results are understood and course correction can take place.
[63] See, for example, Rocha Menocal, A and Sharma, B 2008 ‘Joint Evaluation of Citizens’ Voices and Accountability Report’, DFID, London; also John Gaventa and Gregory Barrett Mapping the Outcomes of Citizen Engagement Development Research Centre, 2010
2.22.	Pakistan’s gender equality indicators are among the worst in the world[64], and women’s exclusion from society outside the home is backed by religious extremism, cultural and social norms, violence against women and, in some cases, a discriminatory legal framework. Women’s access to justice is generally poor. Pakistan has signed and ratified CEDAW[65], but has yet to implement all of the requirements, and is behind on reporting.
[64] For example, Pakistan has been in the bottom three countries since the World Economic Forum Global Gender Gap Index began in 2006.
[65] The Convention for the Elimination of all forms of Discrimination Against Women
2.23.	Equal treatment of women and their more equal participation in public life are mandated under the Constitution of Pakistan. Violence against women (VAW), which affects between 80 and 90 percent of Pakistani women,[66] is one of several factors that constrain women’s empowerment and engagement in social and political processes[67]. There is currently no law in place that specifically outlaws VAW, and other laws that should protect women either do not exist or are weakly implemented. Legal reform, changes in the women’s machineries at provincial level and implementation of reformed legislation are all important activities towards reducing VAW. It is as important to make women and men more aware at community and family levels in order that VAW becomes socially unacceptable, and women are able to leave their homes and play fuller roles in local politics and decision-making without fear of reprisal.
[66] # Human Rights Watch (1999) Crime Or Custom? Violence Against Women in Pakistan http://www.hrw.org/legacy/reports/1999/pakistan/
[67] Ertürk, Y. 2008 ‘Violence against Women: From Victimisation to Empowerment’ UNESCAP
2.24.	There is evidence to show that when women are able to be more actively engaged in community and polity fora, their presence changes the way that things are done and the issues that are addressed. In some cases, strengthened participation by women has supported broader, more responsive policy making, reconciliation between opposed groups and strengthened transparency[68].
[68] Institute for Inclusive Security 2009 ‘Bringing Women into Government: Strategies for Policy Makers’ No.1

Political
2.25.	The political regime in Pakistan has changed since the 2004 “Drivers of Change” analysis but the main structural impediments (institutions impervious to pro-poor change, entrenched power relations and weak political parties), still characterise the political situation.[69] Following the 2008 elections, the federal government has been led by a weak coalition, on occasions divided by internal contradictions. These contradictions stem less from ideological differences than they do from the competition for power. Rather than between right and left, the clearest ideological division in Pakistan is between the Islamist and secularist parties. Islamist parties are not very significant electorally but they have been able to influence the national discourse.
[69] Khalid Nadvi and Mark Robinson, 2004 Pakistan Drivers of Change, Synthesis and Policy Implications, Institute of Development Studies University of Sussex (Commissioned by DFID).
2.26.	The 18th Amendment to the Constitution provides for greater devolution of responsibilities to provincial governments, and provides a platform from which the state can begin to reconstruct improved state-society relationships and build stronger political settlements. The Amendment aims to roll back the powers of the Presidency, introduced by successive military regimes and re-empower provincial governments. Although formally completed there is still confusion over the systems that should be set up (e.g. the division of roles and responsibilities between federal and provincial governments) and the budgets that ministries will receive.
2.27.	Constitutional protection to the Local Government Ordinances (LGOs) expired at the end of 2009, and appointed administrators are still in place at the various tiers. The perceived inadequacy of the government response to severe flooding in July 2010 has been linked in part to the absence of representative local structures[70].
[70] See many press articles by Sarwar Bari, Daniyal Aziz and Human Rights Commission of Pakistan
2.28.	In this local governance vacuum there are opportunities for organised communities to influence service delivery through clear articulation of priorities, constructive engagement with structures and willingness to seek local solutions.
2.29.	Government-civil society/citizen relations in Pakistan over the years have largely been determined by the nature of the government in power and the internal and external situation of the country. The state has been largely comfortable with NGOs that restrict themselves to traditional activities such as welfare, relief or service provision. However, the state has generally discouraged non-profit organisations from social and political advocacy. A recent report by the Pakistan Centre for Philanthropy reports[71] that effective government-civil society collaboration is emerging in areas such as health, education, water, sanitation, physical infrastructure and including rural support programmes, gender and environment.
[71] www.akdn.org/publications/civil_society_pakistan_collaboration.pdf

Institutional
2.30.	Three institutions are central to the way the State and society interact in Pakistan: the political parties, the bureaucracy and the military.
1. Political parties have encountered challenges in guiding policy and to holding the bureaucracy to account for poor service delivery implementation of reforms, partly because their appeal for their constituents derives partly from patronage and not from the efficient delivery of public goods.
2. The bureaucracy: under the structure of rules and regulations inherited from the colonial period, power and decision making resides with the bureaucracy. It is difficult for citizens and parliamentarians to monitor bureaucratic[72] performance. The Pakistan CGA 2011 recommends that service delivery initiatives should be underpinned by independent monitoring involving civil society organisations that seek to build consensus and hold state institutions to account.
  [72] Khalid Nadvi and Mark Robinson, op. cit.
3. The military, stands somewhat, but not entirely apart from these processes during periods of democratic rule but has intervened and run Pakistan for 33 of the 64 years since Independence in 1947[73]. Its growing corporate interests have been described as ‘military capital that is used for the personal benefit of the military fraternity …. [as] a completely independent genre of capital’[74]. Its operations exist at every level, from the individual unit to the military’s charitable welfare foundations. This section of the Pakistan economy is exempt from parliamentary oversight and public accountability. Nevertheless, there have been occasions when civil society has persuaded the military to release public resources. The Pakistan Fisherfolk Forum led, and won a campaign to release fisheries the Rangers held in Badin and the army has faced strong resistance over attempts to transfer land to military farms in Punjab.
  [73] 1958-1971; 1978-1988; 1999-2008.
  [74] Ayesha Siddiqa, Military Inc 2007
2.31.	Within this framework citizens and civic groups[75] have central roles in building effective domestic coalitions in favour of change. There is wide variation in the capacity of Pakistani civil society. Larger NGOs have substantial experience of managing major programmes and have the capabilities and systems to match. They have been able to attract qualified staff from a variety of backgrounds, including the civil service. Smaller, less well funded NGOs find it more difficult to attract and keep high calibre staff at all levels. Community Based Organisations (CBOs) depend on volunteer activists for management and implementation.
[75] Defined as community-based organisations, advocacy and service delivery NGOs, faith-based organisations, mass media, trade unions, business associations, professional associations, and independent research centres
2.32.	Many civil society organisations (CSOs) are not formally registered. In recent years, larger NGOs have increasingly registered themselves under the Companies Ordinance as not-for-profit companies, which puts them under the authority of the Securities and Exchange Commission (SECP). Many CSOs are still seen to lack internal democracy and external transparency. In order to strengthen the sustainability of the CSO sector, the AAWAZ programme will develop the capacity of the civil society groups with which it is working especially in approaches to themes of accountability and inclusion and financial and project management.
2.33.	Civil society groups have made significant contributions to awareness creation in the realm of democratic governance and political rights. The AAWAZ programme will work through fast expanding electronic media, newspapers and journals to articulate issues pertaining to democracy and governance and encourage citizens engagement in holding government to account. A cautious approach will be needed to address what is perceived to be growing religious conservatism linked to religious and ethnic intolerance and support for militant violence within Pakistani society.
2.34.	The Local Government Ordinance (LGO) 2001 provided for the formation of Citizen Community Boards in order to promote citizen’s involvement in planning and development, and tackle poverty and inequality on a sustainable basis. Despite the ending of the LGO in December 2009, groups of 25 non-elected individuals can continue to form CCBs which gives them access to development funds for village level and urban community projects, provided that they contribute 20% of the project costs. This mechanism should continue to be utilised whilst available.

Environmental/climate changes
2.35.	Most of the activities to be financed under AAWAZ are environmentally benign or will result in enhanced environmental benefits. Any potential negative impacts will be monitored by the MO. A Climate and Environment Assurance Note has been completed and approved.

C.	Appraisal of options
2.36.	As stated above (2.5) a comprehensive analysis of options for approaches to delivery of the Outcome was undertaken during design. Objectives to strengthen women’s equality, build peaceful communities and increase demands on local government were reviewed separately and together.

2.37. Criteria were the identified by which to evaluate the efficacy of the options in achieving the objectives, and the options were subsequently ranked against these Critical Success Criteria and compared (see Table 4 below).

Table 4: Comparison of Options
	Critical Success Criteria		1		2		3		4		5
			Do nothing		Gender equality in politics		Community cohesion and tolerance		Community demands for Service Delivery		Combined / (2+3+4)
	Will the feasible option lead to:	Wt	Score	Wt / Score	Score	Wt Score	Score	Wt Score	Score	Wt Score	Score	Wt Score
1	Reform : help to make government officials more accountable	5	1	5	2	10	3	15	4	20	5	25
2	Tackling social and cultural barriers: that prevent women from engaging safely in politics	5	0	0	4	20	3	15	2	10	4	20
3.	Community Peacbuilding resolving local disputes	4	0	0	2	8	4	16	4	16	4	16
4.	Improved service delivery: state providers responding to demands for better services	4	1	4	2	8	3	12	4	16	5	20
5.	Maximised impact of results and analysis coming out of the programme?	3	1	3	2	6	2	6	4	12	3	12
6	Sustainability, in order that the outcomes and impacts are sustainable?	3	1	3	3	9	4	12	4	12	4	12
7	Added value for existing DFID projects and programmes, and those of other donors?	2	0	0	4	8	4	8	3	6	4	8
	Total scores	1		15		69		86		49		108

Note: Weights 1-5; Scores 1-5
2.38 The conclusion was that a combined approach, involving options for gender, peace keeping and community action on service delivery, scores highest and is the preferred option. All options would require a results and analysis facility to develop and maintain a robust evidence base and provide material for dissemination and outreach.

2.39 All benefits are additional to the no-change option. While evidence of positive impact is strong, quantifying these benefits is more of a challenge. The appraisal process attempts to identify benefit streams that reflect real and quantifiable economic benefits at individual and household level.

2.40.	The potential delivery mechanisms were also reviewed. These are also appraised against the critical success criteria and shown below.

1.	Base Case/No Change - Elites will continue to control most of the resources, women and other excluded groups will remain marginalised, the Taliban and other extremist groups will increase their influence
2.	Work only with GoP providers: Federal (MoHR, NCSW) and newly devolved ministries in Provinces (PoWD, Local Government, Service Providers)
3.	Work through a multilateral agency
4.	Engage a Management Organisation to manage consortia of partners with track records in delivery of the focus areas of the programme, and under this option / pre-select partners with experience and expertise and fund them to implement a structured programme / run an open tender for consortia of partners with experience and expertise and fund them to implement a structured programme / run as a challenge fund with regular calls for proposals

Evaluation of Options Against Critical Success Criteria
Critical success criteria	Weighting (1-5)	1. Do nothing	2. GoP agencies	3. Multi-lateral organisation	4a. MO, preselected partners	4b. MO, competitively selected partners	4c. MO runs Challenge Fund
Achieve reform : strengthen the responsiveness of duty bearers in Pakistan	5	1	2	3	3	4	2
Tackle social and cultural barriers limiting participation of women and marginalised groups	5	1	2	3	4	4	4
Support community empowerment: resolve local disputes	4	1	1	2	4	4	4
Improve service delivery: in response to citizens’ demands to deliver	4	1	3	3	4	4	3
Generate and use evidence: maximise impact of results and analysis	3	1	2	2	3	4	2
Build sustainability of impacts	3	1	3	3	3	4	3
Add value to existing DFID projects and programmes and those of other donors	2	1	2	2	3	4	3
TOTALS		26	55	69	91	104	79

2.41.	The above table concludes that the delivery structure that provides the most effective return is that of a management organisation being accountable for delivery being selected with partners through a competitive process. This reflects the benefits of a competitive process to keep costs down, while holding partners to account for specific deliverables which can be measured and reviewed where performance is sub-optimal. These delivery options are not measured in terms of cost-benefit analysis. This is on justified on the basis that management costs are similar on the four top options (multilateral or three management organisation options) and would therefore not have significant impacts on costs.

2.42. The working through government (option 2 above) could potentially have lower costs; however the clear lower returns would ensure lower overall return. Therefore only option 4b is appraised at cost benefit level based on similar costs but lower expected returns for the other options. The conclusions of this analysis in terms of delivery mechanism do not reflect wider views on the various delivery options, but apply only to the context of AAWAZ.

Assumptions used for cost benefit analysis
Increasing the range of social actors in politics through greater gender inclusion
2.43.	Participation of women in political spaces has been shown to contribute to women’s empowerment which is further linked to better status, employment and better health and education outcomes. Furthermore, women tend to spend their income on the welfare and education of children more than men[76]. Conservative estimates have been made as to how the AAWAZ programme could potentially impact health and education service delivery to women through greater awareness about the rights of women, enhanced political participation of women and a more enabling legal environment that enables them to participate more actively in economic and social life. The benefits from increased education of girls and improved access to health services are expected to be significant. However the degree of impact is a challenge to quantify, and the time lag limits the economic value once discounted.
[76] Govt of Pakistan (2010) Development Amidst Crisis: Pakistan Millennium Development Goals Report, 2010, Centre for Poverty Reduction and Social Policy Development, Planning Commission.

2.44. Therefore two benefits are quantified in the cost benefit analysis: (a) time savings expected to accrue for women who are primarily responsible for household level tasks and (b) benefits from increased wage employment in the non-agriculture sector. On the first, studies show that women spend a significant share of their time in villages collecting water, which should reduce as women gain voice[77] leading to modest improvement in basic water services as resources get prioritised more equitably. On the second, the AAWAZ programme is expected to impact the incomes of women through greater awareness about the rights of women, enhanced political participation of women and a legal environment that enables them to participate more actively in economic life. In both cases, it is recognised that these benefits will be very gradual, and very prudent estimates have been used.
[77] Maliha Hussein (2005) Pakistan Water Sector Strategy. Global Water Partnership.

Improved co-ordinated issues-based politics through community cohesion and tolerance

2.45.	The community peace building aims to protect the lives, livelihoods and assets of excluded minorities. The cost of damage to physical infrastructure imposes high costs to the poor but also has significant long term negative impacts on the young especially in terms of the disruption to education facilities for both girls and boys. Not all benefits are quantified; an attempt is made to proxy impacts on livelihoods, income and asset ownership of the target population. This is done by the mechanism of quantifying the narrower benefits of protecting assets and livelihoods.

2.46.	The value of the two most important assets in rural areas, land and livestock, were assessed. The analysis assumed an annual increase in returns of 10 percent to land and to livestock. These reflect the benefits of increased security, reduced vulnerabilities and increased economic negotiating “power” which enable households to benefit from improved prices. The results show that the total value of the land of the target population is estimated at £944 million and their livestock holding is valued at £160 million. Additional benefits, not taken into account in this analysis, include protecting infrastructure.

Greater accountability through improved service delivery
2.47.	Holding providers of basic services to account is a major challenge. Efforts to improve the supply are in place in both KP and Punjab, including with substantial DFID funding. The programme will empower those with less voice, especially women, to articulate demand more effectively as users of facilities and as citizens.

2.48. The two main expected benefit streams would be through increased participation in education of girls from vulnerable groups, and increased demand for health services leading to reduced burden of disease. Given the long education lag, the value of this intervention is captured through a reduced burden of disease of 1% of the female beneficiary population based on communicable disease and reproductive related burden (ie: non-communicable disease burden is not included). This reflects a) modest improvement in services, b) increased use of health services, c) increased access to information through education and increased empowerment - which in turn is assumed to reduce disease through behavioural change linked to greater knowledge. DALYs are used (source: WHO) to provide a quantifiable benefit stream. Assumptions are based on 5000 communities with 200 direct female beneficiaries, with an average per capita income of £500 (ie: lower than average to reflect relative poverty).

2.49.	All three impact options (gender equality in politics, community cohesion and tolerance, and demand for services) are found to have a positive return over no intervention with very prudent assumptions. Gender equality in politics leads to a relatively more modest return reflecting the greater difficulty in quantifying the benefit stream. However this is positive; and it’s clear that long term development cannot be achieved without gender empowerment: it is part of the critical path required for development and MDGs, especially if a longer term perspective is taken.

2.50. The combination all three interventions provides an economic internal rate of return (ERR) of 22% and a net present value of £13.4 million based on 10% discount rate over 15 years (ie: the “socio-economic profit” that benefits targeted households and communities over and above the £34 million investment). The benefits are lagged over three years to reflect gradual build up. They are maintained at a flat rate over the remaining years, with the relatively high discount rate reducing the risk of an over-estimate of medium term benefits beyond the formal life of the proposed interventions. The management related economies of scale of combined interventions lead to higher returns, and so primarily reflect the lower transaction costs associated by going to scale and covering complementary interventions which do not require parallel delivery structures.

2.51.	The above analysis has not covered the wider synergies (e.g. empowered women engaging more effectively in community based peace building leading to higher returns). While intuitively likely, it requires a stronger evidence base to enable quantification. Other expected benefits that are not quantified include a reduction in corruption via an improvement in transparency; protection of infrastructure; increase in social capital; greater tolerance; and improvement in the investment environment.

2.52.	On balance, the net benefits of the preferred option are likely to be substantial and positive. The combination of a gender and community focus will help ensure higher returns as women through the gender specific interventions are more empowered to gain from the wider community benefits. The benefits captured above reflect those directly benefiting targeted groups but do not capture the higher community wide returns. These will be especially significant when going to scale and can lead to real transformational and lasting impacts on the lives of women and girls, which in turn will have significant benefits for their male counterparts.

Risk
2.53.	Sensitivity analysis was undertaken to assess risks associated with the quantified benefit stream. Delay in project benefits, cost escalation, and a reduction in benefits stream were reviewed. The AAWAZ programme is most sensitive to a reduction or delay in the benefits from the community peace initiative – though as the component with the highest quantified return, significant delays would be required to have an impact which leads to actual negative returns. Very probable modest delays or modest cost escalations are unlikely to greatly affect outcomes. The main criteria to ensure positive returns will be solid monitoring and ongoing evaluations to enable informed decisions on when specific interventions (or partners) are not likely to work and so that resources are adjusted to areas where evidence is growing. This aspect is covered further under the management section.

2.54.	The more significant risk lies with increased community conflict or negative trends in terms of gender empowerment that roll back benefits from the interventions in the medium term. Total lack of capacity or willingness of provision of very basic services by government is a similar potential risk, though more likely to occur in specific localities rather than systematically. A halving of the benefits beyond the life of the intervention (in years six to fifteen) suggests that this risk can be absorbed to a significant degree, with the ERR falling to 12% and NPV (at 10% discount and 15 years period) to £1.4 million.

D.	Measures to be used to assess VfM
2.55.	The appraisal has developed a number of measures to assess the cost and benefits - including net present values and internal rates of return – however these measures do not capture the full benefits and therefore will be used as indicative measures. The programme will also undertake a baseline assessment, from the start of the inception phase, and it will monitor unit costs and interim outcomes and impacts, as the programme is implemented (See Management Case, below). This exercise will help develop further measures, including unit cost measures, and undertake impact monitoring before the programme is fully scaled up. The programme (under Output 4 – PARR) proposes to use Randomised Controlled Trials and participatory statistics methodologies, for sample villages and urban communities, to gauge impacts on both empowerment and peace-keeping. This will help provide on-going evidence of impact.

2.56.	On balance the project presents good value. However, it is unlikely that the intervention will present good value if peace-building cannot be undertaken. There is some scope for mitigation of VfM risks and enhancing impacts through good management. For example:
1. AAWAZ community programmes will be implemented in 45 districts, so, if it is difficult to work in an area, because of security or other concerns, this can be offset by expanding the programme elsewhere.
2. There are synergies between the different aspects of the programme and geographic and thematic synergies to other DFID programmes. These will be identified and developed to ensure maximum benefit streams.
3. This programme will support the work of others including Health, Education, PEOP, SNG, and the Border Areas programmes dramatically increasing potential VfM not only for AAWAZ but for the other programmes also.
4. The programme will undertake on-going monitoring allowing it to assess its own effectiveness and modify approaches if necessary.
5. Increasing political voice leads to increased expectations and will make politicians more accountable (e.g., for effective delivery of education, health and water and sanitation programmes).
6. Corruption is a well-recognised problem. This will be managed through open and transparent procurement, auditing and community based monitoring.
7. A clear communication strategy will be developed to ensure the lessons learnt are communicated beyond the targeted population.
8. Each competitively selected implementing partner will have to demonstrate ability to measure value for money. The management organisation will be expected to have capacity to effectively measure returns to each intervention by each implementing partner.
3.	COMMERCIAL CASE

A.	Procurement/Commercial Requirements

3.1.	DFID will procure directly the services of a Management Organisation (MO) to implement the AAWAZ programme and deliver the Outcome on its behalf through a standard competitive procurement process following EU Procurement Directives. DFID Pakistan will monitor and review the MO’s performance. The MO will be led by a firm/organisation, with experience in Pakistan or the region, and will include other international and/or national firms/organisations in a consortium.

3.2.	During the Inception Phase the MO will sub-contract a consortium of Pakistani organisations to implement the programme - Output 1 (Gender equality in politics), Output 2 (Community cohesion and tolerance) and Output 3 (Demand for Services). There are likely to be several organisations with specific geographic and thematic areas of coverage in each consortium. A separate consortium is likely to be required to implement: Output 4 (Evidence and advocacy – PARR). Sub-contracting and procurement of other goods and services by the MO will follow standard DFID procurement rules. DFID will approve the selections but will not play a substantive role in the selection process. The MO will be responsible for contract management and supervising contractor/supplier performance in relation to achievement of logframe indicators.

B.	Using competition to drive commercial advantage for DFID
3.3.	All procurement will be competitive (directly by DFID and indirectly by the MO) and will seek to drive commercial advantage for DFID. As noted above, the MO will closely monitor the management and financial systems of the consortia implementing the programme, to ensure they achieve value for money. The MO will itself be monitored by DFID through regular progress and financial reports and review missions.

C.	Market Place Response
3.4.	There are a number of technically suitable suppliers, who could provide the services required of the MO and the consortia to be sub-contracted by MO. The design team does not expect DFID or MO to face problems in attracting qualified organisations/consortia to submit tenders, though the security situation could make it difficult sometimes for the consortia to attract suitable suppliers/capable individuals.

D.	Cost drivers and value addition
3.5.	The MO will work closely with the consortia it sub-contracts to achieve VfM by ensuring that their costs reflect market prices, overheads are reasonable and they have the capacity to implement the programme effectively. Consortium B (implementing the PARR) will work closely with Consortium A, implementing the gender, community cohesion and demand for services outputs to assess progress against its proposed theory of change, and to recommend how to strengthen performance and maximise results. DFID will monitor the MO’s own cost-effectiveness and VfM.

E.	Procurement Process
3.6.	The MO will be selected by DFID through international competitive bidding, following standard EU procedures. The MO will design a procurement strategy keeping in view the Pakistan environment, best practices and their own policies, which will be approved by DFID Pakistan.

F.	Managing Contractor and Supplier Performance
3.7.	Performance of MO and its contractors (the two consortia) will be managed through clear contracts with robust and appropriate implementation plans, including logical framework / results indicators. The MO will be responsible and accountable for its performance and for managing any poor performance by suppliers.

FINANCIAL CASE

A.	How much it will cost

4.1.	DFID has provisionally allocated up to £34.3 million to finance the full costs of implementing AAWAZ over the next 5 years (April 2012 to March 2017). See Table 5. Adequate funds are available in DFID Pakistan’s Aid Framework until 2014/15, following the approval of DFID Pakistan’s Bilateral Aid Review (BAR). As this programme will continue till March 2017, following programme approval we will consult HMT about the funding after financial year 2014/15. Co-financing with other organisations is not envisaged, since other donors are not engaged or looking to engage in this area to this scale. However AAWAZ will work closely with programmes supported by other donors where possible and encourage other donors to join if they so interest.
Table 5: Budget – £ million (2011 cash prices)
OUTPUT	Year 1	Year 2	Year	Year 4	Year 5	Total
	2012/13	2013/14	2014/15	2015/16	2016/17
Gender equality	1.00	2.50	3.60	3.65	2.30	13.05
Community cohesion and tolerance	0.75	2.05	3.25	3.35	2.75	12.15
Demand for Services	0.60	0.70	0.90	1.05	0.80	4.05
Evidence and advocacy (PARR)	0.20	0.90	1.00	1.40	1.30	4.80
DFID M&E	0.05	0.05	0.05	0.05	0.05	0.25
Total	2.60	6.20	8.80	9.50	7.20	34.30

B.	How it will be funded: capital/programme/admin

4.2.	The total programme will be £34.3m of which £0.25m will be for DFID M&E.

4.3.	The MO will monitor overall progress against logical framework /results and build the capacity of the Consortia implementing the programme.

4.4.	DFID is planning to disburse its funds as follows (Table 6):

Table 6
Sources of funding
(£ million, 2012/13 Cash Prices, FY)

SOURCE OF FUNDING	Year 1 / 2012/13	Year 2 / 2013/14	Year 3 / 2014/15	Year 4 / 2015/16	Year 5 / 2016/17	Total
Programme Resource to MO	2.55	6.15	8.75	9.45	7.15	34.05
Programme Resource for DFID M&E	0.05	0.05	0.05	0.05	0.05	0.25
Programme Resource Total	2.60	6.20	8.80	9.50	7.20	34.30

4.5. The programme will include funding for:

I. Gender equality: Over 400 training sessions for over 180 national and provincial parliamentarians, 30 members of Commissions for the Status of Women, and 60 key bureaucrats on defining and implementing legislation to protect women; organising effectively and strengthening use of evidence, presenting arguments effectively, influencing for policy change, and working constructively with all forms of civil society.

Across all project districts it will involve building the strength of VAW networks to manage and represent 30+ members; gather, validate and aggregate data on VAW; train and further support 60,000 women, girls, men and boys to combat VAW; initiate evidence-based advocacy campaigns to demand implementation of critical legislation and reduce VAW, and support victims of violence.

Across all project districts, 45,000 women will be trained in understanding local authority budgets, using methodologies to evaluate and analyse service delivery; and supported in participating effectively in community dialogues, committees, councils and other fora, and in standing for local elections

II. Community cohesion and tolerance: Across all project districts, approx 10,000 young social workers (women and men) will be trained in peace-building techniques, organising peace rallies (2/district/year) involving at least 225,000 people; bringing together networks of volunteers to help construction/reconstruction efforts; and convening culturally appropriate events for young people.
In project districts, 45,000 citizens (men and women) will be trained and active in resolving disputes in 9000 mediation committees/groups; (approx 1 group per 7,500 citizens).
Across all districts, 2 media peace campaigns/district/year (radio TV and print) will be run, engaging up to 20,000,000 citizens in debates on Peace Building; approx 4,500 journalists will be trained and reporting on peace activism.
In each project district, at least 300 community groups, village councils and local committees will include members of marginalised groups, working cohesively to increase the number of community projects and social events.

III. Demand for Services: Across all project districts, 45,000 citizens will be: trained to understand local authority budgets and spending of public finances; supported to implement a range of techniques for monitoring of public service delivery; strengthened in dialogue with and in presenting demands to local authorities; and facilitated to define local priorities and obtain funding to meet them

IV. Policy Analysis, Research and Results: After the completion of a year long Inception Phase, over next 4 years, 20 policy briefs will be prepared and disseminated through a range of events and media.
Over 4 years, 10 pieces of research will be commissioned to strengthen evidence.
Over 4 years, 8 media campaigns will be instigated based on robust evidence, reaching out to both rural and urban communities and elites.
Over 4 years, strengthened evidence will be used to initiate at least 8 actions (for example cases in law courts, public events, rallies etc).
Analysis will be used to support robust monitoring and course-correction in AAWAZ programme.

C.	How funds will be paid out?
4.6.	The AAWAZ programme will be implemented by two consortia of Pakistani civil society organisations, sub-contracted by the MO. The MO will have overall responsibility for delivering and managing the programme. DFID will channel funds to the MO against invoices paid monthly in arrears.

D.	How expenditure will be monitored, reported, and accounted for?
4.7.	The MO will provide costed annual work plans, for approval, and quarterly narrative and financial progress reports to DFID, which will include reports against the logical framework and agreed results. Expenditure will be monitored / validated against quarterly financial and progress reports. Progress and financial reports will be submitted within 15 calendar days of the end of each quarter.

4.8.	The MO will maintain an asset register. DFID Monitoring Missions will verify the assets and DFID will decide on the handing over of programme assets to the partners at the end of each partnership and programme.

4.9.	The MO will appoint the Pakistani office of an international audit firm, acceptable to DFID, to conduct annual audits of its accounts and those of the civil society consortia. On the basis of these audits, the audit firm will also carry out in-depth tests to confirm that funds have been spent as intended and organisations are delivering value for money. All audit reports will be shared with DFID.

5.	MANAGEMENT CASE
A.	Oversight
5.1.	DFID will establish a Programme Advisory Committee (PAC) comprising Pakistani experts, with understanding and experience of social exclusion, national and provincial politics, political economy and the media to advise on the strategic direction of the programme. The PAC will elect one of its members as the Chair, who will convene quarterly PAC meetings and report to DFID and the MO Team Leader (see next section). Decisions on implementing recommendations of the PAC would be undertaken by DFID in consultation with the MO.

5.2.	Within DFID, the Democracy and Accountability Team Leader and Deputy Programme Manager will have oversight of the AAWAZ programme. A programme of annual reviews will be undertaken by DFID, with participation, as appropriate, of members of the PAC and other experts. DFID Pakistan will aim to draw on PrD, RED and other DFID offices in the region to take part in annual reviews and evaluations. Quarterly review meetings will also take place. Again within DFID, a virtual team will be constituted, led by the Sub National Governance Team Leader, to identify districts of focus for DFID Pakistan programmes. This team will work with the AAWAZ team to identify districts for AAWAZ programme interventions, which will provide additional benefit to other DFID programmes such as transforming education and the voice, accountability and innovation in education. The AAWAZ team will work with the MO to identify the final list of districts for approval. AAWAZ will act as the driver of its own new initiatives, a ‘binder’ for the demand side of other DFID Pakistan programmes, and an investigatory resource for DFID Pakistan and wider.

5.3.	The key stakeholders in AAWAZ are women and people from excluded groups, especially those in the 45 districts where the programme will operate at community level. Due to the security situation, it was not possible for the design team to interview all key stakeholders directly but the voices of women and excluded groups were incorporated into the design through workshops with civil society organisations. Important secondary stakeholders will include DFID (specifically a number of DFID Pakistan programmes which AAWAZ will directly support) and the civil society organisations implementing the programme, whose capacity to deliver effective gender equality in politics, community cohesion and demand for services will be strengthened by the programme. Also important will be the interaction achieved by the groups with the provincial level Ministries of Women and Development (following the devolvement of gender legislation under the 18th amendment), and the National and Provincial Commissions on the Status of Women.

B.	Management
5.4.	The AAWAZ Programme will be managed for DFID by a Management Organisation (MO), which will sub-contract civil society consortia to implement the programme. The MO Team Leader will report to DFID and will be supported by a team of international and/or national specialists in gender, community cohesion, conflict, evaluation and analysis, and advocacy, plus support staff. The MO will seek to maximise synergies across the AAWAZ programme and with other DFID programmes (e.g. STAEP, Border Areas, SNG, PEOP, health and education programmes). They will ensure district focus is in accordance with advice from the DFID team. DFID will select a consultancy firm to lead the MO through competitive tender.

5.5.	The MO will select the two consortia to implement the programme, through competitive tenders, and will supervise their performance. The consortia are:

Consortium A, which will implement the gender equality, community cohesion and tolerance, and demand for services components (Outputs 1, 2 and 3), at community, district, provincial and national levels.

Consortium B, which will form the Programme Analysis, Research and Results (PARR) facility to implement the evidence and advocacy component (Output 4).

5.6.	The MO will be responsible for building the capacity of the two consortia (e.g. management systems, monitoring and evaluation, evidence and advocacy) so that they are well-positioned to continue working effectively for change once AAWAZ ends. The two consortia will be responsible for building the capacity of their civil society partners. Part of the payments to the MO will be linked to performance and delivery of results.

5.7.	The PARR facility, one of the consortia, will be available across DFID Pakistan. In addition to the rigorous monitoring and evaluation, it will synthesise evidence from programme activities in communities and districts and use this to advocate for government reforms directly and through media campaigns. PARR will have access to a rapid and flexible Response Fund (RF) to use in testing findings from AAWAZ and other programmes (which will be triangulated with quantitative data on e.g. access to services), scaling up results and commissioning professional bodies to improve government responsiveness and improve accountability.

5.8.	These two consortia will comprise Pakistani organisations (e.g., NGOs, RSPs, research and advocacy groups), with possible support from international research or consultancy organisation(s). They will work in partnership with local civil society organisations, where appropriate.

5.9.	The organisation of AAWAZ is shown schematically in Figure 2.

Figure 2: Organisation of the AWAAZ Programme

	DFID

	MO			Programme Advisory Committee (PAC)
				Other DFID programmes / Linked to PARR
Consortium A / Gender equality / Community cohesion and tolerance / Demand for services		Consortium B / Evidence/advocacy (PARR)		STAEP – Elections / (Asia Foundation)
				Transforming Education
				Education, Health, Border Areas, SNG
				Other DFID Programmes

5.10. AAWAZ will start with a year long Inception Phase. During this time the MO will finalise the draft logframe, identifying specific inputs under each output; it will tender to Organisations to form Consortia A and B, and establish the groups and geographical areas which will be their focus going forward; it will ensure that Consortium B is establishing all the necessary baselines for its research, and will identify the research questions. During this phase, the DFID AAWAZ team will work with the MO to set out their respective roles and responsibilities in terms of policy dialogue, particularly with high level government partners, both provincial and national. These roles should be made explicit in the first annual report.

5.11. The MO will provide DFID Pakistan with quarterly narrative and financial reports and will produce an Annual Report, reviewing progress against the logical framework and summarising key financial information before each Annual Review mission. During the Inception Phase the MO will develop a detailed work plan and budget for Year 2 (2012/13), and revised results framework, for approval by a DFID review in Month 12. The MO will seek similar detailed narrative and financial reports from its partners as well as identifying a reporting mechanism to ensure consistent flow of information for results, effective communication and risk management to DFID.

C.	Conditionality
5.12.	This is not financial aid to government. The usual conditions will apply regarding appropriate use and reporting of funds.

D.	Monitoring and evaluation
5.13.	AAWAZ is an investigative as well as an implementing programme. It will need rigorous monitoring and evaluation to test the actual effects and assess the potential for scaling up; so it will be evaluated according to the following criteria set out in DFID Pakistan’s Evaluation Strategy:

i.	Strategic importance for DFIDP. Does the programme make a significant contribution to the objectives and results set out in the DFIDP Operational Plan?	√
ii.	Strategic importance for DFID, HMG and/or the international development debate. Will the programme deliver on DFID-wide priorities (e.g. women and girls), is it critical to wider National Security Council objectives for Pakistan (e.g. on conflict) and/or will it help to inform approaches elsewhere (e.g. on low-cost private schools)?	√
iii.	Innovation. Is this a new approach where the evidence-base is, by definition, weak?	√
iv.	Risk. Is an evaluation needed to demonstrate how the programme rolled-out and to capture any lessons?	√
v.	Size. Is it a significant investment of financial resources?	√
vi.	Demand. Do key partners want an evaluation?	√

5.14. A Programme Analysis, Research and Results (PARR) facility will be established to conduct on-going independent analysis and assessments of the three substantive outputs of the programme (gender equality in politics, community cohesion and tolerance and demand for services) to identify good practices and key lessons to be used to advocate for government reforms.

5.15.	The MO will be responsible for overall programme monitoring and will report quarterly and annually to DFID on progress against logical framework milestones and targets. Its reports will be based on detailed monitoring information produced by the implementing consortia. The MO will ensure the consortia collect the information needed to assess the effectiveness, efficiency, cost-effectiveness and value-for-money of the programme, and provide training.

5.16.	During the Inception Phase, the MO will develop a detailed Monitoring and Evaluation Framework, describing the data requirements, data sources, data collection and analysis, and how monitoring and evaluation will be undertaken, including key evaluation questions. The M&E Framework will be linked to the theory of change and the logical framework milestones and targets; and will be aligned with the DFID Pakistan Evaluation Strategy. Special attention will be paid to collecting information on areas where the evidence is weak. The framework will detail how the programme will be monitored to ensure the programme is having the required effect.

5.17.	A number of special surveys will be required to collect monitoring and evaluation information, including perception surveys of politicians and decision makers, women, excluded groups on various topics (e.g. women’s confidence that they can hold government to account for service delivery; men and women’s perceptions of levels of tolerance of violence against women). These will be triangulated with quantitative data on e.g. access to services. Detailed indicators will be finalised through a participatory process during the Inception Phase and reviewed and revised, as necessary, while AAWAZ is being implemented.

5.18.	The PARR will analyse monitoring information, synthesise evidence from AAWAZ and other programmes, evaluate AAWAZ interventions and carry out operational research[78] to:
[78] One of the lessons of the Poorest Areas Civil Society (PACS) programme in India was the importance of information and knowledge management.

- improve the effectiveness of the programme,
- test the AWAAZ theory of change,
- provide robust evidence to use in advocating and championing reform.

5.19.	The PARR will use a range of approaches, including randomised control designs and qualitative participatory and other research methods to provide strengthened empirical evidence on voice, empowerment and development outcomes in Pakistan. By using counterfactuals, it will make it possible to test AAWAZ results and attribution. The evidence from PARR should make a significant contribution to national and global debates and DFID’s understanding of empowerment and accountability. PARR will communicate its evidence to decision-makers, champions and other audiences, using a range of media, and will use it to advocate for reform.

E.	Risk Assessment

5.20.	The volatile environment in Pakistan and especially in conflict-prone districts, exposes development programmes to significant risks. The key risks in implementing AAWAZ are shown in Table 8 and Figure 3.

5.21.	The overall risk is Medium/High.
Table 8: Key risks and mitigation strategies

	Risk	Mitigation	Rating / Probability/ Impact
1	Government responsiveness. Government and other service providers unwilling or unable to respond effectively to increased levels of demand from communities, women, other excluded groups and young people for services.	DFID and other donors are providing substantial support to the Governments of KP and Punjab to improve the quality and supply of education, health and drinking water services. A key issue in improving service delivery is to generate and respond to local demand. AAWAZ, by supporting the growth of community organisations, will voice local demand and help bridge this gap.	L	H

2	Willingness to reform/enforce laws. Parliamentarians and justice system actors unwilling to enact and enforce legislative and policy reforms.	AAWAZ will partner with leading civil society organisations, which have a proven track record in influencing parliamentarians and others to support progressive legislative change (e.g., Abolition of the Hudood Ordinance in 2006).	M	M

3	Conservative groups are able to prevent participation of women, excluded groups and young people in politics and public spaces.	The extent to which conservative groups will be able to do this will vary from district to district. In some very conservative and militant areas, this may be the case. In other areas more inclusive forums, with participation of young people, are challenging conservative groups. AAWAZ and partners will assess challenges on a case by case basis and work with local groups to identify approaches	M	M

4	Community cohesion. Efforts to resolve local disputes and generate increased community cohesion exacerbate rather than reduce tension and intolerance.	Efforts to increase community coherence and resolve local disputes can, if done badly, exacerbate rather than reduce tension and intolerance. This risk will be minimised by partnering with experienced civil society organisations and having robust monitoring and learning systems and quickly sharing emerging good practices among AAWAZ partners. Some non-violent conflict may be necessary and positive in the long term. More negative is the risk it would be protracted, violent and contagious.	L	M

5	Politicians and other decision makers unwilling or unable to respond to evidence-based campaigns and implement evidence-based policies.	This risk will be minimised by ensuring that PARR produces robust evidence and is resourced to communicate this effectively to politicians and key officials directly (e.g., via policy briefs, meetings) and indirectly through the media and public campaigns. Relationships will be developed with key decision-makers to champion reforms.	M	H

6	Media campaigns are ineffective in changing public attitudes and lead to increased intolerance.	The electronic media (e.g., commercial TV stations, web-based media) are becoming increasingly widespread and influencing public attitudes in Pakistan. The PARR would have the resources to partner with professional PR and communication consultants on campaigns to change public attitudes. Media contacts of DFID staff and other programmes (e.g., STAEP) will be involved.	L	M

7	Return to autocratic military rule delaying the transition to a stable democracy.	Pakistan has experienced four periods of autocratic military rule since independence and further intervention cannot be ruled out. Although this would delay the transition towards a stable democracy in Pakistan, AAWAZ would probably continue, laying the foundations for more open accountable and inclusive democratic processes in the country, in future. / Other programmes in the D&A team, as well as colleagues in the BHC, are working with government partners and citizens to strengthen the democratic transition	M	M

8.	Natural disasters and other emergencies. KP and Punjab suffered from the floods in 2010 and KP from the massive earthquake in 2005, as well as population displacement from SWAT and Malakand in 2009. Although such events generally do not affect the whole population of a Province, they impact on implementation of development programmes can be serious.	Although the recent natural disasters have been catastrophic they are also unusual. If there was another serious disaster during the next five years, it could seriously affect programme implementation and heighten tension among groups through competition for scarce resources. However, it is unlikely that a disaster would affect all programme districts. / AAWAZ activities at local level could help strengthen the response to an emergency if resources were able to be distributed more fairly.	L	M

Figure 3: Risk Matrix Summary

		IMPACT
		HIGH	MEDIUM	LOW
PROBABILITY	HIGH
	MEDIUM	[5]	[2], [3], [7]
	LOW	[1],	[4], [6], [8]

F. Results and Benefits Management
5.22.	The logical framework (see Annex 1) sets out the delivery trajectory for the project. The planned indicators and milestones were drafted following discussions with civil society organisations who have worked on similar programmes and are realistic. They will form a good basis for assessing over and under-achievement of the programme.

5.23.	Under-achievement will mean that either the risks (e.g. politicians and others unwilling or unable to support the programme) are more serious than expected or that the consortia implementing the programme do not perform as expected. If this happens, AAWAZ’s outcomes would probably not be achieved.

5.24.	Over-achievement will not present any problems, though the programme would only be able to raise the number of direct beneficiaries with extra funding. Otherwise, over-achievement would make AAWAZ an exemplar and an inspiration for the rest of Pakistan and for all conflicted and fragmented states and nations.

PROJECT NAME	AAWAZ LOGICAL FRAMEWORK
IMPACT	Impact Indicator 1		Baseline / 2009	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
Stable, inclusive and tolerant democracy in Pakistan.	G1 Pakistanis who feel quite safe or very safe over the course of a year.	Planned	38%	38%	40%	44%	50%
		Achieved
			Source
			Gallup & Gilani : Annual polling on Crimes, Violence, Terrorism and Social Evils National Survey
	Impact Indicator 2		Baseline / 2010	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	G2. World Bank “Worldwide Governance Indicators” : Voice and Accountability Score	Planned	-1.01	-0.95	-0.82	-0.75	-0.7
		Achieved
			Source
			World Bank Governance indicators
	Impact Indicator 3
	G3. International Gender Gap rank	Planned	132	125	120	115	110
		Achieved
			Source
			World Economic Forum – Annual Gender Gap Reports
OUTCOME	Outcome Indicator 1		Baseline / 2010	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17	Assumptions
Democratic processes in Pakistan are more open, inclusive and accountable to citizens	O1. No of new/revised laws affecting the status of women enacted and enforced (between 2012 and 2017) (low is better)	Planned	2.63	2.4	1.95	1.45	1	Those in power will act in response to the louder more strategic voices that this programme aims for, and tackle violence and exclusion. Pakistan does not revert to highly unstable democracy or to autocratic rule. Other donors continue to support efforts to establish and consolidate a stable, inclusive democracy in Pakistan. No major environmental/natural disasters. / Parliamentarian activities in support of women and other excluded groups are not disrupted by elections in 2012/2013 / Macro-economic stability
		Achieved
			Source
			Assessment by PARR using DFID-P methodology. Average score, covering extent to which (a) six key laws* have been enacted/ revised; (b) level of public awareness of the laws; (c) level of implementation of laws; (d) resulting changes in behaviour or perception of public (1= completed/high; 2 = In process/medium; 3 = Not yet addressed/low). * Key laws on : (i) Sexual harassment in the workplace; (ii) Domestic violence; (iii) Acid burning; (iv) ‘Anti Women Practices’; (v) Unequal rights in marriage, property and inheritance; (vi)non compoundability of “Honour killings”.
	Outcome Indicator 2		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	O2. Increase in the passing of private member bills introduced/moved by women legislators	Planned	5 %	Election year*	7%	9%	13%
		Achieved
			Source
			Reports of implementing partners Annual survey of politicians and senior officials behaviour in Parliaments FAFEN reports / * The election year falls between March 2012 to February 2013 and during this time the focus of the legislators will be on election campaigning. Legislative business in the first year will therefore be slow.
	Outcome Indicator 3		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	O3. Cumulative % of minority and excluded groups reporting improved tolerance in over the last 12 months in society [KP/Punjab]	Planned	0	2%	8%	15%	20%
		Achieved
			Source
			Independent annual perception survey commissioned by MO.
	Outcome Indicator 4		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	O4. Cumulative % increase in access by women / other excluded groups to priority government services* in project districts	Planned	0%	2%	8%	14%	25%
		Achieved
		Source

INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	34.3 m		0	0	34.3 m		100 %
INPUTS (HR)	DFID (FTEs)
	A1 SDA 50% / A1/A2 Economist 10% / A2 GA 35% / A2 Comms 10% / B1 DPM 75% / B2 PO 10%

OUTPUT 1	Output Indicator 1.1		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17	Assumption
Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab	Cumulative % increase in engagement on gender issues between formal civil society networks and political representatives at provincial and federal levels	Planned	0%	5%	10%	20%	30%	Those in power will respond effectively to increased levels of demand from women for access to services, and strengthened equality under the law Parliamentarians and justice system actors are open to pressure to enact and enforce legislative reforms. Conservative groups accept or are unable to stop greater women’s participation in politics and public spaces Women do not suffer increased violence as a result of enhanced political engagement
	.	Achieved
		Source
		Reports of implementing partners Independent surveys commissioned by MO
	Output Indicator 1.2		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	Cumulative % men/ women reporting reduced tolerance of violence against women in programme districts over the previous year	Planned	0%	2%	4%	7%	10%
		Achieved
		Source
		Independent annual perception survey commissioned by MO.
IMPACT WEIGHTING (%)	Output Indicator 1.3		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
30%	% increase in decision making positions held by women within political parties and political organisations at local and district levels and provincial and national bodies.	Planned	tbc	2% / 1%	8% / 3%	13% / 5%	20% / 10%
		Achieved
		Source					RISK RATING
		Independent annual perception survey commissioned by MO
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	13.5 m		0	0	13.5 m		100 %
INPUTS (HR)	DFID (FTEs)
	A1 SDA 60% / A1/A2 Economist 10% / A2 GA 30% / B1 DPM 75% / B2 PO 10%

OUTPUT 2	Output Indicator 2.1		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17	Assumptions
Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab	Cumulative no of disputes resolved using local community cohesion mechanisms facilitated by the project.	Planned	Baseline tbc	Baseline +500	Baseline +5000	Baseline +15000	Baseline +40,000	Those in power will act in response to the louder more strategic voices that this programme aims for, to respond effectively to increased levels of demand from excluded groups, including young people, for services. Improved resolution of local disputes leads to greater community cohesion and strengthens voice of excluded groups in local and district politics. Conservative groups accept or are unable to stop greater participation by excluded groups and young people in politics and public spaces. Local organisations with access to excluded communities can be identified and contracted.
		Achieved
		Source

	Output Indicator 2.2		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	Cumulative and incremental no of (a) excluded group households; and (b) male/female young people from all groups participating in community organisations and local level peace events and political processes.	Planned	a) tbc b) tbc	500 1000 (50/50)	2500 5000 (50/50)	10,000 20,000 (50/50)	20,000 80,000 (50/50)
		Achieved
		Source
		Annual surveys organised by MO Monitoring data, reports of implementing partners analysed by PARR
IMPACT WEIGHTING (%)	Output Indicator 2.3		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	% of people project districts who consider community cohesion mechanisms to be credible and effective	Planned	0%	1%	3%	6%	12%
20%		Achieved
		Source					RISK RATING
		Perception surveys Reports of implementing partners analysed by PARR
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	12.65 m		0	0	12.65 m		100 %
INPUTS (HR)	DFID (FTEs)
	A1 SDA 35% / A1/A2 Economist 10% / A2 GA 45% / B1 DPM 75% / B2 PO 10%

OUTPUT 3	Output Indicator 3.1		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17	Assumptions
Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab	Increase in the number of direct engagements between communities and local officials to seek improved delivery of health and education services to women and girls (liaising closely with DFID Education and Health programmes);	Planned	tbc	Baseline +2%	Baseline +5%	Baseline + 10%	Baseline + 20%	Those in power will respond to increased demands for services from excluded groups, including young people. Local groups are prepared to work together towards shared priorities Improved resolution of local disputes leads to greater community cohesion and strengthens voice of excluded groups to demand improved service delivery at local and district levels.
		Achieved
		Source
		Monitoring data of programme partners RCTs in adjacent districts FAFEN monitoring data
	Output Indicator 3.2		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	Cumulative % increase of minority and excluded households and women who are confident in their ability to hold governments to account for delivery of services and entitlements.	Planned	0%	Baseline +2%	Baseline +5%	Baseline + 10%	Baseline + 15%
		Achieved
		Source
		Annual perception surveys RCTs in adjacent districts
IMPACT WEIGHTING (%)	Output Indicator 3.3		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	Number of people who think that quality of services has improved (disaggregated by sex and ethnic group/caste/class)	Planned	tbc	2000	5000	50000	100000
30%		Achieved
		Source					RISK RATING
		DTCE Social Audit findings Perceptions survey RCTs in adjacent districts DFID Health and Education programme data
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	3.4 m		0	0	3.4 m		100 %
INPUTS (HR)	DFID (FTEs)
	A1 SDA 20% / A1/A2 Economist 10% / A2 GA 55% / B1 DPM 75% / B2 PO 10%

OUTPUT 4	Output Indicator 4.1		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17	Assumptions
Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa and Punjab	Cumulative no of evidence-based policy briefs (e.g., on inclusive governance, peace-building and accountability shared with politicians/bureaucrats	Planned	0	2	8	14	25	Pakistani politicians and bureaucrats will respond positively to better informed and more strategic citizen demands and ensure more effective policy implementation Media campaigns and public events are effective in changing public (citizens') attitudes and lead to increased tolerance Pakistani politicians and bureaucrats are able to respond citizen demands for greater tolerance .
		Achieved
		Source
		PARR Reports

	Output Indicator 4.2		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	No of cases/issues championed with provincial and national politicians.		0	2	8	13	20

		Source
		PARR Reports. FAFEN Reports
IMPACT WEIGHTING (%)	Output Indicator 4.3		Baseline / 2012	Milestone 2012/13	Milestone 2013/14	Milestone 2014/15	Target (date) 2016/17
	% increase in level of media reporting on gender equality, tolerance and inclusion in political processes.	Planned	0%	3%	8%	15%	25%
		Achieved
20%		Source					RISK RATING
		Annual content analysis of media commissioned by PARR FAFEN reports					Medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	4.5 m		0	0	4.5 m		100 %
INPUTS (HR)	DFID (FTEs)
	A1 SDA 20% / A1/A2 Economist 10% / A2 GA 35% / A2L GA (Pol) 10% / B1 DPM 70% / B2 PO 10%

Activities (to be finalised in inception phase after Management Organisation contracted)
Output 1 : / Gender Equality in Politics	Output 2: / Community Cohesion and Tolerance	Output 3: / Demand for Services	Output 4: / Evidence generated and communicated to policy makers / (PARR)
Capacity building of Civil Society Organisations
National/Provincial levels / 1. E.g. Sensitisation and other training provided to strengthen capacity of decision-makers to be more proactive in addressing the needs of women	District/local levels * / 1. Action taken to build capacity of citizens and communities to resolve disputes peacefully and work together for common solutions in socially inclusive ways.	District/local levels / 1. Citizens trained in analysis of local authority budgets and spending of public finances	1. Monitoring and evaluation findings from Outputs 1 and 2 verified, analysed and assessed against theories of change .
2. Action taken to strengthen the capacity of women in elected bodies, to lead, to build alliances to lobby for legislative reform; implementation of existing laws; and inclusion of women’s issues in government policies/programmes.	2. Young volunteers and peace activists trained to promote values of peace and tolerance and support community peace-building efforts.	2. Citizens trained in different techniques for monitoring of public service delivery and supported to implement them	2. Action research commissioned, as required, to test innovative approaches, deepen understanding and derive lessons.
3. Action taken to strengthen the capacity of women’s and men’s organisations to lobby for inclusion of women’s issues in government policies and programmes.	3. Peace campaigns and awareness raising activities organised (e.g. inclusive citizen peace forums at union, tehsil and district levels).	3. Citizens facilitated to define local priorities and obtain funding to meet them	3. Evidence from Aawaz (and from SPAEP and ICED and other agencies’ programmes) synthesised into key lessons for wider circulation.
District/local levels * / 4. Training programmes run for women and men, including members of excluded groups, to make them aware of their rights, entitlements and responsibilities.	4. Social, cultural and sports events organised to promote the coming together of communities (possibly with separate events for men, women and young people).	4. Citizens trained in techniques to structure arguments convincingly and articulate demands effectively to local authorities	4. Evidence and lessons strategically communicated to decision-makers and others using a range of media (TV, print media, champions, web-based media, policy and ‘good practice’ notes).
5. Action taken to support women’s and men’s organisations to encourage women’s involvement in local organisations and public events by breaking down the social, cultural and religious barriers.	5. District level initiatives/groups networked with those at provincial and federal levels.		5. Evidence-based recommendations made to MO on redesign and/or reframe Outputs 1 and 2.
6. Action taken to support Men /women to disseminate messages about the social, cultural and religious unacceptability of VAW.
7. Support provided to ‘victims’ of violence.

 * Activities at district/local levels will be undertaken in 5000 villages and urban communities, in 500 selected union councils in 45 selected districts in KP and Punjab.