Business Case and Intervention Summary

Intervention Summary
## Title: Vietnam Governance, Economic Management and Social Protection Programme (VGEMS)

What support will the UK provide?
Up to £6 million over three years and ten months (June 2012 to March 2016).

Why is UK support required?
Vietnam’s poverty rate has fallen by 80% in the last 25 years, and the economy grew on average by 5.6% between 1997 and 2009. The challenges Vietnam now faces are a consequence of these striking achievements. Success in reducing poverty across the whole population means that the remaining poverty is concentrated amongst ethnic minority and other vulnerable groups and inequality (historically very low) is now increasing. Rapid growth without addressing structural weaknesses in the economy has increased Vietnams’ integration into the global economy, and therefore increased vulnerability to global economic trends and macroeconomic instability. A new generation of reforms covering macro-economic management, social protection systems and transparency mechanisms need to be adopted to respond to the new demands of the economy and the people. / To address these new challenges, DFID will work with the World Bank to support better evidence and analysis of what works and what does not; provide reform options; and encourage greater public debate about required changes. Specifically, the programme will: / Deepen the debate and provide policy options on Vietnam’s top reform priorities in economic management under the new Vietnam Knowledge Platform. / Improve transparency in Vietnam by measuring, tracking and incentivising the Government’s performance on transparency across different sectors and provinces. / Help establish a new social protection system appropriate for a middle-income Vietnam, targeted effectively at the poor and those most in need. / Undertake poverty, gender and inequality analysis, feeding directly into policy and public investment decisions to change the way in which poverty is tackled in Vietnam. / The project is central to DFID’s responsible graduation from Vietnam in March 2016. It will leave a legacy of the World Bank capable and engaged in these areas, building on our existing partnership. The programme will also leverage both World Bank and Government resources in a creative manner, by supporting the design of new World Bank programmes and increasing the efficiency and effectiveness of the use of the Government’s own resources through analysis and advocacy. / In the absence of DFID support, reforms across the three areas of transparency, accountability, economic management and social protection would be more limited, impacting negatively on Vietnam’s continued sustainable development.

What are the expected results?
The impact of the programme will be ‘Stable growth and sustained poverty reduction with stronger government accountability’. / The key outcome of the programme will be `Significant reforms adopted by Government of Vietnam in the policy areas of transparency, macroeconomic stability and social protection’. By the end of 2015, the Government of Vietnam will strengthen the access to information, make significant monetary and fiscal policy changes and improve targeting and monitoring of social programmes. / The programme will support the Government of Vietnam to: / Undertake governance reforms for greater transparency by working with different actors to advocate for better information on governments policies and operations. This will help Vietnam achieve a significantly higher percentile ranking on the Global Integrity Index indicator for Access to Information. It will also show improvement in the control of corruption, particularly on service delivery. / Design and adopt key reforms for macroeconomic stability by supporting Public Financial Reviews, providing an analytic underpinning for budget support operations and establishing a vibrant knowledge portal on economic issues. This will help Vietnam deliver targets specified in the Socio-Economic Development Plan 2011-15 of a budget deficit within 4.5% of GDP and a Consumer Price Index growth rate at single digit levels. / Improve capacity for measuring and monitoring poverty and to target social transfers by supporting poverty surveys, research and analysis to feed policy and by improving monitoring and evaluation system for social programmes. Better targeted and monitored social programmes will result in an enhanced reduction of poverty among ethnic minorities.

Abbreviations and acronyms

ARIES	DFID’s Activities Reporting and Information Electronic System
CIEM	Vietnam Centre for Economic Management (Ministry of Planning & Investment)
CSOs	Civil Society Organizations
DFID	UK Department for International Development
DPA	Development Partner Arrangement
EMCC	Economic Management and Competiveness Credit
EvA	Evaluation Adviser
GAPAP	Governance and Poverty Policy Analysis and Advice
GI	Government Inspectorate
GSO	Vietnam General Statistics Office
IDA	International Development Association
IFID	International Fixed Income and Derivatives
INGOs	International Non-governmental Organizations
MAR	Multilateral Aid Review
M&E	Monitoring and Evaluation
MOLISA	Vietnam Ministry of Labour Invalids and Social Affairs
NA	National Assembly of Vietnam
NGIS	National Gender Indicators System
NGOs	Non-governmental organizations
NTP-SPR	National Targeted Programme – Support for Poverty Reduction
ODI	Overseas Development Institute (UK)
OOG	Office of the Government, Vietnam
ONA	Office of National Assembly, Vietnam
PAPAP	Poverty Analysis and Policy Advocacy Programme
PFR	Public Finance Review
PREM	Poverty Reduction and Economic Management
PRSC	Poverty Reduction Support Credit
SAV	State Audit of Vietnam
SDA	Social Development Adviser
SEDP	Socio-Economic Development Plan
SEDS	Socio-Economic Development Strategy
SOE	State-owned Enterprise
TA	Technical Assistance
TPO	Third Party Organisation
VASS	Vietnam Academy of Social Sciences
VCR	Vietnam Competitiveness Report
VDR	Vietnam Development Report
VFM	Value-for-Money
VGEMS	Vietnam Governance, Economic Management and Social Inclusion Programme
VHLSS	Vietnam Household Living Standard Survey
VKP	Vietnam Knowledge Platform
VTP	Vietnam Transparency Project
UN	United Nations
WB	World Bank
WGI	World Governance Indicators
WTO	World Trade Organization

Business Case

Strategic Case

A. Context and need for a DFID intervention / Vietnam has made huge strides in reducing poverty and achieving high growth. In 1986, Vietnam launched the doi moi, or restructuring, a government initiative aimed at improving the country’s ailing economic conditions. Since then, the Vietnamese government has implemented significant economic reforms which have transformed the country. Vietnam, today, is a development success story. Over the past two decades, Vietnam has been able to deliver development outcomes that very few countries in the developing world could. During the last 25 years, the poverty headcount ratio has fallen by 80% reaching 14.5% in 2008[1]. With an annual average growth rate of 5.64% between 1997 and 2009[2], Vietnam is among the fastest growing economies in the world. At the end of 2010, Vietnam’s per capita income was US$ 1,130. / However, it is now clear that there are limits to the models of growth and poverty reduction which have been so successful. The future will present Vietnam with three serious challenges which it needs to address if it is to maintain its successful development trajectory: macroeconomic stability, new forms and entrenched poverty and governance challenges especially in transparency. These are described below in more detail as the project will seek to address these challenges and will form the content of the programme. There is a real need for development partners help the Government and other partners think through new and alternative paths for reform in these three areas to unleash a new era of successful development. This is the critical added-value of international partners in middle-income Vietnam. / Vietnam’s governance challenges: The Doi Moi reforms that fuelled Vietnam’s rapid growth were not initially based on good governance but rather on a number of specific governance capabilities appropriate for economic reforms[3]. / Firstly, there was a high level of political stability and a streamlined political process that ensured stability and predictability. / Secondly, the state provided credible protection to the private sector and managed the transition to a market-driven economy in a gradual manner. / Thirdly, the state strongly regulated the state-owned enterprises (SOEs) which contributed significantly to growth. / Finally, the government proved capable in targeting resources, including foreign aid, to the poor. / While these preconditions helped Vietnam transform into and sustain a more market-driven economy, there exist governance weaknesses in key areas which may hold back continued development. Based on the World Governance Indicators (WGI), except for Political Stability, Vietnam has the weakest scores on most other governance areas when compared to peers in Asia (see Table 1). / Table 1: Percentile ranking of countries on different governance dimensions / CHINA INDIA INDONESIA S KOREA MALAYSIA PHILIPPINES THAILAND VIETNAM / Voice & / Accountability 5.2 59.2 48.3 69.2 31.3 46.9 30.3 8.5 / Political / Stability 24.1 10.8 18.9 50 51.9 6.6 12.7 51.4 / Government effectiveness 59.8 55 47.8 84.2 82.3 51.7 58.4 44 / Regulatory / Quality 45 39.2 39.7 78.9 71.3 44 56.5 31.1 / Rule of Law 44.5 54.5 31.3 81 65.4 34.6 49.8 38.9 / Control of / Corruption 32.5 35.9 27.3 69.4 61.2 22.5 46.9 33 / Source: World Governance Indicators, World Bank Institute / A lack of transparency and accountability lies at the root of governance weaknesses. The reforms also brought about a gradual shift towards decentralised administration and service delivery. In the move to a more devolved system of governance, the system of accountability has also changed, but has not kept pace with demands of a more complex State and economy. Notably corruption is a key issue in Vietnam affecting both citizens and firms as well as concerning policy-makers. / Information is vital to any system of accountability. A study commissioned by the World Bank on land management[4] systematically examined how well various transparency provisions are implemented in practice at province, district and commune level. It concludes that although Vietnam has relatively good laws and regulations on the disclosure of information to the public, there is scope for considerable improvement at the enforcement and implementation levels. It is broadly recognised that Vietnamese citizens, firms and enterprises, the media and civil society simply do not have the information they need in a systematic manner.[5] / Access to information (A2I) [6] in Vietnam is not backed by any legislation although it is recognised as a right in the Constitution. There are currently many legal documents regulating access to government information. However, there are two key reasons that an access to information law is still needed: one is to help do better what is already in the law, and the other is to recognise the benefits of making public information the rule, rather than the exception.[7] Whilst legislation is not the end in itself, A2I can help mobilise citizens and generate demands on the Government. In this context, having an overarching legislation on A2I could provide an appropriate stimulus for reform. / There are critical questions about the direction of governance reforms that Vietnam ought to take to sustain growth and to improve delivery of administrative services. Improved transparency is a critical issue underpinning both economic reforms and new poverty work. It is now time for Vietnam to undertake the next generation of governance reforms focusing on transparency and accountability in public administration. / Vietnam’s economic challenges: Until 2007, Vietnam had become accustomed to a benign macroeconomic environment: low to moderate inflation, stable exchange rate, large capital inflows, moderate fiscal deficit, and growing international reserves. As a result, economic management was relatively uncomplicated and the markets were more tolerant to sub-optimal policies. The macroeconomic environment has changed considerably after 2007, as the country became a lower-middle income country and an integral part of the global economy. While benefitting from the global boom, it has also been exposed to global shocks. / At the same time, the expansionary fiscal and monetary policy and investment-led approach followed by Vietnam over the last decade to fuel growth has lead to high public fiscal and trade deficits, high inflation and other macroeconomic imbalances. Between 2005 and 2009, Vietnam had one of the highest Inflation rates in Asia (10.8%)[8] – it reached a high of 23% in August 2011. At 5.8% (2005-2009) and 7% in 2010, Vietnam has the highest fiscal deficit in the region[9]. Its trade deficit at 9.4% of GDP between 2005 and 2009 and 11.2% in 2010 is also the highest[10]. The currency has devalued by nearly 25% against the US dollar over the last 4 years. Public debt has grown at 18% annually between 2001 and 2009 – it was 45% of GDP in 2009[11] - leading to downgrading of its sovereign debt rating by all agencies. The problem has been amplified by medium-term structural constraints in the economy such as stagnant productivity, inadequate infrastructure, skill shortages, poor health of state-owned enterprises (SOEs) and weaknesses in the financial sector. / There is growing recognition among senior policy makers that the attention should turn to maintaining macroeconomic stability, and addressing the structural constraints to growth. The Government of Vietnam has accordingly tightened fiscal and monetary policy and results are beginning to show with falling fiscal and external deficits, and declining inflation. The Government has also prioritised three areas of structural reforms including public investment management, state enterprises, and the financial sector. There are important reform challenges ahead to shift the focus from short-term growth targets to sustainable productivity growth. These include better coordination of fiscal and monetary policy, data transparency and policy communication, financial sector stability, and efficient allocation of resources. However, these will be dependent on the governance reforms of transparency in particular, as highlighted in the Vietnam Development Report 2011 on State Owned Enterprises. / There is, therefore, immediate need for GoV to undertake critical macroeconomic policy reforms to address the economic challenges outlined above. This does not discredit the policy choices made by the Government over the past decade which served the country well. Rather, it recognises that the policy agenda needs to change with time to keep pace with unfolding economic realities. / Poverty and gender challenges in a middle-income country: Vietnam is also facing new challenges in the socio-economic sphere which have emerged from the rapid economic transition of the last two decades. Significant strides in poverty reduction notwithstanding, recent evidence suggests that poverty reduction may have slowed down, inequality is rising and new forms of poverty are visible as a result of rapid economic integration. / Recurrent periods of macroeconomic instability have resulted in negative impacts on the poor and highlighted shortcomings in the social security system. Despite good intentions, government policies have tended to be fragmented in nature. The Socio-Economic Development Plan (SEDP) 2011-15 retains a traditional approach to social welfare, with the focus largely on geographically based public investment targeted at poor areas. Vietnam currently lacks a basic cash transfer program for the poor, which is a critical gap in its poverty reduction and social assistance system. The lack of access to the formal social protection system is the biggest welfare gap in Vietnam today[12]. / However, Vietnam is in the process of reviewing and streamlining the social security mechanisms. The Social Security Strategy that outlines short and medium term priorities for reforms has been prepared by Ministry of Labour Invalids and Social Affairs (MOLISA) and is awaiting approval. Dialogue is underway on development of a new social assistance scheme to provide a minimum standard of living for all poor and vulnerable people. Further development of the social insurance system is also contemplated and includes amendments to the Social Insurance Law to make the current system financially sustainable and to expand coverage as well as modernisation of the Vietnam Social Security’s (VSS) administration and fund management capacities. / Vietnam has made great strides in improving gender equality. The legislative framework has been enhanced with the passing of the Gender Equality Law (2006) and the Anti-Domestic Violence Law (2007). However implementation remains patchy, especially the M&E framework. The approval of the National Gender Development Indicators System (NGIS) marks a significant step forward in tackling this gap. Supporting the implementation of this will be a key priority for the coming period. / There is need for GoV to recalibrate its focus on social equity by strengthening its approach to make poverty reduction more inclusive, better targeting social transfers to the poor and ethnic minorities and tackling new forms of poverty in urban areas. / B. Evidence: / Experience to date / DFID and the World Bank have a strong track record of supporting evidence-based policy making in Vietnam with some evidence of impact. For more than 10 years, DFID has channelled technical support to the Government of Vietnam through the World Bank via a trust fund. The first phase of support, Poverty Analysis and Policy Advocacy Programme (PAPAP) was to assist GoV to have better access to and use qualitative and quantitative research to deepen understanding of poverty and to inform their policies, strategies and programmes. In the second phase of support, Governance and Poverty Analysis and Policy Advocacy Programme (GAPAP), the area of support was widened to cover development analysis and policy advice for improved policy-making on poverty as well as governance issues. Box 2 outlines some key deliverables from this support. GAPAP was rated as a very successful programme, scoring the highest mark of 1 in the end of project completion report in January 2012. GAPAP also provided technical support to the Poverty Reduction Support Credit (PRSC) to which DFID contributed £100 million over 5 years. This cycle has now ended but there are concrete plans for a follow-up policy lending operation called Economic Management and Competiveness Credit (EMCC). DFID will not contribute core support to the credit. / There is as strong demand from the government to receive continued support on poverty and governance analysis and policy advice with products and deliverables. GAPAP has proven to be the right approach, but there is also a need to deepen analysis in some areas e.g. public expenditure and government fiscal policies, or expand is other areas e.g. the land market; and introduce innovative approaches (e.g. using social media) to improve policy influencing of the current portfolio of governance and poverty. / The addition of macroeconomic management and more intensive support to social protection to the current portfolio is in response to the contextual demands: they are the critical issues in Vietnam which needs to be addressed, and thus presents many opportunities for the next 5 years. / Box 2: Deliverables and results from GAPAP / GAPAP improved the understanding of poverty in Vietnam and changed the Government’s approach to targeting poverty programmes / GAPAP supported the Government-led Vietnam Poverty Assessment (2008), which informed the SEDP 2011-2015. Further policy work and research (such as poverty mapping and studies on ethnic minorities, disability and the informal sector) is now shifting the discussion of poverty in Vietnam based on evidence. / Government resources are better targeted at the poor. GAPAP provided technical support to develop a new poverty line for Vietnam. The new poverty lines are much higher than previous ones and, as a result, an additional 5.2 million people now benefit from targeted programmes and policies, such as free health care and regular social transfers. / GAPAP strengthened systems for data collection and management / GAPAP helped develop a highly effective, Government-owned and well-used household survey system which informs Government policy and lies at the core of the Government statistical system. / Data produced from this now informs budget allocations. The General Statistics Office’s provincial poverty count is now used to inform a more efficient and equitable allocation of decentralised resources. / Innovative modules (governance, migration, social protection, services) have been successfully grafted on to the national household surveys to spotlight key policy concerns for the Government and have fed into policy formulation, including for the social protection strategy. / GAPAP changed attitudes to governance and corruption / The Vietnam Development Report (VDR) ‘Modern Institutions’ reframed policy discussions on governance and has been widely read, discussed and internalised. An independent policy impact assessment of the VDR found strong evidence of take-up and citation. / Ground-breaking work was done on Corruption Diagnostics, led by the Government and covering firms, citizens and public servants. This is a significant achievement to open up a sensitive area. / An innovative study on land and transparency has incentivised provinces to improve the provision of information. This work will be taken forward in VGEMS. / GAPAP supported labour market and social welfare reforms that resulted in significant benefits for poor people / Minimum wage increased: Labour Force Surveys and analysis of the labour market and wages were supported by GAPAP and led the Government to raise the minimum wage for the formal sector from 230,000 vnd/month in 2003 to 830,000 vnd/month in 2011. / Paid formal employment increased: GAPAP support to the Labour Force Surveys, the Informal Sector Surveys and the PRSC contributed to one of the key PRSC results of three million more people with paid formal employment. / Improvements in women’s wage employment and maternity leave: New labour regulations, due to be approved by the Ministry of Labour soon, support women wage employment and increase maternity leave from 4 to 6 months. / Sources: The Ministry of Labour, War Invalid and Social Affairs website, the World Bank’s PRSC reports and GAPAP reports, Media sources. / Context evidence / VGEMS is firmly aligned with Government priorities. The Socio-Economic Development Strategy (SEDS) 2011-2020 and the Socio-Economic Development Plan (SEDP) 2011-2015 articulate the Government’s medium and long term visions wand reflect the key challenges. The SEDP 2011-2015 in particular focuses on the policies needed to achieve high quality and sustainable economic growth. These include the need to restructure the economy to increase the share of high value-adding economic activities, improve the living standards of ethnic minority populations, strengthen environmental protection, and mitigate and prevent the adverse impacts of climate change. The SEDP also identifies the need to strengthen effectiveness and efficiency of state management through administrative reform including strengthening transparency and accountability mechanisms and fighting corruption. The Government adopted in late 2011 three top priorities for economic restructuring: public investment, State Owned Enterprise (SOE) reform and banking sector. Underpinning each of these is a need for greater transparency and openness. / There is strong evidence (within country and comparative) on the challenges Vietnam faces in the current context as well as what it needs to do to tackle them. This has been articulated extensively in three critical pieces of diagnostic work – The Vietnam Poverty Assessment published in 2010, the Vietnam Development Report (VDR) 2010 on Modern Institutions and Vietnam Competitiveness Report (VCR) 2010. The first two have been supported directly through GAPAP: / The Vietnam Poverty Assessment presents the trends in poverty reduction in Vietnam, analyses the implications in the context of the post-WTO accession period, and makes the case for strengthening social protection, for enlarging opportunities for the poor and for reducing ethnic minority poverty. It advocates the need for different types of policy interventions for chronic and transitory. / The Vietnam Development Report 2010 focuses on devolution and accountability, two aspects of modern institutions that are the essence of Vietnam’s experience in the past two decades. It examines the central state apparatus in the devolved set-up, local governance, functional devolution to units providing administrative services and direct services, the legal and judicial system and an array of forms of oversight for the devolving system. Finally it examines `access to information’, which is the most critical element holding accountability systems together. / The Vietnam Competitiveness Report 2010 contains a broad assessment of Vietnam’s current competitiveness, an analysis of the key challenges and opportunities ahead, and a proposal for an economic strategy to enable Vietnam to reach a higher level of sustainable growth. It identifies the three most critical tasks Vietnam is currently facing based on this assessment, and makes concrete action recommendations on how to address them. / There is an increasing recognition and acceptance of the role good research and policy engagement can have in policy-making in Vietnam.[13] A study by the Vietnam Academy for Social Sciences helps map out the ways of engaging in policy discussions based on research and points to positive examples in the Vietnamese context. Through GAPAP DFID and the WB have tested how to get challenging messages across to the right constituents: small, informal workshops, targeting provinces, working with National Assembly and engaging with broader stakeholders (see the Policy Impact Study on the Vietnam Development Report 2010 which captures these lessons). / VGEMS: addressing key gaps in an innovative manner / The next five years are set to be dynamic and uncertain and pose a range of complex challenges for Vietnam. In this rapidly changing environment, there is a need for Government to be proactive and forward-thinking. External support can help to enable the Government to be in a position to shape the reform agenda rather than be shaped by the changing context. For this to happen, three key demands can be seen as emerging: / Demand for timely, accurate and wide-ranging data across sectors: There is a need to strengthen both the institutionalised data collection mechanisms (such as the Vietnam Household Living Standards Survey - VHLSS) as well as innovate with citizen feedback mechanisms on quality of governance and public service delivery. / Demand for multiple perspectives for high quality analysis and diagnostics: Equally there is real demand for responsive, high-quality analysis of the key challenges facing Vietnam based on the data and information gathered to develop critical pieces of evidence papers across thematic areas. These may be generated from multiple organisations, both within Government and outside. / Demand to create pressure and consensus for reforms: Whether at the national level when dealing with macro-economic issues or at the local level on basic service delivery, making evidence count is fundamental. Too often good analysis has not been played out in the policy discussions effectively. Traditional dissemination processes have limited utility and there is need to seek new and creative routes to generate debate and influence policy and its implementation. / None of the above is easy or automatic, and nor is demand universal. But there are opportunities and openings which should be grasped. Working on the three levels makes VGEMS innovative: it is proposing new and untested initiatives to raise public awareness and mobilise public pressure for change. This is built into the project as the central aspect. It does not mean that success will be assured, given the context. This takes the lessons from GAPAP and is well grounded in the new context in Vietnam. However, it is important to emphasise that it is not more of the same. VGEMS will move on from gathering evidence to increasing policy impact. / Policy areas for VGEMS / The three policy areas where there is immediate need to address the demands of data, analysis and reducing the gap between evidence, policy and implementation are captured in the matrix below with examples of work that will be completed under VGEMS is presented. / Table 1: Indicative table of interventions by policy sphere and level. / Level of engagement / Policy sphere Data & Information generation Analysis and Evidence Uptake and impact / Transparency Sector Studies on Transparency provide information to Government and other stakeholders on basic compliance. Analysis of Information bottlenecks – structural and operational / Social monitoring tool piloted and tested. Use transparency data for driving cross-provincial/ Ministerial incentives and encouraging external non-governmental monitoring. / New social monitoring tool becomes accepted form of data collection. / Vietnam Transparency Project established and influencing GoV implementation. / Economic management Survey on citizens and firms perceptions provides timely and periodic data on opinions. / Data on competitiveness issues provides timely information on productivity issues. Public Financial Reviews and / policy reform notes on key issues. / Competitiveness analysis provides evidence for policy reforms to boost productivity and growth. A knowledge platform enables wide dissemination and debate. / Evidence provided by policy reform notes and media training on fiscal issues improves accuracy of reporting. / Analytical support to inform policy choices for the Economic Management and Competitiveness Credit / Poverty, gender and social protection Poverty measurement (VHLSS) provides robust and periodic data (including gender disaggregated) which underpins statistical system. / Support the national gender indicators system (NGIS) by providing TA to GSO and line ministries for improving the quality and timeliness of indicators laid out in the NGIS. / National poverty database provides reliable, cost-effective and timely information for targeting of social programmes Poverty Assessment and analytical studies in inequality, ethnic minorities poverty, urban poverty and vulnerability. / Design of a new cash transfer programme for the poor, including improved targeting methodology / Innovative study of perceptions of inequality Poverty Assessment informs the design and implementation of new programmes and approaches to best tackle new poverty challenges. / Piloting of Social Assistance cash transfer programme feeds into scaled up approach to social protection. / Network launched on inequality/poverty to re-invigorate debate and policy impact of evidence. / Why it is right for DFID to intervene / DFID has a 10-year Development Partner Arrangement (DPA) with the GoV that sets out clearly how DFID will support the Government and Vietnam more broadly. As with our Operational Plan, the last 5 years of DFID’s engagement with Vietnam will focus on leaving a strong legacy of effective institutions. This engagement will be key in delivering this both for stronger, more accountable and transparent Government institutions but also stronger international partner institutions to carry on working with the Government of Vietnam after DFID’s graduation. We have a history of engagement with the World Bank particularly on poverty and governance issues which provides a strong platform for continued but more focussed and outwardly-targeted engagement. For economic management the World Bank has a comparative advantage in this field but we have not to date provided substantial support. / At a programme level, DFID support will ensure that our legacy will be achieved in three different ways across the VGEMS programme. This will be the ‘success’ of VGEMS and makes a strong case for DFID intervention: / Local institutions will own and lead the agenda post VGEMS: Progressively the government or local organisations will take over as the donors, including the WB will blend out, for example the Vietnam Knowledge Platform and Vietnam Transparency Project; / Large Government/ WB programmes are established: The World Bank set up successful lending programmes that have the potential to run for many years in areas that we consider priorities, and these are increasingly seen as GoV programmes in key areas e.g. EMCC and Conditional Cash Transfer programme; / The World Bank increases its role in core areas as VGMES progresses: VGEMS is ensuring sustainability by encouraging the WB to allocate internal resources to take over from DFID–funded activities in key areas. This will be done in a smooth manner. / What happens if we don’t / The areas of engagement proposed for this intervention are both broad and require many actors to be engaged. If DFID does not invest in this VGEMS, it will lose the opportunity to influence GoV in these critical areas. While this may not result in policy statis, it could severely delay credible policy-making in key areas. Without DFID’s contribution through the trust fund, the World Bank will find it increasingly difficult to extend technical assistance and policy support to GoV. It will be extremely difficult for the World Bank to find similar funding from other sources to support the proposed interventions. / VGEMS would not be the only actor – and the World Bank will engage on these areas without our support but to a far lesser degree. There is no displacement in the additional support but rather a leveraging of World Bank influence, analytics and assistance budget and staff time. The Asian Development Bank is likely to engage especially on the economic management area but does not have the in-country technical resources. The UN in particular engages on smaller initiatives around the poverty and social protection agenda and on governance. However, their support tends to be on an ad hoc basis in terms of data and evidence production especially on the poverty/data work. They do not have a comparative advantage on economic management. As other bilaterals also graduate and change their development focus, there are fewer actors engaging at such a high level or focussing on policy dialogue. To date, DFID has funded much of the core data work (around VHLSS) and poverty data, as well as substantial work on transparency/governance. Without this support, this work is unlikely to continue at the current level and leave a substantial gap in the overall support in these areas. / Box 1: Poverty trends and new challenges / In 2008, 50 per cent of ethnic minorities, who constitute 15% of the total population, lived below the poverty line, compared to only 9 per cent of Kinh-Hoa majorities. By 2010, ethnic minorities accounted for 65 per cent of individuals in the poorest welfare decile, up from 53 per cent in 2006. Inequality, whilst relatively low for a middle-income country, is creeping up - the “rich-poor” gap, a measure of “absolute” inequality, rose from 8.1 to 9.2 between 2002 and 2010. Initial analysis suggests that households in urban and semi-urban areas, especially migrants, have been particularly hit by the global economic crisis and inflation. With increasing urbanisation, the face of poverty and sources of vulnerability present different challenges than traditional poverty concerns in rural areas.
B. Impact and Outcome that we expect to achieve / The impact of the programme will be ` Stable growth and sustained poverty reduction with stronger government accountability’. This will translate into the following at the end of 2015; / Accountability will improve through enhanced transparency and openness. Vietnam will record a will record a significantly higher percentile ranking on the Global Integrity Index indicator for Access to Information. It will also show improvement on control of corruption, particularly on service delivery, and will be measured through the VHLSS governance module in 2012 and 2014. / Macroeconomic stability will result from a series of policy reforms undertaken by GoV. The impacts are estimated to be in line with targets specified by the SEDP 2011-15 (under Scenario 1 – conservative) and will include (a) Budget deficit within 4.5% of GDP (b) Consumer Price Index growth rate at single digit levels. At the same time, public investment and state-owned enterprises will be made more efficient. / Responses to poverty challenges will be deepened and enhanced by data and analysis, wider, better targeted and monitored social programmes and will be reflected in reduction of poverty among ethnic minorities as measured by the VHLSS 2012 & 2014. / The key outcome of the programme will be `Significant reforms adopted by GoV in the policy spheres of transparency and accountability, macroeconomic stability and social protection’. This will translate into the following at the end of 2015, / Transparency outcomes will be evident in policy as well as in service delivery. In policy terms, it is envisaged that GoV will strengthen the legal and operational environment for access to public information. At the sectoral level, it is expected that strengthened transparency and accountability will improve access to financial information by firms, improve access to services in land administration, health, education for citizens. / In the macroeconomic sphere, the intervention will result in significant policy changes in the area of public financial & fiscal management which will include public investment, SOE governance, inflation management, debt management and fiscal transparency. / In the poverty and social protection sphere, the programme will enable GoV to strengthen the social protection system to protect the poor and vulnerable by amending the social insurance law to increase coverage and financial sustainability. It will also help GoV to pilot a social assistance cash transfer programme particularly to the ethnic minorities. / The likelihood that credible policy choices, if taken, will have envisaged impact is high. Tangible reforms that foster transparency such as Access to Information legislation can strengthen accountability and control corruption. The case of India is a pertinent one, where the Right to Information has enabled citizens to demand timely and better public services. Macroeconomic reforms such as fiscal responsibility measures will have a direct positive effect on inflation. Better public investment will make the economy more efficient and drive up competitiveness. Better targeted and monitored social programmes will have a direct impact on the welfare of the poor, particularly the ethnic minorities. / However, there are key risks which could impact achievement of outcomes and impacts. The key risk is possible external economic shocks that adversely affect growth in Vietnam which could alter government priorities or dent the impact of credible policy choices. Simultaneously, for policy reforms to translate into real impacts will require GoV to take tangible implementation measures.
[1] Vietnam Household Living Standard Survey (VHLSS), 2008
[2] Vietnam Competitiveness Report 2010
[3] `Pro-Growth Anti-corruption and Governance Reforms for Viet Nam’, Dr. Mushtaq. H. Khan, 2009
[4] Survey Report on Information Disclosure of Land Management Regulations, 2010
[5] Vietnam Development Report 2010
[6] Over 85 countries around the world have implemented some form of the FoI legislation.
[7] ibid
[8] ibid
[9] ibid
[10] ibid
[11] ibid
[12] Poverty Reduction In Vietnam: Achievements And Challenges, Vietnam Academy of Social Sciences (VASS), 2011
[13] See Centre for Analysis and Forecasting, Bridging Research and Policy, August 2011

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The generation of feasible options is informed by the theory of change and our current engagement in the thematic areas. / Theory of Change: The theory of change for the programme is based on the rational proposition that reform or change can be brought about by collating data and information, analysing it to produce relevant policy documents and engaging and influencing policy-makers and other stakeholders to effect changes on the basis of evidence provided. Whilst this is presented as a linear change, the reality is that the process is both messier and more complex. / This hypothesis has been developed into a detailed theory of change as encapsulated in the diagram below. The key assumptions in the results chain are given overleaf. / Key Assumptions & Evidence / Moving from Input to Output / Two key assumptions inherent in the proposition are (a) the allocation of resources across output areas will be made efficiently and (b) high-quality personnel will be deployed for the tasks. There is strong evidence of DFID Vietnam being able to manage financial and human resources effectively across a diverse range of programmes including multilateral trust funds. There is also strong evidence that the WB is a reliable and strong partner in terms of delivery, based on past experience in Vietnam and in the Multilateral Aid Review (MAR) assessment. . / Moving from lower-end Outputs to higher-end Outputs / The key assumptions on this count are (a) The programme is designed efficiently and the processes linking lower-end outputs to high-end outputs are clearly articulated (b) Programme delivery is efficient within and across the thematic areas. DFID Vietnam, in partnership with multilateral donors, has successfully delivered similar programmes. It has supported GoV Ministries to improve their information systems and to use it for informing policy. The Governance and Poverty Policy Analysis and Advice Programme (GAPAP), delivered through the World Bank, has successfully supported similar reforms. / Moving from Outputs to Outcomes / The key assumptions on this count are (a) GoV, particularly key agencies like National Assembly, Office of Government, Ministry of Finance, Ministry of Planning and Investment, GSO, MOLISA and Vietnam Fatherland Front (VFF), is keen to engage with donors, civil society, think tanks and experts while deliberating on policy choices and (b) GoV proactively seeks information and evidence to inform internal policy discussions and debate. There is evidence GoV (OoG) seeking advisory support from the World Bank on key macroeconomic issues. GSO and MOLISA have continuously engaged with donors including DFID for developing robust information systems. An impact assessment of the VDR 2010 showed that its uptake across stakeholders including government, media and donors was encouraging. At the same time, knowing that the policy-making process in Vietnam is a black box, evidence and engagement may not be the only factors that determine policy choices. / Moving from Outcomes to Impact / The key assumptions for outcomes to result in impact are (a) External factors such as global financial conditions remain favourable or do not worsen to a point that affects growth in Vietnam adversely (b) GoV takes tangible measures to implement policies at central as well as provincial levels. The capacity of GoV to design implementation guidelines on policies and monitor them is high once there is strong political will and broad consensus. In fact the economic reforms undertaken over the last two decades bear testimony to this assertion. At the same time, there exist significant deficiencies in the implementation of laws in many sectors such as those pertaining to transparency requirements, and in the implementation of policies in many areas at the provincial level. / Leads to policy & / programmatic reforms / Engaging & Influencing / Analysis & evidence building / Generate data, information / Financial: / GBP £6 million / Including mobilising additional WB staff r resources: / DFID staff time: / Team Leader, Economist, SD Adviser, Programme Officer / Significant reforms adopted by GoV in the policy spheres of: / Transparency: access to information and public disclosure of information and administration operation / Macroeconomic policy: stronger market economy measures in place in dealing with public financial management & fiscal issues, and inefficient state enterprises / Poverty & Social Protection: Poverty better measured and monitored, social protection system strengthened / Inputs / Outputs / Information Evidence Influencing / Outcome / Impact / Stable growth and sustained poverty reduction with stronger government accountability / Global Integrity Index moves Vietnam up to a score of 40 by 2015. / Budget deficit within 4.5% of GDP; CPI growth rate below 7 by 2015 / Reduced poverty among ethnic minorities / 1) Data, Information & Analysis: Develop information & undertake analysis on macroeconomic policy & fiscal management (VDR, PFRs, Sectoral reports) / 2) Translate evidence into Policy Notes (PRMs) on key macroeconomic themes, inform policy choices through EMCC / 3) Engaging & Influencing: Establish the Vietnam Knowledge Platform (VKP) to disseminate information and bring together stakeholders, strengthen EMCC policy dialogue and support economic restructuring agenda / Output 2: Support GoV to design and adopt key macroeconomic reforms / 1) Information & Analysis: Undertaking research and analysis – VHLSS, SCOLI, Poverty Mapping, Gender Indicators, Poverty Assessment / 2) Building evidence through piloting: Design & pilot a social assistance programme for the poor and marginalized groups / 3) Engaging & Influencing: Amendments to Social Insurance Law, targeting of poverty & social transfers, monitoring social programmes / Output 3: Strengthen GoV capacity to measure & monitor poverty and to strengthen social protection system / 1) Data, Information, Analysis: Generating evidence on transparency across sectors & need for FoI legislation / 2) Engaging & Influencing: Strengthening advocacy and engaging policy makers for FoI legislation and transparency in key sectors / 2) Pilot testing a social accountability experiment in select provinces and disseminating lessons / Output 1: Engaging with multiple stakeholders for fostering greater transparency & accountability
A. Feasible Options / DFID will graduate from Vietnam in 2016. In this context it is important to consider how best to secure a long-lasting impact of current and future DFID support to the areas outlined in the strategic case. DFID has a long-standing and successful partnership with the World Bank in the fields of poverty and governance. In the process, DFID Vietnam has been able to encourage the World Bank to focus more on equity and impact on GoV’s policies in key areas of engagement. In addition, this partnership has also enabled development of core competencies of both donors and government which could be potentially exploited for effective programme delivery. Ensuring sustainability to the proposed work is critical. / DFID Vietnam also engaged closely with the World Bank while its Country Partnership Strategy 2012-2016 was developed, encouraging the World Bank to work more actively on macro-economic issues and adopt governance as a cross-cutting topic. The World Bank has responded positively and the Strategy paper has prioritised these areas, in addition to equity/inclusion, among a much narrower list of focused topics. / Given this context, we envisage three options. The first is to go through multiple channels - a similar World Bank executed trust fund working on poverty/social protection & governance areas and a private sector - managed facility to work on macroeconomic policy issues. At the time of design the private sector facility was thoroughly considered. The second option is to provide assistance through a single channel namely a World Bank executed trust fund across all three thematic areas. The third option is to the counterfactual, ‘do nothing’ option. This does not mean that no work is undertaken in these areas however, just that DFID’s contribution is not included. / The contents of the programmes would be broadly the same (with details outlined in the strategic case) under options 1 and 2: what changes is the delivery mechanism. / The feasible options are set out for consideration: / Option 1: Multi-channel assistance through a World Bank Executed Trust Fund and a Private Sector Policy Facility for Macroeconomic engagement. / Option 2: Single channel assistance through a World Bank Executed Trust Fund / Option 3: Do Nothing / Option 1: Multi-channel assistance / This option will explore multiple channels (two) for realising the outcomes. / The first channel will be a World Bank executed trust fund to take forward the areas of engagement under the existing WB executed trust fund (GAPAP). Given the strong track record of GAPAP in delivering on governance and poverty, we do not see a case for changing the management partner from the WB. The new phase of support through the WB executed trust fund will involve: / Supporting governance reforms for greater transparency and accountability – this will involve (i) Generating evidence on transparency across sectors & need for legislation on improved transparency including access to information; (ii) Strengthening advocacy and engaging policy makers for transparency in key sectors and better access to information, and (iii) Pilot testing a social accountability experiment in select provinces and disseminating lessons. / Enhance GoV capacity to measure & monitor poverty and to strengthen the social protection system– this will involve (i) Assisting GoV to improve data generation and analysis, research and analytical capacity including VHLSS 2012 and 2014, spacial cost of living surveys, poverty mapping, operationalising the National Gender Indicators System etc. (ii) Helping GoV to design & pilot a social assistance cash transfer programme for the poor and marginalized groups; and (iii) Influencing changes to Social Insurance Law and (iv) better monitoring of social programmes. / We do not consider outsourcing the first two components given the strong track-record of working with the WB on these issues. / Simultaneously, a second channel of assistance will explore working through a facility outside the World Bank on macroeconomic policies, which will be likely contracted out to the private sector to maximise flexibility and responsiveness. This will involve: / Support GoV to design and adopt key macroeconomic reforms by (i) Helping build information base & undertake analysis on macroeconomic policy & fiscal management; (ii) Develop and share evidence products and policy notes on key macroeconomic themes and (iii) Establish the Vietnam Knowledge Platform (VKP) to disseminate information, engage with and bring together key stakeholders to build pressure and consensus for economic reforms. / A private facility has the benefits of bringing in fresh perspectives, being flexible to provide international expertise and is not tied to a particular institution or established institutional arrangements. / We ruled out the options of a Government agency or a local think tank or an academic institution managing the macro-economic component. This component involves working with different agencies such as the Office of the Government, Ministry of Finance, Ministry of Planning and Investment, State Bank of Vietnam, and several non-government agencies. Inter-ministerial coordination is challenging in Vietnam. We consider it more efficient to focus Government’s efforts on improving policy making coordination rather than on administrative management of a programme involving multiple partners like this one. It would also be more difficult for the Government to bring in the international perspectives needed in Vietnam. Given the broad agenda ranging from monetary and fiscal policies to public financial reviews and media/public engagement, a local think tank would not have the capacity to run such a complex programme. / Period of Support: July 2012 to March 2016 / Amount of Funding proposed: £ 6.7 million (for two separate channels) This is more expensive due to the higher overhead costs to set up and run a private facility. / Option 2: Single channel assistance / This option will involve a single channel for realising the outcomes. / This option will work only through a World Bank executed trust fund. It will take forward the existing trust fund priorities relating to governance and poverty & social protection. It will also aim to address emerging macroeconomic policy challenges through the trust fund given the World Bank’s plan to strengthen its engagement in this area, its convening power and the high level of Government trust in its technical capacity. It will also be more efficient for DFID to work with a single partner and manage one programme covering all three areas. It will also benefit by maximising the synergies across the components. For DFID it will enable us to engage in the new Economic Management and Competitiveness Credit (EMCC) which is expected to deliver over $1 billion of credit over the next 5 years, thereby allowing us to leverage and maximise the use of our own resources and exert influence over the broader agenda. Box 3 below outlines how EMCC engagement will work: / Box 3: Economic Management and Competitiveness Credit / Objectives: To support the Government of Vietnam to design and adopt key macroeconomic reforms by i) contributing to analytical work to support the Economic Management and Competitiveness Credit (EMCC) operations, the World Bank’s post-PRSC operations; and (ii) undertaking analysis of fiscal and public finance management. / Outcomes: (i) Better understanding of policy impacts on competiveness and impacts of types of reforms; (ii) Improved analytical information on Public Financial Management to support government decision makers and the reform agenda in investment and development policy operations. / Analytical and Advisory Activities to Support EMCC. Competitiveness is one of the key pillars of the SEDP 2011-15. The EMCC will enable the Government and Development Partners to support critical reforms for Vietnam’s transition from endowment based growth to increased productivity and competitiveness. Competitiveness is a function of many things. But the EMCC will focus on economic management reforms to support: macroeconomic stability; strengthened public sector governance; and private sector development. / One of the significant improvements of EMCC over PRSC is the emphasis on anchoring the policy triggers on solid analytical foundation. For each of the three themes mentioned above, one/ two policy reforms (triggers/policy actions) per EMCC operation will be identified at least 12-24 months prior to the commencement of the operation. Once the triggers for a given operation have been agreed, joint Development Partners-Government working group will initiate analytical work: i) examining how current policies will impact on competitiveness in the short to medium-term; and ii) assessing (where possible) the potential impact of reforms on competitiveness. The analysis will be compiled into a short report for each operation. It should highlight expected results, monitor them, and report them in the program document. VGEMS will contribute support to one/two policy triggers a cycle. / The key components of option 2 will therefore be: / Supporting governance reforms for greater transparency and accountability – this will involve (i) Generating evidence on transparency across sectors & need for legislation on improved transparency including access to information; (ii) Strengthening advocacy and engaging policy makers on transparency in key sectors and better access to information; and (iii) Pilot testing a social accountability experiment in select provinces and disseminating lessons. / Support GoV to design and adopt key macroeconomic reforms by (i) Helping build information base & undertake analysis on macroeconomic policy & fiscal management (VDR, PFRs, Sectoral reports); (ii) Develop and share evidence products and policy notes on key macroeconomic themes; (iii) Establish the Vietnam Knowledge Platform (VKP) to disseminate information, engage with and bring together key stakeholders to create pressure for economic reforms; and (iv) Contribute ring-fenced technical support to the Economic Management and Competitive Credit, the WB’s general budget support operation on economic reforms. / Enhance GoV capacity to measure & monitor poverty and to target social transfers – this will involve (i) Assisting GoV to improve data collection and analysis, research and analytical capacity including VHLSS 2012 and 2014, spacial cost of living surveys, poverty mapping, operationalising the National Gender Indicators System, developing and analysing the national poverty database for better targeting of social programmes (ii) Helping GoV to design & pilot a social assistance cash transfer programme for the poor and marginalized groups (iii) Influencing changes to Social Insurance Law and (iv) better monitoring and targeting of social programmes. / Period of Support: July 2012 to March 2016 / Amount of Funding proposed: £ 6.0 million / Option 3: (Do Nothing counterfactual) / If DFID does not invest in this instrument, it will lose the opportunity to influence GoV in these critical areas. While this may not result in policy statis, it could severely delay credible policy-making in key areas. Without DFID’s contribution through the trust fund, the World Bank will find it increasingly difficult to extend technical assistance and policy support to GoV. It will be extremely difficult for the World Bank to find similar funding from other sources to support the proposed interventions. In the absence of this programme, it will be difficult for DFID to leave a strong legacy product upon graduation from Vietnam. / The World Bank would still engage in the areas of governance, governance and poverty/social inclusion. However the level of depth in their engagement will be much less. Importantly, they would not have staff dedicated to Vietnam in critical areas of poverty and governance. For example experience has shown that in the area of economic management, with their own limited resources for technical support, it could only be experts participating in workshops/seminars and meeting Government experts on an ad hoc basis. They would not be able to undertake studies into a large number of areas required to address the fundamental macro-economic problems in Vietnam. Nor would they be able to sustain their support to a Knowledge Platform over several years so that it takes root. Other multi-lateral agencies do not have comparative advantage or large technical resources to deal with these issues on a continuous basis. Similarly on governance or poverty/social inclusion, the types of work foreseen with the World Bank will not be addressed through other channels. Without DFID further support on core data collection, e.g the VHLSS and poverty analysis, and transparency, there would be a major gap in support in these critical areas. / What VGEMS will do / VGEMS is designed to be a responsive, flexible programme. During the course of the programme it is expected that it will engage on a range of areas. There will be both substantial investments in core areas which are discussed below and are described under option 2 above in broad terms. There will also be a series of other activities which will contribute to the output. For example, in the governance dimension VGEMS will provide follow-up to the Anti-Corruption Diagnostic Survey undertaken in 2012. Some examples of the interventions have been detailed in the strategic case policy intervention table 1. Boxes 4-7 below provide the details of some of the largest initiatives that are planned under VGEMS in the key areas of governance (transparency), economic management, poverty and social protection. / Box 4: The Vietnam Transparency Project / Background / An oft-heard lament in Vietnam is that the laws are sound but implementation is poor, and this is nowhere more true than in the provision of information. In 2010, GAPAP supported the piloting of a novel approach that measured actual transparency over time and provides real feedback on the degree of transparency across provinces and ministries. The Vietnam Transparency Project (VTP), to be a major component of VGEMS, will scale up this approach in several ways: / The VTP will gradually expand to cover a range of sectors. / The exercise for each sector will be repeated annually. / The VTP will take an expanded approach to dissemination and feedback. / The VTP will explore new avenues of integrating the citizenry into the dialogue on transparency using modern technology. / The VTP will work with Vietnamese think tanks, universities and NGOs to generate sustained interest in the VTP and champions for transparency. / In expanding this approach, the VTP will create a forum for keeping the problems with access to information consistently in the spotlight and demonstrating the benefits of greater transparency. / Approach / There are four basic phases to the transparency project: / The Data Phase for each sector consists of the following: (i) a stock taking of how current legislation guarantees transparency in that field; (ii) devise an approach for checking whether that information is actually made public as proscribed by law. / The Feedback Phase consists of: (i) reporting on the results, specifically highlight good and bad performers, and the reasons underlying poor performance; (ii) providing feedback directly to the provinces and/or government agencies; (iii) allow for tracking over time; repeating the data collection annually. / The Analysis Phase will highlight areas of greatest weakness, and the reasons underlying the weakness and may also highlight the consequences of the lack of transparency. / The Diffusion Phase will be introduced gradually to enhance each of the other phases and make a wide range of stakeholders active participants in the VTP. This phase consists of making use of advancements in information technology to allow the public to provide their own experiences with requests for information. / Finally, a key part of the approach for the VTP will be to partner with an NGO or Think Tank or University that has a particular interest in transparency. This will include a dedicated website to be developed to underpin all the phases. / There are several expected outcomes from the VTP, including / Greater attention to transparency as a key development outcome and better understanding of the reasons that transparency remains weak despite legal; / Data for researchers, complementing what the survey-based data; / Incentives for provinces and ministries to improve transparency; / Empowerment of civil society, the media and the National Assembly to pressure provinces and ministries that do not comply with existing legal provisions. / Box 5: The Vietnam Knowledge Platform (VKP) / This initiative aims to strengthen engagement in creation, sharing, dissemination and adoption of knowledge in a systemic manner in the field of economic management. The core of the task is the establishment and active operation of a partnership group with participation from a broad range of stakeholders such as national scholars and local think-tanks, with government counterparts through OOG, and with media outlets (mostly electronic). Given Vietnam’s fragmented institutions, an initiative such as VKP can help to build consensus on critical reforms among competing institutions. The VKP has strong political support from the GoV. It will do three things: / Support data and information generation: Support surveys on citizens and firms perceptions on line and through the VKP web portal. A regular contest can be introduced to encourage the participation of local research institutes and universities in policy research. Effectively share information. / Provide evidence and analysis: Produce policy notes on key macro issues such as public investment, SOE reform, public debt, fiscal decentralisation and deficit, price management; share international good practice in key areas. Bring in external/ well respected international speakers, and use VKP as a way to get evidence and analysis circulating. / Uptake and impact: this will be the main focus of VKP. An Information Portal for the VKP will be created to facilitate the storage, sharing, discussion, and dissemination of knowledge, as well as access to important sources of development knowledge. Existing WB facilities such as Public Information Centers in HCMC, Can Tho, Da Nang and VDIC in Hanoi will also be utilized towards sharing and disseminating knowledge. There will be support to the media about better reporting on technical issues of macroeconomic management / The Vietnam Knowledge Platform should ultimately be managed by Vietnamese counterparts and serve as a forum to discuss and propose solutions to Vietnam’s economic problems. It will also incorporate and promote existing knowledge transfer activities to avoid duplication, fragmentation and achieve sound leverage of resources usage. / The outcomes of the VKP will include / A sustained forum to facilitate the adoption of evidence-based policy making with high level of transparency / Increased participation of private research centers and regional universities in policy research / Adoption of the reform measures recommended through VKP / Box 6: Addressing New and Old Poverty Challenges in Vietnam / Vietnam achieved rapid progress at reducing poverty over the past twenty years: the poverty headcount fell from 58% in the early 1990s to around 14% by 2008. But in 2008, one-fifth of rural households still lived below Vietnam’s (basic-needs) poverty line, an increasing share were ethnic minorities, and the gap between the better off and poorest was continuing to rise. In terms of new challenges, vulnerability is increasing and new forms of poverty arise as a result of rapid economic transformation and global integration. / New thinking, new information, and new policies are needed to address emerging issues linked to rising inequality, also urban poverty and vulnerability. VGEMS will support Vietnam to work in three areas: / Data and Information Systems: / Support the development of the General Statistics Office’s (GSO) core data systems, with particular focus on the 2012 and 2014 2016 VHLSS, also ongoing surveys to measure the cost of living in different regions (2012, 2014 SCOLI). / Support more innovative data collection outside core government systems, e.g. collecting high frequency data to monitor the quality of key social services, also impacts of social policies. / Quantitative data collection systems will be complemented by qualitative field exercises that collection information e.g on the long-run drivers of poverty reduction, perceptions of inequality, specific challenges and opportunities for improving the well-being of ethnic minority households. / Evidence and Analytics to Inform Policy Debates / Studies on emerging topics are underway under the auspices of the 2012 Poverty Assessment, including new work on multi-dimensional poverty, ethnic minority poverty, also new sources of vulnerability. / New work is being launched on inequality, including an innovative study of perceptions of inequality, also inequality of opportunities versus inequality of outcomes. New poverty maps are being prepared, based on the 2010 VHLSS and 2009 Population Census, to assess current and future patterns of regional inequality in the context of Vietnam’s future growth model. / A full Poverty Assessment will be prepared in 2014-15, building on ongoing work e.g. on inequality, urban poverty and vulnerability, poverty and governance other emerging topics. / Working with Partners to Improve Poverty Reduction Policies and Programmes / Key local partners – e.g. research institutes, counterparts in government, development partners, National Assembly – will be actively engaged in the design and execution of analytic work and policy studies. / Better designed programmes: The rich body of work included in the 2012 PA will inform the (re)design of programmes such as NTP-SPR and P-135, as well as support the design of new pilot programmes to reduce poverty in difficult areas e.g. the Central Highlands. / Conditional Cash transfers programme started and scaled up. VGEMS will play a critical role in setting the future frame for the whole social protection system beyond 2015. / Box 7: Social Protection / Vietnam’s economic and social transitions from a low to a middle income country and from a young to an aging society are focusing the attention of policy makers in Vietnam towards systematically strengthening the formal social protection system. Despite rapid progress in poverty reduction, poverty remains high for certain groups and those living in less accessible regions (ethnic minorities), and the gap between the poorest and the better off is rising. Meanwhile, the increased global integration of the Vietnamese economy and the greater mobility of its population create opportunities for Vietnamese citizens through new and better jobs. However, it also exposes growing numbers of people to economic shocks and employment risks which, if not managed well, may undermine the recent success in poverty reduction. Migration and the transition from extended, multi-generational families to nuclear ones weaken traditional informal intra-family or -community support mechanisms and call for more formal social safety nets. / Three social protection system challenges stand out: First, Vietnam currently lacks a basic social safety net program for the poor to help them respond better to economic and life-cycle shocks and address chronic multidimensional poverty and vulnerability among certain groups. Second, its social protection system lacks strong delivery systems, including monitoring and evaluation. Third, the fast aging of Vietnam’s still young population as a result of declining fertility and rising life expectancy underscores the need to further strategically develop its still small and public sector-oriented pension system to widen coverage, including for the informal sector, and ensure financial sustainability as well as fairness between private and public sector and between men and women. VGEMS aims to support the government in tackling these three challenges. / Development of new social assistance cash transfer program: VGEMS will play a critical role in supporting Government in developing a new social assistance cash transfer program which aims to help strengthen the social protection and poverty reduction system and reduce fragmentation and overlap. It will help set the frame for a strengthened role of the social protection system in poverty reduction beyond 2015. / Social protection system strengthening: VGEMS will support technical assistance and advice to Government on key aspects of strengthening social protection service delivery including targeting, delivery systems and monitoring and evaluation. / Amendments to the Social Insurance Code: VGEMS will support extensive policy advice on amendments to the Social Insurance Code foreseen to be adopted in 2013, including on pension policy changes and delivery system reforms. / B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Medium / 2 Medium / 3 Medium / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The contents of the first two options are very similar. They involve non-infrastructure interventions, and thus pose minimum direct impacts on the environment. DFID Vietnam at present also supports Vietnam in climate change capacity building, adaptation and low carbon analytical works through a Trust Fund (VNCLIP) administered by the World Bank in Vietnam. Therefore, there would be opportunities to synergise efforts at macro policy level. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C - Non-infrastructure intervention, therefore minimum or no direct impacts on the environment. C - Some opportunities to synergise with the VNCLIP in that analysis to help design and pilot a social assistance programme for the poor and marginalized groups could consider climate change impacts on those groups. / No opportunity is foreseen regarding the second channel of assistance in terms of influencing climate integration. / 2 C - Non-infrastructure intervention, therefore minimum or no direct impacts on the environment. C – Similar to Option 1 but there might be even more opportunities in terms of synergising with VNCLIP whereby all key components of VGEMS are to be delivered by WB. / 3 C – No direct impacts on environment. However, if the fund is used otherwise for other purposes that involve infrastructure, there would be environmental impacts C – No opportunity is foreseen. / Political Appraisal / This section seeks to identify whether the programme will work in the unique Vietnamese context and draws as far as possible on evidence. It looks at four aspects which are fundamental to the success of VGEMS: (i) political commitment; (ii) leadership and engagement, (iii) challenges of policy influencing and (iv) space for engagement and debate. / There is some evidence of government commitment, particularly at the national level on the core reform agenda, and this is articulated in the Socio-Economic Development Strategy 2011-2020 and the Socio-Economic Development Plan 2011-2015 for reforms to be pushed forward in the three key areas. The SEDP in particular focuses on the broad range of policies needed to achieve high quality and sustainable economic growth. These include the need to restructure the economy to increase the share of high value-adding economic activities, improve the living standards of ethnic minority populations, strengthen environmental protection, and mitigate and prevent the adverse impacts of climate change. The SEDP also identifies the need to strengthen effectiveness and efficiency of state management through administrative reform including strengthening transparency and accountability mechanisms and fighting corruption. The Government adopted in late 2011 three top priorities for economic restructuring: public investment, State Owned Enterprise (SOE) reform and banking sector. On paper, commitment is strong. However, there are significant incentives which run counter to the actual enforcement of the commitment which remain important barriers to fast-paced reform. We expect commitment to vary across the agendas: what VGEMS will need to do is carefully analyse and nurture commitment in sensitive areas. / Leadership and engagement: Evidence of positive engagement can also be seen across different sectors and Ministries, including the Office of Government, Ministry of Finance, General Statistics Office (GSO), and MOLISA, entities which will be critical for the programme. There have been specific requests from Government for policy input especially on the economic agenda. At the province and commune levels, there is increasing evidence of state actors willing to support greater citizens’ access to information, participation and engagement in service delivery. However, to make it systemic and sustainable, there is need to engage key national constituents vis-à-vis provincial agencies. Yet there is more limited evidence of strong leadership which is willing to push the boundaries, support innovation and challenge the status quo. This may have a limiting effect on the scope and success of parts of the programme. It is expected, however, that other parts of the programme will gain traction and we can move forward with these on a responsive basis. / Challenges of policy influencing: Whilst it is relatively easy to assess the challenges and identify solutions thereof it is more difficult to build the incentives and consensus for reforms in these critical areas. The case for intervening is to support evidence-based policy-making by providing data and analysis, transforming them into evidence and engaging, influencing and stimulating debate among key constituents, both state and non-state. The black box of how such processes work in Vietnam is difficult to open up. In 2004, ODI undertook a study which looked at the policy-making processes around the PRSP. In 2008 Martin Rama, the former Lead Economist at the WB in Vietnam, wrote an influential article explaining the processes which drove Doi Moi, recognising informal and quasi formal channels.[14] But as Vietnam has developed, the picture has become more complex and opaque. Who takes decisions, based on what information and produced by whom is not always evident. The assumption that policy is ever evidence-based, even in Western countries, has been challenged.[15] The impact of formal policy dialogue forums with Government – especially for donors – is difficult to assess. However, the WB is far better placed to tackle these issues in the macroeconomic sphere than a private contractor given track record, trust and ability to manoeuvre. / Space for engagement and debate: VGEMS attempts to encourage other actors to be more engaged in the production, utilisation, dissemination and engagement on policy reform issues across the three areas. This is a sensitive issue in Vietnam where civil society is closely controlled and the media has certain lines it cannot cross in terms of reporting. Citizens also struggle to have access to and influence over the elected officials given the political structure of Vietnam and the formalised routes for accountability. For VGEMS to be successful it has to tread a fine line between encouraging and supporting a challenging debate which questions authority and operates outside the hierarchical structures. However there have been good examples of the permitted space for debate occurring and VGEMS needs to capitalise on this. Critically, externals must be seen (and must be) neutral, use evidence and international experience and avoid the really sensitive areas at least in the open debates. / In conclusion, there are distinct political challenges to working in Vietnam in the way VGEMS seeks to. However, there are champions in Government and outside and there is the political willingness and imperative to address some of the key issues. How successful VGEMS is at opening up the policy debates and influencing the agendas rests on the models that have been adopted and which vary across sector (see boxes 1-5 above). We expect some elements to work straight away and are responding directly to Government demand; we expect others to take longer and will require sensitive and careful political stewardship and astute handling. This therefore manages to spread the risk across the programme (see section below).
C. What are the costs and benefits of each feasible option? / A full Economic Appraisal is attached in Annex 2 / The DFID costs are £ 6.7 and £ 6 million in Options 1 and 2 respectively, and 0 in Option 3. The World Bank is assumed to contribute some of their own resources under all scenarios (around £750k in option 1 and £1 million in option 2 and 3). However, their contribution is likely to be put to more effective use in options 1 and 2, as a DFID contribution will justify employing staff in-country rather than providing analysis and advise from another office. / The expected benefits of the programme are challenging to quantify given that they are driven by the extent to which data, analysis and advice is able to influence policy reforms in Vietnam. In order to quantify the benefits, we need to estimate the feasible impacts of some of the policy reforms and make an assumption regarding the likelihood of such reforms taking place. As such, any estimates are likely to be subject to a high degree of uncertainty. We have approached this by taking a very conservative approach to (i) estimating impacts; and (ii) assuming a small chance of the expected reforms occurring. We have also conducted sensitivity analysis on key assumptions. / The following assumptions have been made: / We have assumed that benefits accrue for four years after the programme ends (i.e. an appraisal period of eight years). This represents a conservative approach, since we may expect benefits from improved data and evidence to accrue further into the future. / GDP is assumed to grow at around 5.6% in the base case. / Public expenditure is expected to grow at a similar rate to economic growth (5.6%) / Costs and benefits are discounted using a discount rate of 10% / Data is taken from various sources including: Vietnam MoF website; Public Expenditure Review 2004; and IMF article IV consultation with Vietnam / The quantified benefits are: / On improved transparency and governance: we have quantified improvements in efficiency of public spend on health, education, transport and electricity. The programme is expected to generate public interest in improving the efficiency with which resources are used (technical efficiency), reducing wastage and improving the quality of local services. Technical efficiency can be estimated as a percentage of existing public service expenditure that might be saved as a result of improvements in the implementation of activities and/or improvements in the quality of services. Such fiscal gains could then be ploughed back into those same activities, generating a proportional increase in the quality/quantity of services being provided. Under both options 1 and 2, we adopted a very modest efficiency savings rate of 1% of public spend in the targeted areas. / On economic management: we have quantified a reduction in the fiscal deficit of between 0.1-1%. This would come from a more stabilised macro-economic condition following a number of reforms in public investment, SOE management, and pricing management (e.g less interference and subsidies from state budget of key products). Under option 1 assume a modest reduction of 0.8% while under option 2, a slightly larger reduction of 1%, given the World Bank’s stronger track record in influencing the Government than that of a private sector agency. / On poverty/social protection: we have quantified the scale of transfers expected from effective implementation of a nationwide cash transfer programme targeted at the poorest 15% of households. However, we have not attempted to monetise the benefits as to do so is particularly challenging, and would require disproportionate effort for a programme of this size. / There are also likely to be further benefits that we have not been able to quantify such as: / Wider benefits from improved macroeconomic stability: these could be substantial and could include reductions in public debt and inflation, potentially leading to increased investment, improvements in productivity and growth. / Better targeting of poverty reduction and social protection programmes is likely to lead to a reduction in poverty rates, particularly amongst ethnic minorities. / Spill-over effects of improved governance into other sectors not targeted by the programme e.g. if demonstrated benefits from improved accountability in target areas encourages the GoV to reduce wastage and make better use of public funds across its other programmes. / Improved public confidence in the economy and government decision making / In the tables below, options 1 and 2 are compared to option 3 (do nothing) which is used as the baseline. Both options 1 & 2 look cost-effective with the estimated benefits outweighing the costs in both cases. Option 2 would appear the most cost-effective of the two options with an NPV of around £17m and a Benefit Cost Ratio (BCR) of 4.1. The inclusion of unquantified benefits would further strengthen the economic case. It should be noted that the NPVs given are indicative only as the quantified impacts do rest on a number of assumptions including growth rates, and the level of gains from the intervention. / Option 1: Multi channel assistance (through the WB and a private sector policy facility). All values given in £’000s. / 2012 2013 2014 2015 2016 2017 2018 2019 2020 Total / Programme costs / Staff costs 659 659 572 572 2463 / Governance package 250 350 300 290 1190 / Poverty Reduction package 525 500 400 200 1625 / Macroeconomic reform package 450 350 325 175 1300 / Management 38 37 32 25 132 / WB contribution (relative to op 3) -63 -63 -63 -63 -250 / Total Costs 1859 1834 1567 1200 0 0 0 0 0 6460 / Discounted costs 1859 1667 1295 901 0 0 0 0 0 5723 / Monetised programme benefits / Efficiency savings 468 980 1661 2512 3318 4206 5183 6258 7437 32023 / Improved fiscal discipline 92 168 232 276 365 462 570 688 818 3670 / Total benefits 559 1148 1893 2789 3682 4668 5753 6946 8255 35693 / Discounted benefits 559 1044 1564 2095 2515 2898 3248 3564 3851 21339 / Summary / NPV costs 5723 / NPV benefits 21339 / Net Present Value 15616 / Benefit Cost Ratio 3.7 / Option 2: Single channel assistance (through the WB) / All values given in £’000s. / 2012 2013 2014 2015 2016 2017 2018 2019 2020 Total / Programme costs / Staff costs 496 496 388 388 1767 / Governance package 250 350 300 290 1190 / Poverty Reduction package 525 500 400 200 1625 / Macroeconomic reform package 450 350 325 175 1300 / Management 34 34 28 21 118 / WB contribution 0 0 0 0 0 / Total Costs 1755 1730 1441 1074 0 0 0 0 0 6000 / Discounted costs 1755 1573 1191 807 0 0 0 0 0 4829 / Monetised programme benefits / Efficiency savings 468 980 1661 2512 3318 4206 5183 6258 7437 32023 / Improved fiscal discipline 118 216 299 355 469 594 733 884 1051 4719 / Total benefits 585 1196 1959 2868 3787 4800 5916 7142 8488 36742 / Discounted benefits 585 1088 1619 2154 2586 2981 3339 3665 3960 21978 / Summary / NPV costs 5325 / NPV benefits 21978 / Net Present Value 16652 / Benefit Cost Ratio 4.1 / Given the above analysis from an economic perspective, option 2 (single channel for all three components through the World Bank) emerges as the preferred option. This is supported by analysis from an intuitional perspective which considers the WB to be best placed to deliver on all three agendas and naturally complements DFID’s other programmes in these areas (e.g. on anti-corruption, support to the One UN, Vietnam Private sector challenge fund). It is also important in terms of DFID’s legacy in Vietnam, as it will leave the WB well-positioned to carry on focussing on the toughest and most fundamental development challenges Vietnam faces. One aspect considered critical for the success of the programme is sustainability. Importantly, sustainability has been built into the programme in three ways: / (i) VGEMS will increasing work with long term local partners in key areas (e.g. VTP with local network, VKP with local academic think tanks, cash transfer programme with MOLISA) to anchor its work domestically; / (ii) VGEMS will increasingly share the staff costs with the World Bank, with fixed costs from VGEMS covering 80% in 2012-13 and 60% 2014-15 of international support. By the end of the programme, the World Bank will be in a position to absorb 100% of staff costs. / (iii) VGEMS will maximise synergies with other programmes, including those supported by other trust funds. This will mean staff time can be charged to other TFs, reducing the direct costs for VGEMS and freeing up variable budget for VGEMS activity. / These mark VGEMS as a significant step forward from GAPAP in terms of cost-sharing and place the WB in a strong position to continue work in these areas after the trust fund closes in March 2016.
D. What measures can be used to assess Value for Money for the intervention? / The economic appraisal looks at a number of measures to assess value for money, such as net present value and benefit cost ratio. The appraisal uses a number of financial proxies to value the expected benefits. We will monitor the outcomes and impacts, and analysis to verify the benefits and the value for money indicators claimed in the economic appraisal at Mid-Term Review and selected evaluations planned for the programme. / We will adopt a number of other measures including: / Require the World Bank to monitor unit costs, for example of conducting workshops, and mobilizing consultants for a policy note or a certain piece of analysis as set out under value for money through procurement in the Commercial Case below. / Work with the World Bank to prioritise capacity building for local partners in programme activities in order to sustain results beyond the life of the programme. / Develop weights to attach to the more challenging but rewarding areas of intervention, e.g. ethnic minority poverty/livelihoods, to adjust for the importance DFID attaches to the pro-poor and gender agendas.
E. Summary Value for Money Statement for the preferred option / This appraisal uses available evidence and conservative assumptions to estimate the expected costs and benefits of the proposed programme. The analysis suggests that the programme is likely to offer value for money. On the basis of the analysis, the preferred option is Option 2: single channel assistance to the GoV on areas of improved transparency and governance, economic reform and poverty and social protection, delivered through a World Bank managed Trust Fund. Under this option, taking account of monetised costs and benefits, the Net Present Value is positive (~£17m) and the benefit cost ratio is 4.1 under the central (most likely) scenario.
[14] See Martin Rama, Making Difficult Choices: Vietnam in Transition (2008)

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The intervention only involves indirect procurement. DFID Funding will be transferred to the World Bank via an Administrative Arrangement with World Bank Vietnam. / Sections B, C, D and E are therefore irrelevant.
B. How does the intervention design use competition to drive commercial advantage for DFID?
C. How do we expect the market place will respond to this opportunity?
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
E. What is the intended Procurement Process to support contract award?
F. How will contract & supplier performance be managed through the life of the intervention?

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The Multilateral Aid Review confirmed that the World Bank is one of the nine organisations which have offered very good value for money for UK aid funding. Globally, it has ‘’strong and mostly transparent financial management’’, ‘’adequate cost control systems to ensure costs do not inflate’’ and the ability to ‘’ demonstrate some efficiency improvements’’. [16] DFID and the World Bank in Vietnam have a strong strategic partnership relationship, especially in supporting policy making. / This funding mechanism via World Bank will therefore make the best use of the VFM offered by the Bank and bilateral strategic relationship, help leverage the World Bank’s expertise, and leave a good legacy for World Bank to stay engaged after DFID graduation from Vietnam in 2016. / There is a standard Administrative Arrangement between DFID and the World Bank which will be used to formalize DFID commitment under this intervention.
B. Value for money through procurement / A quick interview with World Bank Vietnam colleagues based on the TPO questionnaire was carried out to assess VFM through procurement. As designed, VGEMS will operate under a Bank Executed Trust Fund with 100% of procurement carried out by World Bank Vietnam. Support to the EMCC programme will be carried out directly by VGEMS in agreement with the WB and other financiers and will not use the multi-donor channel proposed. / On Economy, procurement conducted by World Bank Vietnam will be on a competitive bidding basis both internationally and domestically, based on the value of the service. Calls for proposal will be posted both on World Bank website and high profile domestic/ international recruitment channels to get access to the high quality pool of suppliers. Bidding time will be set long enough for suppliers to get access to calls and prepare bids. World Bank Vietnam has a system to collect updated market data on unit costs for different services, which ensures the commercial advantage and good VFM of the intervention. Poor performing suppliers will be kept track for future dealing. / Between DFID and World Bank Vietnam, a VFM management charge will be negotiated, based on DFID’s Oct 2009 HTN on World Bank Trust Funds and the prevailing World Bank Trust Fund Fees Guidance by IFID. The issue will be consulted with IFID as appropriate. The 2% management fee used in the economic appraisal is tentatively set for the VFM calculation purpose only. / On Efficiency, one professional procurement staff from World Bank Vietnam will be in charge of procuring services for VGEMS, in coordination with the Trust Fund Manager and following World Bank’s global standardized procurement rule and guidance. The procurement plan will be based on the Annual Work Plan, covering monthly registrars of procurement activities. It will be annually reviewed under procurement supervision missions. Areas such as progress of the plan, compliance and VFM will be looked at. Besides, there will be a division of labour between the Trust Fund Manager and the procurement staff to monitor and facilitate the progress under individual contracts so that the inputs are well converted into the desired outputs. Payments will be made by results and there will be contract terms and conditions to deal with poor performing suppliers. / On Effectiveness, DFID Team Leader of the Governance and Social Development Team, and World Bank Trust Fund Manager, will ensure that procurement activities complement and effectively support the achievement of the outcome. Any delays or poor performance with potential adverse impacts on such achievement will be discussed and solved in the right timing. / On a broader picture, to improve further the VFM offered by WB, DFID Vietnam will continue to work with the WB and other partners to move ahead the remainder IDA 16, IDA 17 and the Multilateral Aid review VFM agendas, contributing from the country perspective. Our engagement will be based on the recommendations in the March 2012 ICAI report on the Effectiveness of DFID’s engagement with the World Bank, and key findings in the February 2011 Multilateral Aid Reviews.
[16] ‘’Multilateral Aid Review: Assessment of the International Development Association’’, Feb 2011 and ‘’Multilateral Aid Review, Taking Forward the findings of the UK Multilateral Aid Reviews’’, Mar 2011.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Below is the budget based on focus areas: / Unit: £’000s. / Item 2012/13 2013/14 2014/15 2015/16 Total / Governance 454.6 604.6 511.2 451.2 2021.6 / Economic Management 511.8 461.8 290.1 240.1 1503.8 / Poverty/social protection 729.6 704.6 493.2 261.2 2188.6 / Management (5%) 85 89 65 48 286 / Total 1781 1860 1359 1000 6000 / Staff costs are embedded into each focus area budget line, and are outlined as follows: / International: 1 Senior Governance specialist, 1 Senior Poverty Economist, 0.5 Senior Macro economists. / Local: 1 Governance specialist, 1 Poverty Economist. / VGEMS will pay for 80% of the international staff in years 1 and 2, and 60% in years 3 and 4. It will pay 100% of local staff costs for the four years. The actual WB contribution is likely to be far higher given use of existing staff (hence VGEMS’ leverage) and increase in percentage of VGEMS staff funded directly. / Trust fund structure for profiling funds / The World Bank will establish 5 theme-based child trust funds under VGEMS for the following components: governance, VKP, poverty analysis, social protection and EMCC as set out in figure 1 below. In addition funds will be allocated to undertake preparatory work, regular monitoring of activities and impact evaluation. All activities at the child fund level will follow Bank’s policies and procedures on quality assurance. The flexible framework of the TF would allow for scaling-up existing activities or to initiate new ones depending on resource availability and demand.These will ensure a smooth forecasting and financial distribution. Shifting resources between funds and annual allocation will be based on the Annual Work Plan and done with agreement of DFID and the WB during quarterly meetings: / Figure 1: Financial structure of the VGEMS child trust funds / There is sufficient budget for M&E with a separate fund. The World Bank will set aside £250,000 including lesson learning for the programme as a whole and for individual activities within it.
B. How will it be funded: capital/programme/admin? / Funding will come from DFID Vietnam programme budget.
C. How will funds be paid out? / DFID Vietnam will sign an Administrative Arrangement with the World Bank. Funds will be paid to the World Bank Trust Fund account set up for the intervention. Payments are subject to the work plan/ budget for the next period, quality of time bound deliverables and the actual, up-to-date disbursement. The schedule of payment will be subject to the agreement with FCPD, in consultation with the WB with regards to funding needs. This is to ensure VFM and that funds are not transferred in advance of need.
D. What is the assessment of financial risk and fraud? / The financial/ fraud risk is Low, given Global World Bank ‘s ‘’strong and mostly transparent’’ financial management[17], and World Bank Vietnam’s reputation for strong financial and risk management. The Evaluation of World Bank’s Trust Fund Portfolio ‘’encountered no reported instance of financial mismanagement either in the country studies or the random sample’’ (Trust Fund Support for Development, May 2011). / Alongside its tight fiduciary control framework, the Bank has introduced three measures to assure staff compliance with fiduciary rules i.e. Trust Fund Quality Assurance and Compliance Unit, Accreditation (of staff who manage trust funds) and Letter of representation. / In practical terms, the Bank will maintain separate records and ledger accounts in respect of DFID funding. Financial information relating to the Trust Fund is disclosed and can be tracked at any time using World Bank Client Connection portal. There is an annual management assertion and attestation by the Bank’s external auditors available by every December. There is so far no need for external audits. / Main safeguards are / Payments made by results and not to be made in advance of needs; / Spending of the project being checked regularly using World Bank Client Connection website and reconciled with the implementation of project activities where appropriate; / Annual management assertion and the attestation by the Bank’s external auditors to be timely obtained; / DFID staff to raise and discuss with World Bank colleagues financial/ implementation issues at quarterly review meetings and as appropriate.
E. How will expenditure be monitored, reported, and accounted for? / Expenditures will be monitored via ARIES system and World Bank Client Connection portal. There will be no asset procured under this intervention. / World Bank will make available to DFID (i) current financial information relating to receipts, disbursements and fund balance via World Bank Client Connection portal; (ii) ‘’Single Audit report’’ or the annual management assertion together with annual attestation from the Bank’s external auditors on the adequacy of internal control over cash-based financial reporting for trust funds as a whole.
[17] ‘’Multilateral Aid Review: Assessment of the International Development Association’’, February 2011

Management Case

A. What are the Management Arrangements for implementing the intervention? / The management arrangements for the Trust Fund are relatively simple. They are based on some important principles which are built into the management arrangements. These have been refined as we are experienced in working with the WB as a partner. / WB Programme Management / The World Bank led by the Lead Economist in PREM will be Trust Fund manager responsible for the programme management and oversight. He will coordinate internally within the WB the separate teams and individuals who deliver on various aspects of Programme Management Governance. Whilst this is primarily WB internal organisation, it is envisaged that this will consist of three teams: / Transparency and accountability team, consisting of one national and one international Governance Specialist / Poverty and social protection team, consisting of one national and one international Poverty economists and one national and one international HD economists jointly led by Senior Poverty economist, and Senior HD economist. This team cuts across both PREM and HD inside the WB and will need a heightened level of coordination to maximise the impact of the VGEMS inputs. / Economic management team, led by Lead Economist, and comprised of two international and several national economists located in Hanoi office and part time involvement of some of the international economists from WB's headquarter. This team will also contribute assistance to the EMCC programme with analytic support to one trigger per year. / DFID Management / The programme will be led on the DFID side for the initial 12 months of the programme by the Team Leader Governance and Social Development. After the first year, the responsibility for the project will pass to the Deputy Head of DFID Vietnam. The reasons for this are to ensure consistency in support from the technical level and ensure we maximise the potential for the VGEMS vehicle for policy dialogue for DFID. The support, dialogue and advice from the technical side will come from four areas: / Governance Adviser / Social Development Adviser / Economic Adviser and Prosperity Team leader / Evaluation Adviser (5%). / Each adviser will include 20% time allocation to engage with the World Bank, provide inputs, advice and direction as required (with exception of EvA). This may include contributing to / leading analytical work as appropriate. / How we will work together / VGEMS will adopt a light touch management structure based on core principles. This is linked to the M&E work. It will work in the following way: / Annual VGEMS meeting. This is for direction setting and stock-taking. This will be attended by DFID Head and WB Country Director and serve as an opportunity to share, disseminate and check on overall progress. It will not serve as a review meeting. / Quarterly VGEMS meeting. This will be coordinated jointly by DFID and the WB. It will serve as a review mechanism for Annual Work Plans and be the recipient of Annual reports. This will include the whole team working on VGEMS from both DFID and WB and will assist with making sure lessons are shared etc. / Monthly technical meetings. We expect that the technical staff form both DFID and WB will meet on a monthly basis to discuss technical / implementation issues. This will be on an ad hoc basis and led by both sides. / Review/quality assurance/policy dialogue meetings. Relevant DFID staff will be invited and will attend key meetings on work funded (partially or wholly) by VGEMS. This is a critical condition for DFID to ensure that we maximise our impact by ensuring we engage on the policy-dialogue level. / Planning and reporting structure / The objective is to have an effective but streamlined planning and reporting cycle, recognising the flexible nature of VGEMS and the importance built into the programme of effective on-going close working. / An Annual Work Plan will be prepared by the WB team in May/June for each WB financial year. This will be discussed and agreed with the DFID team at the quarterly meeting. This will be prepared against the logframe and be fully costed. / An Annual Report will be prepared by the WB team by August each f/y. This will be against the previous AWP and against the logframe. / DFID will prepare an Annual Review based on the report, other meetings/evidence as appropriate. / There will be no formal quarterly reports. However, DFID and the WB may agree to have specific updates on a quarterly basis on particular issues which will be mutually agreed upon. / If the formal requirements are deemed to provide insufficient detail or there is a distance between the WB and the DFID team, we will look to revise the management arrangements in order that we ensure good value for money and maximum impact. / How DFID will engage with EMCC? / Given that DFID will contribute to analytic work under EMCC, it is expected that DFID Economist or other delegated leads will play an active role in each EMCC cycle. This includes i) advising the DFID team on priority policy actions; ii) participating in EMCC Technical Working Committee for policy dialogue with the World Bank, other development partners and Government, and iii) providing inputs/support to relevant analytical work and capacity building activities for Government counterparts. / Prior agreement will be reached with the WB Task team Leader for EMCC as to the best use of DFID’s resources for each trigger, in consultation with the GoV and other funding partners. This will avoid duplication and ensure well-targetted support in line with DFID/VGEMS priority areas.
B. What are the risks and how these will be managed? / The key risks are the following: / Risk Mitigation Probability Impact / Vietnam’s macro economic stability is not maintained resulting in reverses in poverty reduction Intense policy dialogue / Policy notes to influence direction / Knowledge platform to help introduce international expertise Medium High / GoV not receptive to policy dialogue and close down innovative angles promoted by VGEMS Engage in wide range of stakeholders to encourage messages through a variety of channels. / Ensure GoV ownership of new innovations by securing a safe home and supportive champion. Medium High / Key VGEMS staff not secured to be in-country on time/ leave prior to end of contract Start procurement early / Ensure sustainability built into approach and gradual shift to WB funding. Medium Medium / Break down in communication between WB and DFID on key technical areas clear expectations established at outset / Adherent to management plan and open dialogue / Securing key staff on DFID side until end of programme Low Medium
C. What conditions apply (for financial aid only)? / NA
D. How will progress and results be monitored, measured and evaluated? / Evidence weak or strong? The programme will work with both government policy makers to provide reform advice and non-government actors such as researchers and the media to create broad consensus and pressure for change. There is medium evidence of the effectiveness of this approach. The programme will gather more evidence across the three areas: governance, economics and social inclusion/poverty. / What will be monitored and how? The programme Log Frame is the main monitoring tool. Based on the Theory of Change and Log Frame, the World Bank will develop and agree with DFID a more detail Monitoring and Evaluation framework six months into programme implementation. This will be aligned to the Annual Work Plan to ensure consistency. DFID will consult with its Evaluation Department to ensure the framework is robust. Tools that will be used will include logs of the following, and possibly others if appropriate: / Activities (research/policy pieces, advocacy events) / Media (citing programme products/activities) / Uptake (evidence of use of research and advice from the programme) / Reporting: The above sources of information and other more independent sources (outlined under Data below) will feed into the following reporting: / WB annual reports to DFID / DFID Annual Reviews and Project Completion Report / Mid-term review after two years of implementation to take stock of progress against the various output, outcome and impact indicators set out in the Log Frame. / Evaluation: There will be independent evaluations in selected areas of programme interventions on their policy impact, effectiveness, and sustainability. The following themes/activities may be subjects for evaluations: / Evaluation of effectiveness of: the social piloting a social accountability experiment in selected provinces, the pilot a new social assistance programme (which will be useful in considering scaling up); support to the revision of the Social Assistance Law and the Vietnam Knowledge Platform (VKP). / Evaluation of policy influencing impact: on policy notes and analysis on macro policy and fiscal management; / Evaluation of scalability and cost effectiveness of some of the media-based innovative methods for advocacy. / The evaluations will combine qualitative and quantitative methods. Data collection for them will include log and document analysis, panels of experts, focus group discussion, structured questionnaires/surveys of beneficiaries and key stakeholders, semi-structure interviews and case studies. / There will also be a lessons learning study at the end of the programme to document lessons from the programme overall approach. / Data for monitoring and evaluation: Apart from the programme generated data outlined above, other sources of data will be used as follows: / Government’s annual reports to the Consultative Group meeting on macro-economic situation, public financial management progress, poverty reduction, and governance progress (transparency, anti-corruption, accountability) / International Monetary Fund’s annual Article 4 Consultation Report (available on IMF website) / World Bank bi-annual Taking Stock (of the economy) / Other thematic reports (e.g. World Bank Vietnam Development Report, poverty analysis by Vietnam Academy of Social Sciences) / Vietnam Household Living Standard Survey (VHLSS – available every two years) / Baseline data exist on all (except one) indicators in the Log Frame. The missing data will be filled in the first year of implementation. / Resources for monitoring and evaluation: Sufficient capacity for monitoring and evaluation will be established. The World Bank will set aside £250,000 for monitoring and evaluation activities including lessons learning. This is included within the overall programme budget. The DFID Lead and the Senior Economist responsible for VGEMS will mutually agree on the use of these funds and it will be a standing item in the quarterly meetings.
Lograme / Quest No of logframe for this intervention: