## Goal Purpose Outputs
PROJECT NAME | Consolidating Science Journalism in Africa and the Arab World: SjCOOP-II
GOAL | Indicator | Baseline | Milestone 1: September 2011 | Milestone 2: March 2012 | Target (October 2012)
Poverty reduction through better science reporting in Africa and the Arab World. | Collection of cases which show how the reporting of SjCOOP participants contributed to the change of policies or regulations and/or to steps that lead toward daily life quality improvement. | 10 cases in SjCOOP-I, documented by the project team. | 13 cases, documented and analysed by communication scientists. | 16 cases, documented and analysed by communication scientists. | 20 cases, documented and analysed by communication scientists.
Comments November 2010
|  |  | On schedule | On schedule | On schedule
Source
Baseline: SjCOOP I final report. Milestones: For the new SjCOOP-II cases a special research effort will be made to understand the societal processes that led to change. A team of communication scientists will develop a specific method to study the impact of the targeted reporting activities of the mentees.
| Indicator | Baseline | Milestone 1 | Milestone 2 | Target (date)
Source
PURPOSE | Indicator | Baseline | Milestone 1: November 2010 | Milestone 2: November 2011 | Target (August 2012) | Assumptions
Quality science reporting and expertise informing public debates | Analysis of structural setting/working conditions/landscape of science journalism shows increased opportunities for science journalism in the media the mentees work for. | high: 7 | high: 7 | high: 8 | high: 9 | established and performing media in Africa and the Middle-East. Advertisers not stopping critical stories through their influence
|  | Medium:18 | Medium:18 | Medium: 19 | Medium: 20
|  | Deficient: 15 | Deficient: 15 | Deficient: 13 | Deficient: 11
Source
Baseline: measured by November 2010 (based on interviews with editors, i.e. the mentee's bosses.) At the milestones these interviews with the editors/bosses will be done again, to see if any change is happening. The distinction between "high", "medium" and "low" opportunities for science journalism will be made on the basis of aggregation of some key variables collected in the interviews with the editors: e.g. space given to health and science pages or stories, the number of full-time editors in health, environment, science.
| Indicator | Baseline: | Milestone 1: July 2011 |  | Target (August 2012)
| Improvement in the quality of reporting on health, environment and science, shown by content analysis of the journalist's (mentee's) articles. | High: 15% of the journalists in the SjCOOP-network (mentees) write very good articles. | High: 17% |  | High: 25%
|  | Medium: 39% of the journalists in the SjCOOP-network (mentees) write acceptable articles. | Medium: 43% |  | Medium: 60%
|  | Deficient: 46% of the journalists in the SjCOOP-network (mentees) do not write acceptable articles. | Deficient: 40% |  | Deficient: 15%
Source
Baseline: SjCOOP I report: Science journalists (that were not involved in the project) rated the quality of the mentee's articles by different criteria set by the project team. Milestones: In SjCOOP-II a team of communications scientists will do a very robust and detailled content analysis of the mentee's articles based on general journalistic quality criteria the mentors have developed and agreed upon as a basis. Also the Online Course in Science Journalism developed in SjCOOP-I will serve as a source for those quality criteria.
INPUTS (£) | DFID (£) | IDRC (£) | Other (£) | Total (£) | DFID SHARE (%) see note 1
| 1,9 M£ | 360,080$ = 242,000£ | 677,890$= 455,000£ | 2,597,000 £ | 73.16%
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Indicator | Baseline | Milestone 1: July 2010 | Milestone 2: October 2011 | Target (August 2012) | Assumption
Fully trained body of science journalism trainers/mentors | Professional level of mentors. | 0 mentors (no mentor's contracts at the onset of the project.) | 5 mentors hired (among all 15 mentors) who have mentoring experience from SjCOOP-I or other special training experience. | 12 mentors have proved that they do a good job as mentors in SjCOOP-II. | 15 mentors (all mentors) will have proved their proficiency by the end of the project. | sufficent number of experienced science journalists who can dedicate the time for mentoring and travel for the meetings; mentors able to stay in touch with mentees over the full period: Electricity, Mobile Phones, Internet available.
Source
mentor's applications and CVs, regional coordinator's reports, mentor's reports, mentee's feedback (interviews or questionaires).
|  | Baseline | Milestone 1: October 2011 | Milestone 2: March 2012 | Target (August 2012)
| Coordinators and Mentors supporting targeted research activities. | 0 mentors actively involved. | 2 mentors and 2 coordinators actively involved in supporting their mentees in targeted reporting activities. (These activities go beyond the ordinary training and consulting the mentors offer at the onset of the project.) | 5 mentors + 3 coordinators actively involved in supporting their mentees in targeted reporting activities. | 7 mentors and 3 coordinators actively involved in supporting their mentees in targeted reporting activities.
Source
Coordinators reports, interviews with mentees, documentation of targeted reporting activities (in-depth journalistic research, journalistic research in transnational teams, investigative research or other journalistic activity that is aiming at changing policy or influencing public debate).
IMPACT WEIGHTING | Indicator | Baseline | Milestone 1 | Milestone 2 | Target (August 2012)
45% (in 2010)
|  | Source |  |  |  | RISK RATING
High
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Indicator | Baseline | Milestone 1: July 2011 | Milestone 2: January 2012 | Target (August 2012) | Assumptions
Increased capability in science journalism | Analysis of journalists-scientist interactions show that journalists (SjCOOP-II-mentees) are recognized as professionals by scientists. | 0 (no interactions) | 10% of all SjCOOP-II-mentees are judged positively by scientists - after having interviewed the scientist for an article/broadcast. | 20% of all SjCOOP-II-mentees are judged positively by scientists - after having interviewed the scientist for an article/broadcast. | 30% of all SjCOOP-II-mentees are judged positively by scientists - after having interviewed the scientist for an article/broadcast. | journalists able to use IT tools and be in touch with their mentors through internet; jounalists who are supported by their editors and bosses; journalists staying in journalism;media outlets continue to exist; relevant journalistic awards exist and can be won; journalists able to travel without problems (visas...)
Source
Data collected by phone calls to scientists after they have been interviewed by the mentees (journalists). In these phone-calls (evaluation-interviews) the scientists will be asked for their judgement on the mentee's behaviour and proficiency as a journalists.
| Indicator | Baseline | Milestone 1: September 2010 | Milestone 2: September 2011 | Target (August 2012)
| Analysis of achievements of mentees as working journalists (awards won, career steps made, new media outlets freelanced for, new areas in science journalism covered, writing skills improved) shows an increasing level of journalistic proficiency in the SjCOOP-network. | High: 11 journalists (11 SjCOOP I mentees) have achieved a high level of proficiency. | high: 21 journalists (11 SjCOOP I mentees + 10 SjCOOP II mentees) | High: 22 journalists (11 SjCOOP I mentees + 11 SjCOOP II mentees) | High: 32 journalists (11 SjCOOP I mentees + 21 SjCOOP II mentees)
|  | Medium: 13 (SjCOOP I mentees) journalists have achieved a medium level of proficiency. | Medium: 24 journalists (13 SjCOOP I mentees + 11 SjCOOP II mentees) | Medium:35 journalists (13 SjCOOP I mentees + 22 SjCOOP II mentees) | Medium: 45 journalists (13 SjCOOP I mentees + 32 SjCOOP II mentees)
|  | Deficient: 36 (SjCOOP I mentees) journalists have a low level of proficiency. | Deficient: 84 journalists (36 SjCOOP I mentees + 48 SjCOOP II mentees) | Deficient: 63 journalists (36 SjCOOP I mentees + 27 SjCOOP II mentees) | Deficient: 43 journalists (36 SjCOOP I mentees + 7 SjCOOP II mentees)
Source:
Baseline: SjCOOP I final report,The information used as a baseline is one of the SjCOOP phase I results Milestones: mentor's reports, questionaires/interviews with mentees. For the ratings - High, Medium, Deficient - an aggregated variable will be used that will contain the following data: number of mentees that have won awards, number of mentees that have made a career step, number of mentees who publish in outlets that are new to them (free lance work), writing skills assessed by mentors, and the number of mentees that have started to cover areas in science that are new to them. All these factors will be weighed and added up in order to then judge wether the professional level of a mentee is high, medium or low.
IMPACT WEIGHTING | Indicator | Baseline | Milestone 1 | Milestone 2 | Target (August 2012)
20% (in 2010) |  |  |  |  | 50%
|  | Source |  |  |  | RISK RATING
High
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Indicator | Baseline | Milestone 1: September 2010 | Milestone 2: September 2011 | Target (October 2012) | Assumptions
capacity built in national and regional associations of science journalists to manage local and regional trainings in science journalism | Associations with a charter, elected board and regular meetings | 7 new associations in Africa and the Middle East have been set up during SjCOOP-I. To become members of the World Federation of Science Journalists (WFSJ) these associations had to fulfil a number of criteria, e.g. have a charter, elected board, etc. | 8 associations: we expect to see one more association being set up. | 9 associations: we expect to see 2 more association being set up. | 10 associations: we expect to see 3 more association being set up. | legal national framework enabling associations to be established; journalists willing to learn how to manage their own activities; leadership of journalists in charge of the associations ; associations of science writers continuously supported by their members and other stakeholders who are not participating or directly benefitting from SjCOOP
Source
Baseline: SjCOOP One Final Report Milestones: interviews / association reports
| Indicator | Baseline | Milestone 1: December 2011 | Milestone 2: June 2011 | Target (September 2012)
| Associations with a range of dedicated activities | 0 associations | 2 associations | 3 associations | 4 associations
Source
Baseline: None of the associations have dedicated staff or regular activities Milestones: interviews with association representatives / association reports
IMPACT WEIGHTING | Indicator | Baseline | Milestone 1 | Milestone 2 | Target (April 2012)
20% (in 2010) |  |  |  |  | 20%
|  | Source |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Indicator | Baseline | Milestone 1: April 2012 |  | Target (November 2012) | Assumptions
evaluation methodology for quality of science journalism and impact stories | (Scholarly) Peer-reviewed publications produced | no (scholarly) peer-reviewed publications so far | 1 (scholarly) peer-reviewed publication submitted |  | 2 (scholarly) peer-reviewed publications submitted | stable socio-plolitical conditions; scientists willing to collaborate with journalists;experts willing to help follow and document the impact-stories step by step; policy advicers and policy makers accessible and willing to respond to our evaluation interviews; journal publication lead in times allow publications within project timeframe
Source
Specialized, peer-reviewed journals with a good reputation in the scientific community, e.g. "Journal of African Media Studies" or "Science Communication". We will decide on where to best submit according to the findings of our research.
Comments November 2010
|  |  | On schedule | On schedule | On schedule
| Indicator | Baseline | Milestone 1: September 2011 |  | Target (November 2012)
| Conference talks on SjCOOP evaluation methodology | 1 conference talk given | 2 conference talks given |  | 3 conference talks given
Source
Conference programmes/proceedings. We aim to present and discuss our methodology at major international conferences on evaluation, journalism education, mass communication research and/or science communication. The baseline is a first conference-talk we held on SjCOOP-I-evaluations in 2007 in a specialized international conference ("Measuring Change - Planning, Monitoring and Evaluation in Media Development" (with proceedings) in Bad Honnef, Germany.
IMPACT WEIGHTING | Indicator | Baseline | Milestone 1 | Milestone 2 | Target (November 2012)
15% (in 2010) |  |  |  |  | 10%
|  | Source |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Notes
1-The budget of the SjCOOP project is in Candian dollars and the amounts funded by the other donors are calculated with the rates May 13, 2010

## Activities
Activities Log
OUTPUT 1 | ACTIVITY 1.1 | Milestone 1: February 2010 | Milestone 2: March 2010 | Milestone 3: July 2010 | Risks | Monitoring Officer
Fully trained body of Science Journalism trainers/mentors | Recruit 15 mentors (8 Males and 7 females) motivated to become science journalists trainers | SjCOOP advertised to recruit mentors | Mentors recruited | Mentors trained and contracts signed | Lack of qualified journalists who apply to become mentors; lack of women interested to participate to the program | Olfa Labassi and Jan Lublinski
| ACTIVITY 1.2 | Milestone 1: July 2010 | Milestone 2: November 2011 | Milestone 3: August 2012 |  | Monitoring Officer
| Train 15 mentors in investigative science reporting aimed at impacting policy | Mentors trained | Mentors succeed first evaluation | Final report on Mentors progress | Mentors not interested to report with the aim of impacting policy regionally | Olfa Labassi and Jan Lublinski
| ACTIVITY 1.3 | Milestone 1: September 2010 | Milestone 2: June 2011 | Milestone 3: January 2012 |  | Monitoring Officer
| Train 15 mentors in six key health, environment and scientific issues | Mentors introduced to key health, environment, and science issues | Mentors trained in key health, environment, and science issues | Mentors support their mentees to report in key health, environment, and science issues | Mentors not interested in persuing the six scientific issues targeted | Olfa Labassi and Jan Lublinski
| ACTIVITY 1.4 | Milestone 1: September 2011 | Milestone 2: June 2012 | Milestone 3: August 2012 |  | Monitoring Officer
| Evaluate mentors implication during the investigative and transborder stories | Mentors first evaluation: after the first series of investigative stories | Mentors second evaluation: after the first series of transborder stories and the internships | Mentors final evaluation: after the last series of transborder stories | Mentors not willing to invest enough time for the investigative and transborder stories | Olfa Labassi and Jan Lublinski
| ACTIVITY 1.5 | Milestone 1: September 2010 | Milestone 2: January 2012 | Milestone 3: December 2012 |  | Monitoring Officer
| Analyse gender aspect of science journalists: disagregate data (male/female) on mentees and mentors, ask gender-sensitive questions in forms and interviews concerning mentoring relationships, also: gender aspect in the everyday working condition of participants. | first data aquisition during the regional workshop, analysis of data | second data auqisition during the regional workshop, analysis of data | report : by the end of the project | Mentees/mentors not willing to participate actively in this kind of discussion | Olfa Labassi and Jan Lublinski
| ACTIVITY 1.6 | Milestone 1: June 2011 | Milestone 2: January 2012 | Milestone 3: August 2012 |  | Monitoring Officer
| Provide leadership training to mentors and coordinators | coordinators and Mentors trained during the World Conference meeting (Doha) | Coordinators and Mentors first evaluation: after the second series of regional meetings | Coordinators and Mentors last evaluation: after the second face-to-face meeting | Coordinators and Mentors not interrested in leadership training | Olfa Labassi and Jan Lublinski
OUTPUT 2 | ACTIVITY 2.1 | Milestone 1: March 2010 | Milestone 2: June 2010 | Milestone 3: February 2011 | Risks | Monitoring Officer
Increased capability in science journalism | Recruit 60 journalists motivated to learn the skills of reporting science | SjCOOP advertised to recruit mentees | Mentees confirmed and invited to regional workshops | Mentees replaced or reconfirmed after evaluation | Lack of commitment of the journalists | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.2 | Milestone 1: September 2010 | Milestone 2: January 2011 | Milestone 3 |  | Monitoring Officer
| Tutor 60 African and Arab journalists in the skills of science journalism | Tutoring in science journalism begins | Tutoring in science journalism ends |  | relationship problems between mentors and mentees; cultural problems of mentors from rich countries | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.3 | Milestone 1: June 2011 | Milestone 2: November 2011 | December January 2012 |  | Monitoring Officer
| Train 60 journalists in investigative science reporting aimed at impacting policy | Training begins | Mentees evaluated | Mentees' skills in investigative reporting evaluated | Low absorptive capacity of journalists to effectively and efficiently understand the concepts and implement it | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.4 | Milestone 1:September 2010 | Milestone 2: June 2011 | Milestone 3: November 2011 |  | Monitoring Officer
| Train 60 journalists in six key health, environment and scientific issues | Mentees introduced to key health, environment, and science issues | Mentees trained in key health, environment, and science issues | Mentees report on key health, environment, and science issues | Journalists not interested in the six scientific issues targeted | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.5 | Milestone 1: June 2011 | Milestone 2: September 2011 | Milestone 3: May 2012 |  | Monitoring Officer
| Establish 15 teams of journalists to do investigative science reporting with the aim of impacting policy at national and regional level | Teams and 'reporter/expert' coalitions established | Series of local 'agenda setting' stories published | Series of regional agenda setting' stories published | Journalists not willing to work as teams, Journalists not interested to report with the aim of impacting policy, editors or media-bosses not supporting publications | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.6 | Milestone 1: September 2010 | Milestone 2:June 2011 | Milestone 3: September 2012 |  | Monitoring Officer
| Collect Data about professional level of mentees | Interviews during the first regional meetings | Interviews during the first face to face meeting | final interviews | Mentees not attending meetings (visa problems,etc.); lack of qualified external evaluators; Mentees not providing correct information | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.7 | Milestone 1: October 2010 | Milestone 2: July 2011 | Milestone 3: October 2012 |  | Monitoring Officer
| Mesure amount of reporting about science | First Mentors reports due directly after first regional meeting | Mentors reports due directly after first face-to-face meeting | Mentors reports due directly after second face-to-face meeting | Mentees not providing information to mentors; mentors not submitting their reports on time, lack of capacity to attempt to impact policy | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.8 | Milestone 1: September 2010 | Milestone 2: June 2011 | Milestone 3: December 2012 |  | Monitoring Officer
| Analyse gender aspect of science journalists: disagregate data (male/female) on mentees and mentors, ask gender-sensitive questions in forms and interviews concerning mentoring relationships, also: gender aspect in the everyday working conditions of participants. | first data aquisition during the regional workshop, analysis of data | second data aquisition during the face-to-face meeting, analysis of data | report: by the end of the project | Mentees/mentors not willing to participate actively in this kind of discussion | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.9 | Milestone 1: June 2011 | Milestone 2: January 2012 | Milestone 3: September 2012 |  | Monitoring Officer
| Keep in touch with former journalists involved in SjCOOP (insure they still involved in the WFSJ's network) | first data aquisition and analysis | second data aquisition and analysis | report: by the end of the project | Former Mentees and mentors who did not graduated or were not choosen to participate to this phase not willing to participate actively | Olfa Labassi and Jan Lublinski
| ACTIVITY 2.10 | Milestone 1: April 2011 | Milestone 2: December 2011 | Milestone 3: September 2012 |  | Monitoring Officer
| Monitoring of the Private website | first data aquisition and analysis | second data aquisition and analysis | report: by the end of the project | Mentees not interested to participate to the private website | Olfa Labassi and Jan Lublinski
OUTPUT 3 | ACTIVITY 3.1 | Milestone 1: September 2010 | Milestone 2: September 2011 | Milestone 3: October 2012 | Risks | Monitoring Officer
capacity built in national and regional associations of science journalists to manage local and regional trainings in science journalism | Train 75 journalists in the establishment and management of associations of science journalists | Mentees, Mentors and Staff of Associations hold regional meetings | Nine associations have charter, board and regular meetings | Ten associations have charter, board and regular meetings | Journalists not interested to establish associations of Science journalists, Journalists not interested to manage associations of Science journalists | Olfa Labassi and Jan Lublinski
| ACTIVITY 3.2 | Milestone 1: September 2010 | Milestone 2: June 2011 | Milestone 3: December 2012 |  | Monitoring Officer
| Analyse gender aspect in national and regional associations: disagregate data on members and board members of associations, ask gender-sensitive questions in the interviews with associations members: on the situation of female and male science journalists in the association as well as in the country/region. | First data aquisition at the face-to-face meeting | data aquisition at face-to-face meetings | Last data aquisition at the face-to-face meeting | Journalists not willing to participate actively in this kind of discussion | Olfa Labassi and Jan Lublinski
| ACTIVITY 3.3 | Milestone 1: September 2011 | Milestone 2: January 2012 | Milestone 3: December 2012 |  | Monitoring Officer
| Provide core funding for 4 to 5 associations: send calls for proposals and select the best appicants to get the funding | First data aquisition | data aquisition at the regional meetings | Last data aquisition at the face-to-face meeting | Lack of good proposals submitted by associations to be funded | Olfa Labassi and Jan Lublinski
OUTPUT 4 | ACTIVITY 4.1 | Milestone 1: April 2011 | Milestone 2: January 2012 | Milestone 3: November 2012 | Risks | Monitoring Officer
evaluation methodology of quality of science journalism and impact stories | Produce (scholarly) peer-reviewed publication | First data aquisition at the face-to-face meeting | data aquisition at regional meetings | Two (scholarly) academic papers submitted to international peer-reviewed journals | Lack of basic data to facilitate the information analysis, difficulties in methodology. | Olfa Labassi and Jan Lublinski
| ACTIVITY 4.2 | Milestone 1: April 2011 | Milestone 2: December 2011 | Milestone 3: February 2012 | Risks | Monitoring Officer
| Hold conference talks on SjCOOP evaluation methodology / produce proceedings manuscripts / produce lessons learned reports and present them to specific expert audiences e.g. the WFSJ programme comittee and the Research Uptake group / collect feedback from experts | First data aquisition at the face-to-face meeting | data aquisition at the face-to-face meeting | three conference talks given (at different stages of the project) | Lack of conferences where we could present the SjCOOP evaluation methodology | Olfa Labassi and Jan Lublinski