Business Case and Intervention Summary

Intervention Summary

## Title: Trade Transparency Project

What support will the UK provide?
The UK will support a number of organisations to collect and analyse trade and consumer data and to design, develop, and produce online tools and mobile applications based on the analysed data. Our support will be used to illustrate to the general public the impact of trade barriers on the prices they pay for everyday consumer goods. This support will help to inform consumers in the developed and developing world about the impact that their government’s trade policy decisions have on them. The support will total £300,000 in the first phase, running from August 2012 to August 2013.

Why is UK support required?
Many Governments, especially in developing countries, believe that tariffs are necessary to protect domestic production and jobs and that, by extension, trade restrictions are good for the poor. The costs of trade barriers to consumers however are rarely emphasised, largely because there are few consumer protection movements in the poorest countries and little information is available to citizens to enable them to understand the real impact of trade protection on the prices they pay for everyday goods. The UK’s support for this initiative would be an innovative means of using the internet to provide clear, accessible information on the costs of trade protection to consumers, enabling them to more effectively engage with government on trade policy.

What are the expected results?
The Trade Transparency Project (TTP) output will be to communicate the impact of trade barriers on consumer prices to a large audience. The expected results of the project are: / Large number of consumers become more informed about the impact of trade barriers on their shopping baskets; / Increased public debate and advocacy on free trade; / Increased number of formal and informal consumer and other citizen groups formed and lobby government on free trade. / Governments’ trade policy decisions become less protectionist as a result of citizen-lead lobbying and advocacy; / Trade increases in countries that lower trade barriers as a result of advocacy; / Increased trade leads to more jobs, increased income and poverty reduction / The reach of the TTP, and its ability to stimulate debate, will be evaluated on the basis of both online and offline metrics.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Strategic Priorities / There is a wide body of evidence showing that growth is the most effective means of raising incomes, creating jobs and reducing poverty in the developing world. We know that trade is a key driver of economic growth and development. For example trade leads to substantial gains in economic growth in the long run (7-12 % increase in income per year) and has a moderate positive effect even in a recession scenario (1-4% increase per year)[1]. / Supporting increased trade in the poorest countries is therefore a critical part of DFID’s wealth creation agenda as identified in DFID’s Structural Reform Plan (2011-15). The critical role of trade is also recognised in the UK’s Trade and Investment White Paper (February 2011) which sets out the Government’s commitment to providing support to developing countries to follow sustainable paths to growth through trade and investment. / The key to achieving increased trade is clear policies that promote trade openness such as reduced tariff barriers. According to the World Bank, in the 1990s per capita income grew more than three times faster for those developing countries that lowered trade barriers (5% per year) than for other developing countries (1.4% per year)[2]. / However the starting point for many Governments in developing countries – supported by NGO opinion in richer countries – is often that tariffs are necessary to protect domestic production and jobs and that, by extension, trade restrictions are good for the poor. The costs of trade barriers to consumers however are rarely emphasised, largely because there are few consumer protection movements in the poorest countries and little information is available to citizens to enable them to understand the real impact of trade protection on the prices they pay for everyday goods. The Trade Transparency Initiative would be an innovative means of using the internet to provide clear, accessible information on the costs of trade protection to consumers. This would demonstrate the case for open markets and generate a real debate on free trade. Promoting transparency and citizen engagement can help to shift the terms of debate on trade and development, encourage advocacy on free trade policies, and ultimately result in freer government trade policies. / The proposed approach which supports free trade by empowering citizens to influence government policies also sits firmly within the Coalition Government’s new approach to development that focuses on the wider transformation that is necessary to achieve open economies and societies. Together Open Societies and Open Economies enable citizens to lift themselves out of poverty and realise their potential. The intervention will use the internet and mobile technology with social and traditional media to promote greater transparency on trade policy, and generate a better understanding of how trade policies affect consumers. / As mobile and internet use has increased exponentially in the developing world new technologies - mobile, internet and other media – are increasingly being used in the transparency and accountability field. While this is a new and largely untested field, these new technologies have significant potential for reaching huge numbers of people and thereby increasing citizen awareness. Over the past five years, the annual growth rate of mobile telephony in Africa has been 550 per cent, more than twice the global average. This provides a critical means for reaching populations in the developing world in order to inform and educate target populations that can demand accountability and potentially influence government policy. / Why should DFID intervene? / While there is an abundance of trade data available publicly, it is very complex and aimed towards expert use. Because of the complexity of the data, it is effectively inaccessible to the public and they are therefore unable to assess the impact that tariffs and other trade barriers have on them. DFID should intervene in order to make this data more accessible so that the general public can understand how much they end up paying as a result of trade protection. / While the UK and other OECD countries have consumer advocacy groups that are able to lobby and advocate on behalf of consumers, there are very few such groups in Africa and the developing world overall. This initiative will help to provide consumer information that would not otherwise be made available. In addition, by releasing this data it could potentially lead to the formation of formal and informal groups who lobby their governments about the high price of protectionism for consumers. However the most easily attributable outcome of the initiative will be citizens who are better informed about trade and who have a greater awareness of how their government’s trade policies affect them. / Lastly, DFID should intervene because this is an innovative project that has not been attempted before. Although there are an increasing number of initiatives that use new technology to promote the government transparency and accountability agenda, there are currently no projects looking at transparency in relation to trade policy and the prices of everyday consumer goods. The potential impact, not only educating consumers but as a means of promoting advocacy and engagement with government trade policies, is considerable. / DFID’s funds would be used for: / Designing, developing, and disseminating a pilot project including, online tools and other media applications to inform and educate consumers in the developed and developing world about free trade; / Providing a platform for disseminating and debating the findings and policy implications of the information generated through the tools created; / Supporting partner organisations to further develop the tools and applications developed under the pilot and disseminate them to reach larger numbers of target users; / Monitoring and evaluation of the initiative.
B. Impact and Outcome that we expect to achieve / The results chain for this initiative are as follows: / Expected Impact: / Governments’ trade policy decisions become less protectionist as a result of citizen-lead lobbying and advocacy; / Trade increases in countries that lower trade barriers as a result of advocacy; / Increased trade leads to more jobs, increased income and poverty reduction. / Expected Outcomes: / Online tool attracts a large number of users; / Large number of users become more informed about the impact of trade barriers on their shopping baskets; / Increased public debate and advocacy on free trade created; / Increased number of formal and informal consumer and other citizen groups formed and lobby government on free trade. / Outputs / Online tools, mobile applications / Social media information / Debates, conferences / Traditional media information / Inputs / Trade and consumer price data / Econometric analysis / Hack and ‘Modding’ days / The assumption of moving from outcomes to impact is a strong one. We are assuming that by reaching a large number of users and by making these users more informed about the impact of trade barriers on their shopping baskets, this will lead to citizen-lead advocacy and lobbying, which will in turn result in government reducing trade barriers in response. The reduction in trade barriers would then lead to increased trade and increased jobs, income and ultimately poverty reduction. As this is a new and innovative approach to trade, there is limited evidence demonstrating the likelihood that this assumption is true. / We have also made a strong assumption moving from outputs to outcomes. The assumption is that by producing online tools/mobile applications, and by releasing the trade information through social and traditional media, formal and informal citizen groups will lobby government to reduce trade barriers. Again the evidence supporting this assumption is limited given the novel nature of the TTP. / While the evidence supporting the assumptions in our results chain is limited, the logic of the chain has been proven through similar interventions linked to government accountability. (See appraisal case.)
[1] Plummer M., “Seizing the Benefits of Trade for Employment and Growth”, OECD, November 2010. http://www.oecd.org/dataoecd/37/39/46391923.pdf
[2] OECD, ILO, WORLD BANK, WTO (11-12 November 2010) “Seizing the benefits of trade for employment and growth”, final report, Prepared for submission to the G-20 Summit meeting Seoul (Korea), http://www.oecd.org/dataoecd/61/57/46353240.pdf

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / OPTION 1 – Use social media, internet and other channels to inform consumers / Eye-catching visualisations and graphics of the impact of trade barriers on the prices of everyday goods will be used to inform consumers about how trade policies affect them. The option will be implemented in two phases to allow an opportunity to assess the level of interest that already exists in this area and try out the best ways to engage more people. / In the first phase, a few countries and products will be chosen and the graphics will be publicised through the DFID social media accounts. In the second phase, the project will be expanded to include more countries and more products. Also, more channels such as mobile phone/tablet applications, radio, press, television etc. will be used to increase the number of people reached. Country-specific communications strategies will be developed based on the most effective means for reaching local target audiences. / OPTION 2 – Building capacity of consumer groups in individual countries and funding them to inform consumers through various media channels / This option will involve choosing a few countries to work in and build the capacity of civil society organisations that are concerned with consumer rights. These CSOs can then lobby for freer trade and could be given specific funding to run a consumer awareness campaign on the impacts of trade barriers. / OPTION 3 – Support another international institution to provide information about trade barriers to consumers / In this option, an existing international organisation will be convinced to undertake a project to publicise information about trade barriers to ordinary consumers. / OPTION 4 – Do Nothing / In this case, DFID would not undertake any action to increase consumer awareness about the effects of trade barriers on prices.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / The evidence available for all these options is limited because there have been very few interventions targeting consumer awareness on trade-related issues. There is a great deal of evidence on consumer awareness programmes in areas such as public health that identify the features of the programmes that successfully change behaviour. But most of this evidence is concentrated in richer countries. / In developing countries, there are now studies of citizen engagement programmes on areas such as election and budget monitoring, crime mapping and maintaining the quality of public services. These campaigns have had varied levels of success and some of the common features of successful programmes are being identified but evidence of impact is limited[3]. This is because of the newness of the field as well as a previous lack of emphasis on impact and evaluation issues. / A programme targeting consumers in developing countries to make them aware of trade related issues, in particular, is a new and innovative idea and evidence available is limited for this reason. / Option Evidence rating / 1 Limited / 2 Limited / 3 Limited / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 C C / On the basis of the evidence provided in this business case and as the proposed programme has limited relevance for environmental and climate change issues, it has been assessed that all options proposed would not generate unmanageable risks associated with the environmental impact of the intervention, or its effects on global climate. There may be some impact from the operational impacts of the programme (e.g. travel required, research materials produced, websites/apps launched). Recommendations to minimise these operational impacts include: / Ensure individuals conducting research or awareness raising activities travel in economy class. On average, business class passengers are responsible for up to 2.1 times the emissions of an economy traveller[4]. Business class travel will also have a negative impact on the value for money of the programme. / Reduce the carbon footprint of the outputs through, for example, use of lower carbon options for website/applications, including choice of servers[5]; use of recycled paper; and minimising printing and printing waste. / All options will likely generate no/low opportunities for addressing environmental impacts or global climate change. However, if this pilot phase is scaled-up/extended, there may be opportunities to build in information on environmental impacts of traded goods, highlighting these additional costs to the consumer. This could utilise work on life-cycle carbon footprinting of products (using the British Standards Institutes PAS 2050 standard[6]).
C. What are the costs and benefits of each feasible option? / ADVANTAGES DISADVANTAGES / Option 1. / Use social media, internet and other channels (e.g. radio, posters) to inform consumers about the impact of trade barriers on prices. Relatively low-cost option as existing channels could be used to communicate. / Reaches a global audience Limited target population – young, urban and middle class who are most likely to access and act on the information / Risk that better informed consumers will not take action to change trade barriers / Option 2. / Use a country–by-country approach with a focus on building capacity of consumer groups and fund them to inform consumers Information included could be more detailed and context-specific than in a global initiative. / Possible that the local knowledge of consumer groups will enable them to reach more diverse groups of people. / Stronger consumer groups may also lead to more trade liberalisation in a shorter time scale through lobbying efforts. High costs - both financial and time. Civil society organisations in developing countries generally have very low capacity. / It may require additional time and resources to contact multiple partners in each country. / The number of countries that could potentially be reached would be small. / Risk that these few countries will feel “targeted”. / Option 3. Support another international institution such as UNCTAD or ITC to run an information campaign for consumers Possibly low cost / Other organisations have more experience of disseminating information and greater geographical reach / Information may be viewed as more “independent” if from an international organisation High transaction costs to start / Consumer awareness does not fit into the remit of any existing trade-related organisations. / As this is a new idea, other organisations may have a different interpretation of the objectives and execution than DFID. / Option 4. / Do Nothing Cost free. Resources for trade transparency programme could be directed to other priorities. Benefits from increased transparency not realised. / Consumers stay ill-informed about trade barriers. / OPTION 1 – Use social media, internet and other channels to inform consumers / Costs: / Phase I of the project will cost £300,000. The breakdown is as follows: / Design Costs – / Cost of retail price and other relevant data - £5,000 / Cost of analytical services for price modelling - £40,000 / Implementation Costs – / Cost of developing graphics, communications tools, web material - £225,000 / Cost of monitoring and evaluation - £20 000 / Dissemination strategy - £10 000 / The details for Phase II of the project will be finalised based on lessons from the implementation of Phase I. The costs of Phase II are likely to be higher as we will expand country and product coverage, develop more tools, and use more channels to reach target audiences. However, we are also exploring the possibilities of partnering with other organisations for this phase and may share costs. / Number of people reached: / Levels of interest are difficult to gauge as there are no examples of similar projects. The target audience of this initiative, given the reliance on internet and social media, is likely to be young and urban. Some of the statistics available on population and internet usage can inform an estimate of the potential number of people the project could reach: / The latest UN population statistics show that approximately a third of the population in sub-Saharan Africa and South Asia is between the ages of 20 and 40[7]. / The proportion of the population living in urban areas is 37 percent for sub-Saharan Africa and 31 percent for South Asia[8]. / Assuming that the age structure of urban areas is not very different from the national level, the urban population aged between 20 and 40 is approximately 89m people in sub-Saharan Africa and 162m in South Asia. / Applying the latest internet penetration statistics[9] for the two regions to this population gives approximately 10m people in sub-Saharan Africa and 16m in South Asia i.e. 26m as the total number of young, urban people with internet access. / The first phase of the project is likely to reach those people who are already engaged on DFID’s website or social media pages, which is approximately 60,000 people, about half of whom are based in developing countries. There is also likely to be a cascading effect as people share the information with their contacts. In order to reach an African audience, we are planning to partner with the social networking application MXit, which has a subscriber base of around 50 million people mostly in developing countries, particularly in southern Africa. Using a conservative assumption that only 1 percent of MXit users are reached in the first phase, a minimum estimate of the number of people who will receive information through the programme would be approximately 530,000 (500,000 plus 30,000 through DFID channels). / In Phase II, the project will expand into other communications channels but the internet and mobiles will remain important. The estimated 26m total of the number of people in South Asia and sub-Saharan Africa that are young, urban and have internet connectivity can be seen as a potential target population. The number of mobile phone subscriptions in South Asia and Sub-Saharan Africa is estimated at well over 1 billion in 2010[10]. While some of this is driven by people that have multiple phones, it is still a very large number of people. As the programme expands, it may include cooperation with civil society or international organisations which would also increase the number of people reached. The project should be able to reach a minimum of 2 million people in Phase II, given the size of the potential target population. / Moreover, the calculations above do not take account of the people reached in developed countries. Given that internet and smartphone penetration rates are much higher in developed countries, it is likely that a large number of people in rich countries will also become better informed through this project even though they are not the main target population. / Benefits: / There are three main benefits of this approach – / Increased transparency and better informed consumers / A possible lowering of trade barriers in several countries / Learning from innovative methods of citizen engagement to use in future projects / The immediate benefit of the project will be that some consumers are better informed about the impact of trade policy on their lives. Transparency is one of the essential characteristics of good governance[11] and the availability of information for ordinary citizens is necessary for a well-functioning democratic society. While the inherent value of greater transparency and better informed consumers is not quantifiable, the importance of this outcome should not be understated. / A longer term benefit of the project is that consumers who are informed about the impact of trade barriers will lobby their governments to reduce existing trade barriers and resist the introduction of more barriers in the future. However, the link between increased transparency and outcomes such as lower trade barriers is uncertain. The existing evidence on transparency and citizen engagement programmes is limited. The studies that do exist provide information about the effectiveness of the programme (e.g. how many people it reached) but very few studies focus on impact. There is some evidence of specific programmes that have worked, particularly those that deal with service delivery or election monitoring, but overall the evidence is anecdotal or in the form of case studies[12]. / However, while it is uncertain that a transparency programme will result in successful lobbying, the possible economic gains from freer trade are very large compared with the cost of the programme. / There is a wealth of evidence on trade openness as a necessary condition for economic growth. For example: / A recent World Bank paper estimates that a 1 percentage point increase in the ratio of trade over gross domestic product is associated with a short-run increase in growth of approximately 0.5% per year, and with an even larger effect in the long-run, reaching about 0.8% after ten years[13]. / The OECD estimates that, on average, $1 worth of increased tariff revenue leads to a $2.16 dollar drop in world exports and a $0.73 dollar drop in world income[14]. / There are many estimates of the potential gains from trade liberalisation. For example, the increase in global income as a result of goods trade liberalisation under the World Trade Organisation Doha negotiations, even taking into account regional and other trade agreements since 2004, is estimated at US$59 billion by 2025[15]. / The results chain from greater transparency to freer trade involves a large number of steps. However, if we take the present value[16] of the simulated estimates of global free trade given above, a transparency project would only need to cause 0.007% increase in global trade liberalisation to break even on a possible total cost of £1m. / In view of the relatively low cost and the advantages of phased implementation to test an innovative approach, Option 1 is the preferred option for the implementation of the project. / OPTION 2 – Building capacity of consumer groups in individual countries and funding them to inform consumers through various media channels / Costs: / DFID has extensive experience of working with civil society organisations on transparency projects in the governance area but not on consumer or trade issues. There are not many CSOs in developing countries that specialise in consumer rights and trade. There are organisations that focus on one or the other and it is possible that some of these could be chosen. It is possible that an organisation that focuses both on trade and consumer rights issues would need to be set up from scratch. Moreover, civil society organisations in developing countries often have very limited capability and building them up is likely to be very costly and time-consuming. For example, the DFID funded Governance and Transparency Fund which is a £131m fund for civil society organisations to work on transparency related programmes. The GTF funded 38 projects (average cost £3m each) and each project was 3 to 5 years[17]. This gives some estimate of how much time and money will be needed to work with a civil society organisation. / Number of People Reached: / The estimated number of people reached will depend on which countries are chosen and how effective the CSOs are. This option will not have the potential global reach of Option 1. However, it is possible that local civil society organisations are able to reach more people within country and have deeper engagement with them. / Benefits: / The two benefits of better informed consumers and freer trade outlined above would apply in this option as well. A local CSO may be able to make the information more locally relevant and so may have greater success in helping people understand some of the trade-related issues. However, a civil society organisation is likely to have more focussed lobbying efforts around trade barrier reductions and less of a focus on disseminating information so the balance between the two benefits may be different from Option 1. The amount of time necessary to build capacity of any existing CSOs will also mean that there will be a delay in disseminating the information. Also, the benefit of testing an innovative approach would not be realised in this option. / OPTION 3 – Support another international institution to provide information about trade barriers to consumers / Costs: / The financial costs of this option will be low. However, they are likely to be higher than Option 1 given that we would pay overheads which for UN agencies can be 13% of total costs. / However, the time and effort to convince another organisation to take on such a project will be high. The existing international organisations that focus on trade and development e.g. the WTO, ITC, UNCTAD, ICTSD etc. do not focus on consumer interests nor have activities related to communication with the general public. There will need to be considerable effort made to convince an organisation to take up an activity that is outside its remit. / Number of People Reached: / The number of people reached will vary depending on how high-profile the organisation in question is and the way in which it chooses to implement a transparency project. However, most of the international organisations that work on trade and development issues have communication channels that reach people who are already interested in the area so the balance of people reached may be skewed towards these rather than ordinary consumers. / Benefits: / If the international organisation concerned has an effective programme, the benefit of more informed consumers and the possibility of reduced trade barriers would be realised through this option as well. However, given that it would take more time to set up, there would be a delay in disseminating information to the general public. There would also be more political considerations for an international organisation engaging in advocacy efforts with governments to lower trade barriers as compared with Option 1, which encourages a grassroots movement led by informed consumers. / OPTION 4 – Do Nothing / Costs: none / Number of People reached: none / Benefits: the resources to be used in a transparency initiative could be directed elsewhere. However, none of the expected benefits from the trade transparency initiative would be realised; there would be continued low levels of transparency on the cost of trade barriers for consumers, and there would be costs associated with the of persistence of, or increase in, trade barriers that might otherwise have been lowered as a result of the initiative.
D. What measures can be used to assess Value for Money for the intervention? / The Value for Money of the intervention can be measured by the unit cost per person informed by the project. For options 2 and 3, an estimate of the number of people reached is not known. For option 1, this unit cost measure for Phase I is £150,000/530,000 = £0.28. The number of people reached by the project will be measured by tracking how many social networking users have accessed the project material. / While a better measure for VFM would be a benefits-to-cost ratio, this will not be possible because the main benefit of the project is greater transparency and consumer awareness about trade-related issues, which is difficult to quantify.
E. Summary Value for Money Statement for the preferred option / In view of the relatively low cost, high number of people reached, speed of implementation and the advantages of phased implementation to test an innovative approach, Option 1 is the preferred option.
[3] See for example, McGee R. and Gaventa J. “Review of Impact and Effectiveness of Transparency and Accountability Initiatives: Synthesis Report”, Institute of Development Studies, October 2010
[4] Kollmuss, A., Lane, J. (2008) Carbon Offsetting & Air Travel, Stockholm Environment Institute Discussion Paper, Part 1: CO2-Emissions Calculations, 28 May 2008. Available at: http://www.co2offsetresearch.org/PDF/SEI_Air_Travel_Emissions_Paper1_%20May_08.pdf
[5] Zapico, J.L., Turpeinen, M., Brandt, N. (2010) Greenalytics: A tool for mash-up life cycle assessment of websites. Proceedings of the 24th International Conference on Informatics for Environmental Protection. Shaker Verlag, Aachen, Germany, 2010. Available at: http://cesc.kth.se/greenalytics-a-tool-for-mash-up-life-cycle-assessment-of-websites/
[6] Available at: www.bsigroup.com/pas2050
[7] United Nations, Department of Economic and Social Affairs, Population Division (2011), World Population Prospects: the 2010 revision
[8] United Nations, Department of Economic and Social Affairs, Population Division (2012). World Urbanization Prospects: The 2011 Revision
[9] Statistics from http://www.internetworldstats.com/. Refer to Internet Usage as at 31st December 2011.
[10] World Development Indicators Online, Mobile Cellular Subscriptions 2010
[11] UNESCAP, “What is Good Governance?” http://www.unescap.org/pdd/prs/ProjectActivities/Ongoing/gg/governance.asp
[12] McGee, R. and Gaventa, J. “Shifting Power? Assessing the Impact of Transparency and Accountability Initiatives”, IDS Working Paper 383, 2011, p. 18. For examples of Case Studies see “Technology for Transparency: The Role of Technology and Citizen Media in Promoting Transparency, Accountability and Civic Participation”, Technology for Tranpsarency Network
[13] Bruckner, M. and Lederman, D. “Trade Causes Growth in Sub-Saharan Africa”, World Bank Policy Research Working Paper 6007, March 2012
[14] OECD Policy Note “Trade, Policy and the Economic Crisis”, May 2010
[15] Bouet, A. and Laborde D. (2009), “The potential cost of a failed Doha Round” IFPRI discussion paper 00886, Washington.
[16] A discount rate of 10% applied over 13 years to get present value of US$59 billion in 2025
[17] DFID Project Database, Governance and Transparency Fund and Burge, R. Learning from DFID’s Governance and Transparency Fund (GTF), June 2010

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Service providers will need to be procured to provide the following: / Collection and analysis of data / Development, design, production and testing of online tools / Development, design and delivery of tools through other media channels (Phase II) / Monitoring and evaluation / Dissemination / Competitive OJEU selection process will be used for any contracts above the £99 000 threshold. Given the small budget for the 2-3 contracts under Phase I (for data analysis, design/production, and monitoring/evaluation) of the programme, and the tight timeline for delivery, we will not use competitive bidding.
B. How does the intervention design use competition to drive commercial advantage for DFID? / Service providers will be selected on a highly competitive basis with robust negotiations to drive down costs. Larger components of the initiative will be put out to tender resulting in selection of best provision of service at the lowest price. Smaller components of the project may not be put out to tender but proposals will be benchmarked against similar work previously procured by DFID. In order to drive commercial advantage and adequate quality of delivery, we will use results-based contracts with service providers
C. How do we expect the market place will respond to this opportunity? / There are a range of organisations which will be keen to compete for contracts as service providers. Given the large number of organisations that could provide the services required, we will be able to negotiate down prices and achieve value for money while maintaining a high standard of delivery.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / This is a relatively low-cost intervention. The key cost elements will be time, expertise and access to software. Key cost elements are: data analysis, development/design of tools and graphics, monitoring and evaluation, and dissemination. / The main cost element will be time cost (day rates). Negotiated day rates will be kept within DFID procurement guidelines. Proposed time costs will be benchmarked against prices previously paid for similar tasks.
E. What is the intended Procurement Process to support contract award? / We will use competitive tender process for any contracts greater than £99,000 and single-source contracting, with close attention to value for money, for smaller contracts. We do not envision in the pilot phase using the OJEU process given the small size of the contracts for each item of spend. All of these are well below the OJEU threshold.
F. How will contract & supplier performance be managed through the life of the intervention? / Milestone contracts with payment on delivery will be implemented across the project to ensure supplier performance. Clear performance criteria agreed for mid-term and Annual reviews along with robust monitoring and evaluation procedures based on the project logframe.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / N/A
B. Value for money through procurement / N/A

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Phase I: FY 2012-13 / Data Analysis £45,000 / Tool Design and Development: £225,000 / Monitoring and Evaluation: £20,000 / Dissemination: £10,000 / Total Phase I costs - £300,000 / Adequate funding for Phase I is available within current resource allocation and Phase I expenditure is not currently expected to extend into the next spending round. / The details (and therefore costs) of Phase II of the project will be finalised based on lessons from the implementation of Phase I. The costs of Phase II are likely to be higher due to possible expanded product and country coverage and additional channels. The potential to partner and share costs with other organisations for this phase will be explored. Costs for the project as a whole are anticipated to be under £2m in total.
B. How will it be funded: capital/programme/admin? / The programme will be funded from TPU’s programme budget for FY12/13
C. How will funds be paid out? / Funds will be paid directly to service providers on an output delivery basis.
D. What is the assessment of financial risk and fraud? / Low. Service providers being considered have previously supplied services to DFID (passing due diligence requirements) and payments are being made on an output basis, limiting risk.
E. How will expenditure be monitored, reported, and accounted for? / Service Providers will be closely managed and contracted to provide regular updates, progress reports, and early drafts. Contracts with service providers will include a requirement to provide robust financial reporting against expenditure and accurate forecasting. Payments will be focused on the satisfactory delivery of outputs; where outputs are not delivered to an adequate level of quality payment will be withheld.

Management Case

A. What are the Management Arrangements for implementing the intervention? / DFID will contract directly with Service Providers for the provision of services. Service Providers will provide regular updates, with progress judged by the Project Manager against agreed delivery plans and timelines. / Decisions on phase II implementation will be taken after a mid-term review of the project in Feb 2013. / The project manager will be the Aid for Trade Policy Officer. The Economic Adviser will lead management of all technical and analytical outputs from service providers. The Aid for Trade Team Leader will have overall management oversight of the project.
B. What are the risks and how these will be managed? / Timing of Delivery Risk: Medium / Managed through close monitoring including regular updates, with progress monitored against initial delivery plans and timelines. Clear timelines for delivery of outputs will be included in all contracts with contract performance being judged not just on delivery but on delivery within a specified timeline. / Financial Risk: Low / Payments will be made on demonstration of delivery of outputs. Close project monitoring with a clear requirement of robust financial reporting
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / The project logframe will be used to monitor progress and results. Progress towards contracted outputs will be monitored via regular updates, progress reports and delivery milestones linked to payment. Prior to online launch of products, user testing will be considered. Once online, outputs will be monitored closely using site analytics, measuring online usage, coverage and interest. Lessons will be drawn from the monitoring of Phase I for any implementation of Phase II.