Intervention Summary

## Title: Tanzania Climate Change Institutional Strengthening Programme

What support will the UK provide?
The UK will provide £2 million over 4 years from April 2011 to March 2015 to fund: i) a climate change programme adviser and ii) a flexible technical assistance fund, which will focus on support to institutional strengthening on climate change in Tanzania. The intervention will complement other climate change work currently funded by DFID Tanzania providing support to civil society and the private sector.

Why is UK support required?
What need are we trying to address? / This intervention will address the adverse impact of climate change in Tanzania. Tanzania’s ability to cope with climate change is limited by a number of factors including poverty, weak institutions and under-investment in key sectors. The scale of the challenge is uncertain, but could be equivalent to a loss of almost 2% of GDP each year by 2030 in Tanzania. Climate change is expected to set back progress that has been made in achieving the Millennium Development Goals (MDGs), and will have a disproportionate impact on poor people and vulnerable groups. / Tanzania like many countries in Africa is extremely vulnerable to the effects of climate change. The frequency and severity of extreme weather events such as drought and flood is already increasing. The problem threatens to become much worse over time with major effects on: agriculture and the availability of food; the cost and availability of energy; the availability of water; and on people’s health as the incidence of diseases such as malaria increases sharply. / There are, however, ways in which the economy can become more resilient to climate change so that damage is limited. There are also investments that will allow the economy to still grow at a fast pace while controlling the consumption of increasingly expensive fossil fuels for energy. There are growing sources of international finance available to help countries adapt their economies to climate change and adopt a more resilient low carbon growth strategy. / The key task for Tanzania is to develop better policies and programmes that will address the problems that are emerging and allow access to the international resources that are (and will be) available to support good climate change plans. Tanzania also needs to develop a better track record in implementing and enforcement of strategies, legislation and effective delivery at the local level. The National Adaptation Plan of Action that was agreed in 2007 requires strengthening and needs to be framed in the context of a comprehensive Tanzanian National Climate Change Strategy that covers all the key sectors. The institutions that will implement this strategy need to become stronger. The resources available to make the economy more climate resilient need to be used well. In addition to the lack of government capacity, climate change does not yet feature as an important political issue at local or national levels. / Development partners can support progress through a number of channels working with both government and non-state actors such as civil society and private sector. This intervention addresses the need to support government and help it design better policies and strengthen its ability to deliver effectively at a national and local level. / What will we do to tackle this problem? / The Tanzania Climate Change Institutional Strengthening Programme (CCISP) (£2m over four years) will put in place essential mechanisms, and gather evidence, to substantially scale-up investment to enable Tanzania to manage the risks and opportunities associated with climate change. This future investment is expected to come through international climate change financing, the Government of Tanzania’s budget and local, regional and international private sector investment. / The intended impact of the programme is to contribute to Tanzania’s achievement of its Millennium Development Goals (MDGs) though better management of climate change risks and opportunities. / The intended outcome of the programme will be that Tanzania accesses climate finance and uses it effectively to address climate change and its impact. (This will build resilience to climate change and identifying opportunities for low carbon sustainable growth). / This new intervention will focus on providing support to government institutions at a national and local level. This will complement other support provided by DFID to civil society and private sector to address the challenges of climate change in Tanzania.

What are the expected results?
What will change as a result of our support? / The key changes which are expected to result from DFID support include: / Tanzania has a comprehensive National Climate Change strategy. / Tanzania is better placed to access climate finance of at least $300m by 2015. Tanzania also has a strong policy and institutional framework to plan, budget and deliver for effective use of the climate finance at a national and local level. / Establishment and implementation of an effective national level policy and financing framework with climate change mainstreamed into key sector policies and annual budgeting processes. / Ministry of Finance and key sector Ministries are more engaged and active on the climate change agenda. Climate Change plans developed in key sector ministries and for key sector investments (such as “green growth” strategy for the Southern Agricultural Growth Corridor for Tanzania). / Performance based climate financing piloted in at least 5 villages/districts by 2015, to enable them to effectively plan and budget for climate change. / Increased number of people, who are better able to cope with the adverse effects of climate change. (Exact number of people to be reached will be determined as part of the monitoring framework for DFID climate change programmes in by end 2011) / 50% of £640m per annum of project aid and concessional borrowing in Tanzania is screened for impacts on climate change by 2015. / Evaluation of the impact of all climate change interventions as part of our DFID Tanzania Operational Plan to help us build a strong evidence base for future programming on climate change. / How will we determine whether the expected results have been achieved? / An M&E framework will be in place for this intervention and to support development of more effective M&E systems for climate change in Tanzania. As the programme will be implemented over 4 years (a relatively short timeframe to show concrete change on the institutional side), monitoring will generally draw on already established monitoring systems. An independent end of programme evaluation will be undertaken to identify lessons learnt and feed into any follow-on programmes of DFID and other development partners. The evaluation is planned to assess the impact of DFID Tanzania’s £10m investments on climate change over the next four years, as well as climate change as a crosscutting issue across the whole of DFID Tanzania’s operational plan.

Business Case for: Tanzania Climate Change Institutional Strengthening Programme

Strategic Case

A. Context and need for DFID intervention / Rationale / Tanzania like many countries in Africa is extremely vulnerable to the effects of climate change. The frequency and severity of extreme weather events such as drought and flood is already increasing. The problem threatens to become much worse over time with major effects on: agriculture and the availability of food; the cost and availability of energy; the availability of water; and on people’s health as the incidence of diseases such as malaria increases sharply. Projections suggest that without policies and programmes that will help Tanzania adapt to climate change the economic costs could be the equivalent of 2% of GDP a year by 2030[1]. Progress and investment towards the achievement of the MDGs will slow significantly. Tanzania’s poor, especially poor women, will be the most severely affected. / Climate change is both a significant threat and a huge opportunity for Tanzania’s development. Current climate variability and future climate change have consequences for all Tanzanians, especially the poor. Tanzania will need support to help its people adapt to the impacts of climate change. Tanzania needs the institutional capacity to respond to these threats and opportunities and the government will need to put in place the right people, financing mechanisms and institutional arrangements to co-ordinate a cross-sectoral response to climate change, to enable it to access climate finance and spend it effectively[2]. DFID as the focal point for the Development Partners in Tanzania on climate change can potentially play a significant role in shaping the support on this agenda. / The DFID Tanzania operational plan for the next four years outlines DFID’s engagement on climate change building on the evidence developed under the Climate Strategic Programme review and a proposed division of labour with other development partners. The goal of the proposed support on institutional strengthening is to enable Tanzania to achieve its MDGs and sustainable economic growth, through better management of climate change risks and opportunities. DFID’s support on climate change will support a broad range of actors including government, private sector and non-government organisations and oversight bodies that can influence change, through strategic technical assistance. It should also be designed to enable Tanzania to be better positioned to access both bilateral and multi-lateral climate change finance. / Context and Evidence / Tanzania / Tanzania has a population of 40 million which is expected to rise to 75 million by 2030 and 110 million by 2050. The population is largely rural, highly dependant on natural resources. Some 80% of the population depend, at least in part, on agriculture for their livelihoods[3]. / Tanzania remains a poor country and despite consistent economic growth. 80% of the population (34 million people) live on less than £20 a month and 34% (15 million people) live on less than £7 a month, which means that they cannot buy essential goods like soap and clothes[4] Between 1992 and 2006 the percentage of people living below the national poverty line decreased by only 5%; from 39% to 34%. Due to the population growth over the same period, this translates in to an increased number of people living in poverty in Tanzania. Tanzania remains committed to a GDP growth rate of 8-10% per annum to transform the economy.[5] / Tanzania and Climate Change / In response to the United Nations Framework Convention on Climate Change (UNFCCC), Tanzania developed its Initial National Communication (INC) on climate change, which included a national inventory of sources of greenhouse gases, identification of vulnerable sectors and actions to be taken for sustainable future socio-economic developments. It was submitted in March 2003. It remains the most comprehensive and authoritative account of climate changes in Tanzania, although the knowledge base on climate change continues to improve. / On a per capita basis, Tanzania is currently one of the world’s lowest emitters of greenhouse gases (GHG) at 2.4 tonnes of CO2 equivalent in 2007, including emissions from land use change and deforestation (LUCF). Biomass, predominantly wood fuels such as charcoal accounts for 90% of energy needs and deforestation, (before taking account of forest replanting etc), accounts for 70% of total GHG emissions.[6] / Tanzania has set ambitious economic growth targets of 8%-10% per annum[7]. The country is committed to moving from a predominantly agricultural economy to a diversified and semi-industrialised economy with a modern rural sector and high productivity. Tanzania, rich in renewable resources, has the opportunity to achieve its projected targets for economic growth on the basis of a low carbon economy. Many of these low carbon options come at less cost than competing high carbon alternatives, particularly when linked to access to carbon finance. However, on current trends and plans, Tanzania is gradually moving towards a high carbon economy. It remains possible to reverse this trend. Policy decisions taken over the next few years will determine whether Tanzania promotes climate resilience and low carbon growth or becomes “locked into” a high carbon economy. / Extreme climate events already cause major socio-economic impacts and reduce economic growth. The 2005/6 drought reduced economic growth by at least 1%. The net economic costs of climate change could be equivalent to 2% GDP per year by 2030.[8] By 2030, total additional costs of building resilience and managing climate risks could be as high as US$ 1,500 to US$ 2,000 million a year. The costs of enhancing climate resilience in new investments are estimated at US 250 – 1000 million. Continued investment in capacity is estimated at US 20 – 50 million per annum and the cost of social protection and accelerated development at US 500 – 1000 million. It is noteworthy that the costs of social protection and building climate resilient livelihoods for the poor are at least as great as the costs of climate proofing infrastructure.[9] Whilst there are many uncertainties about the precise impacts, climate change carries significant risks for Tanzania’s climate sensitive economic sectors such as agriculture and tourism. / Climate change threatens to become much worse over time with major effects on vulnerable sectors: agriculture and the availability of food; the cost and availability of energy; the availability of water; and on people’s health as the incidence of diseases such as malaria increases sharply. Climate change is a threat to the rate of progress in reducing poverty. Floods, droughts, rising temperatures, sea level rise, saline intrusion and changing rainfall patterns will hit the poorest in society hardest; the socially excluded and vulnerable, who have the fewest resources and are least able to benefit from economic growth[10]. Progress and investment towards the achievement of the Millennium Development Goals (MDGs) will slow significantly, particularly on poverty and environmental sustainability, which are already off track.[11] / Institutional Context and Need[12] / The cornerstone of the Government of Tanzania’s (GoT) response to climate change is the National Action Platform for Adaptation (NAPA). The NAPA identifies the some of the challenges and priority actions needed to respond to climate change in Tanzania. While notionally focused on adapting to the impacts of climate change, Tanzania’s NAPA also includes several commitments for reducing carbon emissions. The NAPA has had limited support, only one of the priority areas has been funded. This is in part due to the fact that it is not felt to be sufficiently robust, based primarily on the data in National Communication of 2003, and that more up to date information and studies on climate change are now available e.g. economics of climate change. Secondly there is limited ownership the NAPA, which was externally driven by international adaptation funding, rather than being nationally owned. The Government is planning to address these shortcomings and build on the NAPA by developing a national climate change strategy. / Government roles. Climate change has implications for a range of government ministries. In Tanzania, there are a number of key organisations. The Division for Environment (DoE) within the Vice President’s Office (VPO) co-ordinates action on the environment and has a Climate Change Team, which has led preparation of the NAPA. While DoE is responsible for policy formulation on environmental issues, policy implementation sits with the National Environmental Management Council (NEMC). However as highlighted in the economics of climate change study[13], climate change is also an economic issue and potential large levels of climate finance necessitate the involvement of Ministry of Finance, Planning Commission, key sector ministries and districts to ensure effective delivery. The engagement of these institutions will be critical for successful management of climate finance and effective delivery on climate change. It will also be an opportunity to pilot results based financing for effective delivery climate finance at the national and local level. (These views are based on a DFID funded political economy study on climate change.)[14] / Non-State Actor roles. Non-state actors, such as civil society, media and private sector, also have a critical role to play not only in the delivery of community based adaptation but in advocacy, lobbying and holding government to account for using climate finance and in the formulation and delivery of policy. The private sector is also well placed to drive innovation and deliver practical market solutions in areas such as renewable energy and climate adaptation technology. DFID Tanzania has established challenge funds for non- state actors on climate change to complement its support to government.[15] / Development Partner roles. There are over 40 development partners active in Tanzania. 14 development partners have agreed to deliver their assistance in a harmonised manner, as outlined in the Joint Assistance Strategy for Tanzania (JAST). There is a broad consensus in Tanzania’s development community that climate change is a cross-cutting issue which affects all the sector donor groups (growth, governance, agriculture, health, education and so on) and that it is not simply an environmental issue. However, the current home for development partner co-ordination on climate change is the Development Partners Group for Environment (DPG-E). DFID is the focal point for the development partners on Climate Change, leading the policy dialogue in this area. / Co-ordinated initiatives. The DPG for Environment and Climate Change group has 13 development partners of which seven are providing financial resources directly for climate change. In 2009, there was stocktaking report undertaken of donor activities, which was updated in 2011, which clearly illustrates the need for a joint funding mechanism and framework for co-ordinating development partner efforts on climate change. The Development Partners Group on Environment (DPG-E) is working towards establishing a framework, to reduce transaction costs and improve aid effectiveness through a more co-ordinated response and joint programming including support to civil society, private sector and government. Over the past year DFID and DANIDA have established a secretariat, which has led this work on co-ordination and development of a coherent framework. / DFID Support on Climate Change. In line with the DFID Business and Structural Reform Plans, DFID Tanzania has committed to integrating climate change into its development policy and practice. DFID Tanzania has developed a Climate Change Strategic Programme Review (SPR), which has been undertaken over the past year (2010). The objective of the SPR has been to build an evidence base for our engagement, ensuring that the country office has a firm understanding of the risks and opportunities climate change poses to development and, importantly, provide options to inform DFID’s future response.
Impact and Outcome / The proposed intervention on institutional strengthening is a strategic investment of £2m over four years to put in place essential mechanisms, and gather evidence, to enable substantially scaled-up investment to enable Tanzania to manage the risks and opportunities associated with climate change. This future investment is expected to come through international climate change financing, the Government of Tanzania budget and local, regional and international private sector investment. / The programme will play a key role in supporting the development of robust institutional mechanisms for climate change planning, budgeting and effective delivery at national and local level. / The intended impact of the programme is to contribute to Tanzania’s achievement of its Millennium Development Goals (MDGs) though better management of climate change risks and opportunities. Impact will be assessed by the number of people able to better cope with the adverse effects of climate change and Tanzania’s continued progress towards achieving its MDGs. / The intended outcome of the programme will be that Tanzania accesses climate finance and uses it effectively to support climate change resilience and low carbon sustainable growth. / This new intervention will focus on providing support to government institutions at a national and local level. This will complement other support provided by DFID to civil society and private sector to address the challenges of climate change in Tanzania.
[1] Tanzanian Economics of Climate Change study, DFID, 2011
[2] Political Economy of Climate Change, Argulhas and CEEST for DFID, 2010
[3] pg13-14 Tanzania Economics of Climate Change study, 2011 and World Population Prospects, UN 2010; 2008 and 2007
[4] Rapid Poverty Assessment 2008 (Poverty Monitoring Group) based on 2007 Household Budget Survey
[5] ibid
[6] Ibid and Tanzania Economics of CC study, SEI/GCCAP, 2011
[7] Tanzania Economics of Climate Change study, DFID 2011 and Mkukuta 2, GoT, 2010
[8] Tanzanian Economics of Climate Change study, DFID, 2011
[9] ibid
[10] Vulnerability Climate Change study as part of DFID Tanzania SPR, LTS International, 2010
[11] DFID Tanzania Country Briefing, 2010
[12] Political Economy of Climate Change study , 2010 and DANIDA funded stocktaking report on climate change in Tanzania, 2009
[13] Tanzania Economics of Climate Change Study, SEI/GCCAP funded by DFID, 2011
[14] ibid
[15] AECF REACT is a private sector challenge fund on climate change which DFID Tanzania have established in 2010. There is also a proposed CC and environment window proposed under the DFID Accountability fund supporting advocacy by civil society and media.

Appraisal Case

A. Determining Critical Success Criteria (CSC) / The following three CSC have been identified based on the analysis of need in the Strategic Case, to deliver the programme impact and outcome. These CSC are used to score the feasible options for delivery. / CSC Description Weighting (1-5) / 1 Will ensure the establishment of a strong policy and institutional framework to plan, budget and deliver climate resilient development in Tanzania (institutional strengthening) 5 / 2 Increased capacity to access and use climate finance effectively (financing and delivery) 5 / 3 Improved co-ordination and delivery on climate change programming and climate finance (aid effectiveness) 3
B. Feasible options / To deliver the proposed impact and outcome, there are number of actors that have a significant role to play (as is clearly outlined in the DFID funded political economy of climate change for Tanzania)[16], this includes state and non- state actors such as civil society, research institutions, academia, media and private sector. This is particularly the case in addressing such a broad ranging challenge such as climate change. This intervention and consideration of options will only focus on support to government, as there are other DFID programmes that focus specifically on support to non-state actors on climate change. It is acknowledged that it will be critical for these programmes to work together. / Therefore the following set of 4 options have been considered as potential instruments to support institutional strengthening of the government and complement our support to non-state actors whilst responding to the identified need on climate change. They are: / Do nothing directly to support institutional strengthening of government on climate change / Provide a Climate Change programme adviser / Establish a technical assistance fund / Provide a climate change programme adviser and set up a flexible technical assistance fund. / Option 1: Do nothing. This option would include continued engagement in the policy dialogue on cross cutting issues such as environment and climate change as part of budget support. / Option 2: Climate Change programme adviser only. The Climate Change Programme Adviser will lead the dialogue on climate change with Government of Tanzania (GoT) and development partners, provide technical assistance to GoT and support the development and implementation of the DFID Climate Change Programme in Tanzania. 60% of the post will focus on technical support to GoT and improving aid effectiveness of development partner work on climate change and the remaining 40% will focus on support to DFID climate change programme design and implementation and ensuring the portfolio is climate smart. / Option 3: Flexible Technical Assistance Fund only. Establish a flexible technical assistance fund which would provide strategic support on institutional strengthening. The areas supported will be based on demand and focus on national policy and financing framework for climate change, improving the impact of development partner spend on climate change and effective delivery at a national and local level. / Option 4: CC programme Adviser and TA fund. This option will combine both option 2 and 3. This will include the CC programme adviser managing the TA fund and ensuring coherence of the work with that of other development partners. / Evidence of Impact / Option 1 : Do nothing / Evidence Rating : Medium / In considering the options for support to government, a major part of DFID Tanzania’s programme is budget support, it is therefore important from the outset to consider this as potential instrument through which support can be provided. The 2011 DFID and Irish Aid Country Programme Evaluation[17] states that “cross cutting issues (such as environment and climate change) are often squeezed out in the budget support dialogue process” also that a mix of instruments including technical assistance is required to make the budget support dialogue more effective. DFID already plays a central role in the policy dialogue on climate change as part of the Development Partners Group for Environment, but this would only continue to be effectively carried out by option 2, see below. In addition to this, there are very limited allocations in the government budget for climate change and therefore budget support as the only instrument for taking forward the agenda on climate change would not be sufficient. / Option 2: Climate Change Programme Adviser / Evidence Rating : Medium / Over the past year the climate change agenda has expanded exponentially in Tanzania, in particular the REDD+ agenda. Driven largely by international negotiations (UNFCCC Cop 15) in Copenhagen and potential for climate finance, there has been a surge in government, civil society and development partner interest. Denmark and Norway have already played a substantive role in leading on this support to date. The UK can increasingly play a key role alongside other development partners in helping to shape Tanzania’s domestic response to climate change. DFID is the lead for the Development Partners on Climate Change (as the DPG focal point) but we have to date only allocated 50% of an advisers time to do this task (see below). In recognition of this it is proposed to put in place a climate change adviser, who will play a key influencing role and focus specifically on the Tanzanian climate agenda and priorities, as well as be instrumental in improving development partner/GoT co-ordination on climate change. / There is substantial evidence that a dedicated CC programme adviser would make a significant contribution to achieving the outcomes. DFID has a proven track record in providing effective and well respected coordination of development partner programming in several sectors in Tanzania, for example in education and private sector development. DFID has particular expertise in climate change and governance, which are required for the delivery of this intervention. / Over the past 20 months; DFID Tanzania has had 50% of a climate change programme funded adviser in post based in Dar es Salaam. This position was co-financed by DFID Tanzania and DFID Policy and Research Division. This post was key in establishing DFID’s leading role in Tanzania on climate change, improving development partner co-ordination and also in taking forward climate change related work, including leading on the DFID Strategic Climate Programme Review, the Bilateral Aid review climate change pillar and on climate change as part of the DFID operational plan. The adviser has also worked closely with government, private sector and non - state actors. / Option 3: Technical Assistance Fund / Evidence Rating: Limited / The DFID Tanzania Strategic Programme Review (incl. key analysis such as political economy and the economic impacts of climate change) that has been undertaken over the past year clearly sets out the evidence base and priority areas for engagement on climate change. It also identifies who to engage with, how and the strategic areas for technical assistance support. / In 2009, DFID established a climate change technical assistance fund (£600,000 over 18 months) which has been instrumental in allowing us to engage strategically and also in a flexible manner to requests. The TA fund has been used to meet the costs of: i) establishment of a secretariat for the Development Partners Group for Environment, ii) Climate Change Civil Society Platform with 50 civil society organisations as members and iii) Tanzanian economics of climate change study. The establishment of the secretariat for the development partners group has resulted in more joint programming on climate change including a civil society advocacy fund and agreement of joint strategic priorities for development partner engagement in the short and medium term. These priorities will form the basis for engagement under the new technical assistance fund. / The recent DFID/Irish Aid joint country programme evaluation[18] reinforces the need for using a mix of instruments alongside budget support, such as technical assistance, particularly for tackling cross cutting issues such as climate change and environment. / The evidence base for the proposed institutional and policy interventions will depend on the specific activities implemented under the TA fund. A strong case can be made for mainstreaming climate change in the budget and planning process and the development of a national climate change strategy. / There is relatively good international evidence that the level of international climate funding (and for development activities in other sectors e.g. HIV/Aids in Kenya) is strongly correlated to the existence of a secure and well governed financing mechanism for disbursing the funds and the management of associated fiduciary risks – for example in climate change multi- donor trust fund in Bangladesh and on budget climate finance in Mexico. Hence establishing a robust and effective climate financing mechanism in Tanzania is likely to be highly significant to mobilising additional climate finance. But the evidence that a well designed financing mechanism will lead to the successful implementation of the mechanism is more limited (medium), and will be highly dependent it’s effective governance and wider political risks. / There is limited evidence that large scale cross-sectoral plans or policies such as the proposed National Climate Strategy will result in significant implementation. The National Environmental Management Act (implementation plan) has to date achieved limited implementation impact or mainstreaming of environment into broader GoT budgeting and planning processes, despite development partners funding it’s implementation. However, in other areas there has been more progress such as in mainstreaming HIV/AIDS across GoT ministries and in the national budget process. / Option 4: Climate Change Programme Adviser and Strategic technical assistance fund / Evidence Rating : Medium / Option 4 will not only draw and build on the evidence already set out above for options 2 and 3 but also increase the impact, influence and the effectiveness of both by having a dedicated adviser to oversee the technical assistance fund. Over the past two years DFID Tanzania has had both a technical assistance fund and a dedicated climate adviser, to pilot this approach outlined under Option 4. It has proven to be very successful in i) increasing DFID/Development Partner influence on the climate change agenda, ii) being responsive to demands of key actors in climate change and therefore increasing the impact and influence of engagement i.e. in the run to climate negotiations in Copenhagen, iii) driving forward joint work and programming on climate change by development partners, building on a strong evidence base e.g. economics of climate change, political economy of climate change and support for civil society engagement and iv) ensuring effective oversight of climate change interventions and avoiding duplication of effort. For the adviser having a flexible technical assistance fund has increased their ability to respond quickly to requests and therefore increased their ability to influence key decision makers and have “first mover advantage” when opportunities arise. Therefore by combining both interventions the impact is likely to be more significant and risks associated with fund management will be reduced. / Environmental and Climate Change effects / In the table below: / the quality of evidence for each option is rated as either Strong, Medium or Limited, / the likely impact on climate change and environment is categorised as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Evidence Rating Climate change and environment category (A, B, C, D) / 1 - Do nothing Medium A High risk / C Medium potential opportunity / 2 - CC programme adviser Medium B Medium potential opportunity / 3 - TA fund only Limited B Medium potential opportunity / 4 -CC programme adviser and TA fund Medium A High potential opportunity/C low risk / Evidence Rating: Overall the evidence base for the programme options i.e. options for delivery is medium, however the evidence base for climate change in particular is weak i.e. how the proposed options relate to outcomes and impact. This is in part due to the fact that baseline data and information on climate change is poor as that this is a new area of work for both development partners and government. It is therefore proposed that the chosen intervention should include an explicit output on developing robust monitoring and an evaluation framework to contribute to strengthening the evidence base on climate change in Tanzania and for future DFID climate change programmes. / Option 1, “do nothing” is rated as high risk as there are considerable climate change impacts that need to be addressed and this will fail to do address those without the engagement of government and through budget support alone. Options 2-4 are climate change interventions they are therefore expected to have high to medium positive impact on climate change and environment in Tanzania.
C. Appraisal of options / Resource Costs of Options / Option 1-4 Budget / Option 1: Do Nothing £0 / No leverage or co-financing / Option 2: Climate Change Programme Adviser / (over 4 years, performance to be reviewed every 6 months with initial post for 18 months) £680,000 / (leveraging direct co-finance from others of at least £200,000, however there is potential to identify new areas of joint programming and the post will also result in a significant reduction in transaction costs and more effective management of the £30m per annum in climate finance) / Option 3: TA Fund / Potential areas to be financed: / National Climate Change Strategy incl. Zanzibar (with World Bank and Finland) / Scoping of National Financing Mechanism linked to REDD (with Norway) / Develop climate change action plans and budgets in two key economic sectors (with World Bank) / Southern Agricultural Growth Corridor of Tanzania (SAGCOT) climate change/green growth strategy (with Norway) / Development Partner Group for Environment and Climate Change Secretariat (with Denmark) / Climate Screening of General Budget Support and GoT budget incl. Public expenditure review on climate change (with World Bank) / Support to Ministry of Finance on climate financing incl. establishment of climate desk / Piloting support to district level for results/performance based financing for channelling climate funds sub-nationally focus on REDD and adaptation (Norway and DFID) / Monitoring and evaluation of DFID climate change interventions to assess impact and build evidence base £1,320,000 / (leveraging co-finance from others / of at least £500,000 to £24m*) / Option 4: CC Programme Adviser and TA Fund / (Options 2 and 3 combined) The CC programme adviser will be responsible for overseeing the TA fund and ensuring value for money for DFID as well as ensuring effective delivery and implementation. £2,000,000 / (leveraging co-finance from others of at least £700,000 to £30m potential to identify new areas of joint programming and reduction of transaction costs) / * There is very broad range as it is dependant on what is financed under the technical assistance fund. The high end figure relates to the current USD 40m (£24m exchange rate of 31/05/11) pledged development finance for the decentralised natural resource management, which would work at the district level. / The direct resource costs are outlined in the table above. However there are additional indirect costs associated with Option 3 and 4 in relation to managing the multiple contracts and Memorandums of Understandings with Development Partners. DFID will not lead on the contracting of all the work, where the co-financing is with other development partners, indirect procurement will be used i.e. the systems and procurement processes of the lead donor – refer to financial and commercial case for further details. / Benefits of Options / It is not good value for money to do a full cost benefit analysis, as there is limited evidence and it is difficult to quantify the benefits into monetary values. As far as possible the non-monetised and qualitative benefits have been included, including their potential scale and timescales. / Option 1: Do Nothing / Total Cost: £0 / Quantifiable benefits: None Non-quantifiable benefits: None / As already outlined in the evidence section there are limitations to providing budget support as the only instrument for work on climate change. As outlined in the Joint (DFID/Irish Aid) country programme evaluation pointed out that budget support as an instrument and the policy dialogue process alone is not always sufficient in addressing cross-cutting issues such as climate change. The engagement in the dialogue process will continue under options 2 and 4. It is also not clear whether DFID would have the human resources to adequately engage in the dialogue process on climate change under this option, where no additional resources are envisaged. It is also clear from the economics of climate change study (and summarised in the section on context above) the likely impact that climate change will have the economy, therefore a do nothing option will result in negative impacts on Tanzania’s economy, for example losses of 2% per annum of GDP and on the poor and vulnerable who are least able to cope with floods and droughts. / Risk and Assumption / Management risk: No other development partners will step in to lead on climate change for the development partner group. That the impacts are at least partly attributable to DFID not acting. / Option 2: Climate Change Programme Adviser / Total Cost: £680, 000 over 4 years; £170,000 per year / Quantifiable benefits: N/A Non-quantifiable benefits: Large (Coordination and Delivery) / The CC Programme adviser will be a DFID Adviser (HCS) and will focus both on the effective delivery of DFID programme, wider donor co-ordination and providing technical assistance to government. (See Annex 1 for draft terms of reference). The benefits of improved donor coordination include avoided duplication of effort and maximising co-benefits between development partner programmes on climate change incl. DFID’s assistance in this area. This will result in reduced transaction costs through joint programming and leveraging of additional finance, which at minimum is estimated to be in the order of £200-400,000 directly related to the post. However it will impact on the effectiveness of the USD 50m (£30m) that is spent annually by development partners on climate change. It is not possible to quantify the benefits in economic terms, although they are likely to be significant given the anticipated increase in financial flows on climate financing. In addition, the position will also play a key role in influencing key actors on climate change to improve the likely achievement of the outcomes, this will be significant benefit of the post. / In terms of balance between costs and benefits, the relatively limited funds for the post would provide significant benefits. From an economy perspective, the use of a DFID employee in this role reduces costs, associated with recruitment and is more cost effective than bringing in a long term consultant. It also allows for greater involvement in programme and cross sector engagement (both within DFID and externally). From an efficiency perspective, an adviser would deliver potentially large benefits by mainstreaming both adaptation and mitigation across the broader DFID operational plan, country portfolio and by facilitating other donor support to climate change (through acting as the DPG climate change focal point and membership of the group). / In summary the benefits of the post will be increased leadership and capacity for engagement on climate change both with government, development partners and other stakeholders. This should reduce the transaction costs related to duplication of programming, increased joint programming by development partners on climate change, increase influence and likely achievement of the outcomes, improve lesson learning from best practice and improve delivery of results. / Risk and Assumptions / Management risk: DFID remains the focal point for climate change for the Development Partners Group and other donors are willing to undertake joint programming and work together under a joint framework. / Option 3: Strategic and Flexible Technical Assistance Fund / Total Cost: £1,320,000 over 4 years; approx £330,000 per year / Quantifiable benefits: N/A Non-quantifiable benefits: Large (Access to and effective delivery of climate finance, effective climate change policy and institutions) / A strategic and flexible technical assistance fund to support institutional strengthening in Tanzania on climate change should help position Tanzania to access climate finance and build broader high level ownership of the climate change agenda across government and key sectors. Option 3 enables the implementation of an effective national level policy and financing framework both in mainland and Zanzibar. It envisages targeted support at a national level within sectors and Ministry of Finance and at a sub national level. A list of potential type of outputs that can be expected under the TA fund (refer to table in previous section on resource costs): / National Policy Framework and Capacity / National Climate Change Strategy incl. Zanzibar / National Financing Mechanism linked to strategy, which includes REDD. We envisage a financing mechanism capable of dispersing at least £50m per annum / Support to Ministry of Finance on climate financing incl. establishment of climate desk / Sector Policies and Plans / Climate change action plans and budgets in two key economic sectors such as agriculture / Green Growth strategy for SAGCOT / Aid Effectiveness and Climate Smart Aid / Establishment of Climate Change Secretariat for the Development Partner Group for Environment / Climate Screening of General Budget Support and GoT budget incl. Public expenditure review on climate change (with World Bank) / Monitoring and evaluation of DFID climate change interventions to assess impact and build evidence base / Effective delivery at district level / Piloting support to district level for results/performance based financing for channelling climate funds sub-nationally focus on REDD and adaptation / Given the institutional nature of the technical assistance fund, it is difficult to quantify potential benefits in economic terms and in particular to what extent institutional strengthening can be directly attributed to the fund. It is estimated that the TA fund will leverage other donor finance directly to contribute to undertaking specific pieces of work of at least £500,000 but up to £30m. The broad range reflects the opportunistic nature of the fund, it will respond to priorities/demands and be both strategic and flexible in its approach, ensuring best value for money, wherever possible. (The £24m (USD40m) is the current pledged donor support for pilot work at the district level, which focuses on decentralised natural resource management and climate change.) / The economic scale of these potential benefits maybe derived from the scenarios (climate and economic) as identified in the Tanzania economics of climate change study (GCCAP/SEI, 2011).Option 3 would help unlock the barriers and finance required to deliver resilience funding to meet projected financing needs of $50-75m per annum for immediate priorities and needs rising to $500m pa by 2030.[19] The outputs would provide the necessary conditions to access funds through UNFCCC, Climate Investment Funds, Adaptation Fund and other merging mechanisms. This funding is important to reduce projected impacts of climate change from 2% of GDP by 2030. / Option 3 also enables improved funding strategies to capture the 20% of negative and low cost emissions reductions identified in the economics report[20]. Such finance would help overcome barriers relating to capital intensity that are currently preventing such measures from being implemented. (This is assuming low carbon is prioritised as part of the national climate change strategy.) / In summary, Option 3 provides a strong balance of benefits against costs, and a flexible and strategic approach will reflect the likely capacity of GoT to absorb technical assistance over a 4 year period. / Risk and Assumptions / Management risk: Limited human resources and capacity in DFID and with other development partners to deliver the outputs under the TA fund effectively. Duplication of activities if not managed effectively. / Political risk: The benefits identified assume that there is political commitment and leadership on climate change, particularly from a high level and in the Ministry of Finance. It also assumes political and economic stability that will not destabilise the climate change institutional development and funding mechanism. It assumes that GoT is able to absorb the envisaged economic and technical capacity, and that there is continued momentum to pursue the climate change agenda. / Option 4: Strategic and Flexible Technical Assistance Fund / Total Cost: £2,000,000 over 4 years; approx £500,000 per year / Quantifiable benefits: N/A Non-quantifiable benefits: Very Large ((Access to and effective delivery of climate finance, effective CC policy and institutions, coordination and effective implementation) / The anticipated benefits of this option will be those delivered under both option 1 and 2. It is expected that there will be significant additional benefits of combining these two options such as effective management of the technical assistance fund and ensuring that it levers additional finance and reduces transaction costs through co-financing with other donors. There is a need to ensure that any technical assistance fund is managed effectively and has appropriate technical oversight. This will be addressed through a dedicated CC programme adviser. / It is anticipated that the probability of the risks associated with the technical assistance fund will be substantially reduced with the CC programme adviser in post, as there will be sufficient resources to ensure the effective implementation of the proposed outputs and activities. / There is also some evidence from other sectors that programme funded advisers can be more effective and influential if they are part of programme implementation or have technical assistance fund that is flexible and responsive to needs and demands. / |Summary Table of Key Outputs and How Option 4 will contribute to their delivery / Potential Outputs Option 4 – TA fund and CC Adviser / National Policy Framework and Capacity / National Climate Change Strategy incl. Zanzibar / National Financing Mechanism linked to strategy, which includes REDD. We envisage a financing mechanism capable of dispersing at least £50m per annum / Support to Ministry of Finance on climate financing incl. establishment of climate desk Options 4 will ensure that the support is not duplicating efforts i.e. on the financing mechanism. It will also enable greater coherence, co-financing and reduce transaction costs. It is likely that both the national strategy and the financing mechanism will be delivered through an MoU with development partners or contracted directly through the resource centre. / This output will contribute significantly to accessing international climate finance and unlocking national level benefits outlined below. / Sector Policies and Plans / Climate change action plans and budgets in two key economic sectors such as agriculture / Green Growth strategy for SAGCOT Option 4 will ensure these outputs are managed effectively in what is a complex environment of multiple actors, when working across sectors and also public private partnerships such as SAGCOT. It will also leverage additional finance / This output will contribute to ensuring that climate funds are planned and budgeted for at the sector level. It is also anticipated that this will ensure more effectively delivery in key vulnerable sectors and contribute to unlocking national benefits outlined below. / Aid Effectiveness and Climate Smart Aid / Establishment of Climate Change Secretariat for the Development Partner Group for Environment / Climate Screening of General Budget Support and GoT budget incl. Public expenditure review on climate change / Development Partner framework for joint climate change support / Monitoring and evaluation of DFID climate change interventions to assess impact and build evidence base Option 4 will considerably contribute to improving the effectiveness of climate change spend by developing a joint framework and finance mechanism for donor support on climate change. It is unlikely that this will be fully developed in the life of the project but significant steps will be made in this direction. Development spend will be climate smart. / The impact of this will be a reduction in transaction cost, leveraging of additional finance and more joint programming on CC. Also there will be an improved evidence base on what works in tackling climate change. / Effective delivery at district level / Piloting support to district level for results/performance based financing for channelling climate funds sub-nationally focus on REDD and adaptation Option 4 will contribute to more effectively delivery of climate finance at the local level through piloting performance based financing. / As there are over 7 donors interested in providing support to districts on NRM and CC, the role of the CC adviser will be critical to ensuring the TA funds are effectively spent in this area. / In summary it is expected that Option 4 will increase the level of influence and the likelihood of the outcomes and impact being achieved as well as manage some of the risks associated with both Option 2/3. / Outlined below is a summary of some of the potential benefits and economic justification for Option 4. / Unlocking national level benefits: Given the institutional focus of Option 4, much of the economic justification derives from the programmes ability to unlock finance and remove barriers to deliver resilience and low carbon ambitions. The benefits flowing from national level capacity building and institutional reform cannot however be attributed directly to the intervention as it is one of a number of initiatives engaged in this area (refer to section on context). From an adaptation/resilience perspective, the economics report identifies the current costs of climate change at 1.0% of GDP, rising to 2% of GDP by 2030. The report indicates that current financing requirements for resilience and no regret adaptation are $500m pa including social protection and accelerated development, rising to between $1bln per annum in 2030[21]. Undertaking the activities proposed under option 4 would allow the country to unlock finance and remove current barriers to effective and large scale adaptation finance. It can also provide support to target the most cost effective measures within a chosen sector, by supporting national level assessment of the costs and benefits of individual options for vulnerable sectors. From a low carbon perspective, the economics of climate change report indicates that 20% of Business as usual (BAU) emissions may be avoided at negative or low cost. Strengthened institutions and finance mechanisms resulting from higher levels of capacity can unlock this potential through policy reform and increased capital investment, to ensure that these benefits are captured. / Cost-benefit Analysis: Net Present Value, Internal Rate of Return and Cost Benefit Analysis. / Given the focus upon enabling environment and the short project timescales, there has been limited scope to use NPV type calculations. Rather, we have used proxy assumptions on Benefit Cost Ratio (BCR) to model an expected outcome based on a given amount of spend and effective programming. / Break-even analysis for Option 4 [22] / The overall benefits of the optimal intervention can be considered quantitatively in two main ways. First, at the highest level, Tanzania accessing climate finance and delivering better policies and programmes will reduce the potential loss of GDP as a result of climate change. In this context, although it is not possible to estimate the scale of this impact it is possible to illustrate the GDP benefits required to justify the proposed investment of £2 million. If it is assumed (conservatively) that GDP losses without the programme would otherwise average 0.5% of GDP a year ($75 million p.a. at current prices) the programme would break even over a five year period (with a net present value of greater than zero at a 10% discount rate) if it succeeded in reducing this loss figure by just less than 2%. Although clearly GDP loss will be averted by a range of interventions working together, the contribution required to justify this specific intervention is a small one. / In a second calculation more closely aligned with the immediate objectives of the programme, aggregate benefits can be measured in terms of the programme’s impact on the efficiency of climate change and environment spending (as a result of increased climate finance and better policies and programmes being put in place). In this way if it is assumed the international climate finance available to Tanzania grows from $50 million at present to $300 million by 2015 and then stays at this level the programme would break even over a ten year period (with a net present value of greater than zero at a 10% discount rate) provided it helped increase the efficiency of spending by just less than £1.5m (0.5%). This is a modest efficiency gain to achieve. The calculation takes no account of the fact that in practice the programme will have benefits not just in terms of the efficiency of spending but also in terms of the actual scale of international finance Tanzania is able to access. / Risks and Assumptions (refer to Management Case and Risk Assessment) / Management risk: DFID remains the focal point for climate change for the Development Partners Group and other donors are willing to undertake joint programming and work together under a joint framework. / Political risk: The benefits identified assume that there is political commitment and leadership on climate change, particularly from a high level and in the Ministry of Finance. It also assumes political and economic stability that will not destabilise the climate change institutional development and funding mechanism. It assumes that GoT is able to absorb the envisaged economic and technical capacity, and that there is continued momentum to pursue the climate change agenda. / No additional risks and assumptions to those already outlined in option 2 and 3. It is expected that the risks are likely to be substantially reduced such as those associated with duplication of activities under the technical assistance fund and its effective management by combining the two options under Option 4, which are complementary.
D. Comparison of options / The following table weights the various options set out in C in terms of their contribution to the Critical Success Factors (1=Low, 5=High). They incorporate implicit information about VFM considerations in relation to how likely they are to contribute to CSCs per £spend. / Analysis of Options Against Critical Success Criteria (CSC) / Option 1 Option 2 Option 3 Option 4 / CSC Weight / (1-5) Score / (1-5) Weighted Score Score / (1-5) Weighted Score Score / (1-5) Weighted Score Score / (1-5) Weighted Score / 1 institutional strengthening 5 0 0 3 15 5 25 5 25 / 2 financing and delivery 5 0 0 2 10 4 20 5 25 / 3 aid effectiveness 3 0 0 5 15 1 3 5 15 / Totals 0 50 48 65 / Based on the analysis outlined in section c and the table above it is clear that Option 4 is the optimal intervention and will contribute most effectively to delivering the impact and the outcome. / Theory of Change / The following diagram sets out theory of change for the DFID Tanzania climate change programme of which this intervention on institutional strengthening is one critical component not only in achieving the theory of change but also providing overall oversight through the Climate Change adviser and an M&E framework ( output 4). See diagram below for details: / DFID will support implementation of the institutional strengthening programme to help achieve impacts and outcomes set out in the logframe. The DFID programme outputs are fully consistent with the DFID Tanzania Operational Plan. / There is “medium” evidence that the intervention will contribute to the achievement of the Purpose (outcomes) and Goal (impact). However, implementing development programmes on climate change is a new area of work, therefore the overall evidence base is relatively weak and therefore has risks. The theory of change for the institutional strengthening intervention (and the DFID climate change programme) depends on a number of critical assumptions, which are outlined in the log frame. / Final Climate and Environment Category - A / This intervention specifically addresses climate change and the environment, in terms of DFID’s categorisation of environmental and climate change effects, it can be rated as a high potential opportunity, a category A project; though in terms of risks these would be rated as C. Therefore no additional action is required. The benefits and expected results of the intervention, which have direct impact on climate change, have been outlined in detail above. / Civil Society / Climate Change / and Environment Fund / Government / Institutional Strengthening / Programme / (CC Adviser &TA fund) / Strengthen TZN position in climate negotiations / Increased access to low cost, clean energy / Increased resilience to climate change of Tanzanian economy and people / Private Sector / AECF Renewable Energy and Adaptive Climate Technologies Catalytic Fund / Tanzania is climate resilient and maximises low carbon opportunities for growth and development incl. MDGs / Greater accountability on climate finance, policy and delivery / National framework for CC – national, sector and local priorities / Increased international and bilateral climate finance / Increased donor co-ordination and joint programming / Effective delivery at local level of climate adaptation and renewable energy / Increased investment in climate adaptation and renewable energy / Innovation and access to technology / Monitoring and Evaluation Framework / Climate Change Adviser / Theory of Change for the DFID Tanzania Climate Change Programme
E. Measures to be used or developed to assess value for money / In summary the programme will deliver value for money by: / using the least cost delivery mechanism such as resource centre or direct procurement; / maximising the resources under the technical assistance fund by leveraging additional finance; / exploiting existing arrangements to minimise start up time e.g. indirect procurement through other bilateral and multi-laterals such as DANIDA and World Bank; / leveraging funding from other development partners; / reducing transaction costs in a pooled funding arrangement for development partners; / piloting performance based payments for delivery of climate finance; and / achieving significant returns from its impact on climate change resilience, the more sustainable use of natural resources, and Tanzania’s access to international climate change financing. / Value for money will be monitored and assessed during implementation through a combination of measures that include log-frame targets, programme management costs, and the detailed objectives set out in the terms of reference for contracting under the technical assistance fund. / There are a number of methodological challenges in terms of undertaking a VFM assessment for climate change programme that focuses on institutional strengthening; these challenges are outlined below and addressed in section D of the management case on monitoring and evaluation. / 1. Focus on Capacity Building: / The programme has a key focus on capacity building and strengthening policies and the enabling environment as a precursor to larger public and private sector investor flows into Tanzania. The evidence indicates that climate resilient and low carbon growth require strong basis of institutional and social learning to cope with a wide range of contingencies. . A number of large benefits flow from the programme in terms of increased capacity to deal with climate change policy design, implementation and delivering improvements in the enabling environment. However, these benefits are difficult to quantify, and almost impossible in a formal Cost Benefit Analysis (CBA) framework. Likewise, it is difficult to compare the cost effectiveness of potentially intangible benefits to allow for the preference of one option over another. Even where the benefits of institutional development can be quantified, they are difficult to attribute to the intervention given that it is one of a number of national and international programmes targeting improved climate change institutions and enabling environment. It is likely that institutional development and improved policy would support the implementation of negative and low cost mitigation options by removing barriers to implementation and encouraging international finance to overcome capital costs. It would also support the identification and delivery of no regret adaptation investments. It is not recommended that the programme try to quantify or attribute these benefits. / 2. Benefits accrue after programme conclusion: / Where there are direct investments in mitigation or resilience activities, the benefits of these interventions flow over a number of years in terms of avoided impacts of climate change, and in terms of accruing benefits of avoided GHG emissions. Even where benefits are identified and measured during the lifetime of the project, these are likely to be limited. There is no guidance as to over what timescales these benefits should be measured (e.g. technology life, 10 years), and what discount rates should be used (social discount rate for adaptation, private sector for mitigation?). / 3. Complexity of assessing economic and climate resilience benefits at project level: / The SEI/GCCAP economics study used macro modelling to identify whose potential impacts of climate change. Future climate change would lead to additional and potentially very large economic costs. These are uncertain. However, aggregate models indicate additional net economic costs (on top of existing climate variability) could be equivalent to a loss of almost 2% of GDP each year by 2030 in Tanzania. Assessing these at project level is relatively uncertain. It involves both an assessment of the avoided losses at household or community level. For this reason, the analysis has assumed an implied Benefit Cost Ratio of 2:1 based on existing Cost Benefit Analysis (CBA) studies for adaptation type engagements in sub-Saharan Africa in the agricultural sector.[23] Where benefits have been derived from mainstreaming resilience into wider development programmes, rather than channelling direct funds into projects, then an incremental net increase in the BCR of 0.1 is assumed, based on the existing net economic benefits of the interventions. / 4. Complexity of assessing economic co-benefits: / Both low carbon and resilience interventions are likely to have co-benefits for wider development that are poorly captured in the economic modelling through a carbon price or avoided losses.
[16] Political Economy of Climate Change in Tanzania, 2010
[17] Page xiii, Joint Irish Aid and DFID Country programme evaluation Tanzania 2004/05 to 2009/10, ITAD, 2011
[18] ibid
[19] Pg 59, URT Economics of climate change study, 2011
[20] Pg 103, URT Economics of climate change study, 2011
[21] Pg 59, URT Economics of climate change study, 2011
[22] This analysis is intended to show the minimum impact that the programme requires to justify the investment of £4.2 million. There are two calculations. The first looks at the minimum impact that is required in reducing GDP losses from climate change. The second looks at the minimum impact that is required on the efficiency of climate change and environment expenditure from better policies and programmes. Both calculations use conservative assumptions. Both use a ten year investment period in which costs are incurred up front and benefits accrue from year 3 to year 10. Both use a discount rate of 10%. The GDP calculation assumes that without the programme GDP losses from climate change will be 0.5% of GDP (in practice the evidence suggests they will be much higher than this). The climate finance calculation assumes that international climate change expenditure grows from $50 million p.a. now to $300 million by 2015 (as projected in the programme log-frame). Both calculations show that the programme only has to have a very small impact to be justified.
[23] Further details are provided in Annex 2

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Intervention Procurement Type Procurement Method / Targeted Technical Assistance to support Institutional Strengthening for GoT Direct Long and short term TA procured through existing Resource Centre framework contract or through direct procurement / Indirect (alternative) Joint funding with other development partners bilateral such as Denmark and Norway or multi-laterals such as the World Bank will be on the basis of an Memorandum of Understanding (MoU), where their procurement procedures will apply incl. OJEU / DFID CC Programme Adviser None DFID Home Civil Servant
B. How does the intervention design use competition to drive commercial advantage for DFID? / The Resource Centre framework contract, managed by Procurement Group in UK, has been awarded through a competitive procurement process to ensure value for money. By utilising this existing framework contract for the TA requirements of the institutional strengthening programme, DFID will benefit from this procurement process, the economies of scale already negotiated on TA fee rates and administration, and the rapid mobilisation of TA without further procurement delays. The Resource Centre arrangements allow for member firms to submit alternative CVs and fee rates, thereby driving down costs through internal competition.
C. How do we expect the market place will respond to this opportunity? / There are sufficient firms (at least 3) with relevant expertise, presence in the East African region, and capacity for additional work to respond actively to the opportunities subject to competitive procurement.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / Key Cost driver How is value added How to measure & improve / Technical assistance: consultancy fee rates and expenses & productive efficiency of consultants in line with DFID’s guidance on strengthening vfm e.g. use of economy flights Quality of CC design work undertaken and extent to which CC institutional framework is adopted and implemented by GoT Quality assurance of TA delivery by DFID Tanzania Sustainable Growth Team Deputy Programme Manager and Climate Change Adviser
E. What is the intended Procurement Process to support contract award? / All key procurement processes for direct procurement have already taken place (Resource Centre) to accepted DFID standards, which will greatly enhance start-up time for delivery, essential for a flexible and responsive technical assistance fund. Where suitable technical assistance can not be identified by the resource centre and it is more cost effective to contract someone locally to do the work, then consultants will be procured directly by the local procurement unit in DFID Tanzania office.
F. How will contract & supplier performance be managed through the life of the intervention? / Contract and supplier performance will be managed through existing established mechanisms for already procured providers, including Procurement Group for resource centre and DFID Tanzania procurement unit for local direct contracts. Additional oversight from the DFID Tanzania Sustainable Growth Team Deputy Programme Manager, with technical quality assurance from the Climate Change Adviser, who will quality assure delivery and hold suppliers to account for performance.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / Indirect procurement will be utilised where another development partner already has established management and/or contractual arrangements in place and DFID has a proven track record of value for money cooperation with other donors, for example Denmark and World Bank. The recommendations on procurement under the Multi-lateral Aid Review for specific organisations will be considered in decisions to go into indirect procurement arrangements with development partners. Indirect procurement will be considered under technical assistance fund for the following interventions, where other development partners are providing co-financing or taking the lead: / National Climate Change Strategy incl. Zanzibar (with World Bank and Finland) / Scoping of National Financing Mechanism linked to REDD (with Norway) / Develop climate change action plans and budgets in two key economic sectors (with World Bank) / SAGCOT climate change/green growth strategy (with Norway) / Development Partner Group for Environment and Climate Change Secretariat (with Denmark) / Climate Screening of General Budget Support and GoT budget incl. Public expenditure review on climate change (with World Bank) / Piloting support to district level for results/performance based financing for channelling climate funds sub-nationally focus on NRM, REDD and adaptation. (Norway, Finland, Denmark and Belgium)
B. Value for money through procurement / The bilateral and multilateral partners through whom institutional strengthening funds are channelled for indirect procurement have a strong performance focus, and have requirements for value for money delivery by implementing agents. DFID will have the opportunity to influence procurement as follows: / negotiation of MoU agreement with World Bank and other bi-laterals to ensure VFM is explicitly included with specific requirements to track and measure vfm; / development of the term of reference for the work ensuring vfm is addressed; / participation in selection of programme implementation agent (subject to agreement in MoU) / quality assurance on outputs and sign off on final output and payment; / tranche payments (subject to agreement in MoU) will be made on the basis of outputs and deliverables; / results / performance based payments will be used where appropriate e.g. pilots in districts. / In addition, the DFID Tanzania Sustainable Growth Team Deputy Programme Manager, with technical oversight and quality assurance from the DFID Climate Change Adviser will be able to monitor implementation of indirectly procured services and take remedial action where required.

Financial Case

A. How much it will cost / The total budget for Tanzania Climate Change Institutional Strengthening Programme is £2m over 4 years, comprised as follows: / Intervention/Inputs Budget £m (Yr1 – 11/12) Budget £m (Yr2 – 12/13) Budget £m (Yr3 – 13/14) Budget £m (Yr4 – 14/15) Total / Technical Assistance Fund and CC Programme Adviser 390,000 470,000 470,000 470,000 1,800,000 / M&E 40,000 25,000 25,000 110,000 200,000 / Total Budget 430,000 495,000 495,000 580,000 2,000,000
B. How it will be funded: capital/programme/admin / The full amount will be drawn from the DFID Tanzania programme resource allocation for climate change as outlined in the DFID Tanzania Operational Plan.
C. How funds will be paid out / DFID will enter into contracts and MoUs with certain donors and consultants (implementing partners). Funding tranches will be agreed with each implementing partner separately. The DFID Tanzania Sustainable Growth Team Deputy Programme Manager will authorise payments on the basis of key milestones and deliverables.
D. How expenditure will be monitored, reported, and accounted for / The MoUs with the lead agency/Development partner will include DFID’s standard audit arrangements. Audits will be required within six months of the end of the relevant financial year, conducted either by Agency/Development partner’s Audit office or an independent auditor. In the event of an occurrence that might pose a risk or loss to project funds, the MoU will reserve the right for the funding partners to suspend funding, conduct an independent forensic audit and reclaim mis-spent funds. Payment will be made against requests/invoices on the basis of achievement of agreed outputs/milestones from the implementing partner or resource centre. Implementing partners, in the case of MoUs will provide DFID with annual audited statements of account. / Any capital assets procured under this programme will be treated in accordance with DFID procedures, and declared to the DFID Tanzania Sustainable Growth Team Deputy Programme Manager. Should assets remain at the end of the programme a disposal strategy will be agreed with DFID.

Management Case

A. Oversight / Oversight mechanisms are present both for the Climate Change programme adviser and the technical assistance fund. They are as follows: / Terms of reference, attached in Annex 1, agreed by the DFID Tanzania Head of the Sustainable Growth Team Leader will govern the broad objectives of the adviser for the initial 18 months and will be reviewed annually. The terms of reference will be shared with key stakeholders such as government and key development partners. The Sustainable Growth Team Leader will have oversight and line manage the post. / The technical assistance fund will be managed by Sustainable Growth Team Deputy Programme Manager (DPM), with technical oversight by the CC programme adviser. The DPM will be responsible for oversight and management of contracts and MoUs with partners under the technical assistance fund. The Deputy Programme Manager and CC Programme Adviser will be both responsible for overseeing call down of short term technical assistance, programme monitoring and co-ordination and dissemination of lessons. / The objectives for the post and technical assistance fund are aligned with those of Development Partners Group for Environment and Climate Change, as set out in the DPG’s strategic note on climate change priorities for engagement for the short and medium term. Both inputs will ensure that they are steered and contribute to the delivery of these priorities. The development partners will co-finance some of the interventions outlined under the technical assistance fund, so will play an active role in developing the terms of reference, design, implementation and monitoring and evaluation. A key role of the CC programme adviser will be to ensure greater coordination and coherence of the delivery of DP funded climate change interventions, in line with the priorities set out by the group. The DPG will not have a formal oversight role in the management of the post and technical assistance but feedback will be requested from the two co-chairs on a six monthly basis. / The Government of Tanzania is a key counterpart for this programme, both at national, sectoral and local level. There will be multiple stakeholders who will be engaged depending on the nature of the specific intervention, rather than one coordinating point of reference within GoT. GoT parties will include VPO, Planning Commission, Ministry of Finance, Agriculture, Water and district authorities. They will be engaged from the outset in developing the terms of reference, design, implementation and monitoring and evaluation. The GoT will have a formal oversight function, where appropriate, for some of the technical assistance provided and will be asked for feedback on the CC adviser post on a six monthly basis. / Non-state actors though not directly involved n the delivery of this programme will also be consulted and involved in key aspects of design and implementation e.g. with the development to national policies and strategies and their implementation at sector and district level.
B. Management / The CC programme adviser will be a DFID A2 member of staff with a proven track record of work on climate change, preferably in Africa. They will have a proven ability to work effectively both with development partners and government and experience of delivering institutional strengthening programmes. / The adviser will spend up to 60% of their time working with government and development partners in line with the delivery of the institutional strengthening programme and other DFID interventions on climate change through non-state actors such as civil society and private sector. The remaining 40% of the advisers time will be working on complementary work on climate change delivering on DFID Tanzania’s operational plan in areas of social protection and water resources. As well as ensuring that DFID Tanzania’s aid is climate smart. (see terms of reference attached in Annex 1) / By the end of June 2011, during the first 6-8 weeks of the post, the postholder with their line manager will write and agree a full set of objectives and success criteria along with a project work plan. The detailed work plan will be agreed within 3 months. To meet DFID reporting requirements the adviser’s objectives will need to be signed off by the Head of the Sustainable Growth Team, DFID Tanzania and the Head of Profession. The adviser will be included in DFID’s performance management processes (PMF). There will be six monthly formal reviews to discuss progress against work plan and objectives. The effectiveness of the post will be reviewed annually as part of the annual review process including the effectiveness of the technical assistance fund. Also there will be an opportunity to review the post holders performance in the post on a six monthly and annual basis. If DFID Tanzania do not ascertain that the post holder is having a positive impact and fulfilling the terms of reference, there is an opportunity to re-advertise after 18 months. The adviser will also be expected to form part of the DFID Tanzania advisory group. / The DFID Tanzania office will be responsible for logistics associated with the post such as accommodation, medical and travel. The adviser will follow government/DFID guidelines on ensuring value for money on spend e.g. researching best value options for travel or accommodation. / The CC programme adviser and the DFID Tanzania Sustainable Growth Team Deputy Programme Manager will be responsible for leading and managing provision of technical assistance to the GoT. The adviser will be responsible for overseeing co-ordination of development partners with GoT climate change programming, acting as the focal point for the Development Partners Group. The effectiveness of the technical assistance fund will be reviewed on a six monthly basis alongside the review of the CC programme advisers performance. As part of the annual review Development Partner Group will be consulted to evaluate the effectiveness of the fund, the priorities and focus and whether it should be continued for a further year. The Deputy Programme Manager will monitor spend against forecast on a quarterly basis, based on information provided by project partners.
C. Conditionality / None
D. Monitoring and Evaluation / Evidence Base / DFID Tanzania has had 50% of a climate change adviser over the last 18 months: the post has demonstrated that the CC programme post can be effective both in terms of improving coordination and delivery of climate change by development partners. Similarly DFID Tanzania has a TA fund, which has been successful in leveraging engagement with key stakeholders such as Ministry of Finance. DFID has used programme funded advisers in a wide range of sectors e.g. health and education and there is guidance, which also builds on the experience of secondments. This is equally relevant for the technical assistance that will be provided to government. There are number of factors[24] which will determine if the programme post and technical assistance is effective: / The partner/host organisation is used to accepting technical assistance and has systems and processes to ensure the post/TA is properly managed, including identifying a clear role and outputs. / The post and technical assistance arise from clear demand from the host/partner, which identifies an area where it wants DFID expertise. / The post and TA are timely and take advantage of clear opportunity to influence such as during a process of policy reform or on new policy objective such as climate change. / Post and TA have clear objectives which are agreed by the host/partner and where the host/partner has an active role in managing to ensure the objectives remain relevant. / Post and TA is strategic and is builds on an understanding of what are the influential parts of the host/partner. / All of these factors have been considered and would apply in establishing the climate change post and technical assistance fund. However climate change is a new area of work and engagement and the overall evidence base is quite weak despite the efforts made over the past two years by DFID Tanzania and other development partners. / The climate change institutional strengthening programme will be implemented over 4 years, which is a relatively short timeframe for institutional change to translate into significant impact on the ground and in building resilience of the poor and vulnerable and on the delivery of MDGs. Nonetheless, the process by which each output will contribute to the impact has been carefully considered and milestones have been developed so that it will be possible to judge with some confidence in four years time whether the projected quantitative targets for outcomes in terms of number of poor people better able to cope with the effects of climate change have been achieved. However this requires the development of M&E framework in the first year of the project, which will also set out the questions for the independent evaluation, set out in output 4 of the logical framework. / Monitoring Strategy / As climate change programming is new in DFID it will need to be managed and monitored carefully to ensure it delivers the expected results. The results chain logic and broad M&E framework is set out below. As this is a new and ambitious programme, it is proposed that a more detailed M&E framework is developed in the first year to clearly outline the data requirements, data sources and how the data will be obtained and monitored at the start of the project (baseline) and during (milestones) and the end of the project (targets). This will be part of a broader framework for monitoring and evaluation of climate change for government and development partners under output 4, which will not only be useful for this intervention but also other Climate Change interventions supported by DFID Tanzania in it’s operational plan. / Results Chain E / V / A / L / U / A / T / I / O / N Sources of Data Frequency / Impact DFID Annual Report. One point for MDGs achieved or on track (“green”) and half a point for MDGs that have showed some progress (“amber”). Baseline to be set once 2010/11 released. / Development partner reports, analysis of government district and national strategies and reports. M&E framework for national CC strategy. Independent project evaluation. Annual / Annual for strategy / End of programme / Tanzania is better able to achieve its MDGs through improved management of climate change risks and opportunities. / Outcome Baseline drawn from study for Development Partner Group on Environment and Climate Change: Climate Change Support in Tanzania, Mapping of current and future climate change interventions. To be repeated. (www.climatefundsupdate.org). Annual / End of programme / Tanzania accesses climate finance and uses it effectively to support climate change resilience and low carbon sustainable growth / Outputs M / O / N / I / T / O / R / I / N / G Reporting on National Climate Change strategy. GoT budget annual budget reports. / PER on climate change. / Development Partner Annual Reviews of Decentralised Natural Resource Management and CC partnerships based on M&E framework. / Reports from districts, VPO and PMO-RALG on progress. Annual / Quarterly / 1 Comprehensive climate change strategy in place incl. adaptation and low carbon, with budget allocation and being effectively delivered at sector and district level / 2 GoT and development partner investments and expenditure is climate smart Baseline to be drawn from study for Development Partner Group on Environment and Climate Change: Climate Change Support in Tanzania, DFID screening of portfolio in 2010 excl. budget support. To be repeated. Screening undertaken by other development partners. / Public Expenditure Review on climate change. GoT budgets and expenditure. PETs on climate change funds. Report on climate screening of GoT budget. / SAGCOT Green Growth Strategy. Sector strategies, plans and budgets ( agriculture, water and energy/transport) Annual / (and every 4 years as part of country plan) / 3 Improved aid effectiveness through a comprehensive framework for development partner support in Tanzania on climate change Development partner reports, analysis of government district and national strategies and reports. M&E framework for national CC strategy. Independent project evaluation. Annual / 4 Effective monitoring and evaluation framework for climate change strategy and interventions by government and development partners. M&E Framework for climate change developed in first year. All DFID interventions on CC are evaluated to assess their impact and build evidence for future work of DFID and other DPs. Independent evaluation at end of programme. Six monthly and Annual reviews / Activities PMFs and DP progress reports / DFID Financial forecasts and reporting Six monthly and annual / Monthly and quarterly / Detailed Workplan / ToRs for TA and M&E / Inputs / Technical Assistance Fund / CC Programme Adviser / The CC programme adviser will set out in detail objectives and a work plan within the first six weeks for the post and technical assistance fund. This will be aligned with the logical framework, to show how their work contributes to each output. They will produce a six monthly assessment of progress against the work plan and objectives/success criteria in line with their performance assessment framework (PMF). There will be formal annual reviews of the CC programme adviser and the technical assistance fund which will assess progress. To supplement this, data will also be used from development partners group quarterly and annual reports on progress in the sector and information on climate finance flows (www.climatefundsupdate.org). DFID will undertake an annual review based on discussion with government and other key stakeholders focusing on progress in the sector and Tanzania’s position in relation to climate finance. / Evaluation Plan / As stated above, in the first year a plan for developing an M&E framework on climate change in Tanzania will be established, including a methodology for how outcome indicators will be measured and assessed. The baseline information for the logical framework and an evaluation at the end of the four year period, will be identified and collected in the first year. An evaluation is critical, as this is a new area of work and it will contribute to building the evidence base for future engagement by government and development partners. A separate output (4) has been included focused on ensuring a robust monitoring and evaluation framework for climate change is developed including delivery of this intervention but also the other work on climate change currently programmed under the DFID Tanzania Operational Plan. This will also set out how to monitor and evaluate a crosscutting issue such as climate change. The evaluation will specifically focus on the following questions: / What outputs have been produced as a result of the CC programme adviser and technical assistance fund? Have they been integrated by government into their policy process or carried out separately? / What was the wider impact of the adviser and fund on GoT and other development partners? Has the intervention achieved its proposed outcome and impact? / Where the measures/data sources for the indicator on resilience appropriate? Was the indicator the right one? Did it capture the impact adequately? / Has the post and technical assistance fund resulted in institutional strengthening in Tanzania on climate change? Is it sustainable? Is there evidence for this? / Is Tanzania better positioned to access climate finance? (working from a baseline of $50m) If not why not? / How could the interventions been made more effective? / Has the post and technical assistance fund resulted in improved donor coordination and more effective delivery on climate change? Are these results directly attributable? / Were the DPG strategic objectives achieved? Were they the right objectives? / Was the assumption correct that by having a climate strategy and climate financing mechanism in place in Tanzania, it would leverage substantial climate finance? / Can results/performance based financing be used for climate finance (at the district level)? Is it effective for delivery? / The results of this evaluation will be used to inform future engagement and programming by GoT and development partners on climate change and will also feed into DFID’s wider work on climate change.
E. Risk Assessment / Risks and assumptions were set out for each of the programme options in the appraisal case, section C. Below are the key strategic risks that will affect the chosen option, measures and mitigating actions are also identified for tackling these risks. The overall risk of the project is judged as medium although the risk will be different for the CC programme adviser and the technical assistance fund. This in part reflects the political context that this predominantly governance intervention will operate. / Corruption risk is minimal. All DFID funds will be managed by DFID or other development partners whose financial and procurement systems we are content meet out standards. / The likely impact and probability of each of the risks is assessed in the table below along with mitigating actions and monitoring mechanism which will be in place. / Risk Description Impact on Success / (L,M,H) Probability of Occurring (L,M,H) Mitigating Actions Monitoring Mechanism / Risk 1 Significant natural disaster or economic crisis will undermine results, remove gains or impede progress. High Medium Programme focuses on building resilience to deal with climate shocks and may include support to early warning systems. The support is flexible and responsive to changes in circumstances. WB and IMF reports on the economy. GoT reporting on impact on natural disasters and response required / Risk 2 Financial mismanagement or corruption High Low Funds will be disbursed quarterly or on the basis of deliverables/outputs, in arrears. Funding will be immediately suspended if Annual Independent Audits are late, or there is evidence of corruption Part of DFID monthly/quarterly forecasting and biannual progress reports. Reports on outputs contracted under TA fund / Risk 3 Lack of political will of GoT to implement new polices and focus on institutional strengthening for CC esp. sector and district level High Medium GOT have stated that climate change is an important area of work and a priority / The TA fund will be monitored annually and discontinued if there is a major issue of political will. Minutes from DPG monthly meeting minutes / Follow up political economy study on climate change. / Risk 4 Weak capacity in GoT to absorb and manage technical assistance and policy implementation effectively High Medium Core programme focus is institutional strengthening building on political economy study findings. / The CC post holder will monitor this situation and report on it as part of the six monthly reporting to DFID. / The TA fund will be monitored annually and discontinued if there is a major issue of capacity that cannot be adequately addressed by the programme. Part of biannual progress reports and adviser reporting. Minutes from DPG monthly meetings and Env Working group meetings / Risk 5 International climate finance is not forthcoming and legally binding treaty is not favourable to Tanzania Medium Low Tanzania’s engagement in the negotiations and as part of the Africa group will be critical. This will be supported by the programme DPG reports on bilateral and multilateral climate finance / www.climatefundsupdate.org / Risk 6 CC programme adviser lacks skills to implement TA fund and drive coordination / (management) High Low HCS adviser with previous experience of climate change and track record working with stakeholders such as DPs and GoT in Tanzania Previous PMFs / It is anticipated that the probability of the risks associated with the technical assistance fund will be reduced with the CC programme adviser in post, as there will be sufficient resources to ensure the effective implementation of these outputs and activities. A series of mitigating measures are built into the programme design and key risks will be monitored and updated biannually as part of the progress report of the CC programme adviser. / The programme is rated a category A for climate and environment as it has high opportunity and low risk associated with climate change, as it is a core climate change intervention. The management of the opportunities and the risks are core elements of the programme and are incorporated in the outputs, outcome and impact. The project does not require a full environmental impact assessment.
F. Results and Benefits Management / The logical framework for the 4 year period is attached. The milestones and targets will be reviewed after the first year and once the M&E framework outlined in Output 4 is developed.
[24] This builds on a DFID policy framework for secondments, where many of the factors to make this effective would equally apply to programme posts and technical assistance.