PROJECT TITLE	KOLKATA URBAN SERVICES FOR THE POOR (KUSP) PROGRAMME
GOAL	Indicator	Baseline/2004		Dec 2009	Mar 2011	Government of West Bengal (GoWB) is due to publish its next Human Development Report in 2010-11. No intermediate milestones are therefore indicated. However, these can be captured at Annual Review by assessing improvement in access to health services, access to education, and improvement in income generation as proxy indicators.
Reduced Poverty in West Bengal	Human development index	0.61			0.7
		Source
		West Bengal Human Development Report, Government of West Bengal (GoWB)
	Indicator	Baseline/2004		Dec 2009	Mar 2011
	Proportion of urban poor population	KMA – 17 / Non-KMA – 35		KMA – 13.5 / Non-KMA – 31	KMA – 12 / Non-KMA – 27
		Source
		State Urban Development Authority Household Survey (2004, 2011) & KUSP Household Survey (2009-10)
	Indicator	Baseline/2004		Dec 2009	Mar 2011
	Proportion of the poor, disaggregated by social groups, reporting improvement in livelihood opportunities and security of tenure.	Not Available		Livelihood – 20 / Tenure – 5	Livelihood – 40 / Tenure – 20
		Source
		KUSP Household Survey, 2009-10; KUSP Social Audit, 2009-10; KUSP Impact Assessment Study, 2011

PURPOSE	Indicator	Baseline/2004		Dec 2009	Mar 2011	Assumptions
Improved Quality of Life for 2.4 million poor people in target slums of Kolkata Metropolitan Area (KMA)	Proportion of poor reporting satisfaction on inclusion of their ‘voice’ in urban local body (ULB) decision making and functioning	Not Available		50	70	Political support for sustained poverty reduction and land tenure reforms continues to be favourable and policy regime remains stable / Effective leadership continues at KUSP / GoWB/ULBs support citizens’ feedback and social audit mechanisms / Expenditure indicator serves as a proxy indicator for income indicator.
		Source
		Citizen Report Card 2009-10; KUSP Impact Assessment Study, 2011
	Indicator	Baseline/2004	2008	Dec 2009	Mar 2011
	Proportion of target slum dwellers reporting improvement in access and coverage to basic services disaggregated by social groups	Not Available	37	60	80
		Source
		Citizen Report Card 2007-08; Citizen Report Card 2009-10; KUSP Household Survey, 2009-10; KUSP Impact Assessment Study, 2011
	Indicator	Baseline/2004		Dec 2009	Mar 2011
	Household expenditure	(awaiting inputs from KUSP)		+15% from baseline	+25% from baseline
		Source
		KUSP Household Survey, 2009-10; KUSP Impact Assessment Study, 2011
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	102.1	-	-	102.1	100
INPUTS (HR)	DFID (FTEs)
	0.65 FTEs / Urban Advisor – 0.25 / Economic Advisor – 0.10 / Social Development Advisor – 0.05 / Project Officer (B2) – 0.15 / Deputy Program Manager – (WB) 0.05 / Project Officer WB (C1) – 0.05

OUTPUT 1	Indicator	Baseline/2006-07	Dec 2008	Dec 2009	Mar 2011	Assumptions
Improved Urban Planning and Governance in KMA urban local bodies (ULBs)	Aggregated own source revenue collection of KMA ULBs (Rs. Lakh)	18,654	22,385 (20%)[1]	25,183 (35%)	27,981 (50%)	Sustained political will for decentralisation / Effective coordination with concerned line ministries and support organisations. / Capacities are effectively built at the ULB level to effectively undertake a poverty mainstreamed development agenda
		Source
		Municipal Affairs Department, GoWB
	Indicator	Baseline/2004		Dec 2009	Mar 2011
	Number of ULBs in which e-governance system fully opertionalised with satisfied slum customers	E-governance: 0 / Satisfaction levels: N.A.		E-governance: 41 KMA / Satisfaction levels: 60	E-governance: 41 KMA + 5 non-KMA / Satisfaction levels: 85
		Source
		Annual Reports, Change Management Unit (CMU) KUSP, GoWB; Citizen Report Card 2009-10; KUSP Impact Assessment Study 2011
IMPACT WEIGHTING	Indicator	Baseline/2004		Dec 2009	Mar 2011
40%	Proportion of ULB expenditure spent on pro-poor service delivery and related operation and maintenance (O&M) and proportion of O&M costs met through own sources of revenue	Not Available	Spend: 15 / O&M: N.A.	Spend: 25 / O&M: 55	Spend: 25 / O&M: 70
		Source				RISK RATING
		Municipal Affairs & Urban Development Department, GoWB; Annual Reports of ULBs				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)
[1] Figures in parentheses denote percentage increase from baseline.

OUTPUT 2	Indicator	Baseline/2004	Dec 2008	Mar 2010	Mar 2011	Assumptions
Improved access to urban basic services in target slums and convergence with national programmes	Number of poor getting access to basic services, and proportion of satisfaction of O&M	0 / Satisfaction: / Water – N.A. / Drainage – N.A. / Sanitation – N.A. / Roads – N.A.	0.5 million / Satisfaction: / Water – 45% / Drainage – 23% / Sanitation – 26% / Roads – 40%	1.0 million / Satisfaction: / Water – 65% / Drainage – 55% / Sanitation – 55% / Roads – 65%	2.4 million / Satisfaction: / Water – 80% / Drainage – 80% / Sanitation – 80% / Roads – 80%	KUSP guidelines are effectively in place to institutionalise programme process decision making / ULBs/GoWB willing to address issues of land tenure and services provision targeting informal settlements / Positive ULB-civil society interactions towards achieving KUSP reform agenda
		Source
		Citizen Report Card 2007-08; Citizen Report Card 2009-10; KUSP Impact Assessment Study 2011
	Indicator	Baseline/2004		Dec 2009	Mar 2011
	Number of households taken out of poverty through coordinated Mission approach	N.A.		3,000	7,000

		West Bengal Urban Poverty Eradication Mission (WBUPEM) Annual Reports
IMPACT WEIGHTING	Indicator	Baseline/2004	Dec 2008	Dec 2009	Mar 2011
40%	Proportion of target slum dwellers reporting Honorary Health Workers (HHW) as first point of contact for RCH and immunization purposes	Not Available	65	75	90
		Source				RISK RATING
		Annual Reports, Change Management Unit, KUSP, GoWB; KUSP Household Survey 2009-10; KUSP Impact Assessment Study 2011				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Indicator	Baseline/2004	Dec 2008	Dec 2009	Mar 2011	Assumptions
Economic Development Promoted	Number of poor accessing Innovative/Challenge Fund (I/CF) whose income have increased	0	75,000	100,000	150,000	Ownership of LED initiatives by ULBs / GoWB is committed to livelihood and economic development of the poor
		Source
		I/CF Fund Managers, KUSP
	Indicator	Baseline/2004	Dec 2008	Dec 2009	Mar 2011
	Number of poor youth trained and proportion of these provided work placements	0	Number trained: 800 / Placement: 75	Number trained: 1800 / Placement: 80	Number trained: 3000 / Placement: 80
		Source
		Livelihood Promotion Agency, CMU
IMPACT WEIGHTING	Indicator	Baseline/2004	Dec 2008	Dec 2009	Mar 2011
15%	Number of self help groups (SHGs) mobilised and proportion of these linked to banks	SHGs: Not available / Linkages: 0%	SHGs: 17,400 / Linkages: 30%	SHGs: 50,000 / Linkages: 30%	SHGs: 100,000 / Linkages: 30%
		Source				RISK RATING
		Annual Reports, Change Management Unit, KUSP, GoWB; KUSP Social Audit 2009-10; KUSP Impact Assessment Study 2011
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 4	Indicator	Baseline/FY 2008	Sep 2009	Jan 2010	June 2010	Assumptions
Service delivery mechanisms improved in Kolkata Municipal Corporation (KMC)	Property tax demand, coverage ratio and demand collection ratio (DCR)	Demand: Rs. 478.7 crore / Coverage ratio: 65% / DCR: 58%	Demand: Rs. 490 crore / Coverage ratio: 71% / DCR: 72%	Demand: Rs. 500 crore / Coverage ratio: 75% / DCR: 78%	Demand: Rs. 600 crore / Coverage ratio: 78% / Ratio: 84%	Stable political situation allows reform agenda to continue
		Source
		KMC Annual Reports; JNNURM MIS
	Indicator	Baseline/2008	Sep 2009	Jan 2010	May 2010
	Time taken for approval of application for mutation of domestic property	20 days	10 days	7 days	7 days
		Source
		Citizens’ charter/ exit surveys
IMPACT WEIGHTING	Indicator	Baseline/Apr 2008	Sep 2009	Jan 2010	May 2010
5%	Proportion of KMC expenditure on pro-poor service delivery	25%		35%
		Source				RISK RATING
		KMC balance sheet; KMC Annual Report; JNNURM MIS				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)