Intervention Summary
## Title: Low Carbon Support Programme to the Ministry of Finance

What support will the UK provide?
Funding: / The UK Climate Change Unit (UKCCU) will allocate £4.5 million in grant funding from October 2012 to March 2015 into a low carbon development capacity building programme with the Ministry of Finance (MoF).

Why is UK support required?
What need are we trying to address? / Climate change is a global problem, but its impacts will be felt disproportionately by the world’s poorest people. HMG’s vision for low carbon development (LCD) is for all countries to adopt low carbon pathways that improve economic development and reduce poverty by avoiding or reducing emissions. By bringing a 2 degree world closer, long term costs of adaptation will be reduced, and poverty reduction efforts will not be undermined. / Indonesia is centrally important to the world's efforts to mitigating the impact of climate change. Emission reductions will only be politically and economically sustained if Indonesia is able to move onto a low carbon growth path, that generates employment, growth and poverty reduction. To do this, the Government of Indonesia will need to: / undertake a range of policy reforms which will be complex, politically sensitive and difficult to implement; and / support and encourage its increasingly important domestic investment agency to embrace and adopt a low carbon approach into its investment portfolio. / To achieve the twin objectives of economic growth and low-carbon development Indonesia has to restructure its economy while simultaneously building its democracy and eradicating poverty. This is a transition that goes far beyond the scope of conventional structural adjustment programmes. / There is a strong body of evidence from around the world to show that fiscal polices can be both, the most effective driver (eg, via feed-in-tariffs) or the single biggest obstacle (eg, via fossil fuel subsidies) to low-carbon development.[1] Unless Indonesia is able to design and implement a comprehensive and consistent approach to fiscal policy which directly prioritises low carbon development, the prospects for Indonesia being able to break-out of its future “business as usual” emission trajectory is very low.[2] / As well as policies, experience from the UK, Germany, China and other countries has shown that investment funds that can channel public funds to promote public/private co-investment are vital to catalyse and lead investment in low-carbon and clean technology.[3] / What will we do? / The UKCCU will establish a low carbon policy support team in Indonesia’s Ministry of Finance (MoF) to enable: / key policy departments and ministerial advisory teams to design, formulate and implement fiscal policy that will move Indonesia onto a low carbon growth trajectory; and / the Indonesia Investment Agency to establish financing mechanism for delivering sustainable infrastructure and low carbon development in Indonesia. / Why the UK? / The work proposed within this business case builds on two years’ prior support to the Ministry of Finance, which has also included the full-time secondment of a DFID A1 Climate Finance Specialist. This support has delivered relationships and trust between the UK and Indonesia. Past results and the strong relationship have been the catalyst for the request for the broader and deeper assistance on low carbon development contained in this business case. / This programme will directly contribute to the low carbon development objectives in HMG’s current Country Business Plan for Indonesia and forthcoming operational plan (2012/13 to 2014/15). It forms part of the UK’s overall commitment to support low carbon development under the International Climate Fund (2011-2015). A number of the indicators of results (see below) are standard indicators that can be used to aggregate results across all of the UK’s International Climate Fund (ICF) financed programmes.
[1] Leveraging private investment: the role of public sector climate finance, ODI Background Note, Jessica Brown and Michael Jacobs, April 2011.
[2] Indonesia ‘must promote low-carbon economy’, The Jakarta Post – 25 March 2011. http://www.thejakartapost.com/news/2011/03/25/indonesia-%E2%80%98must-promote-low-carbon-economy%E2%80%99.html
[3] See for example the establishment of the Green Investment Bank in the UK, http://www.bis.gov.uk/greeninvestmentbank

What are the expected results?
The key results from this business case will be: / that the Indonesia Investment Authority will have established a credible and effective mechanism to leverage at least $300m of international donor and private finance specifically for low carbon development. / the publication of a Government White Paper on Low Carbon Development and follow-on regulations that will fundamentally change the environment and framework for low carbon investment. / Supporting MoF with technical assistance, capacity building, outreach to wider stakeholders and communications will enable MoF to: / have built sufficient political and stakeholder support to enable it to take forward low carbon policy reform in Indonesia and be able to tackle some of the real barriers to moving to a low carbon pathway such as in energy subsidies and feed-in-tariffs: / We would expect that by the end of UKCCU support, energy subsidies will be at least 20% lower than 2012 levels and fundamental reform feed in tariffs for renewable energy will have been implemented. Both these measures would transform the economics of renewable energy in Indonesia and are critical for Indonesia if it is to hit its policy of increasing renewables from 3% of installed capacity to 17% by 2025.

Strategic Case

A. Context and need for this DFID intervention / The low-carbon challenge / 1. Indonesia is centrally important to the world's efforts to mitigating the impact of climate change. With estimated greenhouse gas emissions of 1.7Gt (billion tons) in 2005, Indonesia is recognised as being amongst the top ten emitters of CO2e. Its emissions, under a “Business as Usual” scenario are projected to grow to 2.95Gt CO2e by 2020. Indonesia has the world’s third largest area of tropical forest (after Brazil and the DR Congo), as well as extensive carbon-rich peat lands.[4] / 2. In a meeting of the United Nations Conference of the Parties (COP) 15 in Copenhagen, December 2009, the President of the Republic of Indonesia committed Indonesia to reducing emissions by 26% below business as usual projections by 2020 (or up to 41% with international assistance). / 3. In Indonesia, emissions from deforestation and land use change are currently greater than those from fossil fuel combustion. But emissions from fossil fuel combustion are growing very rapidly. Among fossil fuels, oil is currently the main contributor of emissions. However, emissions from the use of coal have been the fastest growing for the last decade. The fast rise of coal (which produces more GHG emissions per unit than oil or gas) is attributed to its increasing use in electric power generation.[5] / 4. By 2030 it is estimated that emissions from fossil fuels will be four times higher than at present, thus potentially off-setting any gains made through controlling Indonesia’s forest and peat land destruction. [6] / 5. Indonesia’s National Action Plan on Reducing GHG Emissions (RAN-GRK 2011) estimates that the 26% target on emission reductions amounts to an annual reduction of 0.754Gt CO2e by 2020 over the government’s business as usual projection 2.9Gt CO2e by 2020. / 6. Emission reductions will only be politically and economically sustained if Indonesia is able to move onto a low carbon growth path, that generates employment, growth and poverty reduction. The Government of Indonesia’s current target for economic growth is 6.5% per year for 2012 to 2014. The dual achievement of low carbon growth and emission reduction targets will be a huge challenge. A major part of that challenge is the development of viable alternatives to “business as usual” carbon-intensive investment patterns that can genuinely provide prosperity and employment and are supported by Indonesian decision makers. / 7. Renewable energy will play a huge role in any future low carbon pathway. However, the current investment in real low-carbon sectors falls well short of the sums required to achieve national targets on emission reductions. For example, Indonesia’s investment in clean energy in 2009 was $354 million. Despite enormous potential to generate power from solar, hydro and geothermal, Indonesia’s investment in 2009 was only about 1% of China’s investment, less than 5% of Brazil’s investment and about 15% of India’s investment. [7] / 8. The national target for renewables, currently contributing less than 3% to Indonesia’s current energy mix, is a 17% contribution to the national energy mix by 2025 with 5% of total energy from geothermal power. To put this figure into context, the Indonesian Ministry of Energy and Mineral Resources estimates that power generation requirements in the country will increase from around 36,000 MW in 2009 to as much as 187,000 MW in 2027 – a more than 5-fold increase. To meet the energy mix target, energy from renewables will need to increase from 1,080 MW in 2009 to 37,790 MW by 2027 a more than 36-fold increase.[8] / 9. Alongside renewable energy, tackling emissions from the manufacturing sector will be crucial, particularly those from the non-metallic minerals, textiles, basic metals, and food and beverage industries. / The importance of policy / 10. There is a strong body of evidence from around the world to show that fiscal polices can be both, the most effective driver (eg, via feed-in-tariffs) or the single biggest obstacle (eg, via fossil fuel subsidies) to low-carbon development.[9] Unless Indonesia is able to design and implement a comprehensive and consistent approach to fiscal policy which directly prioritises low carbon development, the prospects for Indonesia being able to break-out of its future “business as usual” emission trajectory is very low.[10] / 11. There have been numerous studies which have identified the key policy areas that need to be reformed in Indonesia so that low carbon development can be successfully developed.[11] Technically the policies are relatively straightforward, they include: / the underpricing of natural resources and the failure to collect environmental revenues / very weak incentives for efficient natural resources management / fuel and energy subsidies which result in over consumption, create a burden on the budget, do not promote energy efficiency and disincentivise switching to low-carbon alternatives / revenue sharing formulas (other than for oil and gas) which allow sub-national governments to retain up to 80% of revenues from resource sales and taxation, which given the limited number of fiscal instruments at local levels, encourages accelerated depletion of renewable resources; and / “Feed in Tariffs” for low-carbon energy that are too low to encourage investment at the scale required to meet Indonesia’s own Energy Blueprint which seeks to increase the share of renewables from 4% to 17% by 2025. / The specific importance of the Ministry of Finance / 12. There is little doubt that responsibility for overall “climate change” policy is Indonesia is complicated and diffuse. Combating climate change comes with the promise of significant donor funding. This means that there is a good deal of competition for leadership between several agencies in this undefined space, in particular between Indonesia’s planning ministry (BAPPENAS), National Council on Climate Change (DNPI) and Presidential Delivery Unit (UKP4), the Ministry of Forestry and the Ministry of Environment. The UK is attempting to support GoI coordination on climate change through its on-going programme of support to BAPPENAS.[12] / 13. Democratisation and decentralisation are fairly recent initiatives in Indonesia’s fledgling democracy. It is thus hardly surprising to see that the responsibilities of coordinating ministries, line ministries, and the provincial and the local authorities are still poorly defined and often overlapping. The fact that a public agency has been assigned a specific mandate does not necessarily imply that this agency is also equipped with the capacity and clout required to realise that mandate. This observation is particularly pronounced when it comes to the cross-departmental and complex task of combating climate change. / 14. Whilst there are often moving and evolving mandates on climate change, there has been a consistent and sole role for the Ministry of Finance in setting fiscal policies in Indonesia in general and for low carbon development in particular. / 15. This clear political and legal mandate to lead and coordinate fiscal policy on low-carbon development offers Indonesia a very clear opportunity to implement low carbon policies. This opportunity stems from the very powerful and direct role that fiscal policy can play in shaping Indonesia’s development. The MoF is the only public agency that can exercise budget leverage (eg, by allocating funding to low-carbon initiatives or by using budget allocations and transfer mechanisms as a quasi-compliance mechanism). / 16. The situation of the Ministry of Finance is in direct contrast to that of supporting institutions that are working in climate change who are required to still secure mandates, secure budgets, coordinate and have to reach compromises on areas of responsibility. This is perhaps best illustrated by the very difficult process that has been witnessed for the establishment of the Indonesia REDD+ Agency (an agency to manage international carbon finance for the conservation and sustainable management of Indonesia’s forests), which started in 2009 and is not expected to be completed until 2014 at the earliest. / Capacity challenge / 17. Whilst MoF’s mandate is clear, its capacity and ability to push through policies, especially those related to low carbon development, needs support. Indonesia’s energy policies illustrate this point. / The conundrum of fossil fuel subsidies / There is wide global consensus that fossil fuel subsidies are a key obstacle to low-carbon development, eg, by precluding the creation of a level playing field that would allow renewable energy technologies to compete with conventional fossil fuel technologies on an equal footing. / In 2011, Central Government spent $27 billion dollars on energy subsidies, equivalent to nearly 20% of the entire budget, larger than education expenditure (7%), capital expenditure (9%) and health expenditure (1%) all added together. / The state budget allocation for the creation of new energy capacity was a mere US$ 2 billon a year, although an investment of more than US$ 10 billion per annum is required until 2025 to keep up with the rapidly growing demand for electricity. / About 90% of these subsidies accrued to the 40% richest households and about 40% of these subsidies accrued to the 10% richest households, suggesting that the fossil fuel subsidies does little to improve the life of the poorer segments of society. / Despite commitments to pursue low carbon growth, GoI increased subsidies in 2011. In early 2012, the Ministry of Finance announced a programme to start reducing subsidies. But this programme was blocked by Indonesia’s parliament. / 18. Support is needed to: / develop effective fiscal policies; / engage in broad consultation with multiple stakeholder groups (the dominant tradition is to develop policies in-house, behind closed doors); / firmly embed political analysis in strategies to achieve change; / build wide political support for fiscal policy proposals; and / develop expertise in communications to steer through policy change. / 19. Ultimately, MoF needs support so that it can build its capacity beyond technical analysis towards a comprehensive approach to enable it to build support and constituencies that can help push good fiscal policy proposals through Parliament. / The importance of investment / 20. Indonesia’s transition towards a low-carbon economy critically depends on the Government of Indonesia’s willingness, ability and capacity to channel public capital into low-carbon sectors while leveraging private co-investment. This task will only succeed if the GoI is able to lower risk and help with initial costs of capital. It involves the strengthening of existing public financing institutions and the creation of appropriate financing structures and mechanisms, including private-public partnership mechanisms.[13] / 21. An institutional appraisal was undertaken in preparation for this business case to clearly identify which institution within the Government of Indonesia could best deliver a speed up and scale up of investment in low carbon development. This appraisal, which was undertaken by a team of international and domestic independent experts, firmly concluded that from a legal, effectiveness and delivery perspective, the most strategic option open to the UK was to partner with the Indonesia Investment Agency. No other agency or part of the GoI could deliver the speed to scale in investment that is required if Indonesia is to get in any way near to its emission and renewables targets (see above). [14] / 22. The Indonesia Investment Agency is a hybrid between a national development bank and a sovereign wealth fund owned by the Ministry of Finance. It is the only public agency with an adequate legal mandate to structure investment mechanisms (as described above), channel international climate finance, and execute public investment in low-carbon sectors, in addition to its core business, ie, developing infrastructure in strategic sectors. / 23. The UK already has a strong relationship with the Indonesia Investment Agency. This has developed as a result of existing support which has provided technical assistance and advice to the agency for the last two years. Under existing support, the UKCCU financed a capacity audit and strengthening plan which provides the basis for a comprehensive programme of technical support and capacity building for the agency so that it can fully embrace low carbon objectives within its investment targets. This plan would form the basis of partnership with the Indonesia Investment Agency described in this business case. The agency’s senior management has taken full ownership of this programme and demonstrated a high-level of commitment to the proposed joint programme. / 24. The timing is right for the prioritisation of low carbon development within the objectives of the agency. It is currently undergoing major institutional re-structuring, transforming from a structural department within the Ministry of Finance, staffed with civil servants and bound to the operational and administrative rules of the civil service, into a non-structural corporate entity, eg, with the ability to employ experts from the private sector and operate outside of restrictive civil service rules. / 25. But the agency needs expert international advice and support to get this right. No other donor or agency was considered as suitable by the MoF for delivering such support. / Wider significance of the Indonesia Investment Agency / 26. The Indonesia Investment Agency is also crucially important as a pathway to delivering a number of other existing and future investments are expected to be made by the UKCCU, including: / Ongoing UKCCU work on capital investment in low-carbon sectors under the Agence Française de Developpement and UKCCU low carbon development partnership.[15] Several initiatives under this partnership and, more generally, the accelerated deployment of clean technology, depend on the creation of an equity vehicle for renewable energy investment, to be established by the agency. / Planned International Climate Fund work on energy efficiency and renewable energy lending to SMEs with Germany’s development bank (KfW), on which the agency will on-lend concessional climate finance to commercial banks. / 27. Hence, supporting the Indonesia Investment Agency in structuring and implementing low-carbon financing mechanisms and deals is a sound intervention that will safeguard other substantive UK investments with the prospect of creating a transformational impact. / How this programme contributes to HMG’s objectives / 28. This programme will directly contribute to the low carbon development objectives in HMG’s current Country Business Plan for Indonesia and forthcoming operational plan (2012/13 to 2014/15). It forms part of the UK’s overall commitment to support low carbon development under the International Climate Fund (2011-2015). A number of the indicators of results (see below) are standard indicators that can be used to aggregate results across all global programmes. / UK support to MoF to date / 29. The work proposed within this business case builds on two years’ prior support to the Ministry of Finance, which has also included the full-time secondment of a DFID A1 Climate Finance Specialist. Key results from past support are: / With the Ministry of Finance (MoF): / the establishment of a specific policy team within the MoF, which is now a permanent institution with the MoF which is advising all three finance ministers on climate change and low-carbon policies. / using analysis and advice provided under the project, the Government of Indonesia made a budget allocation to low-carbon development, providing some US$110 million seed funding for an anticipated investment mechanism (which will be located in the Indonesia Investment Agency). / Provision of advice resulting in policy changes (eg, waver of import tax on clean technology, feed-in-tariff for electricity generated from biomass and municipal waste). / the start of making policy more open – there have been a small number of multi-stakeholder focus group meetings on selected climate change and low carbon development policies. / capacity building to technical teams on climate and economic modeling, policy analysis and formulation. / a number of policy studies, papers and recommendations (eg, on land-use change and renewable energy sectors, low carbon financing source, structures and mechanisms, access to carbon markets and climate finance, fiscal policy and incentive mechanisms). / delivery of a number of low carbon programme propositions and help to the MoF to engage with the global Climate Investment Fund. / collaboration with local universities and research facilities on a number of topics including Carbon Capture & Storage (eg CCS) / B) With the Indonesia Investment Agency / the institutional re-structuring and strengthening of the agency (from structural MoF Department to quasi-independent corporate entity owned by MoF). / capacity improved for staff to be able to structure and create low carbon investment deals and projects / delivery of low carbon sector studies which have identified clear priorities for future investment. / In partnership with AusAid: / baseline research and inputs to the Ministry of Finance’s Low Carbon Green Paper (2009). / The development and early design work on a Regional Incentive Mechanism to promote low carbon development. / 30. The above support has also delivered relationships and trust between the UK and Indonesia. Past results and the strong relationship have been the catalyst for the request for the broader and deeper assistance on low carbon development contained in this business case. / 31. In February 2012, DFID’s Secretary of State met with Indonesia’s Vice Minister for Finance. During discussions it was agreed that the UKCCU would develop this business case to enable UK support to continue up to March 2015. / Other donors / 32. The UK, Australia and Germany are the only international bilateral partners that have been invited by the Government of Indonesia to directly support capacity building and policy formulation on climate change in Ministry of Finance. / Australia / 33. Australia is currently designing its next phase of climate-related support to the MoF. It too will provide the MoF with a flexible programme of technical assistance. It is intended to start in late 2012. It will form part of a wider programme of ongoing capacity building to the MoF that includes support on treasury, budget, debt and taxation issues. / 34. Australia’s next phase of support will be located in the Fiscal Policy Office and will sit alongside support from the UK and from Germany (see below). It will focus on areas not covered by the UKCCU support but it will be highly complementary to it. These areas are still to be finalised but are likely to include: / carbon taxes; / REDD+ (carbon financing for forest conservation and sustainable management); / the implementation of the RAN-GRK (this is Indonesia’s national action plan for reducing emissions – see Para 5 above); and / operationalising the Regional Incentive Mechanism so that it can direct climate finance to lower levels of government and reward climate friendly development/emissions reduction achievements. / 35. There has been consultation between the UK and Australia on whether both country’s programmes could be combined. The Ministry of Finance does not want this to happen. It would rather coordinate separate programmes than combine donor support into one programme. There are good prospects that this coordination will work. A new ministerial regulation was issued in January 2012 which specifically assigns coordination to the Head of Climate Change Team in the Fiscal Policy Office of the MoF. However, the UK and Australia will ensure that we work closely to support coordination efforts of the Ministry of Finance so that both programmes deliver value to the MoF and avoid any wasteful duplication. / 36. Australia expects that its programme of support to the Ministry of Finance will continue well into the long-term. Indonesia remains Australia’s largest recipient of bilateral aid. / Germany / 37. In late 2011, Germany expanded an existing programme of support to BAPPENAS on climate change planning to include short-term technical assistance to the Ministry of Finance. This support is provided through Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ). / 38. GIZ’s assistance was specifically targeted towards helping BAPPENAS and the Ministry of Finance operationalise the RAN-GRK through the budget system. This support has identified that considerable capacity building and technical system requirements are needed to roll out the RAN-GRK to lower levels of government. MoF is now in discussions with GIZ and Australia on a longer-term programme of support in this area. As with Australia it will be very important that UKCCU and GIZ work together to support coordination in the Ministry of Finance. / 39. The UK has undertaken to use lessons from its wide experience on coordination (in Indonesia and in other countries) to support the Ministry of Finance to coordinate its climate change-related support. / Multi-lateral development banks / 40. The multilateral development banks (Asian Development Bank and the World Bank) have lending programmes in Indonesia but do not currently have mainstream ministry-based climate change policy support or capacity building programmes. The World Bank is currently at a very early stage of discussions for a Green Growth support facility which would be available to support the Ministry of Finance. It is not clear if this facility will be operational during the intended implementation timeframe of this business case.
B. Impact and Outcome / 1. The programme’s impact will be to contribute towards establishing low carbon development as a viable approach at the national, sub-national and sectoral level for promoting growth in Indonesia. / 2. The outcome of the intervention will be a supportive environment for low carbon investment established in Indonesia. / 3. This will be achieved by: / MoF building stronger external networks and sharing evidence and building consensus on future policies. / New initiatives launched to support low carbon development, including at the regional level. / A Government White Paper on Low Carbon Development launched and associated regulations put in place. / A greater emphasis upon low carbon development within the Indonesia Investment Agency that will leverage private and international finance of at least $300m during the life of this programme. / MoF having built sufficient political and stakeholder support to enable it to reduce energy and fuel subsidies (by at least 20% over 2012 levels) and fundamentally reform feed in tariffs for renewable energy. Both these measures would transform the economics of renewable energy in Indonesia and are critical for Indonesia if it is to hit its policy of increasing renewables from 3% of installed capacity to 17% by 2025. / 4. The impact of this programme will be measured by: / the amount of finance leveraged for low carbon investment in Indonesia by the Indonesia Investment Agency; / reductions in the levels of energy/fuel subsidies in Indonesia; and / the viability of feed-in-tariffs for renewable energy. / 5. See the Logical Framework at Annex 1 for more details.
[4] Rizaldy Boer.et.al., Summary for Policy Makers : Indonesia’s Second National Communication under the UNFCCC, Jakarta : Government of Indonesia, 2009; Agus Sari, et.al., Executive Summary : Indonesia and Climate Change – Working Paper. Jakarta : Pelangi Energi Abadi Citra Enviro, 2007
[5] # World Bank, Indonesia-Low Carbon Development Options Study, Factsheet Number 4, “Assessment of Emissions – Key Findings” 2008. http://en.openei.org/wiki/ESMAP-Indonesia-Low_Carbon_Development_Options_Study
[6] # World Bank, Indonesia-Low Carbon Development Options Study, Factsheet Number 4, “Assessment of Emissions – Key Findings” 2008. http://en.openei.org/wiki/ESMAP-Indonesia-Low_Carbon_Development_Options_Study
[7] Pew Charitable Trust, G20 Energy Factbook, 2010.
[8] Government of Indonesia, Energy Blueprint 2005-2025, Presidential Regulation 5/2006.
[9] Leveraging private investment: the role of public sector climate finance, ODI Background Note, Jessica Brown and Michael Jacobs, April 2011.
[10] Indonesia ‘must promote low-carbon economy’, The Jakarta Post – 25 March 2011. http://www.thejakartapost.com/news/2011/03/25/indonesia-%E2%80%98must-promote-low-carbon-economy%E2%80%99.html
[11] Investing in a More Sustainable Indonesia, Country Environmental Analysis, The World Bank, 2009
[12] This support is through the programme “Indonesian Climate Change Trust Fund”. It is co-funded with Australia and with Sweden.
[13] These arguments also read across to the UK’s own initiative to establish a Green Bank in the UK. See: http://www.bis.gov.uk/greeninvestmentbank
[14] In 2007, the Ministry of Finance created the Indonesia Investment Agency to channel public finance and leverage private finance into “strategic sectors”. Since then the agency has built up a portfolio of nearly $1.5 billion in portfolio investments and has a professional staff of 40 people. Further details on the agency, its objectives, portfolio of investments and expertise can be found at: www.pip-indonesia.com
[15] For further details see: http://projects.dfid.gov.uk/project.aspx?Project=202376

Appraisal Case

A. Determining Critical Success Criteria (CSC) / 1. The following are success criteria that are critical to achieving the impact and outcome recorded in the Strategic Case: / CSC Description Weighting / 1 New policies are developed that can support low carbon development. 5 / 2 A GoI partner selected that has clear mandate to reform and implement policy. 4 / 3 Evidenced-based policies can be developed and properly disseminated amongst relevant stakeholders. 4 / 4 Clear GoI political support for UK support. 5 / 5 The policy delivery mechanism and its network succeed in building sufficient consensus and public support to persuade Parliament to ratify any tabled policy proposals. 4
Theory of Change / 2. Promoting good practice in policy making is fundamental to the delivery of quality outcomes for citizens and to the realisation of Indonesia’s ambitions to develop a low carbon economy. Policy makers should have available to them the widest and latest information on research and best practice and all decisions should be demonstrably rooted in this knowledge. / 3. The underpinning logic for the theory of change for this business case is that: / Starting point / low carbon development is not happening quickly enough in Indonesia because the policies that would encourage this to happen are either not in place or if they are in place, they are weak and do not create strong enough incentives. / In the climate change arena, Indonesia, not unlike a lot of countries, has confused and conflicting mandates for different institutions.[16] / The Ministry of Finance is by far and away the most important ministry in setting the framework and incentives for low carbon development which other actors then respond to. / But the Ministry of Finance lacks the capacity and resources to push through policy reforms. In particular it needs to be much more networked with outside stakeholders, it needs to use more evidence and it needs to build support for its policies across other ministries and with parliament. / Change needed / More evidence, more outreach, more input from external experts would enable the Ministry of Finance to identify and develop economic and fiscal strategies to reduce emissions and promote a more efficient use of Indonesia’s resources for sustainable development. / For any policy change to be successful it needs to be properly researched and have a solid evidence base. / Wider stakeholders (other ministries, think-tanks, politicians) need to be involved in policy formulation from the start, for this to happen the Ministry of Finance needs to open-up its policy making process more than it has traditionally done. / Policy needs to be disseminated properly to other ministries and agencies, it needs champions and supporters outside government. / Policy, especially when it is in very sensitive areas, needs to have very strong ministry ownership. / Communication needs to be improved so that wide support can be gained. / UKCCU inputs / Resources and technical assistance to the Ministry of Finance for research, capacity building, outreach, networking, dissemination. / Leading to change in the Ministry of Finance / Evidence-based policy using the latest information on research and best practice. / Open policy dialogue. / Connectivity between the Ministry of Finance and important Parliamentary Committees. / Indonesian-owned policy reforms. / Leading to change in Indonesia / Regulations that slow or stop emission intensive practices at local levels. / Fiscal incentives that promote low carbon energy. / Reductions in subsidies to fuel and energy subsidies. / Contributing to a slow-down in the growth of emissions. / 4. The evidence to support this theory of change and the case for why having the right fiscal environment is important for countries to move onto a low carbon development strategy can be in: / The Stern Review on the Economics of Climate Change (2006); / Indonesia Second National Communication Under The United Nations Framework Convention on Climate Change (UNFCCC) (2010); / National Action Plan on Climate Change (RAN GRK), 2011; / Ministry of Finance Green Paper on Economic and Fiscal Strategies for Climate Change Mitigation in Indonesia (jointly published by Ministry of Finance, Republic of Indonesia and Australia Indonesia Partnership (2009); and / Investing in a More Sustainable Indonesia (World Bank 2009). / 5. It is also entirely consistent with the approach and theory of change outlined in the thematic low carbon development plan of the International Climate Fund which highlights the need for demonstrating the viability of low carbon development, building capacity for developing countries to develop low carbon policies, improving the architecture and delivery of finance and leveraging private sector investment/finance for infrastructure and energy provision.[17] / B. Feasible options / 6. In August 2011, during bilateral government to government talks, the UK and GoI agreed that there would be a strong policy component to the UK’s support to low carbon programme with Indonesia. This followed analysis of potential entry points for influencing low carbon policies in Indonesia which showed that working directly with the government was the most effective route to creating impact in Indonesia. Other routes considered but rejected were: / Working directly with NGOs. Meetings were held with a number of NGOs. Whilst there are strong candidates for work in this area (eg WWF), the barriers they face in terms of influencing policy are considerable. These include: having legitimacy within the Indonesian policy process to be able to directly formulate policies and see them through the policy process, not being able to mobilise the level of financial flows that are required (particularly in energy) to tackle future emissions. NGOs can play a very useful role in raising awareness about climate change and working at provincial levels. Indeed they are expected to form a very important part in the networks and stakeholder outreach envisaged under this business case. / Working directly with the private sector to deliver policy change. The domestic and international private sector will play an increasingly important role in low carbon in Indonesia. Indeed the UK’s largest financial investment towards supporting low carbon development is the current Agence Française de Developpement and UK partnership which is particularly targeted at supporting investment by the private sector into significant low carbon ventures. But whilst this support is vital, the private sector does not have the direct influence over policy. For this, a government partner needs to be selected. / 7. Consequently in undertaking the design of this business case, the first task was to identify which GoI ministry/agency or agencies the UK should support. The second stage was to determine what modalities should be used for such support. / Stage one: identification of the right partner / 8. An analysis of the current institutional landscape suggests that the Office of the President, being tied into a fragile political coalition, lacks the political space and capacity to lead on or coordinate low-carbon policy development. / 9. The coordinating ministries - the National Development Planning Bureau (BAPPENAS) and the Coordinating Ministry for Economic Affairs - lack the mandates or powers to address strategic cross-sectoral issues required to set policies and deliver. These ministries are important but they do not deliver policy and do not have sufficient leverage over line ministries such as Forestry, Energy and important bodies such as PLN (Indonesian’s state monopoly energy supplier). / 10. Recent analysis undertaken by the World Bank and the Government of Australia clearly identify the Ministry of Finance as the central and most important ministry to create the right incentives to encourage development along a low carbon path.[18] / 11. This concurs with UKCCU’s own analysis which has identified the Ministry of Finance as the powerhouse of public reform over the past decade. The Ministry has a number of coherent channels through which it can set, implement and regulate policy as well as determine financial flows. This is summarised in the diagram below. / Source: Fiscal Policy Office, Ministry of Finance / 12. Other options considered in programme design are ranked in the table below. / Option Ability to influence policy Coherent low carbon policy / 1) Office of the President Strong Low opportunity / 2) Coordinating Ministry for Economic Affairs Medium Medium opportunity / 3) Ministry of Planning (BAPPENAS) Strong Low opportunity / 4) Ministry of Finance Strong High opportunity / Stage 2: selecting the right policy mechanism / 13. This forms the core part of the appraisal and is set out in Section C (below). / By managing: / - Investment climate / - Pricing (fiscal) policies / - Direct spending / - Risk and financial markets / - Sectoral rules and law / Ministry of Finance / Policy instruments for influencing low carbon development / Can influence: / - Incentives / - Investments / - Industry / - Int financial flows / - Pro poor approaches / Financial investment policies / - Investment climate / - Banking sector / - Non-Bank Finance institutions / - Municipal finance rules / Fiscal policies / - Tax/fees/charges / - Royalties/rents / - Subsidies/tax breaks / - Relative prices and incentives / - Emissions trading / Budget expenditure policies / - Strategic budget priorities / - Direct and long term investment / - Green procurement / Direct regulation / (in cooperation with other agencies) / - Enforcement/ incentives / - Zoning/land use / - Environmental management / - Building design standards / - Emission standards
C. Appraisal of options / 1. Having selected the Ministry of Finance as the preferred partner, appraisal considered 3 options: / 1 – No further action / 2 – To improve the low carbon policy environment by supporting a multi-donor initiative / 3 – [preferred option] To work directly bilaterally with the Ministry of Finance / Option one / Description: Do nothing / 2. In this option, the Ministry of Finance would continue to apply its own resources to promoting low carbon development. But the effectiveness of this will be lower than in the case of receiving UK support. An important assumption in the “do nothing” option is that no other international partner would be approached to provide the potential support on offer from the UK. There are two reasons for this: / The Ministry of Finance wants to work with the UK to build on the first phase of assistance (2010-2012). The UK through DFID and latterly through the UKCCU has spent the last three years with a senior climate change expert seconded into the heart of the Ministry of Finance. This secondee is the only person in this role and in this role has established excellent relationships with key ministry officials and leaders. / The UK has demonstrated to the Ministry of Finance that it is able to provide advice and support in a way that is acceptable to Indonesia. This was evidenced when DFID’s Secretary of State met with Indonesia’s Vice Minister for Finance in mid-February 2012. In that meeting the Vice Minister requested continuing UK partnership and support to the Ministry of Finance. / 3. The option of doing nothing was rejected on the basis that wasting a strategic opportunity for the UK and Indonesia to work together on low carbon policy, would mean rejecting an opportunity to work with a country whose emissions are of global significance and whose role on the international stage is growing. / Option Two / Description: supporting a multi-donor initiative / 4. This option would involve the UK joining with other donors to support policy reform. Three variants were considered in appraisal. Two involved the UK supporting existing initiatives, a third to support a new proposal that is currently being developed by the World Bank. / Existing initiative: The Climate Change Development Policy Loan (CCDPL) / 5. The CCDPL – is a policy loan with an attached climate change policy matrix. Since it started in 2009, it has disbursed $400m. There would be an opportunity for UKCCU to offer funding under this business case to support the implementation of the policy matrix. This was rejected in appraisal since: / it has limited political buy-in within the Government of Indonesia. The UK has not been invited by GoI to support the CCDPL; and / it is not clear that the policy matrix is intimately linked to the policy CCDPL. When it was originally conceived the loan was required by the GoI to help bridge a budget gap caused by spiralling oil prices in 2008. It was only later that a climate-related policy matrix was added. / 6. Appraisal concluded that the link between the CCDPL and policy change is relatively weak. It would be very hard to identify what value-added would be achieved by a £4.5m grant to this multi-donor process. / Existing initiative: The International Climate Change Trust Fund (ICCTF) / 7. The ICCTF is a multi-donor trust fund initiated by DFID and located under BAPPENAS. It is essentially an expenditure fund in support of climate change related capacity building. Whilst it remains a valuable vehicle for UKCCU to help cross-ministry coordination it does not have the focus upon low carbon development that would be required to achieve the objectives of this business case. / Proposed initiative: Support to the proposed Green Growth Support Facility / 8. As part of the appraisal for this project, the UKCCU consulted with a number of partners. The World Bank suggested that the UK consider providing grant finance to help establish a Green Growth Support Facility (located in the Bank) to provide key technical, policy and capacity building to a number of government ministries and agencies, in particular the Ministry of Finance, the President’s Office and the emerging REDD+ Agency. This proposal has merits, but is still in the very early stages of development. Experience has shown that: / in Indonesia, it takes considerable time to build up relationships, contacts and trust so that they are at the point where international support can be effective; / the ambition of the facility to have multiple clients will be challenging, in Indonesia such facilities in the past have struggled because of competition and rivalries between ministries; and / Indonesian stakeholders are unwilling to engage in cross-government working in fora that are supported or observed by donors. Such deliberations are (rightly) seen as the preserve of government. / 9. Ultimately this option was rejected on the basis that: / The UK has strong political capital invested in its bilateral relationship with the Ministry of Finance. This would be dissipated if this option were selected. This is important as the UK expects its bilateral dialogue with GoI to continue to develop in the coming years; / At the time of preparing this business case, it was not clear that there was as yet strong political ownership of this approach. / 10. It may be that future UK support could be used for this initiative if the Bank is able to generate political support across the relevant ministries in Indonesia. / Option three / Description: working directly with the Ministry of Finance / 11. This option would involve the UK working directly with the Ministry of Finance. Under this option the UKCCU would provide the Ministry of Finance with a flexible programme of technical assistance and capacity building which would provide support to all the principle departments involved in low carbon policy formulation and implementation. / 12. UKCCU support would be delivered through a ministry-based low carbon policy support team which would operate under the guidance of the Fiscal Policy Office. It would offer support to the Indonesia Investment Authority, the Ministerial Assistance Team, the Secretary General of the Ministry of Finance, Special Advisers and, if required to Vice Ministers. / 13. It would be staffed by a full-time team leader, two full-time international advisers and up to five full-time Indonesian experts. Short-term experts would be used on as required basis. Three full-time administrators will support the implementation of the proposed intervention. They would be located in space provided by the MoF in the MoF main building. / 14. Experience under existing DFID support to the Ministry of Finance has shown that senior leaders in the Ministry need to set the work programmes of external programmes of support if they are to generate the required level of ownership. To facilitate this, the support team would have a very flexible mandate. A detailed work programme of activities, outputs and results would be agreed on a three-monthly basis. The role of the Team Leader would be to ensure the delivery of this programme. A Steering Committee consisting of MoF, UKCCU and the support team would be established at the inception of the project to agree the three-monthly work programme. It would then meet every three months to set a new work programme and review progress. / 15. On a 12 monthly basis (or at more regular intervals if required), the Vice Minister of Finance would convene a high level ministry meeting at which senior levels of the Ministry and the Head of the UKCCU would review progress and set strategy for future activities. / 16. The functions of the low carbon policy support team would be to: / Provide expert policy advice on demand to the Ministry of Finance. / Deliver agreed programmes of capacity building to the Ministry of Finance. / Prepare as requested analysis and papers. / Support the Ministry of Finance to expand and boost its outreach to wider stakeholders. / Support the Ministry of Finance to undertake consultations and communications with other ministries, provinces and other Government of Indonesia bodies. / Support the Ministry of Finance to deliver effective communications to outside stakeholders on fiscal reform issues and policies. / Support the delivery of the phase I financed capacity audit and strengthening plan for the IIA. / Assist with the preparation of legal regulations. / Manage all resources and contracts on behalf of the UKCCU. / Economic analysis / 17. It is challenging to undertake a cost-benefit analysis of a policy support project, quantifying causality and impact would suffer from excessive reliance upon estimated rather than real economic values. However because this project is directly related to fiscal policy and with that to budget revenues, it is reasonable to attempt to illustrate that this project could have considerable beneficial economic and climate impacts. / 18. Potential areas of policy involvement include: / Reduction in future energy/fuel subsidies / Direct allocations from the state budget for low-carbon initiatives / Fiscal (both sectoral and regional) incentives in favour of low-carbon development / Taxation (eg, reducing import tax on clean tech equipment, tax cuts for emission reductions achieved, etc.) and fiscal compliance mechanisms (eg, taxing bads) in favour of low-carbon development / Monetary policy (eg, enabling regulations on carbon finance) in favour of low carbon development / Leveraging of private finance towards low carbon development / 19. Taking two of these areas in more detail, this project will seek to support the MoF to: / Engage in an evidence-based dialogue to reduce fuel and energy subsidies. Currently these account for $27 billion (20% of the entire central government budget). Subsidies have grown substantially because of the rise in oil prices. Indonesian subsidies exist to promote a range of social and economic objectives. This project will work within the Ministry of Finance to demonstrate the huge opportunity cost of these subsidies and their success or otherwise in meeting the stated social and economic objectives. If this project was able to tackle this issue alone and play a role in reducing these subsidies this would in itself represent a significant return on the UK’s investment. Indonesia is a net-importer of fuel and so when oil prices rise, its policy of guaranteed subsidies has a huge opportunity cost.[19] / Bring robust analysis and to the very significant issue of fuel and energy subsidies inhibiting investment in renewables. By artificially lowering the price of certain types of energy, subsidies encourage overconsumption and inefficient use of those resources. Lower prices also alter investment decisions and discourage diversification. They have the impact of locking Indonesia into fossil-fuel electricity generation which means the likelihood of achieving emissions reductions is greatly reduced. Reviewing and establishing new feed in tariffs which encourage investment is essential to achieving Indonesia’s targets for renewable energy (see above). / Cost effectiveness of preferred approach / 20. Cost Effectiveness Analysis is generally used where it is difficult to assign a monetary value to the stream of benefits associated with an investment. All of the above analysis suggests that it would be more cost effective to select Option 3 as it has higher prospects for delivery of policy change than Option 2 and that they are significant enough to justify Option 3 over the do nothing scenario. In reality it is very difficult to accurately forecast what policies will be reformed and the ultimate impact. In this programme, a judgement has to be made on whether a £4,500,000 investment would be effective. The measures that will be used to assess effectiveness will be: / observed reductions in subsidies (target is a reduction by 20% by March 2015); / leveraged finance for low carbon projects (target $300m by March 2015) / 21. A budget of £4.5 million is proposed to ensure that there are sufficient resources for policy advice, technical assistance, outreach and dissemination, and capacity building. The drawdown of resources will be based upon agreed work programmes. / Environmental and social impact / 22. Since the proposed initiative is entirely related to promoting sustainable low-carbon economic development, it is not necessary to comment separately upon its environmental impact. Since it is inclusive and based on multi-stakeholder consultation and democratic principles, it is reasonable to assume that its social impact will be positive. / 23. There will be numerous beneficiaries from this project and in implementation, an important role for monitoring and evaluation will be to collect this information. It is expected that: / A reduction in energy/fuel subsidies will be accompanied by a parallel cash-transfer mechanism aimed at supporting the poor. Indonesia has past experience of such schemes and the evidence from them is that they are very effective.[20] / A shift to low carbon energy investment will result in fewer coal powered power stations and lower demand for coal. In turn this will indirectly benefit communities in coal mining areas since Indonesia has struggled to maintain high levels of environmental and social safeguards in domestic coal mining.
D. Comparison of options / 24. The table below provides a summary of the options and the appraisal vis-à-vis the CSCs. The appraisal methodology paid special attention to the political feasibility of each option / Weight Option 1 Option 2 Option 3 / Critical Success Criteria Score / (1-5) Weighted / Score Score / (1-5) Weighted / Score Score / (1-5) Weighted / Score / New policies are developed that can support low carbon development 5 2 10 3 15 4 20 / GoI partner that has clear mandate to reform and implement policy 4 5 20 3 12 5 20 / Evidenced-based policies can be developed and properly disseminated amongst relevant stakeholders 4 2 8 3 12 4 16 / Clear GoI political support for UK support 5 0 0 1 5 5 25 / The policy delivery mechanism and its network succeed in building sufficient consensus and public support to persuade Parliament to ratify the tabled policy proposals. 4 0 0 3 12 4 16 / TOTALS 38 56 97 / 25. The options analysis clearly shows that the preferred option has the best prospects of meeting the critical success criteria.
E. Measures to be used or developed to assess value for money / 1. The direct VFM for this business case rests on an assessment of: / Whether DFID’s proposed investment would yield sufficient technical and other inputs to justify the proposed outputs and impacts. / 2. A single contract will be used to deliver the proposed support and it will be subject to a competitive bids. / 3. In terms of VFM, the key indicator will be the number of policies that the project influences and the volume of investment that is secured into low carbon development. On that basis the project will carefully measure its impacts on policy in Indonesia and specifically seek to measure and report on their impact throughout the project’s implementation.
[16] For example: Min. Development Planning / Bappenas. Coordinates development assistance and Chairs the Indonesia Climate Change Trust Fund (ICCTF). Min. Foreign Affairs. Leads on international negotiations under the UNFCCC. DNPI – the National Climate Change Council. Established in 2008. It is chaired by the President with Coordinating Ministers for the Economy and for Social Welfare as Vice Chairs. It has a membership of 16 line ministries and 1 state agency. However, DNPI faces significant problems in coordinating climate change policies across ministries, especially across the politically-strong ministries with full-ministerial status (Ministries of Finance, Forestry and Energy). Min. Energy and Mineral Resources. Responsible for renewable energy targets, but also for delivering overall energy targets. Ministry of Finance. Sets overall budgets and determines the investment environment and regulations. Responsible for approving all loan finance. Determines energy/fuel subsidy polices. Provincial governments. Responsible for implementation of policies, but often have limited access to financing.
[17] See http://www.decc.gov.uk/en/content/cms/tackling/international/icf/icf.aspx
[18] See Ministry of Finance Green Paper Economic and Fiscal Policy Strategies for Climate Change Mitigation in Indonesia, Ministry of Finance, November 2009. And Investing in a More Sustainable Indonesia, Country Environmental Analysis, The World Bank, 2009.
[19] The literature on fossil fuel subsidies shows that in most cases they are not pro-poor. The majority of the benefit is captured by wealthier households and subsidies take up fiscal resources that could be spent on pro-poor public services. See Low carbon development: Framing Paper, IDS, University of Sussex, 2011.
[20] See A Citizen’s Guide to Energy Subsidies in Indonesia, International Institute for Sustainable Development, 2010.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / 1. The procurement route for the Low Carbon Support Programme to the Ministry of Finance will be through the direct recruitment of technical assistance through an open competition. / 2. Technical assistance will be contracted to manage and deliver a programme of capacity building and technical advice to the Ministry of Finance in Indonesia.
B. How does the intervention design use competition to drive commercial advantage for DFID? / 1. The proposed piece of work will be openly tendered by OJEU rules to ensure competition and value-for-money. A tender will prepared and will be advertised through the OJEU process. Bids will be assessed on a competitive basis for their technical and commercial responses. A tender team will be formed that will also include a representative from the Ministry of Finance. Upon the completion of the tendering process, UKCCU will agree a delivery and payment schedule and sign a contract with the selected service provider. / 2. The outputs for the interventions relating to this project are clearly defined in the logical framework. To achieve best value for money, results and impact, the technical assistance contract will be output focussed where appropriate. The scope of the Terms of Reference (ToR) will require the technical assistance to provide robust methodologies that are likely to achieve the desired results within the given timeframe. / 3. The ToR will capture the specific milestones for the overall project. We expect the Supplier to define appropriate review milestones for ensuring achievement of milestones as per the logical framework indicators. / 4. We considered the alternative option of using a DFID Framework Agreement. But the scope and value of this assignment leaves us with the only option of going through the OJEU route. We also considered the use of existing DFID procurement agents, but the Ministry of Finance requested we conduct a selection/tendering process.
C. How do we expect the market place will respond to this opportunity? / 1. The international supply base is competitive for this assignment. We expect consulting companies will form consortia to enhance their prospect for winning the tender. These consortia will demonstrate strong expertise and experience. They will also demonstrate a strong track record on the facilitation of policy processes and the provision of high-quality and high-level advice on fiscal policy and investment in key result areas such as the land-use and the energy sector. / 2. We would expect consortia to provide the majority of inputs for the technical assistance but where they need to sub-contract for specific inputs we will ensure that this is done competitively.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / 1. Key cost drivers are centred upon technical assistance and capacity building. The value-added will be enhanced by a systemic approach to the services that will be provided, ie, capacity building will be linked to technical advice and to outreach to wider stakeholders. / 2. Performance and delivery, and the monitoring of their value-added, will be improved and guided by having two SMART deliverables at the impact level, ie, the delivery of a white paper on low-carbon development and the Indonesia Investment Authority securing at least $300m of international donor and private finance. / 3. In addition to the critical success criteria outlined earlier, a set of principles has been developed during the pre-preparation stage to guide both the performance and the monitoring of outputs and outcomes. These include: / Creation of a high level of ownership by the Ministry of Finance and the Indonesia Investment Agency; / Approaches that are built on evidence of what works and on previous success; / Interfaces and networks that facilitate stakeholder dialogue and overcome institutional barriers; / A preference for improving existing institutions and policy process over proliferating institutions; / Reduction of complexity for decision makers; and / Innovation through re-combining successful elements of existing approaches and creating synergies between them.
E. What is the intended Procurement Process to support the contract award? / 1. We have consulted with DFID’s Procurement Group for the proposed approach. In the absence of a supplier framework agreement to perform the kind of discrete procurement required, we have been advised to use the OJEU procedure. Subject to the approval of the final Business Case, the preferred supplier will be identified through the Restricted Procedure under the EU Directives. / 2. We expect the tasks related to engaging the supplier to be completed by the end of November 2012. The envisaged timeline under the Negotiated Procedure of OJEU route is as below. / Stage Date / BC Approval 5 May 2012 / Finalisation of ToR 5 June / OJEU Notice 1 July / Expressions of Interest received 1 August / Expressions of Interest evaluated 19 August / Invitation to Tender sent 20 August / Submission of bids 24 September / Bid evaluations and internal assurance 7 October / Selection of Preferred bidder 27 October / Contract finalisation 1 November / Commissioning of technical assistance 15 November / Mobilisation, service commencement December 2012
F. How will contract & supplier performance be managed through the life of the intervention? / 1. Contract and supplier performance will be managed through ongoing in-house monitoring and external evaluation (M&E). It will be led by the Steering Committee and the Lead Adviser against a list of output specifications and a delivery schedule, which shall be agreed with the contractor. / 2. During the inception stage (first three months) MoF, UKCCU and the contractor will also agree a conflict resolution mechanism to handle non-compliance. Ongoing internal M&E will be complemented and strengthened through periodical evaluation conducted by independent 3rd parties.

Financial Case

A. How much it will cost / 1. The recommended option for this intervention will cost £4.5 million. The expected distribution across financial years is as follows: / 2012/3 - £0.5 million / 2013/4 - £2.0 million / 2014/5 - £2.0 million / 2. There are sufficient funds for this in UKCCU bilateral budget. This funding is not novel or contentious in any way.
B. How it will be funded: capital/programme/admin / 1. DFID’s programme resources for the UKCCU in Indonesia.
C. How funds will be paid out / 1. This intervention will be funded through programme funds allocated to Indonesia during the 2011 BAR process.
D. How expenditure will be monitored, reported, and accounted for / 1. As per standard requirement, payments will be made in arrears in accordance with the signed framework contract and the delivery/payment schedule to be agreed during the inception phase.

Management Case

A. Oversight / 1. This intervention will commence with the completion of the open tender and the signing of a framework contract between UKCCU and the selected service provider. The service provider will be responsible for the administration and management of the intervention. / 2. The functions of the low carbon policy support team would be to: / Provide expert policy advice on demand to the Ministry of Finance. / Deliver agreed programmes of capacity building to the Ministry of Finance. / Prepare as requested analysis and papers. / Support the Ministry of Finance to expand and boost its outreach to wider stakeholders. / Support the Ministry of Finance to undertake consultations and communications with other ministries, provinces and other Government of Indonesia bodies. / Support the Ministry of Finance to deliver effective communications to outside stakeholders on fiscal reform issues and policies. / Manage all resources and contracts on behalf of the UKCCU. / 3. UKCCU oversight would be provided by the Lead Adviser and the Head of the UKCCU. UKCCU’s contract and programme manager would also provide support to ensure smooth implementation. / 4. Ministry of Finance oversight would take place at different levels: / Day to day operations / The Fiscal Policy Office of the Ministry of Finance would be the day to day partner of the low carbon policy support team. / Planning / A Steering Committee consisting of MoF, UKCCU and the support team would be established at the inception of the project to agree the three-monthly work programme. It would then meet every three months to set a new work programme and review progress. The principal recipients in MoF, ie the Fiscal Policy Office and the Indonesia Investment Authority would represent MoF on the Steering Committee. / Strategy and political support / On a 12 monthly basis (or at more regular intervals if required), the Vice Minister of Finance I would convene a high level ministry meeting at which senior levels of the Ministry and the Head of the UKCCU would review progress and set strategy for future activities. / 5. The oversight and governance mechanism above would mean that: / Annual high-level meetings between UKCCU and the Ministry of Finance to review progress and discuss strategy. / Quarterly planning, review and progress updates would be provided by the Steering Committee. / The Head of the UK Climate Change Unit and the Vice Minister of Finance would be regularly debriefed on activities of the support following each meeting of the Steering Committee. / Financial oversight will be provided through regular audits to be undertaken by the Government of Indonesia and UKCCU. / Lead Adviser / Mark George / Quality Assurer / Paul Chambers / Project Inputter / Egi Yugini
B. Management / 1. The programme will be administered and managed by the selected service provider. The service provider will set up a transparent and accountable governance mechanism. The Ministry of Finance and UKCCU will jointly review these structures, mechanisms and procedures to ensure that they comply with official procurement guidelines and adhere to international best practice standards.
C. Conditionality / 1. Not relevant.
D. Monitoring and Evaluation / Monitoring / 1. Contract and supplier performance will be managed through UKCCU annual reviews. These reviews will be undertaken by the lead adviser. It will be based upon project progress reports and interviews with project partners. / 2. Monitoring reports will be discussed and agreed with the Steering Committee. / Evaluation / 3. The UKCCU will commission evaluation reports which will assess the extent to which the project is delivering results. Such evaluations will focus on policy changes/reform and seek to assess social impacts through beneficiaries’ analysis. These evaluations will assess finance leveraged and numbers and quality of low carbon projects that have been supported. / 4. Evaluation will be financed from the costs of the project. At least £250K will be reserved from the programme budget for this project for evaluation. The UKCCU will issue a contract for evaluation at the beginning of the programme to cover the whole implementation period. / 5. The findings from evaluation will be disseminated in Indonesia and if considered useful to other low carbon teams in DFID. Results will be fed into the International Climate Fund (ICF) global evaluation and used to generate lessons for future DFID investments in low carbon development. These evaluations are expected to contribute improved evidence into low carbon development policy development.
E. Risk Assessment / 1. There are a number of important risks associated with this programme. / Risk Impact Mitigation measures / Risk of no influence, all the capacity building and advice provided is neither used nor has any impact on policy. UK taxpayers money will have been wasted The Ministry of Finance has requested this support from the UK as a fellow G20 country. / The governance arrangements specifically allow for the MoF to determine the detailed work programmes of the technical assistance and to respond directly to the requirements of Ministers and senior leaders in the Ministry of Finance. / The UKCCU will be a member of the Steering Committee and will be in regular contact with the Fiscal Policy Office. If advice and support provided are judged to be ineffective then measures will be taken to review design and or scale-down support. / Evidence from existing support to MoF suggests that provided advice is delivered in accordance with MoF requirements, it will be effective in supporting reform and policy change. / Risk of corruption UK finance will be wasted, stolen or misappropriated The UKCCU will implement the latest DFID guidance on avoiding corruption in the management of the programme. This guidance will be shared with all project partners and if necessary, appropriate training will be provided and a plan for avoiding corruption will be prepared. / The selected service providers will be subject to unannounced audits on programme budgets and activities throughout the course of the programme as well as to annual monitoring by the UKCCU. / Risk of underspend Results will not be delivered on time. There is considerable risk of underspend in Indonesia. Programmes and projects are often delayed. In designing this intervention, the UKCCU has ensured that there will be adequate management and administrative capacity in the programme so that its activities can be delivered on time and to budget. / 2. Ongoing risk assessment and mitigation will be important, especially because the proposed intervention is designed to be flexible. This ongoing assessment will be the responsibility of the Steering Committee. It will form an integral part of its regular management and monitoring activities. / 3. The risks to the UK of this project not achieving its objectives would be: / Internal project risks / reputational risk that the UK had been unable to deliver on promises to support low carbon development. There is a low likelihood of this happening since the project has been designed in very close cooperation with the Government of Indonesia. The UK is seen as a partner in this work and responsibility for success is a joint responsibility. / External risks / that a number of the projects developed with the Indonesia Investment Agency fail to generate expected returns. There is a medium risk of this, not least because many projects are innovative. The mitigation strategy to address this will be to ensure that any feasibility studies are robustly researched and the best available evidence and analysis is used to establish viability before any finance is committed.
F. Results and Benefits Management / 1. The logical framework will be the main tool to manage and monitor the results and benefits of this intervention. / 2. The key results from this business case will be: / that the Indonesia Investment Authority will have established a credible and effective mechanism to leverage at least $300m of international donor and private finance specifically for low carbon development. / the publication of a Government White Paper on Low Carbon Development and follow-on regulations that will fundamentally change the environment and framework for low carbon investment. / 3. Supporting MoF with technical assistance, capacity building, outreach to wider stakeholders and communications will enable MoF to: / have built sufficient political and stakeholder support to enable it to take forward low carbon policy reform in Indonesia and be able to tackle some of the real barriers to moving to a low carbon pathway such as in energy subsidies and feed-in-tariffs: / We would expect that by the end of UKCCU support, energy subsidies will be at least 20% lower than 2012 levels and fundamental reform feed in tariffs for renewable energy will have been implemented. Both these measures would transform the economics of renewable energy in Indonesia and are critical for Indonesia if it is to hit its policy of increasing renewables from 3% of installed capacity to 17% by 2025.

ANNEX 1: LOGICAL FRAMEWORK

PROJECT TITLE	LOW CARBON SUPPORT PROGRAMME TO THE MINISTRY OF FINANCE / Duration: 30 months (Nov 2012 to April 2015)
Impact	Indicator	Baseline / Jan 2012	Milestone 1 / December 2014	Target / March 2015
Low carbon development is shown to be viable and able to deliver results.	Energy pricing and feed-in tariffs supportive of low carbon investment	Energy/fuel subsidies running at $27 bn per year (2011). / Only feed in tariffs (FiTs) for mini and micro hydro effective.	Subsidies reduced by at least 10% / FiTs for biomass and solar considered effective by investment community	Subsidies reduced by 20% / FiTs and or tariff caps for geothermal considered effective by investment community
		Source
		Ministry of Energy, Ministry of Finance
	Indicator	Baseline / Jan 2012	Milestone 1 / August 2013	Target / March 2015
	Low carbon fiscal incentives / and regulations introduced	Limited	Comprehensive low carbon fiscal package announced for the 2014 Budget	Enhanced measures in place for the 2015 Budget
		Source / Presidential Address on Budget, MoF Budget, Project Reports

Outcome	Indicator	Baseline / Jan 2012	Milestone 1 / Jan 2014	Target / March 2015	Assumptions
Supportive environment for low carbon investment established in Indonesia.	New low carbon incentives & regulations introduced and implemented.	Various low level government initiatives	White Paper on Low Carbon Development / Plans for piloting a regional low carbon incentive mechanism in place.	New Government Regulations on Low Carbon Development / Regional low carbon incentive mechanism fully piloted and results evaluated.	MoF able to gain cross government support for new regulations. / Parliament agrees to new regulations
		Source
		Ministry of Finance, Project reports
	Indicator	Baseline / Jan 2012	Milestone 1 / June 2014	Target / March 2015	Assumptions
	IIA funding into low carbon investment	Public - 0 / Private - 0 / International donor - 0	Public - $25m / Private - $125 / International donor - $125	Public - $50m / Private - $250m / International donor – $250m	Indonesian Green Investment Fund or similar launched
		Source			RISK RATING
		IIA Accounts, financial returns to MoF, Project progress reports			Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£4.5m	0	0	£4.5m	100%
INPUTS (HR)	DFID (FTEs) / A2 Adviser – 20% / B1 Programme Manager – 10% / C1 Programme Assistant – 10%

OUTPUT 1	Indicator	Baseline / Jan 2012	Milestone 1 / Dec 2013	Target / March 2015	Assumptions
High quality technical assistance to the MoF.	Evidence papers presented to Parliament and high level policy seminars	MoF releases very few policy papers	Policy papers: At least 4	Policy papers: at least 8	MoF engages fully with the support team and it quickly establishes its reputation with policy makers in MoF.
		Source
		Project reports, Press reports, MoF website
IMPACT WEIGHTING	Indicator	Baseline / Jan 2012	Milestone 1 / June 2014	Target / March 2015
35%	Staff trained through UKCCU support.	Zero	Programmes delivered for all relevant central MoF departments.	Low carbon training delivered for at least 3 provinces
		Source			RISK RATING
		Project reports, Press reports, MoF website, Minutes of Steering Committee.			Medium

OUTPUT 2	Indicator	Baseline / Jan 2012	Milestone 1 / June 2014	Target / March 2015		Assumptions
Wider stakeholder input to MoF low carbon policy making.	Numbers of outreach events	0	Outreach events: At least 2	Outreach events: At least 4		Board is able to attract interest of credible non-government stakeholders.
		Source
		Minutes of the Steering Committee.
Impact Weighting		Baseline / Jan 2012	Milestone 1 Jan 2013	Target / June 2013
15%	MoF establishes low carbon outreach networks	-	Includes: / Academics / Finance institutions	Plus: / CSOs, NGOs / Chambers of Commerce
						RISK RATING
						Medium

OUTPUT 3	Indicator	Baseline / Jan 2012	Milestone 1 / June 2014	Target / March 2015		Assumptions
Low carbon investment objectives fully incorporated into the operations of the Indonesia Investment Authority.	Number of low carbon funding partnerships established by IIA with other government, private and international donors.	0	2	6 by end of project		IIA staff capacity building programme implemented fully and staff remain in place / IIA able to attract international partners, public funding and private investor interest.
		Source
		IIA Annual reports, / Project monitoring reports
IMPACT WEIGHTING	Indicator	Baseline / Jan 2012	Milestone 1 / June 2013	Target / March 2014
50%	Implementation of IIA’s institutional capacity strengthening plan	Endorsed by MoF	50% of re-engineered business processes in place	Plan fully implemented and future development plan devised and ready for implementation.
		Source				RISK RATING
		Project reports				Medium

Endnotes and references