Business Case and Intervention Summary

Intervention Summary

## Title: Adaptation knowledge for policy and programming

What support will the UK provide?
£3.15 million over 2 years will be required for this adaptation knowledge programme to support a programme on adaptation knowledge and tools.

Why is UK support required?
The UK is now designing and implementing programmes under the UK’s International Climate Fund (ICF), a commitment of £2.9bn to climate change work. Other donors are also designing their Fast-Start adaptation programmes but the ICF is acknowledged as having shown a real lead on EU Fast Start programming to meet Copenhagen commitments, and puts the UK in a unique position in committing funds beyond 2013 as well. To maximise the effectiveness of this spend on climate change adaptation, advance work is required on guidelines and tools on adaptation programming including on monitoring and evaluation, and economic appraisals to ensure that funds generate maximum results and value for money. DFID also needs to support work on coordination and coherence around adaptation thinking across the global adaptation community – not least because DFID personnel working on climate change represent possibly one of the largest teams in the world working on climate adaptation. Lastly, in order to deliver on the Policy Division core offer to country offices, this funding is required to deliver an initial platform of information to all of those working on adaptation, or considering new interventions. Timely work under the proposed framework will help advance these areas while Business Cases are being developed and evidence in support of them is needed.

What are the expected results?
The desired outcome of the intervention is: ‘International investments in climate change adaptation (including from the UK) are of a higher quality and contain lower risks as a result of strengthened tools, knowledge about adaptation, and international coordination’. This is intended to ensure that results from adaptation programming – in terms of numbers of poor people helped to cope with the impacts of climate change – are as strong as possible. / The direct results expected from this knowledge programme are: / International investments in climate change adaptation (including from the UK) are of a higher quality and carry lower levels of risk as a result of strengthened tools, knowledge about adaptation, and international coordination: / Better knowledge around what constitutes best practice in adaptation. (Indicative budget: £850m). / Better international coherence and coordination around climate change adaptation. (Indicative budget: £1,545m) / Project management ‘tools of the trade’ are fine-tuned to support the effective delivery of ICF spending on adaptation. (Indicative budget: £720k). / Delivery on the PD Core Offer of first platform for an Adaptation Value for money themesite.

Business Case

Strategic Case

A. Context and need for a DFID intervention / 1. Climate change adaptation is a vital element of international action on climate change, and significant quantities of global climate finance are expected to flow to adaptation in the coming year and throughout the current four-year SR period. The objectives of the UK’s adaptation activities under the International Climate Fund (ICF) are as follows: / a strong role for developing the building blocks for adaptation – knowledge, capacity, institutions and evidence; / support for scaled-up delivery of direct adaptation programmes in a range of key vulnerable sectors – testing new programmes, identifying low regrets options, high co-benefits projects; / support for effective national- and international-level climate architecture to deliver adaptation financing / In the delivery of UK objectives on adaptation through the International Climate Fund (ICF), a number of gaps have been identified that could compromise our ability to deliver successful programmes and generate required results: / Firstly, there is a knowledge gap – no clear agreement exists internationally about what adaptation “looks like” or how to measure or demonstrate successful interventions especially in the short term. Bridging this gap will be a key element of the building blocks for effective adaptation. / Secondly, there is a coordination and coherence gap – this leads to limited understanding across the international development community of how adaptation actions and investments should be prioritised and how adaptation can be programmed most effectively. There is also no clear understanding about how adaptation should be most effectively planned and implemented at country or local level, or on how to scale up successful adaptation. There are also few channels for international dialogue on adaptation in practice. Without DFID’s continued engagement at the international level, the UK’s ability to influence as one of the largest adaptation donors diminishes. Unless some support is provided to better coordination and international coherence, building an effective architecture may also elude us. / Thirdly, there is a gap in the ‘tools of the trade’ for adaptation – key functions of the project cycle that are well-developed in other areas of development programming, such as M&E and economic appraisal, and options development have not been extensively applied, or adapted, to adaptation programming. The focus of this funding is thus to support shorter-term needs and gaps in policy and programming dovetailing with the longer terms research programme by RED on adaptation. / Most existing work, including research, focuses largely on responses to current climate variability with very little available in the way of evidence to help guide actions aimed at addressing longer-term climate change, and partly because the level of uncertainty around future climate scenarios makes longer-term planning difficult. This needs supporting research aimed at providing developing country and donor policymakers with evidence-related innovations, tools, technologies, and incentives that will help them prepare and plan for longer-term climate change. / These are important aspects of the knowledge agenda but and they are urgently needed for the immediate mobilisation of direct support programmes. Finally, it will also allow the adaptation team to deliver on our core offer to country offices. This is a Policy Division initiative tables in a recent Investment Committee paper on VFM in the sectors. The core offer will help develop a single platform for information on value for money, evidence, and research. The Value for money themesite for adaptation is expected to be up and running by December with core products developed before hand. / The proposed programme will help bridge the first three of these gaps and will directly enhance the quality of UK ICF spend, direct investments in-country, and the effectiveness of global instruments currently under development. It will do this by providing a framework, knowledge products and tools to help country offices and multilateral partners to enhance the strategic nature and the effectiveness of adaptation spend. It will also help develop the products necessary for developing our PD core offer, including the development and content over time of an Adaptation Themesite. A mechanism is proposed to enable quick deployment of resources to each of the areas of work (Policy and Knowledge, Coordination and Coherence, and Tools of the Trade). The ICF Board endorsed this concept in July 2011, and responsibility for making progress on the agenda is within the delegated authority of the Team Leader for Adaptation in DFID’s Climate & Environment Dept. liaising as appropriate with the Deputy Director as Head of Department. / The types of knowledge gaps being addressed will include: / How should decisions be made in an environment of uncertainty: can we build a set of policy principles to support decision-making? / What are the rates-of-return gaps in adaptation compared to non-climate development interventions? / What are “low regrets” and can we build a picture of these for supporting programming? Can we build this from information on vulnerability lock-in? / What is the most effective way of engaging with the private sector on adaptation in terms of modality by sector? / Can we build partnerships for dialogue and agreement, and coordinate a consensus on adaptation practices with the international community? / Aside from the global benefit of addressing adaptation more effectively, this work should also strengthen the UK’s hand in the climate negotiations, building the confidence of Southern governments in proposed adaptation investments overall. More broadly, it will be an important contribution to global thinking on adaptation, reinforcing the UK’s leadership on development and climate change, and providing the basis for stronger partnerships generally on global issues. / The proposed programme builds on RED’s existing and future programme on climate change adaptation research (currently largely, but not exclusively, focused on coping with variability[1]) and seeks to extend it to address research into adaptation and resilience to longer-term climate change. The RED research programme is focused on building a robust evidence base on: / who will be worst affected, when, where and why, including under different warming scenarios; / what works and what doesn’t (esp. when dealing with uncertainty) in what contexts – and why; / what the limits to adaptation are in different contexts; / which interventions provide best value for money or are most cost-effective in particular contexts and how best to assess/measure this; / how to build adaptive capacity/resilience, scale-up successful interventions and ensure sustainability – without undermining local accountability and governance mechanisms, especially given the potential impacts very large-scale on and off-budget climate finance may have in different political contexts; / how to identify and avoid maladaptation, and misattribution of environmental stress symptoms to climate change. / Alongside the research agenda, this proposed programme of ICF support for Adaptation knowledge for policy and programming was endorsed by the ICF Board for £4.75 million over four years, targeting short term needs in terms of programming and policy. It will also include programming gaps where there are synergies with other thematic teams especially on areas such as private sector knowledge products, support to the Monitoring and evaluation workstreams, and knowledge gaps on multilateral climate funds. / Current estimates suggest immediate needs for this work are around £3.15m over the first two years, leaving some space within the original ICF endorsement for further work to respond emerging needs – particularly in the context of the PD Core Offer and priority support to country offices. Any bid for resources between £3.15m and £4.75m will be the subject of a short Submission, or Submissions, for extension(s) in due course. This includes funding for the IIED work on Monitoring and Evaluation. The IIED work on M&E is part of the PD Accountable Grant with IIED with funding to be approved by CED and transferred to PD Cabinet for disbursement and reporting. The total included for this M&E work in the PD Accountable Grant is £2m. The first two years’ of this funding (£85k for FY11/12, and £860k for FY12/13) is included within the £3.15m of this Business Case. The subsequent two years’ (£840k for FY13/14, and £220k for FY14/15) will be the subject of a further Submission in due course, within the original amount of £4.75m endorsed by the ICF Board, and subject to progress with the work during 2012.
B. Impact and Outcome that we expect to achieve / The overall proposed impact is: / ‘Resilience strengthened of poor people in developing countries to climate variability and change’. / The desired outcome of the intervention is: ‘International investments in climate change adaptation (including from the UK) are of a higher quality as a result of strengthened tools, knowledge about adaptation, and international coordination’. / Outputs of the package, then would be as follows: / Output 1: Better knowledge around what constitutes best practice in adaptation including on social protection, local accountability, on private sector incentivisation. / Indicators: / Number of knowledge products produced / Number of hits on Adaptation Themesite and any formal or informal feedback / Increased number of programmes developed in Year 2 -4 of ICF as a result of information. / Output 2: Better international coherence and coordination around climate change adaptation including on monitoring and evaluation, on frameworks on adaptation, and on communities of practice around adaptation. / Indicators: / Visible replication of UK adaptation policies, programming and practices / Positive ICAI evaluation of the ICF and particularly of UK adaptation programming / Output 3: ‘Tools of the trade’ are fine-tuned to support the effective delivery of ICF spending on adaptation including on value for money, low regret options, guidance on cost benefit appraisals, and decision tools on uncertainty. / Indicators: / Number of hits on Adaptation Themesite by topic area / Uptake of Business Cases, and appraisals using Adaptation guidance / Visible replication of UK practices and guidance / This programme will support some assumptions within the Adaptation theory of change (attached below) especially with regards to gaps in evidence/tools being one of the constraints discouraging action. The activities and assumptions supporting delivery of outputs in the ToC around developing, piloting and supporting scaled up innovative and low regrets adaptation programmes include developing incentives on macro-level climate resilient growth, including new decisionmaking tools on uncertainty, and developing VFM and low regrets options. This proposed programmed is intending to enhance likelihood of change occurring. / Adaptation Knowledge products for policy development and programming under the proposed programme / Indicative £000 2011/12 Indicative £000 2012/13 Proposed partner Key product / Output 1- Knowledge and Policy / Support to Adaptation Partnership £200k Delivery partner/ mechanism tbc Key events for mutual learning and planning on key themes of relevance to DFID programming. This will have an element of international coherence to it, and will also partly deliver on Output 2. / Climate resilient growth case studies £35k £70k TBC Country case studies of application of climate resilient growth principles looking across sectors / Social Protection £50k £100k WB Policy guidance note on social protection can be used for ADA, and the social impacts of ADA interventions. Further development of knowledge product on insurance following the strategic review. / Insurance £50k Following systematic review, any subsequent policy development. / Policy and knowledge work around key economic questions (shared) £50k £100k TBC Follow up work on low regret options, more on economics of adaptation at country level and other questions emerging from the economic narrative for climate change within CED. / Coastal zone management, eco-systems and adaptation, gender and adaptation, community based adaptation - Policy and evidence coordination £150k Policy and knowledge on a range of adaptation knowledge and programming gaps. Compilation of knowledge and sector related adaptation evidence of what works / Subtotal £135k £670k £805 / Output 2- Coherence and Coordination / Adaptation Contact Group £100k £250k USAID and other donors Facilitated informal discussions with key strategic ADA partners. Specific knowledge products to feed into dialogue. Although the emphasis is on strategic coordination, this intervention will also deepen knowledge around adaptation, and so will partly deliver on Output 1. / Aid Effectiveness lessons learned for climate finance £50k £250k UNDP/OECD/Other partners Support to OECD/UNDP work on scaling up of public expenditure tracking surveys of climate finance. Action research/evidence papers on governance and issues around aid effectiveness and climate finance. / M and E methodology (Edinburgh group) £85k £860 Initially work led by IIED through the PD Accountable Grant Detailed work to develop methodology for M&E of adaptation, and build consensus around a common approach. Yr 3 and Year 4 budget forecasts 840k and 220k. / Subtotal £235k £1360k £1,595 / Output 3- Tools of the Trade / M&E ICF methodology (shared with other teams) £25k £75k TBC Detailed work to develop methodology for M&E of adaptation for UK ICF purposes supporting M&E workstream / Adaptation economic appraisal guidelines and other economics of adaptation work (shared across teams) £50 £85k Metro-economica and other partners Detailed guidance for conducting economic appraisal of adaptation interventions including development of VFM open source database, comparative data and support to the Core offer. Follow on case studies / Decisionmaking in uncertainty – follow on work (shared across teams) £25k £150k TBC Case study work. Policy guidance and methodologies to be developed / Incentivising Private Sector action on Adaptation (shared across team) 30k 100k TBC Scoping of options for how donors can use private sector delivery mechanisms to support climate change adaptation. / Strengthening local accountability £100k TBC for IIED Tools and guidance to ensure empowerment and accountability are addressed in design of ADA interventions. / Support to conflict-proofing adaptation investments £75k TBC, but possibly International Alert Evidence and summary of best practice to feed into CED ‘How to Note’ on conflict-proofing ADA investments / Subtotal £130k £585k £715 / Total £500 £2,615 £3,115
[1] Eg through our DFD/IDRC Climate Change Adaptation in Africa programme.

Appraisal Case

A. Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / 1 Short-term knowledge gaps and needs of ICF country offices and CED programming on key policy areas addressed. 5 / 2 Coherence/direct link is built with ICF spend and evidence/knowledge 5 / 3 Innovative approaches and programming gaps encouraged and incentivised. 4 / 4 Global adaptation community facilitated and engaged on evidence, ways of working, and policy coherence 4 / 5 Value for money in terms of reduced staff time and reduced time delays of ICF implementation. 3 / 6 Knowledge sharing and active promotion with other pillars on adaptation priorities 3 / What are the feasible options that address the need set out in the Strategic case? / Option A: Develop business cases for individual knowledge interventions as and when they are required. This has the major disadvantage of significantly increased transaction costs for the ICF, as well as staff time in preparing paperwork. A devolved approvals mechanism can guarantee the necessary appraisal rigour (by using the DFID Business Case and professional QA), but does not burden the ICF, especially for spend less than £5m. By investing in knowledge and coherence in a more limited way, there is a risk that we do not respond to known gaps that we are aware could increase the efficacy of UK spend. / Option B: Conduct all capacity building work in-house. This would effectively be the “do nothing” intervention in this case: the scale of the task, and the degree of time required in international coherence and coordination alone, means that this essential workstream cannot be an in-house/admin activity, but can only be delivered using programme funds for the benefit of the global community working on adaptation – donors and counterpart governments alike. Also, this approach misses the opportunity to engage with innovative partners and cutting edge thinking. / Option C: Sub-contract all the key strands of the knowledge work to one thinktank. Working to date with ODI, IDS and IIED on some elements of this package, it has become clear that each brings their own comparative advantage to the adaptation world; aspects to this work (eg. the economic appraisal work) exist where none have previously demonstrated the necessary comparative advantage. Further, work needs to be overseen in-house with elements that are supported by others. / Option D: Single coherent framework to knowledge and tools on adaptation ensuring that individual pieces are commissioned in a coherent way and that the overall outputs are inter-linked. This is the approach discussed above. It also contains elements in it which are shared work across CED on private sector adaptation, on economics of climate change, on follow on work on monitoring and evaluation. / Output E: Single knowledge framework for all of CED combining all areas of climate change. This recognises the fact that some of the guidance and tools products as well as the monitoring and evaluation products are required across the three thematic areas in climate change. Therefore, it proposes a framework coordinated across all the thematic teams. In practice each thematic area (adaptation, LCD and forestry) would need a carefully worked up approach to knowledge programming even within a single programme.
B. Assessing the strength of the evidence base for each feasible option and likely impacts / The recent IPCC report on extreme weather events (SREX) circulating in draft form with a Policymakers Summary prior to formal publication of the full report in February, highlights the need for developing both the short term knowledge gaps on what works, allocation decisions, understanding low regrets, building in robust building blocks as well as the longer term evidence of vulnerability and what is good adaptation. The IPCC is also interested in improving the level of agreement on evidence and level of confidence that people have in the findings. The table below highlights the quality of evidence for each option rated as either Strong, Medium or Limited. / Option Evidence rating Climate change and environment category (A is high risk, B (medium risk/medium opp), C, D is through a multilateral fund) / A – Individual business interventions Medium evidence that this model could work in developing coherence in terms of knowledge. B Transactions heavier, more time consuming, therefore likely negative impacts on full ICF programme are high. / B – In-house capacity (“do nothing”) Medium – Through 10% cadre inputs, it is possible to produce strong quality but perhaps not on a timely basis. A High risk that with in house staff capacity insufficient to deliver the outcomes. Transactions heavier, more time consuming, therefore likely negative impacts on full ICF programme are higher. / C – a single Thinktank Strong evidence through the evidence supporting the accountable grants that they can deliver A High risk that they don’t have the breadth of experience nor can deliver on a timely basis the full breadth of knowledge gaps. / D – Coherent framework for adaptation Strong. This is effectively what good policy teams can achieve. B High potential for delivering on time, with a medium risk that value for money is compromised outsorsourcing to multiple partners. / E – CED framework Strong evidence exists. Effectively, the model that most departments operate under. B The risks of this are delays to the full knowledge deliverables particularly on the adaptation team’s’s ability to deliver against the core offer. / A summary shortlisting of these options is presented below: / Option A has been shortlisted as it proposes that we simply bid for individual outputs and negotiate each contract separately. This is similar to current operations for developing knowledge and tools. It will considerably slow down the process of approving knowledge production and delay the benefits from coherence. / Options B and C have been discounted because further delays would be encountered if all this work is done in-house. The benefits from this work will translate into ICF programming and therefore delays to impacts from this framework will be visible in ICF portfolio quality of adaptation interventions. / Option C will take too long to procure and given the combined need for in-house and external inputs required for the desired impacts, this would both delay impacts, possibly result in less optimal results with less control over products. There seems to be no perceived benefit of going with one single provider for such disparate outputs. / Option D whilst this is the preferred option and ensures the most cost and time effective approach, there are potential losses with less coherence with other climate themes (LCD, forestry). It offers the best balance between coherence, impacts, and cost and time effectiveness. The synergy is kept with the other teams by having approval of line items that would be shared across teams. / Option E implies delaying approvals to accommodate the full spectrum of climate themes into a single knowledge and tools framework. This may make sense longer term, but could reduce the overall potential for other adaptation-specific knowledge products and potentially create more transactions costs where the total value of the knowledge framework rises above £5m. / This suggests that of the above, only Options A, D and E are worth considering further.
C. What are the costs and benefits of each feasible option? / Given the highly qualitative nature of this knowledge framework, a qualitative assessment of the benefits under each feasible option of A, D, E was considered. Assessed against a range of factors linked to the expected outputs, the shortlisted options are the strongest and most feasible and each come with their own tradeoffs. The first option may involve greater scrutiny of each piece being considered but trades-off value for money in terms of staff time. The fourth option although the preferred in this analysis, also trades-off the fact that staff time will still be strongly required to manage the various components and therefore would be less effective than fully contracting to a single supplier. Finally, the last option which would be the best in terms of policy coherence, could in fact potentially delay further whilst the needs of adaptation, LCD and forestry are handled under a super-knowledge framework of some kind. / Direct environmental and climate change impacts are very limited from these programmes. It will largely be restricted to office consumables and travel which can be minimised. Indirect effects of the programmes are potentially more significant as any adaptation programmes involve allocation decisions which will have wide-ranging environmental and climate change impacts. This programme will necessarily improve and help ensure that the assumptions (see examples of activities) laid out in the ToC in Annex A are achieved. Although the programme will not be undertaking major implementation activities, it will engage in the policy arena in a number of areas and may therefore indirectly be part of a causal chain that may result in actions that could have significant environmental impacts. / Social appraisal / Given how the knowledge framework is hoping to test many aspects of the Theory of change for adaptation which has at its heart the need to build resilience in the poor and vulnerable to the impacts of climate change – this framework ought to improve our understanding of these linkages better. Specific pieces of policy work will be included as part of the knowledge framework to target social issues. These include work on local accountability for climate change, adaptive social protection, and social appraisal guidelines. The WDR 2011 highlighted the importance of climate change as the defining social justice issues of our time, with powerful implications for inter-generational equity among national states an among individuals and groups within society.
D. What measures can be used to assess Value for Money for the intervention? / Value for money will be ensured through the competitive bidding for small-scale procurement contracts, through the strengthening of knowledge partners’ capacity to deliver adaptation policy and programming advice, through reduced staff time by removing the need for full business cases for each individual piece of work, and taking advantage of the economies of scale provided through other knowledge frameworks, and policy coherence built from the framework. / The guidelines and tools provided will also ensure an improved quality and lower risk profile to ICF investments of perhaps 1-5% of the full portfolio in each year, which could help strengthen the theory of change supporting the adaptation programme. / The programme will regularly assess its VFM and achievements of impacts, including through annual reviews, as part of the monitoring framework. Indicators developed under the logframe will be monitored in line with standard DFID procedures.
E. Summary Value for Money Statement for the preferred option / This work will add significantly to international efforts on adaptation, including through direct impacts on the quality of UK ICF spend, on direct investments in-country, and through global instruments currently under development. It will do this by providing a framework, knowledge products and tools to help professionals – including DFID country offices and UK-funded multilateral partners – to enhance the strategic nature and the effectiveness of adaptation spend. / Aside from the global benefit of addressing adaptation more effectively, this should also strengthen the UK’s hand in the climate negotiations, building the confidence of Southern governments in proposed adaptation investments overall. More broadly, it will be an important contribution to global thinking on adaptation, reinforcing the UK’s leadership on development and climate change, and providing the basis for stronger partnerships generally on global issues. It will also allow Policy Division to deliver on its offer to overseas offices. / The table below summarises potential interventions under each output. The current running estimate of need is some £3.15m over the next 2 years. One-page summaries of possible major areas of investment were provided with the concept endorsed by the ICF Board, some building on existing work and thinking. Some are already well-developed in terms of thinking (or already in existence), and members of the Adaptation team are poised to work up each. There are a number of other potential areas that could warrant support as adaptation information and evidence needs become clearer. This mechanism can be the main vehicle for supporting those needs over the course of the SR period. / Any bid for resources between £3.15m and £4.75m will be the subject of a short Submission, or Submissions, for extension(s) in due course. This includes funding for the IIED work on Monitoring and Evaluation. The IIED work on M&E is part of the PD Accountable Grant with IIED with funding to be approved by CED and transferred to PD Cabinet for disbursement and reporting. The total included for this M&E work in the PD Accountable Grant is £2m. The first two years’ of this funding (£85k for FY11/12, and £860k for FY12/13) is included within the £3.15m of this Business Case. The subsequent two years’ (£840k for FY13/14, and £220k for FY14/15) will be the subject of a further Submission in due course, within the original amount of £4.75m endorsed by the ICF Board, and subject to progress with the work during 2012.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Procurement will be handled through individual contracts under the umbrella knowledge framework. The framework, and any partnerships under it, will be managed by the Adaptation team in CED. In some cases, support may be a straightforward transfer to a multilateral partner, in others it may be part of an accountable grant. Where possible, the Adaptation team will seek to use existing contractual arrangements, such as accountable grants with large thinktank partners. There may be some direct contracting out, or even tendering necessary, and the team is carefully considering how to minimise administrative burden on CED to this end.
B. How does the intervention design use competition to drive commercial advantage for DFID? / As some of the knowledge is to support initially policy and implementation within DFID as determined by value for money drivers that are internal, a mixture of external providers will be used to deliver against the framework. Some components of Output 1 are likely to be short-term tenders selected either from existing resource centres or selected through small competitive bids. / In other cases, the work will be completed by known multilateral partners who have built a reputation and knowledge working in the particular area.
C. How do we expect the market place will respond to this opportunity? / There will be limited impact on the market as the market itself is both limited in breadth and depth in many of the policy areas. This knowledge framework will support a wider range of partners to develop and learn on the policy areas.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / A key cost driver will be staff admin time for various procurement exercises, and development of policy areas. ICF implementation will be improved by the use of a single framework and the savings that this will make through not developing a large number of individual business cases. Further costs will be associated with development of coherence, including through sharing guidance and policy with ICF implementation partners, to ensure investments deliver genuine value for money based on evidence of what works. / Value added from this knowledge partnership will be determined through delivery against an implementation plan which would have otherwise delayed impacts under other options. / A further element is the financial cost of procuring from a relatively narrow market as services will be required for slightly lengthier timeframes to deliver strong products.
E. What is the intended Procurement Process to support contract award? / Individual initiatives will be the subject of a short Submission for approval to the Team Leader of the Adaptation Team within CED. Individual tendering and contracting processes will take place only after approval of individual items.
F. How will contract & supplier performance be managed through the life of the intervention? / The contracts and suppliers will be managed by the relevant adaptation advisor responsible for different policy areas. Overall lead for the knowledge framework will be Shailaja Annamraju/Economic Adviser in the Adaptation Team in CED. There will be output leads within the Adaptation team who will be responsible for the implementation plan of individual outputs.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The range of knowledge products, urgency, the level of global knowledge and the comparative advantage of the main thinktanks requires a different approach to funding of these wideranging outputs. DFID will naturally be working with knowledge, private sector partners and donors with whom there is a natural fit in terms of expertise, interests and urgency. / The adaptation team will also liaise closely with the research programme in RED on adaptation that is being developed and use that as an input into the delivery of the PD Core Offer on adaptation by CED. However, unlike the research offer which has a homogenous set of outputs and therefore can be contracted to a single supplier, this knowledge framework is intended to support programming and policy and therefore is much wider ranging in terms of the content, expertise required, and products expected.
B. Value for money through procurement / The Adaptation Team will ensure that all work that is procured will build competition in the market and deploy a wide range of expertise from available providers.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The framework will be set up as a single Project on ARIES. Costs will be profiled for separate components against individual items and contract arrangements following approval on Submission to the Team Leader of the Adaptation Team in CED. Individual advisers and the Programme Manager in the Adaptation Team (Nicola Cairs) will remain in close contact with providers under each approved item to ensure that work is done, invoiced and receipted as required for the purposes of accurate forecasting on a monthly basis.
B. How will it be funded: capital/programme/admin? / This will be RDEL programme funding under the ICF.
C. How will funds be paid out? / Funds will be paid out against the Adaptation knowledge framework budget line. Each individual piece of work will have separate submissions sent to the head of the Adaptation team.
D. What is the assessment of financial risk and fraud? / The risk of financial risk and fraud is low. No DFID funds will pass to other governments as Financial Aid so there is no fiduciary risk from that perspective. Individual items of work under the overall framework for knowledge programming will be for small amounts to contracted providers under detailed contract arrangements. The issuing of contracts will ensure that a contractors financial processes and probity are not in doubt. Monthly forecasting based on close monitoring of required inputs will be undertaken through the Adaptation Team’s standard financial management procedures. Individual advisers will be responsible for confirming the quality of the work produced in accordance with the terms of the contract.
E. How will expenditure be monitored, reported, and accounted for? / Expenditure will be monitored through regular reporting against the three outputs, and monthly forecasting. Reports will be required as appropriate, depending on the cost and length of each individual item contracted. An Annual Report on progress with the overall framework will be prepared in line with DFID’s standard reporting procedures.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The Adaptation team will convene regular meetings involving others in CED as well RED to discuss the progress against the knowledge framework to assess whether it is indeed adequately supporting the theory of change for Adaptation.
B. What are the risks and how these will be managed? / The main risk to delivery of results from this work is of slippage of individual items, and the knock-on effects that would have on implementation – and therefore the return on investments from the ICF portfolio of adaptation work. This risk remains low to medium, but failure to develop some of these knowledge products could undermine the quality of the entire adaptation portfolio. / High turnover of DFID staff is a medium-impact risk for delivery of this framework, which is heavily dependent on staff knowledge and expertise. Effective recruitment and structured induction will help to mitigate this risk.
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / Progress against the three outputs will be monitored using the indicators outlined in the section on impacts and outcomes. These include in total: / Number of knowledge products produced / Number of hits on adaptation themesite and any formal or informal feedback / Increased number of programmes developed in Year 2 -4 of ICF as a result of information. / Visible replication of UK adaptation policies, programming and practices / Positive ICAI ICF evaluation and particularly of UK adaptation programming / Number of hits on adaptation themesite by topic area / Uptake of Business Cases, and appraisals using Adaptation guidance / Visible replication of UK practices and guidance / These will be relatively easy to monitor as the number of knowledge products produced can be easily counted through the Themesite and the PD Core Offer to country offices. Regular portfolio reviews conducted of the adaptation programme will also consider the quality of the programmes being developed through the ICF and the links to the knowledge work being undertaken. The most difficult indicator will be visible replication of UK adaptation policies and programmes.
Logframe: See logframe for adaptation.

2: Build global knowledge, capacity, and evidence which demonstrates climate resilient development
3: Develop, pilot and support scaled up innovative and low regrets adaptation programmes in key vulnerable sectors
1: Support effective national and international climate architecture to deliver effective adaptation finance
Climate change impacts specifically incorporated into planning and investments for a range of developing countries, UK ODA, other aid donors and MDBs
Assumptions:
- Vulnerable people, regions and countries identified and these countries demonstrate willingness to incorporate climate impacts in their decision making
- Private sector finance and delivery capacity is mobilised
- Local empowerment development between those most affected and decision makers
- A range of developing countries are willing and able to deliver low carbon climate resilient growth and poverty reduction by end of SR10 period
- Substantial finance and action on adaptation is prioritised for the most vulnerable coutnries
Theory of Change:
When climate change is incorporated in planning and investments not only a risk, but as integral to poverty reduction, it addresses the priority needs of vulnerable people
Vulnerable people in poor countries are prepared and equipped to respond effectively to existing climate variability and the magnified impacts of cc.
Impact
Outcome
Outputs
Example activities
-There are substantial gaps in evidence/tools.
-These act as a constraint to climate resilience and discourage action

Practical examples of adaptation across a range of sectors/countries will fill evidence gaps and encourage scaling up and replication in other sectors/ countries
Development of knowledge tools help inform demonstration projects and vice versa
Scale up low regret interventions in 6 priority sectors: urban, water resources management, agriculture, urban, eco systems and coastal zone management, social protection and DRR.

Improved architecture will increase the scale, efficiency and vfm of climate spend.
Lessons from demonstration activities inform discussions with MDBs and private sector
Capitalisation of national funds will, building on lessons from aid effectiveness, improve ada capacity in-country through strengthening institutions,,
Assisting in development of national plans and improving capacity of national bodies are necessary first steps in LCD capacity development
Testing out new ideas will generate lessons for design of scaled-up financing instruments
Better use of MDB finance will enable us to get greater vfm from a given amount of climate spend
International
Knowledge, evidence, and planning will help countries adopt most effective climate resilience strategies

-Lack of access to finance is a constraint to adaptation: if finance is made available, it will be taken up
-Donors are able to cooperate effectively
National
Knowledge
Capacity
Evidence
Institutions
   Implement low regret options
Test new programmes
Develop VFM, results, and M and E systems
Improve effectiveness of MDB channels including promoting mainstreaming of climate impacts
Ensure that the design of the Green Fund is effective for adaptation finance
Local empowerment and accountability mechanisms developed between decision makers and affected communities

Develop national and local governance and finance mechanisms for climate finance
developing the incentives to building in macro level climate resilient growth.
Climate proofing development programmes

New decision making tools which incorporate uncertainty developed
Encourage high co-benefits
-Pilot activities deliver and can be scaled up/replicated
-DCs are willing to adopt adaptation strategies having seen successful pilot outcomes