Business Case and Intervention Summary

Intervention Summary

## Title: Support to the Public Procurement System in Mozambique

What support will the UK provide?
Taking into consideration the progress Mozambique has made since the approval of its first regulatory framework on public procurement in 2005, this support programme will focus to a large extent on consolidating and strengthening the procurement reform. Significant improvements to the procurement system can be achieved by addressing the numerous human and institutional capacity constraints that exist. This includes strengthening the supervision function of the procurement oversight agency (UFSA) and improving the actual procurement operations in the procurement units (UGEAs) themselves – particularly at provincial level. Investment in information and management systems will help to get a comprehensive overview on the actual public procurement practices in Mozambique and consequently to better orient UFSA’s oversight function. As the technical expertise is considered particularly low at decentralized levels, the project will specifically concentrate on provincial institutions. / The general system strengthening approach will be complemented by a pilot in the education sector, with focus on contract implementation and supply chain management issues. Continuous interactions between UFSA and the pilot sector will help generate lessons that can influence other sectors and/ or future projects in this area. / The total estimated project cost over a period from 2013 to 2016 will be £4.97 million (equivalent to roughly MT198.73 million) with DFID’s financial contribution totaling £3,935,790 (79,2%, of the total costs). DFID’s support will consist of both Technical Assistance (£1,575,681) to UFSA and the Ministry of Education (MINED), and Financial Aid (£2,360,108) which will be transferred to the Ministry of Finance including the Provincial Directorates of Planning and Finance, as well as the Ministry of Education including the two pilot sites in Maputo and Cabo Delgado.

Why is UK support required?
Procurement is notoriously susceptible to corruption in all countries. This is increasingly a matter of concern in Mozambique. International corruption indicators have not shown much improvement over the past 10 years. Weaknesses in Mozambique’s monitoring and oversight and the dominance of public procurement in the economy make this even more acute. Although public procurement systems are not designed per se to combat corruption, it is internationally recognized that effective and transparent public procurement systems are a prerequisite for combating bribery and illicit practices. / Despite some noticeable improvements since the establishment of a modern legal framework in 2005, which was replaced in 2010 by the Decree 15/2010, the public procurement system in Mozambique still faces considerable challenges and risks. Various structural deficits – such as insufficient transparency and information on public procurement, weak internal control and audit mechanisms, or the lack of an effective capacity building system translate into a broad range of operational procurement issues, such as: / Insufficient documentation of procurement process including filing and archiving / Bad planning and timeliness of procurement processes / Non-compliance with procurement regulations on construction contracts for public works / Weak execution, supervision and quality control of public works, goods and services. / One important contributing factor to the low performance of the public procurement system is the weak institutional capacity of both the UGEAs and the oversight body UFSA. With most of the UGEAs, responsible for the actual procurement operations, having been put in place only after 2007, the public procurement system in Mozambique is still very young, and consequently inexperienced. Particularly at decentralized levels, the basic structures are not yet fully operational and have only limited technical expertise. / Whilst school construction and textbook purchase are considered two major issues in the national education system, it is recognised that procurement of goods and services in general is a concern in the sector. Procurement issues range from inappropriate and insufficient definition of standards, non-compliance with global building standards and specifications, lack of transparency in the award of contracts, lack of supervision and quality assurance in the contract management, and authorisation of payments without proper evidence of delivery. / The openness from the Government at present to strengthen the procurement system provides a good opportunity for DFID to enter into this sector.

What are the expected results?
In line with the indicator on procurement reform within the Performance Assessment Framework (PAF) for the General Budget Support (GBS), which links the ongoing efforts with the OECD-Assessment of the Mozambican Procurement System, the proposed impact of this project is: “The public procurement system in Mozambique ensures more efficient Government spending”. / The envisaged outcome of this project is: “Public institutions at the central and provincial levels run transparent and open procurement competitions”. / Outputs for this project include: / A reliable information management system for public procurement is established in the public financial management system e-Sistafe; / The distribution of roles and responsibilities between UFSA and DPPFs in the public procurement system is better defined; / The UGEAs at central and provincial levels master procurement regulations; / UFSA’s supervision activities are based on a comprehensive monitoring system of UGEAs; / UFSA ensures improved private sector access to critical procurement information and bidding opportunities; / MINED has the systems in place for more efficient and organized public procurement at central and provincial levels.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Context / International statistics show that 20% of the GDP in OECD countries is spent through public procurement process. In Mozambique, it is estimated that around 52% of the total public expenditures in 2010 occurred through public procurement. Approximately US$1 billion was spent on goods, services and public works. This accounts for approximately 29% of total public expenditure in 2010. A further 23% of the budget was spent on donor funded investment expenditure (some of which would also use government procurement).[1] / Despite the progressive decentralization of public services, most of the public spending still happens at central (65%) and provincial (27%) levels. The biggest sectors in terms of public spending are education (18%), infrastructures (17%) and health (7%). / The vast majority of DFID Mozambique’s overall support (£330 million) to Mozambique over the next four years will be channelled to the Mozambican Government – of which over half will go on General Budget Support (GBS), one quarter to sector budget support/common funds with the remainder on targeted projects. / DFID is a signatory to both the Paris Declaration on Aid Effectiveness and the Accra Agenda for Action. As a signatory, DFID has committed to both strengthening country procurement systems and using them to the maximum extent possible. At present DFID is among the donors that use Mozambican procurement systems the most. 91% of DFID aid disbursed to the government sector in 2010 used national systems.[2] / The legal framework for public procurement in Mozambique is defined in the Decree 15/2010, which was approved in May 2010 and replaces the first procurement decree from 2005. Despite several weaknesses, it is considered acceptable according to international standards, but its effective implementation is still lagging behind. / Following the development of the legal framework, which defines open competition as the default procurement modality and establishes the institutional set-up for the public procurement system, the 2008 Country Procurement Assessment Review (CPAR)[3] noted a number of improvements in the procurement system in comparison to 2002. / Macro management and oversight of procurement is carried out by the national oversight body UFSA (Unit for Supervision of Acquisitions), a unit which sits under the National Directorate of Assets within the Ministry of Finance. The role and mandate of UFSA includes coordinating all the activities related to public procurement and the management of a centralised data and information system as well as of the capacity development programmes in this area. It is also meant to oversee norms and disputes and ensure implementation of legislation and norms. / The actual procurement operations are decentralized to specialised procurement units (Operational Units for the management of acquisitions – UGEAs) within the different public institutions, which are located at central, provincial, district and municipal levels. According to UFSA, 869 UGEAs have been established between 2007 and 2011 at all levels. / Within the new national poverty reduction strategy (PARP 2011-2014) and its corresponding results matrix, governance and macro-economic issues are considered cross-cutting areas for sustainable poverty reduction. Improving the transparency and integrity of the procurement system is a key objective included in this strategy. Priority actions in procurement also feature very strongly on the Government of Mozambique’s Governance Action Plan (May 2010). / Procurement is notoriously susceptible to corruption in all countries. This is increasingly a matter of concern in Mozambique given that international corruption indicators have not shown much improvement over the past 10 years. Under the Worldwide Governance Indicator 2010 for the Control of Corruption 2010 Mozambique scored with -0.4[4] the same as in 2000.[5] Weaknesses in Mozambique’s monitoring and oversight and the dominance of public procurement in the economy make this even more acute. The World Bank Enterprise survey 2007 found that foreign and international firms expected to pay on average 2.4% of the value of the contract in a gift/ bribe in order to secure a government contract.[6] In the Mozambican national corruption survey 2010, 74% of people continue considering corruption as a “serious” or “very serious” problem. Corruption in procurement of government goods and services is believed to be substantial.[7] / The value of bribes in the construction sector may in fact be much higher. In a recent DFID financed political economy study of procurement in Mozambique[8], interviewees suggested that these bribes can range between 10% and 30% of the value of a contract in order to secure a bid. Corruption might thus also be one of the factors driving delivery of poor quality or incomplete schools. / Although public procurement systems are not designed per se to combat corruption, it is internationally recognized that effective and transparent public procurement systems are a prerequisite for combating bribery and illicit practices. / Need for an intervention / Partly due to donor pressure, the Government of Mozambique has recently shown increasing commitment to further strengthen the public procurement system. However, most of the challenges related to the effective implementation of the procurement legislation as well as the integrity and the transparency of the system, which were highlighted in the CPAR 2008, have not yet been addressed effectively. These include: / insufficient transparency and information to enable effective procurement management and public monitoring / the lack of an effective complaint mechanism to disclose abuse of the systems and allow for effective remedies / weak internal control and audit mechanisms sensitive to “red flags” on fraud and corruption to ensure enforcement and limit abuse / no effective capacity building systems mainstreamed into the national civil service systems / need for alliances within and outside Government to champion and ensure transparency and integrity in public procurement and maintain momentum of the reforms. / These structural deficits translate into a broad range of operational procurement issues, as identified over the past two years by a broad range of audit reports of public institutions and collected in a mapping study of public procurement concerns commissioned by DFID in 2012, such as: / Insufficient documentation of procurement process including filing and archiving / Bad planning and timeliness of procurement processes / Non-compliance with procurement regulations of construction contracts for public works / Weak execution, supervision and quality control of public works, goods and services.[9] / The Public Expenditure and Financial Accountability Assessment 2010 in Mozambique (PEFA)[10] confirms that the implementation of the action plan outlined in the CPAR report is still outstanding. The performance rating of the PEFA indicator related to the competition, value for money and controls in procurement (PI-19) has consequently not changed since the previous PEFA assessment in 2008 (rating the use of competitive bidding procedures and the existence of a complaint mechanism at B, and the justification in case of non-competitive bidding processes at C). / At the same time, the PEFA report 2010 particularly highlights that it is not possible to get a comprehensive overview on the actual public procurement practices in Mozambique given the lack of quantitative data in this area and very limited progress in establishing a reliable management information system. The procurement oversight agency (UFSA) has serious challenges in terms of information collection and management. For example, in 2010, UFSA only collected information about approximately 9% of all procurement carried out.[11] Improving collection and management of procurement information in conjunction with the Center for the Development of Financial Information Systems (CEDSIF)[12] is critical. / Similarly, the Annual Review of the PAF (performance appraisal framework) matrix 2011 states that “strengthening the capacity of the procurement system, in particular the approval of the procurement career and the establishment of an information management system for monitoring purposes” are critical priorities for public financial management.[13] In the 2010 assessment of government performance, budget support donors had highlighted that it was “crucial to fully implement the recommendations of the CPAR 2008, agreed by the Government, posing as an immediate priority the improvement of the UFSA’s (Unit for Procurement Oversight) monitoring and evaluation system”. / One important contributing factor to the low performance of the public procurement system is the weak institutional capacity of both the UGEAs and the oversight body UFSA. With most of the UGEAs, responsible for the actual procurement operations, having been put in place only after 2007, the public procurement system in Mozambique is still very young, and consequently inexperienced. Particularly at decentralized levels, the basic structures are not yet fully operational. Despite the ongoing capacity development efforts of UGEAs, only 40% of the 436 procurement processes reviewed by UFSA in 2011 were compliant with public procurement regulations.[14] / Limited technical expertise in procurement entities, particularly at decentralised levels, both in drawing up tendering documents and in assessing the quality of proposals has also led to a tendency to overly focus on cost and the lowest bidder. In school construction for example this has resulted in poor quality construction (e.g. schools with a maximum life-span of only 7 years). This is confirmed by various audit reports that have observed schools of sub-standard quality and/or incomplete construction.[15] / Whilst school construction and textbooks are considered two major issues in the national education system, it is recognised that procurement of goods and services in general is a concern in the sector. Procurement issues range from inappropriate and insufficient definition of standards, non-compliance with global building standards and specifications, lack of transparency in the award of contract, lack of supervision and quality assurance in the contract management and authorisation of payment without proper evidence of delivery. A number of these issues identified relate to unclear systems and procedures, insufficient expert guidance and specialized trainings and effective supervision. Given the emphasis stated in the PARP and the Education Sector Strategic Plan of 2012-2016 on quality of service delivery, the Ministry of Education needs support to improve procurement and get better value for money on the huge investments in the sector. / Working in partnership / The Government’s efforts to establish a public procurement system are part of the broader public financial management reform in Mozambique SISTAFE (within the sub-system of State Assets), which aims at establishing an integrated, harmonized system of norms and procedures for the application of PFM systems in all state agencies and institutions. The Ministry of Finance seems to be keen to advance with the procurement reform, and also a number of the line ministries (health, public works, and fisheries) interviewed as part of a DFID-funded political economy study expressed their desire for a strengthened oversight agency in this area. While the increase of UFSA’s annual budget from 9 million MT in 2011 to 14 million MT in 2012 can certainly be interpreted as a sign of increased Government commitment for this area, public procurement reform remains vague within the Government’s PFM Vision 2011-2025, without clearly defined strategic objectives and/or milestones. / Despite the high level of need identified and a shared concern within the international community about present procurement practices in Mozambique, only very few donors are currently supporting public procurement. This is despite donors’ increasing use of government procurement systems. Donors spent US$1.7 billion on aid in Mozambique in 2010, and 57% of this used government procurement systems, up from 38% in 2005.[16] DFID’s flexibility and relatively strong ability to work on PFM issues allow us to move the agenda forwards. / The World Bank is in the process of designing a new public sector reform programme focused on lifting key PFM and procurement bottlenecks in service delivery in Mozambique. If approved in 2012, technical assistance will be provided in PFM and potentially also in procurement at central and sector level. DFID is working closely with the World Bank to ensure that the two initiatives complement and mutually support each other. The Bank is a key partner given its expertise in this area. In addition, DFID is planning to collaborate with the German technical assistance GIZ, which has been supporting increased collaboration between UFSA and the Supreme Audit Institution and the Inspector General of Finance[17] (IGF) both at provincial and district level as integral part of its decentralization programme. / In the education sector, the Canadian Cooperation Agency is providing technical assistance to the Ministry of Education (MINED) in procuring text books and implementing related supply chain management. In addition, the German Development KfW is planning to fund technical assistance to the UGEAs responsible for school construction and equipment both at national (CEE) and provincial (UCEE) levels. This will include support to managing the entire tender process including preparation of ToR, evaluation of proposals and contract enforcement in combination with supervision of construction work. Once (the continuation of) these initiatives are fully confirmed, DFID will look at synergies with these programmes. / DFID priorities / Government procurement in Mozambique is a key fiduciary risk for DFID’s entire programme in Mozambique. The integrity of the procurement system is repeatedly identified as a key risk in DFID Fiduciary Risk Analyses. The DFID Operational Plan 2011-2015 states that “corruption appears to be a growing problem. Without progress in tackling corruption and strengthening accountability, future gains will be jeopardised. DFID will therefore prioritise funding in these areas.” The 2010 external evaluation of the CAP[18] found that DFID has paid “less attention to procurement risks” than to some other areas, and felt that “procurement needs more attention”. In the Ministry of Health for example, a sector where DFID is investing heavily, the Ministry’s UGEAs (procurement entities) are seen as “among the least organised of all line ministries at central level, with a high propensity to corrupt practices”.[19] / Beyond fiduciary risks, weaknesses in the system also pose reputational risks for DFID (our reputation can be threatened through actual or perceived misuse of funds). Strengthening procurement systems helps to protect DFID’s investment in the country and get better value for money. / The DFID Bilateral Review states that “we will support countries to manage their money more effectively, so that they get more for what they spend”. Accordingly, improving transparency and value for money and giving poor people more power and control over how aid is spent represent key priorities in DFID’s Operational Plan 2011-2015. A well-functioning procurement system is crucial for reducing waste and corruption and increasing efficient and effective use of aid money that uses government systems. / Accountability and Wealth Creation are critical dependencies of DFID’s Bilateral Aid Review. The current weaknesses in procurement have a negative effect on transparency in the use of public resources and on the environment for fostering a healthy private sector. DFID Mozambique’s Operational plan commits to complementing the significant investment in GBS with capacity-building projects and technical assistance in specific areas of economic governance such as procurement. / A strengthened public procurement system is a pre-condition for proper delivery of quality goods and services as well as efficient use of the limited resources. It is therefore a key factor for delivering tangible results in the education sector in terms of expanding access to education and improving learning outcomes. / A2: Justification for intervention / DFID Mozambique’s Operational Plan commits us to “targeted interventions on procurement to provide better Value for Money from DFID funds that use government systems”. There are significant potential savings to be made across government. DFID’s investments in sectors with high procurement (e.g. Education, Health) make this all the more important. / The challenges for improving procurement in Mozambique are significant and any intervention needs to take a long-term perspective that goes beyond this particular programme. The current procurement system presents considerable challenges and risks, from a technical as well as a political perspective. Many of the (more technical) risks can be factored into the design of a DFID programme (e.g. capacity challenges, coordination between internal control agencies, information management etc). Other challenges (e.g. the institutional architecture) are unlikely to be solved in the short-term, but the programme can respond to them by contributing to a public dialogue between national stakeholders regarding the adequacy of the current set-up, as a step towards reform. Untransparent procurement practices involving the private sector associated with the political elite and certain forms of aid (e.g. from Chinese companies) are unlikely to be directly addressed by this programme. However, there are a number of things that DFID support can do to improve aspects of procurement in the short-term, which can start to increase transparency in the system as a whole and open doors for increased engagement and dialogue around more political issues to be addressed in the longer term. / The openness from the Government at present to strengthen the procurement system provides a good opportunity for DFID to enter into this sector. Significant improvements to the procurement system can be achieved by addressing the numerous human and institutional capacity issues that exist. Investment in information and management systems, in improving the oversight and relevance of the oversight agency for individual procurement units and in strengthening the procurement units themselves – including at sub-national levels – could all have a significant impact. Improved information systems can also help to shed a light on the extent of procurement that is currently happening on the margins of the system. / Support through this programme for more analysis and advocacy around procurement can help address the lack of dialogue between the private sector, the Government, civil society and donors regarding the functioning of the procurement system (e.g. challenges the private sector face because of weaknesses in the process) and the architecture of the system. This has been identified as a key problem both by the CPAR 2008 review and by a more recent analysis commissioned by DFID.[20]
B. Impact and Outcome that we expect to achieve / In line with the indicator on procurement within the Performance Assessment Framework (PAF) for the General Budget Support (GBS), which links the ongoing efforts with the OECD-Assessment of the Mozambican Procurement System, the proposed impact of this project is: “The public procurement system in Mozambique ensures more efficient Government spending”. / The envisaged outcome of this project is: “Public institutions at the central and provincial levels run transparent and open procurement competitions”. / The programme will support as much as possible the implementation of the CPAR recommendations. Outputs for this project include: / (1) A reliable information management system for public procurement is established in e-Sistafe; / (2) The distribution of roles and responsibilities between UFSA and DPPFs in the public procurement system is better defined; / (3) The UGEAs at central and provincial levels master procurement regulations; / (4) UFSA’s supervision activities are based on a comprehensive monitoring system of UGEAs; / (5) UFSA ensures improved private sector access to critical procurement information and bidding opportunities; / (6) MINED has the systems in place for more efficient and organized public procurement at central and provincial levels.
[1] Public Expenditure and Financial Accountability Assessment in Mozambique 2010, MB Consulting in collaboration with the Chartered Institute of Public Finance and Accountancy (CIPFA), March 2011
[2] Government of Mozambique, Paris Declaration Monitoring Survey, 2011
[3] Update of the Country Procurement Assessment Review, June 2008, Republic of Mozambique and the World Bank Joint Report
[4] The score ranges between -2.5 for bad governance and +2.5 for good governance
[5] http://info.worldbank.org/governance/wgi/sc_country.asp
[6] World Bank Enterprise Survey 2007; see: www.enterprisesurveys.org/
[7] Mozambique National Anti-Corruption Survey 2010.
[8] The Political Economy of Procurement in Mozambique: Context, Institutions, Practice and Risks, Internal research paper.
[9] Analysis of Procurement Concerns; Study commissioned by DFID Mozambique, July 2012.
[10] Public Expenditure and Financial Accountability Assessment in Mozambique 2010, MB Consulting in collaboration with CIPFA and CIPFA, March 2011
[11] Ministério das Finanças, Relatório para a Revisão Conjunta Anual 2010, Versão Final, April 2011
[12] The GoM PFM reform agenda has traditionally included a strong emphasis on developing IFMIS modules and applications, to support core PFM processes. CEDSIF is responsible for developing, overseeing the implementation and maintaining the systems and hardware that constitute e-SISTAFE.
[13] Revisão anual 2012, Aide-Mémoire, 7 May 2012.
[14] Ministério das Finanças, Balanço da Implementação do Regulamento de Contratação de Empreitada de Obras Públicas, Fornecimento de Bens e Prestação de Serviços ao Estado, November 2011
[15] See Thorndahl Consult (2010). Procedural and Technical Audit of Danida Support to the Education Sector in Mozambique; Thorndahl Consult (2011). Follow Up to Financial and Technical Audit of Danida Support to the Education Sector in Mozambique (September/October 2010): Take Over and Final Settlement of Accounts; HTC (2010) Relatório de Auditoria e Verificação das Construções 2008 e 2009;
[16] Republic of Mozambique, Ministry of Planning and Development, Preliminar Report, 2011 Survey on Monitoring the Paris Declaration, April 2011
[17] The department within the Ministry of Finance which is supervising internal audit function
[18] DFID Mozambique’s Country Programme 2006-2009, Evaluation Report, May 2010, Evaluation Report EV712.
[19] See: www.enterprisesurveys.org/
[20] Procurement in Mozambique: Economics, institutions, reform and challenges, study commissioned by DFID, July 2011.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / A1. Feasible options that address the need set out in the Strategic case / Critical success criteria / Throughout the design phase of the project, various options and sub-options have been considered and assessed in light of their potential for success and/or risk of failure. Critical elements that fed into the appraisal are: (i) Likelihood to trigger effective change in the present procurement practices even if at limited scale; (ii) The best entry point for generating comprehensive and reliable information on national procurement practices with linkages to the broader PFM strategy of the Government; (iii) The need for a strengthened and well defined institutional set up of the national procurement system; (iv) National ownership and high level political leadership; (v) Broad stakeholder involvement (UFSA, UGEA, Line Ministries, Political leaders, private sector, CSO) across all project initiatives. / Identification of feasible options / While there is a strong interest of many stakeholders (Government, donors, the private sector and the broader public) in improving public procurement, it has proven difficult to establish consensus around priorities. Public procurement involves by its nature a lot of competing interests depending on the perspective of each stakeholder. And given that the procurement system in Mozambique is still in its very initial stage, support needs are widespread. / In order to achieve the proposed outcome of the project “Public institutions at the national and provincial levels run transparent and open procurement competitions”, the availability of comprehensive information about the public procurement system and operations, a strengthened and increasingly interlinked institutional set up, as well as increased interactions between the actors of the procurement system and the private sector are considered indispensable pre-conditions for the success of the project. / The following options are therefore starting from a “basic package”, which would form integral part of any intervention package if DFID decides to support UFSA in building up an operational public procurement system. Subsequently, it will be analyzed whether this “basic package” should be complemented by additional components, which by default would reduce the size of the “basic package”. Finally, this appraisal will consider the counterfactual, or “do nothing” option. / Three possible options had already been disregarded at the very initial stage of the project design. Co-funding a World Bank project on broader PFM issues, including procurement, was rejected, as this would have given less opportunity for DFID to influence effectively the policy dialogue on procurement and to take leadership on this topic within the broader donor community. Whilst this approach would have certainly facilitated donor alignment, it could have negatively impacted DFID’s credibility, if the World Bank intervention in this area is again delayed, as happened repeatedly in the past. / It was also disregarded to include the launch of the “reverse auctioning”-modality[21] as one major component of the project design, since the risk of failure was considered too high against relatively high investment costs even for a pilot experience. “Reverse auctioning” represents an important Government priority, and has also brought some important savings to public spending in Brazil. However, a study on this topic in preparation of this project could not provide any evidence that the necessary pre-conditions for a successful launch of this methodology, such as the existence of a vibrant private sector, are in place in the specific country context of Mozambique. Furthermore, capacities of UGEAs are considered too weak to be able to cope with the introduction of a new procurement modality, which requires a complete new way of doing business. DFID Mozambique prefers instead focusing on the effective implementation of the public bidding procedures, which is the default modality according to Mozambican legislation. / Investing into e-procurement[22] represents another important Government priority, which was rejected at an early stage of the project design given that the indicative budget for the respective e-Sistafe module (the public financial management system) would have largely exceeded the project budget. As no other donor has been interested in co-funding this initiative, it would have been very unlikely that DFID investment would have led to tangible results. Recognizing however the need for more comprehensive information on public procurement practices and increased linkages between the national procurement system and e-Sistafe, discussions with national counterparts and the World Bank around e-procurement led to the idea of designing a less complex management information function on public procurement within the existing e-Sistafe module, as outlined below as integral part of option 1. / Option 1: Basic package with general capacity building / What it consists of / Given that the public procurement system in Mozambique is still very young and consequently weak, strengthening its basic structures is considered a precondition for any successful intervention in this area. Therefore, the first option is taking a general system strengthening approach and will mainly focus on: better defining the institutional set-up and its interlinkages; creating systems for the collection and dissemination of comprehensive procurement information; strengthening UFSA’s oversight and coordination functions both with Government Ministries and the private sector; and investing into some basic capacity enhancement of UGEAs which are responsible for the actual procurement operations in the different Government institutions. / According to OECD, the procurement process can be divided in the following 5 phases[23]: / The inefficient use of funds can result from problems across the entire procurement process – from the definition of needs and creation of bidding documents, to a lack of transparency and competition in the tender process including announcement, bidding, evaluation and award of contracts, to poor contract supervision and final accounting. / Considering the size of the funding envelope and in order to avoid dispersion of activities, the project will focus primarily on the first three steps of the procurement process, which are particularly prone to corruption. It is recognized however that this approach might partly shift procurement issues from the first three steps towards the contract implementation phase. / How it works / Based on the consultant inputs and extensive consultations with UFSA, the following elements should be integral part of the “basic package” : / Output 1: The systematic and comprehensive collection of procurement information is indispensable for UFSA to gain a more realistic picture on the public procurement practices and to be able to take evidence-based decisions about key priorities. The execution module in e-Sistafe provides an excellent opportunity for the systematic collection of critical procurement information at the level of the UGEAs as integral part of the public spending process. Building on increased analytical capacities of UFSA, this information will not only serve as a basis for the preparation of more reliable public statistics on public procurement, but also provide a solid basis for more focused capacity strengthening and monitoring activities at the level of UGEAs. / Output 2 helps define the institutional set-up of the public procurement system and facilitates its standardization. By mapping the existing UGEAs and clarifying the roles and responsibilities of UFSA at central level and its provincial representation with the DPPF (Provincial Directorate of Planning and Finance), it also contributes to strengthening UFSA’s oversight role and its interaction with the different actors of the procurement system in view of aligning its operations increasingly to the actual needs. Furthermore, definition of career profiles will prepare progressive professionalization of the procurement function. / Output 3 enhances and standardizes capacity development of those entities that are responsible for the actual procurement operations within the different line Ministries. Based on lessons learnt from UFSA’s training support in the past, which only had very limited impact on the actual compliance of the procurement operations, the project aims at strengthening considerably the training component of UGEAs. On the one hand, it will enhance the basic training package for UGEAs from presently five to around 10 days adding critical training components linked to information management, interaction with the private sector and practical exercises. On the other hand, it will introduce additional training packages, such as advanced and sector-specific trainings (for the latter see output 6). In view of gradually preparing the professionalization of the procurement function, all trainings will lead to a certificate upon successful completion of a final exam. The project will also continue advocating for a progressive outsourcing and institutionalization of the procurement training within national training institutions, such as the Instituto Superior da Administração Pública (ISAP), which would also help free capacities within UFSA to focus increasingly on its monitoring and oversight functions. The detailed training programme will be designed following a comprehensive needs assessment and complemented by increased on-the-job trainings by UFSA and DPPFs. / Output 4 establishes a comprehensive monitoring system within UFSA, which will orient its supervision activities using a risk-based approach. The project is planning to introduce a complete new approach to monitoring visits, which aims at keeping the monitoring costs as low as possible. This approach entails that UFSA’s supervision visits will be followed systematically by support visits (visitas de acompanhamento) by the DPPFs to the public institutions in their respective provinces in order to systematize the follow up on respective recommendations. These support missions can be conducted at provincial level at no cost. Monitoring through supervision and support missions to those UGEAs most at risk, will be complemented by increased remote monitoring through UFSA’s Portal and systematic management and update of a comprehensive monitoring database. In coordination with GIZ, collaboration with IGF and the Administrative Court will be further strengthened. / Output 5 focuses on improving the quality of UFSA’s web Portal in line with OECD standard criteria in order to ensure that a broad range of private enterprises have access to critical procurement information and bidding opportunities. It will also help establish a harmonized supplier database within e-Sistafe in line with the national procurement legislation. In order to increase transparency of the public procurement system, and help overcome impediments of the private sector in participating in public tenders, output 5 will also facilitate increased interactions between UFSA and the private sector and the pilot UGEAs in the education sector. Lessons learnt will feed back into UFSA’s general communication strategy with the private sector. / All five outputs will mainly focus on the central and provincial levels, although some selected activities, such as the procurement trainings, might also involve selected districts. / Option 2: Basic package plus pilot experience in the Education Sector / What it consists of / A number of the country cases highlight that procurement reforms happen in “waves” or “generations”. Generally, the processes commences with legal and regulatory reform, establishment of institutions, such as a procurement normative and regulatory authority, training of officials, and initiatives to ensure access to information. These reforms are generally accompanied by initiatives to enforce and monitor compliance. This “package” is often referred to as “first generation reforms” and is generally expected to take up to ten years to complete. / While it is generally accepted that these reforms are necessary in building the basic structures upon which the system relies, it is recognized that they are not sufficient to meet the on-going demands for better governance and systems. As a result, some countries have moved towards a “second generation” of reforms, which focuses more on efficiency and effectiveness as well as performance measurement and management.[24] / Taking into consideration the progress Mozambique has made since the approval of its first regulatory framework on public procurement in 2005, the second option will also focus to a large extent on consolidating elements of the “first generation” of procurement reform (see “basic package” under first option). While this approach might therefore not lead to better service delivery and results that are easily perceived as such by the broader public, it represents a stable consensus between DFID and UFSA and can help enhance national ownership and leadership of the reform process. These are considered critical success factors for any effective procurement reform. / In order to raise awareness for the need of more sector-specific interventions and introduce a gradual shift towards better procurement performance (“second generation”), the general system strengthening approach of the first option will be complemented under the second option by a pilot in the education sector with an increased focus on contract implementation (phase 4 of the diagram under option1) and supply chain management issues. As such, it is based on an understanding of public procurement as integral part of the broader public financial management agenda. Continuous interactions between UFSA and the pilot sector will help generate lessons learnt beyond the tender process that can influence other sectors and/ or future projects in this area. As such, the expected results of the pilot will be partly outside of the theory of change, whilst strengthening considerably most of its actual components. It is also expected that the pilot experience might also help overcome certain resistances against change within UFSA and broaden the institution’s perspective of public procurement. / Given that education is part of the priority sectors of the World Bank PFM project (health, education, justice and agriculture), it will be critical to design a sound collaboration mechanism between these two projects in order to build synergies and avoid overlaps or duplications. / How it works / The same outputs 1 to 5 as under option 1 will be completed by sector-specific interventions under the leadership of the Ministry of Education (MINED) in collaboration with UFSA. Critical components of DFID’s support to the pilot sector (output 6) include the establishment of an integrated information management system within MINED (at central level and within the 2 pilot DPECs Maputo and Cabo Delgado), which will allow detailed tracking and monitoring of (on-going) procurement processes including contract implementation. This will be combined with the establishment of a comprehensive supervision system between the national and provincial level. The results of these efforts will be systematically shared with UFSA to facilitate better macro-supervision by the national oversight body. In terms of capacity building of UGEAs, the pilot component seeks to showcase effective improvement of procurement performance not only at central, but also at provincial level by complementing sector-specific procurement trainings with intensive on-the-job training in two pilot provinces. For this purpose, a national consultant will be assigned in average 2 days per week to each pilot province and will also act as project focal point at central level in view of facilitating effective coordination with UFSA. / The counterfactual – “Doing Nothing” / Not intervening at all has been rejected at an early stage of the project design. The current lack of support to the sector by other donors and the high level of need identified means that inefficiencies and corruption risks in the current use of Government finances are likely to continue. DFID’s focus on improved value for money and transparency and accountability in the use of aid makes this intervention critical, despite the challenges that exist. Despite the improvements that have taken place in the legislative framework and some improvements in the use of procurement systems, many of the critical elements identified in the 2008 CPAR remain unaddressed, particularly in terms of capacity, transparency and integrity. / There is a broad consensus among all stakeholders, including both the Government of Mozambique and the international donor community, that UFSA is still lacking the necessary resources to make an effective difference in the national procurement system. After various months of intensive consultations between UFSA and DFID, the project development has raised a lot of expectations at national level, and pulling out at this stage would represent an important reputational risk for DFID. It would also give a contradictory political sign towards Government about the importance of the procurement system. / That said, the two options outlined above will both be appraised against a hypothetical counterfactual that assumes no DFID intervention, in order to ensure that the programme benefits are maximised, and justify the costs. / A2. Appraisal of options / Theory of Change / Through this project, DFID intends to support the procurement reform in Mozambique in view of creating a more transparent system and thus facilitating more efficient public spending across all sectors, but with a particular focus on education. Generally, evidence about successful implementation of public procurement reforms in developing countries is rather weak, partly given that this topic has only received broader international attention after the Paris Declaration on Aid Effectiveness 2005 and the international commitment for increased use of country systems for aid delivery. There is however strong evidence that access to comprehensive and reliable information about public procurement is a critical pre-condition for more transparent and efficient public procurement systems, as without these data, the system cannot be monitored, reviewed and adjusted to achieve better performance. Many countries have achieved “quick wins” by establishing electronic websites to publish procurement related information, which can hugely increase transparency and access to information. While UFSA has already established an online Procurement Portal, its content and particularly the quality of published data still require major improvements. / The most critical precondition for a more transparent public procurement system is the establishment of a mechanism for the continuous collection of reliable procurement data. The use of electronic systems facilitates the collection and analysis of information that are also indispensable for effective oversight, internal control and procurement audits. E-Sistafe therefore represents a unique opportunity for capturing procurement related information in a systematic manner and linking at the same time the procurement operations to the public financial management cycle. More detailed day-to-day management information about on-going procurement processes in the education sector will be collected in a separate database within MINED, the results of which will be regularly shared with UFSA. As UFSA’s oversight, monitoring and capacity development functions are also hampered by the lack of overview about the scope of the public procurement system in Mozambique, it is furthermore necessary to conduct an extensive mapping exercise combined with a training needs assessment of UGEAs, which will inform the detailed implementation strategies for the remaining outputs. In order to ensure the actual use of the collected data for performance monitoring and management decisions, relevant stakeholders will be trained in the analysis, regular update and strategic use of the data. / Capacity development – procurement training / Compliance with procurement regulations still represents a major challenge in Mozambique. Only 40% of the audited procurement processes in 2011 were in line with the official rules and regulations. While any procurement reform needs to be supported by major training efforts, there is very little evidence that trainings have led to better performance in procurement operations. Experiences also show that the pace of capacity development is usually slower than hoped and might not necessarily lead to the desired results within the lifespan of the project. While experiences in Uganda have shown that the effective professionalization of the procurement function requires at least 9-month-training courses, it has so far not been possible to agree on a similar longer-term training approach with the Mozambican Government. Instead, the project design therefore introduces and/or strengthens the following factors of the public procurement training that have had a positive impact on capacity development initiatives in other countries: / The basic training package on public procurement, as well as the specific training related to the education sector will be reviewed and developed based on a consultative needs assessment and an evaluation of the current capacity level of UGEAs as integral part of the mapping exercise. / At the end of each training course, the participants will pass an exam in order to assess a certain set of qualifications and skills and prepare progressive institutionalization of the procurement training. This approach will facilitate progressive institutionalization and professionalization of the procurement function within the public administration. The content of the training will be broadened beyond procedural issues in order to include also, among others, corruption issues, interaction with the private sector and more practical sessions. / The project will facilitate broad stakeholder involvement in the capacity development efforts by extending UFSA’s training initiatives beyond the UGEA members. Specific trainings will be designed for a broad range of institutions and organizations that play a role in the procurement process. This includes training packages and workshops for Directors in the Line Ministries, for the administrative court, internal control and representatives from the private sector. / The effectiveness of the training will be closely monitored and complemented by a helpdesk function as integral part of UFSA’s online Portal. UGEAs will have the possibility to post practical questions through the Portal, which will be answered by UFSA on a daily basis. / In view of creating an enabling environment for the recognition of procurement trainings and qualifications, DFID Mozambique will closely monitor and advocate (as part of the project and through the budget support dialogue) for the approval of the professional career stream for the procurement function within the civil service. It will also try to facilitate progressive embedding of the procurement training into national training institution, such as ISAP. It is assumed that the professionalization of procurement will help reduce the high staff turn over and thus considerably enhance the impact of the capacity building efforts on the UGEA’s performance. / Monitoring / Capacity development initiatives in public procurement are more likely to succeed if they are complemented by a strong monitoring system. Even simple information management tools can be useful for tracking macro level performance. In Tanzania, the average level of compliance in local Government agencies increased from 40% to 66% and from 43% to 74% in central Government agencies over a period of three years following the implementation of a procurement management information system combined with systematic analysis of the collected data and strategic procurement monitoring and audit.[25] Therefore, the project will place a major emphasis on enhancing UFSA’s monitoring function by helping establish a comprehensive monitoring strategy, which will not only inform UFSA’s supervision activities, but also strengthen the role of the internal control and audit institutions in the area of public procurement. Complementary, it will also enhance the day-to-day supervision of procurement operations within MINED as pilot Ministry, with a particular focus on strengthening the relations between the national and provincial level. The results will also be fed back regularly to UFSA. / All monitoring information will in return again enhance the availability of data and thus contribute to a more transparent public procurement system. One necessary pre-condition is that UFSA will carry out various, including sector-specific, analysis of the procurement data in line with the stakeholders’ needs and share these analysis for performance reporting with senior authorities of responsible Line Ministries and relevant audit and internal control institutions. In Uganda, it has been critical that the collected information was shared regularly with the departmental directors of the Line Ministries, where corrective actions were generated as necessary.[26] / As civil society organizations have proven to be of good value for the provision of third party oversight on procurement and improve perceptions relating to corruptions, e.g. in the Philippines[27], the present project will involve local civil society organization in its annual monitoring and evaluation exercises. This might represent an opportunity to build on other DFID-initiatives in the country that support civil society in monitoring critical governance issues. / Outcome & Impact / Taking into consideration the still very low public sector capacity in Mozambique, the different outputs might only lead to minor improvements in the compliance of the tender processes. It can however be reasonably assumed that the strengthened institutional framework of the public procurement system will lead to an increased use of public bidding processes at national and provincial levels. Combined with increased interactions with the private sector and the broader public, but also through a Harmonized Bidder’s Database as integral part of e-Sistafe, the project’s efforts will therefore lead to a more transparent public procurement system. / By making the bid evaluation process clear, especially with respect to the bid announcements and evaluation criteria, a more transparent procurement system will build trust into the public procurement system and consequently lead to more active and competitive behaviour of suppliers, as experiences in the Philippines have shown, where many companies started bidding for the very first time for government projects after the procurement reform had led to increased transparency; e.g. in a bid published by the Department of Tourism six out of seven shortlisted firms had submitted a proposal for the very first time.[28] Given that increased competitiveness leads ultimately to lower prices of the bidding offers, transparent procedures can contribute to more efficient resource allocation and budgetary savings for governments, as reported by Nicaragua, which reduced its pharmaceutical budget by US$8 million after establishing a transparent procurement agency.[29] Again in the Philippines, procurement performance improvements led to 50% savings per unit for textbooks and 39% savings for each classroom that were procured in one Word Bank-financed project. While these two countries are certainly far more advanced in the procurement reform than Mozambique, they showcase the potential long-term benefits of DFID’s intervention if other donors are willing to invest into additional project phases. / Economic Impact / This programme should have a positive economic impact, largely through improving the efficiency and effectiveness of public expenditure. Section C below models economic benefits in terms of efficiency savings realised through improvements to the public procurement system and estimates that benefits worth approximately six times the costs could be delivered. / This intervention is also likely to have an impact on private sector competition. The increase in transparency of procurement system and the subsequent perceived increase of confidence in the system by private firms will increase their responsiveness with regards to public tenders. This could potentially translate into more firms competing for the same tenders, thus contributing to lower their prices. / Beyond the public expenditure impacts, this programme could have indirect positive impacts on growth but there is limited evidence to quantify what these might be or to what extent any causal link with this programme can be developed. Evidence does suggest that government spending in general, and in developing countries in particular, has a positive effect on economic growth[30] e.g. through more investment in public goods such as education, roads, health and energy. It is reasonable to extend this assumption to assume that more efficient public spending would have a larger impact on economic growth. / Governance Impact / Institutional capacity / Weak capacity of Government institutions throughout the public sector is one of the most lasting effects of the civil war in Mozambique. Particularly at provincial and local levels, the capacity of UGEAs is still extremely low. This is an important area of concern for both UFSA and the Ministry of Education given the decentralization process, as it poses enormous fiduciary risks for public spending and effective procurement operations. / Enhancing the institutional set-up and UFSA’s oversight function will be complemented by a large training component, which will facilitate skills development of procurement agents. Efforts to integrate the procurement function into the civil service career stream will contribute to attracting and retaining skilled staff through the professionalization of the procurement function. Creating incentives for line ministries to care about improved performance and enhancing the ability of the business community to monitor procurement decisions are equally important, since achieving sustained improvement in procurement is very difficult without the active participation of all stakeholders. / In the long run, better performing public procurement systems will contribute to greater respect for public procurement institutions and improved public service delivery of critical Government Ministries, leading to potential improvements in social sector services. / Accountability / Greater accountability is one of the key elements underpinning various components of the procurement project. It is both a means for better institutional performance and an objective in itself. Increased access to procurement information will allow better public monitoring of procurement issues and increase Government accountability for public spending both internally and externally. / By providing factual evidence on procurement practices across all Line Ministries and Government institutions and facilitating enhanced dialogue on procurement between all Government stakeholders, the project responds to ineffective supervision and accountability processes within the public sector (both at UFSA’s level and within the Line Ministries), which is one critical reason for the poor performance in public procurement. / Furthermore, the project will enhance the role of the private sector and civil society in monitoring public procurement. Through exchange fora between the Government and the private sector and participation of civil society in the annual monitoring exercise of the project, it will provide a space for a constructive dialogue about procurement issues between a broad range of government leaders, the private sector and other civil society groups. Thus, it will on the one hand enhance mutual understandings around critical procurement issues and requirements, and on the other hand serve as a feedback mechanism from a better informed public on existing concerns and obligations. Furthermore, an enhanced (and evidence-based) political dialogue between the broader donor community in Mozambique and Government stakeholders will contribute to raising awareness on procurement issues of the political elite, and help exert pressure on decision makers to ensure improved transparency and rule-of-law in this area. / Corruption / “Technical fixes alone are not enough”. Political economy issues linked to wider governance reforms need to be examined continuously. Issues related to public procurement are by their nature very political given that this area is particularly prone to corruption. Public and party officials can often play influential roles in the outcome of public bidding processes given the blurring boundaries between the economic and political elite in Mozambique. Also the Bertelsmann Transformation Index (BTI) 2012 Mozambique Country Report finds that “many public tender processes are severely flawed because of (the) conflict of interest” deriving from the involvement of the ruling party and certain families of the elite in public and private business. (…) Although the capacities of audit institutions like the administrative court have been strengthened, actual practices in public procurement are at the best obscure.“[31] / While it is unlikely that the project will reduce the risk that tender processes will be manipulated in favour of companies that are closely linked with the ruling party, a more transparent procurement system can make corruptive practices more costly and consequently less attractive. Based on the political economy analysis commissioned by DFID in 2011, which has identified a number of challenges regarding corruption in public procurement, the project foresees as integral part of its annual review exercises the creation of exchange fora, where civil society and the private sector can point out specific corruption cases or other challenges for improved procurement in the country. / At the same time, increased transparency and access to information will make corruptive practices more difficult, although it is has to be noted that public procurement systems are not designed per se to combat corruption.[32] / Conclusions / Using a pilot sector (option 2) will provide more tangible and visible results that can be transferred – at a latter stage – to other sector Ministries. In addition, the project design process has shown how critical it is to create closer linkages between UFSA and the Sector Ministries to avoid further fragmentation of the procurement processes. Therefore, option 2 is the preferred option from a technical perspective. / 5. Final accounting and audit / 4. Contract implementation / 1. Planning and needs assessment / 2. Product design, documents preparation, and procedures / 3. Tender process / General system strengthening / Education (pilot 2. wave) / Assumptions / - Sufficient resources at UFSA & DPPFs / - Monitoring data used for corrective actions / - Private sector participates in biddings / Improved participation in public tenders / Information about / - procurement operations: how is procurement happening in Mozambique? / - The universe of the public procurement system (UGEA, UFSA, DPPF etc.) / Through / - data collection / - training of stakeholders in the analysis and use of data and information / Supervision of UGEAs based on monitoring system and in coordination with TA and IGF / Procurement training of all stakeholders and day-to day assistance to UGEAs / Increased flow of information with the private sector / 5 / 4 / 6 / 3 / Improved internal control / More transparent public procurement processes / More competitive bidding processes / Efficient public spending / Integrity / Less corruption / Increased compliance with procurement rules / Enhanced confidence in the system / Clear institutional set up / 2 / OC / I / 2 / 1 / Outcome / Outputs / Impact / Strong relationship / Weak relationship / Impact / Outcome / Output / I / OC / 1 / Strong evidence / Medium evidence / Weak evidence / 6
[21] Under the reverse auctioning modality, procurement lots are auctioned to the lowest bidder, who fulfils the technical requirements.
[22] A fully-fledged IT-based procurement management system as integral part of e-SISTAFE
[23] OECD (2007), Bribery in Public Procurement: Methods, Actors and Counter-Measures, Paris; OECD (2007).
[24] OECD/DAC Working Group on Procurement, Strengthening Country Procurement Systems: Results and Opportunities, 2011, p. 141.
[25] OECD/DAC Working Group on Procurement, Strengthening Country Procurement Systems: Results and Opportunities, 2011, p. 79f, 144.
[26] OECD/DAC Working Group on Procurement, Strengthening Country Procurement Systems: Results and Opportunities, 2011, 123.
[27] OECD/DAC Working Group on Procurement, Strengthening Country Procurement Systems: Results and Opportunities, 2011, p. 143.
[28] Guillermo M. Luz, Transparency leads to competitiveness, in: Inquirer Net, 10 March 2012 (http://opinion.inquirer.net/24635/transparency-leads-to-competitiveness)
[29] Anne Janet DeAses, Developing countries: Increasing transparency and other methods of eliminating corruption in the public procurement process, in : Public Contract Law Journal vol. 34, no.3; Spring 2005.
[30] Nurudeen and Usman (2010), Government expenditure and Economic Growth in Nigeria.
[31] http://www.bti-project.de/?L=1; Published every 2 years, the BTI assesses the political and economic transformation processes as well as the quality of political management in 128 transformation and developing countries.
[32] OECD, How to fight corruption effectively, Paris, November 2007.

B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited. / Option Evidence rating / 1 Medium / 2 Medium / The overall evidence rating for both appraised options 1 and 2 is considered medium. It has to be noted that both options also include elements with strong and low evidence, as explained more in detail in the above theory of change. Strong evidence exists particularly for the possibility to obtain “quick wins” in terms of transparency of the public procurement system through the implementation of information management systems and electronic procurement portals. There is however little evidence on whether increased access to information will lead to improved participation in public tenders and thus to more competitive bidding processes. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / According to the assessment made, there is no evidence to suggest that any of the two options will place a significant additional impact on the environment or climate change. / The programme foresees however a lot of trainings and monitoring visits. Both components will include a lot of travel to and from the provinces, which evidently will leave a certain carbon footprint. In the interest of keeping the carbon dioxide emissions – and also the related travel costs – as low as possible, the project design will always combine various activities during one field mission whenever possible. By supporting progressive decentralization of monitoring responsibilities to the Provincial Directorates of Planning and Finance (DPPFs), it will further help reduce the number of related field trips in UFSA. / Furthermore, the production of training material will result in increased waste production. This waste can be minimised by putting in place best practices of waste management at different stages and places of programme implementation and by encouraging UFSA to use increasingly its Portal for publishing manuals, guidelines and other support documents. In this regard, it might even help reduce paper work in the long run.
C. What are the costs and benefits of each feasible option? / This section is a summarised version of a more detailed Economic Appraisal which is available as Annex 5. / C.1 Expected resource costs / The total cost of this programme and the distribution of the total envelope across outputs and types of expenditure will depend on the chosen option. / Option 1 – SUPPORT WITHOUT PILOT EXPERIENCE / Under Option 1, the total cost of the programme would be £4,018,022 over four calendar years. Table 1a below sets out the budget in detail – first by output and then by type of expenditure. / In terms of budget distribution across outputs the programme would have five outputs and a Management and Monitoring and Evaluation (M&E) component. Output 3 (application of legal procedures for public tenders) would receive the biggest share of the budget accounting for just above 34% of it, followed by the Management and M&E component with a total joint share of 32.8%, which is cross-cutting and contributes to all the other outputs. The lowest share would go to Output 1 (establishment of a reliable information management system on public contract system within e-SISTAFE) with 1.0 %. Despite its low share, Output 1 will be fundamental in contributing towards the creation a strong basis for a reliable and improved information management system. / Table 1a: Budget for Option One by Output / £GBP 2013 2014 2015 2016 Total % Total / Output 1 32,291 2,500 2,500 2,500 39,791 1.0 / Output 2 241,000 26,529 26,529 26,529 320,588 8.0 / Output 3 23,875 449,258 449,258 449,258 1,371,650 34.1 / Output 4 38,275 80,113 80,113 80,113 278,613 6.9 / Output 5 400 107,798 107,798 107,798 323,794 8.1 / Management and M&E (by UFSA) 35,575 17,325 69,650 17,325 139,875 3.5 / Management and M&E (by DFID) 270,000 270,000 368,438 270,000 1,178,438 29.3 / Budgeted Total (A) 641,416 953,523 1,104,285 953,523 3,652,747 90.9 / Contingency (10% of A) = B 64,142 95,352 110,429 95,352 365,275 9.1 / Grand Total (= A + B) 705,558 1,048,875 1,214,714 1,048,875 4,018,022 100.0 / Table 1b: Budget for Option One by Type of Expenditure / £GBP Total % Total / Technical Support / Fees CEDSIF 163,120 4.1 / Consultancies & related expenses 1,346,913 33.5 / Workshops: venues, refreshments and reproduction of documents 1,090,756 27.1 / Subtotal 1 - Tech support 2,600,789 64.7 / Administration / Travel: airfares, fuel and per diems (excluding consultancies) 942,425 23.5 / Equipment 29,000 0.7 / Communication and consumables 28,634 0.7 / Auditing 50,000 1.2 / Others 1,900 0.0 / Subtotal 2 - Administration 1,051,958 26.2 / Budgeted Total (A= ST1+ST2) 3,652,747 90.9 / Contingency (10%of A = B) 365,275 9.1 / Grand Total (=A+B) 4,018,022 100.0 / Table 1b presents the budget per type of expenditure and shows that programme technical support would account for a total of approximately £2.6 million (64.7% of the budget). Within this, consultancies would account for 33.5% and workshops would account for 27.1%. Administrative costs would be at just above £1 million (26.2% of total costs). Within this, travel costs would be key drivers at 23.5%; spend on equipment and communications and consumables would account for 0.7% each%, respectively. / On average, while approximately £236k would be spent annually on travel, annual spend on consultancies and workshops would be at approximately £337k and £273k, respectively. / Option 2 – SUPPORT WITH PILOT EXPERIENCE / The total budget for Option 2 would be £4.97 million over four calendar years. Table 2 below sets out the budget in detail presenting costs per output and by type of expenditure. / In terms of budget distribution across outputs the programme would have six (6) outputs and the Management and M&E component. Output 3 (application of legal procedures for public tenders) and Management and M&E would have the biggest shares of the budget with 27.6% and 26.5%, respectively. They would be followed by the pilot exercise in the Education sector with 17.4% of the budget. The lowest shares would go to outputs 1 (establishment of a reliable information management system on public contract system within e-SISTAFE) and 4 (supervision and monitoring of UGEAs) accounting for 0.8% and 5.6%, respectively. Despite these low shares these outputs would contribute towards the creation of a reliable and improved information management system (see Table 2). / Table 2a: Budget for Option Two by Output / £GBP 2013 2014 2015 2016 Total % Total / Output 1 32,291 2,500 2,500 2,500 39,791 0.8 / Output 2 241,000 26,529 26,529 26,529 320,588 6.5 / Output 3 23,875 449,258 449,258 449,258 1,371,650 27.6 / Output 4 38,275 80,113 80,113 80,113 278,613 5.6 / Output 5 400 107,798 107,798 107,798 323,794 6.5 / Output 6 311,388 184,117 184,117 184,117 863,738 17.4 / Management and M&E (by UFSA) 35,575 17,325 69,650 17,325 139,875 2.8 / Management and M&E (by DFID) 270,000 270,000 368,438 270,000 1,178,438 23.7 / Budgeted Total (A) 952,804 1,137,640 1,288,402 1,137,640 4,516,485 90.9 / Contingency (10% of A) = B 95,280 113,764 128,840 113,764 451,648 9.1 / Grand Total (= A + B) 1,048,084 1,251,404 1,417,242 1,251,404 4,968,133 100.0 / Table 2b: Budget for Option Two by Type of Expenditure / £GBP Total % Total / Technical Support / Fees CEDSIF 163,120 3.3 / Consultancy and related expenses 1,918,375 38.6 / Workshops: venues, refreshments and reproduction of documents 1,247,506 25.1 / Subtotal 1 - Tech support 3,329,001 67.0 / Administration / Travel: airfares, fuel and per diems (excluding consultancies) 979,850 19.7 / Equipment 108,000 2.2 / Communication, consumables and others 28,634 0.6 / Auditing 50,000 1.0 / Others 21,000 0.4 / Subtotal 2 - Admin 1,187,483 23.9 / Budgeted Total (A= ST1+ST2) 4,516,485 90.9 / Contingency (10%of A = B) 451,648 9.1 / Grand Total (=A+B) 4,968,133 100.0 / Table 2b presents the budget per type of expenditure for Option 2 and shows that programme technical support would account for a total of £3.3 million (67% of the budget). Within this, consultancies would account for 38.6% and training sessions and workshops would account for 25.1%. Administrative costs would be approximately £1.2 million (23.9% of total costs). Within these, spend on travel, equipment, communications and consumables would account for 19.7%, 2.2% and 0.6%, respectively. On average, almost £480k would be spent annually on consultancies, £312k would be spent annually on training sessions and workshops; approximately £245k would be spent annually on travel and related expenses. / C.2 Expected benefits of the intervention / This intervention is expected to produce substantial benefits via an improved procurement system. The specific mechanisms through which improvements are likely to happen will include: / Improved transparency through improved data collection methods and information management system and more interaction with the private sector. / Better compliance through capacity building and supervision of staff from UFSA, UGEAs and DPPFs the steps in the bidding process (planning, writing ToRs, biddings, awarding of contracts) would be correctly followed leading to cost savings through avoided mis-management; / The reduction (or elimination) of private sector inelasticity of the government demand due to an increased awareness about the institutional framework, rules and procedures. These could possibly contribute to more private sector firms bidding for state tenders and, ultimately reduce the price of offers. / More intensive capacity building in the education sector to include contract management and execution of contracts and tackling procurement as an integral part of the supply chain management. This would lead to cost savings and to improved quality outputs, and as such contribute to better cost effectiveness. / While this intervention will contribute towards the realisation of all benefits mentioned above, its activities will focus more on activities needed to realise benefits (i), (ii) and (iv). In addition, some activities will be conducted towards the realisation of benefits (iii). / In terms of the tangible benefits, the World Bank estimates that modest improvements in the workings of the system could potentially yield substantial savings of the order of 1 to 2 % of GDP and 8 % of public spending[33]. This latter estimate has been used as the starting point for this economic appraisal. / Methodology and key assumptions / For the purposes of this appraisal, benefits are defined as cost savings due to efficiency improvements. For each option efficiency savings are estimated by looking at total public expenditure which could be subject to efficiency improvements – in each case a base case which considers only government expenditure, and a high case which also considers expenditure through common funds which use government procurement systems. / Key assumptions include: / The DFID intervention will not implement the full set of CPAR recommendations and so is not likely to yield the 8% set of savings as estimated by the World Bank. It was assumed that it would contribute around 25% of what is needed translating into a maximum of 2% of savings / Given that Option 2 will entail a broad and focused day-to-day support to the Ministry of Education in addition to the more general support to the national procurement institutions under Option 1, it is assumed that option 2 will yield higher benefits than option 1. The maximum 2% efficiency benefits are estimated for option 2 and 1.5% efficiency benefits for option 1. / Efficiency improvements (and savings) are not expected to be realised before the third year. In the first two years the programme will get underway with training of staff, design and beginning of implementation of a transparent information management system, and other jumpstart activities. Efficiency savings are expected to start in year 3; however they are expected to continue beyond the intervention to 2019. / A base case assumes that benefits only accrue to internal (government own) spending on goods and services. A high case assumes that benefits also accrue to some of the donor resources channelled via common funds that also use government procurement (and that there would be no changes in the common funds that use government procurement over the period). / Modelled Benefits / Table 3 below summarises the benefits modelled using the assumptions above. / Under Option 1 the benefits are estimated to be range from £30.5 million to £32.2 million depending on whether the base or high case scenario is assumed. / Under Option 2 the benefits are estimated to range from £40.7 million to £42.9 million depending on whether the base or high case scenario is assumed. / Table 3: Estimated Benefits from intervention, Options 1 and 2, Base and High Cases / C.3 Balance of costs and benefits / The costs and benefits presented above are discounted at the rate of 12% (consistent with other DFID Mozambique economic appraisals) to enable comparison of costs and benefits in Net Present Value (NPV terms). / Table 4: Balance of Costs and Benefits, by Option / For a discounted cost of £3.0 million, Option One could yield discounted benefits totalling between £15.6and £16.5 million representing an overall positive net present value (NPV) for the intervention of between £14.4 million and £15.4 million, and a benefit to cost ratio (BCR) of between 5.8 to 6.13. / For a discounted cost of £3.7 million, Option Two could yield discounted benefits totalling between £20.1 and £22.0 million. This would represent a positive NPV for the intervention of between £17.0 million and £18.2 million and a BCR of 6.2 to 6.6. / This appraisal shows that Option Two yields the highest NPV and BCR indicating that the extra costs associated with Option Two are more than compensated for through additional benefits. / C.4 Sensitivity analysis / The results arising from the basic assumptions shown above are highly positive, and suggest very high rates of return. This is perhaps to be expected given that for small systems improvements, the efficiency of large procurements could be significantly enhanced. The key assumption in this analysis is that on the rate of efficiency savings. Different assumptions on the efficiency savings rate will change the estimated benefits of this intervention. However, this programme has also been identified as risky and so there is a good chance that these basic assumptions are not upheld. / Table 5 below shows how the analysis is affected if it is assumed that each option only yields half the savings assumed above i.e. 0.75% gains under Option 1 and 1% gains under Option 2. / Table 5: Sensitivity Analysis to Assumption on Efficiency Savings Rate (reduced by 50%) / Although the NPV of each option and associated benefit to cost ratios fall in this case, they remain positive and significant which indicates that even under this assumption both interventions would be worth undertaking, and that Option Two remains preferable to Option One. / C.5 Economic Risks / This intervention has a set of risks that would undermine the successful implementation of the programme in terms of outputs and outcomes (see Business Case, section B of the Management Case). If some of the identified risks are materialised, they would lead to delays in the accumulation of benefits (efficiency gains). In particular, delays in designing and beginning the implementation of a transparent information management system could have knock-on impacts across the rest of the programme. Last but not least, if the transparency of the procurement system does not yield the expected improvements there is also the risk that the private sector remains less responsive to public sector biddings and therefore, the impact on job creation, competition among firms (and price levels) and growth do not occur, thus limiting the potential of the intervention to maximise economic benefits. / C6. Other Economic Appraisal Considerations / In terms of the fiscal impact, this intervention will require GoM counterpart funding of the equivalent of 10% of the total costs. / This intervention is expected to have an impact on private sector competition. The increase in transparency of procurement system and the subsequent perceived increase of confidence in the system by private firms will increase their responsiveness with regards to public tenders. This could potentially translate into more firms competing for the same tenders, thus contributing to lower their prices. / Beyond the public expenditure impacts, this programme could have indirect positive impacts on growth but there is limited evidence to quantify what these might be or to what extent any causal link with this programme can be developed. Evidence does suggest that government spending in general, and in developing countries in particular, has a positive effect on economic growth[34] e.g. through more investment in public goods such as education, roads, health and energy. It is reasonable to extend this assumption to assume that more efficient public spending would have a larger impact on economic growth.
D. What measures can be used to assess Value for Money for the intervention? / In DFID, Value for Money (VfM) means the maximisation of the impact of each pound spent to improve the lives of the poor in an efficient manner. Value for Money can be measured at different levels: economy – capturing the unit costs of, and spending on, key inputs; efficiency – capturing the unit costs of, and spending on, key outputs; and effectiveness – capturing the unit costs of, and spending on key outcomes. / Key indicators to measure and monitor Value for Money at each of these levels are set out below. During programme implementation these indicators will be used as a management tool by DFID, UFSA and MINED in order to monitor the costs throughout the project-cycle. In addition, a number of logframe indicators at output and outcome levels should also be used to assess the extent to which VfM of UK public resources is maximised. / Value for money – Economy / The main cost drivers of this intervention will be consultancies and travel expenses including airfares, fuel and subsistence allowances. These will be carefully monitored over the life of the programme to ensure that costs do not escalate. / Indicator How to calculate Rationale Benchmark/ / Baseline Expected trend / 1. Share of consultancy costs (fees and related costs, such as airfares, fuel and perdiem) of the overall project budget / Total: outputs 1-6 / Output 6 (MINED) Total expenditures on consultancies / Total project costs[35] (accumulated and annual) / Expenditures on consultant costs under output 6 / Total costs of output 6 (accumulated and annual) Consultancy fees will be a significant cost driver within this project. Monitoring consultancy expenditures will ensure that actual spending is in line with plans and also help to avoid situations of cost escalations.. Benchmarks based on initial project budget (total): / Share of consultant budget of total initial project budget: 39% / Share of total consultant budget under output 6 : 59% High initially decreasing over time: The annual costs will vary according to the partners’ needs, but are likely to be high in the initial phases as systems and processes are established and then reduce towards the end of the project. / 2. Share of travel costs (not linked to consultancies) of the overall annual budget Travel expenditures (airfares, fuel and perdiems) that are not linked to consultancies / Total annual project expenditures (accumulated and annual) Travel expenditures are very volatile and are likely to escalate, as travel often represents some type of “incentive” for national partners. Monitoring them will ensure improved budget management and should lead – in case of escalation – to management decisions related to the frequency of travel or type and means of transport. Benchmark based on initial project budget (total): / Share of travel costs in total expenditures: 20% Increasing then stabilising: Travel costs are expected to be lower in year of implementation and then increase in year 2 and stabilise thereafter / 3. Selected unit costs: (a) Roundtrip airfare to the 7 most distant provinces from Maputo; / (b) Fuel for a trip to Maputo from the three closest provinces (Maputo Province, Gaza and Inhambane); / (iii) Catering during seminars and trainings; / (iv) Daily subsistence allowance for UFSA and MINED during official visits Average actual unit costs experienced throughout the year These four unit costs have been critical to the estimation of the project budget and so significant changes in any of these costs could have important implications for the overall budget. Benchmarks used for initial budgeting purposes (MZN): (a) 30,000 / ticket; / (b) 5,000 / province; / (c) 300 MT / person/ day; / (d) 2000 MT / person / day Stable but need to be kept under review: A priori there is no reason these costs should increase, but will be monitored given their important budget implications / Value for money – Efficiency / Indicator How to calculate Rationale Benchmark/ / Baseline Expected trend / 4. Costs of training per certified beneficiary / Basic training / Advanced training / Education training Total annual training costs of (a) basic, (b) advanced and (c) education-specific procurement trainings[36] / total no. of certified beneficiaries of each type of training as per output indicator 3.2 Monitoring how much the project spends per certified beneficiary of trainings will help understand the operational efficiency of the trainings. A baseline will be defined based on actual costs incurred and results achieved in year 1 / The workplan to be developed for 2013 may also provide an indicative benchmark for year 1. Reducing: Unit costs per candidate are expected to be stable, while the success rate of trainees is expected to increase slightly over time so the unit cost per certified beneficiary should fall / 5. Annual unit costs of a monitoring report (sum of supervision and follow-up reports) at / Central level / Provincial level Total annual travel costs (airfares, fuel & per diem) related to monitoring visits / no. of annual monitoring reports (sum of supervision and follow-up reports) at (a) central level and (b) provincial level as per output indicator 4.2 The number of UFSA’s supervision visits has been traditionally low given the high costs related to provincial travels. In view of raising considerably the support visits to the UGEAs, the project is testing a new – and far less expensive - monitoring approach combining UFSA’s supervision visits with cost-free follow-up visits by UFSA at central level and DPPFs at provincial level. This approach requires however many follow-up visits without any benefits of travel allowances. Baseline to be established based on actual costs incurred and results achieved in year 1. / The workplan to be developed for 2013 may also provide an indicative benchmark for year 1. Reducing: The no. of supervision reports (and related costs) is expected to be stable between year 2-4, but the no. of follow-up reports is expected to increase considerably without additional costs, so the overall unit cost should fall. / 6. DFID’s investment into DPPFs in relation to their contributions to the public procurement system (training and monitoring of UGEAs) Proxy indicator: / Annual trainings costs of DPPFs (airfares, fuel, perdiem and reproduction of training material) / no. of follow-up reports at provincial level prepared every year by DPPFs (output indicator 4.2.) In the past, the DPPFs have only played a minor role in accompanying provincial UGEAs, as their relation with UFSA has not been officially defined. At the same time, the project foresees considerable investment into the DPPFs hoping that they will play a major role not only in the training, but also in the monitoring of UGEAs. Given the unclear institutional relation, it will be important to monitor whether the DFID’s annual investment into the DPPFs leads to desired results (outputs) and continuous involvement of DPPFs into the project activities and the larger procurement system. No existing baseline as so far, the role of DPPFs in monitoring and accompanying UGEAs has not been documented. / Baseline will be established based on actual costs incurred and results achieved at the end of year 1. Reducing over time: The level of engagement of DPPFs is expected to increase from year 1 to year 4 but annual spending on them is expected to remain stable so the “unit cost” should fall. / 7. % Total budget spent on: / (a) Output 1; / (b) Output 2; / (c) Output 3: / (d) Output 4; / (e) Output 5; / (f) Output 6; / (g) Mgmt/M&E UFSA / (h) Mgmt/M&E DFID Total spending on given output / total spending / (Accumulated and annual) The budget has been allocated by outputs in a way believed to represent the most efficient allocation of resources across outputs to achieve the programme outcome and impact. If one output starts to take a larger share than planned, another outputs share will fall, which may have consequences for overall delivery. Benchmark as established in budget (total): / (a) 0.8%; / (b) 6.5%; / (c) 27.6%; / (d) 5.6%; / (e) 6.5%; / (f) 17.4%; / (g) 2.8%; / (h) 23.7% Annual variation depending on output (see original budget) e.g. outputs 1 and 2 will be higher in year one than subsequent years / Value for Money - Effectiveness / Indicator How to calculate Rationale Benchmark/ / Baseline Expected trend / 8. Share of supervised tender processes with complete documentation / central / provincial / education sector No. of supervised tender processes with complete documentation at each level/ total no. of supervised tender processes at each level (central, provincial and education sector)[37] Increased supervision of UGEAs by UFSA will increase the compliance of the tender process with procurement rules and procedures and will therefore contribute to good VfM of UK public resources from an effectiveness perspective Baseline from December 2011: / 40% of supervised processes with complete documentation (desagregation not available) Increasing: As the project aims at enhancing considerably capacities of UGEAs, it is expected that the share of tender processes with complete documentation will increase / The above VfM matrix still needs to be discussed with Government officials and can only be fully completed (for 1-2 indicators) at the first annual review, the preliminary version will become an integral part of the MoU to be signed between UFSA, MINED and DIFD. / In order to monitor these VfM indicators, UFSA and MINED will provide annually the following specific financial information linked to the main cost drivers: / Travel Costs: flight tickets, fuel and subsistence costs (across all project activities) / Training costs: (i) basic (act. 3.2); (ii) advanced (act. 3.2); (iii) specialized training in the education sector (act. 6.2) / Travel costs for monitoring the UGEAs: flight tickets, fuel and subsistence costs (act. 4.3) / Costs linked to the annual seminars and Training for the DPPFs: travel costs, logistics for the trainings (act. 2.3, 3.3 e 4.2)
E. Summary Value for Money Statement for the preferred option / Overall the proposed intervention has the potential to yield excellent value for money. Option 2 is the preferred option and is expected to yield discounted net benefits between £17.0 million and £18.2 million and a Benefit Cost Ratio between 6.2 and 6.6. / The programme is however not without its risks, many of which will affect the extent to which the economic benefits set out above can be realised. However, even if the assumption on the efficiency savings delivered by the programme is reduced by half, the programme could yield discounted net benefits of between £7.9 million and £8.5 million and a BCR of between 3.1 and 3.3. / Monitoring the proposed VfM metrics will be a key means of assessing the extent to which the programme remains on track to yield the benefits estimated here.
[33] CPAR (2008,ii)
[34] Nurudeen and Usman (2010), Government expenditure and Economic Growth in Nigeria.
[35] As per accumulated financial project reports
[36] Costs include (i) travel of trainers and/or beneficiaries, (ii) payment of venues, (iii) reproduction of training material and (iv) per diems
[37] See outcome indicator 2

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The project will combine direct and indirect procurement procedures. While the standard procedure will be indirect procurement (through UFSA and MINED), DFID will directly contract suppliers for the provision of goods and services for some activities of particular strategic importance. This will include, mainly the contracting of international technical assistance to UFSA and M&E activities that will be paid by funds set aside on the Technical Assistance budget component.
B. How does the intervention design use competition to drive commercial advantage for DFID? / Direct procurement by DFID will be only used for the following 3 services that relate mainly to international consultancies – (i) one individual international consultant as full-time assistance to UFSA for a period of three years, (ii) one framework contract for the provision of punctual specialized technical expertise and quality assurance at different moments of project implementation, and (iii) one consultant team for the mid-term evaluation. All providers will be selected following international public bidding processes. Supplier proposals will compete on the basis of delivering maximum impact in relation to the financial proposal with a strong focus on sound technical proposals given the limited expertise in public procurement at country level. / For the selection and contracting of a national-international consortium for technical assistance to UFSA and MINED, DFID will seek the support from Charles Kendall Consulting. This will drive a competitive approach to providing value for money, and ensuring that technically competent experts are selected and contribute for the successful delivery of the programme.
C. How do we expect the market place will respond to this opportunity? / For the framework contract and the external evaluation, we expect that it will be difficult to identify an international consultant company with both the required technical expertise, fluency in Portuguese and the necessary sound knowledge of the Mozambican context. As all these criteria are however considered indispensable for the success of the project, both contracts will ideally be based on partnership between and international and local consultant company in order to ensure that high quality interventions are adjusted adequately to the Mozambican context. / For the full-time technical assistance to UFSA, it is fundamental that the consultant (an international consultant is likely to have greater independence in case of political blockages than a national one) will be able to communicate and work in Portuguese with Government counterparts. This might however place some limitations on the number of interested parts. Therefore, also consultants based in Mozambique have the opportunity to apply if they have the necessary experience and knowledge to help deliver the programme and lead the change management process. For the final selection, the necessary technical requirements will be balanced with Portuguese language skills.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Key cost elements are consultant fees and related travel. The decision to base the framework contract for the provision of targeted technical support on an national-international partnership was also influenced by cost-effectiveness reflections. National consultants are slightly cheaper than international ones and do not involve any international travel costs. While experiences during the development phase of the project have shown that technical expertise in public procurement at national level is rather weak, we consider that there are at least some local companies with a strong background in broader public financial management issues that could bring very good value for money if they partner with an international procurement agent. / Consultant costs will be monitored throughout the lifespan of the project as integral part of the VfM measures (at economy level).
E. What is the intended Procurement Process to support contract award? / Terms of Reference for all consultancy inputs will be approved by UFSA and MINED and agreed with DFID prior to starting of the procurement process. While DFID is taking the lead in the procurement process, UFSA and MINED will be equally involved in the selection process and the selection of the supplier will be done based on consensus. All contracts will be awarded based on satisfactory delivery of the outputs. / Terms of Reference for all consultancy inputs will be approved by UFSA and MINED and agreed with DFID prior to starting of the procurement process. While DFID is taking the lead in the procurement process, UFSA and MINED will be equally involved in the selection process and the selection of the supplier will be done based on consensus. All contracts will be awarded based on satisfactory delivery of the outputs. / As the value of the framework contract for targeted technical assistance is over the threshold of the EU Public Procurement Directives, DFID is required to advertise it in the Official Journal of the European Union (OJEU). This will be done through DFID’s Procurement Group (PrG) in October 2012 with the intention of awarding the contract in January / February 2013.
F. How will contract & supplier performance be managed through the life of the intervention? / All contracts will specify clear deliverables and milestones and payments will be linked to these. Supplier performance will be monitored jointly by DFID Mozambique, UFSA and MINED in close coordination with the Partner Committee.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The standard funding mechanism of the project will be channelling funds through the State Asset Directorate of the Ministry of Finance, within which UFSA is located. From there, funds for activities linked to the education sector will be further channelled to MINED (see also section C of the Financial Case). Procurement for related project activities will be undertaken by the MF and MINED as the main counterparts of the project in accordance with national procurement regulations and procedures. / Channelling Funds through the Ministry of Finance is the preferred option because doing procurement through Government systems: / will enhance Government systems and existing public financial management structures within the Ministry of Finance / reflects a coherent approach with the project objective in itself, as it is focused on strengthening the national procurement system / can potentially empower UFSA within the overall institutional set-up and strengthen its coordination role, as it is still a relatively young unit / As ensuring transparent and strong procurement processes is at the core of UFSA’s mandate, it can be reasonably assumed that its procurement processes will follow rigorously national procedures, maximize competition and maintain the necessary integrity of the process. The main challenge will be to ensure that UFSA/MF and MINED take quality standards sufficiently into consideration when assessing the biddings. / Given the substantial fiduciary risk of the project, it has been decided as a safeguard to provide £1,575,681 (40% of the total funding envelope) as technical assistance, which will be directly procured by DFID.
B. Value for money through procurement / Using government systems to procure good and commission services reduces management costs, increases efficiency through economy of scale and develops sustainable procurement capacity within government. All these elements will help provide value for money. / We expect that the procurement will take into account quality, timeliness and cost (more than just the price) factors. The project activities themselves will allow us monitoring procurement issues very closely and propose changes that will help to deliver the project outputs within the agreed timescale.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The total estimated project cost over a period from 2013 to 2016 will be MT198.73 million (equivalent to £4.97 million[38]) with DFID’s financial contribution totaling £3,935,790 (79,2%, of the total costs). The Government’s contribution is expected to be MT 41,3 million (£1,032,346) out of which MT 40,6 million by the Ministry of Finance (MF) and MT0.7 million by the Ministry of Education (MINED). A detailed budget is provided in annex 2. / Over time, stakeholder contributions (DFID, MF and MINED) per calendar year are expected to be as follows (in MT): / Contributions 2013 2014 2015 2016 Total (MT) Total (£) / Amount DFID 40,681,670 36,705,442 43,338,992 36,705,442 157,431,545 3,935,789 / Amount MF 1,219.684 13,120,067 13,120,067 13,120,067 713,900 1,014,497 / Amount MINED 22,000 230,633 230,633 230,633 40,579,884 17,848 / Total 41,923,354 50,056,142 56,689,692 50,056,142 198,725.329 4,968,133 / The breakdown of the budget across the programme outputs is estimated to the following (in £): / Project Outputs Estimated project budget (£) Estimated DFID contribution (£) Estimated Gov.[39] contribution (£) / Output 1: 39,791 28,258 11,533 / Output 2: 320,588 276,238 44,350 / Output 3: 1,371,650 741,025 630,625 / Output 4: 278,613 186,588 92,025 / Output 5: 323,794 180,056 143,738 / Output 6: 609,738 593,513 16,225 / Management & M&E – transferred to UFSA 139,875 139,875 0 / Management & M&E –DFID TA and Mid-term evaluation 1,432,438 1,432,438 0 / Subtotal 4,516,487 3.577.991 938,496 / Contingency (10%) 451,649 357.799 93,850 / Total 4,968,136 3,935,790 1,032,346 / As the project will combine both direct procurement through DFID and indirect procurement through the Ministry of Finance (MF) and the Ministry of Education (MINED), two budget components – one for Technical Assistance (TA) and one for Financial Aid (FA) – will be established for DFID’s contribution with the following spending profile: / DFID contribution 2013 2014 2015 2016 Total (£) / FA 650,192 550,786 608,344 550,786 2,360,108 / TA 366,850 366,850 475,131 366,850 1,575,681 / Total 1,017,042 917,636 1,083,475 917,637 3,935,789 / The TA funds that will be managed directly by DFID (£1,575,681 incl. contingency) are mainly linked to technical assistance and the mid-term evaluation of the project (activities listed in Section B under Direct Procurement). / While the planning cycle of the project will follow the one of the GoM, DFID’s contribution will roughly translate into DFID’s financial years as follows: / DFID contribution 2012/13 2013/14 2014/15 2015/16 2016/17 Total (£) / FA 400,000 560,000 599,350 550,800 249,958 2,360,108 / TA 150,000 370,000 363,650 475,131 216,900 1,575,681 / Total 550,000 930,000 963,000 1,025,931 466,858 3,935,789 / DFID’s financial forecaster will be updated bi-annually: / Beginning of February of each year based on the approved annual work plan of the project and the identified cash flow needs; / In July of each year according to the actual delivery rate of the project. The related assessment will also influence the forecaster of the subsequent years. / Financial Aid / The standard procedure will be the transfer of funds to the Ministry of Finance (£2,360,108 benefiting UFSA, CEDSIF, and the DPPFs as well as the Ministry of Education including the two pilot DPEC). / The responsibility for the management and execution of the funds that are transferred to the MF will be shared between the National Directorate of State Assets (DNPE) in MF (for UFSA, CEDSIF and DPPFs) and the Directorate of Administration and Finance (DAF) of MINED (for the education sector including the two pilots DPEC). / UFSA will be responsible for managing payments to the suppliers of UFSA and DPPFs as well as for the component to be implemented by CEDSIF. MINED in turn will centralize the execution of the pilot component (output 6) and all payments linked to the two pilot provinces. This centralization of payments for both UFSA and MINED will require that payments be made ​​directly to suppliers via e-SISTAFE based on original documents. In case of per diems, an advance of funds will be made to DPPFs and DPECs, who will be responsible for sending back to the central level the proof of payment including all required documentation. In detail, management responsibilities for DFID funds are distributed as follows: / Responsible entity for the management of DFID funds Amount (£) Description / DNPE / UFSA 1,707,244 Outputs 1–5 and managements costs related to the launching, M&E and auditing of the project / MINED / DAF 652,864 Output 6 / Total 2,360,108
B. How will it be funded: capital/programme/admin? / The full funding for this programme will come from programme resource allocation and has been budgeted for in the Operational Plan for DFID Mozambique (2011 – 2014/15). Since the programme will run until 2016 (beyond the current spending round), it will be necessary to obtain approval from HM Treasury for the period 2015/2016 and 2016/2017, once the Business Case is approved.
C. How will funds be paid out? / DFID’s financial support to the reform of public procurement through this project will be properly registered in the State budget as a project financed by external resources with internal resources shared by both the MF and MINED. For the first year of the project, the deadline for registering the project in the State Budget, which is approved by Parliament in December, is likely to be missed. This, however, will not constitute an impediment since projects financed by external resources can be registered into e-SISTAFE and executed in-year i.e. even after the budget has been approved. / The funds will be transferred to the multi-currency single treasury account (CUT), and project expenditures to contractors and suppliers will be processed through the electronic public financial management system e-SISTAFE and reported in aggregate form in the State’s Accounts (budget execution reports - REOs and general state account - CGE). / In terms of flow of funds, DFID will transfer the funds destined to both institutions to a Forex account that will be indicated by the Ministry of Finance for this project. The funds will then be transferred to the CUT and registered in State Budget as a project financed by external resources linked to a budget unit - DNPE. At the beginning of each year, after approval of the budget, the portion of the funds relative to the component of the Education Sector pilot will be decentralized to MINED for implementation of the planned activities. The implementation of the project in the two institutions will be reflected in the Quarterly Budget Execution Reports. / Diagram on the flow of funds / This programme will be subject to a detailed annual planning and budgeting exercise that will clearly define the annual cost of the programme by funding source, disaggregating the respective contributions of the Government (MoF and MoE) and DFID. / In addition to the bilateral agreement with the GoM (Exchange of Letters), a MoU will be signed between UFSA, MINED and DFID which will set out the roles and responsibilities of each stakeholder, related planning, accounting and reporting requirements, and the terms in which the funds will be made available. / UFSA must send requests for disbursement of funds for all project components (including funds for the education sector) to DFID on a bi-annual basis, according to the agreed schedule and with reference to the products to be financed. / DFID funds will be disbursed upon submission of request of funds including the following documents approved by the Partner Committee: / the progress report including the financial report for the previous period in line with the agreed formats in the MoU to be signed by DFID, MF and MINED / the annual workplan, budget and expected cash flow of the project for the subsequent period / All plans and project reports will be joint documents from UFSA and MINED, under the overall coordination of UFSA. DFID will ensure that funds will only be disbursed if the remaining balance from the previous disbursement is lower than 25%. In case, all funds disbursed in the previous period have been spent prior to the mid-year Partner Committee meeting, the second disbursement of the year can be made exceptionally without approval of the submitted documentation by the Partner Committee. / DFID / FOREX ACCOUNT (Bank of Mozambique) / SINGLE TREASURY ACCOUNT (CUT) / DNPE / UFSA – Payments for CEDSIF and DPPFs done directly by UFSA / MINED (Execution of funds decentralized by DNPE) – Direct payments for the 2 pilot DPEC / DPEC 1 / CEDSIF / DPPFs
D. What is the assessment of financial risk and fraud? / The overall level of fiduciary risk for the project – based on the country-level FRA with a special focus on public procurement – is rated as substantial, but improving. / The corruption risk rating is in line with the country-level FRA. This states that despite the fact that “reforms to the PFM system, most notably the introduction of e-SISTAFE and associated improvements in accounting and reporting and the cleaning of the payroll, have significantly reduced the opportunities for corruption of budget funds”, risks associated especially with procurement, an area that DFID Mozambique is directly tackling with this programme, contribute to keep the level of risk substantial and stable. / With regard to the present project, the following risk-areas are identified: / Insufficient contribution from the Government to the project budget and fungibility of internal resources. / Lack of strategic planning and multi-year budgeting. / Poor procurement practices leading to poor VfM and opening opportunities for corruption. / Weaknesses with internal controls and with external audit. / In addition, the following three cross-cutting issues have been identified as a source of fiduciary risk: / The level and quality of financial management capacity at UFSA/DNPE to ensure good planning and budgeting, timely payments and acceptable accounting, recording and reporting of expenditure to adequately monitor project expenditures against budget estimates on a timely basis. At present the level of qualification and experience of staff associated to this function is hard to gauge. It is crucial that UFSA/DNPE allocates sufficient capacity to financial management activities to ensure adequate coverage of UFSA’s increased responsibilities under the project. / Lack of UFSA’s administrative autonomy leading to use of funds for activities other than those for which financial aid is provided. The fact that UFSA is integrated in, and to some extent subordinated to a National Directorate means that there is a risk that funds are not used solely to fund UFSA’s activities but more generally DNPE’s activities if sufficient scrutiny and differentiation of activities is not ensured. Although financial management for DNP as a whole is carried out by the same staff, there are no reasons to suspect that this will be the case as in principle all project expenditure will have to be signed-off by UFSA’s director. Furthermore, audits should flag issues with funds being used other than for intended project purposes, and assurance were given that the institutional set-up and lack of UFSA’s independence and administrative autonomy will not affect the proper execution of the project. / Insufficient control of expenditure due to weak inter-institutional working arrangements in the area of accounting and reporting. UFSA will have to setup adequate coordination and oversight mechanisms to ensure that funds channelled through UFSA to provinces are properly accounted for and reported. More generally, UFSA will have to define clear project guidelines with regards to defining roles and responsibilities (including on financial reporting) of different project stakeholders. / The risk element associated to low financial management capacity is partly mitigated by the fact that UFSA/DNPE is a Ministry of Finance institution, which is likely to have better capacity compared to agencies and institutions under different ministries. Technical assistance provided through the project should also mitigate this risk. / In addition, the most pressing gaps in PFM compliance and capacity are at district level, which will not be covered by the project, implying reduced fiduciary risk when compared to the country as a whole. / The use of DFID’s funds by UFSA/DNPE will be monitored through regular dialogue in the context of overall programme monitoring and evaluation arrangements, and through review of financial and activity reports, financial statements and audit reports. All of these will inform Annual Statements of Progress. / It is imperative that an adequate format for reporting, linking financial information with physical progress and clearly reporting any outstanding balances is jointly agreed at the outset. / Annual financial statements of the project will be audited by independent external auditors. / Country-level PFM reforms that are currently being implemented should also benefit UFSA/DNPE and gradually raise PFM standards.
E. How will expenditure be monitored, reported, and accounted for? / Within DFID, rigorous forecasting and monitoring and accounting of expenditure in ARIES will be undertaken by the project team. / Every 6 months, UFSA and MINED will submit to DFID a joint financial project report, which shall contain statements of disbursements and expenditures, as well as a comparative analysis of the commitments made and funds disbursed by all stakeholders (MF, MINED and DFID). The financial report will also provide all required information for the effective monitoring of the agreed VfM measures. The mid-year financial report (covering the period January to June) will be submitted not later than 31 July of each year and the annual report (covering the entire year) not later than 31 January of the subsequent year. Deviations must be explained and any necessary corrective action should be outlined and agreed as integral part of the bi-annual review process. The detailed accounting and reporting requirements will be specified in the MoU to be signed by DFID, MF and MINED. / Auditing / As DFID’s Financial Aid will be channelled through the Single Treasury Account, they will be part of Government expenditure, subject to the established accounting and audit systems of the GoM in accordance with national legislation. / All funds that are transferred to Government will be subject to an annual audit and shall be conducted in accordance with international Accounting Standards. / At the end of each year, UFSA will be responsible for commissioning an independent external financial audit covering all project components (including the funds which are executed by MINED). The approval of the Terms of Reference and final selection of the auditor will be done jointly by DFID, UFSA and MINED. All audit reports will be discussed at the mid-year reviews.
[38] Throughout the financial case, an exchange rate from British Pound to Mozambican of 1/40 has been applied.
[39] This combines both the contributions from the MF (outputs 1-5) and MINED (output 6).

Management Case

A. What are the Management Arrangements for implementing the intervention? / Partner Committee / The project will be implemented under the overall guidance of the Partner Committee. The Partner Committee will be the main decision-making body for the project and will be composed of representatives from the following institutions: 2 representatives from UFSA and 1 additional one from the Ministry of Finance at the National Director’s level, the DAF Director from MINED and 1 additional representative, 2 representatives from DFID, and one donor, which is supporting the procurement reform and/or the education sector as observer, (e.g the Worldbank, GIZ or Lead Donor of the FASE Common Fund). During the annual review exercise, the Partner Committee will be extended on a rotational basis by two Provincial Secretaries from the Provincial Directorates of Planning and Finance (DPPFs) and 1 from the Provincial Directorates of Education and Culture (DPEC). / The Partner Committee will be co-chaired by the Director of UFSA and DFID. It will meet bi-annually to monitor progress of project implementation and take the necessary decisions to ensure smooth implementation of the subsequent period. Its main role will be: (i) oversee the overall strategic direction of the Procurement project; (ii) review and approve the annual work plan and all financial and progress reports; (iii) analyse periodically the project performance, and (iv) set the parameters for the mid-term evaluation. / In preparation of the meetings, UFSA and MINED will ensure that all required monitoring data regarding output and outcome indicators is available. / DFID Management / Within DFID, the lead adviser for this programme will be the DFID Economist/PFM Specialist and programme management will be provided by a DFID Programme Assistant based in Maputo. Technical oversight will be provided by the Economist/PFM Specialist with support from the Governance and Economic Policy Team Leader. / Given the complexity of the programme combined with the weak national capacities, it will require a higher level of management and technical input by DFID than most of the other programmes, particularly within the first year of programme implementation. A continuous and in-depth support will be critical particularly for the following areas that are likely to not happen if not strongly facilitated and monitored by DFID: / Ensure that a launching workshop with broad stakeholder participation is actually happening and support a design that facilitates a common understanding among all stakeholders about the expected project results / Recruitment and effective establishment of TA both in UFSA and MINED / Ensure that all necessary analysis with the required international expertise is conducted within the first year of the project. This includes continued negotiation to accept international expertise / Help establish the first annual work plan in line with the agreed priorities / Closely monitor preconditions in order to anticipate in case they are not met, and support UFSA and MINED in achieving them / Work closely with UFSA and MINED (potentially with support from international TA) to finalize the outstanding managements arrangements (logframe, VfM measures, M&E System) / Facilitate effective coordination and exchange of lessons learnt and best practices between UFSA and MINED / Monitor the impact on project design, once the roles and responsibilities of the DPPFs have been clarified within the Ministerial Diploma and ensure necessary adjustment of the project design if need be / Ensure a participatory annual review process with effective participation of the private sector and national civil society organizations in the annual workshop. / Project management / UFSA, the principal project partner, will assume the overall responsibility for implementation, coordination and successful delivery of the project. As such, the Director of UFSA will report on progress to the Partner Committee on a six-monthly basis. For the day-to-day management of the project, the Director of UFSA will be assisted by a full-time international expert. / With regard to the pilot component (output 6), the operational responsibility will be shared between the UFSA and the DAF of MINED. The DAF Director of MINED will ensure effective coordination of all interventions in the education sector. A national consultant, which will work part-time in both pilot DPEC (around 80% of the time) and at central level (around (20%), will support effective coordination with UFSA. / A Memorandum of Understanding (MoU) between UFSA, MINED and DFID will outline programme objectives, roles and responsibilities of each partner, and systems for reporting, monitoring, accounting, audit and transfer of funds.
B. What are the risks and how these will be managed? / Overall, the procurement project is assessed as high risk – on the one hand due to the limited existence of evidence for successful procurement reforms, on the other hand due to the outcomes of the following more context-specific risk assessment of DFID’s support to the public procurement system in Mozambique. / According to the assessment most risks have a rating of high or medium, even if the high number of mitigation actions shows that there are numerous influence and pressure opportunities, which can reduce the likelihood of risks or their negative effects materialising. Some mitigation actions are built directly into the programme design itself. / The following risk table focuses on the most critical risks that can undermine successful implementation of the project in terms of achieving its intended outcome and outputs. To facilitate their continuous monitoring as integral part of the annual review exercise, the risks are further specified through a set of specific indicators. / Risk Description Impact[40] Probability Mitigating Actions Risk / rating / 1. Insufficient political leadership at Senior level for implementing the procurement reform effectively across all Sectors, and in particular within the Education Sector as pilot, and enforcing the actual application of procurement rules (political) H M Pro-active political dialogue through GBS fora (Procurement Working group and HOC meetings) and with the Government to ensure that procurement issues across all sectors are addressed more systematically within the aid architecture. / The procurement indicator of the PAF matrix is one of the indicators for the variable tranche 2012 of DFID’s GBS / The monitoring strategy of the project foresees 6-monthly meetings between the Vice-Minister of Finance and the DFID Head in order to facilitate political leadership / Use procurement information, that will be generated out of e-SISTAFE to strengthen UFSA’s communication with Line Ministries at highest level as integral part of the project activities / Indicators to be monitored (at UFSA and MINED): / No. of high-level Government meetings per year where procurement issues are discussed with involvement of at least three different Line Ministries / No. of full-time HR allocated to UFSA and DPPFs in relation to the delivery rate of the project in order to ensure that that UFSA is in the position to take up additional responsibilities / % of MINED’s committed financial contribution, which effectively delivered by MINED / 2. Insufficient technical human resources, particularly at provincial level, hinder UFSA and DPPFs to fulfil their (additional) responsibilities that are supported by the project and might hamper actual delivery and/or quality of services (institutional) H H Promote recruitment of additional staff members within UFSA / Promote approval of UFSA’s organogram and support the formulation of job descriptions within UFSA to facilitate effectiveness of the organogram / Support UFSA in preparing a strategic plan for the procurement reform including medium term budget (Cenário Fiscal de Médio Prazo – CFMP) as integral part of project activities (output 2) / Indicator to be monitored: / No. of full-time HR allocated to UFSA and DPPF in relation to the delivery rate of the project (see above) / 3. The insufficient number of qualified staff in the UGEAs, particularly at decentralized levels, combined with high staff rotation undermines effective capacity building of the procurement function with negative impacts on the compliance and performance of the procurement processes (institutional) H M Use the 6-monthly meetings between the Head of DFID and the Vice-Minister of Finance to raise the need for reviewing UFSA’s institutional set up (see also risk 6) / Pro-active political dialogue through GBS fora (HOC and HOM level) and with government on the need to create / approve a professional career for procurement / Indicator to be monitored: / Approval of the professional classification of the procurement career / 4. Given that UFSA’s representation at provincial level in the DPPFs is not formalized, centralised decision making and the lack of clear hierarchical structures between UFSA and DPPFs will undermine system strengthening. (institutional) M H One project component foresees specific workshops for UFSA and DPPFs to better define the distributions of roles and responsibilities and the communication flow between UFSA and DPPFs / Continuous advocacy (both at technical and political level) within UFSA and the Ministry of Finance to clarify and formalize the relationship and hierarchical linkages between UFSA and the DPPFs / Indicators to be monitored: / Approval of a comprehensive organogram of UFSA reflecting its internal structure and positions, as well as linkages with DPPFs / Dissemination of an official document, such as a Ministerial Diploma, that specifies the relationship between UFSA and its focal points in the DPPFs and clarifies the distribution of roles and responsibilities / 5. Insufficient coordination and collaboration between UFSA and MINED hampers aligned approaches in project implementation between the two Ministries and effective transfer of lessons learnt. (institutional) H M MoU defining roles and responsibilities of each partner to be signed between DFID, UFSA and MINED / 2-monthly technical coordination meetings between DFID, UFSA and MINED / Integrated planning and reporting formats for UFSA and MINED / Framework contract with an internat.-nat. consortium, which shall provide integrated technical assistance to both UFSA & MINED / Indicators to be monitored (at UFSA and MINED): / Nbr. of technical meetings with effective participation and preparation of both UFSA and MINED staff / No. of lessons learnt, templates or formats from MINED used by UFSA and adapted to other sectors (or vice versa) / 6. The weak institutional set-up within the State Asset Directorate of the Ministry of Finance and lack of institutional autonomy hinders UFSA’s function as independent oversight body (institutional) L H Use the 6-monthly monitoring meetings between the Head of DFID and the Vice-Minister of Finance to raise the need for reviewing UFSA’s institutional set up / Indicator to be monitored: / UFSA’s status as unit within the State Assets Directorate will be upgraded towards: (i) becoming a Directorate in itself within the Ministry of Finance in the short run, (ii) ideally becoming an independent institution outside of the Ministry of Finance / 7. Trainings of UGEAs with little impact on the actual day-to-day operations in procurement undermine increased compliance of procurement processes (institutional) M M New training approach will be based on a thorough needs assessment / Outsourcing training to experienced training institutions as integral part of the project design / Regular monitoring and impact evaluation of the training effects as part of the annual review exercise to determine changes and allowing for methodology changes as necessary. / Indicators to be monitored (at UFSA and MINED): / No. of satisfactory training evaluation exercises of (i) basic and advanced trainings and (ii) specialized education trainings conducted and % of recommendations implemented / 8. Interest of the political elite and blurring boundaries with the private sector distort effective programme implementation, e.g. UGEAs are not effectively empowered within Line Ministries in order to ensure compliance with procurement rules (Political economy) M M Use the more intense pilot intervention to advocate in the Ministry of Education to empower the UGEAs and feed back lessons learnt to UFSA / Indicators to be monitored annually: / To be defined / 9. Lack of synergy between DFID’s procurement project and procurement programmes of other donors (PFM programme of the WB, procurement interventions in the education sector of KfW and Candada) leads to duplications and inconsistencies M M DFID is influencing the alignment of the two interventions by co-funding the design of the World Bank PFM programme / DFID has provided the World Bank with an opportunity to comment on the Business Case / Use procurement working group to provide bi-annual updates on DFID’s support programme to support cross learning and avoid duplications / Governance / monitoring structure of the project designed to build synergies with other donors / Indicator to be monitored: / No. of annual DFID presentations on the procurement project in relevant donor groups / No. of coordination meetings / consultations between DFID and other donors intervening in this area / 10. Weak complaint mechanism undermines the enforcement of the procurement legislation (institutional) L M Use the 6-monthly meetings between the Head of DFID and the Vice-Minister of Finance to raise the need for reviewing UFSA’s institutional set up, if deemed necessary / Indicator to be monitored: / To be defined / Through DFID’s continued engagement with GBS, we assume that we will have the opportunity to raise additional issues in the related aid architecture if deemed necessary. / The overall high risk rating will translate as follows into the risk rating at output level / Output: Risk rating: / 1 Info management system on procurement operational Medium / 2 Institutional set-up of the public procurement system clarified High / 3 Increased knowledge of UGEAs in public procurement High / 4 Monitoring system of UGEAs established High / 5 Better access to procurement information for the private sector Medium / 6 Improved procurement practices in the education sector High
C. What conditions apply (for financial aid only)? / The UK’s conditionality policy will apply to the present project, which means that the MoU to be signed by the MF, MINED and DFID and any outstanding payments will be suspended, if any of the following partnership commitments are breached: / Commitment to poverty reduction and the MDGs; / Respecting human rights and other international obligations; / Improving public financial management; promoting good governance and transparency and fighting corruption; / Strengthening domestic accountability; / In Mozambique, public procurement is one of the indicators in the PAF matrix (performance assessment framework), which serves as a basis for determining the General Budget Support in the subsequent year. In the recent revision of the procurement indicator, UFSA has agreed to the following commitments: / Establishment of an information management system on procurement as an additional functionality within e-SISTAFE and subsequent publication of critical data on its Portal / Implementation of a procurement career stream / Increased collaboration between UFSA, the Administrative Court and Internal Control on procurement audits. / Given the political economy dynamics inherent to any public procurement reform process and Mozambique’s rather weak governance environment, which is likely to hamper effective strengthening of the public procurement system, four specific pre-conditions under the third and fourth partnership commitment have been defined for the continuation of the project. Strong Government commitment throughout the lifespan of the project combined with the (partial) achievement of certain project results (outputs 1 and 2) which are considered indispensable for the achievement of the remaining results are therefore consistent critical for the success of the project. The project will therefore be sub-divided into two phases with the satisfactory completion of the following elements being a precondition for the launch of the second phase at the beginning of the second year of project implementation: / The information management function is operational within e-SISTAFE and a first report available (output 1) / No. of full-time HR allocated to UFSA in relation to annual delivery rate of the project in order to ensure that UFSA is in the position to take up additional responsibilities / Job descriptions of UFSA’s HR and of focal points within DPPFs approved in line with UFSA’s new organogram (Output indicator 2.4.) / Dissemination of a Ministerial Diploma clarifying the roles and responsibilities of DPPFs as UFSA’s representatives at provincial level (output indicator 2.2) / These elements will be closely monitored throughout the first year of project implementation through technical meeting and finally assessed at the end of the first year of project implementation as integral part of the annual review exercise.
D. How will progress and results be monitored, measured and evaluated? / Present situation / To mitigate the long term risk related to the insufficient evidence about success of procurement reforms, the programme will place a major emphasis on data collection around the impact of the intervention on the present procurement practices in Mozambique. / At present, there is hardly any data on procurement available given that UFSA has not yet established a comprehensive information management and monitoring system. In this regard, the implementation of the information management system within e-SISTAFE and the establishment of an effective compliance monitoring system in UFSA (outputs 1 and 4) can be considered as a pre-condition for comprehensive and effective project monitoring. Once these systems are set up, it might therefore be necessary to review the baseline data in the project logframe. / Beyond monitoring compliance at the level of UGEAs as integral part of the project activities, there will be also a need to monitor performance of UFSA itself and its provincial arms within the DPPFs. Given some evident vested interests in measuring its own performance combined with the weak internal structure and monitoring capacities of UFSA, dedicated DFID staff will need to support and complement UFSA’s monitoring efforts throughout the entire project implementation period. / Project monitoring and evaluation will happen at the following levels: (i) routine monitoring; (ii) joint review exercises; (iii) lessons learnt from the education pilot; (iv) risk monitoring, and (v) independently commissioned mid-term evaluation of the project with a special focus on the pilot experience. / Project monitoring / Routine monitoring / UFSA will be in charge of the day-to-day collection and monitoring of procurement data based on the information management and monitoring system that will be established in the first year of project implementation as integral part of the project activities. / The data will be collected at two levels: (i) basic data on procurement, such as the type of applied procurement modality, the bidder participation levels or dates of publication and awarding of tenders, will be automated through e-SISTAFE; (ii) compliance of procurement practices in UGEAs with the legislation will be monitored through supervision visits and related information systematically consolidated within a compliance monitoring database to be established at the level of UFSA. These data will serve as basis for the regular joint review exercises and external evaluation of the project. / Technical monitoring meetings between UFSA, MINED and DFID staff / In order to and facilitate effective monitoring of project activities, DIFD’s programme staff from the Governance and Economic Policy Team will meet every two months with the Head of UFSA and the DAF Director from the Ministry of Education. These meetings aim to: (i) accompany project implementation ensuring effective coordination between all stakeholders; (ii) ensure adequate follow up on the decisions and recommendations of the Partner Committee; (iii) discuss constraints or delays in project implementation and identify potential solutions; (iv) facilitate the preparation and exchange of lessons learnt and best practices between the UFSA and the pilot Ministry. / Joint field visits of UFSA, MINED and DFID / In addition, joint field visits will be organized at least once per year in order to review progress in project implementation at the decentralized levels. / Joint review exercises / Joint review exercises will be the default mechanism for project review in order to facilitate maximum transparency and a shared vision among all stakeholders on the progress of the procurement reform and potential obstacles. The joint reviews, which include both mid-annual and annual reviews, aim (i) to assess progress against outputs and outcome based on the established indicators and annual targets as well as project assumptions as defined in the project logframe; (ii) to analyze the value for money of the project by linking the achieved results to the actual annual project costs; (iii) to identify lessons learnt and good practices that impact positively or negatively the achievement of results; (iv) to take the necessary decisions regarding priorities for the continuation of project implementation and necessary corrective actions; and (v) to approve the annual work plans of the project including mid-year adjustments. / Joint annual review / The joint annual review exercise at the end of each year of project implementation (December) represents the most important monitoring event. In addition to measuring progress against the planned results, it shall provide an opportunity for “public monitoring” of the national procurement system through structured feedback from the private sector and civil society on how public procurement operations are perceived by the citizens. The feedback shall be documented and influence the priorities of the following project implementation period. / The annual review will follow the following process: / Preparation of an annual project report (covering January-October) and a draft annual work plan for the following year by UFSA prior to the review exercise (before 15 November of each year); The DAF Director will ensure timely submission of MINED contributions to UFSA in order to ensure the preparation of an integrated report. / A procurement workshop at central level (before the end of November of each year) with participation from the extended Partner Committee, relevant Line Ministries, private sector representatives and civil society groups: During this workshop, critical procurement issues, as perceived by the broader public, will be collected and channelled to UFSA in a facilitated framework. At the same time, UFSA will have the opportunity to report back to the audience on the progress of the procurement reform and collect suggestions for further improvements. This monitoring exercise will build on other DFID-supported civil society initiatives, such as the Citizen Engagement Project or CIP. / The extended Partner Committee will meet the day after the procurement workshop in order to analyze progress towards the planned results and identify potential bottlenecks and lessons learnt taking into consideration the progress report and the outcomes of the procurement workshop. Furthermore, it will take the necessary decisions for further project implementation, discuss the annual work plan and ensure that the required technical assistance to UFSA and MINED is effective (in the first week of December of the year). / All those issues that require higher level intervention will be transferred to a bilateral meeting between the Vice-Minister of Finance and the Head of DFID for final decision. / The annual review exercise at the end of the first year (December 2013) of project implementation is particularly critical, as it will serve to assess the fulfilment of the preconditions for the continuation of the project beyond the inception phase. At the end of year one, the Partner Committee will therefore assess jointly those criteria that will determine the launch of the second project phase, as outlined in Section C of this Management Case. / Furthermore, it will be reviewed whether the following project management mechanisms are in place, which where agreed to be put in place before the end of the first year of project implementation: / Joint mid-year review / The mid-year review will be similar to the annual review exercise, but will follow a lighter process and format. / June of each year: Submission of a joint progress project report by UFSA and MINED including the financial report covering the period Jan.-May. / July: The Partner Committee will meet with its core members in order to analyze progress in the implementation of the annual work plan and agree on necessary adjustments. / If considered necessary, a bilateral meeting between the Vice-Minister of Finance and the Head of DFID will be organized. / A detailed annual M&E calendar is included in the annexes in the attached Portuguese project document. / Monitoring pilot experience / Special attention will be given to the monitoring of the pilot experience in view of identifying and feeding back lessons learnt. The process will need to be specified at the end of the first year of project implementation jointly by UFSA and MINED. / Risk monitoring / Given the overall high risk rating of this project, rigorous risk monitoring will be necessary throughout the entire implementation period based on the indicators identified in the risk matrix under section B of this management case. Ideally, the risk monitoring will be done jointly in a small team composed of UFSA, MINED and DFID in parallel to the preparation of the annual report. The assessment will be submitted directly to the Partner Committee and not be discussed at the public workshop. / In case the risk rating creates major tensions, DFID will use its internal annual review process to update the risks accordingly. / Midterm evaluation the project – Process evaluation / In second half of the third year of project implementation (August/September 2015), an external midterm evaluation will be commissioned composed of a mixed team of national and international consultants which will directly feed into the annual review exercise. For this evaluation, an envelope of £150,762 has been foreseen in the project budget. / The exercise will particularly: / Assess to which extent the intervention caused measurable effects on the achievement of the outputs in view of generating increased evidence on what has worked / Generate feedback and lessons learnt and provide an opportunity to adjust the implementation strategy if need be / Identify best practices from the pilot sector that could potentially be mainstreamed to other sectors / Assess thoroughly UFSA’s and MINED’s internal monitoring and supervision system / Evaluation Priority Evidence Base Strategic Importance Size Demand Feasibility / High / Support to the public procurement system is a new area for DFID Mozambique. Low / There has been some research, but little in countries with a similar context. / Local evidence is very weak. Medium / The project is the first large donor project in support of public procurement in Mozambique and could trigger a lot of interest from other donors. Unknown / as donors yet to decide Medium / Strong demand from other sector budget support partners. High / Evaluation Questions still be to agreed by partners. / Timeline is tight if to feed into new strategic plan. / Evaluation methods / The evaluation will use a participative methodology including surveys and interviews with / all relevant stakeholders of the procurement system (UFSA, UGEAs, Senior officials of critical sector Ministries), / the direct beneficiaries of the procurement reform, such as technical staff within the Line Ministries who are assisted in procurement matters by the UGEAs on the one hand, and private sector representatives on the other hand, / The indirect beneficiaries – represented by civil society organizations – who benefit from better service delivery of Government institutions following the procurement reform / The midterm evaluation will consist of 2 phases: / Provincial procurement workshops in up to 11 provinces based on a methodology designed by the consultant team with participation from the DPPFs, pilot DPECs, relevant Line Ministries, private sector representatives and civil society groups. The workshop results will be further analyzed during the field mission and further consultations of the consultant team. / A national procurement workshop with participation from the DPPFs, pilot DPECs, relevant Line Ministries, private sector representatives, civil society groups and selected donors towards the end of the evaluation. This workshop will serve to deepen the analysis based on the provincial results and share the main findings with a broad range of stakeholders. / In case a new Country Procurement Assessment Report (CPAR) will be conducted in 2013, as presently envisaged, its recommendations will be taken into consideration by the Partner Committee in its discussions about the annual work plan of the subsequent year. / Logical Framework finalized including baseline and targets for all indicators (UFSA/MINED / DFID) / A concept for M&E and the collection of best practices and lessons learnt of the pilot sector is available / Effective VfM measures, on which GoM is able to report are finalized / An effective monitoring system for all logframe and VfM indicators operational in both UFSA and MINED
Logframe / Attached / Quest No of logframe for this intervention: 3671184
List of other annexes (separate documents apart from annex 1) / List of items to be assessed at the first annual review exercise (Dec. 2013) / Detailed project budget / Portuguese Project Document as agreed with UFSA and MINED including planning and reporting formats and integrated annual M&E calendar / Fiduciary Risk assessment / Economic Appraisal
Annex 1 - List of items to be assessed at the first annual review exercise (Dec. 2013) / Given the political economy dynamics inherent to any public procurement reform process and Mozambique’s rather weak governance environment, which is likely to hamper effective strengthening of the public procurement system, four specific pre-conditions under the third and fourth partnership commitment have been defined for the continuation of the project. The project will therefore be sub-divided into two phases with the satisfactory completion of the following elements being a precondition for the launch of the second phase at the beginning of the second year of project implementation: / The information management function is operational within e-SISTAFE and a first report available (output 1) / No. of full-time HR allocated to UFSA in relation to annual delivery rate of the project in order to ensure that UFSA is in the position to take up additional responsibilities / Job descriptions of UFSA’s HR and of focal points within DPPFs approved in line with UFSA’s new organogram (Output indicator 2.4.) / Dissemination of a Ministerial Diploma clarifying the roles and responsibilities of DPPFs as UFSA’s representatives at provincial level (output indicator 2.2) / These elements will be closely monitored throughout the first year of project implementation through technical meeting and finally assessed at the end of the first year of project implementation as integral part of the annual review exercise. / At the same ocasion, it will be reviewed whether the following project management mechanisms are in place, which where agreed to be put in place before the end of the first year of project implementation: / Logical Framework finalized including baseline and targets for all indicators (UFSA/MINED / DFID) / A concept for M&E and the collection of best practices and lessons learnt of the pilot sector is available / Effective VfM measures, on which GoM is able to report are finalized / An effective monitoring system for all logframe and VfM indicators operational in both UFSA and MINED
[40] For the assessment of the probability and impact for the risk, three different categories have been used: L = Low; M = Medium; H = High.