Business Case and Intervention Summary

Intervention Summary
## Title:DFID Burma Accelerated Reform Facility (ARF)

What support will the UK provide?
DFID will provide up to £5 million over the next 18 months (with the possibility of extension) from September 2012 until April 2014. / DFID will also provide multi-sectoral advisory and administrative staff time.

Why is UKsupport required?
Following the political changes of the last 12 months, and the UK’s response to them, DFID Burma has been well placed to take a leading role in using our aid and coordinating others to support reform. The pace of change and the influx of new stakeholders in Burma requires DFID to respond flexibly and quickly to maximise the potential benefits opened up by the reform process. / The Secretary of State has recently approved DFID Burma’s updated Operational Plan focused on helping create a better governed, more peaceful & prosperous Burma that uses its increased wealth to reduce poverty. To support this transformation we will base our support around five pillars: / Good governance and public financial management / Promoting responsible investment / Improving transparency, Accountability and the Rule of Law / Strengthening the work of parliament / Helping the process of ethnic reconciliation. / Progress in these areas will rely on the continuing momentum of the reform process and DFID capitalising on the opportunities that accompany this reform. That is why we are proposing to set up an Accelerated Reform Facility (ARF), under which we could support short-term, relatively low spend interventions targeted at these pillars.

What are the expected results?
The impact of the ARF will be a better governed, more prosperous Burma that uses its increased wealth to reduce poverty. The outcome of the ARF will be short term results that strengthen long term reform in the ARF focus areas. Where relevant, the ARF will contribute to Operational Plan headline results in governance and wealth creation. / The ARF will support short term results work in each of the five pillars. Donor coordination is included in the ARF focus areas as it underpins the success of work across all the pillars.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Since his inauguration in March 2011, President Thein Sein has undertaken a dramatic programme of reform. His government has released several hundred political prisoners, negotiated ceasefires with ten of the eleven major armed groups, drafted new legislation promising greater civil and political freedoms, and taken steps towards opening up the economy. This has all been underpinned by a historic dialogue between the President and Aung San Suu Kyi, whose National League for Democracy agreed to rejoin the political process for April’s by-elections, at which they won a remarkable 43 of 45 seats. The international community has welcomed this process with promises of increased aid and assistance, and the US and the EU have suspended the majority of their economic sanctions. / However, several challenges remain ahead. Most immediately, the Government of Burma will need to resolve the conflict in Kachin state, which first flared up in June 2011, and to manage the intra-communal tension in Northern Rakhine State. In the longer term, he will need to find durable solutions to these problems and, more broadly, to move from ceasefire to full political settlement with all the country’s ethnic groups. Meanwhile, it will take time for the nascent Parliament to find its feet and the wider government to meet the higher standards of accountability and transparently required of it. Economically, an underdeveloped financial sector, governance problems and dense regulation continue to be major barriers to investment. / The UK has responded at the political level to these changes in a number of ways, including by / A visit by the Prime Minister. / The suspension of EU sanctions in April / Stepping up engagement with reformers in government, ASSK, opposition parties & ethnic groups. / This has put DFID in a very strong position to take a leading role in using our aid and coordinating others to support reform. / The Secretary of State has recently approved DFID Burma’s updated Operational Plan focused on helping create a better governed, more peaceful & prosperous Burma that uses its increased wealth to reduce poverty. To support this transformation we will base our support around five pillars: / Good governance and public financial management / Promoting responsible investment / Improving transparency, Accountability and the Rule of Law / Strengthening the work of parliament / Helping the process of ethnic reconciliation. / Progress in these areas will rely on the continuing momentum of the reform process and DFID capitalising on the opportunities that accompany this reform. / While DFID has already been responding to the reforms in these areas – facilitating numerous visits, strengthening donor dialogue and laying the groundwork for relevant World Bank assessments – there is now a strong need for a dedicated funding window, rather than ad-hoc support from a variety of existing programmes or entirely new individual business cases. / The dynamic nature of the reform process requires a responsive mechanism that allows us to move quickly to maximise opportunities when they appear. Reacting fast - whether by drawing on external expertise, facilitating events and visits or procuring basic resources - will deliver the quick wins needed to catalyse the reform process, as well as develop the longer term approaches to ensure we capitalise on the reforms to alleviate poverty. / The ARF will help DFID Burma deliver against these new areas whilst still allowing the programme team to focus on achieving all of the results (health, education, livelihoods) set out in the original Operational Plan. While we bring in new staff and skills, having a responsive umbrella mechanism that can provide quick focused support around our agreed priorities will be key to capitalising on new opportunities. / As part of the Operational Plan we therefore suggested the Secretary of State approved a fast track process for an Accelerated Reform Facility (ARF), under which we could support short-term, relatively low spend interventions targeted at catalysing reform in each of the Operational Plan pillars. The Secretary of State strongly endorsed the need for the ARF, given the nature of the reforms and the need to respond quickly to positive change.
B. Impact and Outcome that we expect to achieve / Eligibility for ARF funding will be determined by the potential for interventions achieving transformational impact in the following six ARF focus areas: / Good governance and public financial management / Promoting responsible investment / Operational Plan pillars / Improving transparency, Accountability and the Rule of Law / Strengthening the work of parliament / Helping the process of ethnic reconciliation / Better donor coordination and aid effectiveness. / Donor coordination is included in the ARF focus areas as it underpins the success of work across all the pillars. / Table 1 below sets out the results chain for the ARF. The outputs correspond to the six ARF focus areas where support will be targeted. / Table 1 / Impact: A better governed, more prosperous Burmathat uses its increased wealth to reduce poverty. / Outcome: Short term results that strengthen long term reform in the ARF focus areas. / Outputs: / Better governance and public financial management / More responsible investment / Improving transparency, accountability and the rule of law / Strengthened Parliament / Helping the process of ethnic reconciliation / Better donor coordination and aid effectiveness. / Due to the uncertainty of the exact interventions the ARF will support, no formal logframe is available. Instead, a drawdown pro-forma will be required to access funding from the ARF. This will provide more detailed results with which an ARF results framework will be produced. This will be used to monitor and report on progress. / In addition, these pro-formas, where possible, will demonstrate how they are contributing to the relevant Operational Plan headline results (see table 2). / Table 2 / Pillar/ Strategic Priority Indicator Baseline (including year) Expected Results (including year) / Wealth Creation Number of development finance organisations that commit capital or attract private investment into Burma. Nil at 2012 / (Output indicator) 2 by 2015 / Governance & Security Improvement in political rights and civil liberties, as measured by Freedom House. “Not Free” in 2012 “Partially Free” in 2015 / Governance & Security Number of people supported to have choice and control over their own development, through DFID support. Nil at 2010 / (Output indicator) 94,000 people by 2015 / (inc. 76,000 women). / Table 3 sets out the type of results that may feature in the drawdown pro-forma. / Additional ARF focus area / Table 3: Sample indicative results from drawdown pro-forma submissions / - Government commitments in key areas. / - Number of research papers produced. / - Number of IFI assessments conducted. / - Number of scoping visits completed. / - Development of long-term and/or joint programmes. / - Leveraging donor/private sector support for ARF priorities

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / There are a number of possible options for the UK to support short term pieces of work that contribute to a better governed, more prosperous Burmathat uses its increased wealth to reduce poverty. / We have dismissed an option of preparing discrete Business Cases as each intervention opportunity arises. For short term pieces of work of this kind this is not feasible and would be an inefficient use DFID Burma staff resources. This leaves us with three feasible options: / Option One: Establish the ARF, as set out in this Business Case. / Option Two: Do Nothing in these new areas and focus only on programmes where we have existing aid commitments / Option Three: Focus all of our reform efforts on one of the six areas of the ARF rather than all six
B. Assessing the strength of the evidence base for each feasible option / As described above, the reform process in Burma is underway but several challenges remain ahead in a wide range of areas and it will take time for the nascent Parliament to find its feet and the wider government machinery to meet the higher standards of accountability and transparently required of it. The private sector is underdeveloped and suffers from years of isolation. This is clear evidence of the need for support. / There is also clear evidence that DFID Burma is well placed to support this reform process. DFID is the largest donor in the country, and one of the few that have dedicated in-country resources in the new areas of the operational plan (through the Senior Governance Advisor and the Economic Advisor) as well as significant technical resources to draw on from headquarters. DFID plays an important role in aid effectiveness as the chair of the Partnership Group on Aid Effectiveness, the chair of the Donor Governance Group and an important part of the multi-donor funds in education, health and livelihoods. DFID has also been a key part of the donor group that has been discussing aid effectiveness with Government. The UK is also well linked to opposition parties and Daw Aung San Suu Kyi and is a strong supporter of civil society through existing programmes – DFID and the FCO are closely in step on these issues. Therefore there is clear evidence that DFID is well placed to support emerging areas of reform in Burma. / If there is a clear need of support and clear evidence of DFID’s ability to play an important role, the only question that remains is whether it is important to support reforms. We address that issue in the next section.
C. What are the costs and benefits of each feasible option? / There are three options to consider. Options 1 and 3 propose to support the reform process (but in different ways) while option 2 proposes not to support the reform process. We show first that there is strong case to support the reform process therefore concluding that option 2 is not a strong VFM option. We then briefly compare options 1 and 3 and make a qualitative argument to show that option 1 is a stronger option. / The first question to answer here is whether it is important to support a reform process or not. This is not something that is quantifiable but we will put two qualitative arguments forward. / Firstly, the reform process has already had a major impact which shows that it can deliver results that benefit poor people. The Government has released many of the political prisoners and it has increased expenditure of health and education (a fourfold increase in health in absolute terms for example). Transparency has begun to increase as evidenced by the national budget being openly debated in parliament (for the first time in DFID’s time in the country), by the Government’s statement of commitments on the Extractive Industries Transparency Initiative (EITI) and by the Government’s agreement to publish the International Monetary Fund (IMF) Article IV report for the first time. Political participation has increased, most notably evidenced by the NLD and Daw Aung San Suu Kyi’s participation in by-elections in April and now as members of parliament. Finally, the international community has responded through suspending or removing many of the sanctions on Burma, through increased aid commitments and through the progressive re-engagement of the International Financial Institutions (IFIs). / Secondly, the outlook for the country in the case of continued reform is strong. Economically, the Asian Development Bank (ADB) predicts that sustained reform could lead to 7/8% growth rates and a tripling of per capita income by 2030 – benefits of this kind would far outweigh the cost of supporting reform. The economy is not the only place where progress could have a major impact – continued reform could see progress across a range of areas from basic service delivery to political participation. / This makes it clear that the impact potential of continued reform is significant and we should clearly be looking to support this where we can. / Option 3 suggests identifying one area of reform and focusing on that whilst option 1 proposes to look at six different areas. / The problem with option 3 here is that, because the reform process is evolving, we do not know which area is most likely to support continued reform. Choosing one area of focus now risks us focusing on the wrong area without the flexibility to move quickly into an area which has more potential. This would be less of a risk if there was a well-established donor community and agreement between donors to focus on different areas (thus ensuring that as many areas as possible get covered). Many donors are still setting up here and are not in a position to put their full weight behind the reform process. This leads to the even bigger risk of missing opportunities to support reform at crucial times. Option 1 allows us to maintain a broad focus at this stage enabling us to quickly support an opportunity in any one of these areas. Therefore, if our objective is to support reform that promotes a more peaceful and prosperous Burma, option 1 is a stronger option.
D. What measures can be used to assess Value for Money for the intervention? / One avenue for assessing VFM is by considering the staff time saved by avoiding writing full Business Cases for small interventions, against the benefits to DFID’s objectives of being able to engage rapidly – in response to opportunities that arise unpredictably - across a broad range of potential areas. DFID Burma will formally conduct a light touch review after six months looking at the use of the facility and its effectiveness. / VFM must also be judged at the level of each intervention. The pro-forma for each intervention must set out the VFM case for the intervention and this pro-form will be reviewed by the ARF project team and then submitted to the head of office.
E. Summary Value for Money Statement for the preferred option / Burma is in the process of reform. Needs across a range of stakeholders are great and DFID is well placed to support these stakeholders and the reform process. / It is clear that the reform process has already had a beneficial impact in Burma and it is clear that continued reform has the potential to significantly benefit the poor people of Burma. / The most cost effective way for DFID Burma to help reformis to set up a facility that allows DFID Burma to flexibly support the reform process. Any support must be done in the key areas identified. The case for support will be assessed against the following criteria: / The likelihood that the proposal will be transformational. / Complementarity with actions by other actors. / Delivery of tangible results within 18 months. / Key risks to DFID/UK. / The DFID programme management implications of the proposal (including the management of DFID financial resources) / Where relevant, the likelihood that the proposal will create further opportunities to deliver against the six areas in future.

Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / The ARF itself will be managed in-house by DFID Burma. At the overall ARF level, there are no procurement implications (i.e. we will not outsource its management). However, there will be procurement requirements for individual interventions, most of which will be outsourced. We anticipate there will be three main instruments: / Accountable grants with not for profit organisations / Contracts with consultants for technical support / Some small direct procurement for which DFID Burma will follow the procurement guidance as set out in the Blue Book. / The approval process for activities within this programme, which is described in the management case below, will include consideration of the commercial implications at the activity level. This will follow DFID compliance requirements.
B. How does the intervention design use competition to drive commercial advantage for DFID? / All contracts will be clearly specified with clear deliverables. Where relevant, competition will be used to encourage innovation and value for money.
C. How do we expect the market place will respond to this opportunity? / We expect there to be a moderate response from the market for relevant interventions. It is likely that bidders will include international and local experts. Where appropriate we will encourage Burmese / International partnerships in the bids.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The financial costs of this programme will primarily be for the time of external experts conducting research and providing direct policy advice, for flights and other transport, and for accommodation and meeting facilities. All costs will be clearly set out by implementing partners prior to activity approval by DFID. These will be assessed at the activity level, and through the programme’s annual review, to ensure they are in line with cost benchmarks established through other DFID Burma programme activity.
E. What is the intended Procurement Process to support contract award? / A range of procurement processes may be used according to the type of award envisaged under “commercial requirements” above: / For accountable grants, this mechanism will be used where partners are not-for-profit organisations who have proposed work which contributes directly to one or more of the outputs of this programme, and where DFID assesses that such an organisation is best placed to do such work in a way which represents best possible value for money. / Competitive procurement will be used where a need for services is identified by DFID. Outcome- or output-based terms of reference for any such services will be agreed and either sourced through existing competitively tendered frameworks or published for new bids according to normal DFID procurement processes. Advice from the Procurement Group on a case-by-case basis will ensure that the agreed process achieves maximum value for money for DFID resources.
F. How will contract & supplier performance be managed through the life of the intervention? / The results of each activity will be agreed with each implementing partner under this programme. This will include a clear set of expected results to be agreed in an appropriate and proportionate format. / These agreed results will be used to manage the performance of all implementing partners, including through contractual outcome- and output-based agreements where these are in place, or through quarterly grant reporting to trigger financial disbursements where relevant. / Formal monitoring and reporting arrangements will be agreed with individual implementing partners on a case-by-case basis and approved through the drawdown pro-forma process.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The facility is proposed to be up to £5m over the next 18 months (with the possibility of being extended). This is an estimate based on an ambitious scenario of demand and may well shift in the dynamic reform environment. The resources for the ARF will come from DFID Burma’s existing programme budget for 2012/13 and 2013/14. / DFID Burma’s B1(D) Programme Manager and B2 Programme Officer who manage the project will be responsible for forecasting and monitoring the costs of the project. The main cost drivers of the ARF will depend on the nature of the individual proposals and each individual proposal will be subject to scrutiny by the programme management team and the head of office.
B. How will it be funded: capital/programme/admin? / The resources for the ARF will come from DFID Burma’s existing programme budget for 2012/13 and 2013/14.
C. How will funds be paid out? / The most appropriate agreement or contract will need to be determined on a case by case basis. We anticipate there will be three main instruments: / Accountable grants with not for profit organisations. / Contracts with consultants for technical support. / Some small direct procurement for which DFID Burma will follow the procurement guidance as set out in the Blue Book. / Contracts will be issued by DFID Burma’s Local Contracts Officer (if under £25k). Drawdown submissions will outline the contracting method and the value for money rationale for choosing it.
D. What is the assessment of financial risk and fraud? / The financial risk and fraud for each of the interventions funded by the ARF will be assessed on a case by case basis in the drawdown pro-forma. The DFID Burma Fraud Office (also the B1(D) programme manager of this ARF) will review the drawdown pro-formas on this basis.
E. How will expenditure be monitored, reported, and accounted for? / Each drawdown pro-forma will include with it information on the overall financial position of the ARF which will enable close monitoring of the financial position. The monitoring for each intervention will be conducted by the programme management team and will be done in accordance to the agreement and funding mechanism for that specific intervention.

Management Case

A. What are the Management Arrangements for implementing the intervention? / For interventions to be eligible for ARF funding they will need to demonstrate the potential to achieve transformational impact in at least one of the following six ARF focus areas: / Good governance and public financial management / Promoting responsible investment / Improving transparency, Accountability and the Rule of Law / Strengthening the work of parliament / Helping the process of ethnic reconciliation / Better donor coordination and aid effectiveness. / A drawdown pro-forma to the Head of DFID Burma will be required to access funding from the ARF. This pro-forma will include detailed results and be assessed against the full criteria of the ARF: / The likelihood that the proposal will be transformational. / Complementarity with actions by other actors. / Delivery of tangible results within 18 months. / Key risks to DFID/UK. / The DFID programme management implications of the proposal (including the management of DFID financial resources) / Where relevant, the likelihood that the proposal will create further opportunities to deliver against the six areas in future. / The project officer will ensure a clear record of decision making, proper due diligence and strong financial management. / The flowchart below shows the role the ARF will play (red) through the identification phase (blue) to the potential development of large longer term programmes of support where this is deemed appropriate (green). The ARF is not designed to fund longer term programmes. So, if any of the work funded by the ARF leads to an option for DFID to support a longer term programme, this would require its own business case to release DFID funding. / Once a need has been identified DFID advisors will produce a short drawdown pro-forma setting out how the proposal fits with the criteria for the ARF, the partners involved, rationale for contracting arrangement, timeframe and resource implications. These will be peer reviewed in the office and approved by the Head of DFID Burma. / Existing programmes of support encompassing the six areas – such as work with the World Bank on public financial management – will continue but future additional support will be consolidated under the ARF. / The ARF will be programme managed by DFID Burma’s B1(D) Programme Manager with support from a B2 Programme Officer. DFID Burma’s A1 Senior Governance Advisor and A2 Economist will be responsible for preparing the majority of pro-forma submissions to the ARF.
B. What are the risks and how these will be managed? / Table 5 highlights the key risks. This risk matrix will be reviewed whenever a pro-forma submission is produced and will be attached to the submission to the Head of Office. / Table 5 / Key risk factors Risk probability (high-1, Medium/high-2, Medium-3, Medium/low-4, low-5) Risk impact (high-1, Medium/high-2, Medium-3, Medium/low-4, low-5) Total Risk Mitigating actions / Backsliding of reforms closes opportunities for progress in ARF focus areas. 3 1 A/R Regular formal and informal political economy analysis underpinning interventions. ARF funding will only be approved in politically favourable environment. / Interventions ad-hoc, piecemeal and not strategic leading to failure of objectives. 2 3 A/R Clear ARF criteria and submission process. Peer review of proposals within DFID Burma. Six month light-touch assessment on ARF approach. / Programme management of the ARF over-burdens stretched programme team leading to insufficient oversight of DFID portfolio and increased risk of fraud and failure of objectives. 3 2 A Programme management implications included as a key ARF criteria. Analysis of programme management capacity planned for DFID Burma. Clear prioritisation of staff time. / Difficulty of measuring ARF impact makes demonstrating value for money challenging. 2 4 A ARF results framework produced as detailed results approved. Annual assessment of progress produced. / Government unable to manage all the different initiatives from development partners leading to failure of objectives. 3 2 A/R Proactive communication with partners working in focus areas. ARF support for donor coordination.
C. What conditions apply(for financial aid only)? / The ARF will not include any financial aid to the Government
D. How will progress and results be monitored, measured and evaluated? / A light-touch assessment of the ARF will be conducted after six months. This will take stock of how the ARF has functioned so far and assess the achievement of the results set out in each approved drawdown pro-forma. This will be performed by the DFID Burma programme team and submitted to the Head of Office. / There will also be an Annual Review and Project Completion report.
No Lograme / Quest No of logframe for this intervention: n/a