Business Case and Intervention Summary	ARIES PROJECT 203368

Intervention Summary
Title: Monitoring and Evaluation of the UK’s Framework for Results for Malaria in the Developing World and Choices for Women: Planned Pregnancies, Safe Births and Healthy Newborns.

What support will the UK provide?
The UK will provide up to £4.5m to evaluate the implementation and outcome of / Breaking the cycle: Saving lives and protecting the future. The UK’s Framework for Results for malaria in the developing world and / Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world.

Why is UK support required?
In December 2010, the Department for International Development published The UK’s Framework for Results for malaria in the developing world and Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world. / Together these two frameworks committed up to £7 billion (up to £4.4 billion for women’s and children’s health and up to £2.5 billion for malaria) to: / help halve deaths from malaria in at least ten high burden countries by 2015, and / save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 newborn babies by 2015. / This included a commitment to evaluate progress and results at the mid-term in 2013 and at a final evaluation in 2015. UK support is required to procure the services of an independent Evaluation Provider(s) to design and deliver an independent and rigorous evaluation to: assess the effectiveness of what was done; assess whether and how the impact and outcome targets have been achieved; and identify, document and disseminate lessons learnt for wider interest where results have or have not been achieved.

What are the expected results?
Evidence and better data as to how the UK has supported efforts to save and improve the quality of the lives of children and women worldwide by: preventing, treating and controlling malaria; and giving women the chance of a planned pregnancy, safe birth and healthy newborn baby. / This will be achieved through the following: / Evaluability Assessment of programme portfolio that will clarify evaluation questions; assess complexity and evaluability concerns; assess relevant evaluation approaches; assess budget implications; assess availability of data sources – including existing evaluations, evidence gaps and the requirement to commission further research; and set out timeframes and milestones. / 2. Mid-term review covering FfR activities up to 2013 and answering the following questions: / Are the planned activities likely to achieve the outputs? If not, what should be done differently or in addition between 2013 and 2015? / If all the outputs are achieved will they achieve the intended outcomes of the frameworks? If not, at this mid-term phase, are extra outputs or altered outputs required? / Are the assumptions in the frameworks correct? If not, do these require revision? Have any assumptions been overlooked? / Are the risks being managed successfully? If not what measures are needed to mitigate them? / What lessons are being learnt for wider interest? / Are project level evaluation activities progressing as planned to answer identified evaluation questions / 3. In-depth case studies on a select number of FfR interventions and thematic areas. The case studies should demonstrate example of best practice and examples where lessons need to be learned. / 4. Evaluation and evaluation report: The evaluation of the FfR will cover the period up to Dec 2015. The scope of the evaluation will be determined following the results of the initial evaluability assessment. / 5. A contribution to the evidence base for malaria control and the improvement of reproductive, maternal and newborn health outcomes for DFID and the wider global community. This will include a synthesis of reproductive, maternal and newborn health (RMNH) and malaria programmatic evaluations with a review of evidence and learning from program level evaluation activities. This will include recommendations on approaches to strengthen evaluation activities across the RMNH and malaria portfolios. This will have the potential to fill key knowledge gaps with the review process generating short papers on key lessons learnt. / 6. Effective dissemination of the findings: a structure will be designed and administered to disseminate key findings and lesson learning to key partners and stakeholders including project implementing partners; national governments; DFID country offices; multilaterals; the private sector and civil society.

Business Case

Strategic Case
Context and need for a DFID intervention / Context / The UK government is committed to reduce poverty in poorer countries, in particular through achieving the Millennium Development Goals (MDGs), including MDG 4 (Reduce child mortality), MDG 5 (Improve maternal health) and MDG 6 (Combat HIV/AIDS, malaria and other diseases). While progress is being made towards attainment of the MDGs, the rate of progress is insufficient to attain the MDG targets in some countries, with particular challenges in reaching the poorest and most disadvantaged / To support attainment of the MDGs, in 2010 DFID produced two frameworks for action to save and improve the quality of the lives of children and women worldwide: by preventing, treating and controlling malaria; and giving women the chance of a planned pregnancy, safe birth and healthy newborn baby. / The Frameworks for Results (FfRs) for malaria and for RMNH in the developing world set out frameworks for delivering on UK Government commitments to: / help halve deaths from malaria in at least ten high burden countries by 2015; / provide access to modern methods of family planning for 10m additional women, including 1m young women aged 15 – 19 by 2015; / prevent more than 5m unintended pregnancies by 2015; / ensure at least 2m safe deliveries, particularly for the poorest 40% by 2015; and / save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 newborn babies by 2015. / Need for evaluation of FfRs / The UK Government is committed to making British aid more effective by improving transparency and value for money and, as part of this, building more and better evaluations into DFID programmes[1]. To honour this commitment the FfRs describe 5 processes that will be used to inform progress, performance and impact as follows: / Routine programme monitoring; / Routine project and programme level evaluation; / Mid-term review (2013); / Global and partner monitoring and evaluation process; and / Final evaluation (2015-6). / The key deliverables from this intervention are the mid-term review and the final evaluation. However, the routine project, programme, partner and global monitoring and evaluation will provide essential information and data to feed into the mid-term and final evaluations, and the evaluation service provider will provide guidance on embedding evaluation questions into our routine project and programme monitoring. / Evaluation of the frameworks is important because: / High priority issue. DFID is committed to lead international action to improve the lives of girls and women by empowering them so that their lives are significantly improved and sustainable transformed through better education, greater choice on family planning and preventing violence against them. This commitment is one of the six departmental priorities highlighted in our Business Plan. The Structural Reform Plan (July 2010) and Business Plan outline DFIDs commitment to conduct a mid term review and to focus on results and evaluation for the malaria and RMNH frameworks for results. / Scale of spend. Together the two frameworks committed up to £7 billion on malaria and reproductive, maternal and newborn health. Programmes to address reproductive, maternal and newborn health and to combat malaria are planned by the majority of DFID Country Offices and there are also substantial programmes led by PRD (Policy and Research Division), PSD (Private Sector Department) and CSD (Civil Society Department). / Cross departmental goals and linkages. The attainment of the specific commitments set out in each Framework can only be achieved by a combination of efforts across a range of DFID departments and divisions (eg bilateral and multilateral programmes, PRD, PSD, CSD etc). Additionally, the Frameworks are closely linked to DFID’s work to put girls and women at the front and centre of development efforts, as set out in A new strategic vision for girls and women: stopping poverty before it starts, and to DFID’s efforts to combat HIV/AIDS as set out in Towards zero infections. The UK’s position paper on HIV in the Developing World. A specific objective of the evaluation of the FfRs is to measure the success of collaborative efforts towards attaining the FfRs commitments and related policy goals, including lessons to be learned for future DFID policy and programme design. / Strengthening the evidence base. There is significant interest in DFID and the wider development community in knowing what works for improving the lives of girls and women and controlling malaria, under what circumstances and at what cost. Both the mid-term review and final evaluation will contribute to the evidence base - addressing evidence gaps on what interventions are effective – and will be a global public good as well as increasing the impact and value for money of DFID programmes. / Innovation. The Frameworks have been innovative in a number of ways including the cross-cutting consultation in the way they were developed and the emphasis on improving the quality of services; increasing access and building demand; empowering women and girls; enhancing accountability; and supporting innovation and public goods. / External stakeholder interest. There has been substantial interest in the Frameworks from civil society and donor partners, and an expectation that DFID will carefully review and assess its new approach to these critical agendas in order to better meet our commitments. / Evaluation processes / DFID uses the definition of evaluation agreed by the OECD’s Development Assistance Committee (DAC):“The systematic and objective assessment of an on-going or completed project, programme or policy, its design, implementation, and results in relation to specified evaluation criteria.” This evaluation will be in line with OECD DAC guidance particularly relating to partnership and transparency. It will be published and is intended to contribute to the global evidence base to help understand what works and what does not work in achieving malaria and reproductive, maternal and newborn health outcomes.
B. Impact and Outcome that we expect to achieved / Impact: / A global reduction in maternal and child mortality and reduced incidence of malaria with accelerated progress towards attainment of MDGs 4, 5 and 6. / Outcome: / Improved effectiveness and value for money of DFID and partner RMNH and malaria programmes. / How outcome will lead to impact: / Evaluation of the FfRs, together with routine, internal monitoring of progress will tell us the extent to which we have achieved the results set out in the FfR and generate evidence on effective policy and programme interventions to prevent, treat and control malaria and to improve the quality of lives of women and children. / DFID will act on recommendations arising from the evaluation through a range of channels which include: / working through country programmes, using appropriate funding approaches in each case, to support countries and communities to achieve our health goals; / working through relevant multilateral institutions that play important strategic coordination, funding and normative guidance roles for the delivery of malaria and RMNH results; / improving the effectiveness and efficiency of the global response through international institutions, partnerships and global civil society; / investing in global public goods including tackling resistance, building and sharing evidence and supporting market efficiencies; / investing in research and working with academic partners to improve the evidence base in terms of what works best to improve outcomes, and to improve the dissemination of this knowledge; and / harnessing UK expertise through better partnerships with academics, civil society, professional bodies and partnerships with other UK government departments to help deliver this framework. / Findings of the mid-term review (MTR) and final evaluation will be disseminated widely as a global public good through mechanisms such as DFID knowledge hubs and professional networks, posting on DFID internal and external websites, and peer reviewed publications. Additionally, DFID’s unique position as a Board member of the Partnership for Maternal, Neonatal and Child Health (PMNCH) and member of the RMNH Alliance provides opportunity to formally and informally share information and mobilize partners to take up evidence. / As DFID and partners implement evidence and revise policy and programmes accordingly, the overall effectiveness and efficiency of the global response to maternal and newborn health and malaria will be strengthened. Through improved efficiency a given level of investment will reach a wider population, and through improved effectiveness programmes will have a greater impact on lives saved and illness averted. As a result, there will be a global reduction in maternal and child mortality and reduced incidence of malaria, and progress towards attainment of MDGs 4, 5 and 6 will be accelerated.
[1] DFID Business Plan 2012 – 15. DFID, May 2012

Appraisal Case

What are the feasible options that address the need set out in the Strategic case? / Option 1 Separate procurement of the full evaluation of the RMNH and malaria FfRs / Under this option the full evaluations of the two FfRs are conducted separately. The procurement processes to identify the evaluation providers are conducted independently of each other. The same provider may be successful in both bids, or different providers may be successful for each bid. / Option 2 Single procurement process and single provider contracted to conduct the full evaluation of both the RMNH and malaria FfRs / Under this option a single provider (or consortium) is identified to conduct both full evaluations / [NB Under both the above options the initial evaluability assessment may be contracted separately.] / Option 3 The ‘do nothing’ counterfactual / Under this option independent, external evaluations of the FfRs are not conducted
B. Assessing the strength of the evidence base for each feasible option / Theory of Change / As illustrated in Figure 1 below, the theory of change assumes that the monitoring and evaluation processes of the FfRs generate evidence on progress towards results and evidence on effective policy and programmatic interventions to prevent, treat and control malaria and to give women the chance of a planned pregnancy, safe childbirth and health newborn. Through the Evaluation Reference Group (ERG) ownership and cross DFID coherence of RMNH and malaria goals across is strengthened. DFID takes action in response to annual results monitoring and the findings of the MTR and final evaluation, changing policy and program activities as relevant to ensure that evidence is adopted and efficiency gains are realized. / Both option 1 and option 2 can be expected to deliver good quality outputs and outcomes. Doing joint evaluations is expected to yield higher benefits, given synergies between the two processes, and lower costs due to efficiencies in procurement and implementation, and a lower burden on DFID staff. / In the table below the quality of evidence for each feasible option is rated as either Strong, Medium or Limited / Option Strength of Evidence Rationale / 1 Limited No evidence to quantify the costs/benefits of separate procurement, but some evidence of duplication from this approach. / 2 Limited No evidence to quantify the costs/benefits of combined procurement, but some evidence of economies of scale from this approach. / 3 Medium Since DFID has committed to publishing an evaluation, there are clear negative consequences of not publishing. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C B / 2 C B / 3 C C / The main climate and environment risks that derive from this programme are related to international travel by the evaluation providers and potentially DFID staff. As it is expected that the majority of the evaluation will involve the analysis of secondary data supplied to the evaluation provider, the amount of travel is expected to be relatively limited. There will be some primary data collection and it will be important for the evaluation provider to use as far as possible existing in-country staff to collect data. This could be, for instance, asking DFID Country Office staff to collect the required data and pass this electronically to the evaluation provider. / There are opportunities in the evaluation to assess the contribution of environmental factors – such as hygiene for maternal and newborn health, spraying and drainage for malaria – in reducing risks. This would provide useful information in terms of future planning. It is important that the ToRs for the evaluation include requirements for evaluation providers to to address environmental and environmental health interventions. / There is little variation in the risks and opportunities between the options. The preferred option has lower risks, because the amount of international travel can be kept as low as possible by ensuring that both RMNH and malaria are addressed within the same mission rather than separately. However, this will only be realisable if the actual number of people travelling to a country is lower from a single evaluation provider (therefore assuming ability of staff to cover both RMNH and malaria) than from two providers. In evaluation of bids it will be important for the technical panel to include weighting for staff to cover more than one area for primary research studies.
C. What are the costs and benefits of each feasible option? / It is not possible to quantify the costs and benefits of the alternative approaches (joint versus separate procurement). As the selection of the evaluation provider will take place through a competitive tendering process, it is only once the contract has been awarded that the exact costs and benefits will be known. But there are good reasons to believe that joint procurement offers greater benefits and lower costs than separate procurement. / Option 1 Separate procurement of the evaluation of the RMNH and malaria FfRs / The procurement process and management of two separate contracts has potential to be duplicative and time consuming both for the procurement team, Policy Division staff and the Monitoring and Evaluation Reference Group (see Management Case), so raising the combined cost of carrying out the two evaluations. The same risk of duplication and inefficiency applies to activities to disseminate the findings of the evaluations. It is also possible that different methodological approaches might be taken if different providers are selected for each FfR, which would reduce the opportunities to identify common lessons and so lower the benefits. This option does not offer economy of scale nor value for money. / Option 2 Single procurement process and single provider contracted to evaluate both the RMNH and malaria FfRs / This option offers economy of scale, with reduced administrative and management requirements when compared to Option 1. Under this option a common methodological approach can be applied to both Frameworks and opportunities to learn from areas that are common to both (for example efforts to strengthen the health system, to reach the poor and most disadvantaged) will be maximized. The evaluation provider will be tasked to prepare MTR and final evaluation reports for each FfR separately, but will also be tasked to undertake a third stream of work which is identifying and reporting on themes that are common to both frameworks. / Option 3 The ‘do nothing’ counterfactual / Under this option DFID there is no mid-term review nor final evaluation of the FfRs. As a result, opportunities to strengthen the RMNH and malaria portfolios towards attainment of results (by acting on findings and recommendations of the MTR) would be lost. Evidence on policy and programmatic approaches to address RMNH and malaria would not be generated. Finally, the transparency and openness to which this Government has committed would not be realized. Therefore although there would be no financial costs, no benefits would be realised either.
D. What measures can be used to assess Value for Money for the intervention? / In relation to the size of spend, the proportion of funds proposed to evaluate the Frameworks for Results is low. / Value for money will be one of the criteria for selection of the preferred provider. Measures will include assessment of the proposed methodological approach and data collection methods to minimize unnecessary travel, workshops or meetings. The assessment will also consider the expertise, salary and length of effort of staff assigned to the project, other direct costs such as per diems, consumables and indirect costs of the provider and any additional costs incurred with a consortium arrangement or proposal for a sub-contract agreement. / The Evaluation Reference Group will monitor the evaluation, including its value for money.
E. Summary Value for Money Statement for the preferred option / The preferred option (joint procurement for the two evaluations) will offer greater value for money by reducing procurement costs and generating greater benefits across DFID and beyond.

Commercial Case

Direct procurement

Clearly state the procurement/commercial requirements for intervention / The evaluation will be carried out by a provider allocated through a tendering process. It is proposed that this is carried out through the Global Evaluation Framework Agreement (GEFA). GEFA has been set up to ensure the provision of services for the design and implementation of evaluations across DFID. Twenty seven suppliers have been appointed to carry out evaluations using a range of methodologies from quantitative, qualitative, mixed methods and participatory methods. / The twenty seven suppliers that are eligible to apply for the tender are Abt Associates, Agulhas, Alcis, British Council, Coffey, GDSI, GHK, Grant Thornton, GRM, HPI, Humanitarian Outcomes, IMC, Indufor, IPE, IOD PARC, Landell Mills, Montrose, Mott MacDonald, NRI, ODI, OPM, PWC, Ramboll Management, SDD, Social Impact, Upper Quartile and WYG. / The suppliers will be invited to tender via a mini-competition between the panel of twenty seven suppliers who match the thematic area and evaluation type, as identified with the skills matrix submitted with the tender documents. Bids for each requirement will be assessed by DFID Procurement Group, the relevant spending department and any other relevant stakeholder. Then a call down contract will be awarded to the supplier with the highest scoring bid following evaluation of the technical and commercial responses. / The process from issue of invitation to tender to contract award should take no longer than 12 weeks but may be longer subject to complexity of the requirement. In line with the UK Government’s transparency initiative the details of any contract awarded by DFID will be published on “Contracts Finder”.
B. How does the intervention design use competition to drive commercial advantage for DFID? / As this evaluation is above the EU threshold of £113,000 the procurement group will run a mini competition from the framework. There will be competition between the suppliers matching the thematic sectors and evaluation types included in the terms of reference. / The initial evaluability assessment may be contracted separately.
C. How do we expect the market place will respond to this opportunity? / We expect that amongst the 27 providers pre qualified by the DFID Global Evaluation Framework Agreement there will be sufficient interest in this contract to ensure a reasonable number of providers provide a tender, either alone or as a consortium. / This procurement process will increase the speed with which DFID can address the evaluation requirements whilst adhering to EU rules on public procurement and DFID best practice. Competitions will take 8-12 weeks from allocation to a buyer rather than the 6-9 months an OJEU can take.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Using the Global Evaluation Framework Agreement (GEFA) adds value to the process by / increasing the speed with which DFID can address GEFA requirements whilst adhering to EU rules on public procurement and DFID best practice. / improving value for money by introducing more competition between suppliers / enhancing accountability for results at all levels with increased transparency
E. What is the intended Procurement Process to support contract award? / The process will be a drawdown contract following a tender through the GEFA.
F. How will contract & supplier performance be managed through the life of the intervention? / Clear outputs will be set out in the evaluation Terms of Reference and the logframe. The performance of the provider in delivering them to the required deadlines will be monitored by the Evaluation Reference Group.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Details on costings will be requested and refined during the tender process, with each bidder submitting a budget alongside any proposal. / DFID has put together an indicative budget which is outlined below, however this is subject to change pending the tender process. Forecast spend / 2012/13 £200,000 / 2013/14 £1.2m / 2014/15 £1.6m / 2015/16 £1.2m / 2016/17 £300,000
B. How will it be funded: capital/programme/admin? / Programme budget – sitting with Group Management Unit (Aries 203368)
C. How will funds be paid out? / Funds will be paid out using a DFID Call Down Contract. The successful organisation will invoice DFID on an agreed schedule; this will be subject to discussion during the tender.
D. What is the assessment of financial risk and fraud? / Low. All 27 eligible bidders have already been subject to stringent financial checks. They have all worked with Government previously and are well respected. The risk of fraud will be mitigated through the use of detailed budgets and workplans with the successful candidate. DFID will expect a tangible result of an evaluation following the end of the contract.
E. How will expenditure be monitored, reported, and accounted for? / A DFID Project Office will be responsible for rigorous forecasting and accounting for expenditure using DFID’s Financial Management Systems (ARIES).

Management Case

A. What are the Management Arrangements for implementing the intervention? / A Monitoring and Evaluation Reference Group (MERG) will be established to provide leadership and cross-DFID coherence on all matters relating to the monitoring and evaluation of the FfRs. The MERG will consist of 10-15 members and include expertise in a range of disciplines including health, evaluation, statistics and finance. Members will include internal experts drawn from across DFID, together with external stakeholders representing civil society and academia to provide independent viewpoint. DFID ERG members will have the knowledge, expertise and an appropriate level of authority to ensure implementation of ERG recommendations. The ERG will establish subcommittees as relevant to conduct specific aspects of its work. Examples include a results methodology committee and programme evaluation committee. Draft Terms of Reference for the ERG are presented in Annex 2. / A DFID Internal Team will be established to and will act as Secretariat to the MERG. The DFID Internal Team will provide the day-to-day oversight and management of the Evaluation Provider. It will monitor operational and financial progress on an ongoing basis and raise any issue that require attention to the chair of the MERG and DFID senior management and Ministers as necessary. / The Evaluation Provider will report directly to the DFID Internal Team. The DFID Project Officer will be the initial point of contact. The Evaluation Provider will provide reports to an agreed timetable to the DFID Internal Team who will then liaise directly with the MERG. / The DFID Internal Team / The Evaluation Provider will be expected to establish a good working relationship with DFID. Regular meetings either in person and/or through conference call will be held with the DFID internal steering group. / The Evaluation Provider is also expected to respond to the needs of the MERG, including attending ERG meetings and/or preparing briefing papers for MERG as the need arises. The Evaluation Provider will be expected to report formally and in person to the MERG at least twice annually.

What are the risks and how these will be managed?
C. What conditions apply (for financial aid only)? / Not applicable.
D. How will progress and results be monitored, measured and evaluated? / Indicators are set out in the project logframe. These will be regularly monitored by the Monitoring and Evaluation Reference Group including formally through DFID’s Annual Review systems. / The MERG will evaluate the performance of the Evaluation Provider on completion through the Project Completion Report. / The Evaluation Provider will be expected to submit progress reports and lessons presented written and orally to the MERG twice annually in line with DFID’s programme cycle as outlined in the requirements section of the ToR.
Lograme / Quest No of logframe for this intervention: 3685513