## Somalia Stability Programme BusinessCase
## UK Department for International Development
29 August 2012

Contents

# Index of terms

AU	African Union
AMISOM	African Union Mission in Somalia
AS	Al Shabaab
BOFS	British Office for Somalia
CSFP	Core State Functions Programme
CDRD	Community Driven Recovery and Development Programme
DFID-S	DFID Somalia
FM	Fund Manager
IGAD	Intergovernmental Authority on Development
IDPs	Internally Displaced Persons
NSC	National Security Council
NRA	Newly Recovered Area
NGO	Non-Government Organisation
OTI	Office for Transition Initiatives
OECD/DAC	Organisation for Economic Co-Operation & Development/Development Assistance Committee
PL	Puntland
SO	Secretariat Office
SCR	Security Council Resolution
SAP	Somalia Accountability Programme
SSF	Somalia Stability Fund
SSP	Somalia Stability Programme
SL	Somaliland
SCS	South Central Somalia
SB	Steering Board
SEED	Sustainable Employment and Economic Development Programme
TFM	Temporary Financing Mechanism
TIS	Transition Initiatives for Stabilization
TFG	Transitional Federal Government
UN	United Nations
UNDP	United Nations Development Programme
UN-JPLG	United Nations Joint Programme on Local Governance and Decentralised Service Delivery
USAID	United States Agency for International Development

# SUMMARY

What support will the UK provide?
The UK will provide £30 million during the 3 financial years 2012/13 to 2015/2016. / These funds will be used to support peacebuilding, improved capacity, and better infrastructure and services to improve stability in the most fragile areas of Somalia - including areas recently recovered from Al Shabaab. The funds will respond to proposals from communities to meet their priorities. Examples could include facilitating a local peace agreement, providing alternative jobs for disbanded militia, building needed infrastructure, delivering priority services, or supporting the creation of new local government administrations such as district and village councils. The process of working with communities to plan and get access to resources will, initself, help manage conflict. / Up to £27 million will be put into the Somalia Stability Fund, to be managed by a Fund Manager working to a Secretariat Office that will have technical staff provided, in part, by donors. Funds will be spent through implementing partners,including international NGOs, local NGOs, civil society organisations, and the private sector. The Fund will be stewarded by a Steering Board that will set the strategic priorities for support and agree criteria for funding in different areas, with the Secretariat Office empowered to oversee day-to-day management and thus ensure the Fund can respond quickly to new opportunities. / The Fund will have specific windows to target the most vulnerable groups, including women and youth. / The Fund will be set up to allow other donors to join. Denmark, the Netherlands, Norway, and the United Arab Emirates have already agreed to join. We are pursuing contributions from the Chinese and the EU. / Alongside the Stability Fund, DFID will also fund interventions which are of high political risk and require direct HMG oversight. These resources will also ensure HMG priorities for stability which fall outside the mandate of the Fund can be met. Interventions may include finalising the Constitution, agreeing a national development and reconciliation framework, and facilitating agreement on contentious issues such as the form of the national government and the protection of human rights.

Why is UK support required?
What need are we trying to address? / Somalia is often considered an entirely failed state. The causes of the conflict are deep and complex and the effects far reaching. There are 1.46 million people displaced and 974,000 Somalia refugees are registered across regional borders, while 43% of the population live on less than US $1 a day. Women and girls suffer the effects of instability and conflict disproportionately, with Somalia ranked the fifth most dangerous country in the world for women. / The intervention is needed to promote stability and address the threat that Somalia poses to the international community and the region, as well as to transform the lives of poor Somalis. Failure to improve stability in Somalia could compromise DFID’s other investments in social and economic service delivery, and allow repeated humanitarian crises. It will also underminethe recent gains of the African Union Mission in Somalia, and limit the potential to establish a permanent and credible government. Continued instability providesspace for terrorism and piracy toworsen in Somalia. / What will we do to tackle the problem? / DFID will provide financial and technical support to implementing partners bilaterally, and through a multi-donor fund. Some funds will be used for the construction of service infrastructure. / Why is DFID funding required / DFID is addressing conflict by helping to resolve disputes between those who contest authority over resources. This will help reduce violence and help establish agreed and legitimate forms of government structures. DFID has designed theStability Fundto addressthe political, security, and developmentissues which create conflict This has not been tried before in Somalia, but the ‘local stability’ approach underpinning it achieved broad consensus at the London Conference. DFID’s experience, expertise, and global knowledge of delivering complex projects in fragile states, and the important role it has played in driving forward the stability agenda in Somalia, makes DFID support particularly required.

What are the expected results?
What will change as a result of our support / DFID support will build a greater number of areas of stability in Somalia, benefiting approximately 4 million people. The outputs will be: / 900 communities receiving improved infrastructure and/or services / 72,000 people who feel safe from armed violence / 87 areas with stronger and more legitimate local administrations / 72 existing peace agreements held and 44 new peace agreements secured. / How will we determine whether the expected results have been achieved? / The programme will be monitored by implementing partners throughout the programme period, and by internal annual reviews. The programme will also make use of third party monitoring, perception surveying, selective interviewing, and focus group discussions. Independent evaluations will take place in Year Two and at the end of the programme. The SSP will also have an annual ‘process evaluation’ to determine whether it’s design and systems for implementation are efficient and effective. A parallel Monitoring and Evaluation Programme will prioritise tracking of the SSP’s results.

# Strategic Case

Background / The SSP is a three-year intervention to improve stability in the most fragile areas of Somalia, including areas recently recovered from Al Shabaab byAMISOM, Kenyan,and Ethiopian forces.[1] The SSP supports emerging areas of stability to build peace and establish services and administrations such that they can benefit from medium-term development programmes. / After two decades of conflict, Somalia is often considered an entirely failed state and there is speculation as to whether it is viable as a unified country.[2] Armed conflict exists to varying degrees across its three zones: SL,PL, and SCS. The causes of conflict are complex, much stems from localised tensions over resources compounded by the militancy and terrorism of AS. An economy centred on control of resources, including illicit financial flows, undermines the political will for lasting solutions. Militia exploit the absence of security,[3] organised crime remains active, and piracy continues to disrupt international trade at significant cost.[4]Somali instability is a threat to the UK and its neighbours. / It is estimated that the international community has collectively spent over US $55 billion on aid to Somalia since the onset of civil war in 1991.[5] The social effects of the conflict are far reaching and the depth of need is profound: 1.46 million people are displaced and 974,000 refugees are registered across regional borders;[6] 43% of the population are estimated to live on less than US $1 a day; the under-five mortality rate is the worst in the world; and, only 30% of the population have access to safe water.[7]Somalia is ranked the fifth most dangerous country in the world for women and girls to live.[8]The unemployment rate across the country is high, encouraging young men to consider the benefit of taking-up arms and criminality. There has been a protracted humanitarian crisis in Somalia for most of the last twenty years. In 2011 this crisis produced the 21st century’s first faminebecause of whichover three million people are still targeted for food assistance[9]. The range of challenges still faced given that an estimated US $55 billion has already been invested in aid demonstrates the need for realism in making achievements in Somalia. / The need for a stability programme / Conflict in Somalia is highly localised and primarily starts within and between communities. Areas of emerging stability are highly undeveloped, and suffer from the absence of, or competition between, political and security actors for control of scarce assets and resources. Consequently, entry points to build stability must improve development and, in parallel, reconcile political and security interests to bring about local peace and the sharing of resources. Somalia faces a series of political, security, and development challenges inhibiting stability from taking root. Thesechallenges vary by zone and atypology has been used to categorise the operational context for the SSP (see Appraisal Case paragraph 33 for details). As areas of stability emerge and better manage conflict, they will be able to reconcile conflict over wider areas, increase development, and build up a growing jigsaw of stability across the country. The ultimate aim is for these areas to be woven into a network of stable areas under the auspices of an agreed national reconciliation framework (see theory of change set out in paragraph 9). The programme will work across all areas of conflict as need demands and as strategically makes sense to enhance stability. / Somalilanddeclared its independence in 1991 and functions as an independent state, although without international recognition. The government has demonstrated political will to deliver basic services, including security and justice. SLhas enjoyed relative stability for some time andthe government takes seriously the need to continue to improve stability, including ensuring foreign direct investment continues in energy and other sectors. Its security risk ratings remain consistently below that of PL and SCS. However, SL struggles with conflict to the east, where there are on-going disputes over the border regions of Sool, Sanaag and Cayn. There is concern that the SL administration is dominated by a single-clan structure, and that instability emerges as other clans feel marginalised from the centre. Areas such as Khatumo Statehave even called for separation from SL. An inability to resolve conflict in these areas means that administrations are appointed, rather than elected, and are overlapping and remain outside a clear framework for delivering services. / Puntland was established as a semi-autonomous region of Somalia in 1998.It has a decentralised system of government with district councils delivering many government functions – some well, others less so. Its government exercises limited control over localised conflicts and militia groups.There are a number of significant threats to stability including underlying clan conflicts between the Majerteen and Warsangali clans, and competition over natural resources (including oil). Also, as pressure mounts in SCSSomalia, AS fighters are moving north into PL, while militia in the Galgala Mountains have aligned themselves with AS.[10]Most piracy operationsare based out of PL. More assertive action is being taken against pirate bases and increasing intolerance by local communities encourages their displacement, but they may also relocate within PL’s borders. Without limited other livelihood possibilities, especially for youths, piracy and extremism will remain viable options. / South Central Somalia is highly fragmented and the types and underlying factors for conflict are multiple and highly localised. Several areas ofSouthernSomalia have recently been recovered from AS, including Mogadishu, parts of Gedo, Hiraan, Lower Juba, and Bay/Bakool Regions. Many areas are subject to overlapping claims for authority as underlying tensions between clans emerge, which AS historically suppressed. While Mogadishu had limited districtscontrolled by AMISOM, it is only in recent months that all districts of the city administration have been recovered. In Mogadishu, and in other ‘newly recovered areas’, the situation remains very fragile, with AS staging targeted attacks, assassinations, and offensives. There is also a risk of warlords regaining control of these areas. In the least secure NRAs, interests focus largely on securing territory. However, in Mogadishu, effortsare underway to deliver a peace dividend. The Transitional Federal Government has little territorial control (without allied forces) beyond Mogadishu, and its mandate ends on 20 August 2012. There is concern about exit strategy, given government troops limited capacity. Reports also indicate that treatment by government forces have been exploitative of local populations, and in particular women. This further limits trust of the population. There are also many areas of southern Somalia that would be classified as something between local areas of stability and NRAs and either continue to be dominated by AS, or have no formal governance. In these areas, AS is able to target and intimidate leadership. These ‘gap’ areas are outside of the reach of TFG-affiliated forces, and AS assassinates leaders who step forward to set up structures to govern and provide services. Other parts of Somalia suffer from active fighting for control although efforts are being made, by the Intergovernmental Authority on Development for example, to mediate a lasting political settlement. / Primarily in Central Somalialocal areas of relative stability have emerged although they are often delimited along clan lines. Some, such as the Galmudug Administration, have established relations with the TFG. In many administrations, there is limited capacity to provide security, and hubs for piracy and AS remain. Militias operating in these areas, though mostly anti-AS, have not shown interest in providing services beyond security. Some areas are far more stable and able to prioritise development interventions. / The SSP’s theory of change is that by resolving localised conflicts that create instability, and joining areas where peace has been established into an overarching framework for reconciling competing interests, the absence of which historically has undermined establishing a unified state, a network of stable areas abiding by an agreed set of governance principles may emerge (see paragraph 23 on how local stability has a multiplier effect on national stability). Local disputes are within and between communities. A lack of governance in these areas means that actors (clans, militias, AS, TFG, and others) endeavour to control and direct the flow of limited resources and establish informal authority. Where areas have stabilised in Somalia, it is because local processes have been able to negotiate settlements between power-brokers and affiliated security actors. The theory of change believes that reducing tensions over resources by bringing together communities to plan and get access to additional services will reduce sources of competition, that working with power-brokers to manage and negotiate settlements peacefully will bring about greater security, and that in some instances formalising some of these negotiations into governance structures will provide a framework for managing conflict and a basis for stability in local settings. Informally, this is already happening in some areas, but a national level resolution is needed that areas can engage with to assure a common basis for the rule of law. / International policy context / The UK Prime Minister’s February 2012 London Conference on Somalia agreed that the international community should make a concerted effort to deliver a step-change in our support to the more fragile areas of Somalia. The conference set out principles to guide international engagement on local stability, and announced a multi-donor Fund to integrate political, security and development interventions and prioritise a rapid and flexible response to emerging opportunities. / Regional bodies have invested considerably in achieving stability across Somalia, primarily for their own security interests. These bodies, with the UN and other donors, are key partners for the UK. Strong co-ordination in the implementation of stability initiatives is needed to ensure appropriate geographical and sector coverage. Beyond the broader context of the UN’s Security Council Resolutions on Women, Peace and Security (including 1325 &1820) and SCRs on Somalia (1772, 2036), the African Union, IGAD and the UN are working closely together (the UN Special Representative for Somalia has been working with IGAD on the Grand Stabilisation Strategy), including on a mapping exercise on key actors in SCS with a view to “…achieving reconciliation and putting in place local administrations responsible for security arrangements, disarmament and the delivery of basic services”[11]. The SSP is aligned with these evolving frameworks and plans for stability, and will continue to be informed by them. / A USAID-funded programme (Transition Initiatives for Stabilization)supports quick-impact, 12-18 month community-driven projects in selected areas to increase economic opportunities, build confidence in the peace process, and promote stability. Project activities are wide-ranging and include small-scale infrastructure, rehabilitation of clinics, markets, local government buildings, livelihoods support, irrigation canals, etc. DFID and HMG colleagues in the British Office for Somaliawill continue to co-ordinate and liaise closely with TIS and other interventions as they evolve. / UK role and contribution / The UK’s priorities are set out in the Strategy for Somalia. The National Security Council has identified Somalia as a priority country - there are specific policies on counter terrorism and counter-piracy.[12]In addition to reflecting the UK’s National Action Plan for SCRs 1325 and 1820, the DFID Somalia Operational Plan has been developed with other UK government departments as a central plank in delivering the UK strategy for Somalia, including meeting the priorities of the NSC. The Operational Plan has also prioritised aims “both to address the humanitarian effects of the conflict and to consolidate local areas of stability by helping local communities to take control of their own affairs.”[13] / The SSP contributes to the fourth structural reform priority in DFID’s Business Plan (2011 – 2015) – to strengthen governance and security in fragile and conflict affected countries, particularly in improving coherence and performance. It builds on HMG stabilisation programmingwhich aimsto establish early political and security conditions needed to promote stability. Additionally it provides a platform for the DFIDSomaliaCSFP,which builds state capability once sufficient stability exists. The SSP supports deliveryof Objective 5 of the UK Somalia Strategy – Promoting Stability at the sub-National Level. / DFID has a strong track record of designing and delivering in complex fragile states contexts, for example in Iraq, Afghanistan, Nigeria, Nepal, Northern Uganda, Eastern DRC, Yemen, and the Middle East. DFID’s knowledge management and the expertise in its specialist networks are a world-class resource. DFIDSomaliahas built up substantial experience from its programme portfolio to deliver in fragile areas across Somalia, including work in areas at threat from insurgents. This experience provides a base of experience and knowledge to deliver a programme dedicated to building stability in areas posing the highest threats to Somalis, its neighbours, and the international community. / Risks of intervention and the consequences of non-intervention / The areas of intervention include the more fragile areas of Somalia where risks, including that of doing harm through injecting new resources, are high. Design work for this programme includes a number ofpilot projects in NRAs to test risk management approaches, methodologies to overcome access restrictions, and promote conflict sensitivity. These projects were preceded by stakeholder consultations and context-specific analysis covering political (including political economy), development and security issues in three areas – Gedo, Bay and Hiraan Regions. / Without this intervention opportunities to consolidate and build stabilityat this potential turning as areas are recovered from militants and new political settlements sought, there is a risk gains will be lost. Somalia’s history demonstrates the risk that failing to followmilitary action with support to build stability can result in a worsening of conflict, insecurity, and a reverse in human development. Without better-targeted and more responsive investment, there is a heightened potential for new conflicts to emerge and old conflicts to re-emerge. / DFID’s humanitarian and stabilisation support to Somalia is foundational for the SSP. DFID Somalia’s humanitarian assistance seeks to promote greater household and community security. The SSP will complement this work by offering a vehicle to transition communities that have reached a sufficient level of resilience into development programming that is adapted to context, and recognises the continued fragility of areas which have reached only a limited level of stability and capacity. Our stabilisation support focuses on NRAs and follows military intervention. The SSP can build on the quick wins and work to develop security in such areas by offering a longer term more comprehensive set of interventions. In turn, the SSP is foundational for DFID’s support on health, wealth, and girls education, working to both complement current support (e.g. by developing facilities prioritised by communities) and by creating the conditions (peace and security and nascent delivery of services) on which those programmes can build. / The mandate of the TFG comes to an end on 20August 2012. While it is probable that small advances will have been made towards an inclusive and credible national political settlement (e.g. a smaller and more representative parliament) it is likely that the successor central government will remain limited in capacity and legitimacy. Without a comprehensive national settlement, notably one that clarifies relations between different levels of government and facilitates service delivery, a risk remains that without flexible and tailored support to emerging areas of stability those areas will not reap the benefits of peace or be incentivised to work towards constructive relations with their neighbours. / Feasibility and evidence / Experience demonstrates that an effective response to the current opportunity should include political, security and development activities – combined and sequenced according to context. The evidence base,as detailed under the appraisal of Options 1 & 2,will include: i) insightsfrom assessments and pilot projects; ii) iterative lesson-learning from process evaluations and monitoring during programme implementation; iii) DFID-S lessons-learned from on-going programmes; iv) lessons from other stability programming, notably TIS;v) experience from international stability programmes, including multi-donor funds and thematic approaches to stability; and v) wider research on breaking cycles of violence and in embedding stability, set out below in the appraisal of options for this intervention.[14] / International support for SSP is high. Building stability and reducing conflict is more feasible on the back of military action, provided political and military strategies are aligned. / Impact and outcome / Intended impact of the programme is a better-governed and more stable Somalia. The outcome is a greater number of areas of stability [in Somalia]. Using an existing programme to estimate an indicative measure of what could be achieved, the four SSP individual outputs would overlap and come together to provide the full outcome of improved stability in over 400 communities. / Output 1: Development projects led and implemented by communities to meet their immediate needs / Output 2: Greater number of communities are safe and more secure / Output 3: Legitimate and representative local administrations established / Output 4: Greater number of inclusive local& regional peace agreements contributing to zonal and national peace. / The relationship between the outcome of a greater number of areas of stability and the impact is based on the concept that a multiplier stability effect (measured by output indicators) will carry from the local to the national level.Governance structures that are seen to bring peace dividends will be perceived as more legitimate and will have a better basis of support against potential spoilers. Trust within communities and with administrators will reduce the space for extremism and criminality. / There are complementary linkages between DFID Somalia’s programmes (as noted with CSFP in paragraph 14) and the SSP at the implementation level, working with communities and local actors to integrate the political, security and development elements of these interventions, to build local stability and strengthen local governance.[15]
[1] Al Shabaab - a proscribed Al Qaeda affiliated terrorist militia with global jihadist aims.
[2] Fund for Peace, published by Foreign Policy, 2011 Failed States Index (www.foreignpolicy.com/failedstates).
[3] UN Office on Drugs and Crime – ‘Organised Crime and Trafficking in East Africa.’ (www.unodc.org/documents/easternafrica)
[4] One Earth Foundation report – ‘The Economic Cost of Piracy 2011’ - estimated at between $7 billion and $12 billion in 2010 alone. (www.oneearth.org)
[5] Norris & Bruton ‘Twenty years of collapse and counting’, Centre for American Progress 2011 (www.americanprogress.org/issues/2011/09/somalia.html)
[6] February 2012. Somalia: Displacement and Worsening Humanitarian Situation. Internal Displacement Monitoring Centre (http://www.internal-displacement.org)
[7] UNICEF statistics (www.unicef.org/infobycountry/somalia)
[8] See the TrustLaw 2011 survey (www.trust.org)
[9] OCHA Somalia – key figures on Somalia (March 2012) (http://ochaonline.un.org/somalia/Reports/SomaliaHumanitarianOverview)
[10] See Africa Confidential 2 March 2012. Vol. 53. No. 5. Pg. 4.
[11] Ibid (footnote 15 above)
[12] CONTEST, the UK government’s Strategy for Countering Terrorism; May 2011. Specific counter-terrorist projects are principally funded by the cross-Government Counter-Terrorism Programme, which is managed by the Foreign & Commonwealth Office. These projects are delivered by and with a range of Departments and agencies, including the Ministry of Defence, Department for Transport, Crown Prosecution Service and the Metropolitan Police Service. Spend is tightly aligned with addressing the highest risks to the UK and UK interests. Priority areas include: Pakistan, Somalia, Yemen and Afghanistan.
[13] DFID Somalia; Operational Plan 2011-2015; May 2011
[14] Examples of evidence include GAPP implementing partners activities (paragraph 31) multi-donor funds in several fragile states (paragraph 34); and various Lesson Learning sources such as DFID practice papers on Peaceful States & Societies (2010), SDD’s Youth, Exclusion, violence, conflict and fragile states (2009)Evaluations of USAID programmes in Yemen & Liberia (2009) – See SSP Source Material for details of reference material
[15] Other programmes include the core state functions programme, which will provide institutional support on the back of stability programming once areas have ‘graduated’ to an appropriate level of stability, the accountability programme looking at generation of demand-side governance, and a monitoring and evaluation programme that cuts across and supports the other three programmes.

# Appraisal Case

Introduction / The SSPwill operate across all three zones of Somalia,as well as support the national reconciliation process. The programme will take a pragmatic approach to its geographical focus, with choices of intervention being determined by access, need, and ability to deliver results. The options appraised here offer two means to improve stability in Somalia, which are then considered against a ‘do nothing different’ counterfactual case. / The first option is to deliver the entirety of the programme (£30 million) through a multi-donor Somalia Stability Fund along with Denmark, the Netherlands, the United Arab Emirates, and Norway. A minimum ofa £15 million UK contribution was announced by the Prime Minister at the London Conference on Somalia. / The second option is to deliver the majority of funding (£27 million) for this programme through the Fund,with the remainder (£3 million) delivered bilaterally on issues of high UK strategic importanceand/or reputational risk that require direct HMG oversight. / The appraisal of Options 1 and 2 focuses on comparing and assessing modalities for building local stability in Somalia and identifies the optimal combination of modality. / The evidence basefor Option 1, the SSF, is medium/limited. The Fund has been shaped by experiences of implementing multi-donor funds elsewhere in fragile states and by what we have learned from implementing smaller scale but relevant work in Somalia. The evidence for Option 2 is also medium/limited and draws on research, policy analysis, and practitioners experience which points to the need to hone in and give more oversight to areas of greatest risk and strategic priority. In the appraisal of the counterfactual (Option 3), the risks and consequences of not prioritising these interventions are assessed. / Option 1: Multi Donor Stability Fund / UK contribution of £30 million / The SSF will broaden support for stability initiatives, enhance co-ordination, and increase aid effectiveness.[16] The full structure and governance of the SSF is provided in Annex III, and an outline is provided in the Management Case below. / The SSF is designed to match support to opportunity. At present most stability and stabilisation initiatives are channelled through bilateral programmes that are dependent on the capacity of centrally-engaged implementing partners (and theirlocal partners). While the individual programmes are well designed, their capacity is limited to the number of staff (particularly Somali national staff), the logistical resources of the implementing partner, and the degree of insecurity under which they judge theycan safely operate. These bilateral programmes have proliferated, creating a highly fragmented and incoherent portfolio of international support, which also undermines the opportunity to leverage change between programmes. Programmes are clustered in and around urban centres in SL and PL and in Mogadishu in SCS, where there is better access and some security. There is a much lower level of coverage in rural and coastal areas, despite these being the primary recruitment ground for AS and other armed militia groups, and where the development need is highest (see Geographical Assessment at Annex V). / As a common funding mechanism, the SSF will provide coherent governanceand management of pooled resources. A Steering Board(SB) will set the strategic direction of the Fund andfacilitate a better coordinated approach to geographical coverage. The SB will be supported by a technical Secretariat Office (SO), staffed in part by donor representatives, tasked with overseeing programmatic decision-making. The SO will, in turn, oversee a Fund Manager. A critical decision for donors is whether a multi-lateral institution is selected as Fund Manager or if a tender will draw a more competitive and responsive pool of applicants (whichmay include multilateral tenders). The economic appraisal of this decision is summarisedat paragraph 63, and in more detail in the Economic Appraisal at Annex II. It is critical that the Fund responds to need and emerging conditions by being flexible and responsive. To achieve this, it will accept proposals at all times at the outset, although as FM mechanisms are finalised, the use of calls for proposals alongside, and in due course instead of, review of unsolicited proposals throughout the year may be considered. / In-depth assessments[17] of thedifferent geographical areas of Somalia highlight the need for a funding mechanism that is able to intervene at different levels, in different ways. In some cases, the engagement might be opportunity-led, such as employing conflict resolution between communities, while in others the engagement might be issue-led – dealing with the consequences of instability. In all, the combination and sequencing of political, security and development interventions will be tailored to the local context, which can be broadly categorised into the following types: / A: AS controlled areas / B: Active conflict areas (including areas where AS control ebbs and flows) / C: Newly Recovered Areas (where AS has withdrawn and interim administrations emerged or are planned) / D: Local areas of stability (with some level of administration) / E: Potential development areas (where medium- and long-term development can be pursued) / The programme will work across all areas of conflict as need demands, and within each category, ensuring interventions are tailored to the very local context. Although specific projects have not yet been selected, DFID Somalia has developed a draft scorecard setting out the criteria against which the Fund’s projects will initially be selected. / Evidence for a flexible, responsive and integrated Fund / Evidence for the design of a flexible, responsive Fund comes from a review of Funds that have been established in a number of fragile states (as listed below). Experience demonstrates that ‘top-down’ approaches to governance and security (centralised, contractually structured, procedurally allocated, mid-to-large scale funding envelopes) have not,in isolation, been successful. This is in large part because they are not able to respond in a timely fashion to rapid changes in the local environment. Though the Afghanistan Reconstruction Trust Fund had many benefits, its limited decentralisation and inability to access its areas of implementation made it less capable of understanding and responding to changes on the ground. In Libya, the Temporary Financing Mechanism was designed without anticipation of how to respond to changes not foreseen at inception. For instance, its rigid governance structure created obstacles to paying salaries for hundreds of thousands of state employees, which was needed to mitigate unrest stemming from unemployment. The Fund must be designed to respond to an ever-evolving context, and have a structure that is flexible enough to respond to needs that are unforeseean at the outset.[18] / Country Fund Fund Manager / Afghanistan National Solidarity Programme World Bank / Office of Transition Initiatives programme USAID/OTI - Afghan Transition Initiative& IOM / Afghan Reconstruction Trust Fund World Bank / PRT Quick Impact Projects Programme Helmand Provincial Reconstruction Team / Libya Temporary Financing Mechanism TFM, International Contact Group / National Transitional Council of Libya / Sudan Common Humanitarian Fund UNDP Fund Management Unit / Nepal, Iraq, Cote D'Ivoire Multi-donor Trust Funds various World Bank / The case has also drawn from lessons learned of past experience in Somalia. This includes the provision of stipend and capacity building support to the central government which delivered poor results, and the Search for Peace work by Interpeace[19], which showed that flexible, Somali-led engagement where evolving Somali political allegiances can be accommodated are more successful. / The SSF will follow a phased approach that integrates political, development, and security interventions. The types of project that might be supported are set out below in paragraph 44.Such interventions will be combined and sequenced to fit the local context. For example, in active conflict areas with limited local capacity, work may focus on facilitating a peace settlement, providing alternative jobs to disbanded militias, and building community security. The entry conditions for interventions in this type of context would be set low to allow actors with limited capacity to benefit from the programme, but the scale of resources would be concurrently low to manage risks (notably of doing harm and of fiduciary risk). This type of support would build agreement and capability, allowing these areas to graduate to a different combination of activities (e.g. the combination of support could be expanding the existing political settlement to neighbouring areas, linking service delivery to more mature programming like health, which can deliver better and more comprehensive services, and strengthening the local administration and security services to assume a fuller range of responsibilities) as results are demonstrated, capacity built, and risk reduced. / Many analyses of Somalia have flagged a clear need to address local political realities,[20] security considerations,[21] and development needs that reduce pressure on scarce resources. Yet there is relatively limited evidence for integrating these strands, as few programmes in Somalia or elsewhere have tested whether work on political, security, and development can have a multiplier effect on one another. As such, DFID Somalia has developed a robust, complementary Monitoring Programme, and the Fund will rigorously measure its approach to learn about what works. / There is some conceptual evidence supporting an integrated approach. The 2011 World Development Report makes a link between institution-building and improved management of violence and conflict, and also points to the importance of cross-sector working and the integration of programmes.[22]Evidence from Afghanistan has shown that improved service provision and accountability can help reduce risk of violence. Moreover, the use of a political-economy lens to assess contexts and identify entry points highlights the importance of looking holistically at environments and how government, security, and economic stakeholders and systems interact to find positive trigger points. The SSP allowsa comprehensive approach at the full set of challenges and to identify entry points across the security, development, and political spectrum which will catalyse change. / The Fund will also target vulnerable groups through a dedicated window. In Somalia, women are marginalised frompolitical decision-making processes, differentially affected by violent conflict (e.g. displacement), make up a majority of the rural labour force, with their potential productive contribution is unrealised.[23] Their role as facilitators of peacebuilding and as breadwinners has evolved considerably over the course of Somalia’s conflict. A report by the UN’s independent expert on Somalia noted that domestic violence, sexual violence, and such harmful traditional practices as female genital mutilation are some of the most common violations of women’s rights in Somalia. The Fund will promote the protection and participation of women in all interventions, with a focus on responding to women and girls’ priorities and solutions. / Youth (particularly adolescent boys & young men) are beginning to return from internally displaced person/refugee camps, and some are also de-mobilising from AS forces. Reintegrating these individuals back into communities and providing them with alternative livelihoods will reduce the risk of them either re-joining AS or joining other militias, and engaging in conflict or criminal behaviours (violence, drug abuse, etc.).[24] Where possible, preventing initial engagement in such activities is also vital.The Somali Child Protection Working Group has documented evidence that children are being recruited by AS, TFG, and other allied militias. The Fund will support young men and adolescent boys in all interventions, target them through the vulnerable groups window, and seek links with both short-term humanitarian assistance such as cash for work programmes, as well as livelihood programming such as the DFIDSomaliaSustainable Employment and Economic Development programme. / IDPs and the urban poor are a growing vulnerable group in Somalia due to displacement by conflict or famine[25]. Many of the displaced people, having lost their livestock and sold their land during the famine of 2011, will not return to their homes and will choose to remain in urban centres. Although there is greater access to urban locations, there are specific challenges in the role of gatekeepers – either the owners of the land where the IDP camps are located, or camp committees that approve access (both for people & aid). The Fund will work with groups from multiple groups simultaneously, establishing points of engagement around alternative livelihoods (e.g. small co-op committees), water, health & sanitation committees (basic services shared across camps), and education committees aligned to schools. / A summary of the type of political, security, and development interventions the Fund will support is provided below. / Security Political Development / Geographically targeted projects along coastal districts where piracy emanates / Community-level security initiatives identified through community development plans but in insecure locations (in light of the expected continuation of fighting between TFG & AS forces into 2013) / Peacebuilding between clan-based groups (political/armed) / Peace building between minority clans and the SL/PL governments / Cross-border projects that support stability among clans and communities that are separated by a national border (e.g. pastoral livelihoods) / Interventions focused on mitigation of risk/prevention of violence against women & girls Support for the implementation of the TFG Roadmap, including support for the new constitution / Targeted conflict resolution projects (geographic specific) looking to resolve legacy disputes that have fuelled longer term instability between communities/clans / Strengthening of nascent administrations as a first-stop to broader sub-zonal dialogue (e.g. facilitating an engagement between Ximan/Xeeb and Galgadud authorities) / Facilitation to national reconciliation initiatives either between individual zones (such as the border dispute between SL & PL) or between the three zones in national stability & development opportunities / Support to a national political policy on SCRs 1325 & 1820 Employment & livelihood support to mitigate the risk of recruitment of adolescent boys into AS or armed militia (i.e. anti-terrorism; anti-piracy) / Programmes that address the cultural and societal challenges that women and girls face / Investment in scarce resources aligned to traditional livelihoods and associated disputes / Investment in strategic resources aligned to traditional livelihoods (complementing DFID Wealth programme – SEED) / Reintegration (return) or integration (with host community) programmes with IDPs / Region/Zone Contextual & Political Economy Analysis (linked to baseline & Option 2 decisions on where to channel SSP funds) / These types of intervention will be combined in each area as according to context (refer to paragraph 36 above for examples of how this might look). / Based on work already commenced by proven partners, including UN JPLG, CDRD, and PACT, as well as on assessments of progress from similar projects on smaller scales (for example the UNDP community safety perception surveys), we have extrapolated the results we can expect to deliver by the end of this multi-year programme. DFID anticipates that : / 910 communities (a rise of 89%) will have development priorities endorsed by the community and by local authorities. This output alone will benefit approximately 4.1 million people (a rise of roughly 1.5 million). / Over 71,000 will feel safe from armed conflict. / 87 districts across Somalia will have in place legitimate local administrations. / These results are all components of building stability. Depending on the activities taken forward, the sum of individuals reached by the different outputs of the programme could be up to 9.7million (the total number of individuals reached will be less than this as some individuals will benefit from more than one activity). In some areas where we are able to overlap programming, communities and individuals will benefit from more than one output and will have more of their needs metWe anticipate that stability will be improved in 400 of the communities where we engage (where output results aggregate/converge to achieve outcome). / Given the imperative to achieve value for money, and to ensure the structure of the Fund meets needs, its managemetn will be put out for competitive tender. This tender will be open to private sector companies as well as NGOs, multilateral institutions, or consortia of organisations. / Risks / There are a number of risks associated with the delivery of assistance in Somalia, including fiduciary and development risks, risks to the security and well-being of project personnel and communities, corruption, and inadvertently generating or exacerbating conflict. These risks may be categorised broadly as development, fiduciary/financial,and political/reputational risks: / Development: the risks that undermine the chances of the Fund being able to support sustainable local stability in each of the three zones in Somalia. / Fiduciary/financial: the risks that exist within the individual stability projects that the Fund will support, or in the FM’s duties while supporting these projects. / Political/reputational: the risks that given the strong UK political emphasis placed on this approach, and the capital put behind it to get coherence around this approach, that any failure may harm the UK’s reputation in Somalia. / A full risk assessment and mitigation measuresis included in the Management Case. The SSF has built-in checks and balances to give it a highrisk management capability. These include the separation of roles and responsibilities within the Fund, robust monitoring processes, the ability to actively engage with external actors and existing coordination mechanisms, and to undertake dialogue with recipients. / The multi-donor dimension of the Fund is in itself a risk mitigation strategy, spreading the exposure across a range of partners. The expected benefits of enhanced co-ordination, shared analysis, reduced administrative and transactions costs, and a common approach balances the risks of greater complexity through the integration ofpolitical, security and development work. / Option 2: Multi Donor Stability Fund plusprioritised bilateral interventions / Commitment of £30 million with £27m to theSSF and £3m to prioritised bilateral interventions / Option 2 looks to retain the flexibility and responsiveness of the SSFand supplement it with high priority bilateral interventionswhich further UK policy priorities and have higher reputational risks to HMG,thus requiring direct UK governmentoversight. / The nature of multi-donor funds with shared governance and decision-making structures implies the Fund may not fully accommodate allHMG priorities. Option 2 combines the innovative approaches of the SSF, and to complementthis with the following additional benefits: / Allows HMG to initiate programmes that will deliver UK policy priorities (such as targeting piracy strongholds). / Offers the opportunity to build links between the Fund and other HMG programmes, both DFID and OGDs e.g. on counter piracy and counter terrorism. / Retains management of political and reputational risks within HMG. / Allows DFID some discretion in decision making to fill gaps in local stability initiatives – targeting at-risk groups and/or certain geographic areas. / The allocation of funds(up to £27 million to the Fund and £3 million to bilateral interventions) will be reviewed on an annual basis. If opportunities to forward the national political settlement through means more appropriate as bilateral support emerge, a recommendation to reduce the amount to the Fund and increase the amount allocated to bilateral work will be considered. In addition to leveraging the investment in DFID’s own programmes, other donor-funded programmes contributing to local stability will be considered as a mechanism to deliver UK bilateral support. / Risks / As noted, bilateral interventions allow for someof the risks of a standalone Fund to be mitigated.However, bilateral interventionsmay increase the risk of aid fragmentation and limited sustainability.These risks will be addressed in the design of each bilateral intervention. Overarching development risks apply to both options, as the outcome and impact (and challenges and opportunities) of engaging in local stability interventions are common to both. The risk assessment and mitigation strategies for a range of categories, encompassing both options, are described in the Management Case. / Option 3: the counterfactual “do nothing different” / Framing a counterfactual serves to highlight a number of points. The counterfactual is based not on “do nothing” but rather “do nothing different”where we wouldcontinue with a set of less integrated interventions. Doing nothing different would continue to place considerable management stretch on DFID Somalia, which limits our ability to extend and deepen the UK@s support to local stability. Consultation also indicatesthat other donors are not ready to even replace the support DFID currently provides, nevermind nor scale up, as is the UK’s strategy.. / The purpose of building stability is to provide a secure foundation for political progress that in turn strengthens the development of a country and its population. Instability, manifested in conflict, creates an environment that: / Heightens the risk of sexual violence to women and to adolescent boys/young men in recruitment (both voluntary and forced) to armed militia; / Forces large-scale population movement; / Disrupts and destroys livelihoods and economic activities; and / Exacerbates the threat to life in times of humanitarian crisis by restricting humanitarian access.[26] / A likely consequence of not doing anything different is that Somalia’sconflict continues. Since the collapse of the Somali state, an estimated one million people in Somalia have died as a consequence of war, famine, and disease. Somalia has the highest rate of maternal mortality in the world. Piracy off its coast poses a threat to international shipping: in the first half of 2011 more than 154 ships were attacked, with 21 hijacked and a total of 362 people taken hostage. The One Earth Foundation estimates that in 2010 the costs of Somali piracy to the global economy ranged between US $7billion and US $12 billion. The costs of such failed states ‘are immense and long-lasting’[27], encompassing more than just security concerns – failed statesincrease the risk of regional instability andmay make it harder for business to invest in neighbouring states. / The present conditions in Somalia facilitate organised crime, providing opportunity for criminals to exploit the situation and accumulate illegal profits. In such circumstances, criminal networks are able to take advantage of the absence or weakness of criminal justice systems, and may often collude with local warlords, control the provision of public goods and services, hamper humanitarian assistance, destroy, corrupt or distort the provision of state institutions and services. Violent conflict is both exacerbated by and exacerbates impunity, even from serious crimes. / The conflict in Somalia has encouraged the trafficking of firearms in the region and is a cause of the high influx of refugees, causing long-term detrimental consequences in the region. In addition, conflicts have spill-over effects such as the disruption of the local economy, human rights violations and the disappearance of vital state functions – effects that are evident in the neighbouring countries in the region. / Without this programme, we will not meet the commitments made by HMG at the London Conference on Somalia in February 2012, where the Fund and local stability approach was announced. The Secretary of State has flagged four key issues for DFID Somalia following the Conference, which include: (i) the Joint Financial Management Board, (ii) local stability approach and in particular the Stability Fund, (iii) AMISOM support, and (iv) ending the transition. The SSP is the most direct mechanism to support priority ii. It also will facilitate priority iii first by helping to consolidate stability on the back of military gains, but also to create conditions that would allow for AMISOM to consider exit. This offers the chance to move forward on the local stability priority and approve the Stability Fund for implementation. The SSP further supports priority iv as it will extend support for a national political dialogue by creating more areas of political stability and greater local governance structures that are able to represent constituencies in a reconciliation framework. / The evidence that acting to address Somalia’s instability and to do that by extending and deepening the UK’s programme is sufficient to discount Option 3.
Assessing the strength of the evidence base for each feasible option / Option 1: Multi Donor SSF only / Option 2: SSF with prioritised bilateral interventions / Option 3: Do nothing different. / Table - rating the quality of evidence for each option (strong – medium – weak) / Option Evidence rating / 1 Medium/Limited (evidence based on MDTF in fragile states) / 2 Medium/Limited (evidence based on research into priority areas) / 3 N/A – counterfactual appraisal / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The risk and opportunity assessment for Options 1 and 2 is based on limited information available on the types of projects to be funded – and in both cases, as it is likely that individual projects will have environmental components.The risk and opportunity are both scored as B (medium risk and medium opportunity). / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 B (medium risk) B (medium opportunity) / 2 B (medium risk) B (medium opportunity) / 3 N/A counter factual option N/A counter factual option / Impact of activities on the environment/ climate / There will be an indirect climate change or environmental impact by the individual projects that are submitted to the SSF or are supported bilaterally. These impacts will be assessed and addressed in the design and appraisal of projects.
Costs and benefits of feasible options / Because exact information on the activities to be funded will not be available until proposals are reviewed, a definitive cost-benefit analysis cannot be compiled (see paragraph 33 on scorecard for assessing project criteria). Instead, the approach taken in this economic appraisal is to identify for each component of the SSP a set of indicative activities (using information based on existing projects across Somalia), their costs and the numbers of individuals who could be reached for a budget of £1m spend on the activity. This information can help inform us as to the balance of activities that might make best use of the available budget, by starting to identify the costs, benefits and the value for money that can be gained. / However, there are several important qualifications to note: / Whilst it is possible to quantify the numbers of beneficiaries reached by the activities, it has not been possible to quantify or to monetize the nature/degree of the benefits themselves. This means we have cannot calculate the “marginal utility” provided by different kinds of activity. Marginal utility is in practice the amount of benefit gained for each additional £1 of activity and in its absence we cannot compare the benefits of different types of activity (e.g. access to a health centre compared to youth mentoring). / Quantified benefits are only one factor in determining the mix of activities in the programme. There will be important strategic and non-quantifiable considerations that need to be factored into decisions including factors such as the absorptive capacity of implementing partners, the quality of the proposals received for funding and the performance demonstrated during implementation. / The evidence base is so weak that it would be imprudent to conclude an optimal mix of activities based on a quantified analysis alone. / Some activities are geographically dependent, and the ability to carry out certain activities will depend on a minimum level of stability in a given area. This level of stability cannot be presumed. / The table below sets out the approximate total cost to all donors of stability spending in Somalia over the next three years (Fund donors plus USAID spend to related activities). UK finance through the SSP programme is approximately 39% of donor spend on stability over three years. / Donor Year 1 / Sept 2012 – Dec 2013 Year 2 / 2014 Year 3 / 2015 Total / Million GBP Percentage of Total / UAE 0.2 0.5 0.6 1.3 2% / Netherlands 0.8 0.4 0.4 1.7 2% / Norway 0.2 0.5 0.6 1.3 2% / Denmark 0.2 0.5 0.6 1.3 2% / UK (SSP) 10.7 9.2 10.1 30.0 39% / UK (ACPP) 1.5 1.5 1.5 4.5 6% / USAID 12.6 12.6 12.6 37.8 49% / Grand Total 26.2 25.2 26.3 77.7 100% / The table below then sets out a set of indicative activities that the fund, and bilateral spend might finance, in three of these four components (within the Stability Fund – political, security and development spending; outside the Stability Fund – high risk political projects) and describes, and provides limited quantification of the benefits expected from those activities. / Political Description of benefit Quantification of benefit / Youth mentoring Unemployed youth, drug addicts, ex combatants, school dropouts, young divorcees and sex workers targeted for mentoring to de-radicalise youth and reduce risk of targeting by insurgents In one quarter, 175 mentees mobilised to target youth / Capacity development of peacebuilders Reduction in conflict following theft, return of stolen livestock, effective engagement of elders, elites, religious leaders in local peace processes. In one quarter, 277 individuals trained in mentoring, mediation and conflict resolution and reconciliation. / Construction of Peace Dividends (community structures shared by communities, clans or villages in conflict) Identification, construction/rehabilitation and training to enable shared management of assets previously the source of conflict e.g. roads, halls, schools or dispensaries. Roads can be used by 40,000 people, 6000 -8000 people might benefit from a school and up to 40,000 from a community centre. / Security / Creation of district and community safety committees and safety plans. Training on firearm safety, conflict management, voluntary surrendering of firearms. Communities feel safer, less violence, accidents with fire-arms or mines/unexploded ordinance, reduced crime. Estimated 20% of population in targeted urban areas, and 25% of population in immediately surrounding rural communities expected to benefit. Results from evaluation of project in Somaliland 2008-10 found 70% decrease in fear of small arms, 39% decrease in threats made with small arms; 74% of respondents consider conflict was reduced. / Development / School rehabilitation or construction Increased number of children with access to education facilities; improved conditions for learning; increased educational attainment levels 15,000 - 20,000 beneficiaries, but up to 70,000 people can benefit from construction of a school in some areas (e.g. IDP camps) / Health Centre/TB centre construction Increased number of people with access to health facilities and improvement in the conditions in health facilities Up to 20,000 people can benefit from a health post or TB centre / Market rehabilitation/construction Reduced transaction costs for traders, job creation and diversification Up to 15,000 -25,000 people can benefit from construction of a market / Road rehabilitation Lower cost of transport, time saved, lower cost of goods, increased access to markets, water, health and education facilities. Between 10,000 - 50,000 beneficiaries depending on the location of the road / Construction of water system Increased number of people with access to clean water, time saved, improved health outcomes From 10,000 - 70,000 people can benefit from construction of a water system, drainage, latrines or berket / Bilateral political / Support to Somali constitution More transparent, legitimate, technically sound and participatory process of drafting and agreeing constitution Somali population is approx. 10m / Building on the table above, the table below sets out the indicative cost of each type of activity across the different political, security and development areas, and consequential cost per beneficiary reached (on average, based on existing activities). / Output/ component % of total budget for the output Value of budget of example intervention(s) (£) Average size of intervention (£) Average number of interventions for £1m Average number of beneficiaries reached for £1m Indicative cost per beneficiary (£) / $1 = £0.6 / Political 0.18 / Youth mentoring/ Youth centres 417,150 29,796 34 5993 166.9 / Capacity development of local level peacebuilders/peace committees 156,655 52,218 19 1768.2 565.5 / Peace Dividends[28] 506,195 72,314 14 204980 4.9 / Security 0.36 / Creation of district and community safety committees and safety plans. 2,500,000 625,000 1.6 10,440 95.8 / Development 0.36 / School rehabilitation 256,855 18,347 55 114,243 8.8 / Health Centres 104,351 8,027 125 365,372 2.7 / Market rehabilitation 214,410 12,612 79 516,024 1.9 / Road rehabilitation 518,151 18,505 54 1,110,570 0.9 / Water and sanitation infrastructure 276,666 12,029 83 1,429,657 0.7 / Bilateral political 0.07 / Support to Somali constitution 8,700,000 8,700,000 0.1 1,149,425 0.9 / Based on the proposed breakdown across components and the estimated number of beneficiaries reached by each activity under the SSP, excluding spending on support to the constitution, DFID’s allocation of £27m to the SSP (which is the £30m minus the cost of support to the constitution) would be able to reach a cumulative total of 9.7m individuals at an average cost of £3.09 per person. Note this figure is simply the sum of numbers reached by different activities, and as such may involve double counting as some individuals will benefit from more than one activity. As we do not yet know the exact nature or location of the projects to be financed, it is impossible to be more precise at this stage. / This suggests that the SSP is extremely viable from a VFM perspective – we might expect an intervention ordinarily to cost up to £10 per beneficiary and consider that good value. Adopting a purely cost per beneficiary approach, it would be possible to reach more individuals by using a different breakdown of activities and percentage sharing of the finances across components. / However, it is clear that for an activity to reach a beneficiary does not mean that each activity will produce an equal amount of benefit felt by that individual. As discussed in paragraph 64/65 above, without any information on the nature or depth of benefits from each type of activity (the marginal utility) we are not able to make quantified comparisons between different activities. / It is also likely that the phenomenon of “diminishing marginal returns” applies. In an ideal world, the split of spending between the different components (political, security, development) and between the different method of disbursing (bilateral vs MDTF) would be made on the basis of where these “marginal benefits” were equal – i.e. were there to be a decision about where or how to spend the next £1 available that £1 would produce the same level of benefit no matter in which activity/component it was spent. Unfortunately, with the information available, it is not possible to calculate that point at which marginal benefits are equal. In the absence of this kind of information, making decisions on a purely quantitative basis would be unwise and questions of distribution of finance across components can only consider the quantitative information available in a larger strategic, practical, and qualitative decision. / For further detail see Annex II: Economic Appraisal
Measures used to assess Value for Money for the intervention / Given the difficulties identified in quantifying or valuing benefits in terms of efficiency and effectiveness above, it will be important for DFID to work itself and encourage others to prioritise developing the evidence base for understanding the cost effectiveness of stability interventions. The Management Case sets out how DFID intends to use its voice on the management board of the Stability Fund to push for meaningful information on programme cost drivers of inputs and activities and cost effectiveness of outputs and outcomes. / The following table reflects indicators in common with other Somalia programmes but including specific indicators for this programme. In practice, economy indicators are genuine VFM indicators, whereas effectiveness and even efficiency indicators are essentially the same as those in the logframe. This is common with other governance programmes where the outcomes and even outputs are so heterogenous that indicators of efficiency and effectiveness do not often help to make comparative judgements and within programmes. Several of our implementing partners and also importantly other donors appreciate the importance of developing the evidence base around demonstrating the cost effectiveness of their interventions and operations. / The table below details VFM indicators to be measured for the SSP programme / Economy Efficiency Effectiveness / Cost of consultants / Cost of fuel/transport / Cost of security for implementing agencies Speed of disbursement of fund / # legitimate local administrations established / # regional peace settlements negotiated / # people benefitting from initiatives completed from agreed community development plans # stable districts / # residents who feel safe in targeted areas / # districts where businesses operate after dark
Summary value for money statement for the preferred option / Given the lack of information linking results with resources that is available from stability activities in Somalia it is difficult to state clearly what the resources will achieve. However, cost analysis suggests that from an efficiency basis, with an estimated average cost per beneficiary reached of £3.09, the fund will impact positively on a large number of people at an acceptable cost. The effectiveness of the fund will derive from factors such as: (i) speed of implementation, (ii) the appropriateness and quality of interventions, (iii) responsiveness to changing situations on the ground and (iv) the coordination of effort and resources from a significant number of influential donors. The investment fund guidelines and fund management arrangements will seek to maximise these factors. / A better understanding of the cost drivers behind stability-oriented activities in Somalia and of the cost effectiveness of different interventions in achieving their intended results is a high priority. There are significant challenges to narrowing this gap in evidence, but DFID will use its influence in the Stability Fund management to ensure intervention level proposals and reporting as well as strategic portfolio management places higher priority on understanding the value for money of stability interventions.
[16] See Somalia Stability Fund document for donors for full details of governance structures & decision-making processes; criteria for eligibility & evaluation of proposals & partners and M&E processes
[17] A governance analysis of a number of districts in Gedo has been carried out by Pact, we have commissioned political economy analyses of Mogadishu and Beletweyne by DRC, and Saferworld has provided an initial assessment of Baidoa. During the first phase of fund disbursal (“rapid disbursement”) we will continue to ask partners to develop their and our basis of knowledge, particularly in areas with limited access and high fragility. Proposals are being submitted from International Alert and Saferworld to provide on-going analysis.
[18] For more detail on the lessons learned from this fund, refer to Annex IV.
[19] Interpeace/Dr Pat Johnson, "The search for peace: Lessons from Somali-led peace processes 1991-2007" in “Making the difference? What works in response to crises and security threats – the debate continues”, European Commission Directorate-General for External Relations, Editor: Andrea Ricci, 2009, pp. 257-262.
[20] For instance International Crisis Group. “Somalia: The Transitional Government on Life Support” Africa Report No 170, 21 February 2011 (http://www.crisisgroup.org/en/regions/africa/horn-of-africa/somalia/170-somalia-the-transitional-government-on-life-support.aspx).
[21] For instance a UN assessment of the Youth at Risk programme found that 44% of conflict was caused at the local level (inter-group) over scarce resources and control of those resources.
[22] World Development Report 2011: Conflict, security and development; World Bank, Washington DC
[23] DFID Somalia; Operational Plan 2011-2015; May 2011 and Bari, Shamsul, “Report of the independent expert on the situation of human rights in Somalia”; Human Rights Council (Eighteenth session, Agenda item 10, Technical assistance and capacity–building); UN General Assembly 29th August 2011.
[24] Kathryn H. Floyd; Somalia’s Stability and Security Situation in Review; International Centre for Political Violence and Terrorism Research; July 2010
[25] “Between protracted and crisis displacement Policy responses to Somali displacement”, Workshop report, 7 November 2011, Nairobi; Refugee Studies Centre, Oxford Department of International Development, University of Oxford
[26] FSNAU; Quarterly Brief - Outcome of Jilaal Dry Season (Jan-Mar '12); 23rd April 2012
[27] Norris and Bruton, “Twenty Years of Collapse and Counting: The Cost of Failure in Somalia”, Center for American Progress, Sept 2011
[28] Peace Dividends here are community structures managed jointly by warring communities, clans or villages

# Commercial Case

The procurement/commercial requirements for intervention / The SSP involves multiple interventions and funding typesas well as the procurement of discrete technical assistance inputs.Implementing partners to the Fund will undertake procurement of goods and services, but where they lack capacity, the Fund Manager will take up the role of procurement. The Fund Manager will be procured through an OJEU tender. Bilateral interventions will use competitive tendering, procurement through Framework Agreements, Memoranda of Understanding and Accountable Grants. / The programme will require partners to work in insecure, highly fragile areas with limited access.Suppliers, whether private sector companies, multilateral institutions, NGOs or consortia of organisations, will be required to demonstrate that they are ableto meet the requisite duty of care to their staff in these environments. / Procurement planning on a project-by-project basis will be required. The design phase and its pilot projects will assist in developing improved knowledge to inform procurement approaches, and developsafeguards to mitigate the risks of doing harm(see below on risks). / The Fund’s full OJEU tender will open to private sector companies, multilateral institutions, NGOs or a consortium of organisations. The FM will manage and deliver the programme through local, national and multilateral partners who meet set criteria (on technical capability and financial controls) – it will be responsible for contracting of implementing partners. The FM’s work will be overseen by anSecretariat Officewith delegated authority to approve expenditure (see below, under Management Case, for further detail). / The UK’s bilateralinterventions will include both direct and indirect procurement by DFID Somalia. The exact division of disbursement between direct and indirect procurement is not yet known. However, it is probable that it will be weighted toward indirect procurement, with DFID providing funding to third party organisations. Indirect procurement will be by Memoranda of Understanding with UN and multilateral agencies, and grant arrangements with INGOs. Value for money will feature prominently in the case-by-case assessment of potential partners (see below). DFID Framework providers will also be used.
How the intervention design uses competition to drive commercial advantage for DFID / The supply base for the SSP will be tested by the SSF and by DFID Somalia in its bilateral interventionsthrough competitive procurement to the maximum extent possible. We will be seeking to expand a supply base that is able to work in geographical areas that are emerging from conflict,and which are characterised by extreme insecurity. / The SSP pilot projects will inform the modalities of implementation, including providing insights on how to best use competition in delivering in the more fragile areas of Somalia. The SSP has also taken account of DFID Somalia’s investment in 2011 and means to achieve value for money in humanitarian programmes in Somalia (see below).
How we expect the market place will respond to this opportunity / Interest in bidding for the role of Fund Manager is high and is expected to include generalist private sector companies such as KPMG, governance sector oriented private sector companies such as GRM International, consortia of smaller private sector companies and NGOs with complementary skill sets, and multilateral organisations. / The market for partners with proposals to the Fund islikely to be, at the outset, limited giventhe operating environment and the requirements of a supplier to demonstrate viability. The market may also be limited by the nature of the wider intervention – combining security, development, and political interventions. Some suppliers may consider engagement in political processes to compromise their impartiality, making their staff more insecure. The Fund’s tiered entry levels and mechanisms to build the capacity of its partners will lead to a broadening of the market. While delivery partners remain limited, there may be a trade-off across DFID’s areas of support. Consultation within DFID Somalia will seek to minimise this, although the nature of a multi-donor trust fund’s decision-making process may limit our influence.
Key cost elements that affect overall price / Somalia’s operating environment generates unavoidable cost differentials,with some areas easier to operate in due to functioning markets and supply routes and others in severe conflict experiencing higher operating costs. Levels of stability in a given location will be a significant element affecting overall price. The ratio of administrative to implementation costs may be high to accommodate security needs. / Factors that could have a major impact on costs include: / i) The costs of security; / ii) The costs of logistics, access and transport;and / iii) Securing the appropriate skill set for technical assistance. / The 2011 analysis on value for money in humanitarian assistance found that before and after unit costs can differ dramatically where planning assumptions turn out to be far from what is possible. These findings are likely to be applicable to the SSP programme whose operating environment is likely to remain unpredictable.
Intended procurement process to support contract award / For direct procurement of bilateral interventionswhere the contract value is under the OJEU threshold, local competitive tenders will be issued by DFID Somalia. When above the OJEU threshold, a pre-approved DFID Framework provider will be engaged, or a full OJEU process undertaken. Competitive bidding will test the market for supplierswherever possible, meeting all HMGrequired standards as well as the operational criteria required under theprogramme. DFID Somalia will liaise with and take advice from Procurement Group as the programme is implemented. / SSF. The contributing donors are seeking a FMas quickly as possible. On the basis that the window of opportunity to support improved stability in Somalia could close,and the UK is committed to operationalising the Fund quickly, mini-competition within DFID’s existing framework providers is being considered. This will also factor in whether multilateral organisations can bid within such a process. The UN’s Multi-Partner Trust Fund Office has put itself forward as a potential FM, however our analysis (see Management Case) suggests that we have insufficient information to select the UN as FM outside of a competitive process.If not a competition within the Framework is not feasible, a full OJEU process will be initiated.
How contract & supplier performance will be managed through the life of the intervention / Where possible, the Fund will use results-based payments with contracts or grants published on-line on its website. This will include detail on the procurement method and the value of the awarded contract or grant. Contracts and grants will detail deliverables against timeframes set out in accompanying implementation plans. / The FM will deploy staff to monitor interventions, provide accurate and timely narrative and financial reports, and manage risks. Partners engaged outside of the SSF will provide quarterly reports on performance against implementation plans and advance quarterly forecasting. / The monitoring &evaluation plan (see below) includes an annual ‘process evaluation’ to determine whether the programme is being operationalised as planned. This will include review of contract and supplier performance. For the Fund, the ‘process evaluation’ will take account of internal auditors’, reporting on compliance to the SB. The M&E function will also be supported by DFID-S Monitoring and Evaluation Programme, being designed in parallel to this programme.

Indirect procurement / Why the proposed funding mechanism/form of arrangement is right for this intervention / The Strategic Casehighlights the various international and regional plans under preparation. The Fund will bring coherence to international assistance in challenging circumstances and, in doing so,will deliver savings for DFID. It will provide a mechanism for co-ordination and strategic dialogue, whileraising the standards of accountability and transparency. / The Appraisal Case sets out the need for DFID to retain the ability to respond bilaterally to politically sensitive interventions which deliver across HMG’s Somalia strategy.
Value for money through procurement / Information on procurement policies, capacities and systems will be placed in an addendum to this Business Case on QUEST when full design of the intervention is concluded and suppliers identified. / Consideration will be given to the additional value of a breakdown of supplier project costs against implementation milestones. This will provide insights into thoseproject costs required to deliver outcomes but which are amenable to find greater efficiencies. It will also provide comparable data and information that can be used to negotiate costs across suppliers. / Lessons have been learnt from DFID support tosimilarinitiatives, notably in monitoring the FM to continuously seek value for money. The value for money indicators and processesrequired in bilateral interventions will be consistent with those required of the FM. / DFID Somalia will continue to use its wider programme commitments with suppliers to leverage savings in overheads and HQ administrative costs. We recognise this as a legitimate cost and that parameters are negotiated by DFID centrally with UN agencies. But, where discretion is allowed, we will negotiate down costs. We will also look for consistency across suppliers. For example, if one UN agency proposes to charge 5% and another 7% for administrative costs, we will seek 5% on the basis of being like suppliers. We will take advice from FCPD, UNCD and Procurement Group in these negotiations. / Due diligence assessments of partners will include an assessment of their procurement procedures. Standardisation of common costs – for example, per diems, external travel – will also be sought.

# Financial Case

Costs, how are they profiled, and how we will ensure accurate forecasting / The programme costs for this intervention are £30 million over financial years 2012/2013– 2014/2015. Adequate funding is available. An allocation of £30 million is affordable and has been planned for under DFID Somalia’s governance Bilateral Aid Review allocation. / The Secretary of State announced a minimum commitment of £15m to the SSF;design work indicates that this should be increased to up to £27m. The allocation to theSSFby financial year is outlined in the table of commitments below (in USD). It should be noted that to allow the Fund to operate on calendar years, the UK’s allocations for both 12/13 and 13/14 are merged. / Donor Year 1 / Sep – Dec 2012 / 2013 Year 2 / 2014 Year 3 / 2015 Total million USD / UAE 0.3 0.8 0.9 2 / Netherlands* 1.33 0.66 0.66 2.65 / Norway 0.3 0.8 0.9 2 / Denmark 0.3 0.8 0.9 2 / UK** 15.4 13 14.5 42.9 / Grand Total 17.63 16.06 17.86 51.55 / *Contribution in EUR€ - €1 = $1.32 / ** Contribution in GBP£ - £1 = $1.62 / At the outset the burden share is weighted towards the UK. As new donors enter the Fund, this will shift, but until then the SB’s constitution (with the UK as the Chair of a troika of donor (chair), civil society representative,and government representative) will ensure that our greater burden share translates into greater decision making authority. The remainder of the UK’s £30 million allocation for this UK budget allocation period (approximately £3m) will be programmed bilaterally by DFID in this programme over the three years to 2014/2015. The cost breakdown by project for the bilateral commitmentswill be determined during a 12 month inception phase (from September 2012). However, the allocation profile of the bilateral commitments is expected to be distributed evenly over the programme period. / The budget for monitoring and evaluation of the programme is accommodated within the £30 million allocation, as is the cost of a programme-funded A1 Team Leader for the Secretariat Office. In the SSF component, other donors’ contributions will also contribute to monitoring and evaluation costs. The programme will benefit from results monitoring by DFID Somalia’s complementary governance Monitoring and Evaluation programme.
How it be funded: capital/programme/admin / All interventions will be funded from the programme budget. The resource requirements for the SSF are set out in the table above. Resource requirements for the bilateralcommitments on an annual basis will be established by Quarter 3 of financial year 2012/2013, and feature in DFID Somalia forecasting. The A1 DFID Team Leader will be funded from the UK’s allocation as a Programme Funded Post (see Management Case). / The funding pipeline for this programme does not invoke contingent liability. / How funds will be paid out / Contributions to the SSF will be made on a quarterly basis against an outline budget agreed by the SB. / Funds will be disbursed against agreed MoUs with multilateral agencies, consultancy service contracts for technical assistance and Fund management, and accountable grant arrangements for NGOs. Release of programme funds will be on a quarterly basis on partners demonstrating achievement of defined results as per individual implementation plans (and showing prior disbursements having been utilised).
Assessment of financial risk and fraud / Somalia’s operating environment presents financial risks, and the risk of fraud and misappropriation of aid. Somalia is perceived as the most corrupt country in the world (Transparency International Corruption Perceptions Index). Its low levels of stabilitymean criminal enterprise and militias target aid – as they do other resources of value. Financial risks include the inflation of contract values (arrived at as a result of menaces or for corrupt gain), contracts for local goods and services that are not fulfilled, or contracts that are given out on a basis other than their competitiveness (due to threats and menaces or cronyism or clan allegiance) will require robust management. / Development and humanitarian agencies exposed to the financial fraud risks of working in Somalia have developed systems to manage these risks. However,on-going assurances as to therobustness of these systems are required. Risk mitigation measures are set out below.Additionally DFID Somalia is recruiting an anti-corruption advisor who will oversee internal and partner risk management, lead on the development of an anti-corruption strategy and work with anti-corruption institutions. The National Audit Office will be visiting DFID Somalia later in 2012 and lessons drawn from this visit will be integrated into the programme.
Monitoring, reporting, and accounting for expenditure / Funds disbursed to implementing partners will be subject to internal and external financial audit measures. These will be detailed in the contracts, MoUs and grant arrangements. Due diligence, also encompassing duty of care measures for staff and financial audit, will be conducted on partners’ systems. / DFID Somalia is rigorous in its scrutiny of partners’ financial reporting and will act swiftly in suspending funding and embarking on investigations in the event of identifying any financial malpractice, suspicious transactions, or discrepancies in financial reporting. DFID Somalia will also utilise,where appropriate, unannounced independent third party monitoring (random checks) of partner expenditure. Partners will be required to respond swiftly to any findings. / The SSFdesign document (attached at Annex III) sets out three pillars for monitoring, reporting and accounting for expenditure and sound programme progress. Pillar 1 – Auditors – to be appointed early, and provide a check and balance on the activities of the FM. Internal auditors will report to the SB (see below under Management Case for respective roles and responsibilities) with a focus on business processes and compliance. External auditors will provide opinion on financial statements and their findings will be published on the Fund web-site. Pillar 2 – Third party monitors. Pillar 3 – Recipient contact – engagement with beneficiary communities to ensure participation and appropriateness of projects and interventions. / Assets procured under the programme will be registered and decisions on their transfer of ownership or sale will be made on a case-by-case basis informed by the utility of the asset to the sustainability of the intervention and their potential resale value.

# Management Case

What are the management arrangements for implementing the intervention? / SSP delivery will be overseen by the Governance & Peacebuilding Team in DFID Somalia. An interim fund management mechanism (while the FM is contracted), to be managed by DFID Somalia and other donors (DFID Somalia has an Interim Stability Fund Manager in place), is under design. Options include financial and fiduciary management by Crown Agent Financial Services or a mini-tender within the Framework Agreement for financial management of the Fund. Whether a procurement process that is faster than a full OJEU process is permitted will inform this decision. Donors have indicated that, prior to contracting the FM, they prefer to pass their funds to DFID (or our nominee) to be managed as a common fund. / The timeline above lays out significant steps in setting up the SSF. We expect in September to receive approval of UK funds, launch the tender (either OJEU or mini-competition), and approve an initial round of rapid disbursal projects. In October we anticipate setting up an interim pooled funding mechanism for the rapid disbursal funds, and approving a second tranche of rapid disbursal projects. The first SB meeting should be held in late November/early December to start setting strategy. In late January we anticipate the first set of results through quarterly reports from the rapid disbursal projects. In late February we expect quarterly reports from the second round of rapid disbursal projects, and also that the FM and SO will be in place if a mini-competition is the selected route. If we undergo an OJEU process we expect the FM and SO to be in place for end May. / SSF: A DFID A1 staff member will be posted as Team Leader of the Fund’s Secretariat Office. They will represent DFID interests in Fund commitments, ensure sound management by the FM, and retain day-to-day responsibility for work with other donors. The Team Leader will report to DFID Somalia’s Senior Governance Adviser (Team Leader – Governance & Peacebuilding). The costs for this post will be met fully from the programme on the basis that 80% of their work will be for the benefit of other partners. This post is principally a resource for the delivery of the SSF, a multi-donor programme; however the postholder’s role will also include input and liaison on DFID bilateral interventions under the SSP. / The proposed management structure for the Fund is as follows: / A Steering Boardwhich meets every six months and takes advice from the SO to set the strategic framework and the priorities for the Fund. They will have oversight of expenditure, review implementation, and results, but will not engage in the day-to-day decision making. Membership will be set at maximum of 15 and include senior representatives from donors, multilateral representatives, Somali Governments, INGOs, Somali civil society, and the private sector. The Chair will be held on a rotating basis with the UK holding the Chair for the first year. / A Secretariat Office: Staffedby representatives with delegated authority from donors contributing to the Fund (either staff or long-term consultants). The SO will advise the SB on overall strategic direction but be delegated to take regular management decisions within the framework agreed by the Board. The SO will have oversight of the FM and ensure coherence with other interventions, as well as the auditors, third party monitors, and beneficiaries. / A Fund Manager: A competitively sourced FM will be responsible for the daily administration of Fund interventions. The FM will establish a project office alongside the SO and have day-to-day oversight of implementing partners, providing accurate and timely narrative and financial reports. / Bilateral interventions under the programme will be managed by appointed DFID-S lead Advisers. The Governance & Peacebuilding programme management team will have administrative responsibility, including incident monitoring and reporting against the risks set out below, ensuring timely progress and financial reporting, and engaging financial and due diligence controls. Lead Advisers will have responsibility for ensuring cross-HMG liaison and wider co-ordination on commitments. / More detailed operational governance of the Fund is covered in the design document (Annex III) and its background documents (Annex IV). / Beneficiaries’ views, both civil society and governmental, on the governance of the intervention have been canvased through consultations in early 2012. They will continue through the pilot projects and through consultation during monitoring and evaluation. The Fund’s governance structure reflects lessons learned from similar funds and best practice to achieve the expected results. / Exit strategy / transition plan / DFID Somalia’s Governance and Peacebuilding Team and other contributing donors to the SSF will need to arrive carefully at the triggers and circumstances that might indicate a need to close the fund, end certain interventions in certain locations, or to extend the Fund to allow 3 year proposals to be funded from 2013 onwards. These triggers will include whether the interventions cease to represent reasonable value for money as well as whether results outlined in implementation plans fail to be achieved. DFID Somalia’s bilateral interventions will be subject to a similar review on exit options, these reviews will be determined by the specific project intervention and its implementation timetable. / Monitoring and evaluation will inform and guide thinking on exit and transition. Annual ‘process’ evaluations are planned which will provide insights into whether the Fund is actually working as intended. / Sept 2012 – May 2013 / May / Apr / Mar / Feb / Jan / Dec / Nov / Oct / Sept / Rapid disbursals approved / Q1 Reports received / Q1 Reports received / Rapid disbursals approved / 1st SB meeting / UK funds approved / Interim pooled fund set up / FM/SO in place / Option 1: Mini competition launched and completed / FM/SO in place / Option 2: OJEU launched and completed
Risks and how they will be managed / Risks and their management have been subject to significant early work in the design of this programme. The table below outlines the risks identified and gives a probability rating and impact rating (1 = low, 3= high). / Risk overview: External assistance to Somalia is often perceived as ‘interfering’ and serving external rather than Somali interests. This perception can fuel conflict anddo harm. Research on the causes of conflict in Somalia found the UN, despite having many years of presence in Somalia delivering assistance, was seen as representing western interests.[29] This has been taken account of by maximising a sense of local ownership and reducing the UK’s and other donors’ imprint at the sites of intervention. / The UN’s (Somalia) Risk Management Unit is helping to reduce financial risk across UN agencies by providing advice on the performance and background of potential local partners. Its advisory resources are also available to INGOs. / HMG Overseas Security & Justice Assistance (OSJA) Guidelines / This is not a discrete security and justice sector programme. However, it is planned to support initiatives that build local security. These will be pursued in tandem with interventions to deliver other community development needs, and work on improving political legitimacy and building local administrations. / The FCO Human Rights Report 2011 notes that the human rights record in Somalia remains poor and unlikely to improve significantly in 2012. Women’s rights in particular are not respected and domestic and sexual violence remain widespread, children remain at risk of recruitment by armed groups, and minority groups continue to face persecution. / The SSP will deliver a range of interventions: development projects meeting immediate local needs - including small scale livelihoods opportunities; support to enhance the legitimacy of local administrations; support to cross-border peace-building (Kenya and Ethiopia); support to inclusivepeace settlements; small-scale counter-piracy initiatives, and initiatives contributing to counter terrorism and community security. The SSP may therefore engage with border guards, local security units and others whose roles place them in a position to protect, and potentially violate, human rights and international humanitarian law. / Geographical areas of focus under the SSP do include areas where anti-insurgent/anti-extremist forces have been documented to have carried out human rights abuses. Insecurity, fragility and low levels of stability and accountability in many of the possible target sites mean risks to the violation of human rights or international humanitarian law (IHL) remains. Any interventions at these sites will expressly seek to assist in the adherence to human rights norms, in building systems and protocols or in the provision of any training. A positive impact on the human rights landscape is anticipated. / Interventions under the SSP that hold risks of a potential violation of human rights and international humanitarian law will be subject, on a case by case basis, to the OSJA Assessment and Approvals Process taking advice from FCO colleagues covering human rights. Until site specific interventions have been selected it is not possible to provide a more detailed risk assessment in relation to human rights and IHL. / Table: Risks and Mitigation / (Probability and Impact - 1= low: 3 = high) / Risk Prob-ability Impact Mitigation / Fiduciary risk through: inadequate financial controls leading to loss of funds and assets. 2 3 - Robust and strict controls in place from the outset guiding the handling of cash and the number of cash transactions. The movement of cash will be kept to a minimum. Reduction in opportunities for corruption to be complemented by transparent and accountable processes. Regular reporting to mitigate and help identify contract period facilitation payments. Clear procurement rules and robust complaints mechanisms in place. / Negative impact of aid and effectiveness through: / mismanagement of expectations; limited funding timeframes; creation of perverse incentives and aid dependency; lack of linkage with DFID and other interventions 2 3 - Continued consultation with wide range of stakeholders and prospective partners and with beneficiary recipients in affected populations in the development and implementation of interventions in design and then in on-going progress monitoring. / - Project specific appraisal will consider reasonable timeframes to mitigate risk of insufficient programme period that risk undermining aid effectiveness. Where appropriate, multi-year funding will be considered. / - Design stage will arrive at agreed standards (salary rates, per diems and similar) in order to mitigate some of these risks. Procurement systems will ensure local market rates are adhered to and, to the extent possible, not distorted by aid in-flows. Funding will not ‘lead’ consultation with target beneficiary communities – needs will. Exit strategies (see above) will be arrived, mitigating aid dependency. / - DFID staff will remain engaged in all relevant co-ordination forums. The DFID staffer in the SSF will retain a co-ordination function. DFID Somalia monitoring plans will look to include indicators on co-ordination and inter-programme linkages and coherence. / Partner risks through: competition for resources; use of non-traditional partners; implementing partners with limited capacity and/or credibility. 1 3 - Consistent processes applied to encourage healthy competition. The resources of the Fund will be managed to provide an enabling and inclusive arena - encouraging and supporting collaboration and coordination. / - Opportunities to expand the reach of the fund using non-traditional partners will be carefully considered. / - Mapping of the presence and capabilities of existing and potential partners, including non-traditional implementing partners. Actively encourage new partners to engage with existing partners. / Social and political risks through: insufficient contextual awareness and understanding with an inability to respond to the changing context; lack of due diligence; lack of access to intervention sites; Doing Harm; conflict 2 3 - Understanding the political economy of sites of intervention are prioritised exercises. These will be revisited and updated quarterly in the course of the intervention. Routine, area specific, assessments of political, security environment changes, drawing on geographical conflict appraisals, partner analysis, HMG, UN risk management, AMISOM and other pertinent reporting. / - Due diligence undertaken (to high standard) and findings triangulated to the extent possible with other partners and information sources. Phased approach to interventions will allow enhanced information base for in-depth due diligence. / - Partners will have experienced Somalia staff and security advisers – allowing access constraints to be understood, and to the extent possible without breaching duty of care, overcome. / - Mitigated by a variety of measures – credible partners, an incremental approach, accompanied by DFID and partner political economy, site and intervention specific appraisal, with appraisal of doing no harm featuring in monitoring and evaluation. / - Early decision will be taken to suspend or wind-down programmes. Situation monitoring and appraisal will provide early warning indicators of potential resumption of conflict. / Monitoring & Evaluation risks through: inability to measure impact 1 3 - Pilot projects will contribute to baselines being established. SMART indicators arrived at in project design – no indicators, or inability to meaningfully measure progress will rule out a project intervention. A separate Monitoring and Evaluation programme is being designed to work across DFID-S governance and peacebuilding programmes.
Conditions that apply(for financial aid only) / Not applicable.
How progress and results will be monitored, measured and evaluated / This programme represents a new approach in collaboration among donor partners. Interest is high in understanding how the programme is implemented, assessing its impact and learning lessons. On this basis, the programme will be subject to theory-based evaluation – does it confirm or refute the theory of change for governance and peacebuilding in Somalia? – evaluation of the effectiveness of its implementation and on the efficiency/ value for money in its use of resources. These are set out below. / Baseline measurements / Baseline measurements and progress targets are, at present, approximated. These will be revised in the light of the pilot projects and confirmed within twelve months of commencement through a monitoring review. This review will also inform a decision on whether to extend the period of the SSF to enable multi-year funding commitments to be made beyond 2014. The exercise will draw on insights from the pilot projects to: / Conclude baselines and confirm how realistic progress indicators are (If found unrealistic and subject to change, a recommendation will be made on re-submitting the Business Case at the appropriate level of delegated authority); / Take stock on how to optimise SSP operational links with the DFID Somalia Governance and Peacebuilding Monitoring and Evaluation Programme, and other relevant monitoring frameworks; / Assess and make recommendations on data availability and the extent of monitoring challenges, particularly for interventions in hard-to-access areas; / Ensure indicators are disaggregated by gender to the degree possible; / Make recommendations on indicators to facilitate project comparison and the aggregation of resultsproduced across the SSP’s project portfolio – to be reflected in guidance for project partners’ monitoring and evaluation plans; / Arrive at the best methods to measure value for money on a costs by project basis across the portfolio of the SSP(with input from an external consultant); and / Frame criteria for project inclusion under mid and end term evaluation (for example on size, timeframe, level of intervention, geographical area and evaluability). / The review will be submitted in a report (of no more than 20 pages) and submitted to the Senior Governance Adviser. On agreement of its recommendations, it will be disseminated to partners. This Business Case, or a revised Business Case if a decision is taken to extend the programme to allow multi-year funding decisions beyond 2015, and the accompanying logframe, will be updated in light of the review. / Performance management and on-going monitoring / Effective monitoring is a big challenge in Somalia. Monitoring of the SSF will embrace a number of techniques, as appropriate to the project. These will include direct monitoring by partners, SSF staff and DFID, third party monitoring, perception surveying, and selective interviewing and focus group discussions. Annual reviews will be undertaken, with an independent evaluation at the end of Year 2 and at the end of the programme. / Details will be set out in the individual project’s monitoring plans. These will be informed by the review (above) specifically with respect to harmonised data and indicators across interventions (to the extent possible). The aggregation of results collected will be facilitated at quarterly intervals – the SSF will have responsibility for aggregating results data from Fund projects. The review (above) and the DFID Somalia Governance & Peacebuilding Monitoring and Evaluation Programme (under design) will determine how (and by who) the aggregation of results can be best met for the bilateral commitments under the SSP. / Annual reviews will be conducted in accordance with DFID requirements. / Independent review will be undertaken at two points in the three year period of the SSP, at the mid-term point and in a final evaluation. Evaluation will focus on three of the OECD/DAC evaluation criteria Relevance – Effectiveness – Efficiency (value for money) but will take account of other criteria as necessary. The evaluations will respond to any changes in DFID project completion reporting requirements. / Relevance - Theory-based evaluation will investigate and test the theory of change and the assumptions behind the SSP. The mid-term evaluation will focus more on the first two levels of interventions – community and inter-community. Informing the latter half of the SSP’s timeframe for implementation. The final end evaluation will focus across the levels of evaluation. / Effectiveness – The evaluations will measure progress, or lack of progress, toward meeting the programme aims in contributing to the delivery of outputs and outcome. The evaluations will also look at process - whether the SSP is functioning and operating as intended – for example in maximising linkages with other programmes and in operating flexibly and in the more fragile areas of Somalia. / Efficiency – The evaluations will take account of the review findings on best methods to measure value for money and assess the extent to which this is being affected. / Dissemination: The SSP will support partners to build in better results processes into their programmes. Lessons learnedand the sharing of practices that are viewed as working better will be shared across all partners – this will include lessons from DFID Somalia’s health, wealth creation, humanitarian and wider governance portfolio as well as other donor programmes. / Lack of access for DFID staff and many others due to security, weak but improving implementing partner capacity and lack of readily available sources of data about Somalia all increase the difficulty of reliable monitoring. DFID will visit to monitor programmes when possible. In addition however, the DFID Somalia Governance and Peacebuilding programme is currently developing an independent third-party monitoring system as part of the £6.5 m Monitoring and Evaluation Programme. If successfully implemented it will: / Independently verify results reported by implementing partners, including through field visits; / Improve the quality and availability of data about Somalia that are relevant to governance and peacebuilding interventions; / Build implementing partner capacity to develop and articulate theories of change for their interventions, and their ability to measure and determine progress against them; / Include the capacity to collect detailed data about Somalia - this capacity could be drawn upon for any additional data collection required for evaluation; and / Repeat and expand on the perceptions survey carried out in Somaliland in 2011. / The business case for this Monitoring and Evaluation Programme is being developed in parallel to this governance business case. / The logframe sets out the monitoring requirements for this programme. Each of the indicators in the logframe will be collected and verified in one of the following ways: / Implementing partners will collect and report the data, which will be independently verified by the third-party monitoring system (bullet 1 above); / The data will be collected directly by programmes funded through the Monitoring and Evaluation Programme (bullet 2 above); / Data will be provided by Somali authorities; and / Data will be public goods provided by other reliable, independent sources. / The logframe baselines and targets are not yet fully completed, however, it is anticipated that they will be completed within six months of the project start date to allow time for rigorous baseline assessments to be conducted. / This makes monitoring of the DFID Somalia Governance programme to a large extent reliable on approval timing and effective functioning of the Monitoring and Evaluation Programme. This is a risk for the CSF Programme. The two business case timelines are similar so timing is unlikely to be a problem, but if the risk of the M&E programme not happening or being ineffective materialises, and the monitoring and evaluation programme is unable to fulfil bullets 1 and 2 to the necessary extent, then we will consider contracting individual consultants to carry out a), and will switch to existing but much less satisfactory sources for b). / Each of the individual components under this programme will be required to have its own log frame and monitoring strategy, which will be supported by the Monitoring and Evaluation Programme (bullet 3 above). / As with monitoring, high quality evaluation is hugely challenging in Somalia. To our knowledge, there has never been a rigorous impact evaluation of a development intervention in Somalia. As set out below, we plan to change that by, for the first time in Somalia, conducting a randomised control trial of (at least) one of the projects under this programme. / As set out in the appraisal case, this entire programme is based on a broad theory of change. Furthermore, each of the individual projects under the programme has its own theory of change. For evaluation purposes, we consider it more feasible and more informative to look at the theories of change of the individual projects, rather than the theory of change of the entire, multi-faceted programme. / The DFID Somalia Evaluation Strategy includes a methodology for assessing the entire DFID Somalia programme to determine priorities for evaluation. Given the very limited capacity for evaluation in Somalia, and the very recent arrival of capacity for evaluation in DFID Somalia, at this stage we must be very selective about which elements of the programme we subject to evaluation. Under the SSP, we will conduct an impact evaluation of the Community Driven Development programme - which will be funded through this programme as well as through the DFID CSFP. / Community Driven Development (CDD) has been subject to randomised control trials in DR Congo (Tuungane), Afghanistan (National Solidarity Programme - NSP), Sierra Leone and Liberia. The results of these evaluations have been very mixed. / In DR Congo, the evaluation found: "on most measures we fail to find evidence that these positive experiences with the Tuungane intervention led to behavioural changes. In general, we found that for many local governance measures the outcomes were relatively strong in both control and treatment areas." / In Liberia: "Our evaluation finds powerful evidence that the programme was successful in increasing social cohesion, some evidence that it reinforced democratic political attitudes and increased confidence in local decision making procedures, but only weak evidence that material well‐being was positively affected. There is essentially no evidence of adverse effects." / In Sierra Leone, the evaluation concluded: "Community Driven Development in Sierra Leone is a practical approach to deliver small-scale local public goods in a way that is equitable, accountable, and low cost, but was not an effective agent of institutional or social change." / The Afghanistan evaluation is still on-going at the time of writing. / In partnership with DFID's Evidence into Action team we are conducting a review of these four evaluations, which aims to determine the reasons for these mixed findings - whether it was the intervention, the context or the evaluation that led to such varied and often disappointing results. We plan to draw lessons from this review, and incorporate them into the design of the Somalia CDD programme. We intend to re-hypothesise the expected impact of this programme in light of the evidence from elsewhere and subject it to similar rigorous evaluation to enhance the global evidence base as well as learn lessons for programming in Somalia. / The evaluation question for the CDD programme, and consequentially the evaluation design, are currently under development by a consortium of participating partners/ stakeholders with additional academic expertise. Broadly speaking however, we intend to ask an evaluation question along the lines of "Does CDD in Somalia improve governance, stability and the effectiveness of aid?", and we plan to use a randomised control trial, possibly including some variation in the details of the programme in different communities. We are also looking at how to link the evaluation to other aspects of the Governance programme - particularly the UN Joint Programme on Local Governance (JPLG) - and whether we can use similar approaches to the next phase of the DR Congo Tuungane evaluation so that findings can be compared across the two programmes. We may choose to use the Monitoring and Evaluation Programme to conduct the data collection for the evaluation (bullet 4 above). The evaluation design will be integrated into the programme and so the timing will be concurrent and the various partners are all interested in the evaluation and committed to learning from it. / While we will focus our efforts on evaluating the CDD programme at this stage, there are other elements of our theories of change of the Governance Programme which we would like to test via a rigorous and rounded impact evaluation that will include a genuine cost effectiveness dimension. These include policing, justice, and local governance. We will consider how to seek an answer to this within the next six months and aim to conduct an evaluation within the next two years.
[29] Wanjiku Nyambura, C. “The Multifarious Interlinked Causes of Conflict in Somalia and the Way Forward”; Journal of Language, Technology and Entrepreneurship in Africa; Vol. 3. No. 1 (2011)

LIST OF Annexes / Logframe / EconomicAppraisal / SomaliaStabilityFundDesign Document / Somalia Stability Fund Background and Supporting Documents / GeographicalAssessment / GAPPtheoryofchangediagram / SSPphasedapproachtocommunity-drivenengagementdiagram