Type of Review: Project Completion Review

Project Title: Education in DRC

Date started: 13/07/2012	Date review undertaken:

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The objective of UK support to the education sector was to reduce the costs of children attending schools thereby increasing the enrolment and completion rates. The original concept was for a two-phase project, where phase one would prepare the ground for the establishment of a £48 million World Bank (WB) trust fund which was also expected to be co-funded by Belgium. The ambition for a Trust Fund proved unworkable and DFID’s assistance was channelled bilaterally to a project with four key components: / Payment for school insurance (to SONAS) through government channels: / The intention was to finance one year’s insurance contributions, to the state insurance provider SONAS, to test out the possibilities of direct financing thus relieving parents of this (minor) element of annual school fees. This proved to be impossible as insufficient fiduciary safeguards could be guaranteed. / Long term educational specialist with the World Bank / DFID agreed to fully finance this recruitment through an Externally Funded Output (EFO) arrangement which was initially signed on April 8, 2009. This EFO was extended for one additional year to March 2012. The education specialist supported the development and finalization of the Education Ministry’s (EPSP) Sector Strategy and the subsequent Interim Education Plan (IEP). Both documents have provided the basis for guiding and implementing reform and developing national policies. This has led to significant improvements in donors coordinating their approaches and funding to achieve greater impact. / National Teacher Census and School Mapping (TCSM). / The TCSM component should have contributed to the project purpose of universal access to quality primary education by providing essential baseline data for the government and donors to reduce school fees, which are the main constraint to access to primary education. This started as a minor component and grew in cost and timeframe until it was the principal element of the DFID programme, in partnership with the GoDRC. The original budget of £1.5m was very much under-estimated; the increase to £7.5m was more realistic and the final budget of £12.3m was the result of more accurate and detailed work by DFID and the Belgian Technical Cooperation (CTB). Increases in budgets were due mainly to the huge logistical challenges involved in visiting every school and collecting valid data on every teacher in the country. The shared governance arrangements between CTB, DFID and the government were insufficient for a project of this size and complexity. It proved not only high risk, but operationally too challenging to implement and this component of the project was closed early. / National Study of Education Exclusion / The final component, for the education exclusion study, funded through an MOU with UNICEF, was added in 2011. The objective of the study was to provide analysis on why children in the DRC (aged 5-17), dropped out of school, were vulnerable to dropping out, or had limited learning achievements. A draft report has been completed and the findings are being discussed government and other donors. / Termination of the programme / The decision was taken by the DFID DRC Head of Office to terminate the Access to Primary Education Programme on 17th August 2011. The Teacher Census and School Mapping was closed early. Components 2 (education specialist to the World Bank) and 4 (the study of education exclusion with UNICEF) continued as planned.

What were the expected results?
The goal was for DRC to make progress towards MDGs 2 and 3 – universal primary education and gender parity in school attendance. / The purpose was to assist the Government of DRC to achieve increased access to quality primary education in DRC. At the outcome level, expected results were that fees charged for school attendance would be progressively reduced; the primary gross enrolment and completion rates and the ratio of girls to boys would increase. Progress has been made on all these indicators, as shown in the table below, but this cannot be directly attributed to DFID investment or activities. DFID leadership of the education donor group and co-leadership of the Education Sector Thematic group has been influential but many factors have contributed to progress and to the remaining challenges in the sector. / Purpose level indicators Results Comments / Fees charged for school attendance are progressively reduced during the life of the project. Achieved. Primary school fees have been progressively abolished from the 2010-11 school year, leaving only Class 6 being charged the largest fees by 2012-13 and only a few legal fees permitted for lower classes. Operational grants are reaching most schools and more teachers are receiving regular salaries. The education exclusion study shows that direct and indirect costs remain the largest barrier to access and equity. Fees are still charged unofficially and loopholes are exploited to fill the gaps between actual state funding and the needs and demands of schools and teachers. / Gross enrolment ratio (GER) increases from 64% to 75% (80% male, 70% female) Achieved but from a different baseline. Administrative data in the MEPSP Interim Education Plan gives 2010 GER as 90.8%, up from the 2006 figure of 83.4%. The GER figure is based on very old projections for age-related population figures and it is therefore not possible to calculate accurately until new census data is available. However, administrative data has become more consistent. There are a very high number of over-age children in the system and high levels of repetition so GER should be much higher than 100% for the goal of UPE (net enrolment). / Girls to boys ratio in primary schools increases from 85% to 95%. Not achieved. Administrative data in the MEPSP Interim Education Plan gives the ratio of girls to boys in primary school as 90% in 2011. The report of the Education Exclusion Study reveals in more detail than ever before how severely girls (especially rural girls from average or poor families) are disadvantaged. This information will be important to planning new and effective programmes to address their needs. / Primary school completion rates increase from 29% to 35%. Achieved but from a different baseline. Administrative data in the MEPSP Interim Education Plan gives a 2010 completion rate of 56.7% (48.6% for girls) and 62% for 2011, up from the 2006 figure of 49.6%. Completion rates are defined as enrolment in Class 6 for DRC administrative data and by UNESCO globally. Slow progress is being made but pass rates at the final examination (TENAFEP) and transition to lower secondary school are very low, indicating low quality of learning achievement.

What was the context in which UK support was provided?
The DRC is a fragile state with the threat of instability and armed conflict affecting the whole country - most acutely in the East. Most people are extremely poor and the country is at the bottom of the Human Development Index. / The Access to Primary Education project was approved just as the newly elected government was being formed in 2006. It was designed to support the new government’s declared reform intentions in the education sector and stated policy objective of free primary school education for all children. The project approach was based around the key objective of reducing school fees, to allow more children to enrol and attend school, by establishing central funding mechanisms progressively to replace the parents’ payments for operational costs and teacher salaries. Many challenges existed at the start of the project and most still exist despite some progress being made. / The government still needs to approximately double the education budget and to spend this in full to achieve the funding levels needed to effectively support education in DRC. Basic education in the DRC continues to attract less donor funding per capita than almost anywhere else in the world. The project was intended to catalyse sector coordination and joint financing through the set up a multi-donor trust fund (MDTF) with the World Bank. / However, insufficient political economy analysis was undertaken at the outset. The programme was based on assumptions that did not prove valid, particularly around the capacity and commitment of government and donor partners. While the government developed a reasonably strong national education strategy (by 2010) and a three year interim education plan (by end 2011), less progress was achieved on systemic reforms required to implement and monitor progress against these plans. Vested interests opposed to reform remain within the Education Ministry. Unless progress can be made to address this, it will continue to hamper improvements to education outcomes of Congolese children.

## Section A: Detailed Output Scoring

Output 1: Mechanism for co-financing established and functioning
Output 1: final score and performance description: / 1.1 Appropriate management structures for the World Bank education project developed to enable the participation of other key stakeholders / 1.2 Joint funding mechanisms established / 1.3 At least one development partner joins the World Bank and DFID in using similar funding channels
Final results: / Not achieved as originally envisaged. The World Bank education project (PARSE) has recently been extended for a year to 2013 in order to complete its slow disbursement but there remain no plans for other donors to participate, no joint funding mechanisms proved feasible and the expected third donor partner, Belgium, withdrew from the primary education sub-sector from 2009. There are no current plans for the World Bank to continue in the education sector for the next Country Assistance Strategy but the World Bank is the supervising entity for a possible $100 million grant (to be decided by end 2012) from the Global Partnership for Education (GPE, formerly FTI). / DFID staff have played leading roles in producing the knowledge, processes and policies that led to the preparation of the funding proposal for the GPE. If the proposal is successful and the government’s plans and budget are implemented, then DFID’s original objectives for this output will have been achieved in part but these cannot be directly attributed to funding from the project. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2: Payment system for teachers’ salaries (SECOPE) and school running cost functioning efficiently and equitably
Output 2: final score and performance description: / 2.1 Reform to education sector payment systems, as recommended by the PER process are carried out / 2.2 Comprehensive teachers census is carried out / 2.3 School mapping of all registered and unregistered primary schools completed, including members of classrooms, teachers and pupils
Final results: / 2.1 Mostly not achieved. The education specialist, who had taken part in the sector Public Expenditure Review (PER), provided considerable support to the development of analysis and plans for PFM reforms. Concrete achievements though have been largely limited to project management units rather than the state institutions. Considerable resistance remains to reform the body responsible for the payment of teacher salaries (SECOPE). / 2.2 and 2.3 Not achieved as the component was terminated. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Phase fee reduction strategy to implement GoDRC’s policy of Free Primary Education in place and implemented
Output 3: final score and performance description: / 3.1 Plan developed by GoDRC to manage the gradual incorporation of qualified unregistered teachers on to the official payroll / 3.2 Plan in place for the rationalisation of schools and the gradual registration of those unregistered / 3.3 Annual GoDRC decree concerning schools fees implemented at school level / 3.4 Mechanisms developed to allow beneficiaries and stakeholders to monitor and provide feedback on receipt of payments, reduction of fees and other reforms / 3.5 Communications strategy on school fees and school financing in place
Final results: Partly achieved but not directly attributable to DFID interventions. / 3.1 and 3.2 The MEPSP Interim Education Plan, completed in June 2012, shows progress already made and future plans to register qualified teachers on to the payroll and to register schools according to need. / 3.3 The capacity of central government to control and monitor the implementation of regulations abolishing some fees is still limited. However, the Ministry of Budget and the MEPSP have publicly stated that the government assumes responsibility for paying teachers and that parents’ contributions will be reduced. Studies show that parents are aware of policy on fee abolition and regulation but that they lack the power to enforce this in the face of vested interests. / 3.4 Several mechanisms for monitoring and feedback have been established within donor-funded projects. The IEP, and specifically new UNICEF programmes and the GPE proposal include the use of citizens’ report cards and satisfaction surveys. / 3.5 An effective communications strategy is in place and was part-funded earlier in the project by DFID through UNICEF. / Impact Weighting (%): 50% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results
This project failed to achieve its stated objectives. The project’s governance structure and management had a significant bearing on this (see lessons below). Many of the underpinning assumptions were actually significant risks and the project while technically logical in its focus failed to design an intervention that took adequate consideration of the incentives at play. Too much political will was assumed and while parts of government were supportive others stood to lose significantly if the project was to achieve its stated outputs. DFID has some responsibility to bear here – and we need to look in much greater depth at the political economy of the sectors we are working in if we are to achieve progress on reform orientated projects in fragile states.
1.1 Has the logframe been changed since the last review? N / The last annual review scored 5 and the decision was taken immediately to terminate the whole project as soon as possible. The early termination of the TCSM component with minimum further loss or expenditure was the priority, involving high political risks and delicate negotiations with government and other partners. Joint development of a new logical framework for the ending programme, which would have covered only the last year of the education specialist and the exclusion study which was already underway, would have been unproductive at that stage. / 1.2 Final Output score and description: C / The activities produced knowledge and understanding that is relevant for future work in the education sector and beyond: for example, for the new DFID education project, the Girls’ Education Challenge proposals, DFID DRC’s strategy for women and girls and PFM programmes. However, they did not meet the specific objectives for the project.
Direct feedback from beneficiaries / Not applicable.
1.4 Overall Outcome score and description: C / Phase One was intended to prepare for major and coordinated donor financing of the sector. The preparations were not completed because the assumptions behind the activities and mechanisms required for Phase Two were not met. Progress at the purpose level cannot be clearly attributed to DFID investments. / Impact and Sustainability / The knowledge and efforts involved during the life of the project have undoubtedly helped to lay the basis for overall progress in the sector. However, little impact can be directly attributed to DFID’s work on this project.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: N / The project was terminated early and therefore did not disburse the funds allocated to it. / 2.2 Key cost drivers / The key cost driver related to the teacher census component. The budget for this increased, for the reasons stated above, to a point where the likely return was insufficient for the proposed level of investment. For this reason the component was terminated early to safeguard taxpayers’ money. / 2.3 Was the project completed within the expected timescale: N / The project was terminated early as progress towards the expected outputs could not be guarenteed.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Not applicable / 3.2 Set out what plans are in place for an evaluation. / Not applicable.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? N / 4.2 Risk funds not used for purposes intended / Since DFID was not using government systems or transferring funds directly to government, these risks were low. / 4.3 Climate and Environment Impact / Not applicable.

5. Value for Money
5.1 Performance on VfM measures / VFM was poor as the objectives were not realised. However, UK taxpayers’ money was safeguarded by early termination of a project that was unable to achieve its stated objectives. The total budget for the TCSM component was £12.4m. The early closure safeguarded £9.5m of UK taxpayers’ money. CTB’s, final spend was £978,744. Negotiations reduced costs of CTB’s 3-month notice period by 28%. £1.9m of project assets were transferred to other DFID implementing partners. 79% of the assets went to existing DFID projects which were intending to procure similar goods thereby resulting in cost savings to those projects. / 5.2 Commercial Improvement and Value for Money / Not applicable / 5.3 Role of project partners / Costs were recovered from the implementing partner and operating charges reduced over the three month notice period. / 5.4 Did the project represent Value for Money: N / See above

6. Conditionality
6.1 Update on specific conditions / Not applicable.

7. Conclusions
Lessons learned for future programmes / The intervention’s logic was not sufficiently robust: Even if all the project’s outputs had been achieved the impact and outcome level statements could not have been attained. It is clear that progress in the education sector cannot be definitively attributed to DFID’s intervention and, therefore, that the causal linkages (input/output/outcome/impact) were not sufficiently developed. Phase 1 was in essence a preparatory phase for a multi-donor trust fund and the project’s ambitions should have been cast as such. / Project governance structures have a significant bearing on success – particularly if the project is reform orientated. Attempting to separate the technical from the policy engagement through two separately negotiated MoUs, one with government and the other with the implementing partner, fails to recognise the shared accountability for project delivery and the high degree of overlap between the technical and policy work. A partnership that attempts to outsource all policy engagement or dialogue with government to DFID with limited engagement from the implementing partner has a high risk of failure. / The political economy of the sector needs to be better understood. The drivers (and spoilers) of change needed to be more clearly identified and the approach designed accordingly. The project assumed to much will and capacity on the part of government. While high level political support existed vested interests within the administration stood to lose if the projects transformational objectives were to be achieved. / A greater level of realism is needed for the time required to achieve transformational change in the DRC context, which is much longer than in many other countries. The level of ambition needs to be appropriate to the length of the intervention. The project’s assumptions and risks needed to be more robustly managed given the potential barriers to success they pose in a reform orientated programme. / Recommendations for future work in the education sector / Focus on school level with links up to policy and plans. / Address both demand and supply side constraints to children’s educational achievement. / Build in real participation by beneficiaries, using an empowerment and accountability approach / Produce and use data, including rigorous impact evaluations / Focus on education outcomes / Build in strategic work, factoring in realistic capacity needs for DFID staff and partners in order to manage the programmes effectively and to keep informed and influential in the policy environment.

8. Review Process
The review was conducted by DFID staff members and includes the Internal Audit report on the early termination of the teachers’ census and school mapping component.