Type of Review: Annual Review

Project Title:PATH Meningitis Vaccine Project 2010-15

Date started:	2010
Date review undertaken:November 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is supporting a product development partnership, the Meningitis Vaccine Project (MVP) to develop a polyvalent Meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections not covered by existing vaccines. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovative technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries. DFID will provide £3,619,788 over 5 financial years (2010-2015) to this project.

What are the expected results?
The Meningitis Vaccine Project (MVP), based at PATH,is aiming to contribute to the elimination of meningitis as a public health problem in Sub-Saharan Africa. / The intended outcomes of the research are: / Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature, and that meets a target price of between £0.82 and £1.65 per dose. / Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity in partnership with Serum Institute of India Ltd.

What is the context in which UK support is provided?
There are research gaps into essential technologies such as vaccines and medicines to treat neglected diseases that affect the world’s poorest populations where there are no current products or where those that exist are either too expensive, difficult to access, no longer produced, highly-toxic or ineffective. / Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases alone in an area of sub-Saharan Africa known as the African meningitis belt, which stretches from Senegal to Ethiopia and has the largest burden of meningitis in the world. Meningitis kills one in ten people who are infected and leaving one-quarter of survivors severely debilitated. The number of cases of meningitis has dramatically reduced since the introduction of the Meningitis A vaccine in 2010, but this vaccine does not target all the disease-causing serotypes. New vaccines are required to prevent meningitis infections by these other serotypes.

## Section A: Detailed Output Scoring

Output 1:Development of an affordable, thermostable, polyvalent conjugate meningococcal vaccine that has a four-year shelf life at room temperature, and that meets a target price of between £0.82 and £1.65 per dose.
Output 1 score and performance description: A Outputs met expectation
Progress against expected results: / Strong progress throughout the year, with five achievements of note: / Good manufacturing practice (GMP) production of Group A, C, W, and Y meningococcal polysaccharides. / Group A, C, Y, and W monovalent conjugate vaccines prepared at laboratory scale. / Development of stability assays. / Development of antigen-specific quantitative assays. / Patent landscape analysis and product development strategy finalized. / The process being used to develop and stabilise the vaccine is the same as was used for the Meningitis A conjugate vaccine but there is no guarantee, as yet, that the procedure will be successful. To manage this risk appropriately MVP are using parallel stability procedures, performed at PATH and the Serum Institute of India Ltd (SIIL), following early discussions with WHO. / Recommendations: / MVP must report on about their progress on stabilising the polyvalent conjugate vaccine in the next reporting period / Impact Weighting (%):75% / Revised since last Annual Review? No / Risk: Low/Medium/HighHigh / Revised since last Annual Review? No

Output 2:Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrates vaccine safety and immunogenicity, at Serum Institute of India Ltd.
Output 2 score and performance description: A Outputs met expectation
Progress against expected results: / The Contract negotiations with SIIL have been concluded and a collaborative agreement between PATH and SIIL signed. During the negotiations period, SIIL conducted a full programme of work, with good progress. Monovalent conjugates have been prepared for Men A, C, Y and W and have been shown to be immunogenic in mice. A production process for the novel Men X polysaccharide has been determined and initial conjugates prepared for testing. Lead monovalent formulations have demonstrated excellent stability at temperatures as high as 45ºC. / Recommendations: / Impact Weighting (%):25% / Revised since last Annual Review? No / Risk: Low/Medium/High High / Revised since last Annual Review? No

## Section B: Results andValue for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A – Output met expectation / 1.3 Direct feedback from beneficiaries / Prior to DFID funding, the programme produced the MenAfriVac vaccine, for serotype A Meningitis. Following a vaccine campaign in Burkina Faso, Mali, and Niger these countries reported the lowest number of confirmed meningitis A cases ever recorded during an epidemic season. Because of the risk that that other serotypes of the meningitis bacterium will become more dominant, there is a demand from Governments, Ministries of Health and community leaders in the affected countries, for a new conjugate vaccine, being developed with DFID funding which will cover these other serotypes.
1.4 Summary of overall progress / MVP has made good progress over the reporting period and is on track to deliver the expected outcomes. This will be an important public health achievement if it can be delivered to the challenging timetable.
1.5 Key challenges / This is early stage science which has many technical challenges. But MVP is building on the successful development the MenAfriVac and they are able to expedite development using the lessons learned from their previous experience / A key leadership role changed during the year with the retiral of the head of the programme. A new Director, Mark Alderson, is now in place and the transition has been managed well. Staff morale remains high.
Annual Outcome Assessment A – Outcome met expectation / MVP has made good progress against the outcome, using its previous experience and building on lessons learned from development of the earlier vaccine. The other funding agency involved (Bill & Melinda Gates Foundation), who funded the development of MenAfriVac, but are not funding this aspect of the work, have expressed their satisfaction with the important progress being made.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The budgeting profile has changed to accommodate technical progress. / 2.2 Key cost drivers / Salaries and staff related costs, laboratory equipment and consumables are the key cost drivers. MVP is managing costs appropriately whilst they explore a range of technical solutions to stabilise the new vaccine. / Vaccine development is a costly process, especially in the latter stages of development. MVP has a partnership arrangement with SIIL, who provide cost effective approaches to development of new vaccines. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The most important development in the epidemiology of meningitis in the African meningitis belt has been the impressive success that has followed the introduction of the Meningitis Aconjugate vaccine. Wherever the vaccine has been introduced at scale (Burkina Faso, Mali,Niger, northern Cameroon, western Chad, and northern Nigeria) the results have been the same—a rapid disappearance of Group A meningococci as a cause of meningitis. / As a result of the success there is an increase in pressure to develop candidate vaccines for the other serotypes. Surveillance data in 2011 and 2012 show the presence of W135 and X meningococcal serotypes. Predictably, with the disappearance of Group A disease these serotypes have assumed more importance. / .3.2 Where an evaluation is planned what progress has been made? / There was an evaluation of the vaccine development programs at PATH, including MVP, funded by the Bill & Melinda Gates Foundation in 2010. The results of the evaluation were shared in late 2010 and responses initiated in 2011. The results of the evaluation were shared with donors, including DFID through the PDP Funders Group.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Product development is high risk and potential vaccine candidates can fail at any stage in the development process. PATH hosts a number of different vaccine development programmes, including MVP. The staff in PATH learn lessons across programmes and have developed much experience at managing these risks. They have taken approaches to ensure the successful completion of the new vaccines. / There is an established programme to roll out the MenAfriVac vaccine, so that once developed the new vaccine developed by MVP will have a clear implementation pathway.
Risk of funds not being used as intended / This is low risk. PATH have well established internal and external audit procedures. An external independent Financial Audit is performed annually to certify the availability of funds and assess adequacy of funds. Copies of the unqualified Audited Financial Statements for 2011 have been examined by DFID. / PATH has a strong a governance structure and robust practices. There were no recommendations associated with financial management in an external review commissioned by the Bill & Melinda Gates Foundation in 2010. / PATH has the right to review SIIL’s project-related data, records, etc. (including detail of all financial transactions). They have no concerns with SIIL’s financial management or performance on the project.SIIL provides semi-annual technical and financial reports to PATH. / Climate and Environment Risk / There are no significant environmental impacts of the vaccine development work at the current time. MVP works with regulators to ensure that environmental issues (associated, for example, with used product and packaging disposal) are appropriately addressed and/or studied as part of the development process, prior to the adoption of new vaccines. The WHO prequalification process for any new diagnostic involves an assessment of potential climate and environment risks. / The principal environmental impact of mass vaccination campaigns is that of waste disposal (needles, syringes, and vials). MVP funded an environmental assessment in Burkina Faso prior to introduction of the Men A conjugate vaccine, in part to develop a countrywide plan for waste disposal. The work, led by WHO has served as a model for waste management in other countries and for other products. / In the longer term the environmental impacts of a polyvalent meningitis vaccine should be positive with reduced inappropriate treatments of disease in poor populations contributing to more effective and efficient utilisation of drugs and associated health services.

5. Value for Money

Performance on VfM measures / Funding vaccine development through a product development partnership (PDP) such as the MVP provides value for money through: / the use of a portfolio approach which allows funding to be redistributed if individual projects are stopped if they do not meet their milestones; / the leveraging of contributions (resources, expertise, funding, access to drugs and other in-kind resources) from the private sector (in low, middle and high income countries); / support for the continued development of the most promising candidates; facilitating opportunities to explore innovative partnerships with private and public sector organisations (in many different countries including low and middle income countries) to reduce costs. / MVP further enhances its value for money through strong partnership working with other PDPs hosted in PATH and its partners as well as global partnerships (such as GAVI), policy-makers, influencers, operational researchers and programme staff on the ground – which can significantly increases the likelihood of vaccine uptake in endemic countries. / The staff at MVP are constantly looking for better technical solutions to develop vaccines and are able to share knowledge and expertise with other vaccine development colleagues. For example PATH colleagues are able to identify new solutions as existing commercial patents end and techniques become available. / 5.2 Commercial Improvement and Value for Money / Through its internal processes, with a focus on the development of new disease diagnostics from existing technology platforms, the programme is able to provide a competitive environment for innovation and improved value for money. In addition the organisation works with the a range of different industrial partners, which improves value for money, by leveraging in resources, staff time and expertise from other organisations / 5.3 Role of project partners / DFID is one of PATHs donors who are involved through regular discussions with the programme directly and through various international and WHO based fora. All donors are aware of the financial constraints and the need to identify ways to increase value for money. / Ensuring value for money in developing products for use in low income countries, where there is no viable commercial market, is central to the way PDPs work with their partners from a range of different backgrounds, including pharmaceutical companies, other private sector organisations, academic researchers, advocacy organisations and local community groups. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Overall MVP has made good progress over the 2011/12 period. The contract negotiations with SIIL took longer than predicted, but during this time the work continued and technical progress was good. / There have been some changes in management structures over the cause of the year, the impacts of which appear to have been managed smoothly. / Recommendations / MVP must report on about their progress on stabilising the polyvalent conjugate vaccine in the next reporting period

8. Review Process
The review was carried out by members of the human development research team in DFID, following review meetings and discussions with the programme, independent scientific experts and other funders. A member of the Product Development Partnership Funders Group was an independent member of the review team. / As the new Product Development Partnership Competition (for the period 2013-18) was launched in February 2012, there has been minimal contact with MVP and other staff at PATH, to minimise the risk of conflict of interest. All discussions with the programme have been limited to reviewing progress against the existing performance framework, risk, financial and programme management. However, a copy of this annual review was shared with them before submission. When the competition is complete, by end of 2012, further discussions will take place.