BUSINESS CASE

Intervention Summary

## Title: Agricultural Model Intercomparison and Improvement Project (AgMIP): Africa and South Asia Regional Components

What support will the UK provide?
How much funding does the UK expect to provide? DFID will provide £6.4m / Period of funding? 3 years (2011 – 2013),

Why is UK support required?
What need are we trying to address? / Climate change is expected to have a significant impact on agriculture, particularly in developing countries. Models help generate information on the type and magnitude of likely impacts. However, currently there are multiple crop and economic models providing divergent results on where impacts will be felt and the severity of these impacts, particularly for key developing country regions. This lack of consistent impact data reduces the ability of development partners and developing country governments to plan responses to the challenges of climate change in relation to agriculture and food security. It also reduces effective decision making on value for money adaptation finance allocations. / What will we do to tackle this problem? / DFID will fund the Sub-Saharan Africa and South Asia regional projects of a global initiative to improve crop and agricultural economic models to provide substantially improved assessments of climate impacts on the agricultural sector. The regional projects will improve the reliability and accessibility of assessments of impacts of climate change on agriculture in SUB-SAHARAN AFRICA and S.Asia and improved identification of potential adaptation strategies. / Who will be implementing the project? / The project will be implemented by a multinational group of experts in agricultural modelling, including from the UK and developing countries, led by a team from Columbia University, University of Florida and USDA-ARS (United States Department of Agriculture – Agricultural Research Service). DFID fund will support teams of specialists (including crop modellers, agricultural economists, climate scientists, and IT specialists) from Sub-Saharan Africa and S Asia, selected through an open, competitive proposal process / Are any other donors supporting this (or similar) projects(s)? / USDA is funding the core AgMIP team.

What are the expected results?
What will change as a result of our support? / Production of reliable and accessible assessments of impacts of climate change on agriculture and trade of agricultural products in Africa and South Asia and improved evidence on priority potential adaptation strategies to support efforts to improve food security and agricultural productivity. There will also be strengthened capacity in these regions to enable future assessments and analyses of impacts beyond this project. / What are the planned outputs of the project attributable to UK support? / Improved crop and agricultural trade models, with specific outputs for Sub-Saharan Africa and South Asia / Improved regional projections of climate change impacts on crop production, trade and associated economic implications and identification and prioritisation of agricultural adaptation strategies / Strengthened capacity of researchers in Sub-Saharan Africa and South Asia to access and use crop and economic models / Researchers and policy makers from both the private sector and government in Sub-Saharan Africa and South Asia better able to access improved and relevant information on regional climate change impacts on agriculture / How will we determine whether the expected results have been achieved? / We will determine whether expected results have been achieved through identifying where improved global and regional agricultural projections have been used in major regional reports and to inform investment decisions. We will also conduct an independent mid-term evaluation and require annual progress reports to ensure milestones and targets are met.

Business Case for:

Agricultural Model Intercomparison and Improvement Project (AgMIP): Africa and South Asia Regional Components

Strategic Case

A. Context and need for DFID intervention / Context / 1. Agriculture is one of the most vulnerable sectors to the impacts of climate change. This is due to both direct impacts on crop yields and indirect impacts such as changes in water availability. As a result, climate change will tend to reduce global agricultural production and intensify the risk of hunger and malnutrition[1]. The 4th Assessment of the IPCC confirmed that most of these impacts are likely to be felt in developing countries, where “even slight warming decreased yields in seasonally dry and low-latitude regions”[2]. / 2. This has significant implications for both food security and economic growth in many developing countries, where even with rapid urbanization; the majority of the poor are projected to continue to live in rural areas until 2040. Most depend on agriculture for their livelihoods, directly or indirectly[3]. Poor rural communities depend upon weather conditions for cultivation, so their capacity to manage climate-related risks is a high priority. There is an expanding evidence base underpinning the need for strengthened climate risk management and climate resilience in the face of increasing impacts of climate variability on economic performance and livelihoods of the poor[4]. Families could find themselves introducing changes in diet preferences and facing more malnutrition and exposure to infectious diseases. / 3. Negative impacts on agriculture in these areas are also likely to lead to impacts on growth and poverty reduction. Recent empirical evidence suggests that compared to growth from other sources, growth in agriculture generates welfare gains that are much stronger for the poorest parts of the population. Cross-country econometric work reported in the 2008 World Development Report[5] shows that a 1% gain in GDP originating in agriculture generates a 6 % increase in overall expenditures for the poorest 10% of the population. GDP growth originating in non-agriculture sectors generates zero growth for the poorest 10% of the population[6]. / 4. A critical area of knowledge required to enable developing countries to adapt their agriculture sector to climate change and to inform investment decisions is evidence of what potential impacts are likely to be and identification of appropriate adaptation options (see figure 1). The use of models enables identification of probable impacts to inform adaptation planning, as well as supporting advocacy and policy on adaptation investments[7]. They also offer a means of testing the impact of different adaptation and mitigation responses and prioritising critical areas for new research, for example novel crop types. / 5. There are three common modelling approaches used for assessing impacts of climate change on crops: Econometric (Ricardian), empirical relationships based on observations and assessments using process based crop models[8] / Econometric Empirical Process Based simulation / Description: Uses historical data to estimate a statistical relationship between some measure of economic value (e.g., value of crop land/ production) as a function of observed climate variables, and then simulates relationships with climate change using predictions of climate models[9]. Description: Uses statistical regression analyses between crop yields and climatic variables over observed historic time periods[10] Description: Models that consider the interactions between plant functional processes and abiotic factors, such as climate variables, carbon (C), and nitrogen (N) balance[11]. These can simulate possible climate impacts on crops and can be integrated with economic models to represent economic responses to changes in productivity[12]. / Pros/Cons: The method does not take into account price changes and other farm level factors such as availability of irrigation water, nor does it simulate any bio-physical process that are likely to be affected by climate change such as CO2 fertilisation[13] Pros/Cons: The advantage of this method is that it focuses on actual recorded yields to explore effects of climate variability. / Disadvantages are that many other factors contribute to yields in particular regions that obscure the impact of climate on crops. It is also unknown if historical relationships will hold under changing climate conditions. Current relationships between crop yields and climate are unable to take account of C02 effects on crop growth[14] Pros/Cons: Exploits the knowledge embedded in crop models to simulate possible climate impacts, including complex bio-physical responses and can be used to represent the effects of adaptations such as change in varieties. Integration with economic models allows prediction on food production that can contribute to assessment of impacts on hunger and poverty. / A potential disadvantage is that it is difficult for modellers to be able to represent all the bio-physical, economic or behavioural responses to climate change[15]. It is also very demanding in terms of computing resources. / Figure 1 Adaptation to Climate Change - Framework of areas of Knowledge needed / Evidence of need for intervention / 6. Current models of projected impacts on agriculture are of limited use as they are subject to a range of uncertainties and based upon a number of major assumptions that produce divergent results. For example, the “simulated responses of maize in Africa to a doubling of CO2 can be as broad as -98% to 16%, or as narrow as -14% to -12%”[16]. Table 1 illustrates the effect of uncertainties about variables such as the role of CO2 fertilisation on estimating impacts on hunger. A recent literature review of the area concluded that “the causes of historical and recent variability in food availability (specifically crop yield variability) are not well understood and evidence for the role of climate as a driver is patchy and poorly quantified”[17] / Table 1: Global-scale impacts of climate change by 2080.[18] / Climate and socio-economic scenario / A1FI A2 B1 B2 / Global temperature change (°C difference from the 1961-1990 period) 3.97 3.21 to 3.32 2.06 2.34 to 2.4 / Millions of people at increased risk of hunger (Parry et al., 2004); no CO2 effect 263 551 34 151 / Millions of people at increased risk of hunger (Parry et al., 2004); with maximum direct CO2 effect 28 -28 to -8 12 -12 to +5 / Millions of people exposed to increased water resources stress (Arnell, 2004) 1256 2583 to 3210 1135 1196 to 1535 / Additional numbers of people (millions) flooded in coastal floods each year, with lagged evolving protection (Nicholls, 2004) 7 29 2 16 / 7. There has not been a systematic setting of standards and protocols to compare agricultural impact models, as has happened in the global climate change models. While, integrated assessments using crop simulation models have tended to be the most common modelling approach used, there are differences between crop models and the extent to which they incorporate different climatic factors and quantify uncertainty, which can lead to divergent results. Some models don’t integrate key drivers that affect food security in developing countries, again limiting their usefulness [19]. There is scope for more poverty focus in crop modelling research. Assessment of agricultural systems can be enhanced through improved simulation models for locally important subsistence crops and varieties. Increasingly, testing and evaluation of models should consider the consequences for crop production on food systems most significant to the poor. / 8. The Inter governmental Panel on Climate Change (IPCC) has recognised and advocated for improvements in these integrated models: “Calls by the IPCC Third Assessment Report to enhance crop model inter-comparison studies have remained largely unheeded: Improvements and further evaluation of economic, trade and technical components within integrated assessment models are needed….[20]” / Why DFID’s intervention is justified and the difference intervening will make to reducing poverty / 9. Securing future agricultural productivity in African and South Asia in the face of the challenges of a changing climate is key to meeting development goals, including poverty reduction and food security. The empirical relationship between agriculture and poverty reduction is well established[21]. For example, in Africa, agricultural growth has been found to be four times more effective in increasing the incomes of the extreme poor than growth originating in other sectors[22]. A number of studies in Africa have emphasised the ‘multiplier’ effects of growth in agricultural incomes, with estimated income growth multipliers of between 1.5 and 3 across a number of African countries. This is a higher multiplier than in any other sector[23]. / 10. There is a key knowledge gap on the impact of climate change on agriculture and food security, particularly in developing countries. Improved models provide the major way to address this gap and improve the evidence base to support efforts to improve agricultural productivity and food security in the context of climate change. / 11. Improved knowledge in this area and capacity for ongoing impact analysis is crucial in developing countries. This is because of the high likelihood of negative impacts from climate change on agriculture in these regions and the importance of this sector for poverty reduction. Investments in adaptation strategies can also have various indirect effects on wages and food prices. Adaptive capacity can enhance greater access to locally traded goods and services[1], which has implications for household livelihoods. Better impact information is needed in order to direct investments in adaptation that improve poor household’s livelihoods. / 12. As set out by the IPCC, there is general consensus that the greatest negative impacts on agriculture resulting from climate change will occur in developing countries. Various studies have projected the potential impacts on poverty and hunger that could occur as a result. For example, one study shows that 65% of the global increase in climate-related hunger is projected to occur in Africa[24]. The World Development Report 2010 suggests that a warming of 2oC is projected to result in a 4-5 % permanent reduction in annual income per capita in Africa and South Asia, driven by agricultural impacts[25]. / 13. This intervention will lead to the production of more robust information on the likely impacts of climate change on agriculture in developing country regions. This will enable key decision makers in these regions to deliver better informed policies and investments to secure agricultural productivity in the face of climate change and make better decisions on adaptation. It will also support aid agencies and the international community to make more effective poverty reducing aid and adaptation investments in the agricultural sector in these regions. / 14. As well as substantially improving information on the impacts of climate change on food security and agriculture in Africa and South Asia to meet the challenges set out above, it is critical that model improvements are done in a way that addresses the specific needs of this region and results are accessed by decision makers that can use them to improve the lives of poor households whose livelihoods are affected by climate impacts. As models and data sets improve around the world, regional scientists and decision makers need to be a part of this to ensure they respond to national and regionally important policy questions and are validated for the specific regional context. Capacity needs to be built in these regions to allow ownership and access to use these tools over the long term. / 15. The ultimate beneficiaries of improved modelling are farmers and the food insecure in Africa and South Asia through the contribution models can make to identifying effective actions in response to climate shocks and trends and their impacts on food security. Modelling does not directly reach these beneficiaries but by targeting and involving key intermediaries, such as policy makers, agricultural planners and innovators, the evidence they generate can lead to improved development interventions. / Why DFID’s intervention is feasible and the consequences of not intervening / 16. DFID intervention is feasible as there is now a global initiative (AgMIP – The Agricultural Model Intercomparison and Improvement Project) that offers a robust platform to address the need set out above in key developing country regions. / 17. The AgMIP project has been developed since June 2008 as a global initiative, bringing together the leading crop and economic modellers. Input has been received from agricultural scientists from around the world including Latin America, Africa, and Asia, Europe, North America, and Australia. Project development also benefited from discussions following a presentation at the World Bank in May, 2009 and one in London with UK and European agricultural modellers early in 2009 as well. Regional members of the Steering Group have also contributed to the development of the capacity building aspects of the project. / 18. Its first workshop was held in October and attended by 75 participants representing the key crop and agricultural economic models, demonstrating the global buy in to the project. It is now at a point where the framework has been established and DFID investment can capitalise on this to support tailored projects for Africa and South Asia. / 19. DFID has a comparative advantage to support research in this area. We already support a number of research initiatives and partners that will benefit from and inform this programme: CGIAR CCAFS programme, CORAF, ASARECA, SAARP and Hadley CSRP. We are able to bring these links and experience of working on agriculture and climate change to the programme. / 20. If DFID chose not to intervene, there would be an increased risk of this global initiative failing to generate results relevant to those regions of Africa and South Asia, likely to be hardest hit by climate change. The leading researchers in this area tend to be from developed countries; our support will ensure that developing country scientists and policy makers are involved in this initiative and provided with the capacity to validate and generate results for their regions, both during and beyond the lifetime of AgMIP. / Links to any other HMG/DFID strategic priorities / 21. This project will contribute to the UK Government’s strategic poverty reduction priorities to combat climate change and boost wealth creation and the UK’s International Climate Change Strategy. It will provide improved information on impacts of climate change on agriculture and food security in Africa and South Asia to governments and actors in those regions. It will also provide evidence needed to support DFID’s broader research investment and commitments in this area; for example it will generate evidence on priority agriculture adaptation options for further research, responding to studies such as the recent Foresight study that identified the role of climate in market volatility.
B. Impact and Outcome / 22. The expected impact (Goal) of this project is an improved evidence base to support efforts to improve food security and agricultural productivity in Africa and South Asia. The expected outcome (Purpose) of this project is reliable and accessible assessment of impacts of climate change on agriculture in Sub-saharan Africa and S. Asia and improved evidence on priority potential adaptation strategies. / 23. As set out in section A and in the evidence review which we conducted to support our case[26], the use of models is a recognised method of generating evidence and conducting assessments of the impacts of climate change in agriculture. Integrated assessments are the most widely used methodology. There is now an established global network of the leading researchers in this area ready to respond to the necessary improvements called for by the IPCC and others in these models, making this impact and goal achievable. / 24. This global network (AgMIP) will improve and run comparisons of the different types of crop and economic models, likely including the Agriculture Ecological Zone methodology, used by FAO. Improved models will then be used to generate substantially improved information on climate change impacts on agriculture. While AgMIP will not be using the econometric or statistical regression methods directly, because of the dis-advantages described in section A, it will lead to better results from integrated approaches that can be used to make useful comparisons with results generated from these approaches.
[1] Parry et al, 2009: Climate Change and Hunger: Responding to the Challenge, World Food Programme
[2] Easterling et al, 2007: Food, Fibre and Forests Product chapter summary, IPCC 4th Annual report
[3] WDR 2008: Agriculture for Development
[4] World Bank Group (2009). Development and Climate Change.
[5] Ligon and Sadoulet, 2008 Background Paper for the World Development Report 2008-Estimating the Effects of Aggregate Agricultural Growth on the Distribution of Expenditures E Ligon, E Sadoulet - Washington DC, World Bank, 2007
[6] World Development Report 2008: Agriculture for Development
[7] Wilby and Desai, 2010: Robust Adaptation to Climate Change, Weather, Vol 65, No 7
[8] Conway 2010: Background note on Crop Modelling and Climate Change Research
[9] Antle et al 2010: Note on crop and economic Modelling Methods for Agricultural Climate Impact Assessment used in AgMIP
[10] ibid
[11] Fourcard et al, 2008: Plant Growth Modeling and Applications: The Increasing Importance of Plant Architecture in Growth Models, Annals of Botany vol 101
[12] Antle et al 2010: Note on Crop and Economic Modelling Methods for Agricultural Climate Impact Assessment used in AgMIP
[13] Conway 2010: Background note on Crop Modelling and Climate Change Research
[14] Antle et al 2010: Note on Crop and Economic Modelling Methods for Agricultural Climate Impact Assessment used in AgMIP
[15] ibid
[16] Challinor et al, 2009: Crops and climate change: Progress, trends, and challenges in simulating impacts and informing adaptation. Journal of Experimental Botany 60, 2775-2789.
[17] Conway 2010: Background note on Crop Modelling and Climate Change Research
[18] IPCC, 2007 Climate Change 2007: Working Group II: Impacts, Adaption and Vulnerability
[19] Conway 2010: Background note on Crop Modelling and Climate Change Research
[20] Easterling et al, 2007: Food, Fibre and Forests Product chapter summary, IPCC 4th Annual report
[21] World Development Report 2008: Agriculture for Development
[22] ibid
[23] ibid
[1] Tol (2006). ‘Exchange Rates and Climate Change: An application of FUND’
[24] Parry et al, 2009. Op.cit.
[25] World Development Report 2010: Development and Climate Change
[26] Conway 2010: Background note on Crop Modelling and Climate Change Research

Appraisal Case

A. Determining Critical Success Criteria (CSC) / List the success criteria that are critical to achieving the impact and outcome recorded in the Strategic Case. / Apply a 1-5 weighting, where 1 is least important and 5 most important based on the relative importance of each criteria to the success of the intervention. / CSC Description Weighting (1-5) / 1 Involvement of the leading crop and economic modellers and researchers to ensure quality of scientific input 5 / 2 Access to quality data and state of the art on-line system to allow ongoing impact analysis 3 / 3 Active participation of regional scientists, supported by targeted capacity building 5 / 4 Involvement of end users to shape policy relevant analytical products and targeted for communication of results 3 / 5 DFID transaction and management costs 2
B. Feasible options / 25. The aim of the programme is to improve the evidence base on the likely impact of climate change on agriculture. By improving the evidence more effective action can be taken to address food security and agricultural productivity concerns. As set out in the strategic case, there is strong evidence for the need to improve the models under-pinning much of this evidence base. There is also a need to ensure improvements involve the active participation of scientists and end users in vulnerable developing country regions. / 26. In determining value for money the options considered were: / Proposed Option (AgMIP): supporting the Africa and South Asia regional components of AgMIP / Creating a stand alone, DFID led programme / Counterfactual – do nothing / 1. AgMIP: The proposed option is supporting the Africa and South Asia regional components of AgMIP. The AgMIP programme is a global initiative with considerable buy-in from experts around the world and as such has traction with developing country policy makers. / It is led by the Columbia University and the University of Florida with start up funding from USDA- ARS (United States Department of Agriculture – Agricultural Research Service). The core team has been set up under AgMIP with an initial AgMIP workshop to develop the first set of draft methodologies for the project. In recognition of the need to ensure genuine participation from developing regions, the AgMIP team has designed regional components to be supported by donor agencies. / 2. Stand-alone DFID-led programme: DFID has identified this as a critical area for investment. As this is a priority investment an alternative approach could be to commission a stand alone project. This approach would allow us to test the market, but would have significantly higher transaction costs and take much longer to get going. By joining AgMIP DFID is able to free ride on the already significant investment made by the US. A global initiative is likely to make the best use of economies of scale in terms of modelling techniques, expert personnel and administration. Additionally, it is unlikely that putting out a tender would result in a programme that brings together all main leading experts in this area as proposed by AgMIP. / 3. Counterfactual: Without DFID’s intervention, it is likely that the AgMIP programme would have developed but not in the regional manner that is intended. DFID’s engagement with AgMIP has been instrumental in developing the programme in Sub-Saharan Africa and South Asia. DFID’s early engagement has helped to shape a programme that will deliver a concrete set of research and capacity building outcomes and influenced the overall programme design by bringing the experience of the African and Asian context to the programme, thus raising the likely overall returns to the aggregate investment. Without DFID intervention it is likely that improvements in models would have taken place, but these would have been focused on the needs of developed countries and not have delivered specific evidence or capacity building for developing country regions. / 27. There is a strong case for positive economic and development benefits from investing in improved crop and agricultural trade models, which is set out in Section C. The AgMIP option is the most cost-effective option for delivering the desired outputs and impact, as compared to establishing a DFID led programme. This is discussed further in sections C and D. We set out below how the preferred option will work and provide a rating of the evidence that underpin it and associated climate/environment impacts. / Climate and Environment Assessment / 28. Given the nature of this intervention it is likely to generate significant climate and environment opportunities, as it will generate an improved evidence base for planning responses to climate change in the agricultural sector in Africa and South Asia. There are likely to be minimal direct climate or environmental risks from this project. Direct impacts are likely to be limited to travel. Participants should be advised that the carbon footprint of all travel supported by AgMIP should be minimised or offset where possible. All documents, reports and paper outputs of research studies funded by AgMIP should be printed on paper made from sustainably managed forests and/or recycled paper. / How the proposed option will work: / 29. The AgMIP regional component projects will build teams of specialists (including crop modellers, agricultural economists, climate scientists, and IT specialists) from each region through an open, competitive proposal process. These teams will conduct project research and ensure the regional validity and utility of the results generated by AgMIP. They will be supported by capacity-building activities and access to the leading crop and economic models. End users will also be engaged throughout the process to ensure AgMIP meets regional demands for information. Gender balance in end-users will be guaranteed through proper stakeholder analysis at a regional level. / 30. The process from input to impact is set out in the results chain below. / In the table below: / Rate the quality of evidence for each option as either A, strong, B, partial, C, limited or D, no evidence / Categorise the likely impact on climate change and environment as A, high risk / opportunity, B, medium risk / opportunity, C, low risk / opportunity, or D, core funding to a multilateral organisation. / Option Evidence rating (A, B, C, D) Climate change and environment category (A, B, C, D) / 1: AgMIP A: Strong / Strong evidence that agriculture will be affected by climate change, particularly in developing countries / Strong evidence that better information on impacts is required by policy makers / Partial evidence that models make a significant contribution to this information need / Strong evidence that improvements in models is required B: Given the likely significant opportunities for improving the evidence on climate change impacts and the low risk of direct climate/environment risks, this has been rated as B / INPUT / DFID funding of £6.4m to support regional AgMIP projects in Sub-Saharan Africa and S. Asia / Process (Activities) / - Build the capacity of teams of regional scientists to undertake data collation, model simulations and improvements. / - Produce research outputs: modelling frameworks and agricultural pathways. Run improved crop and food trade models for the regions under different climate change scenarios. Regional adaptation strategies tested. / - Facilitate interactions with regional end-users to communicate results and to develop relevant end products / Outputs / Improved crop and agricultural trade models as well as calibrated outputs for Sub-Saharan Africa and South Asia / Improved regional projections of climate change impacts on crop production and the associated economic implications and identification and prioritisation of regional agricultural adaptation strategies / Strengthened capacity of researchers in Sub-Saharan Africa and South Asia to access and use crop and economic models / Researchers and end users in Sub-Saharan Africa and South Asia better able to access improved and relevant information on regional climate change impacts on agriculture / Outcome (Purpose) / Reliable and accessible assessment of impacts of climate change on agriculture in SSA and S. Asia and improved evidence on priority potential adaptation strategies / Impact (Goal) / Improved evidence base to support efforts to improve food security and agricultural productivity in SSA and South Asia
C. Appraisal of options / 31. The AgMIP option is the preferred option for delivering the desired impact in terms of value for money and meeting the critical success criteria required to deliver impact. The cost of the DFID AgMIP investment is £6.4m (US$10m). The expected benefits of this investment are reliable and accessible assessment of impacts of climate change on agriculture in Sub-Saharan Africa and S. Asia and improved evidence on priority potential adaptation strategies. Results will be targeted at regional end-users and other development actors able to use the evidence to improve agriculture in these regions and the livelihoods of poor households vulnerable to these impacts. / 32. A recent DFID funded study on the Economics of Adaptation to Climate Change[27] estimated the additional costs of adapting to climate change on a regional and sectoral basis. Using figures from this study, the annual cost of adapting the agriculture sector to climate change is estimated to be around US$ 2.5bn in South Asia and US$2.4bn in Sub-Saharan Africa[2]. A one-off DFID investment of US$ 10m represents just 0.018 % of the estimated additional costs to adapt agriculture to climate change over this period or 0.006% per year over the 3-year investment period. / 33. The adaptation cost estimates quoted above assume that the most effective adaptation solution is invested in, and could be much higher if the selected mix of crops and cropping technologies has not been optimised for the prevailing climate conditions. Our investment in this research should reduce the possibility of additional costs due to having made the wrong choice in adaptation action. This benefit should apply over a period which goes well beyond the project duration. There is therefore, we believe, a strong value for money argument in making this investment rather than doing nothing (counterfactual). / 34. We did not undertake a full cost-benefit analysis of this climate change research. A survey of rates of return to research[28] noted that “there are no rates of return to climate change research available in the literature. The long and very uncertain time horizon for climate change interventions to have an effect on development outcomes do not allow for any credible way to calculate the rate of return to climate change research”[29]. However, as pointed out in the same study and in our reasoning in the paragraph above, this does not mean zero returns to research in this area, as there are likely to be large payoffs associated with early advice on appropriate adaptation actions. We opted instead for a multi-criteria analysis using the success criteria defined above to identify the most cost-effective option. / 35. The AgMIP option allows DFID to buy into a broader global initiative (Figure 1), securing the inclusion of African and South Asian scientists in this unique global partnership, greatly increasing their capacity and access to state-of-the-art crop and economic models and data. In doing so we are capitalising on the potential of this global initiative and the scientific expertise that it brings together to deliver improved information and capacity to enable substantially improved agricultural assessment and management in developing countries under changing climate conditions. / 36. AgMIP brings together the leading crop and economic modellers in a unique global network required to deliver the improvements in modelling. It also allows us to buy in to a state of the art on-line system that will likely be funded from corporate sources. Drawing on these resources, AgMIP will build the scientific capacity of these regions to respond effectively to current and future climate stresses on the agricultural sector and to inform policy and planning. This new capacity will be applicable beyond the immediate AgMIP outputs, for example for shorter-term agricultural forecasting, the identification and prioritization of agricultural adaptations and extensions (including for water resources and pest management). / Figure 1: Overview of funding structure and oversight of Global AgMIP Programme / 37. For the 2011-2013 period, the total estimated budget for the global AgMIP programme is approximately $33 million[3], while supporting the Africa and Asia regional component of this global initiative costs around $10m. This indicates the level of increased funding that would be required to develop a DFID led programme that brought together the required global expertise, data collation and on-line tools. It is unlikely that this would be cost-effective and it would not benefit from the substantial investment costs already made by the USDA in terms of methodological set-up and engagement of global expertise. / 38. DFID’s early engagement has been fundamental in helping shape a programme with a clear set of deliverables and an appropriate working modality for Sub-Saharan Africa and South Asia. Our support will further leverage funds from other partners such as USAID. / Additional Analysis to assess the optimal design of the intervention / Regional interactions: / 39. At the regional levels, AgMIP should minimise duplication of effort and avoid undermining the role of existing research bodies. In particular, AgMIP should forge partnerships with African Regional Institutions in order to deepen and broaden legitimacy and relevance of the models and their application. For Agriculture Research these institutions will include CORAF, ASARECA and CARDESA while on Economics these would include Regional Economic Groupings such as COMESA, ECOWAS and SADC and for Climate Change, these would include ClimDev, ACPC, ACMAD, AGRYMET and ICPAC. The same approaches should be adopted with similar bodies for South Asia. / 40. The regional relationships should be formalised through regional agreements and in addition, local accountability mechanisms should be put in place to facilitate embedding of capacity building. As much as possible, the developed models need to be embedded in regional institutions as part of long-term institutional capacity strengthening. / 41. At the very least, AgMIP should avoid extractive relationships with the regions. The programme legacy should be building capacity to apply the developed models as well as potential to develop new ones. / Poverty and climate model projections: / 42. Vulnerability of agricultural systems to climate change and variability calls for actions to strengthen the adaptive capacity of poor people and make the livelihood systems they depend on stand up to the pressures of climate variability and climate change. Predicting human and societal consequences of climate change is critical. Better information is needed to help reduce uncertainty associated with climate change and social consequences. / 43. The information generated by AgMIP could help communities take appropriate action to adjust their use of natural resources and crop management to changing climate conditions. While AgMIP’s primary interlocutors are at the regional and national levels, attempts should be made to consider the perspectives of local households and communities through interaction with relevant intermediaries to ensure that model results are representative of their conditions and needs and project results communicated effectively. / 44. Local scientists, planners and other stakeholders have a direct responsibility to ensure that processes are relevant and beneficial to small-scale low-asset-base farmers and place greater focus on crop productivity changes for reduced vulnerability of local populations. They will be assisted in this process if crop modelling research is more focused on the particular food security circumstances of poor communities.
D. Comparison of options / 45. Involvement of the leading crop and economic modellers and researchers: The AgMIP initiative has already established a network of the leading crop and economic modellers and recruited key researchers to lead the different scientific components. A DFID led programme would not have the convening power to replicate this and many of the key researchers are already committed to AgMIP / Access to quality data and state-of-the-art on-line system to allow ongoing impact analysis: The AgMIP initiative includes a state of the art on line system, including data storage, funding is being sourced from the commercial sector. By buying into AgMIP, DFID is able to benefit from this rather than having to fund an alternative system. / Active participation of regional scientists, supported by targeted capacity building: Early engagement with AgMIP has enabled DFID to help shape the process for active participation of regional scientists, including funding their participation at the design workshop to ensure AgMIP’s regional participation is effective. Access to the AgMIP network will mean that the regional capacity building is supported by the leading global researchers and modelling techniques. Particularly in Africa there is a limited pool of scientists with sufficient baseline capacity to participate in such a programme, a DFID led programme would be competing with AgMIP in this limited pool. / Involvement of end users to shape policy relevant analytical products and targeted for communication of results; AgMIP already has an established steering group, with representatives of key organisations such as FAO, and WMO to build on. AgMIP has been designed so that regional institutions will be engaged in identifying key policy questions and for dissemenation of results. A key role of the AgMIP regional coordinators will be to build relationships with key regional institutions. / DFID transaction and management costs: AgMIP enables us to deliver the impact and outcome at a lower DFID transaction and management cost. By buying into an already established global initiative, we do not have to invest heavily in costs associated with design and commissioning. We are also able to use USDA’s financial management systems, reducing the ongoing admin costs to DFID. / Option 1: AgMIP Option 2: DFID led Option 3: Counterfactual / CSC Weight (1-5) Score / (1-5) Weighted Score Score Weighted Score Score Weighted Score / 1 Involvement of the leading crop and economic modellers and researchers 5 5 25 2 10 0 0 / 2 Access to quality data and state of the art on-line system to allow ongoing impact analysis 3 5 15 3 9 0 0 / 3 Active participation of regional scientists, supported by targeted capacity building 5 4 20 3 15 0 0 / 4. Involvement of end-users to shape policy relevant analytical products and targeted for communication of results 3 4 12 4 12 0 0 / 5. DFID transaction and management costs 2 5 10 1 2 - n/a - n/a / Totals 72 48 0
E. Measures to be used or developed to assess value for money / Buying-in to global partnerships / Open competition for regional components / USDA’s internal project continuous improvement mechanisms and monitoring of consortium use of funds
[27] World Bank. 2010: The Economics of Adaptation to Climate Change
[2] Based on an average of the highest and lowest estimated costs of adaptations regionally, using different economic assumptions and the wettest and driest climate change projections.
[28] Kunel Sen 2010 Literature review on the rates of return to research
[29] ibid
[3] approximately $25 million for developing regions, $3 million from the USDA to cover US regions, and $5 million (in grants or salaried time) from other national agricultural departments to cover developed country scientist participation in AgMIP)

 Commercial Case (Indirect Cost)

A. Why is the proposed funding mechanism/ form of agreement the right one for this intervention, with this development partner? / 46. DFID will fund the Sub-Saharan Africa and South Asia AgMIP regional components, at a cost of £6.4 million over 3 years. This will be funded jointly by the Agriculture and the Climate and Environment Research Teams. The funding arrangement will be an MOU between DFID and USDA-ARS. / 47. The choice of MoU was established after a satisfactory Due Diligence exercise on USDAs ability to manage DFID money, contractors and in doing so the ability to apply robust procurement and continuous improvement processes to this programme on our behalf. Reporting requirements of the arrangement will require USDA to reconcile funds spent each quarter and annually a report on the technical quality of the programme outputs.
B. What has been done to assess whether the third party organisation has the necessary capability and capacity to obtain best value for money from the funds they are spending on behalf of DFID? Where improvements in capability or capacity have been identified how are these being taken forward? / 48. In conjunction with Procurement Group, a recent Due Diligence exercise was undertaken to establish the strategic and management approaches taken by the organisation to manage projects and programmes. The continuous improvement element of the exercise determined that the staff development aspect would potentially promote capacity development with developing country partners.

Financial Case

A. How much it will cost / 49. DFID will provide £6.4m over 3 years (2011 – 2013), under a MoU with USDA-ARS for the Sub-Saharan Africa and South Asia regional components. / 50. USDA-ARS will hold funds from each donor organization supporting AgMIP in separate accounts under separate agreements with each organization. USDA-ARS will encourage all donor organizations to follow the same funding structure and oversight framework; however this would not be a requirement. / 60. DFID will disburse funds strictly according to need and in conjunction with normal DFID accounting procedures, via the Memorandum of Understanding / Budget / 61. DFID funds will enable the funded participation of developing region agronomists, economists, climate scientists, and IT specialists in AgMIP. Donor funds will support AgMIP research activities to develop scientific capacity and model improvement in the region, as well as AgMIP International and Science Coordinators to oversee funding and research interactions between the AgMIP Leadership Team and developing region participants and their institutions. / Table 2: Proposed Budget for Africa and South Asia Regional Components ( see separate spreadsheet for breakdown) / Y1 Y2 Y3 CUML TOTAL / AgMIP Regional Participation for Africa and South Asia 1,915,200 1,915,200 1,915,200 5,745,600 / AgMIP International Research and Coordination for Africa and South Asia via Columbia University 1,543,393 1,400,393 1,400,393 4,344,179 / TOTAL PROJECTED COST US$* 3,458,593 3,315,593 3,315,593 10,089,779 / Additional DFID budget for mid-term review £50,000 / *exchange rate 19/01/11 £ 2,164,792 2,125,230 2,075,230 6,364,485
B. How it will be funded: capital/programme/admin / 62. The programme will be funded from DFIDs programme budget. Payment frequency and the fiscal year they relate to are set out in the table below. Payment values are indicative, actual payment values will vary according to need. Need will be assessed by quarterly reconciliations / Financial Year Amount Approx Payment Date Note / 10_11 527,964 payment on MoU signing (expected Jan 2011) / 11_12 538,219 Apr-11 1 / 11_12 538,219 Jul-11 1 / 11_12 538,219 Oct-11 1 / 11_12 538,219 Jan-12 1 / 12_13 519,093 Apr-12 1 / 12_13 519,093 Jul-12 1 / 12_13 519,093 Oct-12 1 / 12_13 519,093 Jan-13 1 / 13_14 519,093 Apr-13 1 / 13_14 519,093 Jul-13 1 / 13_14 519,099 Oct-13 1 / 6,314,485 / Note : 1. Payment value and timing subject to reconciliation of previous funds
C. How funds will be paid out / 63. The proposed mechanism for facilitating the funds will be a memorandum of understanding. To mitigate issues such as advance funding, we will build in a quarterly payment system of releasing funds on receipt of an invoice AND a reconciliation of previous funds. The actual payments are not therefore tied to the above budget values and are instead based on project need.
D. How expenditure will be monitored, reported, and accounted for / 64. Fiduciary Responsibility: Due diligence for disbursement of funds will be done through the USDA-ARS and Columbia University through an agreement between USDA-ARS and Columbia University. Reporting, oversight or any other requirements provided in the agreements’ terms of reference provided to USDA-ARS by DFID will be included in this agreement to be implemented in any activities, including any other sub agreements established to carry out the activities. / 65. The Trustees of Columbia University in the City of New York delegates all grant matters to Sponsored Research Administration (SPA). SPA is tasked with handling all aspects of proposal submission, grant and contract setup, legal issues, subcontract creation with other institutions, official signatory, as well as annual and final award reporting. In addition, to SPA, Sponsored Projects Finance handles the necessary involving and other financial matter for all sponsored project awards. / 66. Separately (and prior to submission), a third-party procurement due diligence exercise has been undertaken to establish an understanding of similarities and differences between DFID’s and USDA’s respective procurement systems. This has proved useful and as a result there are no major concerns over the use of DFID’s money in respect of this programme. A copy of the Due Diligence template has been quested.

Management Case

A. Oversight / 67. Overarching governance arrangements for the project/programme. / AgMIP is an initiative that involves stakeholders from across four continents and several countries and therefore may face major challenges in its implementation. The Governance and management arrangements will need to balance a whole set of objectives, expectations and relationships. It will also face the task of harmonising diverse institutional requirements in areas such as financial management and accountability, reporting and quality assurances. / 68. Given these challenges, AgMIP has designed an inclusive governance structure (figure 1) that provides clear and arms length oversight, without interference from any of the key sponsoring partners. The structure will distinguish between corporate management oversight and quality assurance responsibilities. / 69. There are also clear roles and responsibilities (section B) for the governance organs such that any eventuality can be dealt with within that framework. The programme management arrangements need to be transparent, providing regular information that allows full accountability for both technical and financial performance. Programme interventions need to build in mechanisms for accessibility by non-specialists. / Figure 2 sets out the funding structure and oversight of AgMIP Regional Programmes. / Figure 2: Overview of funding structure (black arrows) and oversight (blue arrows) for AgMIP. The AgMIP International Coordinator will oversee developing region finances and organization, while the AgMIP Science Coordinator will oversee scientific interactions / 70. Stakeholders: / The main stakeholders of the regional AgMIP programmes are: / Funders / Implementers / End-users / The oversight structure allows for these stakeholders to provide oversight in both a top-down and bottom-up way. The funders will be represented on the donor forum, which will receive 6-monthly updates and annual reports from the AgMIP leadership team. The implementers are represented both in the leadership team, which will run the overall AgMIP team and provide quality assurance, and in the regions where regional teams of scientists will be set up. End users will be represented both on the steering group, providing technical oversight and challenge function, and in the regions where there will be outreach and engagement with key regional organisations such as sub-regional agricultural research organisations, regional economic organisations and regional climate science organisations, through regional workshops and direct interactions with the regional coordinators.
B. Management / 71. Roles and Responsibilities of AgMIP management bodies: / Leadership Team. AgMIP is led by Drs. Cynthia Rosenzweig (Columbia University/NASA GISS), Jim Jones (University of Florida), and Jerry Hatfield (USDA-ARS). Research activities will be led through the coordination of four project teams: / Crop Modelling (led by Drs. Ken Boote, University of Florida; and Peter Thorburn, CSIRO, Australia) / Economics (led by Dr. John Antle, Oregon State University; and Dr. Jerry Nelson, IFPRI) / Climate Scenarios (led by Dr. Alex Ruane, Columbia University/NASA GISS) / Information Technologies (led by Drs. Cheryl Porter, University of Florida; and Sander Janssen, Wageningen University, Netherlands). / 72. Each project team will have U.S. and international co-leads, and coordinates AgMIP participation from both developed and developing country research institutions to ensure that project activities are conducted with consistent protocols. USDA-ARS scientists are playing key roles in the development and conduct of research as members of each of the project teams. The teams will hold regular teleconferences to facilitate communication among participants and provide a mechanism for regular updates and oversight, enabling the teams to identify and address any problems that may occur. The teams will also help to organize and participate in annual AgMIP meetings. Visits to AgMIP participating field sites will also be conducted by one or more team members. / 73. AgMIP Developing Regions. These will run as self-sufficient components of AgMIP. DFID will support: / Sub-Saharan Africa (including East, West, and Southern Africa) / South Asia / 74. Donor Forum. Direct oversight of the fiduciary responsibility will be provided by the Donor Forum, with representatives from each of the funding agencies. The Donor Forum will be invited to project meetings, supplied with regular updates and meeting reports, including a 6-monthly update and an annual report (including a forward workplan) and encouraged to provide the AgMIP Leadership Team feedback on project activities, monitoring of project milestones, and allocation of project resources. The donor forum will approve annual reports, accounts and forward work plans. / 75. Science Steering Group. AgMIP’s Science Steering Group is made up of international leaders in climate and agricultural modelling. Science Steering Group members will help guide project research activities and provide oversight on the research conduct of the project. Science Steering Group members, many of whom have strong connections to stakeholders and end-users in diverse agricultural regions (including developing regions), will help AgMIP deliver useful products for the broader community.[4] / 76. Science Coordinator. Dr. Alex Ruane (Columbia University/NASA GISS) is the AgMIP Science Coordinator; responsible for assisting the leadership team in coordinating team activities, monitoring regional progress toward AgMIP products, linking with complementary programs and funding opportunities, and organizing research initiatives to achieve AgMIP goals. / 77. International Coordinator. / The International Coordinator will organize the participation of the agricultural scientists in each of five regions, supported by the regional coordinators: Sub-Saharan Africa (consisting of East, West, and Southern Africa), South Asia, Central Asia, East Asia, and Latin America. The International Coordinator’s role includes: / conducting a competitive proposal process for agricultural scientists and their institutions in developing countries, / setting up agreements with the scientists and their institutions selected via the competitive process, / monitoring the progress of the research including delivery of the research products, and ensuring overall compliance with fiduciary responsibility of all parties. / The International Coordinator will also organize at least two research study visits in which developed region AgMIP scientists will visit the developing region scientists at their institutions over the course of the project in consultation with the Steering Group and Team Leaders. Whenever possible, these study visits will involve consistent AgMIP participants to facilitate lasting collaborations between AgMIP developing region scientists and participants from developed countries. / 78. Management Tools: / There will be an initial inception phase that will include regional interaction with key scientists and end users to further define the specific regional outputs, stakeholders and working modalities. This will enable a refined workplan to be produced and updates to the logframe milestones, baselines and targets if needed. / 79. DFID Management: / This project will be jointly funded by the Climate and Environment and the Agriculture Research Teams. Financial management will be provided by the Climate and Environment team and the cross-team Climate and Environment Adviser will provide technical oversight.
C. Conditionality (optional – see HTN) / This is not applicable
D. Monitoring and Evaluation / 80. DFID will monitor AgMIP against the logical framework, which follows DFID guidance and provides an operational m&e framework for monitoring both delivery and impact of the programme. The AgMIP International Coordinator will monitor the progress of the research, including delivery of research products, capacity outputs and overall compliance with fiduciary responsibility. The AgMiP leadership team will provide a six-monthly update and an annual report to the donor forum, These will include progress reports specifically linked to the logframe outputs and milestones. Refinements to the logframe indicators will be made as part of the initial inception phase, a report on this phase will form the basis of the first 6 monthly update for DFID approval / 81. The DFID management team will conduct annual reviews in line with DFID best practice. Provision will also be made for an independent mid-term review of DFID investment in AgMIP. This will enable an assessment of the progress towards the research outputs as well as the capacity building goals, bringing in technical expertise that we do not have in-house.
E. Risk Assessment / AgMIP: Risks considered, assessed and mitigation measures / Risk Impact if Realised Probability of Realisation Mitigation / Risk of funds not being used for their intended purposes, including fraud or corruption risks low - med low This is safeguarded by two principles. The first is the Due Diligence Exercise where we are satisfied that there are systems in place to mitigate this on our behalf and the second is the nature of quarterly reconciliations which substantiate payments. / AgMIP fails to secure sufficient funding for the rest of the global programme low-med low Funding will be provided by DFID to fund the specific Africa and South Asia related activities of the key members of the global teams. This will ensure they have time and resources to deliver for the Africa and South Asia projects regardless of the rest of the global programme. The IT Team is already funded through the USDA core funding, so the minimum data and archival needs will be met. / PIs with the right experience and skills set are not found in Africa and South Asia high low Networks and key institutions have been identified to advertise through. Initial regional workshops will be used as an opportunity to target suitable individuals. This process has already begun and suitable regional participants have been identified through regional attendees of first AGMIP workshop, CCAFS, AGRA and the AGMIP steering group. / PIs do not fully achieve objectives med med Monitoring systems will be put in place to pick up delays and under-achievement in objectives to enable prompt management action, including redefinition of objectives. The International Coordinator will monitor progress against explicit milestones and benchmarks to determine level of fulfilment of project tasks. Annual site visits will also allow on-the-ground evaluation of progress. / PIs will not contribute simulation results from their locally validated models that adhere to AgMIP protocols for calibration and intercomparisons med low This will be an explicit output in PIs TORs and capacity building will be provided. Supervision will be provided by the AgMIP team leaders at annual regional workshops and site visits. PIs will present results annually and receive feedback and training at the yearly international AgMIP meeting. / PIs do not abide by reporting requirements / Related to risk above med low This will be monitored by international coordinator; remedial measures will be put in place including withholding funds if needed; related to above / Local and regional data will not be located/estimated that will suit the input requirements for crop and economic models med low Sufficient time to locate and collate data is built into the work programme. If sources of local/regional data are poor, other sources that will allow outputs to be achieved have been identified: e.g. FAO, IFPRI gridded soil data sets etc. / Researchers will not be supported by their home institutions to continue crop and economic model applications low med The skills and datasets that will be generated from AgMIP participation are in demand for agricultural planning. The goal is for AgMIP to continue past the original three-year period. We will work with end-users and AgMIP participants to support continuing applications. / Mitigation and adaptation decisions for climate change impacts on agriculture will not be made in consultation with local researchers and specialists, or without input from AgMIP results high low Key end users will be invited to participate in workshops throughout the project to help identity key policy questions, increasing relevance of outputs and interactions between the research and policy communities in the regions / The poorest do not benefit from AgMIP results due to elite capture of information and/or skewed interpretation of model results high Low/med Research to be integrated with economic factors impacting poor farmers and overall poverty reduction contributions; relevant end users that can represent poor groups involved regionally and on steering group; poverty impact assessment as part of evaluation / Despite improvements, model methodologies are not capable of generating evidence and reducing uncertainty to a level sufficient for policymakers to act on Med/High Low/Med Ongoing monitoring by DFID team of the emerging products from AgMIP and alternative methods for generating impact information to allow re-direction of funding in this area if necessary. / The project has an overall ‘MEDIUM’ risk.
F. Results and Benefits Management / See Logframe
[4] The Science Steering Group currently consists of Mark Rosegrant (IFPRI), Andre Bationo (AGRA), Martin Parry (ICL), Mark Cane (Columbia University), John Porter (University of Copenhagen), Mannava V.K. Sivakumar (WMO), Michele Bernardi (FAO), PK Aggarwal (India), Phil Thornton (CGIAR ILRI), Lin Erda (China), Diana Liverman (University of Arizona and Oxford University), Eduardo Assad (EMBRAPA), Peter Carbury (representing Australia), Martin van Ittersum (Wageningen University), and Jean-Francois Soussana (INRA France).

REFERENCES