Intervention Summary

## Title: Mozambique Democratic Governance Support Programme

What support will the UK provide?
The UK will provide financial and technical support to a range of non-governmental organisations and groups, including urban communities, civil society organisations, policy orientated think-tanks and the media. The support will help these groups to improve the accountability and responsiveness of government at municipal and central level. Through the support received the groups will be able to aggregate, articulate and press issues which are a priority for the women, men and youth of urban Mozambique. UK support will help improve communication initially in focal urban districts, to ensure that local priorities and concerns are incorporated into government planning at the municipal level, and become a part of the agenda at the national level. Women, men and the youth in target districts will be able to establish channels through which the locally identified priorities for their development can be represented in municipal planning processes and documents. The support provided by the UK will facilitate the space, skills, and human, technical and financial resources for this process to gain traction. / The Democratic Governance Support Programme (DGSP) approach is based on the findings of targeted analysis and design work[1]. This preparatory work has shown that democratic institutions in Mozambique have little incentive to be more proactive in providing and promoting the rights and freedoms of citizens without being held accountable for their actions and omissions[2]. This will not happen without effective demand from society, but the demand also needs to be listened to. The programme aims to facilitate a process that will identify and constructively channel such demand in a manner that is responsive to the needs of the poor, and inclusive of all relevant stakeholders from the outset. [3] / Priorities, in terms of issues, will be defined through a process of discussion and consensus-building. The process will be fully inclusive and take a discursive, rather than adversarial approach, stimulating local processes and mechanisms, not creating new ones. A fundamental part of the programme strategy is to promote gender equity, and so, at every stage, the active participation of women, men, youth, and people who are vulnerable will be emphasised. This approach directly supports the Government of Mozambique’s priority to promote peace and dialogue[4]. / DGSP will focus much of its effort in 5 urban municipalities in the south, centre and north of Mozambique. Analysis[5] of support provided to central level democratic institutions demonstrates little impact and working at the municipal level allows a greater opportunity to bring all actors, (community, political, legislative, executive) together on a pragmatic, problem-solving basis. Urban areas represent a useful incubator for deepening democratic values and processes. They are densely populated and expanding. The populations are relatively better educated, with more access to diverse media, and include large numbers of youth. In the preparatory phase for the project design[6], the youth of Mozambique are highlighted as an important emerging actor for strengthening democracy. / A second programme component aims to reinforce communication, accountability and transparency in government - at the municipal and central level, and between the two. It will link policy makers at both levels of government. It will link communities and the issues they identify as important with national policy debates and media investigations. Access to policy analysis, informed by priorities within the target communities, will be expanded by the use of a challenge fund. Academic, NGOs and think-tanks will be able to bid for small grants from the programme to pursue policy-orientated research. The programme will then use this analysis to stimulate lively, informed, and constructive public debate. / The third component supports the strengthening of a vibrant and diverse media. The media is key to enhancing communication, and promoting accountability[7]. DGSP will establish a second challenge fund to make grants to media houses, which submit proposals according to strictly objective criteria broadly in support of the programme purpose. The project will also provide support to strengthen the overall enabling environment for free, financially sustainable media. / The programme will run between 2011 and 2016 (a five year period) with implementation beginning in the third quarter of 2011. It will cost £10 million over this period. The programme has been designed in such a way that other donor funding will allow an extension of the geographical focus. Other bilateral donors are interested in participating, though there are not donors able to commit funds in the current financial year. / Security issues: A Hypothetical Example / Crime and security are key problems identified in Mozambique, particularly by urban people (Afrobarometer). Addressing crime and security is a potential area that interest groups could identify as part of this programme. Below describes how this might happen in practice. / A community organisation and the Association for Informal Vendors are both very concerned about crime affecting their well-being and their businesses. With the programmes help, they decide together to raise the problem on two local radios broadcasting in the urban area. They invite religious leaders, community leaders from different neighbourhoods, representatives from community policing councils and elected political representatives to a public meeting to discuss what are the main problems being experienced and what needs to be done. Two main issues raised by participants are the lack of police patrolling the streets in poorer neighbourhoods and the lack of street lighting in both poorer neighbourhoods and around market areas. / Municipal assembly representatives agree to raise the issue of street lighting in the municipal assembly. Community associations work together with local radio and the press to ensure crime is being reported in the media and to share views on where street lighting is most urgently needed. Community policing councils are encouraged to do more to channel concerns about crime and security to both the local police and to political representatives. The municipal government as a result holds a public consultation on its draft plan for investment in street lighting, which leads to a shift in prioritisation. A coalition of different groups has begun to form around a single issue. / One constraint identified is the lack of police accountability to municipal structures. The municipal government forms an alliance with community associations to channel concerns about policing to the provincial and national government. They demand a more rational distribution of police across the urban area and shine a light on the informal "privatisation" of police officers who are receiving additional payments for guarding certain businesses in the centre. Police commanders are receiving kick-backs for allocating their officers to do this. The argument about privatisation of the police is backed up by research carried out by a Mozambican NGO. The joint effort by municipal governmend and civil society organisations to expose corruption and gaps in the police forces a discussion at the national level about policing and how it could better serve Mozambican people. / In this example, the facilitation, organisation and networking would be supported by the programmes local facilitator or partner organisation. The issue might then be reinforced through the programmes other two components (described below).
[1] See Annexes 5,6,7,8 & 9; and Appraisal section below
[2] See Annex 9, Political Economy of Democratisation in Mozambique, Macuane, 2010; Mozambique, Balancing Development, Politics and Security, Chatham House, Jeremy Astill-Brown & Markus Weimer 2010;
[3] Outside Mozambique, recent events in Tunisia, Yemen, and Egypt have underlined the importance of entrenching a process of communication and accountability between governments and ever younger, and increasingly well-informed populations
[4] Programa Quinquenal do Goberno para 2010 - 2014 para 16 i.
[5] Annex 8, A review of past and present support to democracy in Mozambique: Macuane, Salimo, Weimer; October 2010
[6] Annex 9, Political Economy of Democratisation in Mozambique, Macuane, 2010
[7] “Uncritical Citizenship in a Low Information Society: Mozambicans in comparative perspective” Robert Mattes & Carlos Shenga, AfroBarometer Working Paper 91. Dec 2007

Why is UK support required?
There is little political pluralism in Mozambique. FRELIMO (Frente de Libertação de Moçambique) is entrenched in power; in the spheres of politics and business. RENAMO (Resistência Nacional Moçambicana) has little credibility as a political force, mainly due to poor leadership. The recent 2009 general elections tightened FRELIMO’s grip on power. The incumbent president, Armando Guebuza, won 75% of the vote. FRELIMO also won 191 out of 250 seats in the parliament. Although voting on the day was peaceful and well organised, election observers commented that electoral processes were flawed. This was a serious concern, which has been consistently noted in prior elections. / Low turnout in these elections, and the findings of Afrobarometer public opinion surveys, suggest dissatisfaction with the current system. Recent riots show that there is risk that frustration can boil over into violence. / Boundaries between party, state and the private sector are blurred. Accountability mechanisms are weak. Parliamentarians lack capacity and resources. Civil society is relatively undeveloped and largely in a service provision role rather than a strong advocate encouraging accountability. / However, there is a liberal constitution and a free media. A new party, the Movimento Democrático de Moçambique (MDM) is gaining support in urban areas and exposure in parliament and the press. There are high profile civil society organisations that are genuinely challenging the status quo. Commentators and academics publicly question the government, but mainly within the view of the urban middle-class. / FRELIMO is not without internal democracy. Moderate voices, like that of Graça Michel, do challenge the more centralising tendencies of the current president. FRELIMO wants to be seen as the party of the ordinary people, and to be democratic and responsive. / Mozambique performs comparatively well in some key areas of governance compared to other countries in sub Saharan Africa. For example, public financial management and government stability. New financial systems have tightened control of government funds. Revenue rose from 10.8% of GDP in 1998 to 17.8% in 2009, and is projected to rise to 18.4% in 2010. However, Mozambique has weaker control over corruption than other countries in the region. In addition, there are major concerns about the weaknesses in the legal and judicial system. / Concerns about the general state of governance have led budget support donors to intensify the political dialogue with government and budget support payments were suspended in 2009/10. There is concern that a lack of accountability, both internally within the government and party and externally, will allow the growing revenue from natural resources to be used for the benefit of the elite rather than for poverty reduction. Oil and gas have recently been discovered, and large deposits of high grade coal are beginning to be exploited. / While the formal institutions of democracy have not demonstrated great enthusiasm for challenging this political status quo, there are other entry points for supporting those who would deepen the democratic process in Mozambique. DFID sees an opportunity to complement the political pressure being applied for greater accountability through the budget support dialogue with practical steps to enhance democratic processes and citizen voice. The DGSP will address the core problem of failed communication, by stimulating and facilitating channels of communication between stakeholders at the municipal level in 5 cities throughout the country, where the main focus of activities will be.

What are the expected results?
As a result of the activities under this programme, women, young people and men will increasingly participate in a meaningful way[8] in the decision-making and political processes at a local level in the target municipalities. They will have a better understanding of the possibilities and limitations of municipal level government, and will have established processes and channels for discussion and communication between citizens and decision-makers. These will act as a decompression chamber for social and economic frustration. Citizens’ priorities will begin to be a part of the municipal agenda. / There will be an improvement in the sustainability of the independent media. An annual report to objectively assess the health of the independent media (reach, regulation, financial flows, investment and advertising) will be operational. Over the life of the project, the revenues of private media will increase in size and diversity by 35%. In the target municipalities, the project will see up to a 20% increase in the use of advocacy by citizens to secure Constitutional rights and freedoms, and an increase to 38% (from an estimated 20%) of citizens reporting that their voice is heard by leaders between elections. These improvements will contribute to strengthened democratic decision-making processes in the project sites. The conduct of elections in the target municipalities will be carried out in accordance with best practice, with the percentage of women candidates for municipal assembly elections rising to 30% of candidates. The improved quality of participation at the municipal level will be amplified through a more vibrant policy debate at the national and local level. This will be informed by successes, challenges and priorities identified through project activities, completing a circle of communication, improved transparency and increased accountability. / The immediate beneficiaries of the project will be the members (women, youth and men) of the communities in target cities who are participating in the awareness-raising and dialogue activities. Beneficiaries at the local level will also include other stakeholders participating in the dialogue process, members of municipal assemblies and local councils, political parties, independent media. Beneficiaries will also include the local implementing partners whose capacity to manage processes of this kind will be enhanced by their participation in the project. Specific beneficiaries may vary depending on the issues identified, such as the local offices of STAE where conflict management training with political party participation may take place, as well as other activities to strengthen political parties in their role pertaining to voter registration and education. / With regard to activities in support of media strengthening, direct beneficiaries will be practitioners in the independent media in all its diverse forms. An increasingly vibrant policy debate will benefit communities and policy-makers over the longer term, and serve to increase positive perceptions of the democratic process in Mozambique. / While there is clear data on some of the measures of progress to be used for the programme, or appropriate proxy data, there will need to be a baseline survey completed in the target municipalities during the planned inception phase. Much of the planned activity is specific to the programme and the target municipalities, or addresses new areas, on which relevant data is sparse, such as the proposed media activities. It will be very important that accurate baseline data is defined from the beginning of the programme in order to be clear on its achievements. It is also the case that there is less quantitative data generally available relevant to democratic participation (aside from voting figures) than there may be for other areas, such as education or health. For this reason the programme proposes a combination of standard indicators, such as election-related data, with more qualitative data, in order to honestly measure the changes which it anticipates.
[8] As defined by Arnstein’s Ladder of participation, see Annex 1 Logframe Purpose Indicator 1

Business Case for: Mozambique Democratic Governance Support Programme

Strategic Case

A. Context and need for DFID intervention / Mozambique’s long running post-independence conflict formally ended in 1992, with the signing of the General Peace Agreement (GPA). The country faced a daunting reconstruction programme in every sector. The FRELIMO (Frente de Libertação de Moçambique) party, which had led the independence struggle, retained power through the countries first multi-party elections in 1994[9]. FRELIMO has stayed in power with increasing dominance ever since, through regular, but flawed, elections in 1999, 2004 and 2009. Armed conflict left neither the new government, the opposition, nor the population, adequately prepared to participate in a functioning democracy. / Mozambique’s formal commitment to democracy is apparent in its legal and planning framework. The Constitution of the Republic establishes a democratic system of government, albeit with a strong bias in favour of Presidential power. The consolidation of democracy, and good governance are central themes of the Government of Mozambique’s current five-year plan (PQG). Paragraph 4 of the PQG Introduction highlights a commitment to continuing with a people-focussed process of decentralisation, promoting good practice in governance in order to combat poverty and promote social, economic and cultural development. Priority actions include (1) the promotion of peace, dialogue and national reconciliation leading to the consolidation of democracy; and (13) reinforcing civil society participation in local development, with particular focus on the involvement of local consultative councils. In its action plan based on the recent African Peer Review Mechanism (APRM) report[10], the Government includes a thematic area of democracy and political governance. / However, the overall conclusion of recent political[11] and economic[12] analysis is that Mozambique now faces great economic and political challenges. There are indications of a growing democratic deficit, in that the government’s formal commitment to democracy is not backed by corresponding action. At the same time, the country faces increases in poverty that demonstrate inequity in the distribution of wealth and services, with women suffering disproportionately[13]. / The overall formal architecture of democracy is in place, with a separation of powers between the executive, legislature and judiciary. Institutions of democracy are established - the National Commission on Elections, newly established Human Rights Commission and Ombudsman’s Office, a separate legislature, state and independent media, civil society and a theoretically independent judicial branch. Democratic processes occur (for example, Mozambique has held regular presidential and parliamentary elections as well as local elections most recently in 2008; and civil society carries out monitoring and advocacy activities). However, the control and influence of the government in democratic institutions and processes compromises their objectivity and independence. As a result they do not fulfil their accountability role adequately. According to Freedom House, “Mozambique is not an electoral democracy[14]”. This assessment is based on the persistent irregularities that are reported over elections, for example, in the last (2009) elections, opposition party members were prevented from registering to stand as candidates. / Although there are certainly critics within FRELIMO, as well as outside, who are disappointed with a tightening central grip on power as well as the rate of development and the gaps in service delivery, the dominance of FRELIMO is buoyed by a general, although diminishing, emotional attachment rooted in its leadership in achieving independence from Portugal. This is an important factor, because due to a combination of affection and apprehension, it results in self-censorship. This contributes to inhibiting robust debate, and facilitates the conflation of ruling party with government. In turn, there is little opportunity for effective political opposition to develop, limiting the scope for serious challenge, and restricting channels for communication. / The dynamism and influence of the other main political force and party, RENAMO (Resistência Nacional Moçambicana), has been declining. Although it maintains armed soldiers, and political support, the party is paralysed by the attitude of its leader[15]. As an institution it is weak, lacking systems and organisation. This is an unhealthy situation politically, although the emergence of the MDM (Movimento Democrático de Moçambique) may signify the beginning of a break in political stagnation.[16] / Vertical systems of accountability, such as Parliament, do not function to their full extent, and so a balance of power and accountability is very difficult to attain. The closed party list system tends to focus the loyalty of a deputado (member of parliament) on his/her party, rather than the constituents who voted. This is reinforced by extremely strict party discipline in FRELIMO, which inhibits independent questioning or debate in the parliamentary session. In the case of members of parliament, very high turnover at elections (65% of deputados entering Parliament after the 2009 elections were new) contributes significantly to generally low levels in capacity[17] for analysis and scrutiny, which need to be constantly reconstructed. / Media is a critical enabler of citizen engagement around good governance and accountability. While multiparty democracy has strengthened civil liberties and improved pluralism in Mozambique, there has been limited progress in opening up government - or private institutions for that matter - to make them more transparent or accountable. / The Mozambique media operate in a political environment in which formal media freedom is acknowledged and respected. There is no definite pattern of state interference in the private media, but evidence that within government some perceive the private media to be “the opposition”, to be treated as such, and discriminated against economically. Media independence and diversity is critical to mitigate the risk of elite groups within political, government and economic circles cooperating to control access to resources. This is a particular danger in economies with large natural resource sectors, and/or high levels of state spending. Low levels of accountability and transparency and high levels of discretion in decision-making are a potentially toxic mixture. / Overall, the size of the media market appears small relative to the economy, but reliable statistics are scarce. Over the past two decades, it is market based investments by local journalists and entrepreneurs which have generated a sustainable if in part economically fragile, non-state media sector. In terms of financial flows, the media market is distorted by a number of factors including biased state spending, lack of systematic audience measurement data, and restrictive foreign ownership rules. The diversity and economic strength of the non-state sector is vital to support democratisation by creating competitive and plural information sources. / Non-governmental organisations (NGOs) have space to operate, but are generally characterised as weak in capacity and organisation, especially when it comes to taking a united position (for example in proposing members for the National Elections Commission). This limits their influence. They have also been susceptible to ‘capture’ by a party keen to soften critical voices. Although they can play a useful role in helping to bridge the gap between citizens and government, they are not strong enough to shoulder all the responsibility. / Mozambique is described as a “low information society” according to AfroBarometer comparative studies across Africa[18]. “Political information remains the single strongest predictor of opinion [forming] and, along with formal education, continues to have a large impact on demand for democracy.” The conclusion of the study is that “…a significant share of the fate of Mozambique’s fledgling democracy will rest on the speed and degree to which the government and donors are able to expand educational opportunities and access to news media, particularly independent media, in order to build critical skills across the body politic.”[19] / For effective communication to develop, there needs not only to be demand, but also, active listening. Most evidence to date points to a party that does not take kindly to challenge, which is usually interpreted as support for the opposition, and a government that does not listen adequately and is not connected to the women and men, and particularly, the youth who are its citizens. / The ‘disconnect’ between ordinary citizens and the people who are supposed to represent them can provide fertile ground for dissent and frustration, as was graphically demonstrated in the early September price riots in Maputo city. President Guebuza is on record as describing it as a deficit in communication between the government and the people. It stultifies the process of demand and discussion which is at the heart of the democratic system. / This programme is consistent with the DFID Mozambique Operational Plan (2011 to 2015), which states that ‘wealth creation and governance are the two areas upon which the success of the programme most depends …. Without progress in tackling corruption and strengthening accountability, future gains will be jeopardised.’ / The programme is also consistent with the DFID Business Plan and Structural Reform Plan priority of using UK aid ‘to support the development of local democratic institutions, civil society groups, the media and enterprise’.
B. Impact and Outcome / The goal of the project is to contribute to improved governance and accountability for Mozambican citizens. The outcomes of achieving this goal may include: / increasing the extent to which political systems provide opportunities for all to influence government policy and practice, / improving the degree of transparency and accountability in allocation of public resources that promotes effective pro-poor policy implementation, / increasing the degree of equity in basic services provision / enhancing the environment for free, vibrant and challenging policy formulation / increasing accountability in target areas / The programme purpose is strengthened democratic institutions in Mozambique better able to provide and protect rights and freedoms provided in the National Constitution. The project focuses on the core informal process of democracy, that of dialogue, consultation and consensus-building. In support of this focus, it will increase access to information regarding democratic processes for women youth and men. / The strategy to be adopted will strengthen the connection between communities and those in authority who serve them, and therefore begin the process of increasing (mutual) accountability. The approach is pragmatic, and will focus around issues which are important on a daily basis in the target communities, and through this, reinforce the value of a democratic process in practice not theory.
[9] 1994 FRELIMO 44% RENAMO 38%, EISA
[10] APRM Country Review Report No. 11 May 2009
[11] AfroBarometer 2008; Bertelsmann Stiftung, BTI 2010 — Mozambique Country Report; Mozambique, Balancing Development, Politics and Security, Chatham House, Jeremy Astill-Brown & Markus Weimer; APRM Country Review Report No.11, June 2009; Political Appraisal, below.
[12] MDG 2010 report, APRM Country Review Report No.11, June 2009
[13] MDG 2010 report
[14] Freedom House Country Report Mozambique 2010
[15] Mozambique, Balancing Development, Politics and Security- Jeremy Astill-Brown & Markus Weimer May 2010. p16
[16] In the 2009 Presidential elections Afonso Dhlakama gained 14.9% of the vote. First-time independent contender Daviz Simango won 8.8%. RENAMO holds 51 seats in the National Assembly to FRELIMO’s 191, and MDM’s 8.
[17] Interview with Secretary of Parliament 25.10.10
[18] Afrobarometer Working Paper 91 “Uncritical Citizenship in a low information society” R. Mattes C. Shenga 2007
[19] Uncritical Citizenship supra.

Appraisal Case

A. Determining Critical Success Criteria (CSC) / Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / 1 Levels of knowledge amongst women, youth and men about democratic principles increase 4 / 2 The media continues to hold government to account and provide balanced information to the population 5 / 3 Democratic processes include the active participation of women and young people 5 / 4 Political parties engage in dialogue with each other and with citizens 4 / 5 More Information is available and accessible to enable citizens and civil society to hold government to account 5 / 6 Oversight fora and government are willing to listen to the views of the population presented through appropriate channels 4
B. Feasible options / The research and analysis conducted in order to define the programme identified two main feasible options for advancing a programme to strengthen democratic institutions. Option 1 was rejected for reasons discussed in the Appraisal Case. / Option 1 / Option 1 is what might be called a conventional approach, focusing on formal institutions and designing activities and assistance which would help them develop institutionally. This would be done through increasing technical and management capacity to help them to fulfil their constitutional mandate. Obvious partners for such an approach could include Parliament, the National Elections Commission, other constitutional bodies, media regulators, and, as has been the case in Mozambique in the past, political parties. / Such a programme would usually be based in Maputo, be relatively neat to manage, and require institutional commitment, at the right level, to the changes desired. Mere agreement to activities and inputs would not be sufficient. In other words, significant political will is needed to move this kind of project along. It is the clear conclusion of the research and analysis conducted that this level of commitment is lacking in Mozambique at the moment. / Taking account of the democratic crossroads at which it is generally agreed Mozambique now stands, to take a formal institutional approach would likely have the effect of bolstering, in fact or appearance, the very top-down, centralised approach which needs to change. It would therefore be necessary to select organisations carefully to ensure that the programme did not strengthen organisations already captured by the ruling party elite. / The media is identified by Mozambican respondents in AfroBarometer research (2008) as playing a critical role in holding leaders accountable, indeed, the private media has worked hard to maintain this position. It is a natural partner in improving mass communication, and an informal approach to democratic strengthening would be weakened if the media were left out. However, traditional training and capacity-building activities have done little to strengthen the position of private media[20], and so an innovative approach is needed if the programme engages with the media in order to make a difference. / Elections are of course a core democratic process, and in the case of Mozambique, they have consistently drawn criticism from independent observers for the lack of a level playing field. There is an ongoing debate around reform, but the key challenges centre around the same issues which affect the conventional approach to democratic institution strengthening. However, through promoting lower level dialogue and co-operation, there are opportunities at a lower administrative level to positively affect this process. (see political appraisal Annex). / These two areas, media and elections, are critical areas to address in the context of deepening democratic culture, but as stand-alone approaches are unlikely to have much overall impact. Alone therefore they do not represent a feasible option. However, they are important components to include in a programme, whether formal, or otherwise. / Option 2 / The second feasible option is one which takes a more informal, process approach. It focuses on an informal institution, or process, of democracy, communication and dialogue. This in turn fosters true participation and accountability. In response to the available analysis and learning, a bottom-up, not top-down, approach is signalled, which is also consistent with avoiding the central-level institutional approaches which have had little impact. The municipal level therefore offers a window of opportunity. Given the rapid urbanisation which Mozambique is experiencing, an urban municipal focus offers greater economy of scale than a much more stretched rural-based programme. / Based on consideration of the available evidence and the options outlined above, the programme is designed to encompass the possibilities for progress identified in the overall analysis. This option is innovative in taking an approach that looks outside a conventional democratic institution-building approach, to find the incentives that are at play which may result in deepening a democratic culture in Mozambique. This has led to a focus at the municipal level. In urban centres poverty and populations are growing, with women and young people the most vulnerable. At this level it is possible for information to flow far more freely. Recent experience shows that significant political shifts can occur in urban areas, balancing the playing field in terms of political power. This setting has also proved to be a flashpoint for frustrations, and it is therefore also significant in terms of managing potential conflict. / Local level facilitators, who are directly supported by the programme, will stimulate and support an ongoing inclusive process of information-sharing, analysis, discussion, prioritisation and action to solve local problems. As a foundation for this process, they will ensure that information is available and accessible to more people so that women, young people and men better understand the possibilities and limitations of democracy particularly at the municipal level. Using the information, they will facilitate processes to bring people together, building coalitions of interest around real issues to advance reform and solve problems. The emphasis on an inclusive approach, bringing together local decision-makers and citizens in a constructive effort, so shifting the current approach to decision-making from one that is top-down, to bottom-up. Combining this approach with supporting the development of a more vibrant and informed media and broader policy debate contribute to the change in attitude which is sought. / The main challenge to a vibrant democracy in Mozambique is political. This also points to the need for the proposed programme to play an active role in stimulating a vibrant policy debate, at the local and national levels. This needs to be supported by communication strategies which include diverse media and actors, especially the Mozambican youth. For this reason, the communication process at the core of the programme needs to include the central level. / Donor-supported activity at the decentralised level of government[21] is mainly geared towards building the local administrative capacity to manage, and respond. This presents an important opportunity for collaboration. If a core part of awareness-raising is to clarify what municipal governments can and cannot do, the next step will be that they are seen to take genuine steps towards fulfilling their mandate. / Approach to Change / The programme approach is based on the premise, derived from the analysis of governance programmes and the political economy of reform in Mozambique, that (formal) democratic institutions have little incentive to become more proactive in promoting the rights and freedoms of citizens as provided for in the national Constitution. Without being held accountable for their actions and omissions these institutions are unlikely to change. For accountability to really take hold, there needs to be effective demand from society, and the demand needs to be listened to. The proposed approach is rooted in learning from both Mozambique and beyond. For example, through analysis of the lack of progress on electoral processes, as evidenced by persistently unsatisfactory elections, which Tollenaere (2006:89) concludes is a trend that demonstrates that electoral support, which has largely focused on conventional institutional support, has been unsuccessful. / At the municipal level processes and institutions of democracy are to a large extent a mirror of the national, Maputo, level, but there are more opportunities for the direct participation of citizens. Importantly, civil society groupings can run for election to the municipal assembly. In a municipal context, there is more connection, and a greater chance of accountability between communities and leaders[22]. / There is no indication that support for institutional capacity building of political parties contributes to a more robust democracy. Local elections appear to provide better opportunities for strengthening opposition parties. Here, there is an incentive for parties to win elections, and local elections afford a little more space for this competition. As donors have not paid much attention to this level there appears to be an opportunity for strengthening democracy based on political spaces at the local level, namely, the municipalities. / Civil society organisations are fragile, however further developing their capacity, independence and rigour, together with defending and expanding the political space in which the media operates, will be critical to strengthening political institutions. Civil society and the media play an important accountability role. Importantly, civil society does includes a range of non-governmental associations and groups, including faith-based groups, which are influential at the community level, as well as registered NGOs. / Although the Assembly of the Republic is an important arena for representing the interests of the electorate, and despite its role of monitoring the actions of the government, there appears to be weak institutional commitment to exercising robust scrutiny. There is little meaningful connection between the electorate and their nationally-elected leaders[23]. Yet Mozambicans are at the same time uncritical of, and dissatisfied with democracy (and how it delivers basic services)[24]. The September 2010 rioting due to price increases was a graphic demonstration of this disconnect as well as the levels of frustration in poor urban communities. / As a result of this lack of progress and the institutionalised resistance to deepening democracy at the central level, the programme takes an approach which seeks to build where there are greater incentives for deepening democracy. This opportunity exists at the municipal level, as identified for example in Options for the DFID programme of support to democratic institutions, November 19 2010, Macuane, Salimo, Weimer, and supported strongly both in the findings of the AfroBarometer Survey of 2008, and the IDS/AustralCowi Baseline Survey to Monitor change in the Local Political Environment in Mozambique, January 2010. DFID experience of funding governance and fragile states further reinforces this approach: “Tying accountability to service delivery provides a clearer focus for governance. It provides an entry point for understanding how citizens and the state interact. Citizens are generally perceived in three ways: as clients for service delivery; through civil society, as implementers of services; and citizens as active participants in formulating and monitoring service delivery policy. This last role is the least developed, but is perhaps the most important for ensuring quality and equitable service delivery in developing countries[25].” This conclusion directly mirrors the citizen participation ladder measurement employed to assess progress at the Purpose level (see Annex 1 Logframe). / The key findings summarised by the Briefing Note: What Really Works? Lessons from 10 years of DFID-funded Research on Governance and Fragile States (2010) are completely at one with the proposed programme approach: / Recognising public services as rights contributes to collective action by social actors / Involving citizens in the formulation of policy improves the outcomes and the likelihood of accountability in the provision of public goods / Networks are important, linking poor people with intermediary and national policy actors / Bureaucracies and donors themselves need to change in order to support citizen engagement in policy processes / The body of evidence gathered in exploring the approach to be adopted is significant, given the geographical and political context and the subject matter. The annexes to this document contain more detail on commissioned research and analysis of the evidence base. / Option Evidence rating Climate change and environment category (A, B, C, D) / 1 Medium C / 2 Medium C
C. Appraisal of options / During July/August 2010, DFID conducted a scoping study to gauge the effectiveness of donor contributions to the area of governance in Mozambique, and point to realistic points of entry for strengthening the democratic environment in terms of democratic institutions. A second phase of work in October/November concentrated on validation of the findings of the scoping study and carrying out further targeted stakeholder interviews, in particular in the provinces of the country. In the course of these stages, the team interviewed members of all political parties in the Assembly of the Republic, as well as those who were not elected. Officers and leaders in the municipalities gave their views, as well as national and municipal level civil society actors and consortia, including women leaders. Representatives of the private sector and academia also gave their insights and priorities, and media practitioners were interviewed in both phases, as were representatives of the National Commission on Elections. / CSC 1: Levels of knowledge amongst women, youth and men about democratic principles increase / There is evidence (for example, Afrobarometer 2008) that there is generally a very low level of knowledge about civic rights, policies and the democratic system in Mozambique. The lack of demand for democracy was identified through the design phase to be a major barrier to increasing accountability. / The National Election Commission, Comision Nacional Electoiral (CNE), and the technical elections agency (STAE) are the most obvious formal entry point for the type of traditional civil and voter education proposed by Option 1. According to interviews conducted during the design process, the Director of STAE was very enthusiastic about receiving support to target young and first time voters. The electoral authority already has a structure at the provincial and local level. However, studies have also highlighted the failure of traditional civil and voter education initiatives to “promote participation of Mozambicans in the exercise of their citizenship rights” (see Annex 7 – Civil and Voter Education). / Option 2 proposes that increasing citizens’ knowledge about democratic processes is undertaken through a combination of national debate and practical involvement of citizens with issues. This is a new approach in Mozambique, and so evidence is limited. This approach would enable bringing together local groups to address issues such as voter registration. Option 2 could therefore engage STAE and CNE in voter education at the municipal level through these issues (thus building on their openness and staffing reach). Lessons learnt through this process could be fed back to the central level. However, this approach would not address institutional weaknesses in CNE and (to a lesser extent) STAE and would limit the number of people covered by the initiative nationally. / CSC 2: The media continues to hold government to account and provide balanced information to the population / Press freedom grew considerably after the enactment of the (current) pluralist constitution, but the sustainability of the independent press is still a challenge[26], and, according to the Press Freedom Index 2010, press freedom in Mozambique is decreasing.[27] Access to public information is still problematic and even entities supposed to be open, such as the Parliament, are perceived as still opaque (MISA, 2010).[28] / Both Option 1 and Option 2 would engage with strengthening the operating environment of the media at the central level. Option 1 may also prioritise capacity building support to the media (for example, training of journalists), which has not proved to be effective in the past in Mozambique[29]. Option 2 would look to involve the media in the reporting of issues at the Municipal level, and to provide practical engagement of the media in democratic processes. / CSC 3: Democratic processes include the active participation of women and young people / In Mozambique there is poor representation of women, compared to men, in decision-making processes in general (see Annex 5 - Social Appraisal). There is significant gender disparity in public institutions. Political power and public office continue to be male-dominated, where gender inequality can be seen to be normal. / The population in Mozambique is young, increasingly well-educated and looking to the future. The young are identified as a key emerging actor through the design process (see Annex 5 - Options for the Programme), less affected by the expectations of the old political regime. Youth represents a huge force which needs to be channelled positively. / Both Options 1 and 2 would prioritise women and youth. Option 1 would look to raise government officials awareness, and to influence policy and practice at the central level. This has the potential to reach a wide number of beneficiaries, but there is little motivation for change. The incentives and demand for change are not sufficient to drive the necessary institutional change (see Annex 9 – Political Economy of Democracy in Mozambique). / Option 2 would include a more practical (demand-driven) approach, involving women and the young in democratic processes, and ensuring they have a greater awareness of their rights. Lessons from this practical experience would be fed to the centre through the policy engagement part of the programme. / CSC 4: Political parties engage in dialogue with each other and with citizens / As a result of programmes run by the international organisations that support political parties, some parties have been able to develop their political programmes and leadership skills in communicating their political platforms. However, this has not resulted in electoral success. The emergence of various ‘new’ parties has been due essentially to financial, rather than political motivation. This cannot be considered democratic progress. Previous experiences in Mozambique with strengthening political parties ‘are not encouraging, but these actors are still important for the democratisation process. Thus, the approach should be different and more conditional’ (Annex 5). / Option 1 would engage with political parties at the central level, and involve the provision of training and technical advice to these political parties. This is the approach that has been adopted by previous programmes. EISA (an Africa-based international NGO) is also piloting this approach at present. Option 1 would risk being as ineffective as previous efforts in this area in Mozambique and also would duplicate the work of others better placed to intervene centrally. / Option 2 would engage political parties in discussions at the Municipal level. This would try to strengthen the connection between people and their parliamentarians: at the municipal and national level. It would also try to a foster issues-based dialogue in Municipal Assemblies, which are considered less closed to outside support (see Annex 9). / CSC 5: More Information is available and accessible to enable citizens and civil society to hold government to account / Despite constitutional guarantees of press freedom and access to information there are still many problems. According to MISA-Mozambique, "press freedom is still something foreign for most local government authorities. Abuse of power and the intimidation of journalists by district administrators and judicial authorities continue to threaten press freedom in many of the country's provinces"[30]. These concerns led to a draft Law on the Right to Information being submitted to the Assembly of the Republic in 2006 by MISA and other NGOs. There has been no debate on this draft since. In 2009 journalist associations prepared a document containing recommendations on changes to the Press Law that was submitted to the government but received no reply. / Both Options would look to make more information available to policy makers and civil society organisations. Option 1 would also look to engage in the legislative framework to try to progress Freedom of Information legislation and ensure there is no back-slide on press laws. This would be done by advocacy and awareness raising among parliamentarians and senior officials. This approach did not enable MISA to achieve lasting change, but there is evidence that their efforts were not sufficiently inclusive. / Option 2 would look to improve the flow of information, especially within target municipalities. This option would encourage coalitions to explore issues and help them gain access to the information that exists on those issues – or to help them generate information (for example on service quality). This option would also aim to link the media to these coalitions to ensure that information is available more widely. A central part of the programme will aim to link such information with policy makers, and will have resources to encourage policy focused research (through a challenge fund). / CSC 6: Oversight fora and government are willing to listen to the views of the population presented through appropriate channels / Assistance has been provided to the Mozambican Parliament since the 1990s but this body still faces serious capacity problems. It is considered to be a closed organisation, unwelcoming of external ‘interference’. With a FELIMO majority of more than 75%, the incentives for the parliament to provide serious scrutiny are limited. Thus the parliament frequently does little more than rubber stamp the output of the Executive. / Option 1 would propose raising the knowledge and skill levels of parliamentarians and parliamentary officials to undertake their roles. Given the current political economy of Mozambique (see Annex 9), this is not likely to prove any more effective than previous efforts in this area. / However, the Municipal areas ‘have been a space for local democratisation and there is evidence that some of them perform relatively better in public service delivery than the [central government] deconcentrated structures’ (AMODE et al, 2010). According to the analysis of options for this programme ‘the possibilities of civic participation in municipal elections opens up an opportunity for a bigger participation of non-state actors in municipal governance, which can consequently further democracy in the country’ (see Annex 5). The municipalities offer a major opportunity, however largely neglected[31], for governance and democratisation interventions. Given their legal-institutional framework, the municipalities function as a local arena for the engagement in the local state by local citizens (as clients, voters, taxpayers), and by implication, between the local and the central level of government (see Annex 5). Option 2 will look to focus on the Municipal Assemblies as entry points where real change can occur. / Cost Comparison / A cost benefit analysis is included in Annex 2. This sets out the costs and returns of the preferred Option 2. Option 1, with its focus on institutional strengthening and capacity development, would probably be the cheaper option to implement. The focus would be on the Maputo, and on technical assistance. Option 2 would have a presence in at least 5 municipalities, and given Mozambique’s poor infrastructure and high transport costs, this will add significantly to the overall level of finance required. Option 2 would also require a central presence to manage and coordinate the programme and to work with on improving the operating environment for the media and information flows. / However, the research done for the design of this programme suggests that Option 1, though potentially cheaper, is less likely to deliver Value for Money because of the lesser likelihood of it delivering results and sustainable change. The Economic Appraisal concluded that, in relation to Option 2: ‘The empirical results [of the economic analysis] demonstrated that the proposed Programme may be expected to produce significantly positive net economic returns under the reasonable and conservative assumptions examined ... Net economic benefits of the Programme under the proposed option are expected to exceed those of other possible options’. / Further appraisal information is available in the annexes: / Annex 2 & 3: Economic Appraisal / Annex 4: Value for Money Analysis / Annex 5: DFID options for engagement / Annex 6: Media assessment / Annex 7: Civic and Voter Education assessment / Annex 8: Overview of donor funding / Annex 9: Political Economy of Democratisation in Mozambique / Annex 10: Political Appraisal / Annex 11: Institutional Appraisal / Annex 12: Social Appraisal
D. Comparison of options / The same weighting is used as for CSC above. The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention. / Analysis of options against Critical Success Criteria (CSC) / Option 1 Option 2 / CSC Description Weight (1-5) Score / (1-5) Weighted Score Score Weighted Score / 1 Levels of knowledge amongst women, youth and men about democratic principles increase 5 3 15 3 15 / 2 The media continues to hold government to account and provide balanced information to the population 5 3 15 4 20 / 3 Democratic processes include the active participation of women and young people 4 2 8 3 12 / 4 Political parties engage in dialogue with each other and with citizens 5 2 10 4 20 / 5 More Information is available and accessible to enable citizens and civil society to hold government to account 5 3 15 4 20 / 6 Oversight fora and government are willing to listen to the views of the population presented through appropriate channels 3 2 6 4 12 / Totals 15 69 25 99
E. Measures to be used or developed to assess value for money / In relation to the outputs in the logframe, value for money can be assessed, in the medium to long term as follows: / Output 1 – Enhanced knowledge of democratic principles by citizens (Women, men and youth) in target Municipalities / Direct Result Potential Areas of VfM / Increased knowledge of democratic principles. e.g. roles and responsibilities of municipal institutions, leadership, equity, citizen’s responsibilities, municipal finances etc… Greater transparency in municipal governance; / More effective and efficient use of municipal resources; / Increased responsibility and mutual accountability; / Reduced corruption; / Citizens better prepared to express to government their needs and preferences for public services and public policy – especially women and youth; / Municipal services more responsive to citizens’ needs – especially women and youth etc… / Output 2 – Private (non-state) media have improved professional standards and greater financial sustainability / Direct Result Potential Areas of VfM / Higher professional standards of the independent media; / Greater financial sustainability. More financially resilient and professional media; / Greater transparency in municipal governance through media monitoring; / Citizens demand more technically efficient government activities (more output for a given amount of spending); / More effective and efficient use of municipal resources / Increased responsibility and mutual accountability; Reduced corruption; / Municipal services more responsive to citizen’s needs – especially women and youth. / Output 3 – Strengthened democratic decision making processes in target municipalities / Direct Result Potential Areas of VfM / Citizens’ “voice” taken into account in decision making in municipal institutions; / The needs of women and youth are considered in municipal, planning, budgeting and decision making fora; / The practice of participatory budgeting and planning which is beginning in some urban locations will be strengthened. Greater transparency and accountability in decision making; / Services which correspond more efficiently and effectively to citizens’ needs; / Increased scrutiny in the allocation and use of public resources and finances; / Municipal government elected leaders more responsive to citizens’ expressed needs and preferences. / Output 4 - Enhanced electoral processes in target municipalities / Direct Result Potential Areas of VfM / Voter registration and election process is free and fair; / Candidates for political office reflect profile of citizenry, especially gender; / Elected officials are more accountable to voters. Selection of competent and effective local politicians has an influence on the quality of legislation, policy and the delivery of municipal services; / Increased transparency and accountability in the management of municipal affairs; / Reduced likelihood of urban social unrest that could otherwise arise from growing economic inequality. / Output 5 – Communications and advocacy strategy for disseminating and sharing practical experience with municipalities, national research and policy institutions as well as other interested parties / Direct Result Potential Areas of VfM / Positive and negative experience of local democratic governance is accessible to other non-target municipalities as well as legislators and policy makers at a national level. The experience of the project could be incorporated into legislation, policy and practice in all municipalities which could improve effectiveness and efficiency; / There exists the potential for a multiplier effect to other non-target municipalities; / Reduced likelihood of nationwide social unrest that could otherwise arise from growing economic inequality. / During the Inception Phase of the programme (see Management Case), the baseline study will be used to identify more specific quantifiable VFM measures of direct relevance to the programme target sites. This may include quantifying and establishing baselines for some of the above indicator areas. This will allow progress on these areas to be measured in a quantifiable way during programme implementation. / The Economic Appraisal undertaken in the design phase concluded that ‘The proposed Democratic Governance Support Programme appears to have been optimally designed to maximise net economic benefits, and it should return good value-for-money, as assessed according to DFID’s standards for Economic Appraisals.’ / By the end of the programme, the Economic Appraisal has estimated that the programme would generate a modest Net Present Value (NPV) of £1.002 million (for a 13.1 percent net return) at the end of the five-year implementation period, and a quite respectable NPV of £4.807 million (for a net return of 62.9 percent) after a further five years. These results are gained from achieving more democratically-responsive municipal expenditure (Annex 3 Economic Appraisal, Table 2).
[20] Annex 8, A review of past and present support to democracy in Mozambique: Macuane, Salimo, Weimer; October 2010
[21] Annex 8, A review of past and present support to democracy in Mozambique: Macuane, Salimo, Weimer; October 2010
[22] IDS AustralCowi Baseline Study to Monitor Change in the Local Political Environment January 2010
[23] AfroBarometer; IDS/AustralCowi Baseline Survey to Monitor change in the Local Political Environment in Mozambique. January 2010; President Guebuza
[24] Uncritical citizens; AfroBarometer last round; IDS/AustralCowi Baseline Survey to Monitor change in the Local Political Environment in Mozambique. January 2010; CH
[25] What Really Works? DFID Briefing Note July 9 2010
[26] Mozambique Media Sustainability Index 2008, acedido no site: http://www.irex.org/system/files/2-Africa_08_mozam.pdf, no dia 05 de Novembro de 2010.
[27] http://en.rsf.org/press-freedom-index-2010,1034.html
[28] MISA (2010). Government Secrecy In an Information Age: A Report on Open and Secretive Institutions in Southern Africa. Windhoek: MISA Regional Secretariat.
[29] See the Africa Media Development Initiative reports, BBC World Service Trust and partners (2006).
[30] As 3
[31] At present only five bilateral donors , namely Germany, Spain, Austria, Denmark, , and Switzerland provide support to less than half of all Mozambican municipalities, the latter three donors through a pool funding arrangement

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / A tender process will be necessary to identify an implementing partner for this programme. DFID will undertake a direct commercial procurement process through the OJEU procedure to select this implementing partner. The implementing partner will then establish a Management Unit to run the programme. / The Management Unit may be selected from the private sector or civil society. It must include both appropriate knowledge and understanding of Mozambique with relevant international comparative experience in community-led approaches to promoting inclusive dialogue and policy formulation (including conflict management). It must also have demonstrated expertise and understanding of the media and policy areas reflected in the project. This may be through the forming of consortia, and/or its proposed key personnel. It will be critical that the project manager demonstrates sound influencing and consensus-building skills, to be able to manage constructively, if necessary, issues arising from the project, which may provoke political sensitivities. / The implementing partner will be tasked to identify and resolve contracting issues for the range of indirect procurement requirements under this programme, which will include: / Establishment of a challenge fund for media organisations; / Establishment of contracts with local service providers in the selected Municipalities; / Establishment of a contract with an independent organisation to conduct the baseline study, mid-term review and evaluation.
B. How does the intervention design use competition to drive commercial advantage for DFID? / The contract will be based on a Terms of Reference. This will be structured around the programme’s five outputs, and the results to be achieved in each area. Bidders will be provided with a set of design documents, which sets out DFID’s analysis and parameters for implementation. / Bidders will be required to provide explanations of their prospective approach to addressing several issues in bids. This will drive a competitive approach to providing value for money, and ensuring that a technically competent implementing partner is selected. These will include: / Monitoring and Evaluation: The development of the monitoring system, the need for a rapid baseline study and an independent approach to review and evaluation are critical elements of the programme management in the inception phase. Implementing partners will need to build on design recommendations to propose a credible approach. / Selection of partners and funding relationships with implementers at the Municipal level: A relatively light management structure is the aim, with the project implemented at municipal level by local partners. There are different options as to how this implementation can occur most effectively. The proposals will need to identify whether different Municipal partners will be used in different locations or whether an alternative approach will be used. It will also be necessary to identify how the right blend of capacity, experience, access and credibility to directly implement the project will be ensured. / Making links between the municipal and central level: The programme will operate at the Municipal level and at the central policy level. Ensuring that the work at these two levels is mutually reinforcing and aimed at enhancing voice and accountability is a critical element that will need to be described in proposals. / Minimising political risks: As described in the appraisal section and the political economy analysis, there are risks associated with the development of coalitions advocating for change. The proposals will need to consider how to minimise this potentially negative risk. / Bidders tendering for the Management Unit contract will be expected to prepare a budget proposal based on the indicative outputs and activities proposed for the full project period (see log frame). / The Terms of Reference will define the main functional activities and deliverables of the Management Unit and will provide an indication of the level of annual financial support to the three limbs of the project. These estimates will be provided to inform the preparation of proposed budgets by bidders. They will however be subject to change during the course of the project.
C. How do we expect the market place will respond to this opportunity? / We expect that a consortium of organisations will form to ensure that the implementer has the necessary experience and knowledge, in both geographical and technical areas, to implement the programme. We would expect that a Mozambique-based civil society organisation would form part of the consortium, together with a development research body. / The necessity for the implementing partner to be able to work in Portuguese will place limitations on the number of respondents. However, we expect that a sufficient number of firms will be interested in forming consortia and bidding for this programme to ensure a competitive process.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / The funds for this programme will be channelled through an implementing partner. The costs of staffing and running the Management Unit will be a significant element of programme costs. To ensure the Management Unit functions efficiently, it will have a target of spending less than 20% of programme funds on administration costs. Although this is higher than the regional average for civil society support programmes (of around 16%, based on research by DFID Uganda) it is considerably lower than the more than 30% administration costs incurred by DFID’s Civil Society Support Mechanism (CSSM) between 2008 and 2009. / In addition, the Management Unit is conceived as a small and flexible unit able to deliver good Value for Money[32]. Its role is to manage for results, but the approach is to stimulate, facilitate and aggregate, rather than implement over the long term. The function of the Management Unit is to manage monitor, co-ordinate and support the implementation of the three project components. It will be most practical that this unit is based in Maputo, although it will need to have outreach to the municipalities where the project is situated. / Mozambique’s poor infrastructure, large size and limited capacity of government and civil society at the municipal level will mean administration costs are higher than the sub-Saharan regional average. While this is not a national project with activities throughout every province, it is nevertheless relatively ambitious geographically in that it will have a presence in the southern, central and northern regions of Mozambique. Travel and the costs associated with working with local partners will therefore also be a significant part of the programme. / Costs will be monitored by the Management Committee and by DFID Mozambique. DFID Mozambique has experience of monitoring the Civil Society Support Mechanism, and through the process of trying to reduce costs in this programme has gained experience that is relevant to DGSP.
E. What is the intended Procurement Process to support contract award? / The value of this procurement is over the threshold of the EU Public Procurement Directives, and so DFID is required to advertise in the Official Journal of the European Union (OJEU).
F. How will contract & supplier performance be managed through the life of the intervention? / Within DFID Mozambique, the programme will be managed by the Senior Programme Officer and a Governance Adviser (lead adviser) providing technical oversight. Both will be members of the Management Committee comprising contributing partners, non-contributing partners funding democratization through other channels, eminent Mozambicans and resource persons. The Management Committee will oversee the development and management of programme components. It will monitor technical and financial performance. / An independent organisation will undertake a mid-term review and final evaluation, and will be responsible for the baseline study. This will provide information on the indicators of performance detailed in the log-frame, which will enable the Management Committee to assess performance against results. / The mid-term evaluation will provide a decision-point on the continuation of the contract, and on possible extension beyond the anticipated end date.
[32] See VFM report and the anticipated benefits, as a result of the overall project investment, at the municipal level.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / As stated in the Direct Procurement (a) section, the implementing partner will be tasked to identify and resolve contracting issues for the range of indirect procurement requirements, which will include: / Establishment of a challenge fund for media organisations and policy advocacy work; / Establishment of contracts with local service providers in the selected Municipalities; / Establishment of a contract with an independent organisation to conduct the baseline study, mid-term review and evaluation. / The Challenge Fund that will be administered by the Management Unit will be a competitive process of providing grants to the best proposals from media organisations and other entities submitting innovative proposals to advance policy advocacy work in support of Output 5. Care will be taken to avoid creating short term subsidies which do not contribute to innovation, and which in the case of media organisations, strengthens the institution, rather than creates dependencies. In designing the operation of the fund, the criteria should give preference to: / a formal partnership between the media outlet and at least one non-media organisation, preferably a public body or municipal structure (media) / projects which generate some income or in-kind services from a commercial partner (e.g. commission fees from mobile companies, or partnership with advertisers) (media) / projects where the targeting of the audience specifies, gender mainstreaming and access using indigenous languages (media) / projects which begin to institutionalise a process of information-sharing and debate (media) / Awards should be made on a quarterly basis, based on independent assessments by a group of three experts, two of which should not be media specialists. / The local CSOs that are expected to be used to implement the programme within the municipalities will need to be contracted by the implementing partner. / The Management Unit will also need to contract an independent organisation to conduct the baseline study and subsequent evaluations. This will need to be done in such a way that the evaluator remains independent of the implementing structure to allow for critical appraisal.
B. Value for money through procurement / The Challenge Fund will offer value for money through it’s competitive nature. It will be designed in a way that: / enables a competitive and open process to identify and fund innovation around communications, especially combinations of traditional (print, electronic) and new media (internet, mobile telephony platforms). The latter is important in part because this is a source a large consumer spending power, and can target key constituencies such as youth and women. / includes funding criteria which to require project activities to be embedded with local ownership (government and citizens) / triggers or encourage co-investments from the media or other private sector player (e.g. mobile providers, via advertising) and so improve sustainability and encourage media operators to develop commercial marketing approaches

Financial Case

A. How much it will cost / The total cost of this programme will be £10 million over 5 years. £150,000 has been spent on the underpinning analysis and design of the programme, and on ensuring the critical issues of Value for Money and gender issues are sufficiently understood and used to inform the programme design. / The remaining £9.85 million will be used for programme implementation. The spend profile is expected to be: / 2011/12 2012/13 2013/14 2014/15 2015/16 2016/17 / £750,000 £1,750,000 £2,000,000 £2,250,000 £2,250,000 £850,000 / Provision has been made in the DFID Mozambique budget for £6.75 million between 2011 and 2015 (according to the profile above). This means that a further £3.25 million will be required from DFID’s subsequent budget allocation. / The breakdown of the budget across the programme outputs is estimated to be as followed: / Project Outputs Estimated budget (£) / Output 1: 1,300,000 / Output 2: 1,500,000 / Output 3: 2,000,000 / Output 4: 1,300,000 / Output 5: 1,500,000 / Subtotal 7,600,000 / Programme Management Unit 1,900,000 / Baseline & Evaluation 300,000 / Monitoring – DFID 50,000 / Total 9,850,000 / £50,000 is included to allow DFID Mozambique to undertake monitoring and related analytical work that will inform the management of the programme. A separate line is included to allow the contracting of an independent organisation to undertake the evaluation of the programme. / Other development partners have expressed interest to join the DFID programme however, the details of their commitments are still to be defined. Any funding made available by other donors would allow DFID Mozambique to a) reduce the funds needed in outer-years or b) expand the geographical coverage of the programme.
B. How it will be funded: capital/programme/admin / The full funding for this programme will come from DFID Mozambique’s programme resource allocation.
C. How funds will be paid out / A single contract will be signed between DFID and the appointed service provider. Funding tranches will be agreed with the service provider but are expected to be paid quarterly in arrears. / The DFID Governance and Accountability Team Leader or an appointed member of the Team will authorise payments on the basis of signed financial statements accounting for previous tranches.
D. How expenditure will be monitored, reported, and accounted for / The Management Unit will be responsible for establishing and maintaining accounting systems for / income received from DFID (and any other donor contribution) / expenditure on sub contracts / funds granted under the challenge funds / expenditure on activities directly arranged or implemented by the Management Unit (e.g. exchange visits, publicity campaigns) / expenditure on operation of Management Unit facility (office, staff, transport etc) / The Management Unit will be responsible for ensuring adequate arrangements for / Accounting for grants made under the challenge funds / Sub contractees accounting for delivery of any services rendered under the programme / The Management Unit will procure independent external financial audits on an annual basis. The ToRs and appointment of the auditor will be approved by the MC. External audits may include audits of recipients of challenge fund triggered by failure to meet criteria established by the Management Unit when approving funding. The Management Unit will present for approval by the Management Committee, the balance sheet, audited accounts and estimates of income and expenditure for the ensuing year. / DFID as Lead Donor will ensure that the Management Unit and Management Committee fulfil their respective roles and obligations with regard to financial reporting and audit and ensure that proper accounting procedures and controls are in place for programme income, expenditures and securities and that all payments and expenditures are documentarily accounted for by way of cash receipts or otherwise.

Management Case

A. Oversight / There will be a Management Committee (MC) to which the Management Unit will report. The MC will meet quarterly. Its purpose is to provide oversight of the programme. As such it will review and approve the annual work plan and will review programme and financial performance. This body will comprise: donor agency representatives[33], civil society representatives, and people independent from, but with an understanding of, government. Through this mechanism, we will ensure that there is stakeholder voice in the management of the programme. Representatives will be paid to attend (if not mandated by an organisation to do so). It will be chaired in the first year by DFID and thereafter the chair will be by election. DFID will retain responsibility for the contractual relationship with the Management Unit, and the TORs for the Management Committee will contain a “force majeure” type clause, which DFID can invoke in extreme circumstances when contractual imperatives are at odds with an Management Committee decision. / Given the potentially sensitive nature of this programme, it is recommended that a separate Advisory Committee (AC) be established. This organ will be responsible for advising on overall policy direction and strategic positioning, but it is not intended to be an additional layer of management, nor will it take decisions as to how or where funds are directed. Its composition is important since it will play a key role in building and maintaining the credibility of the programme as well as managing any political risk which may arise. Members will be selected according to objective and transparent criteria, which should include relevant understanding and experience in the fields covered by the project and a reputation for political independence. It will include women and men who are respected figures and who demonstrate a sound understanding and analysis of democracy and governance in Mozambique, at the same time as having, jointly, access to the different political factions in Mozambique. Their role will be advisory as well as consensus-building. / The Advisory Committee does not represent a significant financial investment, but, given the right composition, will be an invaluable resource. It can help to manage risk, provide sage political guidance, and be an effective advocate for the project and its aims. Members of the Advisory Committee shall have the costs which they incur in attending meetings or other activities, reimbursed. It may be appropriate to pay an honorarium for the time they devote, according to the norm in other similar projects in Mozambique. / Challenge funds are proposed under the project, to stimulate innovation and creativity in the media and policy fields. Criteria for these will be drawn up under the inception phase. The challenge funds should be flexible, allowing applicants to propose innovative concepts. However, this will need to be balanced with management practicalities. It is therefore proposed that decisions in relation to the award of grants be made on a six-monthly basis. The committee for reviewing the proposals will be made up of members of the Management Committee with co-opted members if a specific area of expertise is required. The Management Committee will receive reports on a regular basis from the MU team to monitor implementation under the challenge awards.
B. Management / Within DFID Mozambique, the programme will be managed by the Senior Programme Officer and a Governance Adviser (lead adviser) providing technical oversight. DFID Mozambique’s primary role is to participate in the programme Management Committee, which will oversee the development and management of programme components. DIFD will provide funds earmarked as appropriate for different components of the programme and will participate in joint monitoring of progress with the programme management team. / There will be a small and lightly staffed Management Unit, responsible for the management and operation of the programme. As stated in the Commercial Case, the Management Unit will have a target of spending less than 20% of programme funds on administration costs. The Management Unit will be small and flexible unit able to deliver good Value for Money. Its role is to manage for results, but the approach is to stimulate, facilitate and aggregate, rather than implement over the long term. / The function of the Management Unit is to manage monitor and support the implementation of the three programme components. It will be most practical that this unit is based in Maputo, although it will have outreach through facilitators to the target municipalities. It will have a presence in the southern, central and northern regions of Mozambique. A relatively light management structure is the aim, however initially, to assure quality and consistency of approach, there will be programme staff facilitators in each of the municipal sites. The funding for these facilitators will come from the activity budgets under each output. / The ideal situation with regard to implementation at the municipal level would be to identify strong locally-based partners with the right blend of capacity, experience, access and credibility to directly implement the programme. The design phase suggests that at least in some municipalities, organisations or groups which meet some of these criteria, exist, such as members of the inter-faith Observatorio Eleitoral. However, it is proposed that the most prudent approach will be to identify the right partners during the inception phase. Since the programme will take a tailored approach in each municipality, deciding on the right partner/s for each site will require detailed work and careful consideration, at the time when implementation is planned. It cannot be assumed either that there will just be one partner per site. The programme will avoid picking the reliable ‘usual suspects’ in the registered NGO community, but rather, aim to support legitimate local groups, or groupings, which exist within the target municipalities. The programme will also avoid the common pitfall of picking successful partners, and weakening their capacity through adding too much work, diluting their focus or distorting their priorities. / The Management Unit will employ a small number of professional staff, including a Programme Manager, and administrative and financial support services. The Management Unit will include a publicity and outreach function. It will also provide secretariat support to the Advisory Committee and grant-making activities in the areas of media and public policy. It will undertake monitoring as described elsewhere in the Business Case. / It is proposed that the Programme Manager also play the role of chief technical advisor to the programme, supported by a strong Administrator and Financial manager, together with a Monitoring Expert who will be in charge of lessons learned and communications aspects of the programme. These four individuals will form the core management team and may, at certain stages, commission specific technical assistance for studies, tailor-made training, etc. The chief technical advisor will provide ongoing support and guidance to the municipal facilitators, with a focus on phasing them out as local partners take on their role and acquire, where necessary, the skills which they deploy. / The Management Unit will run the Media Component and the Policy Component directly, including the challenge funds. Extra technical support may be needed to enable these components to function effectively, although this will be defined during the Inception Phase. / It will be the task of a programme facilitator at the municipal level to facilitate a process which brings these stakeholders together, based on mutual interest, to identify and prioritise issues and actions to address them. The programme facilitator will very much be a catalyst for these processes, as well as a channel for appropriate resources to support them. In the early stages s/he will add value through being a part of the programme structure and so conversant with the latest information on progress and challenges experienced across the target sites. This approach will thus also help to ensure that the programme stays on track as a whole, while lessons learned are actively shared between the sites. / As local partners demonstrate the required capacity to manage funds and programme-related planning and reporting, the municipal facilitators who report to the Management Unit will be phased out, their roles fully subsumed by local groups. It is expected that in the target municipalities these staff will not be necessary by the end of the programme. However, given capacity constraints within civil society and in local government, effectiveness and accountability will be better assured through programme staff based at the municipal level as a starting point. / Core strategies of the Democratic Governance Support Programme: / The Management Unit will need to deliver on a number of core areas in the implementation of the programme: promoting gender equity; including youth; building consensus; and improving access to information. / Promoting Gender Equity / A fundamental part of the programme strategy to promote gender equity will be to ensure at every stage the active participation of women, men, youth, and people who are vulnerable. The approach is that priorities in terms of issues will be defined by the communities themselves, rather than determined by the programme, but the process will be facilitated so that issues directly affecting gender are highlighted as part of the overall information and advocacy agenda. The aim is to be fully inclusive, very much building on small local processes and mechanisms, not aiming to create new ones. This approach directly supports the Government’s priority to promote peace and dialogue. / Community-focused discussions are more accessible to women and youth, and can provide an opportunity for them to argue their priorities as well as gaining and developing valuable skills in analysis, discussion and issue prioritisation. The programme will build on this interaction, combined with the support to political parties at the local level as described above, as a possible entry point for discussions leading to gender parity in party lists. Mozambique has exceeded the Southern African Development Community (SADC) minimum quota of 30% gender representation in the National Assembly, but to be really effective, the strategy must be reinforced at every level, including within the party structures of all political parties. At the moment, it is FRELIMO which sets the example. / Including Youth / Mozambique’s young people are increasingly well-educated, have different expectations to their parents and are often disenfranchised through lack of employment, voice and poverty. These people represent a huge force which needs to be channelled positively, and included in policy formulation. The programme will seek to include youth voice at the municipal and national level. / Building consensus - constructive resolution of problems- commitment to non-violent expression / The process of dialogue, consultation, and compromise is a fundamental informal democratic process, which is daily used within very small groups or communities to resolve problems, but rarely includes formal leaders such as members of parliament (MPs) or government officials and very infrequently includes members of municipal assemblies[34]. Therefore the DGSP will aim to include all relevant stakeholders at the municipal level, and particularly, promote the participation of women, the youth and vulnerable community members in this process. It will focus, through facilitation by respected members of the community, on stimulating fora at the community level where officials, political party members, informal community leaders and community members can discuss problems and grievances in a safe and respectful space. Community members will be able to express their grievances, but municipal authorities will also be able to explain the limitations they face, be it in mandate or resources. The process will seek to prioritise issues and place them on the policy agenda for action at the local and, where relevant, national level. / The planned approach is also well-placed to serve as a local mechanism for the early and speedy resolution of complaints and pressures. If left unaddressed, such pressures can lead to outbreaks of violence and conflict, provoking security forces to respond in ways which may exacerbate the problem. This may be a particular risk when the stakes are high due to elections. With this in mind, and with a view to municipal and national elections in 2013 and 2014, the project will incorporate the flexibility to support the local offices of the technical Secretariat for elections administration (STAE) and local party representatives to facilitate inter-party dialogue, as well as to provide targeted technical support in areas including voter education, registration and mobilisation. This will be especially important in urban centres with young populations of many first time voters. / Access to information / Increasing access to information for women, the youth and men will be a key component of the programme. At the municipal level, the dialogue and consensus-building process provides an entry point for communities to better understand democratic processes in a practical way. The project will support strategic and innovative approaches to engage policy makers and enliven the policy debate. The media in its many formats will play a key role in this communication process. At the same time, the project will actively share the lessons it learns as implementation proceeds. / The programme will combine support that expands access to independent and diversified media, with stimulating knowledge through discussion at the community level. This is the level of society which citizens are most likely to seek to access information, articulate and solve problems. / Inception Phase Issues / A number of issues must be resolved during the Inception Phase of 12 months. Successful resolution of these issues will enable the programme to proceed. Thus these issues provide a means of evaluating progress early on in the programme, and enable a decision to be made about whether to proceed or not at the end of the first year. / Issues to be resolved during the Inception Phase will include: / - The Management Unit team (including facilitators) are in place, and possess an appropriate mix of skills and experience. / - An approach to monitoring and evaluation, including the measurement of Value for Money, has been defined and agreed with DFID. / - The focal municipalities have been selected according to agreed criteria and following dialogue with Government and other partners. / - Partner CSOs have been selected in focal municipalities. These organisations have been ‘contracted’ and trained. / - An approach for identifying focal issues at the municipal level has been designed and agreed, and tested, and for engaging diverse organisations at municipal level around identified themes. / - An organisation has been contracted to provide independent evaluation throughout the programme life and has conducted the baseline study. / - A programme name to be used externally has been identified and an identity created. / - An approach to measuring and reviewing political risk in the municipal areas has been defined and agreed with local partners. / - The Management Committee and Advisory Committee have been established and have met at least once to validate decisions listed above. / - Terms of Reference for the annual media study designed and process agreed. / - Management and approach of media and policy grant funds have been agreed with DFID / - Strategy developed for linking learning and experiences across the municipalities / - Strategy developed for channelling municipal demands to national level policy makers (where relevant).
C. Conditionality / Not applicable.
D. Monitoring and Evaluation / One of the responsibilities of the Management Unit will be to oversee and coordinate all monitoring and annual review activities. The programme will be implemented in different locations and by different organisations, therefore, a central coordination mechanism will be needed to ensure a common standard in terms of monitoring and to aggregate data and information which is collected for monitoring purposes. This will need to be the responsibility of a designated person within the Management Unit. Given the number of municipalities covered, there are likely to be successes and failures. Failures need to be identified quickly through the monitoring system, and lessons learnt. Successes need to be analysed for replicability. / The programme will be implemented through agreements with national and possibly international CSOs and media organisations. At the implementation level, partner organisations will be instrumental in monitoring the different components. In addition to supporting monitoring activities, such as surveys, partner organisations should document activities and produce case studies which capture the impact of the programme. / It is important to avoid the risk that citizens and municipal institutions in the target areas are perceived as just suppliers of information to the monitoring and evaluation system. The programme will therefore engage citizens, especially women and youth, and where possible municipal institutions, in participatory analytical initiatives through the different programme activities, which will not only contribute to active citizenship but will greatly enhance the quality of monitoring and evaluation with aspects not captured in the formal monitoring and evaluation system. / MONITORING APPROACH / Whilst the indicators at the goal level can be monitored through verification against the standard international indices, at the outcome and output levels, data collection can be incorporated into the programme activities. In addition to being a mechanism for monitoring progress, the substance of the indicators is also representative of themes which will be addressed during the activities that the programme will facilitate. Monitoring tools will include: / individual and collective interviews; / on-site visits; / focus group discussions; / factual and perception surveys; / participatory analytical tools such as the “ladder of participation”; / case studies; / media monitoring. / Although monitoring is an on-going process, as part of the monitoring function there will also be a need to undertake surveys at regular intervals. A programme of this nature is unlikely to achieve a significant discernable impact in the early years. Impact is likely to be incremental and cumulative and more apparent as the programme progresses, including after it has been implemented. / The Management Committee will review monitoring reports at their quarterly meetings. A framework for monitoring and analysis is presented in the table in Annex 13. / EVALUATION APPROACH / Given the relative lack of relevant and disaggregated (Gender/youth) data at a municipal level, it will be necessary to undertake a baseline survey during the inception phase. This survey will form the bases against which programme monitoring, review and evaluation will be undertaken. Different options exist for this: / Programme partner organisations’ implementation staff undertake the surveys. However, this may present the risk of bias and although it may be a more economic option, it is therefore recommended to adopt the second option below[35]; / Contract an independent team such as the Centre for Policy Analysis at Eduardo Mondlane University (responsible for the Afrobarometer[36]) or the Institute of Development Studies (IDS) team who undertook the Baseline Study to Monitor Change in the Local Political Environment. This team would also take responsibility for the design and implementation of an approach to evaluation, building off the baseline study. This is approach assumed in the Commercial Case section and in the budget. / Taking into account that a programme of this nature is unlikely to generate impact in the short term, the mid-term review will be undertaken at the end of year 3. This will be carried out by the organisation responsible for evaluation. It should identify emerging areas of impact and recommend any changes which may be necessary in the approach to achieve greater impact by the end of the project. In addition, DFID Mozambique will undertake annual reviews through the normal Annual Review process. These will be undertaken with the Management Unit and reviewed by the Management Committee. / It is also recommended that one formal evaluation processes should be undertaken at the end of the fifth year of implementation. This will build on the baseline data. It will be used to inform any decision about follow-up activities, but will have a wider audience. A comprehensive approach to the baseline and evaluation with be developed in the Inception Phase. This will define key evaluation questions and a theory of change (building on what it set out in the Appraisal Case) to be revisited by the evaluation. This will also address issues connected with the scale of an evaluation, such as the need for a control sample, the frequency of data collection and any post-programme evaluation follow-up. / The baseline study, mid-term review and evaluation will be undertaken by the same independent organisation, or consortium, enabling greater objectivity and consistency of approach. Thus responsibility for designing the detailed methodology will be independent to, but contracted by, the Management Unit. / Citizens & Municipal Institutions / National Institutions/Other non target municipalities
E. Risk Assessment / The following matrix identifies key risks and approaches to mitigation of these risks: / Risk Risk assessment Mitigation strategy / likelihood impact / 1) The programme is perceived to be politically threatening to government, the judiciary or other institutions of governance, either directly (by its existence) or indirectly (by association with CSOs supported under the programme Medium to High (depending on location) High Consultation with immediate actors. / Advisory Board selection / DFID/ FCO influencing at Maputo level / Flexibility in programme to accommodate strategic opportunities which arise during the course of the programme / 2) CSO capacity unable to absorb funds and implement activities (AGIR programme) Medium Medium Inception phase clear mapping of which credible CSOs can be effective in the target urban municipalities and how the programme can interlink activities (NOVIB et al supportive of this approach) / Also identify other ‘intermediaries or champions’ / 3) Operational modalities are cumbersome, not cost effective and ineffective in providing intended services Low High Adopt an incremental flexible approach, particularly in the first couple of years, to ensure the programme is responsive to changes in the overall environment, emerging gaps and the needs of CSOs / Ensure clear definition of TORs and an effective procurement process to contract a Management Unit. / Ensure the Management Unit contract is output based and allows flexibility / 4) Officials at the local level are resistant to co-operating with different political parties Medium to High (depends on location) High Local respected mediators – probably religious / Gradual approach / Tailor-made approach for each municipality / Engage politicians at the local level / Advisory Board / 5) Actions attributed to programme strongly identified with a political party being appropriated to “legitimise” or “condemn” government activity Medium to High (depending on issue) Medium Advisory Board / Communications strategy / Political dialogue and ‘influencing’ (DFID/ BHC) / 6) Activities funded by challenge funds (media / policy) being appropriated for political means Low to Medium (depending on activity) Medium A selection panel screens applications against clear assessment criteria including political bias / Selection panel composition carefully defined – objective criteria and perceived political connections / Central level policy informed debate regularly shares information / Communications strategy linked to this / Advisory Board and DFID/ BHC dialogue and ‘influencing’ processes / 7) Programme activities are perceived as creating tension/dissent Medium High Advisory Board and DFID/ BHC dialogue and ‘influencing’ processes / Inclusive nature of fora and dialogue process act to defuse possible tension / Explicit commitment of partners to peaceful approach / Corruption Risk Matrix / The following matrix identifies key risks and mitigation strategies in relation to corruption: / Risk Risk assessment Mitigation strategy / Likelihood Impact / a) Programme-supported CSOs misuse financial support or undertake other corrupt practices Low Medium Establish clear selection processes / Provide support for financial management and internal governance as required. / Establish project monitoring system / b) Implementing bodies (Management Unit, trainers, mentors) misuse funds or engage in other corrupt practices Low High Undertake an effective procurement process for Management Unit. / Ensure supervision and audit arrangements are specified in contractual agreement between donors and the appointed Management Unit. / Project Management Risks/Issues / Project risks are defined as factors outside of the control of DFID. As such, weak management arrangements do not constitute risks. Nonetheless it is recognised that the effectiveness of programme implementation will be dependent upon establishing sound corporate governance and programme management arrangements from the outset. The table below provides an assessment of potential weaknesses in management arrangements and associated measures that will be taken to mitigate them. / Risk Risk assessment Mitigation strategy / likelihood impact / a) Poor Management Unit performance Low High Ensure an effective procurement process with clear MU TORs. / Agree an output based contract with clear breakpoints. / Undertake regular reviews of performance / Retain the right to require changes of approach (based on review findings) and the right to terminate the contract. / b) Management Unit unable to evolve and adapt approach based on learning from implementation experience Low High Undertake an effective procurement process to engage an experienced Management Unit / Adopt an output based contract / Undertake regular (annual) independent reviews / Annual revisions of logframe and workplan required incorporating review findings. / c) Weak contractual management of the Management Unit based on ambiguous donor – Steering Committee /Advisory Board roles and responsibilities Low Medium Define respective roles and responsibilities at the outset. / Ensure clarity between Committee decisions and contractual decisions. / d) Possible splits within Steering Committee /Advisory Board Medium Medium Careful selection of Steering committee and AB representatives / Adopt a consensus based approach to discussion and decision making (without formal votes) / Provide strong leadership of the MC through good procedures for selection of the Chair / Mandate the Advisory Board to help resolve differences of opinion.
F. Results and Benefits Management / The programme will deliver results in all three of the component areas by the end of the programme: / The Municipal Component will raise awareness of citizen’s rights and democratic principles, including around voting and registration. Citizens will be more aware of the roles and responsibilities of government (and its limitations), and how to hold them to account. Government and political parties will be more aware of citizen’s views. Coalitions will have formed around issues that are important to local communities, and these will have stimulated real local change. / The Policy Component will have ensured that issues of concern to citizens are being adequately considered in central dialogues (between government, civil society, parliament, the media and donors, for example). Targeted policy research and case studies from the municipalities will have encouraged debate. Information flows will have been improved, enabling effective dialogue. / The Media Component will have delivered greater financial sustainability to the private sector media, mainly derived through enhanced advertising revenues. Professional standards in all forms of media (from community radio to television) will have been raised. / The outputs of these three components will be mutually reinforcing, and this will enable the programme to improve the democratic environment in Mozambique. / Where possible these results have been described in the attached Logical Framework, which sets out milestones and targets against indicators for the purpose and outputs of this programme.
[33] To include the Head of Cooperation of DFID or designated representatives.
[34] AfroBarometer 2008: around 90% of respondents said never go to formal leaders; around 80% said never go to Municipal Assembly members
[35] This does not preclude the partner staff undertaking surveys as a tool during implementation.
[36] It is recommended that should the Centre for Policy Analysis be used that some professional support should be given to improve their methodology.