Type of Review: Annual Review

Project Title: Bangladesh Education Development Programme

Date started:	11 November 2011	Date review undertaken: 4 November 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
UK is providing up to £120 million over 5 years starting from 2011 FY.

What are the expected results?
The expected results at the end of five year (2011-2016) project period are:

What is the context in which UK support is provided?
Bangladesh, one of the most densely populated countries, is also one of the poorest countries in the world. Its per capita GNI is USD 1529 although several social indicators including gender parity in education, maternal and under-5 mortality rates are better than countries in this income group. Around 80% of the nearly 150 million Bangladesh people still live on less than $2 a day. Chronic malnutrition affects 56% of the poorest children[1]. Over 40% of the country, in an area the size of England and Wales, suffer from natural disasters most years. / Primary education in Bangladesh shows a mixed picture. Average net enrolment rate is 98.7%, with girls doing better than boys. But only 58% children from the lowest quintile enrol in schools. 1 in 3 children drop out before completing primary education and in an average it takes 7.2 years for a child to complete the 5 year primary cycle. Mean maths score of a grade 5 student is 63.26% and it is 68.51% in Bangla, which are way below the 80% targets. / Over 200 million copies of textbooks are printed and distributed every year but an archaic, non-functional teacher training method hampers reforming teaching and learning in classrooms. There is a new national assessment system and a school census to strengthen education management and information system. / 80,000 schools and 400,000 teachers are managed centrally by the Directorate of Primary Education. National Curriculum and Textbooks Board (NCTB) oversee the printing and distribution of textbooks and the National Academy of Primary Education (NAPE) oversee development and implementation of teacher training. However, lack of qualified researchers and trainers stifled innovation and production of quality textbooks and teacher training courses for years. Clearly, there is room for improving quality and equity in Bangladesh primary education.
[1] World Bank study: An Urgent Call for Action: Undernourished Children of South Asia 2009.

## Section A: Detailed Output Scoring

Output 1: Improved quality of teaching and learning / Indicator 2012 Target Status / Proportion of eligible schools receiving textbooks within one month from school opening date 80% schools receive textbooks Achieved / Number of children accessing pre-primary education (PPE) A pre-primary education mapping and a pre-primary education expansion plan is ready Unachieved / Number of teacher recruited and deployed 10,000 teachers Achieved / Number of head teachers and teachers attending training A new Diploma in Education course piloted Achieved
Output 1 score and performance description: SCORE A / All but one indicator targets for this output have been met as of the date of the review. The unmet indicator target is the introduction of pre-primary education. Actions have been taken to ensure that the pre-primary education target is met by December 2012. / Textbooks / Bangladesh prints and distributes over 90 million copies of primary textbooks every year, the largest such exercise in the world. The paper for the textbooks is procured through an international tender managed by the World Bank. The National Curriculum and Textbooks Board (NCTB) manage the printing and distribution through a set of local tenders. The data for demand and supply of textbooks is managed by the Directorate of Primary Education (DPE), who is the executing agency for the programme. / The exercise requires clockwork precision and synchronisation among several agencies internal and external to the government of Bangladesh. To meet the 2012 target the process started in March 2011 with requests to school to place their demand for textbooks. DPE collated the demands and placed a request to the World Bank for paper procurement. At the same time, DPE alerted the NCTB for finalising the manuscripts and the tender documents for printing and distribution. / NCTB floated the tender for printing and distribution. The printers supplied the books to Upazilla education offices by December 2011. Book distribution was monitored by the Department of Primary Education and this is the first time software was used for collating and reporting progress data. A third party validation shared in August 2012 mentioned that 96.8% of students had received books within 31st January and 97.3% students reported that they received new books.”[1] / The quality of the textbooks is assessed every three years through school surveys. Recommendations of the last assessment, done in 2011, have been followed through and a new set of textbooks is ready for printing this year. / Access / Developing a pre-primary education expansion plan was the key action for introducing PPE across the country. Currently around 4000 PPE centres are operational in the country, only 700 of which are run by the government on a pilot basis. The rest of the centres are run by various NGOs. UNICEF is providing technical assistance for developing the expansion plan, which will include a data base of pre-primary service providers, a gaps analysis and recommendations for DPE on identifying ways of working with NGO providers and to introduce PPE in gap areas. The final draft of the plan will be ready by December 2012. / Teacher Recruitment and Training / This is another successful activity this year. A total of 10,000 teachers were recruited following a rigorous selection procedure. The Public Service Commission, who conducts the recruitment, published the list of the new teachers through a Gazette Notification. They also provided the relevant PEDP 3 Working Group with a set of documents including the recruitment advertisements, the question papers and the marking scheme and a sample set of interview cards as evidence of the well run process. However, there was a concern regarding a quota introduced across the public service recruitment for freedom fighters and their children. DPE confirmed that the quota didn’t affect the quality of the candidates selected as no candidate with less than the minimum qualification was selected. Teacher recruitment, along with textbooks printing and distribution, is closely monitored in the national media. The absence of negative reporting in the press also gives confidence about the integrity of the process. / Teacher deployment, however, is an on-going issue in the sector. The last sector programme (PEDP 2) identified this as a major barrier for improving quality of education in Bangladesh. The ministry find it difficult to fill in posts in remote and rural areas. In some areas there were problems of ghost teachers, serious absenteeism and proxy teachers. PEDP 2 successfully piloted an allowance scheme for teachers posted in the hill tracts region and recommended developing a new salary structure and career path for primary school teachers. It is pertinent to mention here that at USD 600 average annual salary, Bangladesh primary teachers are the lowest paid teachers among the countries where DFID support education programmes[2]. The ministry is considering a draft proposal and once approved will send that to relevant ministries for approval. / A new teacher training course has been developed and piloted in 7 training institutes. A team of seven consultants worked at the National Academy for Primary Education (NAPE) developing the new course. The team was provided with additional support on maths and English language from JICA and the DFID supported English in Action project. The piloting, which started last month in 7 institutes, will assess the quality and effectiveness of the courses. The feedback from the pilot will feed into revision of the course module, which will be finalised and rolled out nationwide in 2013. Head teachers, who also teach, attend these courses. There is also separate school management training for head teachers which is held in conjunction with education officer training. / The Quality Working Group, the joint government and DP forum overseeing implementation of this output, has performed well. They met regularly, kept track of the progress of implementation, resolved issues and provided appropriate technical assistance. DPE especially appreciated the TA working on PPE and teacher training. DFID supported English in Action project also provided valuable technical assistance towards developing the English language component of the new teacher training course.
Progress against expected results: / The 2011-12 target for the proportion of eligible schools receiving textbooks within one month from school opening date was 80%. The evidence showed that 86,430 schools and learning centres received full set of textbooks out of 92,222 schools and learning centres. That is about 93% of the total schools. They key evidence considered for this result was the report generated by the textbook distribution and monitoring software developed and installed last year. A third party validation of the distribution also confirmed the achievement. There was also evidence of books were dispatched to the rest 7% of the schools on time but didn’t reach on time. DPE will investigate why those schools didn’t receive books on time and take necessary actions. / The 2011-12 targets for number of children accessing pre-primary education were to prepare an integrated database of PPE provision and an expansion plan. The data base and the plan are expected to be completed by December 2012. / The 2011-12 target, 10,000 teacher recruited, was met. A new teacher training course has been developed and piloted. / Recommendations: / Continue support to the new teacher training course. / Carefully examine the PPE expansion plan to ensure value for money. / Commission a barriers to learning study in order to strategise improvement in learning outcomes. / Impact Weighting (%): 33% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[1] Caveat: “There is no bottom level information to tell whether students of a particular school have received the books anywhere in the system.” P. 4
[2] Draft Minute to Committee of Public Accounts on DFID Education Results and Value for Money. Education Policy Team, October 2012

Output 2: Increased equity in primary education / Indicator 2012 Target Status / Number of new classrooms, toilet and water facilities built 3,000 classrooms, 5,000 toilet blocks and water facilities Unachieved / Number of children accessing non-formal education A non-formal education expansion plan is ready Achieved / Number of school level implementation plan done and approved 40,000 schools received schools level improvement grant Unachieved / School report cards show increased access of the marginalised children Target was not set Unachieved
Output 2 score and performance description: SCORE C / Only one output target, related to expansion of non-formal education, out of four has been met. There is a possibility that a second target, the infrastructure target, will be met by December 2012. Urgent actions have been identified for other targets. / Classroom and Toilet Construction / 10,000 schools, identified last year through a needs assessment exercise, will receive additional classrooms under this programme. Those schools were selected on the basis that those have more than 10 students per classroom and the objective of providing additional classrooms was to reduce the number of children in each classroom. Local Government and Engineering Department (LGED), who are in charge of constructing the classrooms following the prioritised list, have floated tender for 5,766 classrooms in 1,862 schools. / However, the working group overseeing the construction work identified that additional classrooms are being built in a number of schools not prioritised in the list. The issue has been raised with LGED and DPE. In a meeting on 11 November, the ministry has ordered the cessation of all construction work in schools that were not in the prioritised list and agreed to an investigation to be jointly conducted with the donors. The investigation will look into the possibility of data error in the list and will also verify a sample of school sites which were not in the list but received additional classrooms. The investigation will produce a report by the end of December 2012. / Construction of toilet blocks have been stalled as the design hasn’t been finalised yet. There is a standoff between the DPE and the Directorate of Public Health Engineering (DPHE), who are in charge of constructing toilets, regarding the design. DPE felt that the proposed design, fitted with tiles and high maintenance sanitary equipment, is not only expensive but also inappropriate for rural schools. DPE has asked for DP’s assistance in developing a more appropriate design. UNICEF is providing the support. / Non-formal Education / The Ministry wanted to expand their non-formal education strand, targeted towards the out-of-schools children, through this programme. The key action for the expansion was to identify a model of non-formal education that could be scaled up through the government system. There are three non-formal education models operating available in Bangladesh-the BRAC model, the Reaching Out of School Children (ROSC) model developed by World Bank and the Basic Education for Hard to Reach Urban Children (BEHTRUC) model developed by UNICEF. In a workshop on 22 October the Ministry decided to scale up ROSC and BEHTRUC models for rural and urban areas respectively through the Bureau of Non-Formal Education (BNFE). / School Level Improvement Plan / School Level Improvement Plans (SLIP) are developed by school management committees in collaboration with local community based organisations. The SLIPs could include things like small scale infrastructure, e. g a fence or an approach road, to school or teaching learning materials e.g. additional books, dictionaries or other teaching aids like maps and charts. Guidelines for SMCs for developing SLIPs have been finalised and the first round of planning process is currently underway. DPE will scrutinise those plans in order to select schools for grant. The first tranche of grants will be disbursed early in 2013. / School Report Cards / The School Report Card is a mechanism for members of a school community to evaluate the performance of their school. DFID Bangladesh proposed this in order to verify the impact of PEDP 3 at the school level. In the technical assistance mapping exercise in September 2012 this proposal was raised, discussed and agreed among the donors and the department of primary education. Currently, DFID Bangladesh is actively considering two proposals, one from Action Aid on school level accountability and transparency and the other from CAMPE, the Bangladesh Chapter of the Global Campaign for Education, on strategic advocacy on quality and equity in education, Bangladesh in order to push for greater transparency and communication on programme deliverables at school and community level. The plan is to start the pilots in January 2013.
Progress against expected results: / 3,000 classrooms, 9,000 toilet blocks and 5,000 tube wells were 2011-2012 targets for this indicator. 5,766 classroom contracts are being negotiated as of the date of this review. Tenders for toilet construction will be published later this year after finalising the design. / The Ministry has decided on the non-formal education models to adopt, which was the 2011-2012 target for this indicator. An expansion plan is being prepared to roll out non-formal education from March 2013. / 35,000 school improvement grants was the target for 2011-2012. Due to delayed approval of the SLIP guideline, the target will not be achieved this year. / There was no target set for the school report card indicator. / Recommendations: / Commission the transparency and communication pilots [Can we combine this with a push on greater transparency of information so schools/parents etc know what they should be getting under the programme?] / Carefully examine the non-formal education expansion plan in order to ensure results and value for money / Monitor and evaluate SLIPs for efficiency and effectiveness / Impact Weighting (%): 33% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Strengthened government system in order to provide quality education with equity. / Indicator 2012 Target Status / Annual Schools Census 1 school census is done Achieved / National School Assessment 1 assessment is done Achieved / Number of field level education officers trained in school inspection. Target not set Unachieved
Output 3 score and performance description: SCORE B / Annual School Census / Annual School Census (ASC) is a national survey of primary schools that feeds into the Annual Sector Performance Review (ASPR). This gives a snapshot of the primary education sector in terms of number of children enrolled, retained, dropped-out and graduated from the system; number of teachers and their qualification; number of schools and their conditions etc. This year’s ASC was done in February and the analysis has been presented in the 2012 ASPR. Overall, all key indicators showed positive trend in the 2012 annual school census report. DFID fixed tranche, which is 30% of our annual support to the programme, is subject to progress in ASPR numbers. / National School Assessment (NSA). / National School Assessment is a sample survey of learning outcomes of grades 3 and 5 students. It is done once a year with technical assistance from World Bank. This is the only learning outcome assessment done in primary education in Bangladesh. The assessment is a written test that measured students against 27 curriculum objectives. This year the tests were done in July and results will be available in March 2013. / National School Assessment, like the Annual School Census, gives a snap shot of the effectiveness of all activities done under the programme. A negative trend in the assessment will question the effectiveness of the programme. / Field Level Training / PEDP 3 has a comprehensive training package for Upazilla education officers, who are the key persons managing implementation. The training package includes public procurement, financial management, school management and academic supervision. However, effectiveness of this training package was never assessed and the DPs have recommended that an assessment is done.
Progress against expected results: / Annual School Census was conducted in time and the analysis of 2012 ASC will be available in 2013. / National School Assessment was conducted in time and the analysis will be available in 2013. / Training for Upazilla Education Officers (UEO) is continuing. A total of 1500 UEO was trained as of September 2012. / Recommendations: / Develop an assessment of UEO training package. / Commission a study investigating in-depth the key of issues of improving learning outcomes in Bangladesh. / Impact Weighting (%): 33% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log frame been updated since last review? Y / Yes. The log frame was updated prior to this review in order to align the indicators to the jointly agreed Disbursement Linked Indicators (DLIs). / 1.2 Overall Output Score and Description: / Overall output score for this programme is B. This score is based on individual output scores and the weights assigned to different outputs. Overall, the programme is in the positive trajectory. Policy decisions taken this year will pave the way for smooth progress of the programme in the next year. / 1.3 Direct feedback from beneficiaries / Direct feedback from beneficiaries was not collected during the annual review. A set of field visits will be planned to collect direct beneficiary feedback. At the same time, the school level report card will provide more structured feedback.
1.4 Summary of overall progress / The programme has made substantial progress in output 1 and good progress in output 3. Output 2, however, is lagging behind. / Over 90 million copies of textbooks have been printed and distributed and 10,000 teachers recruited this year in order to improve the quality of education. A new teacher training course is being piloted for improving teaching quality. 6,000 classrooms are under construction in overcrowded schools. The Ministry has agreed to roll out non-formal education for out of school children, which will radically improve Bangladesh’s chance of achieving the education MDGs.
1.5 Key challenges / Key challenges for the successful programme implementation are: / Low capacity at the DPE for implementation and proper monitoring of the programme. / Low government allocation to the sector stifling development activities / Adherence to agreements on infrastructure
1.6 Annual Outcome Assessment / Annual outcome of the programme in 2012 is satisfactory. However, the assessment comes with a caveat. The good progress of output 1 could be fully attributed to the technical assistance provided by various development agencies. The target products of this output were mainly TA led studies, plans and training modules. That was also the case for output 3 targets. Output 2 targets, which were about implementing activities, like classroom construction and school level improvement plan, didn’t meet expected level of progress. This alludes to the on-going concern about government capacity to successfully implement this complex and ambitious programme. / This critical risk is a standing agenda in our discussion with the ministry, who have actively addressed performance issues, if and when raised with the senior officers. One good example of that is creating the position of the Deputy Programme Director. Also, there is a scope for greater synergy between DFID support civil service strengthening programmes and BEDP. At the same time, a paper, reviewing the level of ambition of the programme will be commissioned for consideration during the mid-term review of the programme in 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / Only 30% of the annual disbursement of this programme is against satisfactory progress of the ASPR indicators. The rest 70% of the disbursement is against achievement of 9 disbursement linked indicator targets. This year only 4 out of 9 DLI targets have been met. There is a possibility that up to 3 DLI targets will be further met till the end of this year. / DLIs, a feature of this innovative results based instrument, is a source of uncertainty in spending according to the forecast. The annual forecast is made assuming all DLIs will be met, however, as the year progress; the forecast is more realistically adjusted. Overall, there is also some distance to go in order to gain consensus on the financial implications of DLIs which are repeatedly not met: do we re-assess after additional time is given? For how long? / 2.2 Key cost drivers / Key cost drivers for this project are classroom and toilet block construction costs. Cost containment is a key issue for the programme working groups. As mentioned in section on school construction, the cost of toilet blocks is disputed by the disparity working group and a consultant is working on developing a low cost option for toilet blocks. The 2012 draft Minute on DFID Education Results and VfM to the Public Accounts Committee noted that the classroom construction cost in Bangladesh, at USD 15,000, is at the mid-range among the 18 countries where DFID support education programmes. At USD 0.35 the unit cost of textbooks printing and distribution is the lowest. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There hasn’t been any change in evidence in this programme. In the mid-term review additional evidence will be generated in order to assess the impact of the key activities on student enrolment, attainment and learning outcome. Also, the evidence generated through DFID transparency pilots will be used for making changes in programme implementation. Barriers to Learning study, mentioned in detail later in this review, will also test the key assumptions of the programme and make necessary recommendations. / 3.2 Where an evaluation is planned what progress has been made? / Yes, two joint- independent evaluations are planned for this programme. A mid-term evaluation will take plane early in 2014 and the final evaluation will be conducted in 2016.

4. Risk
4.1 Output Risk Rating: High / The Business case assessed the programme as a high risk programme. The key risk factors were fiduciary risks and low public allocation to the sector. The safeguards for fiduciary risks are functioning well; however, the low public allocation risk is still a real risk to the programme. DFID is planning a high level policy paper, based on robust education budget analysis, written by a globally acknowledged specialist and communicated through a high level event in country on this issue. DFID B education adviser is in touch with the US based think tank Brookings Institution and the Office of the UN Special Envoy for Education regarding the paper and a high level event in May/June 2013. DFID B will also ensure, as part of the pilot project activities that education budget is discussed and debated in public forum. We will also try to use other forum like the BBC Sanglap to challenge the current level of government allocation in education. [Again, how are we working to mitigate this?] / 4.2 Assessment of the risk level / Risk level was not assessed for this review. The next review will assess the risk level.
Risk of funds not being used as intended / Risk of funds not being used as intended is medium. UK fund is released on a reimbursement basis, which successfully mitigates the risk of UK fund not being used as intended. The working groups also provide an additional security against funds not being used as intended. The Disparity working group recently identified a case of funds being used for constructing additional classrooms in schools not prioritised in the programme.. The ministry decided to stop construction in the disputed sites until a formal investigation is complete when the donor consortium investigated and raised the issue. / 4.4 Climate and Environment Risk / Climate and Environment risks were not assessed for this review. A full review is planned during the 2013 Joint Annual Review Mission and will be reported in the 2013 APR.

5. Value for Money
5.1 Performance on VfM measures / The business case identified three value for money indicators: / The private return to the individuals who will benefit from education; / The social and welfare benefits to the wider population and economy as a result of a more educated population. / A detailed analysis of the unit costs proposed under the sector plan. / The gross and net enrolment rates, that is how many children are receiving primary education supported by this programme and how many of them are of primary school age, are the key evidence of the first value for money indicator. The 2012 Annual Sector Performance Review (ASPR) showed that the net enrolment rate has increased from 94.8% in 2010 to 98.7% in 2011. This increase translates into additional 800,000 children receiving primary education though the programme. / The wider social and welfare benefits were not clearly defined in the business case. DFID Bangladesh will commission a study to define wider social and welfare benefits of primary education in Bangladesh in order to create a baseline and establish a way of tracking the benefits. / A detail unit cost study will be commissioned early in 2013 in order to generate evidence for the third VfM indicator. / A fourth indicator, learning outcome in Bangla and maths, will be added to the current set of VfM indicators to track the effectiveness of the programme. This will also align the programme with 2010 National Audit Office Review of DFID Education Programme recommendations. Data for the learning outcomes will be available from the National School Assessment. A study on barriers to learning will be also be commissioned to inform the programme. / 5.2 Commercial Improvement and Value for Money / World Bank procedures are followed in procuring goods from the international market and Asian Development Bank procedures are followed for services procured from the international market. Local goods and services are procured following Bangladesh government’s Public Procurement Regulation 2008. DFID Bangladesh cannot intervene directly in those procurements. / 5.3 Role of project partners / Partners in this programme play a significant role in planning, decision making and monitoring the programme. The partners are the eight agencies supporting this programme: Asian Development Bank; AusAid; CIDA; DFID; JICA; SIDA; UNICEF and the World Bank. The partners formed the PEDP 3 Donor Consortium, which is the main body for donor harmonisation and collective decision making. The consortium has four technical working groups: i) Quality Education; ii) Equity in Education; iii) Administration and Monitoring; and iv) Procurement and Financial Management. These working groups, co-chaired by relevant government ministry officials and representatives of development partner agencies, are the key places where programme progress, issues and solutions are discussed. Technical assistance requirements are also discussed and agreed in these working groups. / 5.4 Does the project still represent Value for Money : Y / A robust value for money analysis of the programme progress will be available next year. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / There is no conditionality attached to this programme.

7. Conclusions and actions
BEDP is a complex and ambitious programme. The programme has scored a B against 2011-2012 targets. Three key actions for the next year are: / Commission a unit cost analysis to keep a tab on value for money parameters. / Closely monitor programme progress, identify capacity bottlenecks and provide appropriate TA / Commission a policy paper on annual budget allocation to primary education in Bangladesh. / Include a quality education indicator as a value for money indicator and strategise influencing progress of the indicator.

8. Review Process
This was a desk review written by the DFID B lead adviser based on: i) Joint Annual Review Aide Memoire, July, 2012; ii) DLI Assessment Review Aide Memoire, September 2012; iii) DFID TA Report, September 2012; iv) Third Party Validation Report on Textbooks Distribution, August 2012; v) DLI Evidence Report by DPE, August 2012; vi) Draft Minute to Committee of Public Accounts on DFID Education Results and Value for Money, Education Policy Team, October 2012.