Type of Review: Annual Review

Project Title: Tanzania Revenue Authority - Tax Modernisation project

Date started:	Date review undertaken:
2009	(this phase)	15 to 19th October 2012

## Introduction and Context

What support is the UK providing?
The UK support is part of a donor-funded basket to support the implementation of the Tanzania Revenue Authority’s third corporate plan (2008 to 2013), called the Tax Modernisation Programme (TMP). The support is a continuation of support to the two earlier plans Implemented over the period of 2001 to 2013. The total support budget is US$33.6m of which the UK has contributed £8.6 m in the first phase and £8m is earmarked for this extension phase relating to the third Corporate Plan. Danida is the lead donor. / The donor support in this phase was projected to provide US$25m out of the total capital costs for this plan of nearly US$80m. Changes in funding arrangements (less from the World Bank and more from Danida) mean that donor and GOT funding will now total about US$30m.

What are the expected results?
The objective is to provide an efficient and effective tax administration that provides high quality customer services with fairness and integrity by:- / Increasing revenue collection in a cost effective way through broadening the tax base, increasing levels of compliance, improving the tax structure and better monitoring and controlling the cost of revenue collection; / Improving the efficiency and effectiveness of TRA by integrating its operations / Providing high quality and responsive customer service / Strengthening the efficiency of tax enforcement with fair, equitable and transparent application of tax laws. / Improving TRA staff competence, motivation, integrity and accountability. / These align closely to the TRA’s Corporate Plan goals. / The prime targets in the logframe (2011) and progress against them are summarised below:- / Indicator Milestone 4 (June 2012) : Target Milestone 4 (June 2012) : Actual / Tax revenue as % of GDP 19.3 15.88 / Total annual tax revenues collected by TRA in relation to its annual revenue target Tshs 7406.4 bn Revised Budget target : Tshs 6228.8bn / Outturn : Tshs 6529.3 bn / Average time taken to clear goods at sea ports, border posts and airports DSM Port: 4:00 hrs Airports: 2:00 hrs DSM Port: 4 days Airports: 2 days / Land borders: 1 day / Time taken to register taxpayers on TIN and VAT 2 days 1 day in Dar / (2 days up country) / Total revenue realised from audits/revenue collected 10% 10% (on SMEs) / Cost of collection as % of revenue 2.1% 2.3% / Green = Target met or exceeded / Red = Below target / Amber = Target met (but target was revised below the logframe expectation)

What is the context in which UK support is provided?
The Government of Tanzania established the Tanzania Revenue Authority (TRA) in 1995 as a semi-autonomous agency with the objectives of increasing revenue collection, improving tax policy making, and broadening the tax base; responding to the serious fiscal problems arising from the gap between stagnant revenues and rapidly growing expenditures, which had resulted in an increase of the fiscal deficit from 5% in FY 1994 to 7.9% in FY 1995. The creation of TRA had an immediate impact on collection efficiency, and actual tax revenue collected increased by 26% in the first year of operation. However, despite these commendable reforms, collection performance stagnated at a level of between 11 and 12% of GDP from FY 2000 to FY 2006, and thus remained below the sub-Saharan average. As a result the GOT asked TRA to launch a second generation of reforms to make TRA more investor and taxpayer friendly, strengthen its operational efficiency, and enable TRA to further boost revenue collection. Responding to this request, TRA in 2003 developed its second five-year corporate plan consisting of 70 major initiatives to be implemented in FYs 2003/04 – 2007/08. Five Development Partners (DFID, The World Bank, the IMF, the EU, and DANIDA) supported the preparation and implementation of the plan. / The reforms of the second corporate plan substantially improved the revenue collection system in Tanzania. The tax yield more than doubled from TShs 1.4 trillion in 2003/04 to TShs 3.4 trillion in FY 2007/08, raising the tax/GDP ratio to 14.5%. Broadening the tax base substantially increased the fairness of the tax system, as the number of registered taxpayers increased from 190,000 in July 2003 to 381,000 in March 2008. Despite these improvements, further reforms were required to consolidate results achieved, reach still higher revenue targets (the TRA are set to collect TShs 4.8 trillion in 2009/10) and address remaining weaknesses in TRA operations. / Thus the GoT developed its third corporate plan, spanning five years 2008/9-2012/13, requesting donor support from year two to: / Foster the mobilisation of domestic resources; / Reduce the taxpayer compliance burden, improve the investment climate and facilitate cross-border trade; / Continue to improve the quality of services offered to taxpayers; / Institute a culture of transparency and integrity among TRA staff: / This third TRA Corporate Plan anticipated that GoT will benefit from an increase in revenue collections – from 3,465.8 billion TShs in FY 2007/08 to 8,936.8 billion TShs in FY 2012/13, representing a growth of more than 150%. This translates into an average annual growth rate of about 0.9% of GDP. Increases in tax revenue will improve macroeconomic stability and the long-term sustainability of the budget, helping to sustain improvements in delivery of essential public services while reducing dependence on external aid flows. The increase in revenue collection will also enable the GOT to fund the increases in public investment in power, water and transport infrastructure which were set out in the MKUKUTA. / Thus the TRA has enjoyed considerable donor support since it was established nearly 20 years ago and has moved from being an ineffective revenue institution to a rapidly modernising organisation that is on track to deliver many of its Third Corporate Plan objectives. Revenue has increased from about 10.8% of GDP in 2003/4 to nearly 16% in 2011/2 with future initiatives looking to raise this to 21% over the duration of the next 5 year Fourth Corporate plan. / The DFID support contributes to a basket fund with DANIDA that directly supports the implementation of TRAs corporate plan. Alongside this support there are many other donors active in TRA – including ICF, IMF and IMF AFRITAC EAST, JICA, KOICA, NORAD, TMEA and the US Treasury.

Section A: Detailed Output Scoring

Output 1: Increase Revenue Collection in a Cost Effective way
A : Output met expectation / Overall, revenue collection increased by 22.3% from 2010/2011, resulting in an actual collection of 104.4% of target. This corresponds to an increase in the Tax/GDP ratio from 15.2% in 2010/2011 to 15.7% in 2011/2012 – an all-time high for Tanzania and a very positive change after 3 years of missed targets, in large part reflecting global economic conditions. / Strong TIN and VAT Register growth resulted in targets being exceeded. Arrears management has continued to improve but is still below target especially in the Domestic Revenue Department (DRD) which handles SMEs where the collected arrears are 23% rather than the 65% targeted. In all countries enforcing tax compliance amongst SMEs is always harder than for larger taxpayers. Larger taxpayers tend to be well organised and respond more readily to their tax obligations. SMEs on the other hand are often disorganised (lacking tax knowledge and systems), have cash flow pressures and collecting tax from them is far more numerous. The great success of TRA in expanding the tax base (190,000 in 2003 to 1,035,000) now brings with it greater compliance challenges and hence arrears collections are struggling.
Progress against expected results: / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / Registered Taxpayers (by Department) TIN (696,245) TIN (1,035,281) / VAT (13,230) VAT (17,860) / Large Taxpayers (450) Large Taxpayers (400) / Revenue collection performance (by Department) DRD (100%) DRD (111%) / Customs (100%) Customs (96%) / Large Taxpayers (100%) Large Taxpayers (115%) / Number of taxpayers accounting for 80% of (total LTD) revenue 50 39 / Amount of previous year's arrears collected / total amount of tax arrears at beginning of year DRD (65%) DRD (23%) / LTD (95%) LTD (87%) / Recommendations: / There are issues of funding and staff numbers within TRA that need to be addressed (ideally within the fourth Corporate Plan); a full review of staffing and structure (supported by donors) is needed. Better future focusing of staff resources on higher yielding areas will help to increase revenues. / The rationale behind much of the investment in systems and equipment for revenue authorities is to improve efficiency – less staff to obtain more revenue (as well as making it easier for taxpayers to discharge their obligations). These systems/equipment also bring with them not just capital costs but increased running costs. At the same time TRA is projecting a reduction in running costs (as a % of revenue). / The combination of these realities implies a reduction in manpower (or at the very least manpower remaining constant but with staff being redirected from routine processing towards compliance enhancing activities (taxpayer education, taxpayer audit etc)) but within TRA most units were seeking staff increases. A review of staffing and structure should address these apparent inconsistencies. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High : Medium / Revised since last Annual Review? No

Output 2: Modernisation of TRA operations
B : Output moderately did not meet expectation / Some good progress but refunds are taking longer than expected and electronic return submission is below expectation. ITAX is however now processing almost all transactions and at 98% (and this measure is above target) this is probably as high as it can get as there will always be some transactions, e.g. stamp duty, that are dealt with outside of the main tax management ICT system / The E filing target was for 100% of large taxpayers to submit their returns electronically. This has not been achieved (the current figure is just over 90%). Experience elsewhere suggests that unless E filing is the only option then a number of businesses will prefer to continue with manual filing. This may be due to a reluctance to change processes but is sometimes due to a physical return being required by controls in the business to be signed by someone senior and that person does not have the time or inclination to then submit the return on line (and may be reluctant to delegate his/her authority to lower level staff). / The VAT refund target is to make 90% of refunds within a month but at present 78% are paid out within this period. The level of accuracy of VAT return claims is not as high as it could be and hence a significant proportion of claims require either desk audits or verification at the taxpayers’ premises. This all takes time and this and the internal TRA administrative and approval processes all contribute to a lengthy timescale. TRA is being encouraged to assess all the stages in the process in order to streamline them (for example UK pays over 90% of claims within 7 days). Lack of finances from Ministry of Finance for TRA has also being blamed for the slow rate of VAT refunds.
Progress against expected results: / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / % of large taxpayers that submit their VAT returns electronically 100% >90% / % of VAT refunds made within a month 90% 78% / % of transactions processed by ITAX (CP implementation matrix 2.3.0.0) 95% 98% / Recommendations: / None beyond the plans set out in the fourth Corporate Plan. Further improvements as regards modernisation are dependent on the replacement of ASYCUDA++ (and radically streamlining Customs freight document processing systems) and replacing the ITAX system with a new Tax administration system. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High : Medium / Revised since last Annual Review? No

Output 3: Provide High Quality and Responsive Customer Service
B : Output moderately did not meet expectation / Customs performance (as regards clearance time) is far below expected service levels as shown below – 44% at Dar cleared in 24 hours compared to 95% as planned at 30 June 2012. This disappointing variation needs to be examined in context. At the end of 2010 the TRA took over the document processing operations of the port service provider (Cotecna/TISCAN). That followed the expiry of the company's Build Operate and Transfer (BOT) contract. The Customs and Excise Department within TRA had been handling documents for Pre-Arrival Declaration (PAD) for cargo not exceeding 5,000 US dollars and special consignments, and thus at the handover, that process was extended to all shipments. As part of the transfer TRA took full control of TISCAN’S PAD software and system. This system is a paperless one with all documentation scanned and submitted electronically. It is founded upon a second Customs declaration – the TRA's Pre-Arrival Declaration (PAD). This is a country specific requirement and is not a common requirement in other countries – in most countries pre-arrival declarations are managed through the Authority’s Customs Entry/SAD processing system (e.g. ASYCUDA). The pre-arrival declaration system essentially replicates the working methods of a pre-shipment inspection company in that the documentation of all consignments are scrutinised and uplifts are imposed on values and changes made to the tariff classification (which determines the duty rate). That checking seems to be conducted on a 100% basis and this is not surprising as the agent import statistics show widespread non-compliance with 47% of the over 37,000 declarations checked in the last quarter (to 30th September 2012) being uplifted and 29% being reclassified. Some of the 450 agents have a good track record but many have 100% of their entries uplifted. / Thereafter (after the goods arrive, the customs declaration is input into ASYCUDA++ and 56% are subjected to documentary check or physical examination. Thus some consignments are checked at two stages but the very existence of the two stages of checking itself contributes greatly both to the time taken to clear shipments and also adds to the costs of importing goods. / The processing of Customs declarations by TRA uses a Centralized Data Processing Office (CDPO) which is an excellent concept (as it should result in more efficiency, more effective and consistent checking and it separates the processing officer from the importer/exporter). However the unit only works ‘office hours’ plus Saturday morning and that feature alone impacts hugely and negatively on clearance times. Where centralised units are employed (e.g. UK, South Africa etc) they operate 24/7; changing to a shift operation should not have any significant staffing impact as the workload does not change by moving to a 2 or 3 shift operation. It is difficult to see how a new Customs ICT system will generate the claimed increased trade facilitation if this change is not made. Customs also have a high intervention rate in entry processing – with 38% of entries being subjected to documentary scrutiny and 28% to physical examination. The delays caused by these interventions need to be balanced against the results that are achieved by them. / Taxpayer awareness on taxpayer education is considerably above target. TRA has made good progress on education – as evidenced by the significant rise in the numbers of TIN registrations (under 400,000 at June 2008 and 1,035,000 four years later). / Enquiries via centralised channels are approaching planned service levels (but other enquiry routes e.g. to individual tax offices are not measured and may be far lower).
Progress against expected results: / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / % of customs clearance made within 24 hours Dsm Port (95%) Dsm Port (44%) / Airport (95%) Airport (76%) / % of declarations subjected to scanning or physical verification Dsm Port (40%) Dsm Port (31%)* / Airport (20%) Airport (23%)* / % of taxpayer awareness on tax education programmes 75% 94% / Percentage of written enquiries attended within seven days 95% 86% / (only covers enquiries via centralised channels) / * July 2012 figures / Recommendations: / Reforming the Customs business processes is one of the prime challenges for the next Corporate Plan; at present the vast majority of customs declarations contain errors (that percentage), this needs to be reduced (and declaration processing conducted as per international norms). Assistance from donors in developing a coherent and integrated strategy for improving Customs voluntary compliance is recommended. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High : High / Revised since last Annual Review? No

Output 4: Promote Voluntary Tax Compliance
B : Output moderately did not meet expectation / A key measure of voluntary tax compliance is the % of taxpayers who file returns on time. The target set is a totally unrealistic 100% (a figure not achieved anywhere in the world). For large taxpayers the achieved filing rate is good and is about 90%, However for SMEs the figures are much lower (47% for PAYE, 62% VAT and 63% Corporation Tax). For the smallest taxpayers (the bulk of the 1.035m taxpayers who are operating a presumptive tax regime) the figures are much lower. Despite considerable and creditable efforts at taxpayer education these % are disappointing as most countries can achieve, for VAT and PAYE, compliance rates of approaching 80% A clear strategy to raise these compliance levels is required. / However once a failure to make a return on time does happen (“stop filers”) the TRA is quite good at following up and is doing so within the stipulated timescales. But of course the need to follow up on so many stop filers is a drain on TRA resources and means that manpower is not available for other work.
Progress against expected results: / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / Average number of days taken to identify stop-filers DRD - Direct Taxes (10) DRD - Direct Taxes (10) / DRD - Indirect Taxes (5) DRD - Indirect Taxes (5) / LTD (3) LTD (3) / % of taxpayers filing on time 100% LTU : >90% / DRD :- / Corporation tax - 63% / PAYE - 47% / VAT - 62% / Recommendations: / The next Corporate Plan must address two key challenges:- / the considerable broadening of the tax base will inevitably mean more taxpayers will be potentially non-compliant – that risk will need managing / promoting voluntary customs compliance so that the current 80% of errors on pre arrival declarations is reduced. / New ICT systems can help but unless these issues are tackled voluntary compliance will remain a key issue. For Customs, donor assistance in devising an all-embracing strategy to reduce errors is urgently required. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High : Medium / Revised since last Annual Review? No

Output 5: Enhanced staff performance management system
A : Output met expectation / The objective of having a new staff performance management system for all of TRA has overtaken the idea of having SLAs for TRA’s service departments and good progress is being made towards this. The TRA has achieved ISO 9000 certification (and hence has documented procedures etc and has change control processes) and is proceeding with the implementation of the Gemba Kaizen Management System (a form of TQM). / The number of integrity cases handled is an indicator that can be improved as a smaller number of cases could either mean no corruption or ineffective investigation. The TRA’s Internal Affairs Team has expanded in size and is working well and their many initiatives promise to make an impact on TRA integrity. Anecdotal evidence indicates that corruption is widespread within TRA particularly as regards duty assessment at importation and over VAT refunds; a more detailed evaluation of the type of cases that are dealt with over the final year of this project might help the understanding on whether integrity improvements are actually being achieved. / The final indicator also only bears a tangential relationship to the output but certainly the percentage of female senior managers is increasing.
Progress against expected results: / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / No of integrity cases handled 21 21 / % of objectives met as per SLAs 95% This measure has not yet been activated (and is likely to be overtaken by the new PMS) / % of female employees in decision making positions 20% 22%* / * as at mid October 2012 / Recommendations: / Indicators for this output should be revised. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High : Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the log frame been updated since last review? Y/N / No / 1.2 Overall Output Score and Description: B / The overall output score falls slightly short of an A, two outputs scored an A and three a B. TRA has made good progress in implementing its third Corporate Plan and has improved its operational and institutional performance. The indicators chosen for monitoring in the log frame are narrow; in the next draft Corporate Plan TRA have a wider range of indicators (55). Using all the measures in the plan (perhaps reducing them to a single % achievement figure for each theme) would give a better picture of modernisation progress. / 1.3 Direct feedback from beneficiaries / TRA has found the support provided by the basket fund extremely important for the implementation of their corporate plan. The review did not have the time to meet with the business community. However taxpayer perceptions surveys indicate the service is improving. Any further programme should track the business community’s perception of TRA service provision.
1.4 Summary of overall progress / The third corporate plan contained 98 initiatives and most of these (76) have been completed at end June 2012. The remaining 22 initiatives are at different stages of implementation but the majority are on schedule to be completed during the final year of the plan. These are listed below and initiatives likely to be extended into CP4 are in italics. / Impact analysis of parastatal privatisation on revenue generation: completed / Conduct sectoral risk analysis on Mining and Energy (electricity, coal and gas) – postponed to late in 4th Plan as several recent studies undertaken by other organizations. / Conduct sectoral risk analysis on Public Administration; on-going / Introduce a new system for Domestic Tax Administration – initial work underway but implementation will depend on funding (2014/5 being the earliest) / Introduce a new Customs Administration System (implementation will begin during 2013 but going live will be mainly in 2014) / Implement Electronic Requests for Staff Imprests & Advances: this initiative has been replaced by the introduction of the Portal software on the Intranet and will be completed in 2012/3 / Conduct a study on the viability of introducing tax amnesty for non-compliant registered taxpayers and unregistered businesses. There is little support for this initiative at present within the TRA / Assess the effectiveness of ICT utilization (operational & support systems):on-going / Develop and Implement Business Continuity Management System: PMU, ongoing and will continue in CP4 / Develop and implement Corporate Social Responsibility (CSR) Strategy: TPS, will be done in 2012/3 / Develop and Implement Service Culture Programme (SCP) to TRA staff: TPS, will be done in 2012/3 / Develop a medium and long term revenue mobilisation strategy: this is ready for Board submission; contains tax administration reforms / Introduce taxation in secondary schools curriculum and establish tax clubs; curriculum prepared by outside consultant and ready for Board review. Almost 100 tax clubs established / Implement Gemba Kaizen Management System: PMU, this is underway (and will continue in CP4) / Implement Business Process Re-engineering in Domestic Tax Operations; completed / Establish Taxpayers Advocate Services; DFID supported consultants expected to commence work shortly / Develop Corporate Human Resources Development (CHRD) Policy and Strategy - will be done in 2012/3 / Implement One Stop Border Posts (OSBP) for Customs operations; ongoing, but will continue into CP4 / Enhance tax collection from real estate: Pilot survey in 3 Dar municipalities completed and rates will go live in January 2013 / Introduce an additional employer's package on retirement; ongoing / Develop an exit awareness policy and strategy for retirees; ongoing / Map TRA blocks using Geographical Information System. Implementation is underway. / Of the above initiatives the key two concern the replacement of the Customs and Tax IT systems. The Customs one has been tendered for and a vendor selected. The challenge is the funding of the system ($20m, including $8m in maintenance etc). The Tax system is not far away from tendering but progress on implementation will, inevitably, depend on the availability of funding.
1.5 Key challenges / The major challenge for any Revenue Authority is to improve voluntary tax and Customs compliance (as part of increasing revenue yields both in absolute terms and as a percentage of GDP). The TRA in its third corporate plan has tackled these challenges in a systematic way and has made good progress as evidenced by the year on year revenue improvements. This has partly been the result of improved voluntary compliance brought about by increased taxpayer education and awareness and partly by better compliance enforcement. These actions have also highlighted the urgency of improving the tax and Customs computer systems (that are both time consuming and expensive) as well as the need to improve the operation of the TRA itself (HR, Internal Audit, Internal Affairs, Quality management etc). / The initiatives within the third Corporate Plan were both wide ranging and ambitious and have occupied a great deal of senior management time and energy to implement (as well as placing considerable strain on the TRA’s financial resources). That they have made so much progress is a credit to the TRA’s PMU and augurs well for the next Corporate Plan.
1.6 Annual Outcome Assessment / The outcome assessment is between an A and a B. The table below shows that 2 indicators were exceeded, 3 were missed and one was met (albeit with targets lower than envisaged at the start of CP3). / Indicator Milestone 4 (June 2012) : Target Actual (June 2012) / Tax revenue as % of GDP 19.3 15.88 / Total annual tax revenues collected by TRA in relation to its annual revenue target Tshs 7406.4 bn Revised Budget target : Tshs 6228.8bn / Outturn : Tshs 6529.3 bn / Average time taken to clear goods at sea ports, border posts and airports DSM Port: 4:00 hrs Airports: 2:00 hrs DSM Port: 4 days Airports: 2 days / Land borders: 1 day / Time taken to register taxpayers on TIN and VAT 2 days 1 day in Dar / (2 days up country) / Total revenue realised from audits/revenue collected 10% 10% (on SMEs) / Cost of collection as % of revenue 2.1% 2.3% / Green = Target met or exceeded / Red = Below targetAmber = Target met (but target was revised below the logframe expectation) / For a Revenue Authority the key indicator of performance is inevitably revenue collection. This was projected in the third Corporate Plan as an increase in revenue collections from Shs 4.6 trillion during the year 2008/09 to Shs 8.97 trillion during the year 2012/13 and subsequently increasing the revenue yield as a % of GDP from 14.7% in 2008/9 to a projected 20.3% during the five year period. Revenue is now standing considerably above the levels at the start of the project in monetary terms but whilst there has been a continual increase in the revenue/GDP ratio it is still considerably below the 20% projected. The revenue/GDP ratio is a controversial indicator (as the denominator is outside the control of an RA) and the numerator is also affected by tax policy changes (which the RA does not control). Whether a level of 20/21% in an economy such as that of Tanzania is feasible is questionable but the consistent year on year increase in revenues (20% or more in three of the four years of the current corporate plan) is most encouraging. / The lower than expected revenue yields have had a bearing on the average cost of collection % (which now stands at 2.3% rather than 2.1% as forecast for the end of Year 4 of the 3rd Plan). Again this is a debatable indicator as it is easy to reduce investments in new systems etc and show an immediate cost reduction (but the revenue cost of that will only show up several years downstream). Tax collection is a business where it is very cost effective to collect 80% of revenues from large taxpayers (at a cost of under 1%) but the marginal cost of collections from SMEs is far higher. In addition service improvements can be costly and yield little revenue (but reduce business costs etc). / The average clearance time is far above what was forecast and is due to the reasons explained under output 3. Although the replacement system for ASYCUDA++ is being designed with faster clearance times in mind, a change in TRA Customs mindset and improvements in voluntary compliance (far more honest declarations) are also needed.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Yes / 2.2 Key cost drivers / None at this stage – only £0.5m is still to be disbursed as the DFID basket contribution. The graet bulk of the spending has been on Outputs 2 and 5 – integration of TRA operations and improving staff competence. Spending has been in line with that set out in the Project Memo. / 2.3 Is the project on-track against original timescale: Y / Yes as regards the planned activities but the key headline results (Revenue and Revenue/GDP ratios) are markedly below the levels forecast at the outset of the Programme. These were, with hindsight, too optimistic (a lesson that needs to be borne in mind for the 4th Corporate Plan).

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No. / The KPIs are measured by TRA through their monitoring of the third Corporate plan and are underpinned by what appear to be robust data flow mechanisms within the TRA. Thus the data flows from TRA are good. / 3.2 Where an evaluation is planned what progress has been made? / Not planned

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium overall. One output is rated as high risk, one at low risk and three at medium. Those ratings are agreed. / 4.2 Assessment of the risk level / At this late stage in the support programme the risks are unlikely to change and the achievement of the outputs is unlikely to alter in any substantial way.
Risk of funds not being used as intended / This seems unlikely given that DFID are contributing to a basket. The World Bank used to perform no objection checks on procurement. Now that they are no longer a contributor, DANIDA is reviewing the procurement approval process with the help of a procurement specialist and will advise us on the outcome. / 4.4 Climate and Environment Risk / None at this late stage in the Programme

5. Value for Money
5.1 Performance on VfM measures / There are no overall value for money measures in this programme bar the cost of revenue collection (which is decreasing). There is a limit to how much further this can be decreased; experience from many RAs is that reductions in this ratio can lead to a falling off in revenue compliance in subsequent years. The investment by DFID in the basket funding can also be compared to the huge increase in Tanzania’s revenues – increasing from 4052 billion shillings in 2008/9 to 6529 billion shillings in 2011/12. This increase over the 4 years is equivalent to over US$1526m – over 50 times the donor investment. The basket fund donors will be carrying out a VfM assessment of large goods procurement, the Customs IT system before any funding is provided. / Any further programme will need to establish clear VfM indicators and make sure monitoring mechanisms are in place to track expenditures in year. / 5.2 Commercial Improvement and Value for Money / See above / 5.3 Role of project partners / DANIDA is the lead partner in contributing to the basket fund. TRA are the partner institution and they manage the disbursement of the funds against agreed activities. / 5.4 Does the project still represent Value for Money : Y/N / Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / There are no conditions

7. Conclusions and actions
TRA is making good modernisation progress and is looking to build on this and go much further in their fourth Corporate Plan. That plan, whilst only in draft, is impressive and if the required funding (costs to be established) can be mobilised it will take the TRA to a much higher level. So a key action is a recommendation that DFID “QA” that plan when it nears completion. That step is recommended as there are issues of management and poor resource usage that must be addressed during that plan’s duration.

8. Review Process
The review was based on a few days of pre-reading and then 5 days in country, the majority of that time being spent in the partner institution, with the DFID consultant working alongside a consultant provided by DANIDA. In addition to the examination of documents provided and meetings with TRA managers, activities were observed at first hand on the ground.