Type of Review: Annual Review

Project Title: Africa Risk Capacity

Date started:	December 2010	Date review undertaken: November 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Africa Risk Capacity (ARC) provides an innovative approach to manage the risk of food insecurity caused by extreme droughts; slow onset disasters that can often overwhelm the capacities of African governments and do not attract humanitarian aid early enough. / ARC is a pan-African mechanism to pool drought risk and provide African Governments with timely and reliable contingency funding in the event of a severe drought and complement, but not replace, current national and international efforts to address food security needs. A risk pool is a mechanism where individual risks are transferred and combined. Countries participating in ARC will commit to pay small, regular premiums in return for reducing the risk of spikes in drought assistance costs as a result of an extreme event. / DFID is providing £2.5 m for the design of Africa Risk Capacity (December 2010 to July 2013) with other donors also contributing (see section 5.1). The design is led by the Africa Union, which is providing the mandate to build high level buy-in across Africa. The World Food Programme is providing assistance and coordination on the technical, legal and institutional mechanisms of ARC. / This is the second and final Annual Review for DFID’s current contribution to ARC. A Project Completion Report is due in June 2013.

What are the expected results?
The expected results from the current phase of DFID’s contribution to the Africa Risk Capacity include: / Impact – Sub-Saharan countries better able to manage extreme drought risk (by 2015): / At least 4 drought vulnerable countries covered by contingency plans linked with access to regional contingency finance; / $465 million extreme weather contingency funds available to sub-Saharan countries. / Outcome – ARC, an African-owned disaster risk pool for sub-Saharan Africa, in place providing a contingency funding mechanism for planned responses to extreme climate emergencies (by 2013): / At least 6 national governments requesting participation in ARC; / At least 6 countries with developed drought response contingency plans linked to regional contingent funds; / 100% of required funds committed against ARC donor appeal. / Output 1 – Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool (by 2013): / 15 countries that are (or have been) in dialogue with ARC and actively considering ARC participation; / 15 Africa RiskView and ARC training workshops held for stakeholders (350 people); / Economic rationale for ARC participation established and plan for monitoring benefits of participation developed / Output 2 - Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders (by 2013): / Agreement on core technical content of the design proposal by sufficient stakeholders; / Agreement on operational manual by stakeholders sufficient for initial operation of the entity. / 10 independent reviews of discrete technical portions of the ARC Project complete. / Output 3 - Consultation and political engagement carried out (by 2013): / 100 consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept; / 10 different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.); / 20 Positive mention of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments. / Output 4 - Plan for the creation of the legal and organizational structure of ARC entity fully defined (by 2013): / Legal structure of ARC finalised; / Establishment process agreed upon by ARC stakeholders and underway / the ARC facility defined.

What is the context in which UK support is provided?
Extreme weather events across Africa regularly place the lives and livelihoods of the most vulnerable at risk. Droughts are particularly significant and often lead to food crises with significant humanitarian impacts and longer-term economic costs. Climate change is leading to more frequent and intense extremes in weather increasing the longer-term risk of greater humanitarian need and economic impacts. / As the Humanitarian and Emergency Response Review (HERR)[1] showed, the current system of response to drought is not as timely or equitable as it needs to be. The International system is trying to address the need for fast and predictable responses to emergency situations; for example through the Crisis Response Window (CRW) of the International Development Association (IDA) and the United Nations Central Emergency Response Fund (CERF). However, such funds are generally only available on an ad hoc basis in the immediate aftermath of a disaster and only then can relief be mobilised for the people who need it most. This results in a time lag between the onset of a crisis and the availability of resources to deal with the consequences. In the meantime, lives are lost; families sell or consume their assets and undertake other strategies with detrimental consequences, such as taking children out of school and reducing food consumption. / The HERR showed anticipation and the early provision of relief can stop a crisis becoming a disaster. This is particularly important for slow-onset events, such as the impact of drought of food availability. Analysis undertaken during the current design of Africa Risk Capacity found that the cost of delaying relief for three months after a failed harvest had negligible impact whereas delaying the response for six months led to losses of $1,200 in assets per household. Loss of assets reduces families’ future income potential, but too often the cost of delay is also in lives.[2]
[1] Available from: http://www.dfid.gov.uk/what-we-do/key-issues/humanitarian-disasters-and-emergencies/how-we-respond/humanitarian-emergency-response-review/
[2] The final report, undertaken by D Clarke (University of Oxford) and R V Hill (IFPRI) is available from: http://www.foodsecurityportal.org/could-weather-indexed-insurance-replace-food-aid-africa-cost-benefit-analysis-africa-risk-capacity?print

## Section A: Detailed Output Scoring

Output 1: Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool
Output 1 score and performance description: / Output score: A+ – Outputs moderately exceeded expectation / Two of the indicators for this Output have already reached their 2013 Target and the other has achieved as much as possible given the pace of the political process.
Progress against expected results: / Milestones for this Annual Review and results to date are reported below: / 1.1 - Ten countries that are or have been in dialogue with ARC and actively considering ARC participation. To date 23 countries have been directly engaged by the project, however 34 AU Member States were represented at the Government Experts’ Meeting in Johannesburg in September to finalise the text of the ARC Specialised Agency Establishment Agreement. The project has already reached the Target for 2013 (fifteen). To help formalise country engagement the Project Team have required that countries expressing an interest in participating in ARC must sign a pre-participation agreement (PPA). This is a commitment by both sides to work towards preparing a country for full participation in ARC at the end of the PPA period. To date, five countries have signed PPAs: / Malawi / Lesotho / Niger / Kenya / Senegal / 1.2 - Ten Africa RiskView and ARC training workshops held for stakeholders, including government and their partners, and regional body representatives (200 people). Twenty workshops conducted (16 of which occurred in Second Annual Review Period), reaching approximately 600 people. The project has already reached the Target for 2013 (15 workshops or 350 people) / 1.3 - Economic rationale for ARC participation established and plan for monitoring benefits of participation developed. Two cost benefit analyses have been completed providing a robust assessment of the economic case for ARC and providing solid economic rationale for ARC. The DFID Chief Economist reviewed the draft report and felt it provided an extremely valuable analysis, particularly in terms of the value of early and predictable action in assisting those affected by livelihood shocks and the cost-effectiveness of scaling existing in-country mechanisms to identify and respond to such needs. The second study, by the Boston Consulting Group, built on the initial analysis to further explore ARC’s value proposition. This work is not yet published. Work on monitoring and evaluation not yet started. / Recommendations: / The Project Team need to continue momentum in country engagement to ensure that, as far as possible, the current levels of interest shown in ARC translate into commitments to participate and so help achieve the project’s Outcome. / The key focus for this Output should now be on moving beyond dialogue (Indicator 1.1) and workshops (indicator 1.2) to start the transition process from design to implementation. Indicator 1.3 is likely to be particularly important here; both in terms of starting the monitoring and evaluation work stream and also communicating the economic rationale formally to potential donors. This work needs to be closely linked to other work streams, such as the operational manual (indicator 2.2) and the donor engagement (3.2). / A further challenge in this Output is to move from the economic case for ARC (to which the CBA work has contributed) to the results of the Dynamic Financial Analysis (DFA) that will actually be needed to make the case for the appropriate level of donor support needed to capitalise ARC (indicator 2.1). / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders
Output 2 score and performance description: / Output score: A – Outputs met expectation / This Output is on track to reach its Targets in 2013.
Progress against expected results: / Milestones for this Annual Review and results to date are reported below: / 2.1 - ARC financing strategy and institutional structure defined - Final draft developed and dialogue on-going with required stakeholders to finalize ARC financing strategy and institutional structure. A conference of African plenipotentiaries[3] convened in November adopted the ARC Specialized Agency Establishment Agreement. The agreement specifies the two-tiered institutional and governance structure of ARC – a parent body (ARC Agency), which is a Specialised Agency of the African Union to be governed by its member states and to perform ARC’s policy and quasi-governmental functions, that will establish a financial affiliate (ARC F), likely to be a mutual insurance or cooperative insurance company established under the national law of a country which offers a robust and appropriate regulatory regime, to carry out all of ARC’s insurance functions. It represents the culmination in a year-long design and expert, donor and member state consultation process by the ARC Project, following the AU protocols and procedure for the establishment of a Specialised Agency of the African Union. In order to understand the financial requirements to create a solvent and sustainable risk pool a dynamic financial analysis (DFA) for ARC F has been conducted with a final report available by the end of 2012. / 2.2 - ARC participation, operation and M&E guidelines developed - Draft of ARC operational manual completed for consideration and revision by ARC stakeholders. Partially completed as of end October 2012, on track for first ARC Conference of Parties (CoP) in January 2013. Whilst formally this milestone has not been achieved, the work under this indicator is keeping pace with the formal Africa Union process. Now that ARC’s institutional structure and establishment process has been defined, all aspects with respect to ARC operation, guidelines and country participation criteria in ARC F will be developed. / 2.3 - Ten independent reviews of discrete technical portions of the ARC Project e.g. Africa RiskView, dynamic finance analysis, institutional structure, M&E, climate change stress tests. Seven conducted by October 2012. To date the following independent reviews of discrete technical portions of the ARC Project have been conducted: two ARC cost-benefit analyses (by IFPRI/Oxford University and BCG); reviews of Africa RiskView by European Commission’s Joint Research Centre (JRC) and risk modelling firm AIR and an independent overview of possible legal structures of ARC. Swiss Re and the African Centre of Meteorological Application for Development (ACMAD, in Niger) are currently testing the software for commercial market and weather research purposes respectively and, in addition, over 25 external users are testing Africa RiskView Online with an additional approx. 80 external requests to use the tool (not counted in the milestone total). Forthcoming independent analysis include a climate change stress test analysis using Africa RiskView and a full Dynamic Financial Analysis (DFA) building on the initial work presented in the ARC World Bank feasibility study produced in 2011. / Recommendations: / Further work is required to ensure that this Output is achieved. In particular, the operational manual (indicator 2.2) is a key document and in relation to indicator 2.3 the focus should be on ensuring that reviews of the ARC Project are not only complete but also publicly available (for example through the Project website). Communication of the analysis and the design process more widely will be a crucial activity in the next six months and the Project Team should ensure that have a suitable strategy in place so all communication is suitable, robust, appropriate and timely. / It is also now worth considering whether all the necessary components of ARC have been subject to independent review. In particular, the country risk profiles should be made publicly available as soon as possible and the Project Team should also consider whether the application of Africa RiskView at the country level needs to be analysed in more detail. At present, the only focused independent technical review of Africa RiskView is the work undertaken by the Joint Research Centre of the European Commission. This report is not widely available and was conducted early in the design process. We recommend the team evaluate the customisation of Africa RiskView at a national level. / An additional challenge around indicator 2.1 and 2.2 regards the acceptability of the proposed system to potential participating countries and potential donors. Both sets of stakeholders will have expectations and may require different degrees of evidence that the proposed systems will be transparent, sufficiently robust with acceptable governance structures and due diligence procedures in place (including monitoring and evaluation and fiduciary risk management). A robust, independent Fiduciary Risk Assessment (FRA) will need to be conducted for ARC F and the proposed monitoring and evaluation system. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[3] A Government representative fully authorized to represent his or her government (e.g., ambassador).

Output 3: Consultation and political engagement carried out
Output 3 score and performance description: / Output score: A – Outputs met expectation / The Targets for this Output have largely been achieved. There has been a considerable effort made during the last year to strengthen and deepen political engagement with ARC across a range of African and international stakeholders.
Progress against expected results: / 3.1 - 80 consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept (for May 2012). The total following the first Annual Review was 115; and additional 76 have been conducted this review period. The target for June 2013 is 100; which has now been achieved. / 3.2 - Seven different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.). To date the ARC project officially has five grant-giving donors: DFID, Rockefeller Foundation, SIDA, World Food Programme’s internal Saudi innovation fund and the International Fund for Agricultural Development (IFAD), however the Swiss Agency for Development and Cooperation (SDC) intends to become a financial contributor to the ARC design phase – as well as the post-design phase – by the end of 2012. In addition, the project received in-kind support from the World Bank’s Global Facility for Disaster Reduction and Recovery (GFDRR) at the start of the project for the initial ARC feasibility study. The Republic of South Africa will support some of the costs associated with the plenipotentiary conference in November 2012. KfW Bankengruppe supported the costs of additional cost-benefit analysis and will host the ARC donor meeting planned for early 2013. KfW is also considering a financial contribution to the ARC post-design phase, together with DFID, the Swedish International Development Cooperation Agency (SIDA) and SDC. / 3.3 - Ten positive mentions of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments. 11 following first Annual Review and an additional 13 during this review period. This includes coverage in Africa Union, Regional and National contexts. The target for June 2013 is 20; which has now been achieved. / Recommendations: / There is more work to do to ensure this Output will be achieved. It’s important that the Project Team continue to build the case for donors to invest in ARC to ensure that the discussions and current contributions to design work lead to concrete commitments to support implementation. This in turn will also require work across other Outputs to pull the case for ARC together, including Output indicator 1.3 (economic rationale) and Output indicators 2.1 (financing and institutional structure) and 2.2 (operational manual and monitoring and evaluation guidelines). / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 4: Plan for the creation of the legal and organisational structure of ARC entity fully defined
Output 4 score and performance description: / Output score: A+ – Outputs moderately exceeded expectation / The Targets for this Output have largely been achieved.
Progress against expected results: / 4.1 - Legal structure of ARC defined, and vetted by the AU, donors, potential Member States, and legal experts - On-going dialogue with stakeholders regarding legal structure and incorporate input. The ARC Specialized Agency Establishment Agreement, adopted by countries at the plenipotentiary conference in South Africa (November) represents the culmination of a year-long design and expert, donor and member state consultation process by the ARC Project on the legal and institutional structure of ARC. Following the completion of the initial “Overview of Possible Legal Structures of ARC” report written by the ARC Legal Advisory team, and a round of initial consultations with donors and the AUC, the project embarked the process necessary, following AU protocols and procedure, for establishing ARC as a Specialized Agency of the African Union (ARC Agency). The process allowed for extensive feedback and incorporation of input and comments from industry, AUC and government experts through two stakeholder meetings – the ARC Validation Workshop and the Government Experts’ Meeting held in May and September 2012 respectively. The Target for this indicator is that the legal structure of ARC is finalised. This Target has therefore now been achieved. / 4.2 - Process for establishment of the ARC facility defined - Review of the most appropriate jurisdictions and venues for the establishment of ARC completed. A preliminary review of potential jurisdictions – “ARC F Jurisdictional Review” – has been completed by the ARC Project Team with the external legal counsel of 11 attorney and law firms, covering 11 potential ARC F jurisdictions. The Target for June 2013 is that the Establishment process agreed upon by ARC stakeholders and underway. This Target has therefore now been achieved. / Recommendations: / The Project Team needs to continue to influence and facilitate the political process. As the design work starts to be put into practice and implementation it is particular important that this Output is seen in relation to work on Output 1 and 2. It will be necessary to create the space and time to ensure all necessary parties are fully consulted and engaged (this includes African governments but also international organisations, donors and relevant private sector actors, such as the re-insurance industry). / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## If the project involves more than 4 Outputs please copy the box above and paste below.

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / Yes. The logframe was updated as a result of last year’s Annual Review (2011) in discussion with the ARC Project Team. The main changes were recorded on the latest version of the Project logframe and included a greater focus on what the Project can deliver (recognising the difference between the design process and implementation) and tightening the language used in specific indicators. / 1.2 Overall Output Score and Description: / A – Outputs met expectation / Many of the Targets for June 2013 have been achieved. This is in-line with the original timings for the Project before the no-cost extension was granted and the quality of the material generated has been of a consistently high-standard. However, more of the material generated needs to be made publicly available. / 1.3 Direct feedback from beneficiaries / No formal feedback was sought for this Annual Review from ‘beneficiaries’ – the term is perhaps more relevant for the implementation of ARC rather than the design process. However, implicit feedback is positive as there is considerable interest across Africa in ARC as evidenced by the fact the team have undertaken technical workshops in 18 different African countries and six countries have signed Pre-Participation Agreements (PPAs).
1.4 Summary of overall progress / Progress on the design of ARC has been very good and the major milestones have been achieved. There is still a considerable amount to be done to ensure a smooth transition from design to implementation but much of this will start to fall outside the direct scope of this phase of DFID’s support to ARC and hence the direct control of the Project Team; at the end of the design process countries need to be fully informed as to whether participation in ARC is right for them. The role of the Project Team will be to provide the information necessary for the Government in question to make an informed choice. / The building blocks for the implementation for ARC are now largely in place and the design of ARC is close to being successfully delivered. This is an excellent achievement in itself – but the best legacy of the design process will be a fully operational ARC and the Project Team can now start to focus on doing everything possible to ensure that happens over the next six months.
1.5 Key challenges / Pulling together all the strands of ARC to present a robust and coherent pitch for African Governments, international organisations, potential donors and other stakeholders to participate in, and support, ARC implementation; / Ensuring a clean transition between design and implementation. This includes questions around availability of material from the design phase, the role of the World Food Programme Project Team in ARC implementation (re the ARC Secretariat); / Supporting the Africa Union to ensure that the details of the ARC Specialised Agency meet the needs of participating countries and potential donors. These needs may be aligned, differ by degrees or in some cases be contradictory. This will include the need for appropriate and acceptable transparency, due diligence, reliability with a clear governance structure; / For the Project Team to start the process of ceding responsibility for ARC to the ARC Specialised Agency. Project Team staff have spent a lot of time in the last couple of years on ARC – however ownership now needs to broaden and this will require continued good management of the process. / However – the key challenge moving forward is to ultimately ensure there is sufficient interest and capital to operationalise ARC.
1.6 Annual Outcome Assessment / There has been good progress towards the achievement of the Outcome, but many crucial activities are only starting now and the next six months are therefore crucial to see the Outcome of the project realised. / Outcome indicator 1.1 – Draft detailed proposal for ARC risk pool.[4] This indicator has not formally been achieved at the time of this review – although the full Dynamic Financial Analysis should be available by the end of the year. A positive sign of interest in ARC is that six Pre-participation agreements have been signed. It is yet to be seen whether this will translate into request to join ARC once fully operational (this is the Target for 2013); / Outcome indicator 1.2 – In dialogue with at least three countries on contingency planning for contingent funds.[5] The Project Team are in direct contact with at least six countries on contingency planning through the PPAs but also with others through events such as the contingency planning workshop (South Africa, September 2012). However, attribution for this Outcome indicator will be difficult as the majority of countries engaged in this dialogue process already have well-advanced ‘contingency’ plans – although the format and scope with vary by national context. The cost-benefit work demonstrated that the value of ARC was greatest when contingent plans involve scaling up existing programmes – such as safety nets – on account of improved targeting and quicker delivery of aid to those who need it. / Outcome indicator 1.3 – Required capitalisation envelope determined by the number of countries.[6] This Outcome is on track but depends on activities that are still to be completed at the Output level. / Other positive outcomes of the design process are also being seen – such as new links being created between African countries on the issue of drought-related food security. For example, Ethiopia sharing experience of safety net schemes and disaster management / response directly with Niger through a series of workshops.
[4] The Indicator itself is ‘No. of risk pool participation requests received by project from national governments’.
[5] The indicator is ‘No. of countries with developed drought response contingency plans linked to regional contingent funds’.
[6] The indicator is ‘Percentage of funds committed against ARC donor appeal’

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Taking into account six month no cost extension letter (issued July 2012) to obligate the funds until 30 June 2013 and disburse the funds by 31 December 2013). / Initial payment of £ 2.1m was paid in Dec 2010. Two further disbursement each for £ 200,000 were made in August and December 2011. Latest World Food Programme ARC Interim uncertified Financial Statement as at 30 September 2012 shows an un-programmed balance of just USD 253,110 at 30 September. / 2.2 Key cost drivers / DFID funding has supported ARC design process. The key cost drivers have been: / Project Team staff costs; / Consultant cost – for additional technical work; / Travel (consultation and workshops). / 2.3 Is the project on-track against original timescale: Yes / The ARC Project logframe was revised in line with the recommendations of the Annual Review that took place in December 2011. The main change was a six month no-cost extension of the project to June 2013 to allow for in-country capacity building activities to continue for the 12 months (as originally envisaged) after the ARC project becomes operationally active in-country in order to enable full achievement on Output 1. This will also allow for enhanced achievement, and also provide a contingency buffer, across all other outputs. Given a design project of this size, scope and political sensitivity, it faced several challenges and constraints in its first year, many beyond the project's control. In particular delays in signing the World Food Programme – Africa Union Special Agreement, which has anchored the project firmly with the African Union Commission (AUC), took six months to secure. Delays with the World Bank supervised feasibility study also prevented effective movement on country consultations. Subsequent milestones and timelines have been adjusted accordingly and should be considered in each of the changes detailed below.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is increasing evidence of the challenges of responding to drought-related food insecurity (e.g. ‘A dangerous delay: The cost of late response to early warnings in the 2011 drought in the Horn of Africa’[7] and ‘The Economics of Early Response and Disaster Resilience’)[8] and the impact of climate change on the frequency and intensity of drought events (e.g. IPCC special report on Managing the Risks of Extreme Events and Disasters to Advance Climate Change Adaptation).[9] This evidence strengthens the case for an innovative approach to managing the risk of drought-related food insecurity and in particular to explore funding mechanisms that can release funds at the earliest possible opportunity. / The project has also built the evidence base for ARC itself through the cost benefit analysis work conducted by Clark and Hill. This study demonstrated that, given certain assumptions and under specific scenarios, that the benefits of investing in ARC are greater than the cost. The report concludes that if ARC can address a number of details (such as disbursement through well targeted safety net or state-contingent schemes that can be scaled-up quickly and that ARC covers extreme, rather than more frequent, smaller loss events) that it could lead the way in replacing the existing ad hoc food aid system in sub-Saharan Africa. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation planned
[7] Available from: http://policy-practice.oxfam.org.uk/publications/a-dangerous-delay-the-cost-of-late-response-to-early-warnings-in-the-2011-droug-203389
[8] Available from: https://www.dfid.gov.uk/.../Econ-Ear-Rec-Res-Full-Report%20.pdf
[9] Available from: http://www.ipcc-wg2.gov/SREX/

4. Risk
4.1 Output Risk Rating: Medium / See individual Outputs for specific ratings. / 4.2 Assessment of the risk level / Low – the Project Outputs have largely been achieved.
Risk of funds not being used as intended / Low - The World Food Programme (WFP) is a trusted partner for the delivery of humanitarian interventions. / For the WFP in general, the Multilateral Aid Review (MAR) found that financial resource management was deemed ‘satisfactory’. In particular it was noted that the WFP was the first UN organisation to implement International Public Sector Accounting Standards (IPSAS), since when it has achieved unqualified annual audits. Further, its financial accountability systems and processes are strong and the organisation is making on-going improvements. However, it was also noted that more effective risk management, including systematic risk assessment, is needed across the organisation. / The funds have all been used directly by the Project Team for the design process. / 4.4 Climate and Environment Risk / There is a low risk from a climate and environmental perspective; the most significant impact is the considerable amount of travel undertaken as part of the consultation and engagement with African governments. There is high opportunity from the programme given that it focuses on improving African capacity to reduce the risk from drought and ensure early responses.

5. Value for Money
5.1 Performance on VfM measures / ARC was approved before the current DFID Business Case format and Project Memorandum was not explicit in stipulating value for money measures. / The Project Team have been building the economic case for ARC through the Cost-Benefit analysis work mentioned above (Output 1). This explicitly considers whether investing in ARC makes sense compared to a range of different intervention-scenarios. / An important measure of the value for money from DFID’s investment in the design of ARC is the leverage that this funding has had in generating additional funding and interest from other donors. Current levels of funding are set out below: / Donor Contribution (US$) / DFID 3.9 million / Rockefeller Foundation 1 million / the Swedish International Development Cooperation Agency (SIDA) 3.1 million / The Kingdom of Saudi Arabia 1 million / The Global Facility for Disaster Reduction and Recovery (GFDRR) In-kind grant to support an initial World Bank financial feasibility study / International Fund for Agricultural Development (IFAD) 0.2 million / Swiss Agency for Development and Cooperation (SDC) Remaining balance, including 0.3 m to incorporate flood risk / 5.2 Commercial Improvement and Value for Money / None at this stage of the Project with six months to run. / 5.3 Role of project partners / The World Food Programme is coordinating the Project and leading technical input (such as Africa RiskView) / 5.4 Does the project still represent Value for Money : Yes / We have few similar examples with which to compare this particular design process. Based on results to date it is reasonable to suggest that the investment in the Project has been value for money – although no firm analysis has been undertaken to assess this. The reasons for this are twofold: / Africa RiskView – This has been a crucial element of the design process as it is this software, once adapted for specific country contexts that will provide the objective means of triggering ARC payouts. This is an extremely valuable product in its own right and has generated considerable interest amongst African stakeholders as a means of providing external validation for their own measures of vulnerability. Discussion are on-going with Google and NASA to start the process of further developing Africa RiskView and potentially including additional hazards, such as flooding. / Delivery of results to a high standard – the technical and consultative work that has been conducted during ARC has been done to a high standard. In particular, managing and supporting the African Union political process, conducted technical workshops across Africa and ensuring the multiple work streams of ARC have progressed at a suitable pace has required excellent organisation and capacity. The technical papers have all been produced by specialists outside the core Project team or independently reviewed and been found to be robust. This is perhaps to be expected given the level of resourcing provided to the Project but is still a notable achievement given how far the process has come in the last year. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / No conditions attached at this time.

7. Conclusions and actions
The current phase of DFID support to the Africa Risk Capacity is drawing to a close and the expectation, confirmed by this Annual Review, is that all Output and Outcome Targets will be achieved. / The Project has already exceeded some of the initial Targets at the Output level and the Project Team have done an excellent job in progressing the multiple elements of ARC in parallel, including the technical and political work streams. / The Project Team now need to ensure that the final outstanding areas of work can be completed on time and that all work to date can be brought together, consolidated and communicated clearly to all interested parties. This is crucial to ensure a smooth transition from design to implementation and will require delicate handling, balancing the different processes and stakeholders expectations. / Actions / Building on the results of the Annual Review, DFID will: / Continue to work closely with the Project Team to ensure the design work is successfully concluded, setting the stage for implementation of ARC; / Start work on the Project Completion Report in June 2013; / Building on specific comments across the Project Outputs, DFID will work with the Project Team to: / Ensure that the momentum generated to date continues – but balanced by the need to ensure that the full range of stakeholders are engaged. This might require a more nuanced approach by the Project Team to dealings with particular groups of stakeholders; / Continue to build the case for investment in ARC – this means working across the full range of Outputs where Targets have yet to be reached. Much of this work is already planned and will commence now ARC is established. But it is important not to neglect any of the remaining issues, such as: / Putting in place and independently reviewing a Monitoring system – tracking disbursement and effectives of targeting approaches and the contingency plans at country level; / Ensuring evaluation is built into ARC processes – in terms of the operation of ARC SA and ARC F and also disbursement at the country level; / Robust evaluation of the Governance for ARC SA – including an independent FRA to ensure appropriate standards of due diligence; / Building on the economic case to make a robust case for capitalisation; / Evaluate the national level customisation of RiskView; / Ensure that all remaining evidence required to make the case is in place. / Communicate widely and broadly the material generated by the design process to ensure all parties have the opportunity to critically evaluate the assumptions and methods that underpin ARC; / Ensure that the country risk profiles are available and provide a clear, detailed rationale for the operation of ARC at the country level. Such as how and where ARC fits in with other risk measures for more frequent impacts. / Consider developing a plan for technical development of Africa RiskView to potentially include additional sources of information. Flexibility and iteration should be built in early to ensure expectations of stakeholders are managed and that learning can take place. / A further set of actions concern potential DFID support to the implementation of ARC. Assuming the necessary approvals are in place, the Business Case process will start in December 2012 and aim for completion by the end of the design process (the no-cost extension for the project until June 2013).

8. Review Process
This review was conducted by Africa Regional Department lead advisor (Alex Harvey) with input from the ARC Project Team. / The following documents have been used: / ARC Annual Report, January- November 2012 (Quest: 3745909); / ARC Project logframe (Quest 3676518); / Cost-Benefit Analysis of the Africa Risk Capacity Project (ref above)