Business Case and Intervention Summary

Intervention Summary
## Title: GIRL HUB ETHIOPIA

What support will the UK provide?
DFID Ethiopia will invest £8.8m over the course of 2.5 years (September 2012 - March 2015). Of this, an initial £1m of funding for start up costs was approved in November 2011. This Business Case provides a proposal for the additional £8.8m.

Why is UK support required?
What need are we trying to address? / Adolescent girls aged 10-19 make up 24% of the Ethiopia population[1]. Nearly 7 million adolescent girls in Ethiopia live on less that US$2 a day[2]. Half of all Ethiopian girls are married by the age of 15 and less than half of girls aged 15-19 have completed primary education[3]. Nine out of ten girls need permission before leaving their house[4]. / Men and boys, and the community at large, neither value nor support girls. For example, 51% of boys agree that there are instances when a husband is justified in hitting or beating his wife[5] and 10% of married adolescent girls have experienced physical violence at the hands of their husbands[6]. / Adolescent girls fall through the cracks of development programming – with funding for gender work typically reaching older women, and youth work being targeted at boys. The Nike Foundation estimates that adolescent girls receive only 2 cents in every dollar of Official Development Assistance[7]. / What will we do to tackle this problem? / Girl Hub will influence partners working in Ethiopia to drive greater resources to girls. For example, Girl Hub will strengthen an alliance between the Ethiopian Government, donors and NGOs to increase the impact of existing work to end child marriage in Ethiopia. Girl Hub will also work with the secretariat of the $6.2 billion Promotion of Basic Services programme to develop evidence on the value for money of investment in adolescent girls – with an intention to influence the delivery of health, education, water and transport services for girls. / Girl Hub will drive behaviour change among girls and the wider community by developing a branded social communications platform named ‘Yegna’, meaning ‘ours’ in Amharic. The Yegna platform will feature a radio drama, which will create role models and highlight relevant social issues for girls. This will stimulate discussion in communities and will aim to create a safe, informed and inspiring conversation about the value of girls, the challenges and opportunities they face. Girl Hub will work with community-based organisations in order to reach and represent the most vulnerable girls. / Who will be implementing the support we provide? / Girl Hub is a strategic collaboration between DFID and the Nike Foundation. In Ethiopia, Girl Hub will be a DFID team. It will be based in a separate office, but use DFID systems and report to the DFID Ethiopia Head of Office as well as the Nike Foundation. Girl Hub will collaborate with government, development, private sector and civil society partners to use girl-centred approaches to implement existing policy, legislation and regulations. The Yegna platform will be implemented through a Creative Management Agent (CMA), which will be procured through DFID procedures. The other elements of the programme will be delivered by Girl Hub through a mixture of DFID staff, Girl Hub and Nike Inc staff, some of whom will be seconded to DFID Ethiopia.
[1] Ethiopia Demographic and Health Survey (2011)
[2] Ethiopia Demographic and Health Survey (2005)
[3] Ethiopia Demographic and Health Survey (2011)
[4] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[5] ibid
[6] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[7] Chaaban, J. and W. Cunningham. "Measuring the Economic Gains of Investing in Girls. The Girl Effect Dividend." The World Bank, Policy Research Working Paper p.23

What are the expected results?
What will change as a result of Girl Hub Ethiopia? / Girl Hub Ethiopia aims to help Ethiopia break the inter-generational cycle of poverty by 2030. At impact level, by 2020, Girl Hub Ethiopia aims to see 3 million girls inspired and their world transformed. This will be achieved by Girl Hub Ethiopia’s influencing role to: / Decrease the number of girls suffering from gender-based violence / Decrease the number of girls who marry or give birth before the age of 18 / Increase the number of girls who have completed primary and transitioned to secondary education / Increase the number of girls with control over economic assets / What are the planned outputs attributable to UK support? / At outcome level the programme aims to improve attitudes and behaviours towards girls which will be measured by an improvement in: / girls' perception of themselves (including the way they value themselves, their opinions and their abilities); / girls' access to information, supportive social networks and influence over their own life choices; / boys', parents' and community members’ perceptions and behaviours toward girls; and, / amount of new partner (government/donor/NGO) resource allocations for girls due to influencing by Girl Hub Ethiopia. / By 2015, the following outputs are planned to be achieved with UK support: / Nearly 10 million citizens will be inspired into action by branded social communications products and outreach strategies / Seven new initiatives targeting adolescent girls will be implemented due to Girl Hub Ethiopia’s catalytic and convening role / 12,000 citizens (half of whom are girls) will participate in research and girl-centred participatory M&E to generate real-time, robust evidence and insight for use by communications, systems, investments and policies / Girl Hub Ethiopia organisational development achieved and effective / How will we determine whether the expected results have been achieved? / A monitoring and learning strategy has been developed to define baselines and track progress of the impact, outcome and output indicators in the logframe. Girl Hub Ethiopia will be subject to DFID’s Annual Review process. There will be a mid-term review in 2013 and a project completion report in 2015. These reviews will done by a team combining Nike Foundation, Girl Hub and DFID expertise, and will include staff external to the Girl Hub collaboration, to ensure objectivity. At end of the project, independent evaluation will be used to determine whether expected results have been met.

Strategic Case

A. Context and need for a DFID intervention / A1 The Ethiopian Context / Ethiopia matters to the UK for a range of development, foreign policy and security priorities. It is populous, poor, vulnerable but comparatively stable in the Horn of Africa. From a low base, Ethiopia’s growth and expansion of basic services in recent years have been among the most impressive in Africa. The UK Government has an opportunity to make our support more transformational and accelerate Ethiopia’s graduation from aid dependency. The Government of Ethiopia (GoE) is capable and committed to growth and development, and is a proven partner in making rapid progress towards the Millennium Development Goals (MDGs). But its approach to political governance presents both substantive challenges to sustainable development and reputational risks to partners. / Ethiopia lies at the heart of an unstable region that has experienced almost continuous conflict and environmental shocks in recent decades. Ethiopia and its neighbours – including Somalia, Sudan, South Sudan and Eritrea – languish at the bottom of the Human Development Index. Poverty and instability in the Horn of Africa are among the drivers of migration to Europe, and also contribute to an environment in which fundamentalism and radicalisation can prosper. UK interests in the region include progress towards the MDGs, resolving conflict, bolstering stability, accelerating sustainable growth and development, mitigating the impact of climate change, tackling migration, and countering terrorism. A stable, secure and prosperous Ethiopia is critical to UK interests. / Ethiopia has come a long way in a short time, and has achieved stability through decentralised regional government. But Ethiopia has yet to successfully manage its democratic transition. The Ethiopian People’s Revolutionary Democratic Front (EPRDF) took power in 1991 and has held it since then. They have made progress towards a functioning democracy and respect for human rights, but there is still a long way to go. Ethiopia has a capable government that is demonstrably committed to addressing poverty, with an impressive record of pro-poor spending, sound financial management and relatively little corruption. The late Prime Minister Meles and others in GoE have played a role on global issues, including climate change, reform of the international financial architecture, and global health. / Ethiopia has made impressive progress towards the MDGs. In the last five years, with substantial support from the UK and others, Ethiopia has: halved the incidence of malaria; deployed 34,000 more health extension workers; doubled the immunisation rate[8]; rolled out an innovative social safety net to protect almost 8 million of the most vulnerable people[9]; and put 4 million more children in primary school[10]. Strong macroeconomic leadership has helped Ethiopia achieve annual growth of over 7 per cent for the last decade. GoE’s new Growth and Transformation Plan (GTP) targets a doubling of the economy and achievement of the MDGs by 2015, and a greater (if still limited) role for the private sector and accelerated industrialisation. The GTP provides a platform to align UK support with GoE’s ambitions, make it more transformational, and accelerate Ethiopia’s graduation from aid dependency. / Despite recent progress, Ethiopia remains one of the world’s poorest countries, with more than 30 million people living in extreme poverty. It is comparatively under-aided, receiving less than the African average per capita aid[11]. Strong progress towards some of the MDGs is from a very low base, and will be difficult to maintain as the needs of harder to reach populations are prioritised. Population momentum will see the current estimated population of 83 million people rise to around 120 million by 2030[12], which is likely to be accompanied by rapid urban growth. Ethnic nationalism and underdevelopment fuel instability and insurgency in parts of the Ethiopian periphery, threatening the delivery of Ethiopia’s development objectives. External shocks, including climate change and fluctuating commodity prices, threaten growth. Ethiopia was badly affected by the oil and food price shocks in 2008, and will find it difficult to avoid price rises as global prices rise again in 2011. / Ethiopia can absorb more aid and use it well. DFID is a leader within the development community, championing results, aid effectiveness and transparency. DFID works closely with UK Government partners in pursuit of shared objectives for a stable, secure and prosperous Ethiopia. / A.2 The Ethiopian adolescent girl context[13] / Being born a girl in Ethiopia is a major indicator of disadvantage. Widespread and extreme chronic poverty in Ethiopia masks patterns of social exclusion which result in some social groups facing more extreme and concentrated poverty, higher barriers to accessing assets and services, and a more difficult and less certain path out of poverty. Social exclusion on the basis of gender[14] creates significant additional barriers for women and age is an additional dimension of exclusion. When compared to boys in similar circumstances, girls in Ethiopia face high barriers to access services, assets and additional challenges to forging a route out of poverty. / Girls have less access to education and health services: While over 80 per cent of girls nationwide are now enrolled in primary school, only 16% are enrolled in secondary school.[15] With secondary schools concentrated in urban areas, access and opportunity for rural girls remain very limited. For example, most reproductive health services designed for young people are in secondary schools and urban areas.[16] In a nationwide survey of 12-24 year old girls, amongst those who had given birth, 92% rural girls and 51% urban girls had their first birth at home. 60.4% rural births in contrast to 19.4% urban births were attended by a female relative; 48.6% urban births but only 8.4% rural births were attended by a doctor, nurse or health officer.[17] And while messages about HIV/AIDs, contraception and female genital mutilation (FGM) have reached the majority of girls in urban and in rural areas - far fewer have information on menstruation, puberty, relationships or on violence in relationships.[18] / Girls have less access to legal services: Nationwide, 15% urban girls (12-24) who had been sexually abused sought medical care and 22% sought legal assistance. 7% of rural girls sought medical care and less than 1% sought legal assistance.[19] / Girls have less access to employment and training opportunities. Nationwide, 30% of urban girls (12-24) - and less than 20% of rural girls - report ever having worked for pay, with petty trade and domestic work being the main sources of income. In 2010, domestic work paid around 142 birr ($8.50, £5.20) monthly.[20] 9% girls (12-24) in urban areas - but less than 1% girls in rural areas - report having received vocational training, but most have not put their skills to use. They haven’t been able to find a job, have lacked start-up capital or haven’t known where to start.[21] / Existing cultural norms further limit opportunities and choice for young women and girls. Very early marriage and early motherhood continue to curtail the opportunities of too many teenage girls. In Amhara Region, 50% of girls are married by 15.[22] 81% of marriages for rural girls are arranged by their parents or extended family[23] - and 48% rural girls (12-24) did not want to get married or were undecided about their marriage.[24] For most Ethiopian girls, first sex takes place within marriage. 22.1% girls (12-24) report not having wanted their first sexual encounter, in comparison to 1.8% boys, and 33% of these girls were coerced into their first sexual experience.[25] Whilst national and age specific fertility rates have reduced over the last 10 years in Ethiopia, these are still a high 79 births per 1,000 women aged 15-19.[26] / Ethiopia continues to have one of the highest reported rates in the world of physical violence by male towards female partners. Forms of violence against girls include traditional practices such as female genital mutilation and marriage by abduction and rape, which remain highly prevalent in some parts of the country. More than 50% of girls questioned in a nationwide survey in 2009 thought there were circumstances where a husband would be justified in beating his wife.[27] / Girls in Ethiopia lack voice and influence. While women and youth are represented at all levels of Government, initiatives are focussed on mobilising rather than hearing from women and young people.[28] There are also few opportunities for social networking. While 83.4% girls nationwide go to religious institutions, only 6.2% go to youth clubs[29] and 21% of girls report they have no friends[30].Only 14% urban girls (21% urban boys) and 6% rural girls (12% rural boys) have their own radio. Just 18% urban girls (24% urban boys) - but less than 1% rural girls (2% rural boys) - have their own mobile phone reflecting the very limited network coverage in rural areas. [31] Adolescent girls lack the confidence and mean to report violence committed against them although 47% of girls know that there is a law in Ethiopia against, for example, wife beating[32]. / A.3 The Policy Context / There are clear imperatives for mobilising effort towards improving support for young women and girls in Ethiopia. / Achieving the Millennium Development Goal targets: Given the size of the country and scale of the problem achieving the gender related MDG targets will make a significant contribution to progress towards the MDGs both in Sub-Saharan Africa and globally. / DFID’s Business Plan (2011-2015) recognises the role of women in development and commits to lead international action to improve the lives of girls and women; in particular to work to empower and educate girls. / Following the launch of the Business Plan, DFID set out its Strategic Vision for Women and Girls. This sets out four pillars for greater and more effective action in order to ‘stop poverty before it starts and transform societies’ by: / Delaying first pregnancy and support safe childbirth / Getting economic assets directly to girls and women / Getting girls through secondary school / Preventing violence against girls and women / DFID Ethiopia’s Operational Plan committed to putting girls and women at the front and centre of all its programmes, including work to: build assets; create economic opportunities; promote voice and political empowerment; support specific initiatives to reduce violence against girls and women and stop early marriage. / The Government of Ethiopia (GoE) recognises in its Growth and Transformation Plan (GTP) (2011-2016) the potentially profound effect of supporting and harnessing the contribution of women and young people to the speed, equity and sustainability of national growth and development. Promoting gender and youth empowerment is one of the seven GTP strategic pillars. The GoE has also sought in recent years to eliminate discriminatory legal provisions. A new Ministry of Women, Youth and Children’s Affairs has been established to spearhead implementation of GTP commitments to empower women and young people – bringing together functions previously undertaken by a number of different Ministries. The Federal Ministry of Women’s Affairs, heads of Regional Women’s Affairs Bureaux and heads of Woreda (sub-regional) offices of Women’s Affairs have now become members of cabinet at their respective levels, and there are gender focal points in all line ministries. The GoE has allocated more resources to gender equality than previously and is in the process of establishing mechanisms for the implementation of national policies.[33]. The GoE has recently established a Youth Federation structure at all levels down to communities to facilitate young peoples’ involvement in governance, involving both young men and women, organised in different age categories, and including a youth leadership development programme. / A.4 Rationale and evidence for intervening / There is good evidence that investing in a girl is transformational, and stops poverty. Adolescent girls’ well-being is fundamental to determining social and development outcomes. Adolescence is a crossroad when life-changing events such as dropping out of school, marrying or having children, have consequences for young women and the next generation. High and unwanted fertility, intergenerational poverty, and poor health (including poor maternal and child health, and HIV) are propagated or halted by adolescent girls in the poorest communities. This concept underpins DFID’s strategic vision for girls and women and the Nike Foundation ‘Girl Effect’ (described in detail in the theory of change section). / The economic cost of dropping out of school to marry and have children or contribute unpaid domestic labour is high, and limits progress toward development goals. Pregnancy and childbirth-related deaths are the number one killers of 15-19 year old girls worldwide (each year nearly 70,000 die). The opportunity costs of adolescent pregnancy amount to $207.9 million per year and $10.4 billion, or 14.65% of GDP over a lifetime[34]. Adolescent pregnancy is expensive. High health care costs, higher social welfare costs; less educated, less skilled workforce, limiting human resources available for socio-economic development; increased dependency of young mothers on male providers perpetuating gender inequality; increase population momentum and fewer opportunities to rely on growing youth population to help accelerate economic development; reduced prospects for eradicating poverty. / Girls have fallen through the cracks. Adolescent girls are not being reached by development interventions. The needs of adolescent girls rarely get attention in the face of competing Government and donor priorities, are rarely distinguished from the wider categories of “youth”, “women” and the “girl child”, or recognised in their cross-sectoral complexity. Children’s programs predominantly focus on girls and boys aged 0-5 years. Youth programs (often defined as girls and boys aged 15-30) tend to reach males who are older. Population Council research on four countries’ youth programs indicated program benefit by a ratio of 2:1 males to females, and almost half of all beneficiaries were over 20 years of age. Women’s programs do not typically capture girls, and if they do, they often fail to address the root causes of poverty. Domestic work burdens also result in girls’ diminishing opportunities for social participation and access to programmes. / Most existing targeted interventions are small scale. NGOs typically face constraints in terms of the sustainability and spread of impact, delivering at scale, and quality control. Civil Society Organisations (CSOs) in Ethiopia are almost exclusively involved in community level service delivery and awareness-raising. Foreign-funded CSO involvement in policy advocacy is illegal. There are a few targeted community level CSO programmes specifically for adolescent girls, funded by the Nike Foundation and Population Council. Further activities to meet the needs of adolescent girls depend to a large extent on the availability of funding and support from development partners. The UN is currently the main development partner across Government supporting initiatives on the empowerment of young people, including young women and girls. There are few government/development partner initiatives exclusively focused on adolescent girls. / A generally favourable policy environment in Ethiopia has already helped deliver some successes. For example, government prioritisation of gender parity in education has achieved increases in girls’ access to education at all levels, and NGO support to government and with communities to implement existing policy and legal frameworks at community level has demonstrated small scale solutions for girls, e.g. in relation to early marriage and female genital mutilation (FGM). However there are constraints and barriers to achieving more for girls, ranging from legal constraints to civil society organisations operating in the field of gender in Ethiopia to capacity and financial constraints in government. / A.5 What is Girl Hub? / Girl Hub is a strategic collaboration between DFID and the Nike Foundation that seeks to transform the lives of adolescent girls, with girls themselves as active participants in identifying and creating solutions to the challenges that they face. It is designed to combine the best of DFID and the Nike Foundation, to bring energy and inspire efforts to do more and better for girls at scale and to expedite progress towards eliminating gender inequality and ensuring faster progress towards the MDGs. / Girl Hub is a catalyst for expanding the ‘girl effect’ – the evidence that investing in an adolescent girl is one of the best ways of ending intergenerational poverty. Girl Hub measures its success through tangible changes in the lives of adolescent girls, focusing on areas which evidence shows to be particularly important for the girls themselves, their future children and for wider economic and social development. This includes the numbers of girls avoiding child marriage, delaying their first pregnancy and birth, accessing and completing secondary school, and benefiting from economic opportunities and assets. / Girl Hub delivers results for girls through a unique combination of: expertise on and learning from adolescent girls; communications; innovation investments; and influencing others to take action to scale, all drawing on both the public and private sector. / Girl Hub seeks to empower millions of adolescent girls. Instead of implementing large scale service delivery programmes, Girl Hub develops social communications to inspire and engage girls, and shape how societies view and value girls. It also informs and influences decision makers to invest in effective policies and programmes that benefit girls. / The first phase of Girl Hub has operations in three different African country contexts, in Nigeria, Rwanda and Ethiopia, as well as in London to drive global initiatives, with some staff based in Portland, US. / Both Nike Foundation and DFID contribute programme funds and staff to the Girl Hub: / DFID provides an £11.6m Accountable Grant that funds the start-up and core activities in UK, Rwanda and Nigeria from central funds. This includes £0.7 million specifically for communications work funded by DFID Rwanda, and also £0.7 million for the design of Girl Hub Ethiopia up to October 2011. This business case is for a separate funding stream directly from DFID Ethiopia to fund Girl Hub Ethiopia (starting with £1 million approved in November 2011). Globally to date DFID has seconded 6 full time staff to Girl Hub, including 3 Country Directors and a Deputy Managing Director, all working for Girl Hubs as secondees to Nike Foundation. / Nike Foundation contributes £10.7m in funding and in-kind contributions, plus an estimated 25 full time employees to deliver Girl Hub strategies across the three countries and globally. / The Nike Foundation brings its capabilities in creative development (brand marketing, social communications, design innovation and consumer insights) and a specialism in developing solutions with and for adolescent girls. DFID brings its deep expertise in designing and delivering development programs at scale, its role as a major bilateral donor, relationships with government and other development partners and research and measurement expertise. / Why set up a Girl Hub in Ethiopia? / Since early 2010, Girl Hub activities have been taking place in Ethiopia using funds from the DFID central grant. As part of DFID Ethiopia’s Operational Plan in November 2011, DFID approved a £1 million initial business case to set up a Girl Hub in Ethiopia. This decision was based on the overwhelming evidence that adolescent girls are neglected by development programmes and yet with the necessary support, can be transformational in improving development outcomes. There was also an appetite to test new ways of approaching gender within DFID Ethiopia. The DFID Ethiopia Operational Plan includes commitment to drawing on private sector expertise and dedicating staff and resources to innovative ways of working as an effective way of implementing DFID Ethiopia’s strategy for women and girls. / What has Girl Hub achieved in Ethiopia? / In preparation for this Business Case Girl Hub developed a progress report, to capture learning and results delivered in Ethiopia to date (using both the original central grant and separate DFID Ethiopia start up funds). Highlights from this report are summarised below[35]: / Use brand and communications to inspire and enable: / In partnership with the BBC World Service Trust, a short film was produced featuring the lives of 4 everyday girl heroes. Over 160 film screenings took place in communities throughout Amhara and Oromia regions, with audiences of around 110,000 people, of which 38% were women or girls. Some screenings featured facilitated discussions with community leaders. These results exceeded the original programme targets of 66 planned screenings, reaching 32,750 people, of which 20% were women and girls. Six debates on issues arising from the films were aired on national radio and popular demand has resulted in repeat airings of these debates, the copying and distribution of the film on DVD and a request from the Ethiopia Radio and Television Agency to broadcast the film on national TV, demonstrating contextual relevance and resonance. / Influence leaders to deliver for girls: / Girl Hub Ethiopia has played a key role in establishing the Alliance to End Child Marriage with government and other relevant partners. The purpose of the Alliance is to support the delivery of the National Strategy on Harmful Traditional practices, building a network of practitioners and improving social communications work on ending child marriage to deliver greater impact at scale. The Alliance has been endorsed by over 30 partners nationally, and is lead by a steering committee of seven partners. / Girl Hub Ethiopia has started discussions with the Secretariat of the Promotion of Basic Services Programme to design a high-level advocacy experience that will build the necessary commitment within Ministry of Finance to drive a larger share of national and donor resources to girls. This $6.2 billion programme is supported by multiple donors and reaching all of Ethiopia’s population (bar those in Addis Ababa) with basic services in health, education, roads, agriculture, water and sanitation. / Girl-led insights, evidence and learning: / Girl Hub Ethiopia did deep qualitative work with girls in Addis Ababa and in a rural location in Amhara district. Activities included 1:1 interviews, self documentation, diaries, and focus group discussions. Girl Hub Ethiopia used these ‘Insights’ to develop a social communications strategy so as to create credible role models who Ethiopian girls and society at large can relate to. Girl Hub Ethiopia has also started to use an innovative story collection methodology called SenseMaker in Ethiopia, as a monitoring tool as well as for grounding programme activities and social communications products in girls’ needs and realities. / Girl Hub Ethiopia has developed a Monitoring and Learning strategy, Logframe, Value for Money strategy and developed a methodology to establish a baseline for societal attitudes, perceptions and behaviours toward girls. / Girl Hub Ethiopia has commissioned a social exclusion analysis to build the evidence on the most excluded girls in Ethiopia. This has been used to develop a strategy to increase effort to reach ‘the last girl’ across Girl Hub Ethiopia operations. The strategy will ensure that Girl Hub tracks which girls we reach, what it costs and takes account of UNICEF’s work on the value for money of reaching the most marginalised girls. / Girl Hub Ethiopia organisational development achieved and effective / Girl Hub Ethiopia has built a small team since the start of 2012, growing from two full-time staff members to seven. Of these, two are DFID Home Civil Service (HCS) staff and two are seconded from Nike Foundation. Another two staff appointed in country are bringing skills in finance and administration. Girl Hub has moved to as separate office, which has been equipped for use as of September 2012. / Girl Hub conducted an internal audit in June 2012, which addressed the recommendations of the Independent Commission for Aid Impact Report on Girl Hub, the most recent DFID annual review of the central grant and a DFID Internal Audit to DFID Ethiopia on Girl Hub.[36] On the basis of this internal audit, Girl Hub Ethiopia has developed a plan with milestones to address priorities such as strategic workforce planning and child protection capacity.
B. Impact and Outcome that we expect to achieve / DFID Ethiopia will support Girl Hub Ethiopia with the aim of helping Ethiopia break the inter-generational cycle of poverty by 2030. At impact level, by mid 2020, Girl Hub Ethiopia aims to see 3 million girls inspired and their world transformed. This will be achieved by Girl Hub Ethiopia’s influencing role to: / Decrease the number of girls suffering from gender-based violence / Decrease the number of girls who marry or give birth before the age of 18 / Increase the number of girls who have completed primary and transitioned to secondary education / Increase the number of girls with control over economic assets / At outcome level the programme aims to improve attitudes and behaviours towards girls which will be measured by an improvement in: / girls' own perception of themselves (including the way they value themselves, their opinions and their abilities); / girls' access to information, supportive social networks and their influence over their own life choices; / boys', parents' and community members’ perceptions and behaviours toward girls; and, / amount of new partner resource allocations for girls due to influencing by Girl Hub Ethiopia. / What are the planned outputs attributable to UK support? / By 2020, the following outputs are planned to be achieved with UK support: / Nearly 10 million citizens will be activated and inspired by branded social communications products and outreach strategies / Seven new initiatives targeting adolescent girls will be implemented due to Girl Hub Ethiopia’s catalytic and convening role / 12,000 citizens (half of whom are girls) will participate in research and girl-centred participatory M&E to generate real-time, robust evidence and insight for use by communications, systems, investments and policies / Girl Hub Ethiopia organisational development achieved and effective / Which girls will we work with? / There are an estimated 8.5 million girls in Ethiopia aged 10-19, of whom 40 % or c.3,600,000 are living under US$1.25 a day.[37] However this statistic does not describe the full range of vulnerability girls experience due to both their sex and their circumstances. Girls who are vulnerable because they are girls can be found above the poverty line. / Girl Hub is committed to reaching the last girl, and has a developed a reach strategy which will ensure that focused, inclusive and enabling interventions set out in the integrated strategy below will reach the different groups of girls to give the greatest returns. / In summary, Girl Hub will work with: / 1. ‘Invisible girls’ or those who are the poorest and most vulnerable, which roughly overlaps with the lowest 20% in terms of income poverty. These are girls who may be affected by one or several of the following: / Working in exploitative circumstances, including domestic work / Living on the street; / Affected by HIV/AIDS; / Are sexually exploited; / Are living with disabilities; / Lack reliable adult care; / Are displaced or in humanitarian settings; or, / Are living in institutions. / These girls are unlikely to have completed primary school. They can only be found and reached with time intensive, face-to-face interaction. Girl Hub Ethiopia will partner with organisations (e.g. NGOs and community based organisations), who are highly experienced in this kind of work to amplify their work and promote impact at scale. / 2. ‘Connected’ yet vulnerable girls are probably living in the 20-50% category in terms of income poverty, but moving in and out of poverty. They share some of the circumstances described above but have some protection through assets, education and adult care. However they are highly vulnerable to shocks. Girl Hub Ethiopia will work to build the protective assets of these girls and create an environment which supports their resilience. We will do that through social communications and working with existing scale partner programmes to improve girl-centred design. / 3. ‘Integrated’ but vulnerable girls, living in the 50-100% income wealth category, but for whom the environment of gender discrimination makes it impossible for them to achieve their full potential and still leaves them vulnerable to violence, discrimination and exploitation. Girl Hub Ethiopia will reach these girls through work to improve the enabling environment for more inclusive and focused interventions on major issues such as gender-based violence. / Data will be disaggregated routinely by these ‘categories’ so that we can track who are reaching, with what and to what effect. This will enable us to build on existing evidence, which shows greater value for money from investment in the poorest girls[38].
[8] Federal Democratic Republic of Ethiopia (2010) Health Sector Development Programme III, Annual Performance Report: EFY 2002 (2009/10). Federal Ministry of Health, Addis Ababa.
[9] Devereux et al (2006) Ethiopia’s Productive Safety Nets Programme. Trends in PSNP Households with Targeted Transfers. Institute of Development Studies, Sussex.
[10] Federal Democratic Republic of Ethiopia (2010) Education Statistics Annual Abstract: 2009 - 2010. Ministry of Education, Addis Ababa
[11] OECD.STAT: data extracted on 20 Jul 2011 07:17 UTC (GMT)
[12] Population Division of the Department of Economic and Social Affairs of the United Nations Secretariat, World Population Prospects: The 2010 Revision, http://esa.un.org/undp/wpp/index.htm, data extracted on Wednesday July 20, 2011; 4:33:42 AM
[13] The sections following draw heavily on scoping work, commissioned by DFID Ethiopia, by Helen Derbyshire, independent consultant.
[14] “Gender” refers to the cultural norms and expectations – on roles, responsibilities and relationships - that shape women’s and men’s lives.
[15] EMIS (2009-2010) Educational Statistics, Annual Abstract
[16] National Adolescent and Youth Reproductive Health Strategy (2007-15)
[17] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[18] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[19] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[20] Figures reported in the Ethiopia Young Adult Survey, Population Council/UNFPA 2010
[21] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[22] EDHS (2011)
[23] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[24] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[25] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[26] EDHS (2011)
[27] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[28] UNICEF (2010)
[29] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[30] ibid
[31] Ethiopia Young Adult Survey, Population Council/UNFPA (2010)
[32] Ethiopia Demographic and Health Survey (2011)
[33] UNICEF (2010)
[34] Chaaban, J. and W. Cunningham. "Measuring the Economic Gains of Investing in Girls. The Girl Effect Dividend." The World Bank, Policy Research Working Paper #5753. 2011. - see page 32, table 3.
[35] Girl Hub Ethiopia Narrative Report 2012
[36] See Girl hub Ethiopia Internal Audit Report, Louise O’Rourke, July 2012
[37] EDHS poverty data 2011
[38] 47.5 % of girls complete primary school, EDHS 2011

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / A1: Generating feasible options: / When we invest in girls, remarkable things happen. One extra year of secondary school boosts a girl’s eventual wages by up to 25 per cent. When women and girls earn income they reinvest 90% of it into their families, compared to typically 30-40% for men. Work commissioned by the World Bank for the Nike Foundation estimates that if Ethiopian girls completed secondary school, the total contribution over their lifetimes to the Ethiopian economy would be US$6.8 billion. However, currently less than 2% of the £3.5 billion in official development assistance (ODA) reaches girls. If it does reach them, it is unlikely to be reaching them early enough, or with the right things. / The ‘girl effect’ theory of change hypothesises that by investing in an adolescent girl, we not only transform her life chances, but also the life chances of her future children and her community. If we invest in enough girls, we can unleash the potential of whole nations. The theory of change addresses both the demand and supply side constraints to tackling poverty for adolescent girls. / On the demand side, the theory of change refers to the need to ‘ignite a girl’s potential’. This means finding safe ways to increase a girl’s self-efficacy to a level at which she believes she can and should aspire to complete education, be healthy, and lead a fulfilling life. / On the supply side, the theory of change refers to ‘transforming her world’ with the need to both ‘deliver resources’ to girls and to ‘remove barriers’ that prevent them from staying in school, staying healthy and earning a safe income. This includes changing the hearts and minds of those around her – men, boys, her family and community - so that she is valued and listened to. It also includes developing scale solutions to ensure that a fairer share of existing ODA reaches girls and is effective at meeting their needs. / The Girl Effect Theory of Change is based around the principle that small amount of targeted resource can have a major impact on delaying first pregnancy and age of marriage, on getting girls through school and on improving girls’ control over economic assets. Simply put - investing more in good quality interventions targeted to adolescent girls represents good value for money. / The Girl Hub Theory of Change sets out the evidence and assumptions underpinning the proposition that investment in Girl Hub Ethiopia will ignite girls’ potential, deliver resources to girls, and remove barriers. In order to catalyse the Girl Effect at scale, the Nike Foundation has developed an ‘integrated strategy’ to guide all Girl Hub operations. This sets out how Girl Hub Ethiopia will deliver the girl effect at scale. Globally, Girl Hubs will: / Use brand and communications to inspire and enable / Influence leaders to deliver for girls / Produce girl-led insights, evidence and learning / Cultivate innovations in the market. / The theory of change below interprets the global Girl Hub integrated strategy for the Ethiopian context. / Figure 1: Theory of Change (Key assumptions are shown in the yellow ovals) / This theory of change will therefore test: / The success of the Girl Hub Ethiopia model as a catalyst and influencer; / The use of a branded social communications platform to achieve the girl effect at scale / The value for money of investing more in adolescent girls. / Assumption Evidence base / Girl Hub Ethiopia can understand and adapt to the evolving local political economy Having the political space and support to work on adolescent girls’ rights and social communications is an assumption. Early consultation with GoE and others has confirmed an appetite for increased donor programming on girls, in support of delivery of the Growth and Transformation plan objectives. The political governance environment under the Civil Society Proclamation does not permit international civil society organisations to work directly on womens’ rights. However there has been a positive response from government for DFID and Nike Foundation to work with and for girls through Girl Hub. Girl Hub will collaborate with government, development, private sector and civil society partners to use girl-centred approaches to implement existing policy, legislation and regulations. Girl Hub Ethiopia will use management tools, which seek qualitative data from partners and work with an Independent Advisory Group to ensure interventions are appropriate to the Ethiopian context. The impact of the political governance environment and the civil society legislation on Girl Hub Ethiopia’s ability to register as an independent organisation in the future will also be monitored. / Strategic partnership encourages innovation and generates excitement about the girl effect To be tested – as above. Positive evidence to date, for example through the Ethiopian Health Minister’s engagement in the UK Family Planning Summit in July, interest and demand from development partners. / It is possible to reach the poorest and most vulnerable girls Girl Hub Ethiopia has used existing global and Ethiopia-specific evidence to conduct analysis, which has informed a reach strategy (outlined above). Girl Hub Ethiopia will contribute to building the global evidence base on who the most vulnerable and excluded girls are, what the social, political and economic structures and processes are that we need to engage to reach them, what it costs and what the impact is. Girl Hub Ethiopia will track its own success in reaching excluded girls through the Monitoring and Learning Strategy. / Unleashing the girl’s potential can break the intergenerational cycle of poverty Strong evidence in some sectors, e.g. the impact of girls’ education on fertility rates. Girl Hub will commission research to understand the evidence as necessary. DFID’s Research and Evidence Department will fund a longitudinal study, including Ethiopia, to build the global evidence base. / A dedicated Girl Hub can align resources and actors to deliver for girls. To be tested – Monitoring and Learning Strategy (including vfm analysis) and logframe. / Decision makers are convinced by girl-driven data and evidence To be tested - as above. The logframe tracks progress, for example in resource allocation. / Branded communications and outreach amplify behaviour and attitude change. There is sufficient evidence to suggest that this is a reasonable assumption. The design of Yegna draws on global evidence of what works in social communications approaches and the experience of private sector marketing. Girl Hub Ethiopia’s Monitoring and Learning Strategy and value for money strategy are designed to build evidence on the added value of brand and of integration of social communications across a platform, and combined with scale outreach interventions. / A2. Summary of Feasible Options / Initial approval of £1 million for Girl Hub Ethiopia was based on the evidence that investing in girls is good value for money and made the case that dedicating increased resource to adolescent girls through setting up a Girl Hub would be more effective in delivering results for girls than the alternative of ‘business as usual’ (i.e. gender mainstreaming across the DFID Ethiopia programme). It also assessed the evidence for setting up Girl Hub Ethiopia or a counterfactual. / All Girl Hubs are required to deliver against the Girl Hub Integrated Strategy components listed above. This appraisal case will focus on alternative ways of delivering against the Integrated Strategy. The appraisal case reviews the state of evidence for alternatives on the cost efficiency for components one and two only. Component three is set out as one main option and the fourth component ‘Cultivate innovations in the market’ refers to the setting up of the Girl Hub in Ethiopia. The latter will not be appraised as approval for this has already been given, but is detailed within the management section of this business case. / The options for cost efficient delivery of components one and two are summarised in the illustration below: / Component 1: Use brand and communications to inspire and enable / Output: Branded social communications strategies and outreach activated / Within this component, the following options have been considered: / Option 1: Produce a single social communications campaign based on a youth magazine for girls and other related products: This option would involve Girl Hub producing and distributing its own media content. An example might be, a poster campaign linked to a magazine which has comic strips, articles, letters and stories which provide information to girls and stimulate debate about the challenges they face. This can create rapid impact in the short term. In this approach international experts are often used to take editorial control and ensure the messages are consistent with development aims. / Option 2: Produce a social communications platform based on radio drama and other branded products: This option would see Girl Hub work with the Ethiopian private sector/media industry to produce a long-running radio drama using role models which girls can relate to. This would be complemented by a radio talk show to create the opportunity to debate the issues raised by the drama. The radio drama and talk show would be part of a single brand which could be expanded to incorporate development interventions such as school clubs. / Assessing the evidence base for each option / There is a wide evidence base that the use of social communications (or social marketing) can change behavior. Review of this evidence reveals the following lessons about what makes social communications more or less effective in delivering behavior change goals: / Mass media has delivered changes in knowledge, attitudes and behaviour, from ‘The Archers’ to Brazilian telenovelas. / Drama is an effective way to engage large audiences and to deal with a range of relevant issues. / Behavioural interventions are most effective when they are relevant and entertaining, when they provide models of desired behaviors, and when they are linked to social and cultural narratives. / Modeling through mass entertainment is not sufficient. Effective strategies need to factor in the opportunities and obstacles found on the ground and in communities. / Both media and interpersonal intervention activities should be linked to existing resources in the community and, wherever possible, provide increased access to preventive services, supplies, and other supporting elements. / Duration of listening is associated with more positive outcomes than the other measures. There may be a stronger correlation between exposure to these programs and behaviour change. / Using mass media alone can stimulate conversations among listeners, which create opportunities for social learning as people, individually and collectively, consider new patterns of thought and behaviour. / Social conversations about educational content create a learning environment, in which people evaluate previously held ideas, consider options and identify steps to initiate social change. Listening together is important. / Strategies for dealing with resistance to change need to be built in, e.g. engaging religious leaders, or men and boys. / This evidence points towards building a long-running and sustainable campaign – such as that suggested through option two – which can sustain different story strands over a long period of time, address various themes relevant to the desired behaviour change, and spark conversations within communities. / Option Two also aims at building a sustainable solution by building the capacity of the Ethiopian media industry to drive and support social and economic change by producing programming which can reach an excluded audience and as champions for the girl effect at scale. / Assumptions to be tested: / The potential power of branding / The Nike experience in creating successful brands suggests that brands thrive by creating cultural relevance, and that individuals adopt brands as symbols of aspiration. There is less evidence of the potentially powerful role that ‘branding’ can play in ensuring that any development communications initiative has traction in society. Girl Hub has assessed a brand called ‘Yegna’ as part of the development of option 2, which would be rooted in Ethiopian culture and speak to the aspirations of an emerging adolescent mind-set. Girl Hub Ethiopia will test the assumption and build the evidence that branding will make the social communications platform more effective. / Radio and music / Evidence from an FCO funded Audience Survey in Ethiopia has revealed that over 70% of the population has access to a radio and that nearly 60% of people listen to the radio every day[39]. TV is popular in urban areas and in public places, such as bars, hotels and restaurants. However, in the more remote regions, this access decreases to as little as 10.5% of the population, in comparison to 61% accessing the radio in the same area. Girls have more control over radio than TV (60% as opposed to 43%). The same survey documented that consumption of printed media is very low in Ethiopia (just 13.3%). This partly due to issues around distribution (size of the country, limited road network and transportation systems) and due to low literacy levels, with radio/TV easier to understand than written language. The Audience Survey found that music was a very popular and powerful storytelling vehicle, something that was used to explore issues in society and something that people across social divides were hugely passionate about. / There is no directly comparative evidence from Ethiopia for a social communications platform. The Girl Hub Monitoring and Learning Strategy, linked to the logframe, will test the validity of the assumption (based on the evidence set out above) that a branded social communications platform can lead to attitudinal and behavioural change in the Ethiopian context. / Component 2: Delivering for Girls / Within this component, the following options have been considered: / Option 1: Influencing others. In this option, Girl Hub Ethiopia would play a convening and influencing role with other partners active in Ethiopia to adjust their programming so that girls benefitted from a greater share of development resources. / Option 2: Direct implementation by Girl Hub. In this option, Girl Hub Ethiopia would implement projects and programmes which directly benefit girls, for example through directly sponsoring girls through secondary school, or developing end child marriage projects or setting up skills training and micro-finance programmes. / Component 2: Assessing the evidence base for each option / Girl Hub will collaborate with government, development partners, private sector and civil society partners. Girl Hub will use bespoke communications and training materials, based on evidence, to inspire and support partners to do more and better for girls. This might include for example providing assistance to: / Co-commission research and evidence on what is happening to girls / Use evidence and amplifying girls’ voices in policy debates / Create girl-led programme design workshops which start with girls’ experience and engage girls’ in innovating new solutions / Develop and support networks of girl champions or new partnerships to advocate for girls or share resources and lessons. / There are currently around 25 development partners in Ethiopia providing around US$3.5 billion in aid annually. Girl Hub Ethiopia will seek 3-5 opportunities at any one time to work with partners in the following three ways. Girl Hub Ethiopia will look for: / Opportunities to increase the focus on girls in existing national or large donor programmes. For example, Girl Hub provided technical assistance to DFID E to put girls at the centre of their Operational Plan. Girl Hub Ethiopia has been invited by the World Bank Secretariat of the Promotion of Basic Services Project to influence future design and implementation of a c.$500 million/year providing services to three quarters of Ethiopia’s population. Influence in this programme has the potential to reach 33 million adolescent girls in the long term. Girl Hub will provide technical and communications support to increase government and funder understanding of the potential returns to greater investment in adolescent girls. / Opportunities to co-design new scale programmes, taking a girl-centered approach. To date this has included Girl Hub Ethiopia providing technical assistance to design teams for new DFID programmes in Ending Child Marriage, Community Security and Justice and Adolescent Reproductive Health. Girl Hub Ethiopia is working with a consortium of partners led by Save the Children under the Girls Education Challenge Fund to raise £10 million to support education for 18,000 of the most excluded girls in Afar region. Girl Hub has provided support including insights with excluded girls and technical advice on girl-centered programming. / Opportunities to support existing girl champions to achieve impact at scale through networking. For example, Girl Hub Ethiopia is a founding member of the national Alliance to End Child Marriage, a network of 30 partners chaired by government. Girl Hub is a member of the Steering Committee, bringing technical assistance to develop an effective network, design a communications strategy and build technical excellence. / Girl Hub Ethiopia will select and prioritise partnerships based on reaching the goals set out in the logframe. For example, we will focus on partners who have a strong shared interest in decreasing the number of girls who marry or give birth before the age of 18 or seek to get girls into secondary school. Girl Hub Ethiopia will use the Quarterly Assessment Scorecard process as an active management tool to monitor how well the number and quality of partnerships are delivering against logframe results. / Option two would require a model fully staffed to deliver directly to girls in a range of sectors. / Component 3: Research and girl-centred participatory M&E generate real-time, robust evidence and insight / The purpose of the Research and Participatory Monitoring and Evaluation component is a) to strengthen the two other components, and b) to generate an evidence base across both the ‘Girl Effect’ and ‘Girl Hub’ theories of change. This component therefore covers: / work to understand more about what happens to girls and what matters to them / work to track changes in attitudes, behaviours and results for girls / Girl Hub Ethiopia’s own work to learn more about what is working to inform management decisions on on-going value for money assessment. / Within this component, the following option has been considered: / Participatory research, monitoring and learning, using mixed methods. This option considers using participatory methodologies, which allow girls themselves to identify their main concerns, and uses technology to share real-time data with communities. The approach uses a hybrid methodology that combines story collection with a participatory attitude and behaviour survey, using the SenseMaker tool. SenseMaker is an exciting new methodology, which has not been used previously in Ethiopia[1]. The content of stories collected using SenseMaker would inform creative development processes such as the development of storylines for the radio drama and for influencing leaders. / The outputs from SenseMaker research will be used to ensure that the content of the social communications platform is grounded in what girls are telling us. Similarly, research will be driven by insights from girls themselves and integrated into communications and advocacy materials to influence decision-makers. Girl Hub Ethiopia will commission at least 3 pieces of research a year, on themes drawn from participatory and insights work with girls (including SenseMaker findings). It will ensure that the content of communications and advocacy products for decision makers reflect girls’ voices and what matters to them. / Girl Hub Ethiopia’s own work to learn more about what is working has been underway since November 2011. Girl Hub Ethiopia routinely collects information to inform management decisions and on on-going value for money work through a collaborative qualitative assessment scorecard (QAS) exercise. The Girl Hub Ethiopia team fill in a scorecard on a quarterly basis to document their perspectives on progress and results. The results of the QAS will be shared twice a year with select external partners, in order to challenge/validate Girl Hub Ethiopia’s self-evaluations and provide an informed outsider’s perspective on Girl Hub Ethiopia progress toward achieving outputs. Lessons learned will inform decisions, as described above. The scorecards cover each of the four outputs in the Girl Hub Ethiopia logframe, identifying key achievements, challenges, lessons learned and strategies for action moving forward. / In developing the above option, we considered the alternative of relying on existing data or tools, such as annual quantitative surveys to track changes in girls’ lives in a quantitative manner. This would be lower cost, although some methodological innovation would be needed to ensure that the quantitative data was reflecting the experiences of adolescent girls. However, given the importance of monitoring the direct impact of the social communications platform, elevating girls’ voices in scale interventions and building mechanisms for Girl Hub to learn, document and share lessons we have disregarded this option. / B. Assessing the strength of the evidence base for each feasible option / Girl Hub Ethiopia is an innovative collaboration which is testing new approaches to delivering results for girls. The evidence base for investing in adolescent girls is strong, but evidence regarding the effectiveness of different approaches to working with girls will be closely monitored through this programme, in order to strengthen the evidence base of what works to achieve better results for girls. / What is the likely impact positive and negative on climate change for each feasible option? / This programme offers the opportunity to relay positive environmental and climate change messages, which relate to girls through the social communications platform, reaching a targeted 5 million people. The option assessed above with the largest potential negative impact is the campaign including a youth magazine, which would require paper, packaging and transportation for delivery. Whilst recycled or sustainably sourced paper would be an option in many countries, this is not presently readily available in Ethiopia. Producing a digital option of the magazine would fail to reach the target group in terms of limited internet coverage in Ethiopia and access to it by poorer girls and their families. / The other options considered have minimal impact on climate change. Delivering these options would require around 36 air flights (including within Africa, from UK and US). Where possible video conferencing or audio-conferencing will be utilised to reduce air travel. Girl Hub Ethiopia will use DFID travel policy. Colleagues contracted by Nike Foundation or Girl Hub delivering inputs to Girl Hub Ethiopia will use NF or GH travel policy. At NF / GH, carbon is offset on an annual basis in an effort to minimise the organisations carbon footprint. / Component Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 1 C C / 2 C C / 2 1 C C / 2 C C / C. What are the costs and benefits of each feasible option? / Girl Hub Ethiopia’s approach to assessing VfM is influenced by the complexity of measuring social change. The methodological difficulties of measuring complex social outcomes (such as girls’ empowerment) highlight the need for an adaptive management technique, which promotes monitoring and evaluation of progress, and learning from success and failure to promote adaptation alongside experimentation. Girl Hub has begun to collect cost efficiency data in the start up phase and this will be used as we track the impact of interventions to determine value for money. / Component 1: Use brand and communications to inspire and enable / The social communications component will receive most of DFID’s investment. This section summarises the cost efficiency of the two possible delivery models described above. / Option 1: Produce a social communications campaign based on a youth magazine for girls and other related products / A social communications campaign would use international expertise to produce and distribute content. In the short term this might seem cost effective because there are immediate and quantifiable results. This approach is sometimes suited to specific campaigns (such as the use of bednets or uptake of contraceptives). However, over time, the necessary costs of re-engaging with communities would offset the initial benefits. / Option 2: Produce a social communications platform based on radio drama and other branded products / Yegna is designed to engage with commercial media in a sustainable way, building capacity to attract audiences and to develop sustainable funding of programmes through donor and commercial funds. Evidence from the Girl Hub screenings of the BBC World Service Trust Heroes films (described above) in rural Ethiopia have: / Allowed Girl Hub Ethiopia to develop unit costs / Revealed a large appetite for social communications. / As described above, due to demand, the planned 66 screenings, increased to 160 screenings, with an audience more than 3 times expected. This evidence of audience demand suggests that it is a credible assumption that working with the private sector to develop programmes and market them to new audiences would make Yegna attractive to a range of donor funders and or private sponsors. / Girl Hub has drawn from one example of a social communications platform delivered through the private sector in Kenya. 'Shujaaz' is a comic book and radio programme that reaches 6 million readers per month, equal to 50% of Kenyans under 35s. There has been a measurable impact on the self-efficacy of Kenyan youth and 32% of fans discuss themes with each other, while 36% say they have acted on stories they have read or heard about. ‘Shujazz’ raises £450,000 per annum through multiple sponsors and £900,000 per annum through corporate advertisements and product placements. It costs less than £0.01p per sponsor per 'adopter' per month. / There is a strong case for the use of radio as the most cost efficient medium for social communications in Ethiopia, particularly with regard to reaching rural girls and those in the bottom 40%. The cost of reaching nearly 10 million Ethiopians is nearly £4 million, equating to £0.39 per listener. / Table 1: Costs and benefits of output 1 Yegna Radio and talkshow / Total Participants 9,891,000 / Total Cost (Sep'12-Mar'15 including NF contribution) £3,900,830 / Unit cost/participant £0.39 / There is no available evidence to assess the cost effectiveness of the Yegna platform, since this will require assessing the cost per level of change in girls’ lives. However, given the breath and frequency of radio listenership, and the evidence set out above on what makes social communications work, Option 2, Produce a branded social communications platform, is the preferred option. Girl Hub Ethiopia’s Monitoring and Learning Strategy will build the evidence to test the impact of this approach to social communications. The associated value for money strategy has created the analytical tools and management strategies to build the following: / Economy: trend analysis of unit costs / Efficiency: ratio of programme to management costs of Yegna; £ per person reached by social communications / Effectiveness: score card ranking based on trend analysis of numbers or % of people attributing changes in attitudes and behaviours to girls as a result of social communications/costs of social communications. / Equity: scoring of qualitative case study analysis of trends in costs and benefits of trying to reach ‘the last girl’ / Sustainability: Yegna brand – scoring based on trend analysis of performance against target in private income as % of total revenue required to cover estimated costs and level of girl engagement. / Component 2: In order to influence partners to deliver just seven new initiatives for girls' (in programmes of for example between £10 million and £30 million) in Ethiopia by March 2015, the costs would be just over £2 million, equal to about £304,000 per scale partner (see table 2 below). Given the overall aim of reaching 3 million girls, the cost of influencing equates to £1.40 per girl. / Table 2: Costs and benefits of component 2 Scale Partners Girls benefiting from more resources / Total number of scale partners 7 3,000,000 / Total Cost (Sep'12-Mar'15 including NF contribution) £2,127,438 / Unit cost/Scale Partner/girl £303,920 £1.40 / Using evidence from a comparator organisation that directly implements education, health, HIV and emergency programmes in Ethiopia, reaching 750,000 beneficiaries requires a budget of £5.5 million and 412 staff. Extrapolating from these figures, directly reaching the target of 3 million girls would require £22 million and 1,648 staff. / As indicated above, the costs associated with influencing have a far greater return for the inputs than for option 2, where Girl Hub would need to employ significantly greater numbers of staff and resources to reach the same number of girls. For this reason of cost effectiveness, Option 1: Influencing others is the preferred option / Component 3: Research and girl-centred participatory M&E generate real-time, robust evidence and insight / Girl Hub seeks to engage at a minimum 12,000 citizens in participatory monitoring, costing £110 per participant. If community members themselves are trained to carry out story collection, there is a possibility of increasing the number of participants thereby reducing the unit cost. / Table 2: Costs and benefits of component 3 Participatory Monitoring and Learning / Total participants/Products 12,000 / Total Cost (Sep'12-Mar'15 including NF contribution) £1,331,364 / Unit cost/Beneficiary/product £110 / Cost per participant data does not capture the full range of uses of the participatory monitoring and research. As noted, the Sensemaker data will be used in the development of compelling and realistic storylines for social communications. The methodological approach also engages communities directly in analysis of behaviours and values, which is expected to lead to change. It is challenging to translate cost efficiency into cost effectiveness data, since we will define the benefits of using SenseMaker and the value of those benefits to participants through the piloting process. However, during the first SenseMaker pilot project, undertaken by Girl Hub in June 2012, girls and caregivers expressed a strong affinity for the methodology. They reported that it allowed them convey something of importance to them and made them feel as if their knowledge and perspectives were recognised and valued. There was also strong demand for feedback and desire to talk about other stories coming out of their communities, indicating good potential for community ownership of the SenseMaker approach in the future. / Integration of the PM&E component with the other outputs is very important. Girl Hub’s Monitoring and Learning Strategy will help to establish what the benefits to participants are. This will then position Girl Hub Ethiopia to translate cost efficiency data into wider cost benefit, both to direct participants and others engaging with the programme. / Nike Foundation Integrated Strategy Components / Which option? / Campaigns? / Component 1: Brand and communications / Integrated platform, focused on radio? / Girl Hub Ethiopia / Influencing others? / Component 2: Delivering for girls / Direct implementation by Girl Hub?
D. What measures can be used to assess Value for Money for the intervention? / Early work Girl Hub commissioned with DFID’s Office of the Chief Economist on Value for Money and Adolescent Girls reviewed the available evidence and set out the value for money case for investing in adolescent girls[40]. / There are no established value for money (VfM) comparators for the Girl Hub. Therefore a VfM strategy was commissioned during the start-up period of the programme, to create a range of tools and metrics for assessing resource allocations focused on adolescent girls in the Ethiopian context. / Girl Hub Ethiopia understands VfM as an approach to enhancing impact that incorporates economy, efficiency and effectiveness as well as a fourth dimension, equity. Equity is about ensuring that effectiveness analysis considers whether the most marginalised are participating and benefiting equally from programme processes and outcomes. It inevitably makes interventions more expensive and requires integrating social exclusion analysis (or an understanding of how social norms and relations make some social groups ‘harder to reach’) to planning, monitoring and evaluation work. Considerations of equity are especially critical for Girl Hub Ethiopia in assessing the value for money of targeting the most vulnerable and marginalised girls. Girl Hub Ethiopia has developed a reach strategy (described above), to ensure that Girl Hub’s interventions address the diverse needs of different girls in Ethiopia. This will be integrated into both the M&L and VfM strategies, so that we build evidence on what the relative costs and returns are to reaching different groups and to ensure transparency about our commitment to actively promoting greater social equity and progressive realisation of human rights for all girls. / The general objectives of the proposed Girl Hub Ethiopia VfM framework are: / To demonstrate a VfM conscious approach to management decision-making. / To generate data and enable trend analysis of key VfM metrics related to the efficiency of the delivery mechanism and the cost effectiveness of different aspects of the programme that will facilitate: / Learning & evidence based decision-making, especially for resource allocation; / Accountability - regular reporting to DFID, the Nike Foundation, partners and girls; / Generation of benchmarks or VfM lessons of interest to other practitioners; / Meta-level inductive quantitative and qualitative analysis of the value for money of the Girl Hub Ethiopia initiative during the final review/evaluation; and / Macro level economic analysis of Girl Hub Ethiopia’s VfM at impact assessment. / The strategy provides clear direction for tracking the following unit costs at output level: / Cost per person reached via social communications / Cost per person engaged in participatory monitoring and evaluation / Ratio of additional pounds raised from donors and other partners to Girl Hub investment (advocacy and/or total) / On-going and regular collection of VfM data is incorporated into the Girl Hub Ethiopia Monitoring and Learning Framework. The data generated will be used to inform a management strategy that ensures regular learning feeds into decision-making. This is necessary since the Girl Hub is working on issues of complex social change and has a strong focus on learning and evidence. VfM analysis will allow Girl Hub Ethiopia to periodically review activities in order to build knowledge of the types of interventions that best deliver transformative results for girls, to test the assumptions set out in the girl effect theory of change and to allocate resources towards those interventions that show greatest value for money.
E. Summary Value for Money Statement for the preferred option / This provisional assessment suggests that Girl Hub Ethiopia is expected to yield significant returns on DFID’s total £9.8 million investment. The first two options chosen, of a branded social communications platform (Yegna) and influencing others as opposed to direct implementation, are the most cost effective approaches considered in the appraisal case. The creative participatory monitoring and research is a more innovative approach and combined with the other options, will be monitored from a value for money point of view, guided by the value for money strategy, throughout the lifetime of the project. / Given the potential transformational effect, this project is considered a cost-effective strategy to help deliver sustainable progress towards the MDGs and end the cycle of inter-generational poverty. For example, current average female earned income levels in Ethiopia are estimated at $624 per annum at purchasing power parity. If the earnings of just 5% of the girls aged 15-19 were to increase to this level (an estimated increase of $62 per annum) then this could lead to a $223.6m (0.28%) increase in GDP based on a 10-year earnings projection. / Girl Hub London is working with DFID Research and Evaluation Department to develop research to understand the longer-term and intergenerational stream of value derived from investment in girls which is combusted through Girl Hub – a study which will include Ethiopia.
[39] Audience Survey Ethiopia 2011. Ward, D., with Ayalew, S. Electoral Reform International Services, 2011
[1] SenseMaker is a software platform for collecting and analysing stories which allows storytellers to interpret their own stories through responding to a series of questions. The software generates narrative patterns through the aggregation of a mass number of individual stories.
[40] Economic returns to investment in adolescent girls: Making the case for DFID Ethiopia, Lindi Hlanze, DFID, December 2010

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Intervention title: Girl Hub Ethiopia / Girl Hub Ethiopia is funded by DFID (86%) and Nike Foundation (14%). Girl Hub Ethiopia uses DFID policies and standards across all operations, including procurement of goods and services, for all DFID funded activities. Nike Foundation funds cover the majority of the music production, some staff positions and all PR related activities. Cost-sharing arrangements are in place, for example for the early development of the girls club/outreach components of Yegna. Girl Hub Ethiopia uses Nike Foundation policies and standards for Nike Foundation funds, which are approved by the Girl Hub Country Director and General Manager, Global Initiatives, and currently managed from the Foundation in the US. The Girl Hub Internal Audit (June 2012) sets out when each process is to be used. / Girl Hub will need to procure specialist goods and services, given the nature of the project. This includes research services for girl insights, social communications and various forms of expertise in the music and media industry. Where possible Girl Hub will invite consortia to bid for assignments, to reduce transaction costs (see Creative and Management Agency below). / Procurement Route: Direct / As above, all contracts funded by DFID are issued by DFID, following blue book guidance. Similarly, contracts issued by Nike Foundation or Girl Hub for delivery in Ethiopia follow Nike Foundation or Girl Hub procurement policies. The DFID A1 leading the Girl Hub Ethiopia team will have the authority to approve all DFID expenditure under this business case and delegated authority of USD $5,000 over Nike Foundation funding. / Creative and Management Agency (CMA) for “Yegna” / Delivery of the Yegna branded platform requires co-ordinating a large number of national and international contractors with specialist expertise. DFID will contract a Creative and Management Agency to deliver the “Yegna” project component. Using a CMA to out-source programme making, production, broadcast and entertainment services will minimise contract management for DFID, while ensuring Girl Hub Ethiopia retains creative control, management and financial oversight. The CMA contract value will be approx. £1.5 million per annum for 2.5 years, to deliver all aspects of the project. This will include creative development, production and on-going management/administration. / Other Project Component Contracts – Infuencing Scale Partners and Research M & L / In addition to the CMA, a summary the estimated number of contracts required for the delivery of outputs over the lifetime of project is below: / Anticipated contract Volume (Sep'12-Mar'15) Nature Total value Output / 10 Establishing listener groups across country, gathering insights around Economic Empowerment and research work on girl group social communication platforms £220,800 Output 1 / 17 Analysis and evidence collection on collaboration with scale partners, brand and communication work on building action network for girls, Girls expertise on Girls Education Challenge fund £449,364 Output 2 / 22 Age+sex desegregated data collection, SenseMaker research, advocacy work under 4 pillars and sub-regional studies, research on drivers of change for girls £315,000 Output 3 / 3 Research on social marketing and Girl Journalists that can feed into Yegna project implementation £26,480 Output 4 / Given the volume of contracts, efficient contract management is a priority for effective delivery of the programme. Girl Hub Ethiopia uses a tracking system to manage existing vendor contracts and pipeline plans. Contract trackers are updated monthly by the Girl Hub Ethiopia Finance Manager, in line with the Girl Hub Ethiopia 90-Day Project Plan. The Girl Hub Ethiopia team works closely with the DFID procurement team and the Nike Foundation Core Functions Team as appropriate, though the process of TOR design, competition & vendor selection and is responsible for ensuring appropriate authorisations and maintenance of records. This ensures a transparent and efficient procurement process in line with DFID and Nike Foundation rules respectively. / The table below shows the anticipated volume of contracts which will be required in each six month period of implementation: / Period Volume Amount / Sep'12-Mar'13 12 £233,456 / Apr'13-Sep'13 12 £233,456 / Oct'13-Mar'14 11 £214,002 / Apr'14-Sep'14 13 £252,911 / Oct'14-Mar'15 4 £77,819 / Total 52 £1,011,644
B. How does the intervention design use competition to drive commercial advantage for DFID? / Commercial factors have been considered and incorporated into the design of the programme to maximise value for money. Selection of supplier proposals for goods and services will be based on competition to ensure delivery of results against the budget allocation. Girl Hub Ethiopia will use competition to ensure that procurement of services meets quality standards and delivery targets. Where there are capacity gaps in the local market, Girl Hub Ethiopia will draw on the unique mix of skills available through DFID and Nike to innovate, raise the bar and build capacity locally. / For the procurement of IT and equipment, DFID’s Crown Agent procurement services will be used. Quotations will be sought through a competitive process for the various research, monitoring and learning requirements planned in line with DFID procurement rules. / The advertising and social communications market as a whole is not very developed in Ethiopia. For example, in radio the need for high quality production and audience reach will limit the number of potential suppliers available. Girl Hub Ethiopia will continue to use a mix of international and local talent. Nike Inc is a global leader in building brands through marketing and communications and will make available private sector techniques and experience to the Girl Hub by seconding staff on short term assignments e.g. creative, design and innovation, and brand experts to drive quality and build local capability. / A local competitive process has been followed to appoint the successful Creative & Management Agency (CMA). Specialist legal advice from DFID, Nike and a UK based legal agency has been used to ensure the contract will address the specific requirements of the branded social communications platform. This has necessary clauses on intellectual property rights, music, child protection and gender equality. Contract performance and review will be ensured by milestone payment against key deliverables. / A detailed work plan will be developed by the CMA and signed off by DFID. This will ensure transparency over sub-contracting of services. It will also be used to monitor delivery against agreed milestones, reduce transaction costs, ensure a clear division of labour between Girl Hub Ethiopia and the CMA. In the start up of Yegna delivery, Nike Foundation will fund 3 international experts to drive quality and build capacity in the CMA (Creative Director, Producer and Design Director). / The Girl Hub Ethiopia Monitoring and Learning Strategy and financial management templates will allow Girl Hub Ethiopia to track the costs of delivery of Yegna against results.
C. How do we expect the market place will respond to this opportunity? / Work during the start up phase has shown that there is a limited pool of vendors to respond to the very specific requirements of the Girl Hub Ethiopia. There are not many suppliers/companies with the necessary skills, scale and capacity within Ethiopia to deliver the range of services to the quality Girl Hub Ethiopia requires. Therefore, identifying suppliers with the potential to develop quickly will be important and creating commercial solutions that allow Girl Hub Ethiopia to retain quality control (e.g. through milestone based contracts) will be essential. / At the same time, this presents a unique opportunity to develop the market in Ethiopia. The market responded better than expected to the recent procurement process to tender for a Creative & Management Agency (CMA) for delivery of the social communications platform. Given the large number of contracts required for Girl Hub Ethiopia outputs opportunities will be sought to use consortia and/or resource centre arrangements to ensure economies and reduce transaction costs. / For research consultancy services, Girl Hub Ethiopia will establish a database to register interested and qualified local experts, which would ultimately speed up procurement while ensuring competition in the long term. The Girl Hub Ethiopia Finance Manager is also building a database of unit costs for those services which DFID Ethiopia does not usually contract. Nike Foundation uses a contract management system to encourage transparency and knowledge sharing across the organisation.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The major cost driver for Girl Hub Ethiopia interventions will be staff and operational costs. A second set of cost drivers relates to the CMA, various research, monitoring and learning, and professional fees for services. Cost will be driven by the availability of contractors (specialist international and local expertise) that offer the desired unique skill sets (see finance section for details). Other cost drivers for the procurements of services will include rising inflation costs for general living costs and goods, as well as potential foreign exchange loss. / With the requirement of international expertise and significant travel due to the short term and varied nature of the expertise required, Girl Hub Ethiopia will negotiate fair consultancy/technical advisory rates, minimise travel and related expenses cost following DFID practice. / Under the VfM strategy, all costs are tracked through Girl Hub Ethiopia’s budget templates and financial reporting process. This tracks costs directly against specific outputs in the logframe. Delivery costs of outputs will be monitored quarterly as part of the VfM strategy, against pre-determined rates. It is planned to include the in-kind contribution that Girl Hub Ethiopia receives from both funders (DFID E and NF) to calculate an accurate unit cost rate per beneficiary for all outputs. This will be used as a baseline to assess annual progress in terms of both and cost and achieving value for money.
E. What is the intended Procurement Process to support contract award? / Girl Hub Ethiopia will use DFID Ethiopia and Nike Foundation procurement processes to support contract awards. As above, the majority of procurement will be service related and where appropriate Crown Agents will be used. The procurement process starts with the identification of need, in line with project plans and logframe by respective Girl Hub Ethiopia staff. They develop Terms of Reference which are approved by Girl Hub Ethiopia Country Director (A1 HCS DFID staff member) and shared with the Girl Hub Ethiopia Finance and Operation Manager (to confirm availability of budget) and DFID E/NF[2] procurement team members (for quality control). DFID E/NF Procurement officers then lead the competitive process and negotiations with contractors. Competitive tendering will be undertaken for high value contracts in line with DFID requirements, at least 3 quotations at national level above £25,000. Specific to for the CMA, a national tendering process was undertaken. As the services involved radio, music production and entertainment services (i.e B type service) only available in Ethiopia and so approved by the PRG (waiver from EU competition). / High level selection criteria for the procurement of services will be as followed, supplemented where appropriate depending on the nature of the service being sought: / Relevant experience, including context / Knowledge of specific area of expertise in developing markets / Understanding of gender issues & commitment to the girl / Financial / Cost effectiveness. / As noted, the Girl Hub Ethiopia project will involve a large number of contracts and for the CMA in particular substantial sub-contracting. Girl Hub Ethiopia has used specialist legal advice to design contract templates, appropriate to the specialist nature of the media products. The CMA will develop a risk management strategy for Yegna delivery, which will be agreed with Girl Hub Ethiopia. This will provide a shared monitoring tool to ensure, for example, that the Girl Hub Child Protection Policy is properly operationalized by subcontractors. / Through the tendering process, the CMA procurement processes were evaluated by the DFID procurement team in terms of the Blue Book to ensure adequate standards, terms and conditions in procurements of goods and services, financial procedures and recruitment.
F. How will contract & supplier performance be managed through the life of the intervention? / Girl Hub Ethiopia’s Deputy Director will be responsible for overall quality control and assessing timeliness of contract and supplier performance in line with work plans. The CMA will issue and manage the contracts with regard to Yegna. DFID Ethiopia will issue and pay contracts, with Girl Hub staff responsible for contract management. Nike Foundation or Girl Hub contracts will be issued by Nike Foundation through the contract management system, with support from the Nike Foundation and Girl Hub Operations Team. The Girl Hub Ethiopia Finance Manager will monitor the budget, track contracts and procurement pipelines, ensure appropriate sign off for services delivered and authorisations as well as administer payments for both DFID and Nike Foundation funds. / As above legal advice has been used to ensure comprehensive and adequate contract templates for the CMA. These have strengthened contracts to ensure key performance indicators and milestone payment against key deliverables. Depending on the nature and value of contracts, detailed work plans and/or inception reports will be required from the vendor. The types of contracts will include mini, standard and call down (framework). Any amendments or extensions of any vendor contract will be done following a review by Girl Hub Ethiopia and DFID procurement staff and to discuss whether it is a no cost extension or whether corrective action is to be taken by a non-performer or whether it is a cost extension for additional services, in line with budget, required to deliver the project desired result. The Girl Hub Ethiopia Brand Manager will assure and sign off deliverables are achieved to the required timeframe and quality, and the Girl Hub Ethiopia Deputy Director will take oversight and provide assurance on process. Where deliverables are not achieved, payment will not be made until agreed corrective action is taken. / The Creative and Management Agency will be responsible for appointing, contracting and managing suppliers across the different work streams - the “Yegna” radio drama and talk show, music album, “Yegna” clubs and outreach, marketing, and monitoring and learning. A selection of vendors with the appropriate skills and potential for the success of delivering the “Yegna” project have been identified, tried and tested, by Girl Hub Ethiopia during the 12 month start up. The CMA will be responsible for overseeing these sub-contractors, managing their outputs, maintaining high production standards, making payments against deliverables and ensuring budgets are adhered to, and taking corrective action with vendors where deliverables are not met. Where vendors are not in place, the CMA will need to work closely with Girl Hub Ethiopia to appoint these through a transparent and competitive procurement process in line with CMA procurement guidelines as agreed with GHE/DFID as part of the contract. The CMA contract will contain a clause on the on-boarding and off-boarding of vendors and will include a provision for a 6 monthly joint review (CMA & GH E) of vendor performance. Girl Hub Ethiopia work with the CMA to identify opportunities to minimise risks, reduce costs, increase efficiencies and improve VfM overall during periodic reviews. / The CMA must consider ‘Duty of Care’ at the beginning on any procurement and throughout the duration of the contract. All suppliers subcontracted by the CMA will fall under the Duty of Care of the CMA. DFID’s new DoC to Suppliers Policy of 19 July 2012 will be consulted at all times.
[2] Depending on which funding source is being used.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / In advance of DFID Ethiopia’s Stage One Business case, £0.7 million from DFID Accountable Grant for Girl Hub was invested in work for Ethiopia. The Stage One Business Case approved £1 million to set up an office and deliver additional preparatory work to underpin this Business Case. This included work to develop the log frame; value for money strategy; monitoring and learning framework; budget; risk assessment; and, updated management arrangements. / From 1st November 2011, DFID Ethiopia’s £1 million contribution was matched by £230,000 from Nike Foundation. During start up the percentage split of funding was 24% and 76% from NF and DFID Ethiopia respectively. The level of the NF contribution reflected the need to service contracts which were on-going with deliverables in Ethiopia and had been funded by the Central Grant. These contracts were funded by Nike Foundation from 1 November 2011 to ensure continuity and reduce transaction costs. / With the approval of this submission for £8.8 million, DFID Ethiopia’s total cash contribution to Girl Hub Ethiopia with effect from November 2011 will be £9.8m over three and a half years. Nike Foundation’s cash contribution will be £1.6 million. Nike Foundation funding covers the following: branding, media and creative expertise, PR costs and the majority of the music and album creation. Nike Foundation also provides in-kind staff contributions of approx. 25 FTE staff to the Girl Hub’s globally. / Costs per financial year (excluding in-kind contributions from both DFID and NF) are set out below: / Nov 2011/ August 2012 September 2012/ / March 2013 April 2013/ March 2014 April 2014/ March 2015 Total % / DFID £1m £1.9 £3.3m £3.6m £9.8m 86% / Nike Foundation £0.2m £0.3 £0.5m £0.6m £1.6m 14% / Total £1.2m £2.2m £3.8m £4.2m £11.4m 100 / The budget is based on estimates of the costs for delivering project results set out in the log frame. Girl Hub Ethiopia has developed preliminary unit costs for proposed activities (inputs). The total project budget (November 2011 – March 2015) has therefore been calculated to show the expected cost of delivery of each output. Costs per output are presented below: / Area of spend DFIDE Contribution(Nov'11-Mar'15) DFIDE Percentage NF Contribution(Nov'11-Mar'15) NF Percentage / Output one: Branded Social Communications and outreach £4,548,456 46% £812,943 50% / Output two: Catalysing & Convening £3,009,409 31% £519,533 32% / Output three: Research, Monitoring and Learning £1,301,517 13% £183,743 11% / Output four: Organisational Development (advocacy, operating expenses, staff costs not specific to one output) £994,526 10% £100,802 6% / Total £9,853,909 100% £1,617,021 100% / The breakdown for the Output 4 operational costs are as follows: / Office set up and running costs (rent, maintenance, office furniture & supplies, utilities, telephone, cleaning & security services, IT services, insurance, vehicle purchase/hire costs) / Capital/Asset items: provides for the purchase of IT and office equipment as well as the purchase of vehicles. / Staff costs include: salaries, social insurance, provident fund, medical expenses, travel expenses for various meetings, staff development. / Workshop and visits for PR activities. / Staff costs have been calculated using DFID and GH/NF salary scales allocated against outputs in line with how staff will spend their time (e.g. influencing partners or delivery of Yegna). We have assumed that staff will be appointed in country, with exceptional cases to promote capacity building where skills are not available in Ethiopia. Staff costs are currently estimated to be about 15% of the overall budget. / We will minimise staff costs by drawing down on GH/NF in-kind contribution through staff time dedicated to Girl Hub Ethiopia. This will be either % allocation of existing staff or additional support from Nike Inc staff working on short term assignments. Staff in the Girl Hub Ethiopia country team will have technical and strategic oversight, as well as call-down support, from colleagues based in Girl Hub London and NF Beaverton who dedicate time to Girl Hub Ethiopia. This in-kind support covers the following areas and activities: / Nike Foundation, Girl Hub London and Beaverton staff time to support technical excellence, and local capacity building in e.g. brand and creative; design and innovation; insights; finance and operations; girl experts; monitoring and learning; performance and planning. / Line management of Country Director by General Manager, Global Initiatives / Internal Audit / Strategic oversight by the NF senior management team / Financial forecasting is undertaken monthly with all Girl Hub Ethiopia Team members, based on forecasts from contractors and against the GH E 90 day workplan, to monitor forecast and spend, in line with DFID’s Finance for All Strategy. This review process takes into account both DFID and Nike Foundation funding. In addition, Girl Hub Ethiopia will profile the project budget as per DFID’s requirements. / DFID spend is tracked in the DFID Ethiopia financial systems and all budget adjustments are undertaken in compliance with DFID processes and reporting requirements. Nike Foundation expenditure is tracked using the contract management and Intaact Financial system. The Girl Hub Ethiopia Finance Manager will consolidate the financial reports produced by both systems on a monthly basis, detailing actuals versus budget / reforecast.
B. How will it be funded: capital/programme/admin? / Girl Hub Ethiopia will be funded by both DFID and Nike Foundation. The funding from DFID will be provided from programme resources and has been budgeted for in the Operational Plan for DFID Ethiopia. / There will be contingent liabilities related to staff employed under DFID Ethiopia fixed term contracts. These have been taken in account in the indicative budget for Girl Hub Ethiopia.
C. How will funds be paid out? / As a DFID team, Girl Hub Ethiopia will utilise DFID systems and procedures for the financial management of DFID Ethiopia funds. The Girl Hub Ethiopia Finance Manager will receive and review invoices, which will then be approved and paid out by the DFID E Accounts team, ensuring segregation of duty. Nike Foundation funds will be managed by the Girl Hub Ethiopia team using the Nike Foundation and Girl Hub financial and contract management systems. Girl Hub Ethiopia will provide both DFID and Nike Foundation with their financial plan and payment forecast for every quarter as well as an update on a monthly basis. / We have considered whether to set up Girl Hub Ethiopia with a single pooled fund for both the NF and DFID cash contributions. We have considered two management options: / managed by DFID Ethiopia. Given the limited capacity of the DFID Ethiopia office to procure the international PR, creative and media services, which will be funded by the NF contribution, this would not be advisable. / managed by GH or Nike Foundation, to ‘blend’ DFID Ethiopia funds with the DFID Accountable Grant. This is not possible because neither GH nor NF is a legally registered entity in Ethiopia. / DFID Ethiopia and NF will review opportunities to simplify the financial structures and mechanisms during annual review. For example, we will review the potential for the Yegna social communications platform (and associated Creative and Management Agent contract) to be financed through a multi-donor fund mechanism, allowing other donors and private sector to contribute to costs. / A small monthly cash imprest advance of £900 will be managed by the DFID contracted Administrative Assistant from August 2012, to cater for immediate office running costs and incidentals facilitating the smooth functioning of the Girl Hub Ethiopia office. A policy is in place for its administration including cash counts, supervision and monthly reconciliation, in line with DFID’s requirements. / All payments for contracts are set out in the Commercial Case. / Details related to budget decision making and planning are set out in the management case below.
D. What is the assessment of financial risk and fraud? / Ethiopia has relatively low levels of corruption and the Government has demonstrated commitments in fighting corruption. A recent corruption survey conducted in Ethiopia classified the level of corruption in the basic services as petty and suggests the risk of corruption is low in most public sectors and overall was designated as moderate.[41] / DFID has the risk appetite for innovative investments targeted at poverty reduction but acknowledges and proactively manages fiduciary risks associated with implementing innovative approaches. Girl Hub is a strategic collaboration between DFID and the Nike Foundation that aims to provide girl centred strategies to improve the condition of adolescent to girls eliminate poverty. The Girl Hub collaboration is new and operating in a complex political governance environment. Keeping Girl Hub Ethiopia as a DFID team reduces financial risk and fraud: Girl Hub Ethiopia will be included in DFID Ethiopia’s risk register and anti-corruption work. / The Girl Hub Ethiopia conducted its own internal audit in May 2012. In response an Internal Audit Response work plan has been developed which sets out the responsible position and key actions for addressing all key risks financial within a 3 – 6 – 9 month timeframe. The Internal Audit Report assessed a number of financial and operational risk elements: / · Organizational Risk: Nike Foundation/Girl Hub has developed policies including cash management and advance policy, fixed asset management policy, procurement policy, and a vehicle management policy, consistent with DFID rules and regulations. Each of these policies contains clear guidelines for implementation at an operational level ensuring transparency and competition and is further supported by model templates, to ensure that responsibilities assigned cater for segregation of duty, conflict of interest, supervision and appropriate authorisations. / · Risk of Fraud - Credible counterparts and service providers will be identified to minimize the risk of fraud in delivering the innovative needs of Girl Hub Ethiopia; / Girl Hub Ethiopia has developed a risk register which is reviewed on a quarterly basis to ensure risk are appropriately identified and managed.
E. How will expenditure be monitored, reported, and accounted for? / This business case sets out the overall commitment of DFID and GH/NF finance and has been approved by both organisations. The Head of DFID Ethiopia and the General Manager, Global Initiatives GH/NF will sign off jointly on annual budgets. / A consolidated budget has been developed for Girl Hub Ethiopia, detailing by line item the DFID and Nike Foundation budget lines. This will be updated by GH Ethiopia and reviewed and agreed on a quarterly basis by the Head of DFID Ethiopia and the General Manager, Global Initiatives Nike Foundation. / In order to ensure flexibility as Girl Hub Ethiopia learns and refines its strategy through innovation and with new scale partners, DFID expenditure can be varied between budget lines, with funding for more successful elements brought forward. However, to maintain oversight and balance to the programme, expenditure between outputs should not vary from the budget by more than 10% unless agreed in advance by both the Head of DFID Ethiopia and the Nike Foundation General Manager, Global Initiatives. / DFID delegated authority, systems of monitoring, reporting and accounting will be used for DFID funds. For DFID funds DFID Ethiopia systems will be used for inspecting invoices to ensure Value for Money and compliance with DFID procedures. Nike Foundation funds will be managed through the Intaact finance and ‘Root’ contract management systems.
[41] Transparency Ethiopia Diagnostic Survey, 2009

Management Case

A. What are the Management Arrangements for implementing the intervention? / Girl Hub will work within the existing policy framework of the Government of Ethiopia’s Growth and Transformation Plan and with government and other partners who are receptive to increased programming for girls. Under Ethiopia’s civil society legislation the limitations associated with being an independent legal entity would limit Girl Hub’s capacity to deliver results. Due to this unique aspect of the operating environment in Ethiopia, at the present time, Girl Hub will not be registered as an independent legal entity. Instead, the management arrangement will be for Girl Hub to be a DFID Team, using DFID systems and procedures and staffed by DFID employees. This arrangement will be reviewed during the course of the project, with a view to registering Girl Hub as a separate entity in the future. / Girl Hub Ethiopia is currently managed by an A1 DFID HCS staff member who will report jointly to the DFID Ethiopia Head of Office (for managerial and accountability of DFID funding) and the Nike Foundation General Manager, Global Initiatives (for strategic oversight and accountability of NF funding). This staff member, titled, the Girl Hub Ethiopia Country Director (Girl Hub Team Leader) is responsible for the overall management of the programme – including financial reports, compliance and administrative functions quality control, managerial and technical oversight and therefore, impact, of the programme. / Girl Hub Ethiopia will be governed under the global arrangements for the strategic collaboration between DFID and Nike Foundation. These are described below. / In October 2011, DFID and Nike Foundation Senior Management put in place a central governance framework for the Girl Hub collaboration. A Joint Senior Strategic Collaboration Group (SSCG), co-chaired by the President of the Nike Foundation and the DFID Director General of Country Programmes, meets every six months to provide strategic oversight and joint accountability. This group: / Sets Big Vision thinking and Strategic / Reviews programmes at a high level / Prioritizes Annual Country Plans / Finalises Accountability for DFID / NF strategic collaboration. / Communicates across DFID / NF / Contributes to Annual Review / Reports on the progress of Girl Hub Ethiopia will be monitored by this group every six months. / A Girl Hub Ethiopia Strategic Collaboration meeting will be held quarterly, co-Chaired by the Head of DFID Ethiopia and the General Manager, Global Initatives GH/NF. These meetings will provide the mechanism to review and agreed content of progress reports and agree decisions related to Ethiopia, before presentation to the SSCG meetings. / Lines of accountability are summarised in the table below: / Authority Head of DFID Ethiopia General Manager, Global Initiatives, Nike Foundation / Budget approval Joint sign off of total financial contribution/financial management through this single Business Case. / Joint sign off of annual budgets – aligned with the NF integrated strategy / DFID delegated authority and processes for DFID Ethiopia funding Alignment of total budget with integrated strategy. / NF delegated authority and processes for NF funding. / Country Director: recruitment, succession and performance reviews Joint Joint / Staff: Decisions on HR and resourcing DFID Ethiopia headcount and number of secondees. Overall org structure and talent planning. All GHE staff. / Staff: Duty of Care All staff DFID and GH secondees working in the Girl Hub Ethiopia team. Supplementary Duty of Care for Nike visitors by NF / Policies and Procedures Overall authority for DFID Ethiopia funding. Overall authority for Nike Foundation funding / Strategy & Direction DFID Ethiopia Operational Plan Girl Hub Ethiopia delivers the integrated strategy, as agreed in the SSCG. / Risk Management Operational and political risk management Strategic risk management / Governance (recommendations following Internal Audit / Annual Review) Recommendations related to GH E from DFID audit processes. Recommendations related to GH E from NF audit processes. Annual review recommendations. / Girl Hub Ethiopia will establish an Independent Advisory Board of Ethiopian decisions makers and girl champions. The role of this group, which will meet biannually, will provide strategic advice to the Girl Hub Ethiopia Country Director. / Similarly, Girl Hub Ethiopia and DFID Ethiopia will participate in global quarterly learning reviews between countries and the pillar leads on the DFID ‘vision house’ for women and girls. The role of these review is to: / Share insight, evidence & learning, innovation and results / Communicate across and beyond DFID / NF / Review progress at a working level / Strategize on how to align DFID / NF to improve impact. / Report to Senior Strategic Collaboration Group / Contribute to Annual Review / The Nike Foundation/Girl Hub Leadership Team, which comprises the NF Senior Management Team, Country Directors and Directors of Operations, Brand, Girl Expertise and Insights meets annually in October for Annual Strategy Setting (under the Integrated Strategy) and consolidate budgets. During this meeting long-term decisions are made under the Integrated Strategy and key priorities decided for the upcoming financial year. / Girl Hub Ethiopia will recruit for posts both nationally and internationally. For national posts Girl Hub Ethiopia will competitively use DFID HR systems. For international posts, Girl Hub Ethiopia will recruit through either the DFID or the Nike Foundation or Girl Hub HR systems, depending on the source of funding. Both DFID and GH/NF staff will be involved in recruitment processes. Posts are likely to be a combination of DFID and/or Nike Foundation or Girl Hub staff, international and local hires. For postings of over three months, NF or Girl Hub staff will be seconded into DFID Ethiopia. The staffing structure of Girl Hub Ethiopia will be reviewed on a quarterly basis, as part of the Quarterly Review Process. / The table below shows the current and likely future staffing structure for Girl Hub Ethiopia. Girl Hub Ethiopia currently has 8 full time staff, on permanent HCS, fixed term and consultancy contracts. Over the next six months strategic workforce planning is underway to grow the team to about / 15 staff in country. Girl Hub Ethiopia will draw on DFID Ethiopia, Nike Foundation and Girl Hub Human Resources function and grading systems. Line management and performance processes will be based on DFID standards and reflect the Nike ‘coaching for excellence’ standards as appropriate.
B. What are the risks and how these will be managed? / The risks to this programme are fully detailed in the Girl Hub Ethiopia risk register. This has been summarised below: / Risk Probability Impact Mitigation strategy Risk following mitigation / Strategic – Political risk that Girl Hub is seen as inappropriate in Ethiopian context. Flawed theory of change or slow pace of partnerships means Girl Hub Ethiopia fails to deliver agreed results. Moderate High Independent Advisory Group. Stakeholder mapping and influencing strategy completed. HMG/DFID political capital mobilised. Active portfolio management approach with scale partners. Implementation of QAS process. Moderate / Deployment - Issues in programme delivery impede Girl Hub Ethiopia’s ability to deliver results Moderate High Annual planning is integrated with global planning, milestones are reviewed on a regular basis, Yegna business plan is signed off by Sept 2012, monitoring baselines in place by October 2012 Moderate / Funding - Funding structure and processes to not adequately support delivery of results Moderate High Internal audit report recommendations are implemented. Value for Money strategy. Moderate / Reputational - Girl Hub strategy and/or activities negatively impact stakeholders Moderate/low High Child protection strategy in place and audited, communication and advocacy strategy in place. Moderate / Operational - Operational challenges impede Girl Hub Ethiopia’s ability to execute against short term and long term plans Low Moderate Office move is well implemented. Milestone based contract developed with Yegna Creative Management Agency, full staff complement are recruited. Low / We judge Girl Hub Ethiopia to be a medium risk innovation. This is due to the innovative nature of the Girl Hub Strategic Collaboration, the political governance context and the lack of comparable initiatives in the Ethiopian Context. / Girl Hub Ethiopia will use quarterly risk register reviews to ensure the appropriateness and effectiveness of risk management strategies set out in the register, and update the register as necessary. The risk registered is reviewed on a quarterly basis by the Nike Foundation Risk Management Committee.
C. What conditions apply (for financial aid only)? / Not applicable as the programme does not include financial aid to Government of Ethiopia.
D. How will progress and results be monitored, measured and evaluated? / Girl Hub Ethiopia will be reviewed through the regular DFID systems of annual and mid-term reviews and project completion report. Each review will cover the full contributions from DFID and Nike Foundation. These reviews will done by a team combining Nike Foundation, Girl Hub and DFID expertise, and will include staff external to the Girl Hub collaboration, to ensure objectivity. Annual Reviews of the Girl Hub Ethiopia and the DFID Accountable Grant to Nike Foundation for Girl Hub will follow a shared timetable. At end of the project, independent evaluation will be used to determine whether expected results have been met. / Girl Hub Ethiopia has developed a detailed monitoring and learning strategy to align with both the Global Girl Hub Monitoring and Learning Plan and the Nike Foundation Integrated Strategy. A monitoring and learning strategy has been developed to define baselines and track progress of the impact, outcome and output indicators in the logframe. Regular and systematic monitoring and learning is central to Girl Hub Ethiopia’s management strategy, and has been designed to ensure that the programme effectively measures impact, builds knowledge and incorporates lessons learned into decision-making processes. Rigorous monitoring and learning is also fundamental to Girl Hub Ethiopia’s efforts to understand the dynamics driving complex social change and of the types of interventions and approaches that deliver transformational results and unleash the girl effect at scale. / The Girl Hub Ethiopia Monitoring and Learning Strategy includes testing and measuring success against two elements of the Girl Hub Theory of change: / Girl Hub Ethiopia as a catalyst and influencer of scale partners or the ‘leverage’ model; / The use of branded social communications platforms to achieve the behaviour change at scale / The strategy uses a range of qualitative and quantitative data collection methodologies including longitudinal attitude/behaviour surveys, qualitative scorecard assessments for scale partners, participatory research and radio listenership studies to generate robust evidence of programme impact on girls. / Monitoring and evaluation of the impact on girls of partner pilot and scale programmes will be built into each collaborative programme. This will include measuring cost and assessing value for money. Girl Hub Ethiopia will play a role in ensuring the quality of monitoring and evaluation design, and collating and analysing information generated at the project level and will seek to answer questions related to implementing the girl effect in Ethiopia. / Girl Hub Ethiopia will develop a Research Strategy to complement the M&L and VfM strategies. GH E funded research will focus on building quantitative and qualitative evidence on what is happening to girls during adolescence. Girl Hub Ethiopia will commission primary research to fill gaps in national data, including a national attitude/behaviour survey to track how public opinion and behaviour changes over time. / Finally, Ethiopia will be a Girl Hub pilot for two innovations in research: / ‘SenseMaker’, an innovative story collection research tool, which will develop a new system of real-time evidence, feedback and learning within Ethiopia, engaging girls as powerful sources of knowledge and elevating their voices. / Longitudinal research, in collaboration with DFID Research and Evidence Department (RED), to determine the impact of the girl effect on girls throughout their lives.
Logframe / Quest No of logframe for this intervention: 3676648